## Sheet1
Year | Order | Order Description | Planned Conductor Miles | Total Installed Miles | UG Miles | Project Start Date | Project Completed Date | Construction Start Baseline | Construction Complete Baseline | Approx months in Construction | Latitude | Longitude | HFTD
2019 | 35040742 | OCGC - 2018 MONTE RIO 1112 OH TO UG DEMO | 0.53 | 0.53 | 0.53 |  |  | N/A | 2019-04-05 |  | 38.4146 | -122.9514 | Tier 3 - Extreme
2019 | 35052718 | OCGC CWSP: ANGWIN OH TO UG DEMO - PH 2 | 0.42898 | 0.42898 | 0.42898 |  | 2019-07-26 | N/A | 2019-07-24 |  | 38.5653 | -122.4416 | N/A
2019 | 35089880 | OCGC PIH SILVERADO 2104 - ANGWIN UG_PH 2 | 0.40095 | 0.40095 | 0.40095 |  |  | N/A | 2019-10-09 |  | 0 | 0 | N/A
2020 | 35103325 | CWSP - MORAGA 1102 & 1104 - OCB | 1.3095 | 1.3095 | 0.71117 | 2019-09-04 | 2020-03-30 | 2020-01-25 | 2020-03-20 | 1.8333 | 0 | 0 | Tier 3 - Extreme
2020 | 35112076 | OCGC FULTON 1107-OH TO UG MARK W SPG | 2.2019 | 2.2019 | 0.69261 | 2019-09-27 | 2020-02-25 | 2019-11-24 | 2020-03-23 | 4 | 0 | 0 | Tier 2 - Elevated
2020 | 35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | 1.16 | 1.16 | 0.71231 | 2019-10-24 | 2020-12-01 | 2020-04-30 | 2020-05-27 | 0.9 | 0 | 0 | Tier 3 - Extreme
2020 | 35114431 | CWSP - MORAGA 1101 - LR108540 - PH5 | 1.4369 | 1.4369 | 0.031439 | 2019-12-06 | 2020-03-30 | 2020-01-02 | 2020-03-31 | 2.9667 | 0 | 0 | Tier 3 - Extreme
2020 | 35113871 | SILVERADO 2104 RECONDUCTOR - PHASE 2 | 0.12311 | 0.12311 | 0.12311 | 2019-08-08 | 2019-12-17 | 2019-10-01 | 2019-12-13 | 2.4333 | 0 | 0 | N/A
2020 | 74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE | 0.84754 | 0.84754 | 0.84754 | 2019-09-27 | 2020-06-26 | 2020-04-01 | 2020-09-30 | 6.0667 | 37.8317 | -122.1857 | N/A
2020 | 35031662 | CWSP - LOS GATOS 1106 - LB44 - PHASE 2.1 | 0.56402 | 0.56402 | 0.09678 | 2019-10-04 | 2020-03-25 | 2020-02-02 | 2020-03-23 | 1.6667 | 37.1933 | -122.0204 | N/A
2021 | 35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  |  | 0.71231 | 2019-10-24 | 2020-12-01 | 2020-04-30 | 2020-05-27 | 0.9 | 0 | 0 | Tier 2 - Elevated
2021 | 35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  |  | 1.9223 | N/A |  |  |  |  | 0 | 0 | Tier 3 - Extreme
2021 | 35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  |  | 1.8491 | N/A |  |  |  |  | 39.6394 | -121.4295 | Tier 3 - Extreme
2021 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 2.0121 |  | 2.0121 | N/A |  |  |  |  | 38.7821 | -120.6094 | N/A
2021 | 35116801 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 0.91345 |  | 0.10985 | N/A |  |  |  |  | 38.0441 | -120.2479 | Tier 3 - Extreme
2021 | 35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | 0.7197 |  | 0.7197 | N/A |  |  |  |  | 0 | 0 | Tier 2 - Elevated
2021 | 35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | 1.6809 |  | 1.4809 | N/A |  |  |  |  | 0 | 0 | Tier 2 - Elevated
2021 | 35192284 | ECOP - SILVERADO 2104 - H05-LR726 | 2.0701 |  | 2.07 | N/A |  |  |  |  | 38.6154 | -122.4315 | Tier 2 - Elevated
2021 | 35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | 2.23 |  | 2.2299 | N/A |  |  |  |  | 37.2551 | -122.3815 | Tier 2 - Elevated
2021 | 35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | 2.9 |  | 2.9 | N/A |  |  |  |  | 37.2551 | -122.3815 | Tier 2 - Elevated
2021 | 35223024 | ECOP - SILVERADO 2104 - H05 - LR726 PH 2 | 2.24 |  | 2.24 | N/A |  |  |  |  | 38.6152 | -122.4293 | Tier 2 - Elevated
2021 | 35223026 | ECOP - SILVERADO 2104 - H05 - LR726 PH 3 | 1.8 |  | 1.8 | N/A |  |  |  |  | 38.6152 | -122.4293 | Tier 3 - Extreme
2021 | 35223037 | PSPS - OAKHURST 1101 - OAKHURST | 0.020076 |  | 0.02 | N/A |  |  |  |  | 37.3227 | -119.6344 | N/A
2021 | 35223343 | FRRB - BIG BEND 1102 - LAKE MADRONE PH1 | 0.85019 |  | 0.85019 | N/A |  |  |  |  | 39.6444 | -121.4314 | N/A
2021 | 35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | 3.7511 |  | 3.7511 | N/A |  |  |  |  | 39.6348 | -121.3915 | Tier 2 - Elevated
2021 | 35225821 | FRRB - BIG BEND 1102 - LAKE MADRONE PH2 | 0.63371 |  | 0.63371 | N/A |  |  |  |  | 39.6444 | -121.4314 | Tier 2 - Elevated
2021 | 35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | 0.90871 |  | 0.90871 | N/A |  |  |  |  | 39.6394 | -121.4295 | Tier 2 - Elevated
2021 | 35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | 1.5968 |  | 1.5968 | N/A |  |  |  |  | 39.6348 | -121.3915 | Tier 3 - Extreme
2021 | 35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | 2.9483 |  | 2.9483 | N/A |  |  |  |  | 39.5047 | -121.4524 | Tier 3 - Extreme
2021 | 35227652 | CWSP - VACAVILLE 11046542 PH 1.3 | 1.1 |  | 0.55 | N/A |  |  |  |  | 38.3423 | -122.0077 | Tier 3 - Extreme
2021 | 35227656 | CWSP - VACAVILLE 11046542 - PH 2.3 | 1.3299 |  | 1 | N/A |  |  |  |  | 38.3423 | -122.0077 | N/A
2021 | 35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | 0.61004 |  | 0.61004 | N/A |  |  |  |  | 38.7514 | -122.6117 | Tier 3 - Extreme
2021 | 35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | 0.23996 |  | 0.23996 | N/A |  |  |  |  | 39.6425 | -121.4237 | Tier 3 - Extreme
2021 | 35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | 0.5 |  | 0.5 | N/A |  |  |  |  | 39.6343 | -121.4112 | Tier 3 - Extreme
2021 | 35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | 0.22992 |  | 0.22992 | N/A |  |  |  |  | 39.6425 | -121.4237 | N/A
2021 | 35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | 0.37008 |  | 0.37008 | N/A |  |  |  |  | 39.6425 | -121.4237 | N/A
2021 | 35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | 0.32008 |  | 0.32008 | N/A |  |  |  |  | 39.6425 | -121.4237 | N/A
2021 | 35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | 0.36004 |  | 0.36004 | N/A |  |  |  |  | 39.6425 | -121.4237 | N/A
2021 | 35233302 | FRRB - WYANDOTTE 1103 - W1 PH 1.6 | 0.12008 |  | 0.12008 | N/A |  |  |  |  | 39.6425 | -121.4237 | Tier 3 - Extreme
2021 | 35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | 0.089962 |  | 0.089962 | N/A |  |  |  |  | 39.6425 | -121.4237 | Tier 2 - Elevated
2021 | 35233304 | FRRB - WYANDOTTE 1103 - W1 PH 1.8 | 0.3 |  | 0.3 | N/A |  |  |  |  | 39.6425 | -121.4237 | Tier 2 - Elevated
2021 | 35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | 0.28996 |  | 0.28996 | N/A |  |  |  |  | 39.6425 | -121.4237 | N/A
2021 | 35233306 | FRRB - WYANDOTTE 1103 - W1 PH1.10 | 0.26004 |  | 0.26004 | N/A |  |  |  |  | 0 | 0 | N/A
2021 | 35233307 | FRRB - WYANDOTTE 1103 - W1 PH1.11 | 0.6 |  | 0.6 | N/A |  |  |  |  | 0 | 0 | N/A
2021 | 35233308 | FRRB - WYANDOTTE 1103 - W1 PH1.12 | 0.92992 |  | 0.92992 | N/A |  |  |  |  | 0 | 0 | N/A
2021 | 35233309 | FRRB - WYANDOTTE 1103 - W1 PH1.13 | 0.37008 |  | 0.37008 | N/A |  |  |  |  | 0 | 0 | N/A
2021 | 35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 | 0.15 |  | 0.15 | N/A |  |  |  |  | 0 | 0 | N/A
2021 | 35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | 0.72822 |  | 0.72822 | N/A |  |  |  |  | 0 | 0 | N/A
2021 | 35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | 1.1 |  | 1.1 | N/A |  |  |  |  | 0 | 0 | N/A
2021 | 35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | 1.6 |  | 1.6 | N/A |  |  |  |  | 0 | 0 | N/A
2021 | 35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | 0.96004 |  | 0.96004 | N/A |  |  |  |  | 0 | 0 | N/A
2021 | 35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 | 1.3186 |  | 1.3186 | N/A |  |  |  |  | 39.6645 | -121.4316 | N/A
2021 | 35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 | 0.24621 |  | 0.24621 | N/A |  |  |  |  | 0 | 0 | N/A
2021 | 35235669 | FRRB - WYANDOTTE 1103 - W4 PH 4.1 | 0.41098 |  | 0.41098 | N/A |  |  |  |  | 39.646 | -121.4244 | N/A
2021 | 35235671 | FRRB - WYANDOTTE 1103 - W4 PH 4.2 | 0.49242 |  | 0.49242 | N/A |  |  |  |  | 39.646 | -121.4244 | N/A
2021 | 35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 | 2.3958 |  | 2.3958 | N/A |  |  |  |  | 39.655 | -121.459 | N/A
2021 | 35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 | 1.3201 |  | 1.3201 | N/A |  |  |  |  | 39.646 | -121.4244 | N/A
2021 | 35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 | 1.16 |  | 1.16 | N/A |  |  |  |  | 39.646 | -121.4244 | N/A
2021 | 35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 | 0.95 |  | 0.95 | N/A |  |  |  |  | 39.646 | -121.4244 | N/A
2021 | 35236990 | FRRB - WYANDOTTE 1103 - W3 PH3.9 | 0.77652 |  | 0.77652 | N/A |  |  |  |  | 39.646 | -121.4244 | N/A
2021 | 35236991 | FRRB - WYANDOTTE 1103 - W4 PH 4.8 | 1.2689 |  | 1.2689 | N/A |  |  |  |  | 39.646 | -121.4244 | N/A
2021 | 35236993 | FRRB - WYANDOTTE 1103 - W4 PH 4.9 | 0.39773 |  | 0.39773 | N/A |  |  |  |  | 39.646 | -121.4244 | N/A
2021 | 35236995 | FRRB - WYANDOTTE 1103 - W4 PH 4.10 | 1.972 |  | 1.972 | N/A |  |  |  |  | 39.646 | -121.4244 | N/A
2021 | 35237889 | FRRB - WYANDOTTE 1103 - W3 PH3.2 | 1.3674 |  | 1.3674 | N/A |  |  |  |  | 39.6343 | -121.4112 | N/A
2021 | 35237890 | FRRB - WYANDOTTE 1103 - W3 PH3.3 | 0.80795 |  | 0.80795 | N/A |  |  |  |  | 39.6343 | -121.4112 | N/A
2021 | 35237891 | FRRB - WYANDOTTE 1103 - W3 PH3.4 | 0.45833 |  | 0.45833 | N/A |  |  |  |  | 39.6343 | -121.4112 | N/A
2021 | 35237893 | FRRB - WYANDOTTE 1103 - W3 PH3.5 | 0.28958 |  | 0.28958 | N/A |  |  |  |  | 39.6343 | -121.4112 | N/A
2021 | 35237894 | FRRB - WYANDOTTE 1103 - W3 PH3.6 | 0.85985 |  | 0.85985 | N/A |  |  |  |  | 39.6343 | -121.4112 | N/A
2021 | 35237896 | FRRB - WYANDOTTE 1103 - W3 PH3.8 | 1.1121 |  | 1.1121 | N/A |  |  |  |  | 39.6343 | -121.4112 | N/A
2021 | 35239095 | FRRB - WYANDOTTE 1103 - W4 PH 4.3 | 1.1326 |  | 1.1326 | N/A |  |  |  |  | 39.6348 | -121.3915 | Tier 3 - Extreme
2021 | 35239096 | FRRB - WYANDOTTE 1103 - W4 PH 4.4 | 0.88125 |  | 0.88125 | N/A |  |  |  |  | 39.6348 | -121.3915 | Tier 3 - Extreme
2021 | 35239097 | FRRB - WYANDOTTE 1103 - W4 PH 4.5 | 1.0127 |  | 1.0127 | N/A |  |  |  |  | 39.6348 | -121.3915 | Tier 3 - Extreme
2021 | 35239098 | FRRB - WYANDOTTE 1103 - W4 PH 4.6 | 1.3792 |  | 1.3792 | N/A |  |  |  |  | 39.6348 | -121.3915 | Tier 2 - Elevated
2021 | 35239099 | FRRB - WYANDOTTE 1103 - W4 PH 4.7 | 0.65758 |  | 0.65758 | N/A |  |  |  |  | 39.6348 | -121.3915 | Tier 3 - Extreme
2021 | 35239522 | FRRB - WYANDOTTE 1103 - W2 PH2.9 | 0.25 |  | 0.25 | N/A |  |  |  |  | 39.6343 | -121.4112 | Tier 3 - Extreme
2021 | 35239523 | FRRB - WYANDOTTE 1103 - W2 PH2.10 | 0.25 |  | 0.25 | N/A |  |  |  |  | 39.6343 | -121.4112 | Tier 3 - Extreme
2021 | 35239937 | FRRB - WYANDOTTE 1103 - W2 PH2.11 | 0.58712 |  | 0.58712 | N/A |  |  |  |  | 39.6343 | -121.4112 | Tier 2 - Elevated
2021 | 35240545 | FRRB - WYANDOTTE 1103 - W2 PH2.12 | 0.1089 |  | 0.1089 | N/A |  |  |  |  | 39.6343 | -121.4112 | Tier 2 - Elevated
2021 | 35240546 | FRRB - WYANDOTTE 1103 - W2 PH2.13 | 0.087121 |  | 0.087121 | N/A |  |  |  |  | 39.6343 | -121.4112 | Tier 2 - Elevated
2022 | 35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | 1.8097 |  | 0.032576 | N/A |  |  |  |  | 0 | 0 | Tier 2 - Elevated
2022 | 35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | 2.69 |  | 2.69 | N/A |  |  |  |  | 38.3423 | -122.0077 | N/A
2022 | 35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | 2.4604 |  | 4.3544 | N/A |  |  |  |  | 40.6242 | -122.3039 | Tier 2 - Elevated
2022 | 35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | 0.13883 |  | 0.13883 | N/A |  |  |  |  | 38.7307 | -120.7828 | Tier 2 - Elevated
2022 | 35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | 0.24 |  | 0.24 | N/A |  |  |  |  | 38.7293 | -120.7998 | N/A
2022 | 35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | 0.44 |  | 0.44 | N/A |  |  |  |  | 38.8858 | -121.0157 | Tier 2 - Elevated
2022 | 35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK | 0.72008 |  | 0.72 | N/A |  |  |  |  | 38.3949 | -120.804 | Tier 3 - Extreme
2022 | 35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | 0.17992 |  | 0.18 | N/A |  |  |  |  | 38.5766 | -122.5839 | Tier 3 - Extreme
2022 | 35223063 | PSPS - DUNBAR 1101 - OAKMONT | 0 |  | 0.3197 | N/A |  |  |  |  | 38.4438 | -122.602 | Tier 3 - Extreme
2022 | 35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | 0.13996 |  | 0.13996 | N/A |  |  |  |  | 0 | 0 | Tier 3 - Extreme
2022 | 35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | 0.84564 |  | 0.84564 | N/A |  |  |  |  | 40.6242 | -122.3039 | Tier 3 - Extreme
2022 | 35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | 2.5314 |  | 2.5314 | N/A |  |  |  |  | 40.6242 | -122.3039 | Tier 3 - Extreme
2022 | 35227658 | CWSP - VACAVILLE 11046542 - PH 2.5 | 0.53996 |  | 0.26 | N/A |  |  |  |  | 38.3423 | -122.0077 | Tier 3 - Extreme
2022 | 35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | 0.62008 |  | 0.62008 | N/A |  |  |  |  | 38.7561 | -122.6052 | Tier 3 - Extreme
2022 | 35227870 | CWSP - VACAVILLE 11046542 - PH 2.2 | 1.4201 |  | 0.06 | N/A |  |  |  |  | 38.3423 | -122.0077 | Tier 3 - Extreme
2022 | 35228774 | PSPS - DUNBAR 1101 - OAKMONT PH 2 | 0 |  | 1.0008 | N/A |  |  |  |  | 38.4438 | -122.602 | Tier 3 - Extreme
2022 | 35228775 | PSPS - DUNBAR 1101 - OAKMONT PH 3 | 0 |  | 0.90341 | N/A |  |  |  |  | 38.4438 | -122.602 | Tier 3 - Extreme
2022 | 35231620 | CWSP - HIGHLANDS 1102628 PH 1.2 | 2.6023 |  | 2.6782 | N/A |  |  |  |  | 38.9822 | -122.6031 | Tier 3 - Extreme
2022 | 35231621 | CWSP - HIGHLANDS 1102628 PH 1.3 | 2.5144 |  | 1.3655 | N/A |  |  |  |  | 38.9822 | -122.6031 | Tier 3 - Extreme
2022 | 35233948 | CWSP - OREGON TRAIL 110335002 PH1.3 | 2.5871 |  | 2.5871 | N/A |  |  |  |  | 40.6242 | -122.3039 | Tier 3 - Extreme
2022 | 35233950 | CWSP - OREGON TRAIL 110335002 PH1.5 | 2.7542 |  | 2.7542 | N/A |  |  |  |  | 40.6242 | -122.3039 | Tier 3 - Extreme
2022 | 35233995 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.2 | 0.5 |  | 0.5 | N/A |  |  |  |  | 0 | 0 | Tier 3 - Extreme
2022 | 35233996 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.3 | 0.71019 |  | 0.71 | N/A |  |  |  |  | 0 | 0 | Tier 3 - Extreme
2022 | 35234383 | CWSP - OREGON TRAIL 110335002 PH3.6 | 1.1985 |  | 1.1985 | N/A |  |  |  |  | 40.6242 | -122.3039 | Tier 3 - Extreme
2022 | 35234399 | CWSP - OREGON TRAIL 110335002 PHASE 6.3 | 0.48011 |  | 0.48011 | N/A |  |  |  |  | 40.6242 | -122.3039 | Tier 3 - Extreme
2022 | 35234526 | PSPS - MARTELL 1101 - SUTTER CREEK PH1.3 | 0.58996 |  | 0.59 | N/A |  |  |  |  | 38.3949 | -120.804 | Tier 3 - Extreme
2022 | 35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | 1.1201 |  | 1.1201 | N/A |  |  |  |  | 38.7577 | -122.6359 | Tier 3 - Extreme
2022 | 35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 | 0.47992 |  | 0.47992 | N/A |  |  |  |  | 38.7577 | -122.6359 | Tier 3 - Extreme
2022 | 74008802 | INST ROSSMOOR 1109 FDR_MORAGA BK5 EMERG | 0 |  | 0.2642 | N/A |  |  |  |  | 37.9561 | -122.0286 | Tier 3 - Extreme
2022 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 2.1311 |  | 0.36553 | N/A |  |  |  |  | 38.7821 | -120.6094 | Tier 3 - Extreme
2022 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 1.3095 |  | 0.59375 | N/A |  |  |  |  | 38.7821 | -120.6094 | Tier 3 - Extreme
2022 | 35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | 1.5352 |  | 1.5352 | N/A |  |  |  |  | 0 | 0 | Tier 3 - Extreme
2022 | 35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | 1.1098 |  | 1.1098 | N/A |  |  |  |  | 0 | 0 | Tier 3 - Extreme
2022 | 35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | 4.3356 |  | 4.3356 | N/A |  |  |  |  | 0 | 0 | Tier 3 - Extreme
2022 | 35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | 0.60606 |  | 0.56818 | N/A |  |  |  |  | 38.9024 | -122.7519 | Tier 3 - Extreme
2022 | 35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | 1.3826 |  | 1.1828 | N/A |  |  |  |  | 38.9024 | -122.7519 | Tier 3 - Extreme
2022 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 2.6678 |  | 0.24223 | N/A |  |  |  |  | 0 | 0 | Tier 3 - Extreme
2022 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 2.7725 |  | 0.31515 | N/A |  |  |  |  | 0 | 0 | Tier 3 - Extreme
2022 | 35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | 1.4847 |  | 0.090341 | N/A |  |  |  |  | 0 | 0 | Tier 3 - Extreme
2022 | 35144944 | PSPS - SNEATH LANE 1107 - LR 48338 | 0.2553 |  | 0.2553 | N/A |  |  |  |  | 37.6433 | -122.4679 | Tier 3 - Extreme
2022 | 35145540 | PSPS - FROGTOWN 1702 - CB | 1.2723 |  | 0.53902 | N/A |  |  |  |  | 38.0453 | -120.5253 | Tier 3 - Extreme
2022 | 35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | 1.04 |  | 1.04 | N/A |  |  |  |  | 38.7576 | -122.6358 | Tier 3 - Extreme
2022 | 35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | 4.0903 |  | 4.0903 | N/A |  |  |  |  | 38.3526 | -122.5226 | Tier 3 - Extreme
2022 | 35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | 1.1701 |  | 1.17 | N/A |  |  |  |  | 38.046 | -122.646 | Tier 3 - Extreme
2022 | 35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | 1.34 |  | 1.34 | N/A |  |  |  |  | 37.8682 | -121.8573 | Tier 3 - Extreme
2022 | 35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | 2.04 |  | 2.04 | N/A |  |  |  |  | 38.7238 | -122.6197 | Tier 3 - Extreme
2022 | 35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | 0.47992 |  | 0.48 | N/A |  |  |  |  | 38.7215 | -120.8714 | Tier 3 - Extreme
2022 | 35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | 0.8 |  | 0.8 | N/A |  |  |  |  | 38.5527 | -122.7132 | Tier 3 - Extreme
2022 | 35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | 1.54 |  | 1.54 | N/A |  |  |  |  | 38.7561 | -122.6052 | Tier 3 - Extreme
2022 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 0.3 |  | 0.3 | N/A |  |  |  |  | 40.6253 | -122.4633 | Tier 2 - Elevated
2022 | 35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | 1.14 |  | 1.14 | N/A |  |  |  |  | 37.9632 | -121.9407 | Tier 2 - Elevated
2022 | 35219096 | CWSP - KIRKER 2104442850 PH 1.1 | 1.6701 |  | 1.67 | N/A |  |  |  |  | 37.9907 | -121.896 | Tier 2 - Elevated
2022 | 35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | 2.5 |  | 2.5 | N/A |  |  |  |  | 38.8983 | -120.9827 | Tier 2 - Elevated
2022 | 35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | 1.9299 |  | 1.9299 | N/A |  |  |  |  | 38.7569 | -122.607 | Tier 2 - Elevated
2022 | 35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | 0.27992 |  | 0.27992 | N/A |  |  |  |  | 38.7569 | -122.607 | Tier 2 - Elevated
2022 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 0.57008 |  | 0.57 | N/A |  |  |  |  | 39.3878 | -121.4038 | Tier 2 - Elevated
2022 | 35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | 0.05 |  | 0.05 | N/A |  |  |  |  | 39.2376 | -121.0592 | Tier 2 - Elevated
2022 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 0.77008 |  | 0.77 | N/A |  |  |  |  | 39.4738 | -121.5307 | Tier 2 - Elevated
2022 | 35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | 1.6299 |  | 1.63 | N/A |  |  |  |  | 38.0443 | -122.6155 | Tier 2 - Elevated
2022 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 1.7299 |  | 1.73 | N/A |  |  |  |  | 0 | 0 | Tier 3 - Extreme
2022 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 1.8299 |  | 1.83 | N/A |  |  |  |  | 0 | 0 | Tier 3 - Extreme
2022 | 35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | 0.47008 |  | 0.47 | N/A |  |  |  |  | 38.549 | -122.72 | Tier 3 - Extreme
2022 | 35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | 1.55 |  | 1.55 | N/A |  |  |  |  | 38.7249 | -122.6186 | Tier 3 - Extreme
2022 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 0.82008 |  | 0.82 | N/A |  |  |  |  | 40.6253 | -122.4633 | Tier 3 - Extreme
2022 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 4.5 |  | 4.5 | N/A |  |  |  |  | 40.6253 | -122.4633 | Tier 3 - Extreme
2022 | 35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | 0.15 |  | 0.15 | N/A |  |  |  |  | 39.362 | -123.1283 | Tier 3 - Extreme
2022 | 35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | 0.57008 |  | 0.57008 | N/A |  |  |  |  | 0 | 0 | Tier 3 - Extreme
2022 | 35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | 1.7799 |  | 1.7799 | N/A |  |  |  |  | 38.7138 | -120.9394 | Tier 3 - Extreme
2022 | 35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | 0.85 |  | 0.85 | N/A |  |  |  |  | 38.7577 | -122.6359 | Tier 3 - Extreme
2022 | 35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | 1.0394 |  | 1.0394 | N/A |  |  |  |  | 38.7577 | -122.6359 | Tier 3 - Extreme
2022 | 35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | 0.58883 |  | 0.58883 | N/A |  |  |  |  | 38.7577 | -122.6359 | Tier 3 - Extreme
2022 | 35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | 0.7214 |  | 0.7214 | N/A |  |  |  |  | 38.7577 | -122.6359 | Tier 3 - Extreme
2022 | 35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | 0.43295 |  | 0.43295 | N/A |  |  |  |  | 38.7577 | -122.6359 | Tier 3 - Extreme
2022 | 35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | 0.58087 |  | 0.58087 | N/A |  |  |  |  | 38.7577 | -122.6359 | Tier 3 - Extreme
2022 | 35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | 0.3483 |  | 0.3483 | N/A |  |  |  |  | 38.7577 | -122.6359 | Tier 3 - Extreme
2022 | 35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | 2.8756 |  | 2.8756 | N/A |  |  |  |  | 38.7577 | -122.6359 | Tier 3 - Extreme
2022 | 35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | 0.54924 |  | 0.54924 | N/A |  |  |  |  | 38.7577 | -122.6359 | Tier 3 - Extreme
2022 | 35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | 1.3801 |  | 1.3801 | N/A |  |  |  |  | 38.7249 | -122.6186 | Tier 3 - Extreme
2022 | 35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | 1.55 |  | 1.55 | N/A |  |  |  |  | 38.7249 | -122.6186 | Tier 3 - Extreme
2022 | 35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | 1.3201 |  | 1.3201 | N/A |  |  |  |  | 38.7573 | -122.606 | Tier 3 - Extreme
2022 | 35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | 0.32008 |  | 0.32008 | N/A |  |  |  |  | 38.7573 | -122.606 | Tier 3 - Extreme
2022 | 35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | 1.01 |  | 1.01 | N/A |  |  |  |  | 38.7561 | -122.6052 | Tier 3 - Extreme
2022 | 35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | 1.8 |  | 1.8 | N/A |  |  |  |  | 38.7561 | -122.6052 | Tier 3 - Extreme
2022 | 35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | 1.5701 |  | 1.5701 | N/A |  |  |  |  | 38.7561 | -122.6052 | Tier 3 - Extreme
2022 | 35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | 1.49 |  | 1.49 | N/A |  |  |  |  | 38.7561 | -122.6052 | Tier 3 - Extreme
2022 | 35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | 1.3 |  | 1.3 | N/A |  |  |  |  | 37.9632 | -121.9407 | Tier 3 - Extreme
2022 | 35232650 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.2 | 1.7098 |  | 1.7098 | N/A |  |  |  |  | 38.8983 | -120.9827 | Tier 3 - Extreme
2022 | 35233953 | CWSP - OREGON TRAIL 110335002 PH2.3 | 0.84034 |  | 0.84034 | N/A |  |  |  |  | 40.6242 | -122.3039 | Tier 3 - Extreme
2022 | 35233955 | CWSP - OREGON TRAIL 110335002 PH2.4 | 0.54924 |  | 0.54924 | N/A |  |  |  |  | 40.6242 | -122.3039 | Tier 3 - Extreme
2022 | 35233957 | CWSP - OREGON TRAIL 110335002 PH2.5 | 0.10208 |  | 0.10208 | N/A |  |  |  |  | 40.6242 | -122.3039 | Tier 3 - Extreme
2022 | 35234756 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.9 | 2.782 |  | 2.782 | N/A |  |  |  |  | 38.7576 | -122.6358 | Tier 3 - Extreme
2022 | 35234758 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.10 | 0.58201 |  | 0.58201 | N/A |  |  |  |  | 38.7576 | -122.6358 | Tier 3 - Extreme
2022 | 35234862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.11 | 0.079924 |  | 0.079924 | N/A |  |  |  |  | 38.7576 | -122.6358 | Tier 3 - Extreme
2022 | 35234865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.12 | 0.64754 |  | 0.64754 | N/A |  |  |  |  | 38.7576 | -122.6358 | Tier 3 - Extreme
2022 | 74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | 2.4191 |  | 2.1633 | N/A |  |  | C |  | 38.9024 | -122.7519 | Tier 3 - Extreme
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reporting Year
Note on C1: Mason, Derek: Double click on a description to view span information for that order.
Note on G1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work Plan EOD Date
Note on H1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Extracted Operative Date where available in SAP.
Note on G9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: P6 Business Case Date
Note on I9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: P6 Construction Start Date
Note on J9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CN24 Out Date