## Public Queue
PG&E Wholesale Distribution Queue Posted: |  |  | 2024-04-26
Interconnection Requests Received Through: |  |  | 2024-03-31
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Date Interconnection Request Received by PG&E | Revised Queue Number (5/31/12) | Interconnection Process Type Applied For | Current Process Type | Current Interconnection Request Status | Customer Requested COD (from application) | Updated Commercial Operation Date | Actual In-Service Date | Facility County | Substation | Generation Type | Summer Max Capacity (MW) | Date Interconnection Request Deemed Complete | Date Initial Review Provided to Applicant | Initial Review Results (and Fail Reasons if Failed) | Date Supplemental Review Provided To Applicant | Supplemental Review Results (and Fail Reasons if Failed) | Electrical Independence Test Results | Date System Impact Study / Phase 1 Provided To Applicant | Date Facilities Study / Phase 2 Provided To Applicant | Interconnection Agreement Status | Notes
2006-02-23 | 0001-WD | Independent Study | Independent Study | In Service | Not Provided | 6/15/2009 | 5/6/2009 | CONTRA COSTA | WILLOW PASS SUB | Engine | 3.852 | 3/30/2006 | N/A | N/A | N/A | N/A | N/A | 8/3/2006 | 3/8/2007 | Executed | No former queue position
2006-09-22 | 0002-WD | Fast Track | Fast Track | Withdrawn | 1/1/2008 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Other | 1 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2007-03-21 12:00 | 0003-WD | Fast Track | Independent Study | In Service | 8/8/2008 | 8/11/2008 | 8/1/2008 | UNINC EL DORADO | PLACERVILLE SUB | Hydro | 0.375 | 4/27/2007 | 5/21/2007 | Fail Screens: 10 | N/A | N/A | N/A | 8/10/2007 | 2/8/2008 | Executed | No former queue position
2007-03-21 12:00 | 0004-WD | Fast Track | Independent Study | In Service | 5/22/2009 | 5/22/2009 | 3/12/2009 | UNINC EL DORADO | PLACERVILLE SUB | Hydro | 0.58 | 4/27/2007 | 5/21/2007 | Fail Screens: 10 | N/A | N/A | N/A | 8/16/2007 | 2/20/2008 | Executed | No former queue position
2007-06-07 | 0005-WD | Fast Track | Independent Study | In Service | 1/6/2009 | 9/1/2008 | 11/25/2008 | YUBA | WHEATLAND SUB | Engine | 1.6 | 7/16/2007 | 8/6/2007 | Fail Screens: 10 | N/A | N/A | N/A | 11/1/2007 | 7/25/2008 | Executed | No former queue position
2007-06-15 | 0006-WD | Independent Study | Independent Study | In Service | 3/31/2011 | 2/1/2010 | 9/13/2011 | ALAMEDA | OAKLAND L SUB | Engine | 4.5 | 1/11/2008 | N/A | N/A | N/A | N/A | N/A | 4/23/2008 | 3/31/2009 | Executed | Former queue position: W2
2007-11-16 | 0007-WD | Fast Track | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | HERDLYN SUB | Solar PV | 2 | 12/12/2007 | 1/3/2008 | Fail Screens: 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W3
2008-03-30 | 0008-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SHASTA | WHITMORE SUB | Solar PV | 0.52 | 05/05/2008 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W3a
2008-04-15 | 0009-WD | Independent Study | Independent Study | In Service | 11/1/2009 | 7/1/2009 | 11/20/2009 | SANTA CRUZ | PAUL SWEET SUB | Engine | 2 | 7/16/2008 | N/A | N/A | N/A | N/A | N/A | 4/1/2011 | 1/27/2009 | Executed | No former queue position
2008-06-02 | 0010-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SIERRA | ALLEGHANY SUB | Hydro | 0.05 | 9/8/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W4
2008-07-14 | 0011-WD | Independent Study | Independent Study | In Service | 7/8/2009 | 3/24/2009 |  | MONTEREY | CASTROVILLE SUB | Engine, Turbine | 5.069 | 8/7/2008 | N/A | N/A | N/A | N/A | N/A | 12/19/2008 | N/A | Executed | Former queue position: W5
2008-07-28 | 0012-WD | Fast Track | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CRUZ | BEN LOMOND SUB | Hydro | 0.06 | 12/19/2008 | 1/8/2009 | Fail Screens: 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W6
2008-09-12 | 0013-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | LAMONT SUB | Reciprocating Engine | 1.6 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Duplicate entry; former queue position: W7
2008-09-22 | 0014-WD | Independent Study | Independent Study | In Service | 3/15/2012 | 12/21/2012 | 4/10/2013 | MONTEREY | GONZALES SUB | Engine | 1.416 | 9/22/2008 | N/A | N/A | N/A | N/A | N/A | 1/19/2010 | N/A | Executed | Former queue position: W8
2008-09-26 | 0015-WD | Independent Study | Independent Study | In Service | 6/30/2010 | 4/28/2011 | 4/28/2011 | MERCED | EL CAPITAN SUB | Steam Turbine | 0.75 | Complete | N/A | N/A | N/A | N/A | N/A | 3/10/2010 | 10/19/2010 | Executed | Former queue position: W9
2008-10-03 | 0016-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | TEMBLOR SUB | Solar PV | 17 | 12/23/2008 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W10
2008-11-05 12:55 | 0017-WD | Independent Study | Independent Study | In Service | Not Provided | In Service | 6/14/2010 | SANTA BARBARA | SANTA MARIA SUB | Engine | 1.426 | 12/9/2008 | N/A | N/A | N/A | N/A | N/A | 8/2/2009 | N/A | Executed | Former queue position: W11
2008-11-12 09:21 | 0018-WD | Independent Study | Independent Study | In Service | Not Provided | 12/22/2009 | 12/22/2009 | SOLANO | VACA DIXON SUB | Solar PV | 2.5 | 3/5/2009 | N/A | N/A | N/A | N/A | N/A | 5/19/2009 | 8/7/2009 | Executed | No former queue position
2008-11-19 16:39 | 0019-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | TULARE | SAND CREEK SUB | Solar PV | 1.5 | 1/27/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W12
2009-01-11 | 0020-WD | Independent Study | Independent Study | In Service | 6/17/2009 | 6/17/2019 | 6/2/2009 | SAN JOAQUIN | METTLER SUB | Reciprocating Engine | 0.3 | Complete | N/A | N/A | N/A | N/A | N/A |  | N/A | Executed | No former queue position
2009-02-10 18:36 | 0021-WD | Independent Study | Independent Study | In Service | Not Provided | 9/9/2010 | 8/12/2010 | SAN FRANCISCO | SAN FRAN L SUB | Solar PV | 4.3875 | 3/5/2009 | N/A | N/A | N/A | N/A | N/A | 4/23/2009 | 2009-10-21 | Executed | Former queue position: W15
2009-02-13 | 0022-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | ANTELOPE SUB | Solar PV | 10.5 | 2009-03-06 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W13
2009-02-13 | 0023-WD | Independent Study | Independent Study | In Service | 12/1/2013 | 4/10/2015 | 3/16/2015 | KERN | BLACKWELL SUB | Solar PV | 12 | 5/6/2009 | N/A | N/A | N/A | N/A | N/A |  | N/A | Executed | Former queue position: W14
2009-03-10 | 0024-WD | Independent Study | Independent Study | In Service | 6/8/2010 | 6/8/2010 | 4/5/2010 | NEVADA | HIGGINS SUB | Hydro | 0.037 | 3/24/2009 | N/A | N/A | N/A | N/A | N/A |  | 6/29/2009 | Executed | Former queue position: W16
2009-03-11 14:23 | 0025-WD | Independent Study | Independent Study | In Service | Not Provided | 4/28/2010 | 8/31/2009 | NEVADA | HIGGINS SUB | Hydro | 0.522 | 4/6/2009 | N/A | N/A | N/A | N/A | N/A | 6/3/2009 | 7/24/2009 | Executed | No former queue position
2009-03-30 | 0026-WD | Independent Study | Independent Study | In Service | 12/24/2012 | 7/15/2013 |  | YUBA | WHEATLAND SUB | Turbine | 3.2 | 4/10/2009 | N/A | N/A | N/A | N/A | N/A | 7/24/2009 | 8/21/2011 | Executed | Former queue position: W17
2009-05-14 | 0027-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | TEMBLOR SUB | Solar PV | 20 | 2009-06-10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W18
2009-06-05 12:51 | 0028-WD | Independent Study | Independent Study | In Service | 12/24/2012 | 6/17/2013 | 5/2/2013 | SOLANO | PEABODY SUB | Turbine | 1.5 | 7/9/2009 | N/A | N/A | N/A | N/A | N/A | 10/26/2009 | 10/3/2011 | Executed | Former queue position: W21
2009-06-17 | 0029-WD | Independent Study | Independent Study | In Service | 5/1/2010 | 6/30/2011 | 6/3/2011 | KINGS | AVENAL SUB | Solar PV | 5.76 | 7/21/2009 | N/A | N/A | N/A | N/A | N/A | 3/2/2010 | 9/10/2010 | Executed | Former queue position: W20
2009-06-25 | 0030-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | PLACER | BONNIE NOOK SUB | Solar PV | 0 | 8/17/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2009-07-03 12:30 | 0031-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | MERCED FALLS SUB | Solar PV | 6 | 8/13/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W28
2009-07-03 12:32 | 0032-WD | Independent Study | Independent Study | In Service | 6/1/2011 | 4/24/2015 | 4/20/2015 | KERN | GOOSE LAKE SUB | Solar PV | 15 | 8/4/2009 | N/A | N/A | N/A | N/A | N/A | 10/14/2010 | 6/25/2012 | Executed | Former queue position: W25
2009-07-03 12:35 | 0033-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | SMYRNA SUB | Solar PV | 10 | 8/4/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W26
2009-07-16 12:59 | 0034-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | STOREY SUB | Solar PV | 0.036 | 8/13/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W27
2009-07-20 | 0035-WD | Independent Study | Independent Study | In Service | 5/30/2011 | 12/31/2010 | 5/27/2011 | KINGS | AVENAL SUB | Solar PV | 0.036 | Complete | N/A | N/A | N/A | N/A | N/A | 10/1/2009 | 1/31/2010 | Executed | Former queue position: W19
2009-07-20 | 0036-WD | Independent Study | Independent Study | In Service | 5/30/2011 | 12/1/2010 | 5/18/2011 | KINGS | AVENAL SUB | Solar PV | 0.054 | Complete | N/A | N/A | N/A | N/A | N/A | 9/15/2009 | 5/17/2010 | Executed | Former queue position: W22
2009-07-20 | 0037-WD | Independent Study | Independent Study | Withdrawn | 7/14/2010 | Withdrawn | Withdrawn | ALAMEDA | NEWARK SUB | Reciprocating Engine | 0.32 | 8/5/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W23
2009-07-20 | 0038-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CLARA | EDENVALE SUB | Reciprocating Engine | 0.42 | 2009-08-05 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W24
2009-07-22 14:46 | 0039-WD | Independent Study | Independent Study | Withdrawn | 6/1/2011 | Withdrawn | Withdrawn | KERN | SMYRNA SUB | Solar PV | 0.6 | 8/10/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W29
2009-08-03 | 0040-WD | Independent Study | Independent Study | In Service | 4/29/2015 | 2/27/2015 | 4/14/2015 | KERN | TWISSELMAN SUB | Solar PV | 1 | Complete | N/A | N/A | N/A | N/A | N/A | 8/6/2010 | N/A | Executed | Former queue position: W30
2009-08-10 | 0041-WD | Independent Study | Independent Study | In Service | 4/1/2010 | 8/31/2012 | 7/6/2012 | KERN | TUPMAN SUB | Steam Turbine | 0.03 | 9/2/2009 | N/A | N/A | N/A | N/A | N/A | 10/28/2009 | 7/1/2010 | Executed | Former queue position: W31
2009-08-20 | 0042-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | RIO BRAVO SUB | Solar PV | 0.03 | 2009-09-09 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2009-08-24 15:25 | 0043-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | BUTTE/PLUMAS | OROVILLE SUB | Solar PV | 0.2 | 9/17/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W33
2009-09-01 16:37 | 0044-WD | Independent Study | Independent Study | Withdrawn | 12/1/2014 | Withdrawn | Withdrawn | FRESNO | COALINGA #2 SUB | Solar PV | 0.018 | 9/23/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W32
2009-09-14 09:30 | 0045-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | SAN BERNARD SUB | Solar PV | 0.001 | 10/19/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W43
2009-09-14 09:30 | 0046-WD | Independent Study | Independent Study | Withdrawn | 12/31/2011 | Withdrawn | Withdrawn | KERN | ELK HILLS SUB | Solar PV | 0.2 | 5/3/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W44
2009-09-15 10:02 | 0047-WD | Independent Study | Independent Study | Withdrawn | 5/1/2011 | Withdrawn | Withdrawn | FRESNO | FIREBAUGH SUB | Solar PV | 1.85 | 10/27/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W46
2009-09-16 16:38 | 0048-WD | Independent Study | Independent Study | Withdrawn | 3/1/2011 | Withdrawn | Withdrawn | KERN | LAKEVIEW SUB | Solar PV | 1.85 | 10/2/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W36
2009-09-16 19:53 | 0049-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | TEMBLOR SUB | Solar PV | 0.55 | 11/04/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W34
2009-09-16 19:55 | 0050-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | GOOSE LAKE SUB | Solar PV | 0.058 | 11/04/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W35
2009-09-16 19:56 | 0051-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | GOOSE LAKE SUB | Solar PV | 4.49 | 11/4/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W38
2009-09-16 19:57 | 0052-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | CORRAL SUB | Solar PV | 9.6 | 10/29/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W37
2009-09-23 15:31 | 0053-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | KETTLEMAN HILLS SUB | Solar PV | 4.66 | 11/02/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W41
2009-09-23 15:31 | 0054-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | KETTLEMAN HILLS SUB | Solar PV | 2 | 11/02/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W42
2009-09-24 08:06 | 0055-WD | Independent Study | Independent Study | In Service | 5/1/2011 | 12/15/2016 | 12/1/2016 | FRESNO | ORO LOMA SUB | Solar PV | 3 | 10/27/2009 | N/A | N/A | N/A | N/A | N/A | 6/24/2010 | 2013-06-14 | Executed | Former queue position: W47
2009-09-25 10:45 | 0056-WD | Independent Study | Independent Study | Withdrawn | 12/1/2014 | Withdrawn | Withdrawn | FRESNO | COALINGA #1 SUB | Solar PV | 3.2 | 10/9/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W45
2009-09-25 11:04 | 0057-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | GUERNSEY SUB | Solar PV | 0.21 | 11/04/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W40
2009-09-25 11:05 | 0058-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | GUERNSEY SUB | Solar PV | 0.21 | 11/04/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W39
2009-10-02 17:05 | 0059-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | SAN BERNARD SUB | Solar PV | 0.21 | 10/20/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2009-10-06 14:56 | 0060-WD | Independent Study | Independent Study | Withdrawn | 5/1/2011 | Withdrawn | Withdrawn | FRESNO | ORO LOMA SUB | Solar PV | 0.21 | 10/27/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W48
2009-10-20 | 0061-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | SCHINDLER SUB | Solar PV | 0 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2009-10-21 09:48 | 0062-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | SAN JOAQUIN SUB | Solar PV | 20 | 11/24/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W49
2009-10-27 | 0063-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | EL NIDO SUB | Solar PV | 0.21 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W50
2009-10-28 | 0064-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SONOMA | FULTON SUB | Solar PV | 0.21 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W51
2009-10-28 13:43 | 0065-WD | Independent Study | Independent Study | In Service | 3/1/2011 | 2/18/2012 | 7/2/2012 | FRESNO | GIFFEN SUB | Solar PV | 10 | 12/7/2009 | N/A | N/A | N/A | N/A | N/A | 3/16/2011 | 7/14/2011 | Executed | Former queue position: W52
2009-10-30 17:59 | 0066-WD | Independent Study | Independent Study | In Service | 3/1/2011 | 5/1/2011 | 9/26/2011 | FRESNO | SCHINDLER SUB | Solar PV | 0.21 | 12/3/2009 | N/A | N/A | N/A | N/A | N/A | 3/19/2010 | N/A | Executed | Former queue position: W54
2009-10-30 18:00 | 0067-WD | Independent Study | Independent Study | In Service | 3/1/2011 | 5/1/2011 | 8/31/2011 | FRESNO | SCHINDLER SUB | Solar PV | 0.8 | 12/3/2009 | N/A | N/A | N/A | N/A | N/A | 4/1/2010 | N/A | Executed | Former queue position: W55
2009-11-03 11:48 | 0068-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | SCHINDLER SUB | Solar PV | 0.5 | 12/3/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W56
2009-11-11 13:55 | 0069-WD | Independent Study | Independent Study | Withdrawn | 12/1/2011 | Withdrawn | Withdrawn | KERN | BLACKWELL SUB | Solar PV | 12 | 12/4/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W57
2009-11-13 17:13 | 0070-WD | Independent Study | Independent Study | Withdrawn | 3/1/2011 | Withdrawn | Withdrawn | SOLANO | VACA DIXON SUB | Solar PV | 10 | 12/1/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W58
2009-11-17 | 0071-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CLARA | HICKS SUB | Reciprocating Engine | 4.8 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W59
2009-11-18 | 0072-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | LE GRAND SUB | Solar PV | 15 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W60
2009-11-20 11:29 | 0073-WD | Independent Study | Independent Study | Withdrawn | 6/28/2011 | Withdrawn | Withdrawn | FRESNO | CHENEY SUB | Solar PV | 20 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W61
2009-11-20 11:56 | 0074-WD | Independent Study | Independent Study | In Service | 6/28/2011 | 11/30/2012 | 6/28/2012 | FRESNO | HURON SUB | Solar PV | 10 | 12/8/2009 | N/A | N/A | N/A | N/A | N/A | 6/30/2010 | N/A | Executed | Former queue position: W62
2009-11-23 17:08 | 0075-WD | Independent Study | Independent Study | In Service | 11/30/2012 | 12/31/2012 | 5/10/2013 | FRESNO | GATES SUB | Solar PV | 10 | 12/9/2009 | N/A | N/A | N/A | N/A | N/A | 5/7/2011 | N/A | Executed | Former queue position: W63
2009-11-23 17:25 | 0076-WD | Independent Study | Independent Study | Withdrawn | 5/7/2012 | Withdrawn | Withdrawn | FRESNO | GATES SUB | Solar PV | 20 | 12/9/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W64
2009-11-25 10:36 | 0077-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | BUTTE | ANITA SUB | Solar PV | 8.25 | 4/9/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W67
2009-12-10 09:11 | 0078-WD | Independent Study | Independent Study | In Service | 9/28/2011 | 1/13/2012 | 6/19/2012 | FRESNO | CANTUA SUB | Solar PV | 10 | 1/7/2010 | N/A | N/A | N/A | N/A | N/A | 3/6/2011 | 6/8/2011 | Executed | Former queue position: W66
2009-12-10 13:45 | 0079-WD | Independent Study | Independent Study | In Service | 9/28/2011 | 6/1/2011 | 9/26/2011 | FRESNO | STROUD SUB | Solar PV | 10 | 12/28/2009 | N/A | N/A | N/A | N/A | N/A | 1/21/2011 | N/A | Executed | Former queue position: W65
2010-01-19 14:22 | 0080-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | MERCED SUB | Solar PV | 2.5 | 1/26/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W68
2010-01-19 14:24 | 0081-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | MERCED SUB | Solar PV | 1.8 | 11/24/2009 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W53
2010-01-20 | 0082-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | EL NIDO SUB | Solar PV | 20 | 1/26/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W69
2010-01-20 | 0083-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | EL NIDO SUB | Solar PV | 12 | 1/26/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W70
2010-01-20 | 0084-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | MERCED SUB | Solar PV | 20 | 1/26/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W71
2010-01-21 11:30 | 0085-WD | Independent Study | Independent Study | Withdrawn | 12/1/2011 | Withdrawn | Withdrawn | FRESNO | GIFFEN SUB | Solar PV | 12 | 2/17/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W74
2010-01-21 11:30 | 0086-WD | Independent Study | Independent Study | Withdrawn | 4/1/2011 | Withdrawn | Withdrawn | MERCED | SANTA NELLA SUB | Solar PV | 6 | 2/19/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W78
2010-01-21 12:35 | 0087-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | LASSEN | HAMILTON BRANCH SUB | Solar PV | 20 | 3/7/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W82
2010-01-21 12:35 | 0088-WD | Independent Study | Independent Study | Withdrawn | 1/1/2011 | Withdrawn | Withdrawn | COLUSA | COLUSA JUNCTION | Solar PV | 16 | 3/7/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W83
2010-01-21 12:35 | 0089-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SACRAMENTO | CATLETT SUB | Solar PV | 13 | 3/7/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W84
2010-01-21 12:35 | 0090-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | EL DORADO | CLARKSVILLE SUB | Solar PV | 20 | 3/7/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W85
2010-01-21 12:35 | 0091-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | EL DORADO | CLARKSVILLE SUB | Solar PV | 20 | 3/7/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W86
2010-02-01 10:12 | 0092-WD | Independent Study | Independent Study | Withdrawn | 4/1/2011 | Withdrawn | Withdrawn | TULARE | STONE CORRAL SUB | Solar PV | 2 | 2/17/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W73
2010-02-01 10:12 | 0093-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | CHOWCHILLA SUB | Solar PV | 10 | 2/17/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W75
2010-02-01 10:12 | 0094-WD | Independent Study | Independent Study | In Service | 4/1/2011 | 10/31/2014 | 3/30/2015 | KINGS/TULARE | CORCORAN SUB | Solar PV | 12 | 2/4/2010 | N/A | N/A | N/A | N/A | N/A | 8/31/2010 | 5/2/2012 | Executed | Former queue position: W76
2010-02-01 10:12 | 0095-WD | Independent Study | Independent Study | In Service | 12/1/2011 | 10/31/2014 | 12/9/2014 | KINGS/TULARE | CORCORAN SUB | Solar PV | 10 | 2/4/2010 | N/A | N/A | N/A | N/A | N/A | 9/22/2010 | 7/11/2012 | Executed | Former queue position: W77
2010-02-05 | 0096-WD | Independent Study | Independent Study | In Service | Not Provided | 5/31/2015 | 4/3/2015 | KERN | 7TH STANDARD SUB | Solar PV | 20 | 3/17/2010 | N/A | N/A | N/A | N/A | N/A | 6/21/2010 | N/A | Executed | Former queue position: W72
2010-02-09 | 0097-WD | Fast Track | Fast Track | In Service | 6/30/2010 | 7/1/2011 | 10/18/2011 | SANTA CLARA | SARATOGA SUB | Hydro | 0.108 | 4/26/2010 | 10/6/2010 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | Former queue position: W79
2010-02-09 12:22 | 0098-WD | Fast Track | Fast Track | In Service | 4/1/2010 | 8/25/2010 | 8/5/2010 | MARIN | OLEMA SUB | Engine | 0.08 | 4/2/2010 | 4/26/2010 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | Former queue position: W79a
2010-02-12 | 0099-WD | Independent Study | Independent Study | Withdrawn | 8/31/2010 | Withdrawn | Withdrawn | YOLO | DEEPWATER SUB | Solar PV | 20 | 4/15/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W79b
2010-02-12 | 0100-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | CHOWCHILLA SUB | Solar PV | 3 | 3/28/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W93
2010-02-17 | 0101-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | LE GRAND SUB | Solar PV | 1.5 | 2/17/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W80
2010-02-17 | 0102-WD | Independent Study | Independent Study | In Service | 5/1/2012 | 8/24/2012 | 11/13/2012 | KERN | TWISSELMAN SUB | Solar PV | 1.4701 | 3/7/2010 | N/A | N/A | N/A | N/A | N/A | 7/9/2010 | N/A | Executed | Former queue position: W81
2010-02-17 | 0103-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | TWISSELMAN SUB | Solar PV | 1.5 | 3/7/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W86a
2010-02-17 | 0104-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | LE GRAND SUB | Solar PV | 1.5 | 2/17/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W87
2010-02-26 | 0105-WD | Independent Study | Independent Study | In Service | 12/31/2010 | 6/30/2012 |  | SHASTA | JESSUP SUB | Steam Turbine | 6 | 3/26/2010 | N/A | N/A | N/A | N/A | N/A | 9/20/2010 | N/A | Executed | Former queue position: W90
2010-02-26 11:52 | 0106-WD | Independent Study | Independent Study | Withdrawn | 1/17/2014 | Withdrawn | Withdrawn | FRESNO | SAN JOAQUIN SUB | Solar PV | 20 | 3/8/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W91
2010-03-01 | 0107-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | EL DORADO | DIAMOND SPRINGS SUB | Hydro | 0.4 | 3/15/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W92
2010-03-09 10:15 | 0108-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | SCHINDLER SUB | Solar PV | 20 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W94
2010-03-09 10:15 | 0109-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | SAN JOAQUIN SUB | Solar PV | 20 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W95
2010-03-18 14:21 | 0110-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SOLANO | PEABODY SUB | Reciprocating Engine | 4.8 | 4/15/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W95a
2010-03-23 08:19 | 0111-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | LE GRAND SUB | Solar PV | 1.5 | 4/22/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W102
2010-03-23 08:22 | 0112-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | LE GRAND SUB | Solar PV | 1.5 | 4/22/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W101
2010-03-23 23:18 | 0113-WD | Independent Study | Independent Study | Withdrawn | 1/1/2015 | Withdrawn | Withdrawn | KERN | TWISSELMAN SUB | Solar PV | 15 | 4/7/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W96
2010-03-23 23:28 | 0114-WD | Independent Study | Independent Study | Withdrawn | 1/1/2015 | Withdrawn | Withdrawn | KERN | TWISSELMAN SUB | Solar PV | 15 | 4/7/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W97
2010-04-01 | 0115-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN LUIS OBISPO | CARRIZO PLAINS SUB | Solar PV | 6 | 5/14/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W98
2010-04-13 11:03 | 0116-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | EL PECO SUB | Solar PV | 3.5 | 5/12/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W108
2010-04-13 11:03 | 0117-WD | Independent Study | Independent Study | Withdrawn | 9/1/2011 | Withdrawn | Withdrawn | TULARE | STONE CORRAL SUB | Solar PV | 7 | 5/12/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W109
2010-04-13 11:03 | 0118-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | GOOSE LAKE SUB | Solar PV | 3 | 5/3/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W110
2010-04-13 11:03 | 0119-WD | Independent Study | Independent Study | Withdrawn | 6/1/2011 | Withdrawn | Withdrawn | KERN | SAN BERNARD SUB | Solar PV | 6 | 5/6/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W111
2010-04-14 16:35 | 0120-WD | Independent Study | Independent Study | In Service | 1/1/2015 | 12/31/2012 | 5/3/2013 | FRESNO | GATES SUB | Solar PV | 10 | 4/26/2010 | N/A | N/A | N/A | N/A | N/A | 5/7/2011 | N/A | Executed | Former queue position: W99
2010-04-15 14:44 | 0121-WD | Independent Study | Independent Study | Withdrawn | 9/1/2011 | Withdrawn | Withdrawn | MADERA | CHOWCHILLA SUB | Solar PV | 2 | 5/6/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W107
2010-04-15 17:08 | 0122-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | COPUS SUB | Solar PV | 20 | 5/4/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W100
2010-04-21 11:15 | 0123-WD | Independent Study | Independent Study | Withdrawn | 9/1/2011 | Withdrawn | Withdrawn | TEHAMA | TYLER SUB | Solar PV | 17.5 | 4/27/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W104
2010-04-22 16:20 | 0124-WD | Independent Study | Independent Study | In Service | 5/1/2011 | 12/15/2016 | 11/18/2016 | KINGS | AVENAL SUB | Solar PV | 15.8 | 5/4/2010 | N/A | N/A | N/A | N/A | N/A | 2/10/2011 | 02/08/2013 | Executed | Former queue position: W112
2010-04-26 | 0125-WD | Independent Study | Independent Study | Withdrawn | 3/30/2012 | Withdrawn | Withdrawn | KERN | OLD RIVER SUB | Solar PV | 5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W103
2010-04-26 14:43 | 0126-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | COPUS SUB | Solar PV | 10 | 5/5/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W105
2010-04-26 14:43 | 0127-WD | Independent Study | Independent Study | Withdrawn | 12/31/2011 | Withdrawn | Withdrawn | KERN | LAKEVIEW SUB | Solar PV | 18 | 5/5/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W106
2010-05-03 14:55 | 0128-WD | Independent Study | Independent Study | In Service | 6/28/2011 | 6/28/2011 | 8/17/2011 | ALAMEDA | CASTRO VALLEY SUB | Fuel Cell | 1.4 | 6/4/2010 | N/A | N/A | N/A | N/A | N/A | 8/10/2010 | N/A | Executed | Former queue position: W113
2010-05-03 14:55 | 0129-WD | Independent Study | Independent Study | In Service | 7/15/2011 | 7/15/2011 | 7/29/2011 | SAN FRANCISCO | DALY CITY SUB | Fuel Cell | 1.4 | 6/8/2010 | N/A | N/A | N/A | N/A | N/A | 8/10/2010 | N/A | Executed | Former queue position: W114
2010-05-17 13:47 | 0130-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | LE GRAND SUB | Solar PV | 3 | 8/4/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W142
2010-05-18 05:28 | 0131-WD | Independent Study | Independent Study | Withdrawn | 3/1/2015 | Withdrawn | Withdrawn | KERN | SAN BERNARD SUB | Solar PV | 10 | 5/18/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W117
2010-05-18 05:33 | 0132-WD | Independent Study | Independent Study | Withdrawn | 3/1/2015 | Withdrawn | Withdrawn | KERN | SAN BERNARD SUB | Solar PV | 10 | 5/18/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W118
2010-05-18 06:06 | 0133-WD | Independent Study | Independent Study | Withdrawn | 3/1/2015 | Withdrawn | Withdrawn | KERN | COPUS SUB | Solar PV | 20 | 5/18/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W116
2010-05-24 15:26 | 0134-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | CUYAMA SUB | Solar PV | 20 | 5/24/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W119
2010-05-24 15:57 | 0135-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | TUPMAN SUB | Solar PV | 20 | 6/10/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W120
2010-05-26 17:26 | 0136-WD | Independent Study | Independent Study | In Service | 12/1/2012 | 12/1/2012 | 6/19/2013 | KINGS | GUERNSEY SUB | Solar PV | 10 | 5/31/2010 | N/A | N/A | N/A | N/A | N/A | 4/3/2011 | N/A | Executed | Former queue position: W121
2010-06-01 | 0137-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | ARVIN SUB | Solar PV | 10 | 6/15/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W122
2010-06-01 | 0138-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | WHEELER RIDGE SUB | Solar PV | 20 | 6/15/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W123
2010-06-01 | 0139-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SONOMA | FULTON SUB | Solar PV | 0.5 | 6/14/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W124
2010-06-01 09:00 | 0140-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | LAMONT SUB | Solar PV | 20 | 6/15/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W125
2010-06-02 15:30 | 0141-WD | Independent Study | Independent Study | In Service | 2/1/2011 | 2/1/2015 | 10/17/2014 | YOLO | PUTAH CREEK SUB | Solar PV | 2 | Complete | N/A | N/A | N/A | N/A | N/A | 2/2/2011 | 1/22/2013 | Executed | Former queue position: W126
2010-06-08 16:14 | 0142-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | MCFARLAND SUB | Solar PV | 3 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W127
2010-06-18 16:14 | 0143-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | EL NIDO SUB | Solar PV | 5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W129
2010-06-18 16:31 | 0144-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | EL NIDO SUB | Solar PV | 10 | 6/22/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W130
2010-06-21 12:27 | 0145-WD | Fast Track | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MARIN | NOVATO SUB | Solar PV | 1 | 7/30/2010 | 7/30/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W132a
2010-06-21 14:38 | 0146-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | STROUD SUB | Solar PV | 20 | 8/8/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W131
2010-06-21 14:40 | 0147-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | GIFFEN SUB | Solar PV | 1.5 | 7/8/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W132
2010-06-28 15:51 | 0148-WD | Independent Study | Independent Study | Withdrawn | 6/1/2011 | Withdrawn | Withdrawn | FRESNO | HURON SUB | Solar PV | 20 | 7/8/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W133
2010-07-12 | 0149-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | COALINGA #1 SUB | Solar PV | 4 | 9/22/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W134
2010-07-23 11:13 | 0150-WD | Independent Study | Independent Study | Withdrawn | 1/1/2015 | Withdrawn | Withdrawn | FRESNO | GATES SUB | Solar PV | 5 | 7/26/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W139
2010-07-23 11:43 | 0151-WD | Independent Study | Independent Study | Withdrawn | 1/1/2015 | Withdrawn | Withdrawn | FRESNO | GATES SUB | Solar PV | 5 | 7/26/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W138
2010-07-25 06:09 | 0152-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | CANTUA SUB | Solar PV | 20 | 7/26/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W137
2010-07-26 09:18 | 0153-WD | Independent Study | Independent Study | Withdrawn | 8/31/2012 | Withdrawn | Withdrawn | FRESNO | ORO LOMA SUB | Solar PV | 2 | 8/17/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W135
2010-07-26 09:18 | 0154-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | ORO LOMA SUB | Solar PV | 20 | 8/17/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W136
2010-07-27 12:00 | 0155-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MONTEREY | JOLON SUB | Solar PV | 8.5 | 7/27/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W140
2010-07-29 12:00 | 0156-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN LUIS OBISPO | SAN MIGUEL SUB | Solar PV | 12 | 7/29/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W141
2010-08-05 | 0157-WD | Independent Study | Independent Study | Withdrawn | 12/1/2011 | Withdrawn | Withdrawn | KERN | MCFARLAND SUB | Solar PV | 18.3 | 8/17/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W143
2010-08-06 11:00 | 0158-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | MARICOPA SUB | Solar PV | 11.5 | 8/16/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W144
2010-08-06 13:27 | 0159-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MONTEREY | JOLON SUB | Solar PV | 3 | 9/1/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W146
2010-08-06 13:28 | 0160-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MONTEREY | JOLON SUB | Solar PV | 3 | 9/1/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W145
2010-08-19 | 0161-WD | Independent Study | Independent Study | Withdrawn | 2/11/2011 | Withdrawn | Withdrawn | CONTRA COSTA | HERDLYN SUB | Solar PV | 1.5 | 8/20/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W147
2010-08-25 07:36 | 0162-WD | Independent Study | Independent Study | In Service | 12/24/2012 | 12/24/2012 | 11/26/2013 | ALAMEDA | CAYETANO SUB | Engine | 4.308 | 10/6/2010 | N/A | N/A | N/A | N/A | N/A | 5/22/2011 | N/A | Executed | Former queue position: W148
2010-08-30 07:10 | 0163-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | ROUGH & READY SUB | Solar PV | 16 | 10/6/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W149-Rev
2010-09-03 08:44 | 0164-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | SANTA RITA SUB | Solar PV | 3 | 9/13/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W150
2010-09-03 14:14 | 0165-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | TWISSELMAN SUB | Solar PV | 3 | 11/7/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W151
2010-09-03 14:14 | 0166-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | KETTLEMAN HILLS SUB | Solar PV | 3 | 11/12/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W152
2010-09-03 14:14 | 0167-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | KETTLEMAN HILLS SUB | Solar PV | 3 | 11/12/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W153
2010-09-07 10:00 | 0168-WD | Independent Study | Independent Study | In Service | 3/31/2012 | 11/30/2012 | 9/13/2012 | FRESNO | WEST FRESNO SUB | Solar PV | 1.5 | 9/7/2010 | N/A | N/A | N/A | N/A | N/A | 6/2/2011 | N/A | Executed | Former queue position: W154
2010-09-07 10:00 | 0169-WD | Independent Study | Independent Study | In Service | 12/24/2012 | 12/24/2012 | 10/29/2013 | SAN JOAQUIN | CORRAL SUB | Engine | 5 | 9/16/2010 | N/A | N/A | N/A | N/A | N/A | 4/1/2011 | N/A | Executed | Former queue position: W155
2010-09-10 16:23 | 0170-WD | Independent Study | Independent Study | Withdrawn | 12/14/2012 | Withdrawn | Withdrawn | MADERA | FIGARDEN SUB | Solar PV | 3 | 12/8/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W156
2010-09-10 16:24 | 0171-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | MERCED FALLS SUB | Solar PV | 3 | 12/8/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W157
2010-09-10 16:24 | 0172-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | MERCED FALLS SUB | Solar PV | 3 | 12/8/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W158
2010-09-10 16:26 | 0173-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | LE GRAND SUB | Solar PV | 3 | 12/9/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W159
2010-09-10 16:26 | 0174-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | LE GRAND SUB | Solar PV | 3 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W160
2010-09-13 16:00 | 0175-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MENDOCINO | Withdrawn | Solar PV | 1.1 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2010-09-21 17:32 | 0176-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | TWISSELMAN SUB | Solar PV | 3 | 1/18/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W163
2010-09-21 17:33 | 0177-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | SANTA RITA SUB | Solar PV | 3 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W161
2010-09-21 17:35 | 0178-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | SANTA RITA SUB | Solar PV | 3 | 9/21/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W162
2010-09-22 10:00 | 0179-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN LUIS OBISPO | CHOLAME SUB | Solar PV | 5 | 11/18/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W164
2010-09-28 06:55 | 0180-WD | Independent Study | Independent Study | Withdrawn | 12/24/2012 | Withdrawn | Withdrawn | MONTEREY | PRUNEDALE SUB | Reciprocating Engine | 4.308 | 12/8/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W166
2010-09-28 15:00 | 0181-WD | Independent Study | Independent Study | Withdrawn | 3/31/2013 | Withdrawn | Withdrawn | SOLANO | PEABODY SUB | Solar PV | 14 | 9/28/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W165
2010-09-29 11:55 | 0182-WD | Independent Study | Independent Study | Withdrawn | 3/31/2012 | Withdrawn | Withdrawn | YOLO | PLAINFIELD SUB | Solar PV | 20 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W167
2010-09-29 12:02 | 0183-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | YOLO | WOODLAND SUB | Solar PV | 20 | 1/19/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W168-Rev
2010-09-29 12:07 | 0184-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | YOLO | WOODLAND SUB | Solar PV | 5 | 1/19/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W169
2010-09-30 11:56 | 0185-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | MIDWAY SUB | Solar PV | 20 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W170-Rev
2010-10-08 15:55 | 0186-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | SCHINDLER SUB | Solar PV | 20 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W171
2010-10-12 16:12 | 0187-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | WESTPARK SUB | Reciprocating Engine | 19.4 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W171a
2010-10-20 09:54 | 0188-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | BUTTE | PEACHTON SUB | Solar PV | 6 | 11/3/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W172
2010-10-20 15:00 | 0189-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | REEDLEY SUB | Solar PV | 9 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W173
2010-10-20 15:00 | 0190-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | GUSTINE SUB | Solar PV | 20 | 10/22/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W174
2010-10-20 15:00 | 0191-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | GOOSE LAKE SUB | Solar PV | 9 | 10/22/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W175
2010-10-20 15:00 | 0192-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | GOOSE LAKE SUB | Solar PV | 15 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W176
2010-10-20 15:00 | 0193-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | GUSTINE SUB | Solar PV | 20 | 10/22/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W177
2010-10-21 15:00 | 0194-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | BUTTE | PEACHTON SUB | Solar PV | 6 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Duplicate entry; former queue position: W178
2010-10-26 07:15 | 0195-WD | Independent Study | Independent Study | Withdrawn | 6/20/2012 | Withdrawn | Withdrawn | COLUSA | COLUSA JUNCTION | Solar PV | 5 | 1/21/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W179
2010-10-27 15:00 | 0196-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | DEVILS DEN SUB | Solar PV | 20 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W181
2010-10-28 16:08 | 0197-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | PLACER | PLEASANT GROVE SUB | Solar PV | 5 | 1/21/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W205a
2010-10-28 19:12 | 0198-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | LAMONT SUB | Reciprocating Engine | 3.2 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W182
2010-11-01 12:20 | 0199-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | PLACER | PENRYN SUB | Solar PV | 0.096 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W180
2010-11-05 06:27 | 0200-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | SMYRNA SUB | Solar PV | 20 | 1/24/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W184
2010-11-05 10:59 | 0201-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | LAMMERS SUB | Solar PV | 16 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W186
2010-11-12 16:15 | 0202-WD | Independent Study | Independent Study | Withdrawn | 3/31/2012 | Withdrawn | Withdrawn | FRESNO | DEVILS DEN SUB | Solar PV | 20 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W187
2010-11-16 15:00 | 0203-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | ELK HILLS SUB | Solar PV | 20 | 12/20/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W188
2010-11-16 18:29 | 0204-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | LAMMERS SUB | Solar PV | 8 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W185
2010-11-23 13:23 | 0205-WD | Independent Study | Independent Study | Withdrawn | 8/31/2012 | Withdrawn | Withdrawn | SAN JOAQUIN | TRACY SUB | Solar PV | 2 | 1/21/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W189
2010-11-23 13:23 | 0206-WD | Independent Study | Independent Study | Withdrawn | 8/31/2012 | Withdrawn | Withdrawn | SAN JOAQUIN | TRACY SUB | Solar PV | 3 | 1/12/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W190
2010-11-23 13:23 | 0207-WD | Independent Study | Independent Study | Withdrawn | 8/31/2012 | Withdrawn | Withdrawn | SAN JOAQUIN | WEBER SUB | Solar PV | 4 | 1/11/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W191
2010-11-23 13:23 | 0208-WD | Independent Study | Independent Study | Withdrawn | 8/31/2012 | Withdrawn | Withdrawn | SAN JOAQUIN | TRACY SUB | Solar PV | 4 | 1/12/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W192
2010-11-23 13:23 | 0209-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | LAMMERS SUB | Solar PV | 1 | Complete | 2/16/2011 | Fail Screens: 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W193
2010-11-23 13:23 | 0210-WD | Independent Study | Independent Study | Withdrawn | 8/31/2012 | Withdrawn | Withdrawn | SAN JOAQUIN | WEBER SUB | Solar PV | 4 | 1/12/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W194
2010-11-24 17:41 | 0211-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | CHENEY SUB | Solar PV | 1.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W195
2010-11-24 17:41 | 0212-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | CHENEY SUB | Solar PV | 1.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W196
2010-11-24 17:41 | 0213-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | CHENEY SUB | Solar PV | 1.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W197
2010-11-24 17:41 | 0214-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | CHENEY SUB | Solar PV | 1.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W198
2010-11-24 17:41 | 0215-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | CAMDEN SUB | Solar PV | 1.5 | 12/20/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W199
2010-11-29 07:32 | 0216-WD | Independent Study | Independent Study | Withdrawn | 8/31/2012 | Withdrawn | Withdrawn | SAN JOAQUIN | WEBER SUB | Solar PV | 4 | 1/12/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W200
2010-11-29 07:32 | 0217-WD | Independent Study | Independent Study | Withdrawn | 8/31/2012 | Withdrawn | Withdrawn | SAN JOAQUIN | WEBER SUB | Solar PV | 2 | 11/30/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W201
2010-11-30 10:01 | 0218-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | YUBA | OLIVEHURST SUB | Solar PV | 1.2 | 12/1/2010 | 5/10/2011 | Fail Screens: 2, 5, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W183
2010-12-08 08:33 | 0219-WD | Independent Study | Independent Study | Withdrawn | 12/1/2011 | Withdrawn | Withdrawn | KINGS | HARDWICK SUB | Reciprocating Engine | 0.925 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W202
2010-12-14 10:00 | 0220-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Solar PV | 20 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W203
2010-12-16 11:12 | 0221-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | WEST FRESNO SUB | Solar PV | 1 | 1/24/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W204
2010-12-17 09:09 | 0222-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | TWISSELMAN SUB | Solar PV | 1.5 | 12/20/2010 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W205
2010-12-20 16:54 | 0223-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | CALAVERAS | FROGTOWN SUB | Solar PV | 15 | 1/19/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W207
2010-12-20 18:26 | 0224-WD | Independent Study | Independent Study | In Service | 6/13/2013 | 9/30/2015 | 10/24/2016 | FRESNO | WOODWARD SUB | Hydro | 8 | 1/6/2011 | N/A | N/A | N/A | N/A | N/A | 9/20/2011 | N/A | Executed | Former queue position: W206
2010-12-23 09:38 | 0225-WD | Independent Study | Independent Study | Withdrawn | 12/14/2012 | Withdrawn | Withdrawn | FRESNO | REEDLEY SUB | Solar PV | 3 | 1/28/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W208
2010-12-23 14:26 | 0226-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | NAPA | HIGHWAY SUB | Solar PV | 6.7 | 1/28/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W209
2010-12-30 10:26 | 0227-WD | Independent Study | Independent Study | In Service | 12/24/2012 | 12/24/2012 | 10/23/2013 | SAN JOAQUIN | WEBER SUB | Engine | 4.2 | 1/31/2011 | N/A | N/A | N/A | N/A | N/A | 5/23/2011 | N/A | Executed | Former queue position: W210
2010-12-31 11:22 | 0228-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | BONITA SUB | Solar PV | 0.096 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W211
2011-01-04 15:13 | 0229-WD | Cluster | Cluster | Withdrawn | 9/30/2012 | Withdrawn | Withdrawn | KINGS | GUERNSEY SUB | Solar PV | 12 | 2/15/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W212
2011-01-04 17:58 | 0230-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CLARA | SWIFT SUB | Solar PV | 5 | 9/26/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W213
2011-01-14 12:50 | 0231-WD | Independent Study | Independent Study | Withdrawn | 10/1/2012 | Withdrawn | Withdrawn | FRESNO | COALINGA #1 SUB | Solar PV | 6 | 1/24/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W214
2011-01-19 10:00 | 0232-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | MERCED FALLS SUB | Solar PV | 3 | 2/2/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W215
2011-01-21 15:00 | 0233-WD | Fast Track | Independent Study | In Service | 4/15/2012 | 10/22/2013 | 1/10/2014 | STANISLAUS | RIVERBANK SUB | Engine | 1.2 | 5/10/2011 | 6/2/2011 | Fail Screens: 2, 10 | 8/2/2011 | Fail | N/A | 9/10/2012 | N/A | Executed | Former queue position: W216
2011-01-26 12:55 | 0234-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | VICTOR SUB | Solar PV | 0.095 | Complete | 2/8/2011 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W217
2011-01-26 17:47 | 0235-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA BARBARA | CUYAMA SUB | Solar PV | 3 | 1/26/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W218
2011-01-26 17:47 | 0236-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA BARBARA | CUYAMA SUB | Solar PV | 3 | 1/26/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W219
2011-01-28 12:35 | 0237-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | STANISLAUS | CROWS LANDING SUB | Solar PV | 20 | 4/4/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W220-Rev
2011-01-28 12:47 | 0238-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | CAMDEN SUB | Solar PV | 1.5 | 5/2/2011 | 5/20/2011 | Fail Screens: 2, 10 | 6/27/2011 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W221
2011-01-28 12:47 | 0239-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | CAMDEN SUB | Solar PV | 1.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W222-Rev
2011-01-28 18:24 | 0240-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | CAMDEN SUB | Solar PV | 1.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W223-Rev
2011-01-28 18:24 | 0241-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | CAMDEN SUB | Solar PV | 1.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W224-Rev
2011-01-28 18:29 | 0242-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | CAMDEN SUB | Solar PV | 1.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W225-Rev
2011-01-31 16:50 | 0243-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV | 25 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W226-Rev
2011-01-31 16:50 | 0244-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | GOOSE LAKE SUB | Solar PV | 20 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W227-Rev
2011-01-31 16:50 | 0245-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | LAKEVIEW SUB | Solar PV | 30 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W228-Rev
2011-02-01 11:00 | 0246-WD | Cluster | Cluster | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | GANSO SUB | Solar PV | 20 | 2/1/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W229
2011-02-01 11:01 | 0247-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | CHOWCHILLA SUB | Solar PV | 3 | 2/1/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W230-Rev
2011-02-02 09:30 | 0248-WD | Independent Study | Independent Study | In Service | 6/30/2012 | 2/28/2014 | 10/23/2013 | KERN | OLD RIVER SUB | Engine | 2 | 2/3/2011 | N/A | N/A | N/A | N/A | N/A | 5/18/2012 | 1/29/2013 | Executed | Former queue position: W231-Rev
2011-02-09 11:51 | 0249-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | YOLO | DAVIS SUB | Solar PV | 16 | 2/14/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W232
2011-02-10 15:56 | 0250-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | CHENEY SUB | Solar PV | 1 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W233-Rev
2011-02-18 08:06 | 0251-WD | Independent Study | Independent Study | Withdrawn | 9/1/2012 | Withdrawn | Withdrawn | KERN | CHARCA SUB | Solar PV | 2 | 5/2/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W234
2011-02-18 08:06 | 0252-WD | Independent Study | Independent Study | Withdrawn | 9/1/2012 | Withdrawn | Withdrawn | KERN | WASCO SUB | Solar PV | 2 | 5/2/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W235
2011-02-22 14:32 | 0253-WD | Cluster | Cluster | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | TAFT SUB | Solar PV | 20 | 2/25/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W236-Rev
2011-02-22 14:34 | 0254-WD | Independent Study | Independent Study | Withdrawn | 1/31/2012 | Withdrawn | Withdrawn | KERN | GOOSE LAKE SUB | Solar PV | 20 | 2/22/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W237
2011-02-22 14:35 | 0255-WD | Cluster | Cluster | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | MIDWAY SUB | Solar PV | 10 | 3/14/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W238-Rev
2011-02-25 12:25 | 0256-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | COPUS SUB | Solar PV | 2 | 3/10/2011 | 5/6/2011 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W239
2011-02-25 14:18 | 0257-WD | Independent Study | Independent Study | Withdrawn | 12/1/2013 | Withdrawn | Withdrawn | EL DORADO | APPLE HILL SUB | Hydro | 5 | 2/25/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W240
2011-02-25 17:51 | 0258-WD | Independent Study | Independent Study | Withdrawn | 12/1/2013 | Withdrawn | Withdrawn | FRESNO | SCHINDLER SUB | Solar PV | 20 | 1/5/2012 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W240-A1
2011-02-25 17:51 | 0259-WD | Cluster | Cluster | Withdrawn | 12/1/2014 | Withdrawn | Withdrawn | FRESNO | SCHINDLER SUB | Solar PV | 20 | 4/14/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W240-A2
2011-02-28 16:38 | 0260-WD | Fast Track | Fast Track | Withdrawn | 5/30/2013 | Withdrawn | Withdrawn | SANTA BARBARA | CUYAMA SUB | Solar PV | 3 | Complete | 4/27/2011 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W240a
2011-02-28 17:28 | 0261-WD | Fast Track | Fast Track | Withdrawn | 1/30/2013 | Withdrawn | Withdrawn | SANTA CLARA | EDENVALE SUB | Solar PV | 3.25 | 3/21/2011 | 6/20/2011 | Fail Screens: 2, 10 | 3/7/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W243-Rev
2011-02-28 17:28 | 0262-WD | Fast Track | Fast Track | Withdrawn | 1/30/2013 | Withdrawn | Withdrawn | SANTA CLARA | PIERCY SUB | Solar PV | 1.35 | 6/6/2011 | 6/14/2011 | Fail Screens: 2, 10 | 3/7/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W245c
2011-02-28 17:35 | 0263-WD | Fast Track | Fast Track | Withdrawn | 1/30/2013 | Withdrawn | Withdrawn | SANTA CLARA | LLAGAS SUB | Solar PV | 2.2 | 3/21/2011 | 6/21/2011 | Fail Screens: 2, 10 | 3/7/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W245d
2011-02-28 17:43 | 0264-WD | Fast Track | Fast Track | Withdrawn | 1/30/2013 | Withdrawn | Withdrawn | SANTA CLARA | MORGAN HILL SUB | Solar PV | 1.1 | 6/6/2011 | 6/21/2011 | Fail Screens: 10 | 3/7/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W245a
2011-02-28 17:46 | 0265-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CLARA | MORGAN HILL SUB | Solar PV | 1.1 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W241-Rev
2011-02-28 17:47 | 0266-WD | Fast Track | Fast Track | Withdrawn | 1/30/2013 | Withdrawn | Withdrawn | SANTA CLARA | EDENVALE SUB | Solar PV | 3.1 | 5/24/2011 | 6/21/2011 | Fail Screens: 2, 10 | 3/7/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W241a
2011-02-28 17:50 | 0267-WD | Fast Track | Fast Track | Withdrawn | 1/30/2013 | Withdrawn | Withdrawn | SANTA CLARA | MORGAN HILL SUB | Solar PV | 1.5 | 3/21/2011 | 6/7/2011 | Fail Screens: 2, 10 | 3/7/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W245-Rev
2011-02-28 17:53 | 0268-WD | Fast Track | Fast Track | Withdrawn | 1/30/2013 | Withdrawn | Withdrawn | SANTA CLARA | MORGAN HILL SUB | Solar PV | 1.2 | 3/21/2011 | 6/21/2011 | Fail Screens: 10 | 3/7/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W244-Rev
2011-03-01 09:47 | 0269-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CLARA | EDENVALE SUB | Solar PV | 3.25 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Duplicate entry; former queue position: W245b
2011-03-01 15:01 | 0270-WD | Fast Track | Fast Track | Withdrawn | 3/8/2012 | Withdrawn | Withdrawn | CONTRA COSTA | TIDEWATER SUB | Solar PV | 0.999 | 3/18/2011 | 4/26/2011 | Fail Screens: 2, 6, 10 | 11/16/2011 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W245e
2011-03-01 15:01 | 0271-WD | Fast Track | Fast Track | In Service | 12/30/2012 | 4/5/2014 | 2/21/2014 | BUTTE | WYANDOTTE SUB | Solar PV | 0.999 | 10/25/2011 | 11/22/2011 | Fail Screens: 2, 10 | 3/8/2012 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | Former queue position: W301
2011-03-01 16:13 | 0272-WD | Fast Track | Fast Track | In Service | 3/8/2012 | 3/31/2013 | 1/31/2014 | SAN BENITO | HOLLISTER SUB | Solar PV | 1.5 | 3/23/2011 | 4/20/2011 | Fail Screens: 2, 10 | 10/3/2011 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | Former queue position: W245f
2011-03-01 16:33 | 0273-WD | Fast Track | Fast Track | Withdrawn | 3/8/2012 | Withdrawn | Withdrawn | TEHAMA | GERBER SUB | Solar PV | 1.5 | 3/23/2011 | 4/29/2011 | Fail Screens: 2, 5, 10 | 8/10/2011 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W245g
2011-03-01 17:51 | 0274-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SOLANO | VACA DIXON SUB | Solar PV | 2 | 4/8/2011 | 5/4/2011 | Fail Screens: 2, 10 | 9/19/2011 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W246a
2011-03-01 18:51 | 0275-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | TRACY SUB | Solar PV | 2.296 | Complete | 4/11/2011 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W242-Rev
2011-03-01 18:51 | 0276-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | DIABLO | CONTRA COSTA SUB | Solar PV | 2.296 | 3/16/2011 | 4/11/2011 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W247-Rev
2011-03-01 18:52 | 0277-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | WEBER SUB | Solar PV | 2.296 | Complete | 2011-04-11 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W246b
2011-03-02 01:58 | 0278-WD | Fast Track | Fast Track | Withdrawn | 5/30/2012 | Withdrawn | Withdrawn | SANTA CLARA | TRIMBLE SUB | Solar PV | 1.5 | Complete | 6/8/2011 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W245h
2011-03-02 01:58 | 0279-WD | Fast Track | Fast Track | Withdrawn | 5/30/2013 | Withdrawn | Withdrawn | SAN JOAQUIN | DIXON LANDING SUB | Solar PV | 1.5 | Complete | 4/28/2011 | Fail Screens: 6, 10 | 8/23/2011 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W245i
2011-03-02 01:58 | 0280-WD | Fast Track | Fast Track | Withdrawn | 5/30/2013 | Withdrawn | Withdrawn | SANTA CLARA | TRIMBLE SUB | Solar PV | 1 | Complete | 6/8/2011 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W245j
2011-03-02 01:58 | 0281-WD | Fast Track | Fast Track | Withdrawn | 5/30/2013 | Withdrawn | Withdrawn | ALAMEDA | NEWARK SUB | Solar PV | 1 | Complete | 4/28/2011 | Fail Screens: 2, 10 | 8/23/2011 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W245k
2011-03-02 01:58 | 0282-WD | Fast Track | Fast Track | Withdrawn | 5/30/2013 | Withdrawn | Withdrawn | ALAMEDA | SAN LEANDRO U SUB | Solar PV | 2 | Complete | 6/8/2011 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W245l
2011-03-02 01:58 | 0283-WD | Fast Track | Fast Track | Withdrawn | 5/30/2013 | Withdrawn | Withdrawn | ALAMEDA | SAN LEANDRO U SUB | Solar PV | 1 | Complete | 6/8/2011 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W245m
2011-03-02 01:58 | 0284-WD | Fast Track | Fast Track | Withdrawn | 5/30/2012 | Withdrawn | Withdrawn | ALAMEDA | JARVIS SUB | Solar PV | 1.5 | Complete | 5/12/2011 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W245n
2011-03-02 01:58 | 0285-WD | Fast Track | Fast Track | Withdrawn | 5/30/2012 | Withdrawn | Withdrawn | CONTRA COSTA | JARVIS SUB | Solar PV | 1.5 | Complete | 5/17/2011 | Fail | 10/26/2011 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W245o
2011-03-02 01:58 | 0286-WD | Fast Track | Fast Track | Withdrawn | 5/30/2012 | Withdrawn | Withdrawn | CONTRA COSTA | EDES SUB | Solar PV | 1.5 | Complete | 6/8/2011 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W245p
2011-03-02 01:58 | 0287-WD | Fast Track | Fast Track | Withdrawn | 5/30/2012 | Withdrawn | Withdrawn | SAN JOAQUIN | TRACY SUB | Solar PV | 2 | 3/22/2011 | 5/4/2011 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W245q
2011-03-02 07:45 | 0288-WD | Fast Track | Fast Track | In Service | Not Provided | 10/15/2013 | 11/19/2013 | SAN JOAQUIN | LOCKEFORD SUB | Solar PV | 1.5 | 3/18/2011 | 4/8/2011 | Fail Screens: 2, 10 | 6/16/2011 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | Former queue position: W246-Rev
2011-03-02 11:13 | 0289-WD | Fast Track | Fast Track | Withdrawn | 3/3/2013 | Withdrawn | Withdrawn | FRESNO | STROUD SUB | Solar PV | 1.45 | 3/18/2011 | 4/19/2011 | Fail Screens: 2, 10 | 6/2/2011 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W249
2011-03-02 11:15 | 0290-WD | Fast Track | Fast Track | Withdrawn | 1/30/2012 | Withdrawn | Withdrawn | FRESNO | STROUD SUB | Solar PV | 1.45 | Complete | 4/7/2011 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W246c
2011-03-02 12:42 | 0291-WD | Fast Track | Fast Track | Withdrawn | 11/1/2012 | Withdrawn | Withdrawn | SAN JOAQUIN | VICTOR SUB | Solar PV | 0.87 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W246d
2011-03-02 12:42 | 0292-WD | Fast Track | Fast Track | Withdrawn | 11/1/2012 | Withdrawn | Withdrawn | STANISLAUS | WESTLEY SUB | Solar PV | 1.74 | 4/14/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W246e
2011-03-02 12:47 | 0293-WD | Fast Track | Fast Track | Withdrawn | 9/25/2013 | Withdrawn | Withdrawn | BUTTE | NORD SUB | Solar PV | 6.01 | Complete | 6/1/2011 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W248
2011-03-02 13:08 | 0294-WD | Fast Track | Fast Track | Withdrawn | 2/29/2012 | Withdrawn | Withdrawn | FRESNO | KINGSBURG SUB | Solar PV | 1.8 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W246f
2011-03-03 09:25 | 0295-WD | Fast Track | Fast Track | Withdrawn | 1/30/2012 | Withdrawn | Withdrawn | CONTRA COSTA | BRENTWOOD SUB | Solar PV | 1.25 | Complete | 5/24/2011 | Fail Screens: 2, 6 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W260
2011-03-08 | 0296-WD | Fast Track | Fast Track | Withdrawn | 8/30/2012 | Withdrawn | Withdrawn | MENDOCINO | UKIAH SUB | Solar PV | 12 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W250
2011-03-08 | 0297-WD | Fast Track | Fast Track | Withdrawn | 8/30/2012 | Withdrawn | Withdrawn | MENDOCINO | UKIAH SUB | Solar PV | 2 | Complete | 8/26/2011 | Fail | 11/15/2011 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W251
2011-03-08 | 0298-WD | Fast Track | Fast Track | Withdrawn | 8/30/2012 | Withdrawn | Withdrawn | SAN JOAQUIN | MORMON SUB | Solar PV | 2 | Complete | 9/21/2011 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W252
2011-03-08 | 0299-WD | Fast Track | Fast Track | Withdrawn | 8/30/2012 | Withdrawn | Withdrawn | SAN JOAQUIN | CARBONA SUB | Solar PV | 2 | Complete | 6/28/2011 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W253
2011-03-08 | 0300-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MENDOCINO | HOPLAND SUB | Solar PV | 2 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Duplicate entry; former queue position: W254
2011-03-08 | 0301-WD | Fast Track | Fast Track | Withdrawn | 8/30/2012 | Withdrawn | Withdrawn | SAN JOAQUIN | LAMMERS SUB | Solar PV | 2 | Complete | 6/28/2011 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W255
2011-03-08 | 0302-WD | Fast Track | Fast Track | Withdrawn | 8/30/2012 | Withdrawn | Withdrawn | SHASTA | DESCHUTES SUB | Solar PV | 2 | Complete | 7/29/2011 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W256
2011-03-08 | 0303-WD | Fast Track | Fast Track | Withdrawn | 7/1/2012 | Withdrawn | Withdrawn | MENDOCINO | CALPELLA SUB | Solar PV | 2 | 6/15/2011 | 8/26/2011 | Fail Screens: 2, 10 | 11/14/2011 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W257
2011-03-08 | 0304-WD | Fast Track | Fast Track | Withdrawn | 7/1/2012 | Withdrawn | Withdrawn | MENDOCINO | CALPELLA SUB | Solar PV | 2 | 6/15/2011 | 8/26/2011 | Fail Screens: 2, 10 | 11/14/2011 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W258
2011-03-08 | 0305-WD | Fast Track | Fast Track | Withdrawn | 7/1/2012 | Withdrawn | Withdrawn | SAN JOAQUIN | AVENA SUB | Solar PV | 2 | 6/15/2011 | 8/26/2011 | Fail Screens: 2, 4, 10 | 11/14/2011 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W259
2011-03-15 13:44 | 0306-WD | Fast Track | Fast Track | Withdrawn | 7/1/2012 | Withdrawn | Withdrawn | MENDOCINO | UKIAH SUB | Solar PV | 2 | 8/1/2011 | 8/29/2011 | Fail Screens: 2, 10 | 11/14/2011 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W261
2011-03-15 13:53 | 0307-WD | Fast Track | Fast Track | Withdrawn | 8/30/2012 | Withdrawn | Withdrawn | SAN JOAQUIN | LODI SUB | Solar PV | 2 | Complete | 8/26/2011 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W262
2011-03-21 | 0308-WD | Independent Study | Independent Study | Withdrawn | 3/31/2012 | Withdrawn | Withdrawn | KERN | POSO MTN SUB | Solar PV | 1.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W263
2011-03-22 | 0309-WD | Fast Track | Fast Track | Withdrawn | 6/1/2012 | Withdrawn | Withdrawn | KERN | ELK HILLS SUB | Solar PV | 2.8 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W264
2011-03-22 11:25 | 0310-WD | Cluster | Cluster | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | LE GRAND SUB | Solar PV | 3 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Duplicate entry; former queue position: W265
2011-03-24 07:45 | 0311-WD | Fast Track | Independent Study | In Service | 1/2/2013 | 12/20/2013 | 3/17/2014 | NAPA | CALISTOGA SUB | Engine | 0.84 | 4/12/2011 | 4/28/2011 | Fail Screens: 2, 4, 10 | N/A | N/A (Independent Study) | Pass | 1/18/2012 | N/A | Executed | Former queue position: W268
2011-03-24 11:36 | 0312-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | OLD RIVER SUB | Solar PV | 3 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Duplicate entry; former queue position: W269
2011-03-24 13:26 | 0313-WD | Fast Track | Fast Track | Withdrawn | 5/16/2013 | Withdrawn | Withdrawn | KERN | TEJON SUB | Solar PV | 2.05 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W266
2011-03-24 13:26 | 0314-WD | Fast Track | Fast Track | Withdrawn | 2/15/2013 | Withdrawn | Withdrawn | KERN | ELK HILLS SUB | Solar PV | 2.05 | 4/7/2011 | 7/7/2011 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W267
2011-03-28 08:54 | 0315-WD | Cluster | Cluster | Withdrawn | 12/31/2012 | Withdrawn | Withdrawn | KINGS | CORCORAN SUB | Solar PV | 8 | 4/28/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Duplicate entry; former queue position: W269a
2011-03-28 12:03 | 0316-WD | Fast Track | Fast Track | Withdrawn | 2/28/2013 | Withdrawn | Withdrawn | KERN | ARVIN SUB | Solar PV | 2 | 5/16/2011 | 6/2/2011 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W270
2011-03-28 15:00 | 0317-WD | Cluster | Cluster | Withdrawn | 12/3/2012 | Withdrawn | Withdrawn | FRESNO | SAN JOAQUIN SUB | Solar PV | 8 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W271
2011-03-29 09:00 | 0318-WD | Cluster | Cluster | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | CANTUA SUB | Solar PV | 20 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W271-1a
2011-03-29 16:26 | 0319-WD | Fast Track | Fast Track | Withdrawn | 3/1/2013 | Withdrawn | Withdrawn | FRESNO | CANTUA SUB | Solar PV | 2 | 9/8/2011 | 10/26/2011 | Fail Screens: 2, 10 | 12/12/2011 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W271-2a
2011-03-29 22:11 | 0320-WD | Cluster | Cluster | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | STROUD SUB | Solar PV | 20 | 6/15/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W271-aa
2011-03-30 15:29 | 0321-WD | Independent Study | Independent Study | Withdrawn | 8/31/2013 | Withdrawn | Withdrawn | SUTTER | MERIDIAN SUB | Solar PV | 5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W273f
2011-03-30 15:30 | 0322-WD | Independent Study | Independent Study | Withdrawn | 8/31/2013 | Withdrawn | Withdrawn | SUTTER | BARRY SUB | Solar PV | 19 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W273d
2011-03-30 15:39 | 0323-WD | Cluster | Cluster | Withdrawn | 12/1/2013 | Withdrawn | Withdrawn | FRESNO | SCHINDLER SUB | Solar PV | 5 | 5/9/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W271a
2011-03-30 16:10 | 0324-WD | Cluster | Cluster | Withdrawn | 12/15/2013 | Withdrawn | Withdrawn | KERN | MIDWAY SUB | Solar PV | 10 | 4/14/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W274-ac
2011-03-31 | 0325-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | MCFARLAND SUB | Solar PV | 18.3 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Duplicate entry; former queue position: W271b
2011-03-31 | 0326-WD | Cluster | Cluster | Withdrawn | 12/15/2013 | Withdrawn | Withdrawn | TEHAMA | VOLTA PH #1 SUB | Solar PV | 4.5 | 5/31/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W271c
2011-03-31 01:06 | 0327-WD | Fast Track | Fast Track | Withdrawn | 12/29/2011 | Withdrawn | Withdrawn | SONOMA | FITCH MTN SUB | Solar PV | 0.955 | 4/27/2011 | 10/10/2011 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W272
2011-03-31 07:34 | 0328-WD | Fast Track | Fast Track | Withdrawn | 6/27/2012 | Withdrawn | Withdrawn | AMADOR | PINE GROVE SUB | Solar PV | 1.5 | 4/28/2011 | 5/26/2011 | Fail Screens: 2, 10 | 2/7/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W273
2011-03-31 07:54 | 0329-WD | Cluster | Cluster | Withdrawn | 1/1/2014 | Withdrawn | Withdrawn | KERN | BLACKWELL SUB | Solar PV | 10.08 | 5/23/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W273e
2011-03-31 08:15 | 0330-WD | Fast Track | Fast Track | Withdrawn | 10/30/2011 | Withdrawn | Withdrawn | FRESNO | AUBERRY SUB | Solar PV | 1.2 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W273-aa
2011-03-31 11:59 | 0331-WD | Independent Study | Independent Study | Withdrawn | 9/1/2013 | Withdrawn | Withdrawn | KERN | RIO BRAVO SUB | Solar PV | 20.8 | 5/12/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W273a
2011-03-31 13:46 | 0332-WD | Cluster | Cluster | Withdrawn | 1/8/2013 | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV | 24 | 5/11/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W273b
2011-03-31 13:46 | 0333-WD | Cluster | Cluster | Withdrawn | 1/12/2013 | Withdrawn | Withdrawn | KERN | AVENAL SUB | Solar PV | 20 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W273g
2011-03-31 13:46 | 0334-WD | Cluster | Cluster | Withdrawn | 1/12/2013 | Withdrawn | Withdrawn | KERN | LAKEVIEW SUB | Solar PV | 30.3 | 5/11/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W273h
2011-03-31 14:48 | 0335-WD | Cluster | Cluster | Withdrawn | 2/29/2012 | Withdrawn | Withdrawn | FRESNO | HELM SUB | Solar PV | 21.2 | 8/1/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W273ba
2011-03-31 15:25 | 0336-WD | Cluster | Cluster | In Service | 3/31/2015 | 4/15/2016 | 1/15/2016 | SOLANO | PEABODY SUB | Engine | 9.6 | 9/20/2011 | N/A | N/A (Cluster) | N/A | N/A (Cluster) | N/A (Cluster) | 1/24/2012 | 1/18/2013 | Executed | Former queue position: W273bb
2011-03-31 15:34 | 0337-WD | Cluster | Cluster | Withdrawn | 12/31/2015 | Withdrawn | Withdrawn | KINGS | AVENAL SUB | Solar PV | 50 | 5/3/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W273c
2011-03-31 15:47 | 0338-WD | Fast Track | Fast Track | Withdrawn | 1/29/2012 | Withdrawn | Withdrawn | STANISLAUS | WESTLEY SUB | Reciprocating Engine | 1.5 | 5/3/2011 | 5/26/2011 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W274
2011-03-31 15:54 | 0339-WD | Cluster | Cluster | Withdrawn | 12/24/2011 | Withdrawn | Withdrawn | SUTTER | PEASE SUB | Solar PV | 1 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W274-aa
2011-03-31 15:54 | 0340-WD | Cluster | Cluster | Withdrawn | 12/24/2011 | Withdrawn | Withdrawn | SUTTER | PEASE SUB | Solar PV | 20 | 5/17/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W274-ab
2011-03-31 15:54 | 0341-WD | Cluster | Cluster | Withdrawn | 12/31/2013 | Withdrawn | Withdrawn | FRESNO | GIFFEN SUB | Solar PV | 3 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W274b
2011-03-31 15:58 | 0342-WD | Cluster | Cluster | In Service | 12/31/2013 | 4/18/2017 | 8/28/2017 | FRESNO | GIFFEN SUB | Solar PV | 9 | Complete | N/A | N/A (Cluster) | N/A | N/A (Cluster) | N/A (Cluster) | 2/18/2012 | 5/9/2013 | Executed | Former queue position: W274a
2011-03-31 15:58 | 0343-WD | Cluster | Cluster | In Service | 12/31/2013 | 5/11/2015 | 10/24/2015 | FRESNO | MENDOTA SUB | Solar PV | 5 | Complete | N/A | N/A (Cluster) | N/A | N/A (Cluster) | N/A (Cluster) | 11/29/2011 | 12/28/2012 | Executed | Former queue position: W274d
2011-03-31 15:59 | 0344-WD | Cluster | Cluster | Withdrawn | 12/31/2013 | Withdrawn | Withdrawn | FRESNO | MENDOTA SUB | Solar PV | 7 | 5/5/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W274c
2011-03-31 16:20 | 0345-WD | Cluster | Cluster | Withdrawn | 6/1/2013 | Withdrawn | Withdrawn | STANISLAUS | SALADO SUB | Solar PV | 20 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W274da
2011-04-01 16:03 | 0346-WD | Fast Track | Fast Track | Withdrawn | 5/31/2012 | Withdrawn | Withdrawn | SANTA CLARA | PIERCY SUB | Solar PV | 3 | 6/13/2011 | 11/9/2011 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W274e
2011-04-01 16:03 | 0347-WD | Fast Track | Fast Track | Withdrawn | 5/31/2012 | Withdrawn | Withdrawn | SANTA CLARA | PIERCY SUB | Solar PV | 3 | 6/13/2011 | 11/9/2011 | Fail Screens: 2, 6, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W274f
2011-04-19 | 0348-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | HARDWICK SUB | Gas Turbine | 0.925 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Duplicate entry; former queue position: W275
2011-04-19 16:59 | 0349-WD | Fast Track | Fast Track | In Service | 8/15/2011 | 4/2/2012 | 4/2/2012 | SHASTA | WHITMORE SUB | Hydro | 0.522 | 4/25/2011 | 5/2/2011 | Fail Screens: 2, 4, 9, 10 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | Former queue position: W276
2011-04-26 14:18 | 0350-WD | Fast Track | Fast Track | Withdrawn | 12/30/2012 | Withdrawn | Withdrawn | FRESNO | MENDOTA SUB | Solar PV | 1.002 | 6/28/2011 | 9/1/2011 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W276a
2011-05-11 11:44 | 0351-WD | Fast Track | Fast Track | Withdrawn | 9/29/2012 | Withdrawn | Withdrawn | KERN | OLD RIVER SUB | Solar PV | 1.52 | Complete | 2011-06-24 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W277
2011-05-12 | 0352-WD | Fast Track | Fast Track | Withdrawn | 8/1/2012 | Withdrawn | Withdrawn | KERN | OLD RIVER SUB | Solar PV | 1.52 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2011-05-20 13:02 | 0353-WD | Fast Track | Fast Track | Withdrawn | 11/30/2011 | Withdrawn | Withdrawn | ALAMEDA | HERDLYN SUB | Solar PV | 2.575 | 6/16/2011 | 7/13/2011 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W279
2011-06-08 15:37 | 0354-WD | Fast Track | Fast Track | In Service | 6/1/2012 | 6/15/2013 | 4/26/2013 | CONTRA COSTA | CONTRA COSTA SUB | Solar PV | 1.5 | 6/24/2011 | 8/10/2011 | Fail Screens: 6, 10 | 3/5/2012 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | Former queue position: W278
2011-06-28 | 0355-WD | Fast Track | Fast Track | Withdrawn | 7/30/2012 | Withdrawn | Withdrawn | MERCED | GUSTINE SUB | Reciprocating Engine | 1.6 | 8/9/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W280
2011-06-28 | 0356-WD | Fast Track | Fast Track | Withdrawn | 7/30/2012 | Withdrawn | Withdrawn | MERCED | GUSTINE SUB | Reciprocating Engine | 1.6 | 8/10/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W281
2011-06-28 11:07 | 0357-WD | Fast Track | Fast Track | Withdrawn | 11/3/2011 | Withdrawn | Withdrawn | PLACER | CATLETT SUB | Solar PV | 0.066 | 7/19/2011 | 10/10/2011 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W282
2011-07-02 11:52 | 0358-WD | Fast Track | Fast Track | In Service | 7/30/2011 | 11/20/2012 | 7/9/2013 | TEHAMA | RED BLUFF SUB | Solar PV | 0.5 | 9/14/2011 | 11/22/2011 | Fail Screens: 2, 10 | 3/8/2012 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | Former queue position: W282a
2011-07-13 14:46 | 0359-WD | Fast Track | Fast Track | Withdrawn | 3/15/2012 | Withdrawn | Withdrawn | MADERA | CHOWCHILLA SUB | Solar PV | 0.75 | 7/26/2011 | 11/4/2011 | Fail Screens: 2, 10 | 1/20/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W283
2011-07-18 11:54 | 0360-WD | Fast Track | Fast Track | In Service | 1/15/2012 | 8/30/2013 | 2/4/2014 | FRESNO | REEDLEY SUB | Solar PV | 1.225 | 7/26/2011 | 11/2/2011 | Fail Screens: 2, 4, 5, 7, 9, 10 | 1/9/2012 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | Former queue position: W284
2011-07-18 12:44 | 0361-WD | Fast Track | Fast Track | In Service | 1/4/2012 | 1/31/2014 | 1/9/2014 | FRESNO | MCCALL SUB | Solar PV | 1 | 7/26/2011 | 8/29/2011 | Fail Screens: 2, 10 | 11/4/2011 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | Former queue position: W285
2011-07-18 13:46 | 0362-WD | Fast Track | Fast Track | Withdrawn | 5/15/2012 | Withdrawn | Withdrawn | FRESNO | CARUTHERS SUB | Solar PV | 1 | 7/26/2011 | 8/29/2011 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W286
2011-07-18 14:08 | 0363-WD | Fast Track | Fast Track | Withdrawn | 5/10/2012 | Withdrawn | Withdrawn | SHASTA | COTTONWOOD SUB | Solar PV | 1.5 | Complete | 11/28/2011 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W287
2011-07-18 14:14 | 0364-WD | Fast Track | Fast Track | Withdrawn | 6/7/2012 | Withdrawn | Withdrawn | TEHAMA | CORNING SUB | Solar PV | 0.5 | Complete | 11/28/2011 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W288
2011-07-18 14:32 | 0365-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | BUTTE | BUTTE SUB | Solar PV | 0.001 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2011-07-18 14:32 | 0366-WD | Fast Track | Fast Track | Withdrawn | 8/10/2012 | Withdrawn | Withdrawn | TEHAMA | LOS MOLINOS SUB | Solar PV | 0.25 | 7/26/2011 | 11/22/2011 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W289
2011-07-18 14:32 | 0367-WD | Fast Track | Fast Track | Withdrawn | 5/15/2012 | Withdrawn | Withdrawn | TEHAMA | LOS MOLINOS SUB | Solar PV | 1.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W290
2011-07-18 14:50 | 0368-WD | Fast Track | Fast Track | Withdrawn | 9/8/2011 | Withdrawn | Withdrawn | TEHAMA | CORNING SUB | Solar PV | 0.5 | 7/26/2011 | 11/22/2011 | Fail Screens: 2, 4, 10 | 3/29/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W294
2011-07-18 15:10 | 0369-WD | Fast Track | Fast Track | In Service | 6/7/2012 | 7/31/2012 | 6/21/2013 | TEHAMA | GERBER SUB | Solar PV | 0.245 | 7/26/2011 | 11/22/2011 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | Former queue position: W296
2011-07-18 15:19 | 0370-WD | Fast Track | Fast Track | Withdrawn | 2/15/2012 | Withdrawn | Withdrawn | SHASTA | JESSUP SUB | Solar PV | 1 | 7/26/2011 | 11/22/2011 | Fail Screens: 2, 4, 5, 10 | 1/19/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W291
2011-07-18 15:55 | 0371-WD | Fast Track | Fast Track | Withdrawn | 3/15/2012 | Withdrawn | Withdrawn | MERCED | EL CAPITAN SUB | Solar PV | 1.5 | 7/26/2011 | 8/12/2011 | Fail Screens: 10 | 8/23/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W292
2011-07-18 16:04 | 0372-WD | Fast Track | Fast Track | Withdrawn | 8/8/2012 | Withdrawn | Withdrawn | TEHAMA | CORNING SUB | Solar PV | 1.5 | 7/26/2011 | 11/22/2011 | Fail Screens: 2, 4, 10 | 3/29/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W293
2011-07-19 16:36 | 0373-WD | Fast Track | Fast Track | Withdrawn | 9/8/2012 | Withdrawn | Withdrawn | TEHAMA | RED BLUFF SUB | Solar PV | 1 | 7/26/2011 | 11/28/2011 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W295
2011-07-25 | 0374-WD | Independent Study | Independent Study | In Service | 1/1/2013 | 4/23/2013 | 3/22/2013 | SAN LUIS OBISPO | SAN LUIS OBISPO SUB | Steam Turbine | 1.5 | 5/21/2012 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 8/16/2012 | N/A | Executed | Former queue position: W297
2011-07-25 09:12 | 0375-WD | Fast Track | Fast Track | Withdrawn | 3/30/2013 | Withdrawn | Withdrawn | SAN JOAQUIN | MANTECA SUB | Solar PV | 2 | 8/16/2011 | 10/28/2011 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W298
2011-07-28 10:01 | 0376-WD | Fast Track | Fast Track | In Service | 10/30/2011 | 1/6/2014 | 1/27/2014 | TEHAMA | TYLER SUB | Solar PV | 0.245 | 10/25/2011 | 11/22/2011 | Fail Screens: 2, 10 | 3/8/2012 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | Former queue position: W306
2011-07-28 10:08 | 0377-WD | Fast Track | Fast Track | Withdrawn | 12/30/2012 | Withdrawn | Withdrawn | BUTTE | BUTTE SUB | Solar PV | 1 | 8/9/2011 | 11/22/2011 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W305
2011-07-28 10:18 | 0378-WD | Fast Track | Fast Track | In Service | 12/30/2012 | 2/5/2014 | 2/21/2014 | BUTTE | WYANDOTTE SUB | Solar PV | 0.49 | 8/8/2011 | 11/22/2011 | Fail Screens: 2, 4, 5, 10 | 7/19/2012 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | Former queue position: W304
2011-07-28 11:23 | 0379-WD | Fast Track | Fast Track | Withdrawn | 8/30/2011 | Withdrawn | Withdrawn | BUTTE | HONCUT SUB | Solar PV | 0.25 | 8/8/2011 | 11/22/2011 | Fail Screens: 2, 4, 5, 10 | 11/2/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W300
2011-07-28 11:43 | 0380-WD | Fast Track | Fast Track | Withdrawn | 12/1/2012 | Withdrawn | Withdrawn | YUBA | LIVE OAK SUB | Solar PV | 1.25 | 2/29/2012 | 4/30/2012 | Fail Screens: 2, 5, 10 | 9/5/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W303
2011-07-28 11:51 | 0381-WD | Fast Track | Fast Track | Withdrawn | 12/15/2012 | Withdrawn | Withdrawn | BUTTE | NORD SUB | Solar PV | 1 | 10/25/2011 | 11/22/2011 | Fail Screens: 2, 5, 10 | 4/12/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W299
2011-07-28 11:52 | 0382-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | YUBA | LIVE OAK SUB | Solar PV | 0.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W302
2011-08-02 | 0383-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | CONTRA COSTA | FAIRVIEW SUB | Microturbine | 1.2 | 9/9/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W307
2011-08-04 14:11 | 0384-WD | Fast Track | Fast Track | In Service | 1/5/2013 | 12/31/2013 | 12/30/2013 | SAN LUIS OBISPO | TEMPLETON SUB | Solar PV | 1.4992 | 9/8/2011 | 10/21/2011 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | Former queue position: W308
2011-08-05 15:34 | 0385-WD | Fast Track | Fast Track | In Service | 1/5/2013 | 9/29/2013 | 11/27/2013 | SAN JOAQUIN | LOCKEFORD SUB | Solar PV | 0.98 | 9/2/2011 | 12/21/2011 | Fail Screens: 2, 10 | 2/27/2012 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | Former queue position: W309
2011-08-08 | 0386-WD | Fast Track | Fast Track | Withdrawn | 9/1/2012 | Withdrawn | Withdrawn | YOLO | DAVIS SUB | Solar PV | 0.15 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W311
2011-08-08 | 0387-WD | Fast Track | Fast Track | Withdrawn | 9/1/2012 | Withdrawn | Withdrawn | YOLO | DAVIS SUB | Solar PV | 0.15 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W312
2011-08-08 | 0388-WD | Fast Track | Fast Track | Withdrawn | 9/1/2012 | Withdrawn | Withdrawn | YOLO | DAVIS SUB | Solar PV | 0.15 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W313
2011-08-08 10:06 | 0389-WD | Fast Track | Fast Track | Withdrawn | 9/1/2012 | Withdrawn | Withdrawn | YOLO | DAVIS SUB | Solar PV | 0.15 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W310
2011-08-10 | 0390-WD | Fast Track | Fast Track | Withdrawn | 10/31/2012 | Withdrawn | Withdrawn | SAN LUIS OBISPO | TEMPLETON SUB | Solar PV | 1 | 8/19/2011 | 9/14/2011 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W314
2011-08-10 11:41 | 0391-WD | Fast Track | Fast Track | Withdrawn | 2/15/2013 | Withdrawn | Withdrawn | MONTEREY | MORRO BAY DIST SUB | Solar PV | 0.25 | Complete | 9/19/2011 | Fail Screens: 2, 4, 6, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W316
2011-08-10 12:00 | 0392-WD | Fast Track | Fast Track | Withdrawn | 5/30/2013 | Withdrawn | Withdrawn | BUTTE | TRES VIAS SUB | Solar PV | 0.25 | 11/22/2011 | 11/22/2011 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W317
2011-08-10 12:11 | 0393-WD | Fast Track | Fast Track | In Service | 4/18/2012 | 10/31/2013 | 8/27/2013 | YUBA | OLIVEHURST SUB | Solar PV | 0.25 | 8/12/2011 | 11/22/2011 | Fail Screens: 2, 5, 10 | 1/26/2012 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | Former queue position: W318
2011-08-10 12:28 | 0394-WD | Fast Track | Fast Track | In Service | 10/15/2012 | 8/30/2013 | 1/10/2014 | SAN LUIS OBISPO | PASO ROBLES SUB | Solar PV | 0.98 | 8/19/2011 | 9/12/2011 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | Former queue position: W319
2011-08-10 12:34 | 0395-WD | Fast Track | Fast Track | Withdrawn | 10/15/2012 | Withdrawn | Withdrawn | SAN LUIS OBISPO | TEMPLETON SUB | Solar PV | 0.75 | Complete | 9/19/2011 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W320
2011-08-11 11:27 | 0396-WD | Fast Track | Fast Track | Withdrawn | 8/15/2012 | Withdrawn | Withdrawn | SAN LUIS OBISPO | CHOLAME SUB | Solar PV | 0.5 | Complete | 9/19/2011 | Fail Screens: 2, 4, 6, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W315
2011-08-23 16:38 | 0397-WD | Fast Track | Fast Track | In Service | 12/15/2013 | 8/30/2013 | 1/10/2014 | SAN LUIS OBISPO | TEMPLETON SUB | Solar PV | 0.75 | 10/14/2011 | 11/4/2011 | Fail Screens: 2, 6, 10 | 12/1/2011 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | Former queue position: W321
2011-08-23 20:12 | 0398-WD | Fast Track | Fast Track | Withdrawn | 12/30/2012 | Withdrawn | Withdrawn | FRESNO | SCHINDLER SUB | Solar PV | 2 | 9/8/2011 | 10/6/2011 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W322
2011-08-31 | 0399-WD | Fast Track | Fast Track | Withdrawn | 12/20/2011 | Withdrawn | Withdrawn | SANTA CLARA | MILPITAS SUB | Hydro | 0.15 | 9/12/2011 | 1/18/2012 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W323
2011-09-06 14:19 | 0400-WD | Fast Track | Fast Track | In Service | 1/1/2013 | 3/1/2014 | 12/18/2013 | SHASTA | PIT #1 PH | Solar PV | 1.5 | 11/16/2011 | 12/29/2011 | Fail Screens: 2, 9, 10 | 4/10/2012 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | Former queue position: W324
2011-09-08 10:28 | 0401-WD | Independent Study | Independent Study | Withdrawn | 10/1/2012 | Withdrawn | Withdrawn | SANTA CLARA | DIXON LANDING SUB | Reciprocating Engine | 6.4 | 10/18/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W325
2011-09-13 09:00 | 0402-WD | Fast Track | Fast Track | Withdrawn | 3/31/2011 | Withdrawn | Withdrawn | MERCED | MERCED SUB | Biomass | 0.225 | 3/16/2012 | 4/12/2012 | Fail Screens: 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W326
2011-09-22 09:06 | 0403-WD | Fast Track | Fast Track | Withdrawn | 3/13/2013 | Withdrawn | Withdrawn | KERN | GOOSE LAKE SUB | Solar PV | 1.5 | 12/2/2011 | 1/6/2012 | Fail Screens: 2, 4, 10 | 9/26/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W327
2011-09-22 09:08 | 0404-WD | Fast Track | Independent Study | Withdrawn | 3/13/2013 | Withdrawn | Withdrawn | KERN | GOOSE LAKE SUB | Solar PV | 1.5 | 12/2/2011 | 1/6/2012 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W328
2011-09-22 09:10 | 0405-WD | Fast Track | Independent Study | Withdrawn | 3/13/2013 | Withdrawn | Withdrawn | KERN | GOOSE LAKE SUB | Solar PV | 1.5 | 12/2/2011 | 1/6/2012 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W329
2011-09-22 14:28 | 0406-WD | Fast Track | Fast Track | Withdrawn | 3/1/2013 | Withdrawn | Withdrawn | MERCED | DOS PALOS SUB | Solar PV | 2 | 10/25/2011 | 11/10/2011 | Fail Screens: 2, 10 | 12/28/2011 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W330
2011-09-30 10:55 | 0407-WD | Fast Track | Fast Track | Withdrawn | 5/15/2012 | Withdrawn | Withdrawn | TEHAMA | SYCAMORE CREEK SUB | Solar PV | 0.75 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W339
2011-09-30 11:19 | 0408-WD | Fast Track | Fast Track | Withdrawn | 1/21/2012 | Withdrawn | Withdrawn | BUTTE | ORO FINO SUB | Solar PV | 1.25 | 10/14/2011 | 11/21/2011 | Fail Screens: 2, 10 | 4/25/2012 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W331
2011-09-30 14:48 | 0409-WD | Fast Track | Fast Track | Withdrawn | 1/21/2013 | Withdrawn | Withdrawn | TEHAMA | CORNING SUB | Solar PV | 1.25 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W338
2011-09-30 17:22 | 0410-WD | Fast Track | Fast Track | Withdrawn | 1/21/2012 | Withdrawn | Withdrawn | BUTTE | SYCAMORE CREEK SUB | Solar PV | 1.25 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W340
2011-10-03 13:29 | 0411-WD | Fast Track | Fast Track | In Service | 3/1/2013 | 3/1/2014 | 12/18/2013 | SHASTA | MCARTHUR SUB | Solar PV | 1.5 | 11/16/2011 | 12/29/2011 | Fail Screens: 2, 10 | 4/10/2012 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | Former queue position: W332
2011-10-07 09:34 | 0412-WD | Fast Track | Fast Track | Withdrawn | 1/21/2013 | Withdrawn | Withdrawn | SUTTER | PEASE SUB | Solar PV | 0.5 | 10/24/2011 | 11/28/2011 | Fail Screens: 2, 5, 10 | 10/25/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W334
2011-10-07 09:57 | 0413-WD | Fast Track | Fast Track | Withdrawn | 1/21/2013 | Withdrawn | Withdrawn | KERN | TAFT SUB | Solar PV | 0.5 | 10/18/2011 | 10/31/2011 | Fail Screens: 2, 10 | 11/18/2011 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W341
2011-10-07 10:12 | 0414-WD | Fast Track | Fast Track | Withdrawn | 1/21/2013 | Withdrawn | Withdrawn | TEHAMA | GERBER SUB | Solar PV | 0.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W337
2011-10-07 11:04 | 0415-WD | Fast Track | Fast Track | Withdrawn | 1/21/2013 | Withdrawn | Withdrawn | BUTTE | TRES VIAS SUB | Solar PV | 0.25 | 10/14/2011 | 11/21/2011 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W333
2011-10-07 11:10 | 0416-WD | Fast Track | Fast Track | Withdrawn | 1/21/2013 | Withdrawn | Withdrawn | TEHAMA | CORNING SUB | Solar PV | 0.5 | 10/31/2011 | 12/14/2011 | Fail Screens: 2 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W353
2011-10-08 13:00 | 0417-WD | Fast Track | Fast Track | Withdrawn | 5/31/2012 | Withdrawn | Withdrawn | KERN | STOCKDALE SUB | Solar PV | 1.5 | 10/18/2011 | 11/14/2011 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W335
2011-10-08 13:00 | 0418-WD | Fast Track | Fast Track | Withdrawn | 5/31/2012 | Withdrawn | Withdrawn | KERN | STOCKDALE SUB | Solar PV | 1.5 | 10/18/2011 | 11/14/2011 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W336
2011-10-13 | 0419-WD | Fast Track | Fast Track | In Service | 2/15/2013 | 10/13/2014 | 4/3/2015 | MERCED | MERCED SUB | Solar PV | 1.497 | 10/19/2011 | 2/17/2012 | Fail Screens: 2, 10 | 4/5/2012 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | Former queue position: W342
2011-10-13 08:36 | 0420-WD | Fast Track | Fast Track | In Service | 2/15/2013 | 10/13/2014 | 4/3/2015 | MERCED | MERCED SUB | Solar PV | 1.4994 | 10/27/2011 | 2/17/2012 | Fail Screens: 2, 10 | 4/5/2012 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | Former queue position: W343
2011-10-18 | 0421-WD | Independent Study | Independent Study | Withdrawn | 9/1/2014 | Withdrawn | Withdrawn | CONTRA COSTA | BRENTWOOD SUB | Solar PV | 3 | 10/26/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W345
2011-10-20 02:15 | 0422-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | GALLO SUB | Solar PV | 3 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W346
2011-10-21 15:04 | 0423-WD | Fast Track | Fast Track | Withdrawn | 6/1/2012 | Withdrawn | Withdrawn | CALAVERAS | CORRAL SUB | Solar PV | 0.97 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W344
2011-10-21 15:04 | 0424-WD | Fast Track | Fast Track | Withdrawn | 6/1/2012 | Withdrawn | Withdrawn | KERN | WILSON SUB | Solar PV | 1.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W347
2011-10-21 15:04 | 0425-WD | Fast Track | Fast Track | Withdrawn | 6/1/2013 | Withdrawn | Withdrawn | FRESNO | TIVY VALLEY SUB | Solar PV | 1.5 | 11/8/2011 | 12/9/2011 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W348
2011-10-21 15:04 | 0426-WD | Fast Track | Fast Track | Withdrawn | 6/1/2012 | Withdrawn | Withdrawn | PLACER | WHEATLAND SUB | Solar PV | 1.5 | 11/3/2011 | 12/28/2011 | Fail Screens: 2, 4, 5, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W349
2011-10-21 15:04 | 0427-WD | Fast Track | Fast Track | Withdrawn | 6/1/2012 | Withdrawn | Withdrawn | FRESNO | TIVY VALLEY SUB | Solar PV | 1.5 | 11/8/2011 | 12/9/2011 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W350
2011-10-21 15:04 | 0428-WD | Fast Track | Fast Track | Withdrawn | 6/1/2012 | Withdrawn | Withdrawn | EL DORADO | PLACERVILLE SUB | Solar PV | 1.5 | 11/3/2011 | 11/4/2011 | Fail Screens: 2, 4, 10 | 12/13/2011 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W351
2011-10-21 15:04 | 0429-WD | Fast Track | Fast Track | Withdrawn | 6/1/2012 | Withdrawn | Withdrawn | TULARE | OROSI SUB | Solar PV | 0.97 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W352
2011-10-24 | 0430-WD | Independent Study | Independent Study | Withdrawn | 12/28/2012 | Withdrawn | Withdrawn | KERN | DEVILS DEN SUB | Solar PV | 20.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W363
2011-10-28 12:54 | 0431-WD | Fast Track | Fast Track | Withdrawn | 3/1/2013 | Withdrawn | Withdrawn | SONOMA | LAKEVILLE SUB | Solar PV | 1.5 | 3/20/2012 | 6/13/2012 | Fail Screens: 2, 10 | 9/12/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W354
2011-10-28 13:19 | 0432-WD | Fast Track | Fast Track | Withdrawn | 3/1/2013 | Withdrawn | Withdrawn | SONOMA | LAKEVILLE SUB | Solar PV | 1.5 | 3/20/2012 | 6/13/2012 | Fail Screens: 2, 10 | 9/12/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W355
2011-10-31 11:53 | 0433-WD | Fast Track | Fast Track | In Service | 12/15/2013 | 6/28/2013 | 6/27/2013 | YOLO | DAVIS SUB | Solar PV | 1 | 11/23/2011 | 1/25/2012 | Fail Screens: 2, 4, 10 | 4/21/2012 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | Former queue position: W356
2011-10-31 11:53 | 0434-WD | Fast Track | Fast Track | Withdrawn | 9/15/2013 | Withdrawn | Withdrawn | YOLO | DAVIS SUB | Solar PV | 1 | 11/23/2011 | 1/25/2012 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W358
2011-10-31 11:53 | 0435-WD | Fast Track | Fast Track | Withdrawn | 9/15/2013 | Withdrawn | Withdrawn | YOLO | DAVIS SUB | Solar PV | 1 | 11/23/2011 | 1/25/2012 | Fail Screens: 2, 4, 10 | 4/21/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W360
2011-10-31 11:53 | 0436-WD | Fast Track | Fast Track | Withdrawn | 9/15/2013 | Withdrawn | Withdrawn | YOLO | DAVIS SUB | Solar PV | 1 | 11/23/2011 | 1/25/2012 | Fail Screens: 2, 4, 10 | 4/21/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W361
2011-10-31 11:54 | 0437-WD | Fast Track | Fast Track | Withdrawn | 9/15/2013 | Withdrawn | Withdrawn | YOLO | DAVIS SUB | Solar PV | 1 | 11/23/2011 | 1/25/2012 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W359
2011-10-31 11:55 | 0438-WD | Fast Track | Fast Track | In Service | 12/15/2013 | 7/28/2013 | 6/27/2013 | YOLO | DAVIS SUB | Solar PV | 1 | 11/23/2011 | 1/25/2012 | Fail Screens: 2, 4, 10 | 4/21/2012 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | Former queue position: W357
2011-11-04 10:29 | 0439-WD | Fast Track | Fast Track | Withdrawn | 10/1/2012 | Withdrawn | Withdrawn | FRESNO | GATES SUB | Solar PV | 2 | 12/9/2011 | 12/29/2011 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W362
2011-11-08 11:26 | 0440-WD | Fast Track | Independent Study | Withdrawn | 9/1/2012 | Withdrawn | Withdrawn | TULARE | OROSI SUB | Solar PV | 1.5 | 2/13/2012 | 3/9/2012 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W410
2011-11-08 11:28 | 0441-WD | Fast Track | Fast Track | Withdrawn | 9/1/2012 | Withdrawn | Withdrawn | TULARE | OROSI SUB | Solar PV | 1.5 | 2/13/2012 | 3/9/2012 | Fail Screens: 2, 10 | 6/25/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W408
2011-11-08 11:32 | 0442-WD | Fast Track | Independent Study | Withdrawn | 9/1/2012 | Withdrawn | Withdrawn | TULARE | OROSI SUB | Solar PV | 1.5 | 2/13/2012 | 3/9/2012 | Fail Screens: 2, 10 | 6/18/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W403
2011-11-08 14:34 | 0443-WD | Fast Track | Fast Track | In Service | 10/15/2012 | 1/31/2014 | 1/10/2014 | SAN LUIS OBISPO | TEMPLETON SUB | Solar PV | 0.49 | 11/14/2011 | 12/8/2011 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | Former queue position: W364
2011-11-09 09:31 | 0444-WD | Fast Track | Independent Study | In Service | 9/1/2012 | 9/16/2013 | 11/14/2013 | FRESNO | KINGSBURG SUB | Solar PV | 1.5 | 2/13/2012 | 3/29/2012 | Fail Screens: 2, 10 | N/A | N/A (Independent Study) | Pass | 9/25/2012 | N/A | Executed | Former queue position: W407
2011-11-09 09:31 | 0445-WD | Fast Track | Fast Track | Withdrawn | 9/1/2012 | Withdrawn | Withdrawn | TULARE | KINGSBURG SUB | Solar PV | 1.5 | 2/13/2012 | 3/9/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Duplicate entry; former queue position: W409
2011-11-09 09:34 | 0446-WD | Fast Track | Fast Track | In Service | 9/1/2012 | 9/16/2013 | 11/14/2013 | FRESNO | KINGSBURG SUB | Solar PV | 1.5 | 2/13/2012 | 3/29/2012 | Fail Screens: 2, 4, 7, 9, 10 | 6/20/2012 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | Former queue position: W404
2011-11-09 09:34 | 0447-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | TULARE | KINGSBURG SUB | Solar PV | 1.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Duplicate entry; former queue position: W405
2011-11-09 09:34 | 0448-WD | Fast Track | Independent Study | In Service | 9/1/2012 | 9/16/2013 | 11/14/2013 | FRESNO | KINGSBURG SUB | Solar PV | 0.75 | 2/13/2012 | 3/29/2012 | Fail Screens: 2, 10 | N/A | N/A (Independent Study) | Pass | 9/25/2012 | N/A | Executed | Former queue position: W406
2011-11-15 13:53 | 0449-WD | Fast Track | Fast Track | Withdrawn | 9/15/2012 | Withdrawn | Withdrawn | TEHAMA | RED BLUFF SUB | Solar PV | 0.75 | 11/29/2011 | 1/4/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W375b
2011-11-15 14:01 | 0450-WD | Fast Track | Fast Track | Withdrawn | 1/1/2013 | Withdrawn | Withdrawn | GLENN | ELK CREEK SUB | Solar PV | 0.25 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W365
2011-11-15 14:20 | 0451-WD | Fast Track | Fast Track | Withdrawn | 1/28/2013 | Withdrawn | Withdrawn | GLENN | GLENN SUB | Solar PV | 0.5 | 11/29/2011 | 2/9/2012 | Fail Screens: 2, 5, 9, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W366
2011-11-15 14:35 | 0452-WD | Independent Study | Independent Study | Withdrawn | 10/1/2012 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN H (MARTIN) SUB | Hydro | 0.241 | 1/24/2012 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W367
2011-11-15 14:40 | 0453-WD | Fast Track | Fast Track | Withdrawn | 1/28/2013 | Withdrawn | Withdrawn | KERN | TAFT SUB | Solar PV | 0.75 | 12/20/2011 | 2/7/2012 | Fail Screens: 10 | 4/12/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W368
2011-11-15 14:54 | 0454-WD | Fast Track | Fast Track | Withdrawn | 1/1/2013 | Withdrawn | Withdrawn | SAN LUIS OBISPO | SAN MIGUEL SUB | Solar PV | 0.75 | 3/26/2012 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W369
2011-11-15 15:13 | 0455-WD | Fast Track | Fast Track | Withdrawn | 3/28/2013 | Withdrawn | Withdrawn | TEHAMA | LOS MOLINOS SUB | Solar PV | 2 | 11/29/2011 | 12/23/2011 | Fail Screens: 2, 10 | 10/15/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W375a
2011-11-15 15:18 | 0456-WD | Fast Track | Fast Track | Withdrawn | 1/28/2013 | Withdrawn | Withdrawn | TEHAMA | CORNING SUB | Solar PV | 0.5 | 11/29/2011 | 12/22/2011 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W370
2011-11-15 15:22 | 0457-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SHASTA | COTTONWOOD SUB | Solar PV | 0.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W371
2011-11-15 15:42 | 0458-WD | Fast Track | Fast Track | Withdrawn | 1/28/2013 | Withdrawn | Withdrawn | SHASTA | PANORAMA SUB | Solar PV | 1.25 | 11/29/2011 | 12/22/2011 | Fail Screens: 2, 10 | 5/12/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W372
2011-11-15 15:53 | 0459-WD | Fast Track | Fast Track | Withdrawn | 1/28/2013 | Withdrawn | Withdrawn | SHASTA | DESCHUTES SUB | Solar PV | 0.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W373
2011-11-15 16:09 | 0460-WD | Fast Track | Fast Track | Withdrawn | 1/28/2013 | Withdrawn | Withdrawn | TEHAMA | DAIRYVILLE SUB | Solar PV | 0.25 | Complete | 11/22/2011 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W374
2011-11-15 16:14 | 0461-WD | Fast Track | Fast Track | Withdrawn | 1/28/2013 | Withdrawn | Withdrawn | GLENN | GLENN SUB | Solar PV | 0.25 | 11/29/2011 | 1/20/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W375
2011-11-16 11:30 | 0462-WD | Fast Track | Fast Track | Withdrawn | 1/28/2013 | Withdrawn | Withdrawn | SAN JOAQUIN | LOCKEFORD SUB | Solar PV | 1 | 8/16/2012 | 9/7/2012 | Fail Screens: 2, 6, 10 | 11/30/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W376
2011-11-16 11:42 | 0463-WD | Fast Track | Fast Track | Withdrawn | 1/28/2013 | Withdrawn | Withdrawn | SHASTA | RED BLUFF SUB | Solar PV | 0.5 | 11/30/2011 | 12/22/2011 | Fail Screens: 2, 10 | 5/17/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W377
2011-11-16 11:48 | 0464-WD | Fast Track | Fast Track | Withdrawn | 1/28/2013 | Withdrawn | Withdrawn | SACRAMENTO | GRAND ISLAND SUB | Solar PV | 0.5 | 3/27/2012 | 4/11/2012 | Fail Screens: 2, 10 | 8/10/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W378
2011-11-21 16:11 | 0465-WD | Fast Track | Fast Track | Withdrawn | 8/1/2013 | Withdrawn | Withdrawn | SUTTER | BOGUE SUB | Solar PV | 1.5 | Complete | 6/1/2012 | Fail Screens: 2, 5, 10 | 9/12/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W379
2011-11-21 16:16 | 0466-WD | Fast Track | Fast Track | Withdrawn | 8/1/2013 | Withdrawn | Withdrawn | SUTTER | BOGUE SUB | Solar PV | 1.5 | Complete | 6/1/2012 | Fail Screens: 2, 5, 10 | 9/12/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W380
2011-11-29 12:56 | 0467-WD | Fast Track | Fast Track | In Service | 5/1/2012 | 7/31/2012 | 9/22/2012 | MARIN | LAS GALLINAS A SUB | Solar PV | 0.97 | 12/9/2011 | 1/4/2012 | Fail Screens: 2, 10 | 1/20/2012 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | Former queue position: W381
2011-12-08 13:07 | 0468-WD | Fast Track | Fast Track | Withdrawn | 1/28/2013 | Withdrawn | Withdrawn | FRESNO | FIGARDEN SUB | Solar PV | 2.25 | 8/16/2012 | 9/7/2012 | Fail Screens: 2, 5, 6, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W382
2011-12-08 14:04 | 0469-WD | Fast Track | Fast Track | Withdrawn | 3/28/2013 | Withdrawn | Withdrawn | MONTEREY | SOLEDAD SUB | Solar PV | 2 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W391b
2011-12-09 08:37 | 0470-WD | Fast Track | Fast Track | Withdrawn | 6/28/2013 | Withdrawn | Withdrawn | MERCED | EL CAPITAN SUB | Solar PV | 1 | 8/16/2012 | 9/7/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W386
2011-12-09 08:57 | 0471-WD | Fast Track | Fast Track | Withdrawn | 6/28/2013 | Withdrawn | Withdrawn | TEHAMA | MCARTHUR SUB | Solar PV | 0.25 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W384
2011-12-09 14:47 | 0472-WD | Fast Track | Fast Track | Withdrawn | 6/1/2013 | Withdrawn | Withdrawn | LAKE | HARTLEY SUB | Solar PV | 1.5 | 12/19/2011 | 1/11/2012 | Fail Screens: 2, 10 | 2/1/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W383
2011-12-09 14:47 | 0473-WD | Fast Track | Fast Track | Withdrawn | 6/1/2012 | Withdrawn | Withdrawn | MONTEREY | JOLON SUB | Solar PV | 1.5 | 12/13/2011 | 1/5/2012 | Fail Screens: 2, 4, 10 | 1/31/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W385
2011-12-11 16:58 | 0474-WD | Independent Study | Independent Study | In Service | 5/28/2012 | 6/12/2013 | 6/1/2011 | PLACER | PLEASANT GROVE SUB | Engine | 5.04 | 2/6/2012 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 6/7/2012 | N/A | Executed | Former queue position: W396
2011-12-12 07:20 | 0475-WD | Fast Track | Fast Track | Withdrawn | 6/28/2013 | Withdrawn | Withdrawn | TEHAMA | GERBER SUB | Solar PV | 0.25 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W387
2011-12-12 07:22 | 0476-WD | Fast Track | Fast Track | Withdrawn | 6/28/2013 | Withdrawn | Withdrawn | SHASTA | DESCHUTES SUB | Solar PV | 1.5 | 8/16/2012 | 9/7/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W391a
2011-12-12 08:20 | 0477-WD | Fast Track | Fast Track | Withdrawn | 6/1/2013 | Withdrawn | Withdrawn | SHASTA | OREGON TRAIL SUB | Solar PV | 1.25 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W401
2011-12-12 11:49 | 0478-WD | Fast Track | Fast Track | Withdrawn | 6/28/2013 | Withdrawn | Withdrawn | KERN | LERDO SUB | Solar PV | 0.25 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W388
2011-12-12 12:43 | 0479-WD | Fast Track | Fast Track | Withdrawn | 6/28/2013 | Withdrawn | Withdrawn | BUTTE | WYANDOTTE SUB | Solar PV | 1.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W389
2011-12-12 15:21 | 0480-WD | Fast Track | Fast Track | Withdrawn | 6/28/2013 | Withdrawn | Withdrawn | AMADOR | ELECTRA SUB | Solar PV | 0.75 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W390
2011-12-13 | 0481-WD | Independent Study | Independent Study | Withdrawn | 12/31/2012 | Withdrawn | Withdrawn | KERN | TEMBLOR SUB | Reciprocating Engine | 1 | 1/24/2012 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W391
2011-12-20 13:14 | 0482-WD | Fast Track | Fast Track | Withdrawn | 6/28/2013 | Withdrawn | Withdrawn | SHASTA | ANDERSON SUB | Solar PV | 0.25 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W394
2011-12-20 14:24 | 0483-WD | Fast Track | Fast Track | Withdrawn | 6/28/2013 | Withdrawn | Withdrawn | FRESNO | RAINBOW SUB | Solar PV | 0.75 | 8/16/2012 | 9/7/2012 | Fail Screens: 5, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W392
2011-12-20 14:30 | 0484-WD | Fast Track | Fast Track | Withdrawn | 6/28/2013 | Withdrawn | Withdrawn | FRESNO | MERCED FALLS SUB | Solar PV | 1.5 | 3/16/2012 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W393
2011-12-20 14:33 | 0485-WD | Fast Track | Fast Track | Withdrawn | 6/28/2013 | Withdrawn | Withdrawn | BUTTE | ELK HILLS SUB | Solar PV | 0.5 | 8/16/2012 | 9/6/2012 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2011-12-20 14:37 | 0486-WD | Fast Track | Fast Track | Withdrawn | 6/1/2013 | Withdrawn | Withdrawn | BUTTE | SYCAMORE CREEK SUB | Solar PV | 0.5 | 8/16/2012 | 9/7/2012 | Fail Screens: 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W393a
2011-12-22 20:04 | 0487-WD | Fast Track | Fast Track | Withdrawn | 12/1/2012 | Withdrawn | Withdrawn | TULARE | OROSI SUB | Solar PV | 1.5 | 2/13/2012 | 3/29/2012 | Fail Screens: 2, 10 | 6/18/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W411
2011-12-22 20:05 | 0488-WD | Fast Track | Fast Track | Withdrawn | 12/1/2012 | Withdrawn | Withdrawn | TULARE | OROSI SUB | Solar PV | 0.5 | 2/13/2012 | 8/6/2012 | Fail Screens: 2, 10 | 6/18/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W414
2011-12-22 20:05 | 0489-WD | Fast Track | Independent Study | Withdrawn | 12/1/2012 | Withdrawn | Withdrawn | TULARE | OROSI SUB | Solar PV | 1.5 | 2/13/2012 | 2012-03-29 | Fail Screens: 2, 4, 10 | 6/18/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W421
2011-12-22 20:07 | 0490-WD | Fast Track | Independent Study | Withdrawn | 12/1/2012 | Withdrawn | Withdrawn | TULARE | OROSI SUB | Solar PV | 1.5 | 2/13/2012 | 3/29/2012 | Fail Screens: 2, 4, 10 | 6/18/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W419
2011-12-22 20:07 | 0491-WD | Fast Track | Independent Study | Withdrawn | 12/1/2012 | Withdrawn | Withdrawn | TULARE | DINUBA SUB | Solar PV | 1.5 | 2/13/2012 | 3/29/2012 | Fail Screens: 2, 4, 10 | 6/18/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W420
2011-12-22 20:10 | 0492-WD | Fast Track | Independent Study | Withdrawn | 12/1/2012 | Withdrawn | Withdrawn | TULARE | DINUBA SUB | Solar PV | 1.5 | 2/13/2012 | 3/29/2012 | Fail Screens: 2, 4, 10 | 6/18/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W417
2011-12-23 13:45 | 0493-WD | Fast Track | Fast Track | Withdrawn | 6/1/2012 | Withdrawn | Withdrawn | LAKE | CLEAR LAKE SUB | Solar PV | 1.5 | 1/18/2012 | 2/16/2012 | Fail Screens: 2, 10 | 3/1/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W392a
2011-12-23 15:09 | 0494-WD | Fast Track | Fast Track | Withdrawn | 12/31/2012 | Withdrawn | Withdrawn | MERCED | GUSTINE SUB | Solar PV | 2 | 3/29/2012 | 8/3/2012 | Fail Screens: 2, 4, 10 | 10/29/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W392d
2011-12-23 15:14 | 0495-WD | Fast Track | Fast Track | Withdrawn | 12/31/2012 | Withdrawn | Withdrawn | MERCED | GUSTINE SUB | Solar PV | 2 | 3/29/2012 | 8/2/2012 | Fail Screens: 2, 10 | 10/30/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W392b
2011-12-23 15:19 | 0496-WD | Fast Track | Fast Track | Withdrawn | 5/29/2013 | Withdrawn | Withdrawn | KERN | TUPMAN SUB | Solar PV | 2 | 5/21/2012 | 7/2/2012 | Fail Screens: 2, 4, 10 | 10/9/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W392c
2011-12-23 15:27 | 0497-WD | Fast Track | Fast Track | Withdrawn | 5/29/2013 | Withdrawn | Withdrawn | KERN | BLACKWELL SUB | Solar PV | 2 | 5/21/2012 | 6/25/2012 | Fail Screens: 2, 4, 10 | 10/2/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W423
2011-12-23 15:29 | 0498-WD | Fast Track | Fast Track | Withdrawn | 5/29/2013 | Withdrawn | Withdrawn | KERN | BLACKWELL SUB | Solar PV | 2 | 5/21/2012 | 6/25/2012 | Fail Screens: 2, 4, 10 | 10/2/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2011-12-23 15:31 | 0499-WD | Fast Track | Fast Track | Withdrawn | 3/22/2013 | Withdrawn | Withdrawn | KERN | DEVILS DEN SUB | Solar PV | 2 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W392e
2012-01-03 21:43 | 0500-WD | Fast Track | Fast Track | Withdrawn | 2/1/2013 | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV | 1.5 | 2/13/2012 | 3/29/2012 | Fail Screens: 2, 9, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W418
2012-01-03 21:44 | 0501-WD | Fast Track | Fast Track | Withdrawn | 2/1/2013 | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV | 1.5 | 2/13/2012 | 3/29/2012 | Fail Screens: 2, 9, 10 | 6/27/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W412
2012-01-03 21:44 | 0502-WD | Fast Track | Fast Track | Withdrawn | 2/1/2013 | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV | 1.5 | 2/13/2012 | 3/29/2012 | Fail Screens: 2, 4, 9, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W415
2012-01-03 21:44 | 0503-WD | Fast Track | Fast Track | Withdrawn | 2/1/2013 | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV | 1.5 | 2/13/2012 | 3/29/2012 | Fail Screens: 2, 9, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W416
2012-01-10 15:14 | 0504-WD | Fast Track | Fast Track | Withdrawn | 6/1/2013 | Withdrawn | Withdrawn | FRESNO | TIVY VALLEY SUB | Solar PV | 1.5 | 1/23/2012 | 2/16/2012 | Fail Screens: 2, 10 | 6/28/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W395
2012-01-13 17:23 | 0505-WD | Fast Track | Fast Track | Withdrawn | 5/1/2013 | Withdrawn | Withdrawn | TEHAMA | RED BLUFF SUB | Solar PV | 2 | 1/25/2012 | 3/5/2012 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W397
2012-01-19 14:13 | 0506-WD | Fast Track | Fast Track | Withdrawn | 3/15/2013 | Withdrawn | Withdrawn | KERN | COPUS SUB | Solar PV | 1.5 | 1/24/2012 | 2/14/2012 | Fail Screens: 2, 10 | 4/17/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W398
2012-01-23 | 0507-WD | Fast Track | Independent Study | Withdrawn | 6/30/2013 | Withdrawn | Withdrawn | MERCED | ORO LOMA SUB | Solar PV | 2.996 | 2/29/2012 | 4/11/2012 | Fail Screens: 2, 4, 9, 10 | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | Former queue position: W399
2012-01-23 | 0508-WD | Fast Track | Independent Study | Withdrawn | 6/30/2013 | Withdrawn | Withdrawn | MERCED | DOS PALOS SUB | Solar PV | 2.996 | 2/29/2012 | 4/11/2012 | Fail Screens: 2, 4, 9, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W400
2012-01-30 09:43 | 0509-WD | Fast Track | Fast Track | Withdrawn | 1/1/2014 | Withdrawn | Withdrawn | FRESNO | REEDLEY SUB | Solar PV | 1.7 | 2/17/2012 | 3/9/2012 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W422
2012-01-30 10:27 | 0510-WD | Fast Track | Fast Track | Withdrawn | 7/15/2013 | Withdrawn | Withdrawn | YOLO | PUTAH CREEK SUB | Solar PV | 0.75 | 2/10/2012 | 2/28/2012 | Fail Screens: 2, 4, 10 | 5/5/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W402
2012-02-03 | 0511-WD | Fast Track | Fast Track | Withdrawn | 4/15/2012 | Withdrawn | Withdrawn | PLUMAS | CRESCENT MILLS SUB | Solar PV | 0.65 | 2/23/2012 | 5/8/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W413
2012-02-17 11:58 | 0512-WD | Fast Track | Fast Track | Withdrawn | 6/30/2013 | Withdrawn | Withdrawn | FRESNO | AUBERRY SUB | Solar PV | 2.99 | 4/16/2012 | 5/24/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W426a
2012-02-17 11:58 | 0513-WD | Fast Track | Fast Track | Withdrawn | 6/30/2013 | Withdrawn | Withdrawn | FRESNO | AUBERRY SUB | Solar PV | 2.978 | 4/16/2012 | 5/24/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W426b
2012-02-17 16:51 | 0514-WD | Fast Track | Fast Track | Withdrawn | 1/1/2014 | Withdrawn | Withdrawn | FRESNO | SAN JOAQUIN SUB | Solar PV | 2 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W425
2012-02-17 16:51 | 0515-WD | Fast Track | Fast Track | Withdrawn | 1/1/2014 | Withdrawn | Withdrawn | FRESNO | GIFFEN SUB | Solar PV | 2 | 5/24/2012 | 6/25/2012 | Fail Screens: 2, 9, 10 | 10/30/2012 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W426
2012-02-17 16:52 | 0516-WD | Fast Track | Fast Track | Withdrawn | 1/1/2014 | Withdrawn | Withdrawn | FRESNO | HELM SUB | Solar PV | 2 | 6/29/2012 | 7/26/2012 | Fail Screens: 2, 4, 9, 10 | 10/29/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W424
2012-02-21 12:01 | 0517-WD | Fast Track | Fast Track | Withdrawn | 6/1/2013 | Withdrawn | Withdrawn | SAN JOAQUIN | CORRAL SUB | Solar PV | 2 | 2/28/2012 | 3/29/2012 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W427
2012-02-27 09:04 | 0518-WD | Fast Track | Fast Track | Withdrawn | 6/15/2013 | Withdrawn | Withdrawn | SUTTER | LIVE OAK SUB | Solar PV | 0.5 | 3/16/2012 | 4/2/2012 | Fail Screens: 2, 5, 10 | 7/24/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W428
2012-02-27 09:21 | 0519-WD | Fast Track | Fast Track | Withdrawn | 3/15/2013 | Withdrawn | Withdrawn | SANTA BARBARA | SANTA MARIA SUB | Solar PV | 0.5 | 10/5/2012 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W429
2012-02-27 16:10 | 0520-WD | Fast Track | Fast Track | Withdrawn | 4/1/2013 | Withdrawn | Withdrawn | LAKE | HARTLEY SUB | Solar PV | 1 | 3/2/2012 | 5/8/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W430
2012-02-27 16:10 | 0521-WD | Fast Track | Fast Track | Withdrawn | 4/1/2013 | Withdrawn | Withdrawn | LAKE | CLEAR LAKE SUB | Solar PV | 1.5 | 3/5/2012 | 5/8/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W431
2012-03-02 15:37 | 0522-WD | Fast Track | Fast Track | Withdrawn | 4/1/2013 | Withdrawn | Withdrawn | FRESNO | TIVY VALLEY SUB | Solar PV | 1.5 | 3/8/2012 | 3/22/2012 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W432
2012-03-06 09:36 | 0523-WD | Independent Study | Independent Study | Withdrawn | 10/15/2012 | Withdrawn | Withdrawn | KINGS | GUERNSEY SUB | Biomass | 1.6 | 5/15/2012 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W434
2012-03-06 09:37 | 0524-WD | Independent Study | Independent Study | Withdrawn | 10/15/2012 | Withdrawn | Withdrawn | KINGS | GUERNSEY SUB | Biomass | 1.6 | 5/15/2012 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W435
2012-03-06 09:39 | 0525-WD | Independent Study | Independent Study | Withdrawn | 10/15/2012 | Withdrawn | Withdrawn | MADERA | DAIRYLAND SUB | Biomass | 1.6 | 5/15/2012 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W433
2012-03-09 22:00 | 0526-WD | Fast Track | Fast Track | Withdrawn | 4/1/2013 | Withdrawn | Withdrawn | SHASTA | PANORAMA SUB | Solar PV | 0.7 | 3/19/2012 | 4/11/2012 | Fail Screens: 2, 9, 10 | 7/27/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W436
2012-03-12 09:29 | 0527-WD | Fast Track | Fast Track | Withdrawn | 4/5/2013 | Withdrawn | Withdrawn | SOLANO | PEABODY SUB | Solar PV | 3 | 3/21/2012 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W439
2012-03-12 18:10 | 0528-WD | Fast Track | Fast Track | Withdrawn | 4/1/2013 | Withdrawn | Withdrawn | FRESNO | CHENEY SUB | Solar PV | 1.5 | 3/21/2012 | 4/5/2012 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W438
2012-03-12 20:53 | 0529-WD | Independent Study | Independent Study | Withdrawn | 11/1/2013 | Withdrawn | Withdrawn | SANTA BARBARA | FAIRWAY SUB | Reciprocating Engine | 19.956 | 7/10/2012 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W437
2012-03-15 16:02 | 0530-WD | Independent Study | Independent Study | Withdrawn | 10/1/2012 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN H (MARTIN) SUB | Hydro | 0.24 | 3/26/2012 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W440
2012-03-27 | 0531-WD | Independent Study | Independent Study | Withdrawn | 9/1/2012 | Withdrawn | Withdrawn | BUTTE | ESQUON SUB | Biomass | 0.7 | 5/3/2012 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W443a
2012-03-27 10:30 | 0532-WD | Fast Track | Fast Track | Withdrawn | 1/1/2014 | Withdrawn | Withdrawn | FRESNO | REEDLEY SUB | Solar PV | 1.495 | 4/5/2012 | 4/21/2012 | Fail Screens: 2 | 5/15/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W444
2012-03-28 21:46 | 0533-WD | Fast Track | Fast Track | Withdrawn | 7/1/2013 | Withdrawn | Withdrawn | SAN BENITO | HOLLISTER SUB | Solar PV | 0.25 | 4/13/2012 | 5/1/2012 | Fail Screens: 2, 6, 10 | 6/13/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W445
2012-03-28 22:50 | 0534-WD | Fast Track | Fast Track | Withdrawn | 7/1/2013 | Withdrawn | Withdrawn | SAN BENITO | HOLLISTER SUB | Solar PV | 0.25 | 4/13/2012 | 5/1/2012 | Fail Screens: 2, 6, 10 | 6/6/2012 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W446
2012-03-28 22:53 | 0535-WD | Fast Track | Fast Track | Withdrawn | 7/1/2013 | Withdrawn | Withdrawn | SAN BENITO | HOLLISTER SUB | Solar PV | 0.25 | 4/13/2012 | 5/1/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W447
2012-03-29 13:39 | 0536-WD | Fast Track | Fast Track | Withdrawn | 9/1/2012 | Withdrawn | Withdrawn | KERN | CHARCA SUB | Solar PV | 2 | 4/23/2012 | 8/9/2012 | Fail Screens: 2, 10 | 9/21/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W456
2012-03-30 11:05 | 0537-WD | Fast Track | Fast Track | Withdrawn | 8/1/2014 | Withdrawn | Withdrawn | MADERA | BONITA SUB | Solar PV | 2 | 4/6/2012 | 4/23/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W447a
2012-03-30 15:29 | 0538-WD | Cluster | Cluster | Withdrawn | 1/5/2013 | Withdrawn | Withdrawn | MARIPOSA | BEAR VALLEY SUB | Solar PV | 5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W449
2012-03-31 23:32 | 0539-WD | Cluster | Cluster | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | COPUS SUB | Solar PV | 20 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-04-02 17:08 | 0540-WD | Fast Track | Fast Track | Withdrawn | 8/1/2014 | Withdrawn | Withdrawn | MERCED | EL NIDO SUB | Solar PV | 2 | Complete | 4/23/2012 | Fail Screens: 2, 9, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W448
2012-04-03 08:05 | 0541-WD | Fast Track | Fast Track | Withdrawn | 3/1/2013 | Withdrawn | Withdrawn | YUBA | EAST MARYSVILLE SUB | Solar PV | 2 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W450
2012-04-03 10:32 | 0542-WD | Fast Track | Fast Track | Withdrawn | 7/31/2013 | Withdrawn | Withdrawn | YOLO | DUNNIGAN SUB | Solar PV | 1 | 4/18/2012 | 6/11/2012 | Fail Screens: 2, 5, 10 | 8/24/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W441
2012-04-03 10:50 | 0543-WD | Fast Track | Fast Track | Withdrawn | 7/31/2013 | Withdrawn | Withdrawn | MERCED | ATWATER SUB | Solar PV | 1.5 | 4/18/2012 | 5/23/2012 | Fail Screens: 2, 10 | 7/27/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W442
2012-04-03 10:54 | 0544-WD | Fast Track | Fast Track | Withdrawn | 7/31/2013 | Withdrawn | Withdrawn | MERCED | EL CAPITAN SUB | Solar PV | 1 | 4/16/2012 | 5/23/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W443
2012-04-06 09:17 | 0545-WD | Fast Track | Fast Track | Withdrawn | 6/30/2013 | Withdrawn | Withdrawn | KERN | WASCO SUB | Solar PV | 1.5 | 4/23/2012 | 6/22/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W451
2012-04-06 11:45 | 0546-WD | Fast Track | Fast Track | In Service | 12/1/2012 | 11/17/2013 | 11/12/2013 | TUOLUMNE | PEORIA SUB | Solar PV | 1.47 | 4/16/2012 | 5/5/2012 | Fail Screens: 2, 10 | 9/20/2012 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | Former queue position: W452
2012-04-06 12:23 | 0547-WD | Fast Track | Fast Track | Withdrawn | 7/1/2013 | Withdrawn | Withdrawn | KERN | ORO LOMA SUB | Solar PV | 2 | 4/13/2012 | 5/8/2012 | Fail Screens: 2, 10 | 9/28/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W454
2012-04-09 14:55 | 0548-WD | Fast Track | Fast Track | Withdrawn | 6/15/2013 | Withdrawn | Withdrawn | FRESNO | SAN JOAQUIN SUB | Solar PV | 5 | 5/17/2012 | 6/12/2012 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W455
2012-04-10 10:13 | 0549-WD | Fast Track | Fast Track | Withdrawn | 1/31/2013 | Withdrawn | Withdrawn | YOLO | PUTAH CREEK SUB | Solar PV | 2 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W457
2012-04-10 10:14 | 0550-WD | Fast Track | Fast Track | Withdrawn | 1/31/2013 | Withdrawn | Withdrawn | YOLO | MADISON SUB | Solar PV | 2 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W458
2012-04-10 10:14 | 0551-WD | Fast Track | Fast Track | Withdrawn | 1/31/2013 | Withdrawn | Withdrawn | LAKE | CLEAR LAKE SUB | Solar PV | 2 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W459
2012-04-10 10:14 | 0552-WD | Fast Track | Fast Track | Withdrawn | 1/31/2013 | Withdrawn | Withdrawn | SOLANO | PEABODY SUB | Solar PV | 2.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W460
2012-04-10 10:14 | 0553-WD | Fast Track | Fast Track | Withdrawn | 1/31/2013 | Withdrawn | Withdrawn | GLENN | LOGAN CREEK SUB | Solar PV | 1.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W461
2012-04-10 11:43 | 0554-WD | Fast Track | Fast Track | Withdrawn | 7/1/2013 | Withdrawn | Withdrawn | SAN LUIS OBISPO | TEMPLETON SUB | Solar PV | 3 | 4/20/2012 | 6/7/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W453
2012-04-11 11:23 | 0555-WD | Fast Track | Fast Track | Withdrawn | 5/1/2013 | Withdrawn | Withdrawn | TEHAMA | RED BLUFF SUB | Solar PV | 1.333 | 4/16/2012 | 5/7/2012 | Fail Screens: 2, 4, 9, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W462
2012-04-11 16:44 | 0556-WD | Fast Track | Fast Track | Withdrawn | 4/1/2013 | Withdrawn | Withdrawn | TULARE | ANGIOLA SUB | Solar PV | 1.26 | 5/4/2012 | 5/24/2012 | Fail Screens: 2, 10 | 8/31/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W462a
2012-04-12 11:40 | 0557-WD | Fast Track | Fast Track | Withdrawn | 4/1/2013 | Withdrawn | Withdrawn | TULARE | DINUBA SUB | Solar PV | 1 | 5/4/2012 | 5/24/2012 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W462b
2012-04-12 16:40 | 0558-WD | Fast Track | Fast Track | Withdrawn | 9/1/2012 | Withdrawn | Withdrawn | SAN LUIS OBISPO | MESA SUB | Solar PV | 3 | 4/18/2012 | 5/11/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W463
2012-04-13 | 0559-WD | Fast Track | Fast Track | Withdrawn | 9/30/2012 | Withdrawn | Withdrawn | KERN | MAGUNDEN SUB | Solar PV | 1 | 7/20/2012 | 9/4/2012 | Fail Screens: 2, 6, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W464
2012-04-13 12:00 | 0560-WD | Fast Track | Fast Track | Withdrawn | 9/30/2012 | Withdrawn | Withdrawn | KERN | RENFRO SUB | Solar PV | 1 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W465
2012-04-13 12:00 | 0561-WD | Fast Track | Fast Track | Withdrawn | 9/30/2012 | Withdrawn | Withdrawn | KERN | KERN PP DIST SUB | Solar PV | 1.5 | 7/20/2012 | 9/5/2012 | Fail Screens: 2, 6, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W466
2012-04-16 13:00 | 0562-WD | Fast Track | Fast Track | Withdrawn | 11/21/2013 | Withdrawn | Withdrawn | TEHAMA | CORNING SUB | Solar PV | 0.5 | 5/30/2012 | 7/19/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W467
2012-04-16 16:43 | 0563-WD | Fast Track | Fast Track | Withdrawn | 7/1/2013 | Withdrawn | Withdrawn | SAN LUIS OBISPO | STONE CORRAL SUB | Solar PV | 3 | 4/23/2012 | 5/11/2012 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W470
2012-04-16 17:42 | 0564-WD | Fast Track | Fast Track | Withdrawn | 11/21/2013 | Withdrawn | Withdrawn | KERN | TAFT SUB | Solar PV | 0.5 | 5/30/2012 | 6/13/2012 | Fail Screens: 2, 10 | 9/13/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W468
2012-04-16 17:45 | 0565-WD | Fast Track | Fast Track | Withdrawn | 11/21/2013 | Withdrawn | Withdrawn | BUTTE | TRES VIAS SUB | Solar PV | 0.25 | 5/30/2012 | 6/14/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W469
2012-04-17 14:31 | 0566-WD | Fast Track | Fast Track | Withdrawn | 7/2/2013 | Withdrawn | Withdrawn | KERN | POSO MTN SUB | Solar PV | 3 | 4/23/2012 | 8/30/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W471
2012-04-20 15:38 | 0567-WD | Fast Track | Fast Track | Withdrawn | 2/1/2014 | Withdrawn | Withdrawn | BUTTE | NORD SUB | Solar PV | 1.5 | 4/30/2012 | 6/4/2012 | Fail Screens: 2, 5, 10 | 7/27/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W473
2012-04-20 15:46 | 0568-WD | Fast Track | Fast Track | Withdrawn | 2/1/2014 | Withdrawn | Withdrawn | PLACER | EAST NICOLAUS SUB | Solar PV | 1.5 | 4/30/2012 | 6/4/2012 | Fail Screens: 2, 4, 5, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W472
2012-04-20 15:58 | 0569-WD | Fast Track | Fast Track | Withdrawn | 2/1/2014 | Withdrawn | Withdrawn | COLUSA | RICE SUB | Solar PV | 1.5 | 4/30/2012 | 6/4/2012 | Fail Screens: 2, 4, 5, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W474
2012-04-20 16:10 | 0570-WD | Fast Track | Fast Track | Withdrawn | 2/1/2014 | Withdrawn | Withdrawn | GLENN | ORLAND B SUB | Solar PV | 1.5 | 4/30/2012 | 6/4/2012 | Fail Screens: 2, 4, 5, 9, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W475
2012-04-20 16:22 | 0571-WD | Fast Track | Fast Track | Withdrawn | 2/1/2014 | Withdrawn | Withdrawn | TEHAMA | CORNING SUB | Solar PV | 1.5 | 4/30/2012 | 6/4/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W476
2012-04-20 16:33 | 0572-WD | Fast Track | Fast Track | Withdrawn | 2/1/2014 | Withdrawn | Withdrawn | SAN JOAQUIN | LOCKEFORD SUB | Solar PV | 3 | 4/30/2012 | 5/12/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W477
2012-04-25 12:01 | 0573-WD | Fast Track | Fast Track | Withdrawn | 7/1/2013 | Withdrawn | Withdrawn | MADERA | CHOWCHILLA SUB | Solar PV | 2 | 5/1/2012 | 6/25/2012 | Fail Screens: 2, 10 | 10/1/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W478
2012-04-25 15:41 | 0574-WD | Fast Track | Fast Track | Withdrawn | 7/1/2013 | Withdrawn | Withdrawn | MADERA | CHOWCHILLA SUB | Solar PV | 2 | 5/1/2012 | 6/25/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W479
2012-04-26 19:03 | 0575-WD | Fast Track | Fast Track | Withdrawn | 7/1/2013 | Withdrawn | Withdrawn | SAN JOAQUIN | LOCKEFORD SUB | Solar PV | 2 | 5/14/2012 | 5/30/2012 | Fail Screens: 2, 4, 10 | 9/25/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W480
2012-04-30 15:44 | 0576-WD | Fast Track | Fast Track | Withdrawn | 5/1/2013 | Withdrawn | Withdrawn | KERN | STOCKDALE SUB | Solar PV | 3 | 5/3/2012 | 5/24/2012 | Fail Screens: 2, 6 | 9/4/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W481
2012-04-30 16:52 | 0577-WD | Fast Track | Fast Track | Withdrawn | 7/1/2013 | Withdrawn | Withdrawn | MERCED | EL CAPITAN SUB | Solar PV | 3 | 5/21/2012 | 6/11/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W482
2012-04-30 17:21 | 0578-WD | Fast Track | Fast Track | Withdrawn | 7/2/2013 | Withdrawn | Withdrawn | TEHAMA | CORNING SUB | Solar PV | 2 | 5/21/2012 | 6/15/2012 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Former queue position: W483
2012-05-07 11:30 | 0579-WD | Fast Track | Fast Track | Withdrawn | 5/12/2013 | Withdrawn | Withdrawn | CONTRA COSTA | LONE TREE SUB | Solar PV | 3 | 5/21/2012 | 6/19/2012 | Fail Screens: 2, 6, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-05-08 14:57 | 0580-WD | Fast Track | Fast Track | Withdrawn | 7/1/2013 | Withdrawn | Withdrawn | AMADOR | IONE SUB | Solar PV | 2 | 7/2/2012 | 8/3/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-05-21 15:58 | 0581-WD | Fast Track | Fast Track | In Service | 2/15/2013 | 4/15/2014 | 6/11/2014 | SONOMA | CLOVERDALE SUB | Solar PV | 1.5 | 7/2/2012 | 7/27/2012 | Fail Screens: 2, 5, 10 | 9/27/2012 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2012-05-21 15:58 | 0582-WD | Fast Track | Independent Study | Withdrawn | 2/15/2013 | Withdrawn | Withdrawn | SONOMA | CLOVERDALE SUB | Solar PV | 1.49 | 7/2/2012 | 7/27/2012 | Fail Screens: 2, 5, 10 | 9/27/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-05-22 12:00 | 0583-WD | Fast Track | Fast Track | Withdrawn | 6/19/2013 | Withdrawn | Withdrawn | CALAVERAS | CALAVERAS CEMENT SUB | Solar PV | 2 | 5/31/2012 | 7/13/2012 | Fail Screens: 2, 10 | 10/9/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-05-22 12:38 | 0584-WD | Fast Track | Fast Track | Withdrawn | 7/1/2013 | Withdrawn | Withdrawn | YOLO | ZAMORA SUB | Solar PV | 2 | 5/31/2012 | 7/3/2012 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-05-22 13:43 | 0585-WD | Fast Track | Fast Track | Withdrawn | 7/1/2013 | Withdrawn | Withdrawn | YOLO | WOODLAND SUB | Solar PV | 2 | 7/11/2012 | 8/7/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-05-23 12:50 | 0586-WD | Independent Study | Independent Study | Withdrawn | 1/1/2014 | Withdrawn | Withdrawn | CALAVERAS | STANISLAUS PH | Hydro | 4.8 | 6/25/2012 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-05-23 16:00 | 0587-WD | Fast Track | Fast Track | Withdrawn | 11/15/2013 | Withdrawn | Withdrawn | KERN | SMYRNA SUB | Solar PV | 2 | 6/28/2012 | 7/16/2012 | Fail Screens: 2, 10 | 9/19/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-06-14 14:17 | 0588-WD | Fast Track | Fast Track | Withdrawn | 2/1/2014 | Withdrawn | Withdrawn | PLACER | EAST NICOLAUS SUB | Solar PV | 1 | 8/2/2012 | 8/23/2012 | Fail Screens: 2, 10 | 9/29/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-06-14 14:20 | 0589-WD | Fast Track | Fast Track | Withdrawn | 2/1/2014 | Withdrawn | Withdrawn | COLUSA | RICE SUB | Solar PV | 1 | 8/2/2012 | 8/23/2012 | Fail Screens: 2, 4, 10 | 9/29/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-06-14 15:04 | 0590-WD | Fast Track | Fast Track | Withdrawn | 2/1/2014 | Withdrawn | Withdrawn | TEHAMA | CORNING SUB | Solar PV | 1 | 8/2/2012 | 8/23/2012 | Fail Screens: 2, 4, 10 | 9/29/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-16 15:07 | 0591-WD | Fast Track | Fast Track | Withdrawn | 5/12/2013 | Withdrawn | Withdrawn | CONTRA COSTA | LONE TREE SUB | Solar PV | 1.75 | 8/21/2012 | 10/1/2012 | Fail Screens: 2, 6, 10 | 11/21/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-20 | 0592-WD | Independent Study | Independent Study | Withdrawn | 1/15/2013 | Withdrawn | Withdrawn | MERCED | SANTA RITA SUB | Biomass | 0.3 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-30 11:50 | 0593-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | BUTTE | PARADISE SUB | Solar PV | 1.5 | 9/28/2012 | 10/17/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-30 11:55 | 0594-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | GLENN | GLENN SUB | Solar PV | 0.75 | 9/28/2012 | 10/17/2012 | Fail Screens: 2, 4, 5, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-30 11:59 | 0595-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | BUTTE | ANITA SUB | Solar PV | 0.75 | 9/28/2012 | 10/18/2012 | Fail Screens: 2, 5, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-30 12:12 | 0596-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | SHASTA | BURNEY SUB | Solar PV | 0.333 | 9/28/2012 | 10/12/2012 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-30 12:42 | 0597-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | GLENN | ORLAND B SUB | Solar PV | 1.25 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-30 13:27 | 0598-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | KERN | ARVIN SUB | Solar PV | 0.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-30 13:32 | 0599-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | FRESNO | REEDLEY SUB | Solar PV | 1.25 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-30 13:42 | 0600-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | MADERA | BONITA SUB | Solar PV | 0.75 | 9/28/2012 | 10/16/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-30 13:44 | 0601-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | SHASTA | GIRVAN SUB | Solar PV | 0.75 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-30 13:58 | 0602-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | COLUSA | ARBUCKLE SUB | Solar PV | 0.75 | 9/28/2012 | 10/16/2012 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-30 14:02 | 0603-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | SHASTA | ANDERSON SUB | Solar PV | 0.333 | 9/28/2012 | 10/22/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-30 14:09 | 0604-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | GLENN | LOGAN CREEK SUB | Solar PV | 1 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-30 15:08 | 0605-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | SAN JOAQUIN | LOCKEFORD SUB | Solar PV | 1.333 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-30 17:26 | 0606-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | TEHAMA | CORNING SUB | Solar PV | 1.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-30 17:35 | 0607-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | KERN | LERDO SUB | Solar PV | 0.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-30 17:39 | 0608-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | TEHAMA | CAPAY SUB | Solar PV | 0.333 | 9/28/2012 | 10/26/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-30 17:48 | 0609-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | SHASTA | COTTONWOOD SUB | Solar PV | 0.5 | 9/28/2012 | 10/17/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-30 17:57 | 0610-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | PLACER | LINCOLN SUB | Solar PV | 1.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-30 18:05 | 0611-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV | 1.333 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-31 09:32 | 0612-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | GLENN | PEABODY SUB | Solar PV | 2.75 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-31 10:55 | 0613-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | SOLANO | VACA DIXON SUB | Solar PV | 1.25 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-31 11:22 | 0614-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | LAKE | CLEAR LAKE SUB | Solar PV | 1.25 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-31 11:33 | 0615-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | SANTA CLARA | LLAGAS SUB | Solar PV | 1.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-31 11:46 | 0616-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | SOLANO | NOTRE DAME SUB | Solar PV | 1.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-31 13:40 | 0617-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | EL DORADO | OLETA SUB | Solar PV | 0.75 | 9/28/2012 | 10/16/2012 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-31 13:52 | 0618-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | MADERA | COARSEGOLD SUB | Solar PV | 2 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-31 14:07 | 0619-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | LASSEN | MCARTHUR SUB | Solar PV | 0.5 | 9/28/2012 | 10/17/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-31 14:46 | 0620-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | SOLANO | SALINAS SUB | Solar PV | 1.5 | 9/28/2012 | 10/19/2012 | Fail Screens: 2, 5, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-07-31 16:18 | 0621-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | MONTEREY | ATWATER SUB | Solar PV | 1 | 9/28/2012 | 10/18/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-08-02 09:32 | 0622-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | GLENN | GLENN SUB | Solar PV | 0.5 | 9/28/2012 | 10/19/2012 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-08-09 16:19 | 0623-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | FRESNO | SANGER SUB | Solar PV | 0.5 | 9/28/2012 | 10/18/2012 | Fail Screens: 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-08-10 12:56 | 0624-WD | Fast Track | Fast Track | Withdrawn | 11/1/2013 | Withdrawn | Withdrawn | KERN | LAMONT SUB | Solar PV | 1.5 | 9/28/2012 | 10/27/2012 | Fail Screens: 2, 4, 10 | 12/10/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-08-10 13:06 | 0625-WD | Fast Track | Fast Track | Withdrawn | 11/1/2013 | Withdrawn | Withdrawn | KERN | LAMONT SUB | Solar PV | 1.5 | 9/28/2012 | 10/27/2012 | Fail Screens: 2, 4, 10 | 12/10/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-08-10 13:13 | 0626-WD | Fast Track | Fast Track | Withdrawn | 11/1/2013 | Withdrawn | Withdrawn | KERN | LAMONT SUB | Solar PV | 1.5 | 9/28/2012 | 10/27/2012 | Fail Screens: 2, 4, 10 | 12/10/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-08-10 14:32 | 0627-WD | Fast Track | Fast Track | Withdrawn | 12/1/2013 | Withdrawn | Withdrawn | KERN | WASCO SUB | Solar PV | 2 | 8/29/2012 | 9/11/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-08-10 15:10 | 0628-WD | Fast Track | Fast Track | Withdrawn | 8/1/2013 | Withdrawn | Withdrawn | MONTEREY | PASO ROBLES SUB | Hydro | 5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-08-13 10:28 | 0629-WD | Fast Track | Fast Track | Withdrawn | 11/1/2013 | Withdrawn | Withdrawn | KERN | MAGUNDEN SUB | Solar PV | 1.5 | 9/28/2012 | 10/27/2012 | Fail Screens: 2, 4, 6, 10 | 12/12/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-08-13 10:29 | 0630-WD | Fast Track | Fast Track | Withdrawn | 11/1/2013 | Withdrawn | Withdrawn | KERN | MAGUNDEN SUB | Solar PV | 1.5 | 9/28/2012 | 10/27/2012 | Fail Screens: 2, 4, 6, 10 | 12/12/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-08-14 10:37 | 0631-WD | Fast Track | Fast Track | Withdrawn | 6/30/2013 | Withdrawn | Withdrawn | FRESNO | AUBERRY SUB | Solar PV | 1.75 | 8/31/2012 | 9/19/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-08-14 10:37 | 0632-WD | Fast Track | Fast Track | Withdrawn | 6/30/2013 | Withdrawn | Withdrawn | FRESNO | AUBERRY SUB | Solar PV | 1.75 | 8/31/2012 | 9/19/2012 | Fail Screens: 2, 10 | 2018-07-10 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-08-14 17:11 | 0633-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | AMADOR | MARTELL SUB | Solar PV | 0.5 | 9/28/2012 | 10/19/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-08-14 17:25 | 0634-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | BUTTE | SYCAMORE CREEK SUB | Solar PV | 1.25 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-08-15 09:22 | 0635-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | BUTTE | WYANDOTTE SUB | Solar PV | 1.75 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-08-16 10:39 | 0636-WD | Fast Track | Fast Track | Withdrawn | 10/31/2013 | Withdrawn | Withdrawn | GLENN | ELK CREEK SUB | Solar PV | 0.25 | 9/28/2012 | 10/18/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-08-21 18:27 | 0637-WD | Fast Track | Fast Track | Withdrawn | 5/1/2014 | Withdrawn | Withdrawn | FRESNO | OLD KEARNEY SUB | Solar PV | 2 | 8/29/2012 | 9/13/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-08-23 09:18 | 0638-WD | Fast Track | Fast Track | Withdrawn | 6/1/2013 | Withdrawn | Withdrawn | TEHAMA | GERBER SUB | Solar PV | 1.5 | 9/10/2012 | 9/28/2012 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-08-29 08:44 | 0639-WD | Fast Track | Fast Track | Withdrawn | 6/1/2013 | Withdrawn | Withdrawn | TEHAMA | CORNING SUB | Solar PV | 1.5 | 9/10/2012 | 9/28/2012 | Fail Screens: 2, 4 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-09-04 11:29 | 0640-WD | Fast Track | Fast Track | Withdrawn | 12/31/2013 | Withdrawn | Withdrawn | FRESNO | REEDLEY SUB | Solar PV | 1.5 | 9/12/2012 | 10/3/2012 | Fail Screens: 2, 10 | 10/24/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-09-06 | 0641-WD | Fast Track | Fast Track | Withdrawn | 12/1/2013 | Withdrawn | Withdrawn | MERCED | CANAL SUB | Solar PV | 2 | 9/25/2012 | 10/3/2012 | Fail Screens: 2, 10 | 2013-08-13 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-09-06 16:09 | 0642-WD | Fast Track | Fast Track | Withdrawn | 2/1/2014 | Withdrawn | Withdrawn | YOLO | PUTAH CREEK SUB | Solar PV | 1.5 | 9/12/2012 | 10/2/2012 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-09-07 | 0643-WD | Fast Track | Fast Track | Withdrawn | 12/1/2013 | Withdrawn | Withdrawn | MERCED | EL NIDO SUB | Solar PV | 2 | 10/5/2012 | 10/19/2012 | Fail Screens: 2, 4, 5, 10 | 12/19/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-09-07 12:01 | 0644-WD | Fast Track | Fast Track | Withdrawn | 12/15/2014 | Withdrawn | Withdrawn | MERCED | MERCED SUB | Solar PV | 1.3 | 9/25/2012 | 2013-06-21 | Pass | 2/6/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-09-07 12:15 | 0645-WD | Fast Track | Fast Track | Withdrawn | 12/15/2014 | Withdrawn | Withdrawn | MERCED | MERCED SUB | Solar PV | 1 | 9/25/2012 | 10/10/2012 | Fail Screens: 2, 4, 10 | 12/6/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-09-07 16:24 | 0646-WD | Fast Track | Fast Track | Withdrawn | 1/29/2014 | Withdrawn | Withdrawn | NORTH BAY | PEABODY SUB | Solar PV | 3 | 9/25/2012 | 10/26/2012 | Fail Screens: 2, 4, 5, 10 | 1/15/2013 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-09-19 | 0647-WD | Fast Track | Fast Track | Withdrawn | 6/21/2013 | Withdrawn | Withdrawn | SAN BENITO | HOLLISTER SUB | Solar PV | 3 | 10/8/2012 | 11/6/2012 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-09-24 15:22 | 0648-WD | Fast Track | Fast Track | Withdrawn | 11/10/2013 | Withdrawn | Withdrawn | TULARE | REEDLEY SUB | Solar PV | 1.25 | 10/5/2012 | 10/23/2012 | Fail Screens: 2, 10 | 11/30/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-09-25 09:23 | 0649-WD | Fast Track | Fast Track | Withdrawn | 12/24/2013 | Withdrawn | Withdrawn | KERN | WASCO SUB | Solar PV | 2 | 10/5/2012 | 11/5/2012 | Fail Screens: 2, 10 | 2/20/2013 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-09-25 14:58 | 0650-WD | Fast Track | Fast Track | Withdrawn | 11/12/2013 | Withdrawn | Withdrawn | KERN | CHARCA SUB | Solar PV | 2 | 10/5/2012 | 11/5/2012 | Fail Screens: 2, 10 | 1/3/2013 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-09-25 17:40 | 0651-WD | Fast Track | Fast Track | Withdrawn | 12/1/2014 | Withdrawn | Withdrawn | FRESNO | CAMDEN SUB | Solar PV | 2 | 10/9/2012 | 11/13/2012 | Fail Screens: 2, 5, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-09-27 20:14 | 0652-WD | Fast Track | Fast Track | Withdrawn | 3/15/2013 | Withdrawn | Withdrawn | PLACER | EAST NICOLAUS SUB | Solar PV | 1.5 | 10/11/2012 | 10/31/2012 | Fail Screens: 2, 5, 10 | 1/23/2013 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-10-02 16:06 | 0653-WD | Fast Track | Fast Track | Withdrawn | 3/1/2013 | Withdrawn | Withdrawn | SUTTER | BOGUE SUB | Solar PV | 1.5 | 10/11/2012 | 10/29/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-10-02 16:11 | 0654-WD | Fast Track | Fast Track | Withdrawn | 3/1/2013 | Withdrawn | Withdrawn | SUTTER | BOGUE SUB | Solar PV | 1.5 | 10/11/2012 | 10/29/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-10-02 16:27 | 0655-WD | Fast Track | Fast Track | Withdrawn | 3/1/2013 | Withdrawn | Withdrawn | SOLANO | VACA DIXON SUB | Solar PV | 1.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-10-02 16:53 | 0656-WD | Fast Track | Fast Track | Withdrawn | 3/1/2013 | Withdrawn | Withdrawn | PLACER | LINCOLN SUB | Solar PV | 1.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-10-02 17:18 | 0657-WD | Fast Track | Fast Track | Withdrawn | 3/1/2013 | Withdrawn | Withdrawn | SUTTER | LINCOLN SUB | Solar PV | 1.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-10-02 17:22 | 0658-WD | Fast Track | Fast Track | Withdrawn | 3/1/2013 | Withdrawn | Withdrawn | PLACER | LINCOLN SUB | Solar PV | 1.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-10-03 10:32 | 0659-WD | Independent Study | Independent Study | Withdrawn | 3/1/2014 | Withdrawn | Withdrawn | YOSEMITE | CANAL SUB | Solar PV | 2.5 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-10-11 12:45 | 0660-WD | Fast Track | Independent Study | Withdrawn | 12/31/2013 | Withdrawn | Withdrawn | SAN BENITO | LOS OSITOS SUB | Solar PV | 3 | 10/29/2012 | 11/8/2012 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-10-23 15:57 | 0661-WD | Fast Track | Fast Track | Withdrawn | 7/11/2014 | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV | 1.5 | 11/5/2012 | 11/28/2012 | Fail Screens: 2, 10 | 1/9/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-10-24 10:47 | 0662-WD | Fast Track | Fast Track | Withdrawn | 10/31/2014 | Withdrawn | Withdrawn | CALAVERAS | CORRAL SUB | Solar PV | 2 | 11/6/2012 | 11/26/2012 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-10-09 11:14 | 0663-RD | Fast Track | Fast Track | In Service | 2/1/2013 | 7/25/2013 |  | SONOMA | MIRABEL SUB | Micro Turbine | 0.03 | 10/25/2012 | 11/5/2012 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2012-11-02 16:37 | 0664-WD | Fast Track | Fast Track | Withdrawn | 7/1/2014 | Withdrawn | Withdrawn | TULARE | ANGIOLA SUB | Solar PV | 1.5 | 11/16/2012 | 12/11/2012 | Fail Screens: 2, 4, 10 | 1/25/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-11-02 17:12 | 0665-WD | Fast Track | Fast Track | Withdrawn | 7/1/2013 | Withdrawn | Withdrawn | TULARE | ALPAUGH SUB | Solar PV | 1.5 | 11/16/2012 | 12/11/2012 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-11-09 12:00 | 0666-WD | Fast Track | Fast Track | Withdrawn | 6/30/2013 | Withdrawn | Withdrawn | FRESNO | AUBERRY SUB | Solar PV | 1.33 | 12/3/2012 | 12/18/2012 | Fail Screens: 2, 10 | 1/28/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-11-08 10:29 | 0667-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Storage | 0.054 | 11/14/2012 | 11/14/2012 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2012-11-15 07:36 | 0668-WD | Independent Study | Independent Study | Withdrawn | 10/3/2014 | Withdrawn | Withdrawn | MONTEREY | OIL FIELDS SUB | Solar PV | 6 | 12/3/2012 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-11-15 08:41 | 0669-WD | Fast Track | Fast Track | Withdrawn | 10/3/2014 | Withdrawn | Withdrawn | MONTEREY | SAN MIGUEL SUB | Solar PV | 2 | 12/3/2012 | 12/12/2012 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-10-30 08:42 | 0670-RD | Fast Track | Fast Track | In Service | Not Provided | 7/1/2015 | 7/2/2015 | SAN FRANCISCO | JAMESON SUB | Solar PV | 1.1456 | 11/28/2012 | 12/12/2012 | Fail Screens: B, D, F, H, J, K, M | 2/5/2013 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2012-11-20 16:02 | 0671-WD | Fast Track | Fast Track | Withdrawn | 1/15/2014 | Withdrawn | Withdrawn | SANTA CLARA | LOS ESTEROS SUB | Wind | 1.4 | Complete | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-11-23 11:56 | 0672-WD | Fast Track | Fast Track | Withdrawn | 3/17/2014 | Withdrawn | Withdrawn | SAN JOAQUIN | VICTOR SUB | Solar PV | 0.75 | 12/3/2012 | 12/24/2012 | Fail Screens: 2, 10 | 1/29/2013 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-11-23 12:27 | 0673-WD | Fast Track | Fast Track | Withdrawn | 3/17/2014 | Withdrawn | Withdrawn | MERCED | EL CAPITAN SUB | Solar PV | 1.5 | 12/3/2012 | 12/28/2012 | Fail Screens: 2, 10 | 1/23/2013 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-11-06 | 0674-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | EAST GRAND SUB | Solar PV | 0.09709 | 11/26/2012 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-11-06 | 0675-RD | Fast Track | Fast Track | In Service | Not Provided | In Service | 12/13/2012 | SAN MATEO | EAST GRAND SUB | Solar PV | 0.07045 | 11/26/2012 | 11/29/2012 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2012-10-10 | 0676-RD | Fast Track | Fast Track | Withdrawn | 6/30/2013 | Withdrawn | Withdrawn | SAN FRANCISCO | KERMAN SUB | Engine | 0.34 | 11/28/2012 | 12/6/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-10-12 | 0677-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | SAN LEANDRO U SUB | Other | 0.7 | 12/12/2012 | 12/12/2012 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-11-29 09:59 | 0678-WD | Fast Track | Fast Track | Withdrawn | 10/31/2014 | Withdrawn | Withdrawn | SAN JOAQUIN | MORMON SUB | Solar PV | 2 | 1/7/2013 | 1/23/2013 | Fail Screens: 2, 5, 10 | 3/4/2013 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-11-30 16:58 | 0679-WD | Independent Study | Independent Study | Withdrawn | 4/1/2015 | Withdrawn | Withdrawn | SOLANO | PEABODY SUB | Solar PV | 0.036 | 12/21/2012 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-11-20 | 0680-RD | Fast Track | Fast Track | In Service | Not Provided | 8/31/2013 |  | SAN FRANCISCO | OCEAN AVE SUB | Solar PV, Storage | 0.036 | 12/06/2012 | 12/06/2012 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2012-11-20 | 0681-RD | Fast Track | Fast Track | In Service | Not Provided | 8/15/2013 |  | SAN FRANCISCO | SAN FRAN A (POTRERO PP) SUB | Solar PV, Storage | 0.054 | 12/06/2012 | 2013-08-28 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2012-11-30 12:17 | 0682-RD | Fast Track | Fast Track | In Service | Not Provided | In Service | 2/8/2013 | KERN | TEJON SUB | Storage | 0.32 | 12/7/2012 | 12/12/2012 | Fail Screens: B, C, F, H, I, J, K | 12/27/2012 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2012-12-06 15:00 | 0683-RD | Fast Track | Fast Track | Withdrawn | 12/21/2012 | Withdrawn | Withdrawn | STANISLAUS | RIVERBANK SUB | Solar PV | 0.42 | 12/12/2012 | 12/12/2012 | Fail | 12/20/2012 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-11-15 | 0684-RD | Fast Track | Fast Track | In Service | Not Provided | 8/15/2013 |  | MONTEREY | JOLON SUB | Solar PV, Storage | 0.6 | 12/12/2012 | 1/2/2013 | Fail |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2012-12-07 13:53 | 0685-WD | Fast Track | Fast Track | In Service | 11/13/2013 | 9/1/2014 | 1/14/2015 | TULARE | REEDLEY SUB | Solar PV | 0.75 | 12/19/2012 | 1/11/2013 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2012-12-05 10:24 | 0686-WD | Fast Track | Fast Track | In Service | 12/31/2013 | 10/6/2014 | 3/23/2015 | SAN BENITO | HOLLISTER SUB | Solar PV | 1.5 | 12/17/2012 | 1/3/2013 | Fail Screens: 2, 10 | 2/12/2013 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2012-12-06 15:28 | 0687-WD | Independent Study | Independent Study | Withdrawn | 6/16/2014 | Withdrawn | Withdrawn | FRESNO | REEDLEY SUB | Solar PV | 1.5 | 12/21/2012 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-10-10 | 0688-RD | Fast Track | Fast Track | In Service | Not Provided | In Service | 8/13/2013 | BUTTE | CHICO B SUB | Solar PV | 0.2795 | 4/29/2013 | 7/8/2013 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2012-12-04 18:40 | 0689-RD | Fast Track | Fast Track | In Service | 11/7/2012 |  |  | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Storage | 0.015 | 12/20/2012 | 1/3/2013 | Fail | 2/13/2013 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2012-12-20 16:17 | 0690-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | DUMBARTON SUB | Engine, Solar PV | 1.812 | 12/27/2012 | 1/20/2013 | Fail Screens: B, C, D, F, I, J, K, M | 3/11/2013 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2012-12-17 16:00 | 0691-WD | Independent Study | Independent Study | In Service | 12/20/2013 | 11/22/2015 | 1/9/2015 | SANTA CLARA | DIXON LANDING SUB | Engine | 1.6 | 1/8/2013 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 5/14/2013 | N/A | Executed | No former queue position
2012-12-21 12:31 | 0692-RD | Fast Track | Fast Track | Withdrawn | 11/3/2014 | Withdrawn | Withdrawn | SANTA BARBARA | CUYAMA SUB | Solar PV | 1 | 1/22/2013 | 2/1/2013 | Fail Screens: I, J, K, M | 3/11/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-12-21 12:31 | 0693-RD | Fast Track | Fast Track | Withdrawn | 11/3/2014 | Withdrawn | Withdrawn | SANTA BARBARA | CUYAMA SUB | Solar PV | 1.5 | 1/22/2013 | 2/1/2013 | Fail Screens: I, J, K, M | 2013-03-11 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-12-26 11:50 | 0694-WD | Fast Track | Independent Study | Active | 12/31/2013 | 1/29/2016 |  | SAN JOAQUIN | LOCKEFORD SUB | Solar PV | 1 | 1/22/2013 | 3/7/2013 | Fail Screens: 2, 6, 10 | N/A | N/A (Independent Study) | Pass | 7/17/2013 | 12/23/2013 | Executed | No former queue position
2012-12-21 10:33 | 0695-WD | Fast Track | Fast Track | Withdrawn | 11/1/2013 | Withdrawn | Withdrawn | MARIN | OLEMA SUB | Solar PV | 2 | 1/22/2013 | 2/6/2013 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-01-22 11:32 | 0696-WD | Fast Track | Fast Track | Withdrawn | 1/13/2014 | Withdrawn | Withdrawn | SHASTA | JESSUP SUB | Solar PV | 2 | 2/11/2013 | 3/4/2013 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-01-15 16:26 | 0697-WD | Fast Track | Independent Study | Withdrawn | 4/1/2015 | Withdrawn | Withdrawn | KINGS | HENRIETTA SUB | Solar PV | 2 | 2/11/2013 | 3/5/2013 | Fail Screens: 2, 4, 10 | 4/15/2013 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-01-18 13:24 | 0698-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | CUPERTINO | STELLING SUB | Solar PV | 0.03 | 1/30/2013 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-01-30 07:57 | 0699-RD | Fast Track | Fast Track | In Service | 2/15/2013 | In Service | 6/28/2013 | SAN FRANCISCO | SAN FRAN K SUB | Wind | 0.0015 | 1/31/2013 | 1/31/2013 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-01-08 14:19 | 0700-WD | Independent Study | Independent Study | In Service | 3/27/2014 | 12/31/2014 | 3/6/2015 | PLACER | DEL MAR SUB | Hydro | 0.32 | 2/14/2013 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 7/12/2013 | N/A | Executed | No former queue position
2013-02-01 16:41 | 0701-RD | Fast Track | Fast Track | Withdrawn | 9/15/2013 | Withdrawn | Withdrawn | FRESNO | WEST FRESNO SUB | Cogeneration | 10 | 2/11/2013 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-02-08 08:20 | 0702-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | WEST FRESNO SUB | Turbine | 10.6 | 2/11/2013 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-12-28 15:53 | 0703-WD | Fast Track | Fast Track | Withdrawn | 11/1/2013 | Withdrawn | Withdrawn | PLACER | LINCOLN SUB | Solar PV | 1.5 | 2/21/2013 | 4/17/2013 | Fail Screens: 2, 5, 9, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-12-28 16:06 | 0704-WD | Fast Track | Fast Track | Withdrawn | 11/1/2013 | Withdrawn | Withdrawn | PLACER | LINCOLN SUB | Solar PV | 1.5 | 2/21/2013 | 4/17/2013 | Fail Screens: 2, 5, 9, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-02-07 17:06 | 0705-RD | Fast Track | Fast Track | Withdrawn | 12/30/2013 | Withdrawn | Withdrawn | FRESNO | SAN JOAQUIN SUB | Gas Turbine | 3 | 2/28/2013 | 3/12/2013 | Fail Screens: B, F | 5/21/2013 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-02-07 17:16 | 0706-RD | Fast Track | Fast Track | Withdrawn | 12/30/2013 | Withdrawn | Withdrawn | FRESNO | KERMAN SUB | Gas Turbine | 3 | 2/28/2013 | 3/7/2013 | Fail Screens: B, F | 6/3/2013 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-02-06 16:02 | 0707-RD | Fast Track | Fast Track | Withdrawn | 12/30/2013 | Withdrawn | Withdrawn | FRESNO | STROUD SUB | Gas Turbine | 3 | 2/28/2013 | 3/14/2013 | Fail Screens: B, F | 5/30/2013 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-02-06 16:22 | 0708-RD | Fast Track | Fast Track | Withdrawn | 12/30/2013 | Withdrawn | Withdrawn | FRESNO | SAN JOAQUIN SUB | Gas Turbine | 3 | 2/28/2013 | 3/12/2013 | Fail Screens: B, F | 5/20/2013 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-02-06 16:29 | 0709-RD | Fast Track | Independent Study | In Service | 12/30/2013 | 11/16/2015 | 9/23/2015 | FRESNO | KERMAN SUB | Solar PV | 1.3387 | 2/28/2013 | 3/11/2013 | Fail | 5/24/2013 | Fail | Pass | 12/30/2013 | N/A | Executed | R21 Transition to WDT SGIA
2013-01-18 14:31 | 0710-WD | Fast Track | Fast Track | Withdrawn | 2/1/2014 | Withdrawn | Withdrawn | MERCED | CANAL SUB | Solar PV | 2 | 3/8/2013 | 3/27/2013 | Fail Screens: 2, 4, 5, 10 | 6/5/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-02-19 10:04 | 0711-RD | Fast Track | Fast Track | In Service | 5/15/2013 | In Service | 2/6/2015 | ALAMEDA | EDES SUB | Engine | 1.33 | 3/7/2013 | 3/20/2013 | Fail Screens: B, D, I, J, K, M | 6/13/2013 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-03-04 08:00 | 0712-RD | Fast Track | Fast Track | In Service | Not Provided | In Service | 4/4/2013 | SAN MATEO | LOS ALTOS SUB | Solar PV | 0.02989 | 3/4/2013 | 3/7/2013 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-03-01 15:07 | 0713-RD | Fast Track | Fast Track | In Service | 9/1/2013 |  |  | SOLANO | JAMESON SUB | Solar PV | 0.99937 | 3/11/2013 | 3/22/2013 | Fail | 4/30/2013 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-02-12 12:32 | 0714-WD | Independent Study | Independent Study | Withdrawn | 6/2/2014 | Withdrawn | Withdrawn | KERN | CHARCA SUB | Solar PV | 2 | 3/21/2013 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-02-08 11:44 | 0715-WD | Independent Study | Independent Study | Withdrawn | 5/22/2013 | Withdrawn | Withdrawn | MERCED | SANTA RITA SUB | Biomass | 0.25 | 3/21/2013 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-02-28 13:25 | 0716-WD | Fast Track | Fast Track | Withdrawn | 1/31/2014 | Withdrawn | Withdrawn | SONOMA | CLOVERDALE SUB | Solar PV | 1 | 3/21/2013 | 4/9/2013 | Fail Screens: 2, 10 | 5/30/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-03-05 09:05 | 0717-WD | Fast Track | Fast Track | Withdrawn | 2/4/2014 | Withdrawn | Withdrawn | SANTA CLARA | MILPITAS SUB | Hydro | 0.15 | 3/21/2013 | 5/1/2013 | Pass | 6/24/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-03-06 16:55 | 0718-WD | Fast Track | Fast Track | In Service | 6/16/2014 | 4/10/2015 | 4/16/2015 | MERCED | SANTA RITA SUB | Solar PV | 1.5 | 3/28/2013 | 4/10/2013 | Fail Screens: 2, 10 | 6/6/2013 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-03-06 17:24 | 0719-WD | Fast Track | Independent Study | Withdrawn | 6/15/2014 | Withdrawn | Withdrawn | KERN | TWISSELMAN SUB | Solar PV | 3 | 3/28/2013 | 4/17/2013 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-03-19 10:19 | 0720-WD | Independent Study | Independent Study | Withdrawn | 9/26/2014 | Withdrawn | Withdrawn | KERN | WASCO SUB | Solar PV | 2 | 4/4/2013 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-03-20 09:24 | 0721-WD | Independent Study | Independent Study | Withdrawn | 9/19/2014 | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV | 3 | 4/4/2013 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-03-07 11:16 | 0722-WD | Fast Track | Fast Track | Withdrawn | 9/16/2014 | Withdrawn | Withdrawn | FRESNO | STROUD SUB | Solar PV | 1.5 | 4/4/2013 | 4/17/2013 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-03-25 19:53 | 0723-WD | Fast Track | Fast Track | Withdrawn | 7/30/2014 | Withdrawn | Withdrawn | YOLO | DAVIS SUB | Solar PV | 1.7 | 4/4/2013 | 4/15/2013 | Fail Screens: 2, 4, 5, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-03-28 09:26 | 0724-RD | Fast Track | Fast Track | Withdrawn | 9/26/2014 | Withdrawn | Withdrawn | FRESNO | MENDOTA SUB | Solar PV | 3 | 4/15/2013 | 5/21/2013 | Fail Screens: F, I, K, L, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-03-22 07:54 | 0725-WD | Fast Track | Fast Track | Withdrawn | 1/1/2014 | Withdrawn | Withdrawn | LAKE | CLEAR LAKE SUB | Solar PV | 1.99 | 4/19/2013 | 4/26/2013 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-03-13 | 0726-RD | Fast Track | Fast Track | Withdrawn | 5/31/2014 | Withdrawn | Withdrawn | CONTRA COSTA | MT EDEN SUB | Other | 2.14 | 4/15/2013 | 4/22/2013 | Fail Screens: B, F, I, J | 6/13/2013 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-04-12 12:08 | 0727-WD | Fast Track | Fast Track | Withdrawn | 2/20/2014 | Withdrawn | Withdrawn | YOLO | PUTAH CREEK SUB | Solar PV | 0.5 | 5/3/2013 | 5/22/2013 | Fail Screens: 2, 10 | 7/8/2013 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-04-19 | 0728-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | NEWARK SUB | Solar PV | 1 | 4/25/2013 | 5/7/2013 | Fail | 6/11/2013 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-04-23 17:11 | 0729-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CRUZ | PAUL SWEET SUB | Engine, Solar PV | 4.8219 | 5/1/2013 | 5/1/2013 | Fail Screens: B, C, F, H, I, J, K | 7/19/2013 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-04-11 16:15 | 0730-WD | Fast Track | Fast Track | Withdrawn | 8/30/2012 | Withdrawn | Withdrawn | MARIN | NOVATO SUB | Solar PV | 0.72 | 5/17/2013 | 6/12/2013 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-04-07 19:25 | 0731-WD | Fast Track | Fast Track | In Service | 6/7/2013 | 12/21/2014 | 3/12/2015 | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Storage | 0.0432 | 5/17/2013 | 2013-08-08 | Fail | 6/16/2014 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-04-07 19:55 | 0732-WD | Fast Track | Fast Track | In Service | 6/7/2013 | 2/22/2015 | 3/5/2015 | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Storage | 0.0432 | 5/17/2013 | 2013-08-08 | Fail Screens: 6, 7, 10 | 6/16/2014 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-04-22 13:02 | 0733-RD | Fast Track | Fast Track | In Service | Not Provided | In Service | 1/29/2014 | MADERA | MADERA SUB | Engine | 0.085 | Complete | 5/13/2013 | Fail | 5/15/2013 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-04-29 16:40 | 0734-RD | Fast Track | Fast Track | In Service | 7/1/2013 | In Service | 11/25/2013 | SAN FRANCISCO | SAN FRAN A (POTRERO PP) SUB | Solar PV | 0.08768 | 6/19/2013 | 6/24/2013 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-04-30 17:02 | 0735-RD | Fast Track | Fast Track | Withdrawn | 12/31/2013 | Withdrawn | Withdrawn | SANTA CLARA | LLAGAS SUB | Solar PV | 1.84 | 5/24/2013 | 6/13/2013 | Fail Screens: C, H, I, J, K, M | 8/15/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-04-30 17:05 | 0736-RD | Fast Track | Fast Track | Withdrawn | 12/31/2013 | Withdrawn | Withdrawn | PLACER | LINCOLN SUB | Solar PV | 2.3 | 5/24/2013 | 6/10/2013 | Fail Screens: F, G, I, J, K, L, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-04-30 17:07 | 0737-RD | Fast Track | Fast Track | In Service | 12/31/2013 | 10/30/2015 | 12/21/2015 | GLENN | ORLAND B SUB | Solar PV | 1.56 | 5/24/2013 | 6/12/2013 | Fail Screens: I, J, K, M | 8/1/2013 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-04-30 17:09 | 0738-RD | Fast Track | Detailed Study | Withdrawn | 12/31/2013 | Withdrawn | Withdrawn | SAN JOAQUIN | LOCKEFORD SUB | Solar PV | 1.82 | 5/24/2013 | 6/10/2013 | Fail Screens: H, I, J, K, M | 8/8/2013 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-04-30 17:12 | 0739-RD | Fast Track | Detailed Study | Withdrawn | 12/31/2013 | Withdrawn | Withdrawn | FRESNO | REEDLEY SUB | Solar PV | 1.04 | 5/24/2013 | 6/10/2013 | Fail Screens: I, J, K, M | 7/30/2013 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-04-30 17:13 | 0740-RD | Fast Track | Fast Track | Withdrawn | 12/31/2013 | Withdrawn | Withdrawn | KING | JACOBS CORNER SUB | Solar PV | 1.88 | 5/24/2013 | 6/14/2013 | Fail Screens: G, I, J, K, M | 8/7/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-04-11 12:04 | 0741-RD | Fast Track | Fast Track | In Service | 8/31/2013 |  |  | KINGS | AVENAL SUB | Other | 0.12 | 5/15/2013 | 6/4/2013 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-04-05 17:30 | 0742-WD | Fast Track | Independent Study | In Service | 3/15/2014 | 2/1/2016 | 12/19/2016 | BUTTE | TRES VIAS SUB | Solar PV | 0.25 | 5/24/2013 | 2013-08-30 | Fail Screens: 2, 10 | 8/30/2013 | Fail | Pass | 2014-03-13 | N/A | Executed | No former queue position
2013-05-14 12:09 | 0743-RD | Fast Track | Fast Track | In Service | Not Provided | In Service | 6/24/2013 | SAN FRANCISCO | SAN FRAN P(HUNTERS POINT) SUB | Solar PV | 0.02185 | 5/16/2013 | 5/20/2013 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-04-03 08:28 | 0744-RD | Detailed Study | Detailed Study | Withdrawn | 1/3/2016 | Withdrawn | Withdrawn | CONTRA COSTA | RICHMOND R SUB | Solar PV | 0 | 5/30/2013 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-03-29 08:47 | 0745-WD | Fast Track | Fast Track | Withdrawn | 9/12/2014 | Withdrawn | Withdrawn | MERCED | GUSTINE SUB | Solar PV | 0.036 | 5/28/2013 | 6/18/2013 | Fail Screens: 2, 10 | 8/23/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-04-04 09:12 | 0746-RD | Fast Track | Fast Track | In Service | 5/31/2013 |  |  | TUOLUMNE | CURTIS SUB | Solar PV | 0.036 | 5/30/2013 | 5/29/2013 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-04-25 12:52 | 0747-RD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SOLANO | GRAND ISLAND SUB | Wind | 0.054 | 5/30/2013 | 6/13/2013 | Fail Screens: B, F, H, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-05-08 16:51 | 0748-WD | Fast Track | Fast Track | In Service | 6/5/2014 | 3/1/2015 | 12/5/2016 | TEHAMA | CORNING SUB | Solar PV | 0.32 | 7/11/2013 | 7/30/2013 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-04-23 16:37 | 0749-WD | Fast Track | Fast Track | Withdrawn | 1/1/2014 | Withdrawn | Withdrawn | MONTEREY | LOS OSITOS SUB | Solar PV | 0.42 | 6/7/2013 | 6/19/2013 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-05-02 11:21 | 0750-RD | Fast Track | Fast Track | Withdrawn | 2/3/2014 | Withdrawn | Withdrawn | SOLANO | VACA DIXON SUB | Solar PV | 0.6 | 5/28/2013 | 6/24/2013 | Fail Screens: F, I, J, K, M | 8/26/2013 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-04-30 15:04 | 0751-RD | Fast Track | Fast Track | In Service | 7/31/2013 |  |  | SANTA CLARA | EL PATIO SUB | Solar PV | 0.831 | 2013-06-04 | 2013-06-11 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-04-24 13:27 | 0752-RD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | ALAMEDA | HERDLYN SUB | Wind | 4.5 | 6/13/2013 | 6/24/2013 | Fail Screens: B, F, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-04-30 16:58 | 0753-RD | Fast Track | Fast Track | Withdrawn | 12/31/2013 | Withdrawn | Withdrawn | SOLANO | PEABODY SUB | Solar PV | 2.1 | 6/13/2013 | 7/3/2013 | Fail Screens: F, G, H, I, J, K, M | 9/6/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-05-29 16:04 | 0754-RD | Fast Track | Fast Track | In Service | 1/2/2014 |  |  | SOLANO | PEABODY SUB | Solar PV | 1.13 | 6/13/2013 | 7/8/2013 | Fail | 9/9/2013 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-05-29 16:08 | 0755-RD | Fast Track | Fast Track | In Service | 1/2/2014 |  |  | FRESNO | GATES SUB | Solar PV | 1.22 | 6/13/2013 | 7/17/2013 | Fail | 8/27/2013 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-05-06 10:38 | 0756-RD | Fast Track | Fast Track | Withdrawn | 8/15/2015 | Withdrawn | Withdrawn | SANTA BARBARA | CUYAMA SUB | Solar PV | 0.99 | 6/21/2013 | Withdrawn | Withdrawn | 7/10/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-05-29 16:06 | 0757-RD | Fast Track | Fast Track | Withdrawn | 1/2/2014 | Withdrawn | Withdrawn | SAN LUIS OBISPO | ATASCADERO SUB | Solar PV | 0.90985 | 6/21/2013 | 7/15/2013 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-05-29 16:07 | 0758-RD | Fast Track | Fast Track | In Service | 1/2/2014 |  |  | FRESNO | GATES SUB | Solar PV | 2 | 6/21/2013 | 7/22/2013 | Fail | 8/21/2013 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-05-21 10:16 | 0759-WD | Fast Track | Independent Study | In Service | 9/16/2014 | 8/18/2018 | 3/20/2019 | FRESNO | STROUD SUB | Solar PV | 2.2 | 6/21/2013 | 7/12/2013 | Fail Screens: 2, 10 | 9/6/2013 | Fail | Pass | 3/5/2014 | N/A | Executed | No former queue position
2013-05-31 09:55 | 0760-RD | Fast Track | Fast Track | Withdrawn | 6/15/2013 | Withdrawn | Withdrawn | ALAMEDA | Customer-owned Newark NUMII 115KV | Battery | 1 | 6/27/2013 | 7/11/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-06-05 16:10 | 0761-WD | Independent Study | Independent Study | Withdrawn | 11/29/2013 | Withdrawn | Withdrawn | BUTTE | ESQUON SUB | Cogeneration | 0.71 | 7/3/2013 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-06-11 13:00 | 0762-RD | Fast Track | Fast Track | Withdrawn | 12/1/2014 | Withdrawn | Withdrawn | FRESNO | TIVY VALLEY SUB | Solar PV | 1.5 | 7/11/2013 | 7/16/2013 | Fail Screens: F, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-06-11 13:11 | 0763-RD | Fast Track | Independent Study | Withdrawn | 10/8/2014 | Withdrawn | Withdrawn | MERCED | WILSON SUB | Solar PV | 1.5 | 7/11/2013 | 7/16/2013 | Fail | 8/19/2013 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | R21 Transition to WDT SGIA
2013-06-12 11:51 | 0764-RD | Fast Track | Fast Track | In Service | 12/1/2014 | 11/6/2015 | 2/4/2016 | KERN | ELK HILLS SUB | Solar PV | 1.5 | 7/11/2013 | 7/17/2013 | Fail | 8/23/2013 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | R21 Transition to WDT SGIA
2013-06-25 17:25 | 0765-WD | Fast Track | Fast Track | In Service | 8/2/2013 | 12/1/2014 | 6/18/2014 | TEHAMA | JESSUP SUB | Solar PV | 0.24919 | 7/11/2013 | 7/30/2013 | Fail Screens: 2, 4, 10 | 9/5/2013 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-06-21 10:01 | 0766-RD | Fast Track | Independent Study | Withdrawn | 1/30/2015 | Withdrawn | Withdrawn | FRESNO | TIVY VALLEY SUB | Solar PV | 1.5 | 7/11/2013 | 7/16/2013 | Fail | 8/23/2013 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | R21 Transition to WDT SGIA
2013-06-27 11:31 | 0767-WD | Fast Track | Fast Track | In Service | 8/9/2013 | 2/24/2015 | 6/16/2014 | BUTTE | HONCUT SUB | Solar PV | 0.25 | 7/11/2013 | 8/1/2013 | Fail Screens: 2, 10 | 9/4/2013 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-06-28 15:55 | 0768-RD | Fast Track | Fast Track | Withdrawn | 7/14/2014 | Withdrawn | Withdrawn | KERN | TWISSELMAN SUB | Solar PV | 3 | 7/11/2013 | 7/22/2013 | Fail Screens: F, I, J, K, M | 9/23/2013 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-05-09 13:43 | 0769-WD | Fast Track | Fast Track | In Service | Not Provided | 5/8/2015 | 7/24/2014 | SUTTER | LIVE OAK SUB | Solar PV | 1.25 | 7/11/2013 | 8/1/2013 | Fail Screens: 2, 5, 10 | 9/18/2013 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-05-10 17:01 | 0770-WD | Fast Track | Independent Study | In Service | Not Provided | 12/1/2014 | 2/25/2015 | MERCED | EL CAPITAN SUB | Solar PV | 1.5 | 7/11/2013 | 7/18/2013 | Fail Screens: 2, 10 | 8/22/2013 | Fail | Pass | 11/5/2013 | N/A | Executed | No former queue position
2013-06-17 15:54 | 0771-WD | Fast Track | Fast Track | Withdrawn | 9/30/2014 | Withdrawn | Withdrawn | SONOMA | CLOVERDALE SUB | Solar PV | 0.997 | 7/18/2013 | 8/7/2013 | Fail Screens: 2, 10 | 10/3/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-06-11 15:30 | 0772-WD | Fast Track | Independent Study | Withdrawn | 6/2/2015 | Withdrawn | Withdrawn | FRESNO | ORO LOMA SUB | Solar PV | 2 | 7/18/2013 | 8/7/2013 | Fail Screens: 2, 10 | 9/30/2013 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-05-10 10:16 | 0773-WD | Fast Track | Fast Track | Withdrawn | 10/1/2014 | Withdrawn | Withdrawn | SONOMA | LAKEVILLE SUB | Solar PV | 1.5 | 7/25/2013 | 8/5/2013 | Fail Screens: 2, 10 | 10/22/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-05-10 11:25 | 0774-WD | Fast Track | Fast Track | Withdrawn | 10/1/2014 | Withdrawn | Withdrawn | SONOMA | LAKEVILLE SUB | Solar PV | 1.5 | 7/25/2013 | 8/5/2013 | Fail Screens: 2, 10 | 10/22/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-07-05 11:46 | 0775-RD | Fast Track | Fast Track | Withdrawn | 7/14/2014 | Withdrawn | Withdrawn | FRESNO | REEDLEY SUB | Solar PV | 1.7 | 7/25/2013 | 8/5/2013 | Fail Screens: I, J, K, M | 8/28/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-06-25 09:27 | 0776-RD | Fast Track | Fast Track | Withdrawn | 11/4/2013 | Withdrawn | Withdrawn | SOLANO | CORDELIA SUB | Engine, Solar PV, Wind | 1.8429 | 7/25/2013 | 8/15/2013 | Fail Screens: D, F, H, J, K, M | 9/25/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-07-19 14:26 | 0777-RD | Fast Track | Fast Track | In Service | 4/11/2014 |  |  | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Solar PV | 0.027 | 7/25/2013 | 7/25/2013 | Fail | 7/25/2013 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-07-22 14:55 | 0778-RD | Fast Track | Fast Track | In Service | 5/31/2014 |  |  | ALAMEDA | MT EDEN SUB | Engine, Solar PV | 4.137 | 8/1/2013 |  |  | 8/26/2013 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-07-12 09:20 | 0779-RD | Detailed Study | Detailed Study | Withdrawn | 6/16/2014 | Withdrawn | Withdrawn | KERN | LAMONT SUB | Cogeneration | 8 | 8/8/2013 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-07-23 09:28 | 0780-RD | Fast Track | Independent Study | Withdrawn | 6/16/2014 | Withdrawn | Withdrawn | MONTEREY | CASTROVILLE SUB | Other | 3.2 | 8/8/2013 | 8/26/2013 | Fail | 10/9/2013 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | R21 Transition to WDT SGIA
2013-06-24 10:38 | 0781-RD | Fast Track | Independent Study | Withdrawn | 12/30/2014 | Withdrawn | Withdrawn | TULARE | OROSI SUB | Solar PV | 1.5 | 8/8/2013 | 8/26/2013 | Fail | 9/30/2013 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | R21 Transition to WDT SGIA
2013-07-29 16:36 | 0782-RD | Fast Track | Fast Track | In Service | 10/8/2013 |  |  | SANTA CLARA | TRIMBLE SUB | Storage | 0.018 | 8/8/2013 | 8/21/2013 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-07-29 17:20 | 0783-RD | Fast Track | Fast Track | In Service | 12/26/2013 | In Service | 4/11/2014 | SANTA CLARA | MORGAN HILL SUB | Storage | 0.036 | 8/8/2013 | 8/21/2013 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-07-30 10:50 | 0784-RD | Fast Track | Fast Track | In Service | 12/26/2013 | 9/30/2013 | 3/3/2014 | SANTA CLARA | TRIMBLE SUB | Storage | 0.054 | 8/8/2013 | 8/27/2013 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-07-25 14:46 | 0785-RD | Fast Track | Fast Track | Withdrawn | 11/1/2015 | Withdrawn | Withdrawn | SOLANO | GRAND ISLAND SUB | Wind | 3 | 8/15/2013 | 9/4/2013 | Fail Screens: B, F, I, J, K, M | 10/4/2013 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-07-29 17:06 | 0786-RD | Fast Track | Fast Track | In Service | 12/7/2013 |  |  | CONTRA COSTA | RICHMOND R SUB | Engine, Solar PV | 0.67575 | 2013-08-28 | 2013-09-17 | Pass | 2013-09-17 | Complete | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-07-22 09:52 | 0787-RD | Detailed Study | Detailed Study | Withdrawn | 12/31/2013 | Withdrawn | Withdrawn | PLACER | LINCOLN SUB | Solar PV | 2.3 | 8/15/2013 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-08-02 14:11 | 0788-RD | Fast Track | Fast Track | Withdrawn | 9/18/2013 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN Z (EMBARCADERO) SUB | Storage | 0.054 | 8/15/2013 | 8/26/2013 | Pass | 11/7/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-07-29 16:07 | 0789-RD | Fast Track | Fast Track | Withdrawn | 7/1/2014 | Withdrawn | Withdrawn | KERN | KERN OIL SUB | Solar PV | 3 | 8/22/2013 | 9/10/2013 | Fail Screens: F, I, J, M | 10/9/2013 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-07-19 12:33 | 0790-RD | Fast Track | Fast Track | In Service | 10/20/2014 |  |  | YOLO | UC DAVIS MTR STA | Solar PV | 13.6446 | 8/22/2013 | 9/13/2013 | Fail | 10/15/2013 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-08-02 14:50 | 0791-RD | Fast Track | Fast Track | In Service | 9/18/2013 |  |  | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Storage | 0.036 | 8/22/2013 | 8/27/2013 | Fail | 10/4/2013 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-07-02 14:12 | 0792-WD | Fast Track | Fast Track | Withdrawn | 11/25/2014 | Withdrawn | Withdrawn | FRESNO | CAMDEN SUB | Solar PV | 2 | 8/22/2013 | 9/13/2013 | Fail Screens: 2, 10 | 11/19/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-08-09 15:54 | 0793-RD | Fast Track | Fast Track | Withdrawn | 11/23/2013 | Withdrawn | Withdrawn | SANTA CLARA | SAN JOSE B SUB | Other | 0.036 | 8/29/2013 | 9/23/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-08-20 10:07 | 0794-RD | Fast Track | Fast Track | In Service | 11/23/2013 |  |  | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Storage | 0.054 | 8/29/2013 | 8/29/2013 | Fail Screens: A | 11/7/2013 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-08-02 16:53 | 0795-WD | Fast Track | Fast Track | Withdrawn | 10/15/2013 | Withdrawn | Withdrawn | TUOLUMNE | PEORIA SUB | Solar PV | 3 | 8/29/2013 | 9/17/2013 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-08-15 12:17 | 0796-RD | Fast Track | Independent Study | Withdrawn | 12/1/2014 | Withdrawn | Withdrawn | FRESNO | TIVY VALLEY SUB | Solar PV | 1.5 | 8/29/2013 | 9/9/2013 | Fail | 10/15/2013 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | R21 Transition to WDT SGIA
2013-08-09 13:16 | 0797-WD | Fast Track | Fast Track | Withdrawn | 5/1/2015 | Withdrawn | Withdrawn | SAN BENITO | HOLLISTER SUB | Solar PV | 1 | 8/29/2013 | 9/13/2013 | Fail Screens: 2, 6, 10 | 11/21/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-08-09 15:40 | 0798-WD | Fast Track | Independent Study | Withdrawn | 5/1/2015 | Withdrawn | Withdrawn | MADERA | CASSIDY SUB | Solar PV | 1 | 8/29/2013 | 9/18/2013 | Fail Screens: 2, 10 | 11/19/2013 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-08-09 15:53 | 0799-WD | Fast Track | Independent Study | Withdrawn | 5/1/2015 | Withdrawn | Withdrawn | MADERA | CASSIDY SUB | Solar PV | 1 | 8/29/2013 | 9/18/2013 | Fail Screens: 2, 10 | 11/19/2013 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-08-09 16:16 | 0800-WD | Fast Track | Independent Study | Withdrawn | 5/1/2015 | Withdrawn | Withdrawn | MADERA | CASSIDY SUB | Solar PV | 1 | 8/29/2013 | 9/18/2013 | Fail Screens: 2, 5, 10 | 11/19/2013 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-08-12 13:35 | 0801-WD | Fast Track | Fast Track | Withdrawn | 5/1/2015 | Withdrawn | Withdrawn | SAN JOAQUIN | CARBONA SUB | Solar PV | 1 | 8/29/2013 | 9/18/2013 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-08-12 13:38 | 0802-WD | Fast Track | Fast Track | Withdrawn | 5/1/2015 | Withdrawn | Withdrawn | SAN JOAQUIN | CARBONA SUB | Solar PV | 1 | 8/29/2013 | 9/19/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-08-12 13:40 | 0803-WD | Fast Track | Fast Track | Withdrawn | 5/1/2015 | Withdrawn | Withdrawn | SAN JOAQUIN | CARBONA SUB | Solar PV | 1 | 8/29/2013 | 9/16/2013 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-08-20 16:20 | 0804-RD | Fast Track | Fast Track | Withdrawn | 9/1/2014 | Withdrawn | Withdrawn | EL DORADO | DIAMOND SPRINGS SUB | Other | 0.506 | 8/29/2013 | 9/9/2013 | Fail Screens: B, C, G, I, J, K, M | 10/21/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-08-21 15:56 | 0805-RD | Fast Track | Fast Track | Withdrawn | 8/19/2015 | Withdrawn | Withdrawn | TEHAMA | CORNING SUB | Other | 3 | 8/29/2013 | 9/10/2013 | Fail Screens: B, F, I, J, K, M | 10/7/2013 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-08-19 13:33 | 0806-RD | Fast Track | Fast Track | In Service | 11/30/2013 |  |  | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Storage | 0.054 | 9/5/2013 | 9/26/2013 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-08-09 16:06 | 0807-RD | Fast Track | Fast Track | Withdrawn | 1/5/2015 | Withdrawn | Withdrawn | SAN LUIS OBISPO | MESA SUB | Solar PV | 3 | 9/5/2013 | 9/23/2013 | Fail Screens: I, J, K, M | 10/22/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-08-21 15:15 | 0808-RD | Fast Track | Fast Track | Withdrawn | 4/30/2015 | Withdrawn | Withdrawn | SAN JOAQUIN | MANTECA SUB | Solar PV | 3 | 9/5/2013 | 9/10/2013 | Fail Screens: B, I, J, K, M | 10/15/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-07-26 14:42 | 0809-RD | Fast Track | Fast Track | Withdrawn | 3/31/2024 | Withdrawn | Withdrawn | LAKE | CLEAR LAKE SUB | Solar PV | 1.24 | 9/12/2013 | 9/25/2013 | Fail Screens: B, I, J, K, M | 11/6/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-08-16 16:42 | 0810-RD | Fast Track | Fast Track | Withdrawn | 2/20/2015 | Withdrawn | Withdrawn | SAN LUIS OBISPO | TEMPLETON SUB | Solar PV | 3 | 9/12/2013 | 9/24/2013 | Fail Screens: F, G, I, J, K, M | 10/29/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-08-19 10:08 | 0811-RD | Fast Track | Fast Track | Withdrawn | 2/18/2015 | Withdrawn | Withdrawn | TEHAMA | CORNING SUB | Solar PV | 2 | 9/12/2013 | 9/23/2013 | Fail Screens: F, G, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-08-23 17:10 | 0812-RD | Fast Track | Fast Track | Withdrawn | 2/23/2015 | Withdrawn | Withdrawn | TULARE | OROSI SUB | Solar PV | 3 | 9/12/2013 | 9/26/2013 | Fail Screens: F, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-08-23 14:01 | 0813-WD | Fast Track | Fast Track | Withdrawn | 12/1/2014 | Withdrawn | Withdrawn | SHASTA | JESSUP SUB | Solar PV | 1.406 | 9/12/2013 | 9/24/2013 | Fail Screens: 2, 10 | 10/28/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-08-29 13:03 | 0814-RD | Fast Track | Fast Track | Withdrawn | 10/8/2014 | Withdrawn | Withdrawn | LAKE | HARTLEY SUB | Solar PV | 1.5 | 9/12/2013 | 10/9/2013 | Fail Screens: B, D, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-08-09 15:16 | 0815-RD | Fast Track | Fast Track | Withdrawn | 11/23/2013 | Withdrawn | Withdrawn | ALAMEDA | OAKLAND D SUB | Storage | 0.036 | 9/19/2013 | 9/24/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-08-15 14:13 | 0816-RD | Detailed Study | Detailed Study | In Service | 2/9/2014 |  |  | COLUSA | COLUSA SUB | Engine, Solar PV | 0.036 | 9/19/2013 | N/A | N/A | N/A | N/A | Pass | 1/22/2014 | N/A | Executed | No former queue position
2013-09-05 14:29 | 0817-RD | Fast Track | Detailed Study | Withdrawn | 3/31/2014 | Withdrawn | Withdrawn | BUTTE | WYANDOTTE SUB | Solar PV | 0.054 | 9/19/2013 | 10/8/2013 | Fail Screens: D, I, J, K, M | 11/22/2013 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-05 14:52 | 0818-RD | Fast Track | Fast Track | Withdrawn | 3/31/2014 | Withdrawn | Withdrawn | BUTTE | PARADISE SUB | Solar PV | 0.32 | 9/19/2013 | 10/8/2013 | Fail Screens: I, J, K, M | 11/19/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-05 15:35 | 0819-RD | Fast Track | Fast Track | Withdrawn | 3/31/2015 | Withdrawn | Withdrawn | MADERA | BONITA SUB | Solar PV | 0.42 | 9/19/2013 | 10/8/2013 | Fail Screens: I, J, K, M | 11/19/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-05 16:01 | 0820-RD | Fast Track | Fast Track | Withdrawn | 3/31/2014 | Withdrawn | Withdrawn | GLENN | GLENN SUB | Solar PV | 0.6 | 9/19/2013 | 10/8/2013 | Fail Screens: F, I, J, K, M | 11/26/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-05 16:34 | 0821-RD | Fast Track | Fast Track | Withdrawn | 3/31/2014 | Withdrawn | Withdrawn | LAKE | CLEAR LAKE SUB | Solar PV | 1 | 9/19/2013 | 10/8/2013 | Fail Screens: F, I, J, K, M | 11/19/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-05 17:33 | 0822-RD | Fast Track | Fast Track | Withdrawn | 3/31/2015 | Withdrawn | Withdrawn | EL DORADO | OLETA SUB | Solar PV | 0.03 | 9/19/2013 | 10/8/2013 | Fail Screens: F, I, J, K, M | 11/19/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-05 18:06 | 0823-RD | Fast Track | Fast Track | Withdrawn | 6/1/2015 | Withdrawn | Withdrawn | SHASTA | DESCHUTES SUB | Solar PV | 0.03 | 9/19/2013 | 10/8/2013 | Fail Screens: H, I, J, M | 11/26/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-05 18:12 | 0824-RD | Fast Track | Fast Track | Withdrawn | 3/31/2014 | Withdrawn | Withdrawn | SHASTA | COTTONWOOD SUB | Solar PV | 0.2 | 9/19/2013 | 10/8/2013 | Fail Screens: I, J, K, M | 11/22/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-05 18:19 | 0825-RD | Fast Track | Detailed Study | Withdrawn | 6/1/2015 | Withdrawn | Withdrawn | GLENN | GLENN SUB | Solar PV | 0.018 | 9/19/2013 | 10/8/2013 | Fail Screens: I, J, K, M | 11/26/2013 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-05 18:29 | 0826-RD | Fast Track | Fast Track | Withdrawn | 3/31/2014 | Withdrawn | Withdrawn | BUTTE | ANITA SUB | Solar PV | 0.001 | 9/19/2013 | 10/8/2013 | Fail Screens: I, J, K, M | 11/19/2013 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-05 18:39 | 0827-RD | Fast Track | Fast Track | Withdrawn | 6/1/2015 | Withdrawn | Withdrawn | FRESNO | FIGARDEN SUB | Solar PV | 0.2 | 9/19/2013 | 10/23/2013 | Fail Screens: I, J, K, M | 1/2/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-05 18:41 | 0828-RD | Fast Track | Detailed Study | Withdrawn | 3/31/2015 | Withdrawn | Withdrawn | GLENN | LOGAN CREEK SUB | Solar PV | 1.85 | 9/19/2013 | 10/23/2013 | Fail Screens: F, I, J, K, M | 1/10/2014 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-05 20:45 | 0829-RD | Fast Track | Detailed Study | Withdrawn | 6/1/2015 | Withdrawn | Withdrawn | SHASTA | DESCHUTES SUB | Solar PV | 1.85 | 9/19/2013 | 10/23/2013 | Fail Screens: I, J, K, M | 1/10/2014 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-05 20:58 | 0830-RD | Fast Track | Fast Track | Withdrawn | 6/1/2015 | Withdrawn | Withdrawn | SHASTA | GIRVAN SUB | Solar PV | 0.55 | 9/19/2013 | 10/23/2013 | Fail Screens: I, J, K, M | 1/10/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-05 21:03 | 0831-RD | Fast Track | Fast Track | Withdrawn | 3/31/2014 | Withdrawn | Withdrawn | SUTTER | LIVE OAK SUB | Solar PV | 0.058 | 9/19/2013 | 10/23/2013 | Fail Screens: I, J, K, M | 1/2/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-05 21:08 | 0832-RD | Fast Track | Fast Track | Withdrawn | 6/1/2015 | Withdrawn | Withdrawn | SHASTA | ANDERSON SUB | Solar PV | 4.49 | 9/19/2013 | 10/23/2013 | Fail Screens: I, J, M | 1/10/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-05 21:14 | 0833-RD | Fast Track | Detailed Study | Withdrawn | 3/31/2015 | Withdrawn | Withdrawn | MERCED | ATWATER SUB | Solar PV | 9.6 | 9/19/2013 | 10/23/2013 | Fail Screens: I, J, K, M | 1/2/2014 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-05 21:16 | 0834-RD | Fast Track | Detailed Study | Withdrawn | 6/1/2015 | Withdrawn | Withdrawn | LASSEN | MCARTHUR SUB | Solar PV | 4.66 | 9/19/2013 | 10/23/2013 | Fail Screens: F, I, J, K, M | 1/10/2014 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-05 21:25 | 0835-RD | Fast Track | Fast Track | Withdrawn | 6/1/2015 | Withdrawn | Withdrawn | GLENN | CAPAY SUB | Solar PV | 2 | 9/19/2013 | 10/23/2013 | Fail Screens: I, J, M | 1/10/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-05 21:37 | 0836-RD | Fast Track | Fast Track | Withdrawn | 6/1/2015 | Withdrawn | Withdrawn | AMADOR | ELECTRA SUB | Solar PV | 3 | 9/19/2013 | 10/23/2013 | Fail Screens: I, J, K, M | 1/2/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-05 21:44 | 0837-RD | Fast Track | Fast Track | Withdrawn | 6/1/2015 | Withdrawn | Withdrawn | KERN | LERDO SUB | Solar PV | 3.2 | 9/19/2013 | 11/5/2013 | Fail Screens: I, J, M | 1/7/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-05 22:33 | 0838-RD | Fast Track | Fast Track | Withdrawn | 3/31/2014 | Withdrawn | Withdrawn | MONTEREY | SALINAS SUB | Solar PV | 0.21 | 9/19/2013 | 11/5/2013 | Fail Screens: I, J, K, M | 1/7/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-09 15:14 | 0839-RD | Fast Track | Fast Track | Withdrawn | 3/31/2014 | Withdrawn | Withdrawn | TEHAMA | CORNING SUB | Solar PV | 0.21 | 9/19/2013 | 11/5/2013 | Fail Screens: F, I, J, K | 1/7/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-08-14 12:16 | 0840-RD | Fast Track | Fast Track | Withdrawn | 4/30/2014 | Withdrawn | Withdrawn | MARIN | IGNACIO SUB | Solar PV | 0.21 | 9/26/2013 | 10/16/2013 | Fail Screens: I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-03 11:35 | 0841-RD | Fast Track | Fast Track | Withdrawn | 12/30/2014 | Withdrawn | Withdrawn | MONTEREY | JOLON SUB | Solar PV | 0.21 | 9/26/2013 | 10/16/2013 | Fail Screens: I, J, K, M | 12/9/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-04 10:46 | 0842-RD | Fast Track | Fast Track | Withdrawn | 12/30/2014 | Withdrawn | Withdrawn | GLENN | FIGARDEN SUB | Solar PV | 1.5 | 9/26/2013 | 10/16/2013 | Fail Screens: F, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-10 13:32 | 0843-RD | Fast Track | Fast Track | Withdrawn | 12/30/2014 | Withdrawn | Withdrawn | MADERA | DAIRYLAND SUB | Solar PV | 1.5 | 9/26/2013 | 10/16/2013 | Fail | 11/27/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | R21 Transition to WDT SGIA
2013-09-16 15:34 | 0844-WD | Fast Track | Fast Track | Withdrawn | 6/16/2014 | Withdrawn | Withdrawn | SHASTA | PIT #1 PH | Solar PV | 0.2 | 10/3/2013 | 10/23/2013 | Fail Screens: 2, 10 | 12/12/2013 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-14 10:03 | 0845-WD | Fast Track | Fast Track | Withdrawn | 7/31/2014 | Withdrawn | Withdrawn | YOLO | PUTAH CREEK SUB | Solar PV | 2.4 | 10/3/2013 | 10/11/2013 | Fail Screens: 2, 10 | 12/5/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-23 16:05 | 0846-RD | Fast Track | Fast Track | In Service | 1/30/2014 |  |  | SAN FRANCISCO | SAN FRAN Z (EMBARCADERO) SUB | Solar PV | 4.8 | 10/3/2013 | 10/24/2013 | Fail Screens: J, M | 12/2/2013 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-09-12 18:30 | 0847-RD | Fast Track | Fast Track | Withdrawn | 6/1/2015 | Withdrawn | Withdrawn | BUTTE | SYCAMORE CREEK SUB | Solar PV | 2 | 10/3/2013 | 10/21/2013 | Fail Screens: F, I, J, K, M | 12/4/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-19 10:33 | 0848-RD | Fast Track | Fast Track | Withdrawn | 12/30/2014 | Withdrawn | Withdrawn | TEHAMA | CORNING SUB | Solar PV | 0.8 | 10/3/2013 | 10/21/2013 | Fail | 12/18/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | R21 Transition to WDT SGIA
2013-09-23 17:15 | 0849-RD | Fast Track | Fast Track | Withdrawn | 5/1/2015 | Withdrawn | Withdrawn | YUBA | BANGOR SUB | Other | 0.5 | 10/3/2013 | 10/21/2013 | Fail Screens: B, F, G, I, J, K, M | 12/3/2013 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-25 11:29 | 0850-WD | Fast Track | Fast Track | Withdrawn | 7/31/2015 | Withdrawn | Withdrawn | SAN LUIS OBISPO | SAN MIGUEL SUB | Solar PV | 1.5 | 10/10/2013 | 10/30/2013 | Fail Screens: 2, 4, 6, 10 | 12/10/2013 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-10-02 10:19 | 0851-RD | Fast Track | Fast Track | In Service | 12/31/2013 | In Service | 3/13/2014 | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Solar PV | 0.16376 | 10/10/2013 | 10/24/2013 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-09-21 09:04 | 0852-RD | Fast Track | Fast Track | Withdrawn | 8/28/2015 | Withdrawn | Withdrawn | KINGS | TULARE LAKE SUB | Solar PV | 3 | 10/17/2013 | 10/29/2013 | Fail Screens: F, I, J, K, M | 12/11/2013 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-09 09:15 | 0853-RD | Fast Track | Fast Track | Withdrawn | 6/1/2015 | Withdrawn | Withdrawn | YUBA | DOBBINS SUB | Solar PV | 0.5 | 10/17/2013 | 10/29/2013 | Fail Screens: F, G, I, J, K, M | 1/3/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-10-01 16:55 | 0854-WD | Fast Track | Fast Track | Active | 4/1/2014 | 3/30/2018 |  | CONTRA COSTA | LONE TREE SUB | Solar PV | 0.93834 | 10/17/2013 | 11/6/2013 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-10-08 10:08 | 0855-RD | Fast Track | Fast Track | Withdrawn | 12/30/2013 | Withdrawn | Withdrawn | SAN MATEO | RED BLUFF SUB | Other | 2 | 10/17/2013 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-25 12:47 | 0856-RD | Fast Track | Fast Track | Withdrawn | 12/30/2014 | Withdrawn | Withdrawn | BUTTE | WYANDOTTE SUB | Solar PV | 1.5 | 10/24/2013 | 11/7/2013 | Fail Screens: F, G, H, I, J, K, M | 12/23/2013 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-25 13:58 | 0857-RD | Fast Track | Independent Study | In Service | 12/30/2014 | 12/22/2017 | 12/8/2017 | MERCED | ORTIGA SUB | Solar PV | 3 | 10/24/2013 | 11/7/2013 | Fail Screens: 4, 5, 7, 9, 10 | 12/12/2013 | Fail | Pass | 5/6/2014 | N/A | Executed | R21 Transition to WDT SGIA
2013-09-09 13:10 | 0858-RD | Fast Track | Fast Track | Withdrawn | 3/31/2014 | Withdrawn | Withdrawn | TEHAMA | RED BLUFF SUB | Solar PV | 0.75 | 10/24/2013 | 11/8/2013 | Fail Screens: H, I, J, K, M | 12/31/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-10 15:45 | 0859-RD | Fast Track | Fast Track | Withdrawn | 6/1/2015 | Withdrawn | Withdrawn | TEHAMA | CORNING SUB | Solar PV | 1.25 | 10/24/2013 | 11/8/2013 | Fail Screens: F, I, J, K, M | 12/30/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-09-10 19:11 | 0860-RD | Fast Track | Independent Study | Withdrawn | 6/1/2015 | Withdrawn | Withdrawn | BUTTE | SYCAMORE CREEK SUB | Solar PV | 1.25 | 10/24/2013 | 11/8/2013 | Fail | 12/30/2013 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | R21 Transition to WDT SGIA
2013-10-14 16:57 | 0861-RD | Fast Track | Fast Track | Withdrawn | 12/30/2013 | Withdrawn | Withdrawn | FRESNO | MANCHESTER SUB | Storage | 0.036 | 10/24/2013 | 11/14/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-10-14 17:09 | 0862-RD | Fast Track | Fast Track | Withdrawn | 12/30/2013 | Withdrawn | Withdrawn | SAN FRANCISCO | CASTRO SUB | Storage | 0.054 | 10/24/2013 | 11/5/2013 | Fail | 1/3/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-10-03 14:26 | 0863-RD | Fast Track | Fast Track | In Service | 12/30/2013 |  |  | SAN FRANCISCO | SAN FRAN Z (EMBARCADERO) SUB | Engine | 0.32 | 10/24/2013 | 11/22/2013 | Fail | 1/17/2014 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-10-15 15:21 | 0864-RD | Fast Track | Fast Track | In Service | 12/30/2013 |  |  | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Storage | 0.42 | 10/31/2013 | 11/15/2013 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-10-15 16:30 | 0865-RD | Fast Track | Fast Track | In Service | 12/30/2013 |  |  | SANTA CLARA | MONTAGUE SUB | Storage | 0.6 | 10/31/2013 | 11/15/2013 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-10-21 09:53 | 0866-RD | Fast Track | Fast Track | Withdrawn | 11/28/2013 | Withdrawn | Withdrawn | SAN JOAQUIN | LAMMERS SUB | Steam Turbine | 1 | 10/31/2013 | 11/5/2013 | Fail | 12/11/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-10-17 11:21 | 0867-RD | Fast Track | Fast Track | In Service | 12/30/2013 | In Service | 2/7/2014 | SAN MATEO | MILLBRAE SUB | Storage | 0.03 | 10/31/2013 | 11/15/2013 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-10-14 16:28 | 0868-WD | Fast Track | Fast Track | In Service | 1/5/2015 | 5/29/2015 | 1/21/2015 | KERN | BAKERSFIELD SUB | Solar PV | 0.03 | 11/7/2013 | 11/25/2013 | Fail Screens: 2, 6, 10 | 1/3/2014 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-10-09 14:33 | 0869-WD | Fast Track | Fast Track | Withdrawn | 1/20/2014 | Withdrawn | Withdrawn | TUOLUMNE | PEORIA SUB | Solar PV | 0.2 | 11/7/2013 | 11/21/2013 | Fail Screens: 2, 10 | 1/3/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-10-30 16:13 | 0870-RD | Fast Track | Fast Track | In Service | 12/25/2013 |  |  | KINGS | CAMDEN SUB | Solar PV | 0.018 | 11/7/2013 | 11/20/2013 | Fail | 1/8/2014 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-10-15 12:46 | 0871-WD | Fast Track | Fast Track | Withdrawn | 7/21/2014 | Withdrawn | Withdrawn | TEHAMA | RED BLUFF SUB | Solar PV | 0.001 | 11/13/2013 | 11/25/2013 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-10-16 10:55 | 0872-WD | Fast Track | Fast Track | In Service | 6/1/2015 | 7/1/2015 | 11/30/2015 | TEHAMA | CORNING SUB | Solar PV | 0.2 | 11/13/2013 | 12/5/2013 | Fail Screens: 2, 4, 10 | 1/23/2014 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-10-30 10:38 | 0873-RD | Fast Track | Fast Track | Withdrawn | 12/30/2013 | Withdrawn | Withdrawn | SOLANO | CORDELIA SUB | Solar PV, Wind | 1.85 | 11/13/2013 | 11/19/2013 | Fail Screens: B, F, H, I, J, M | 12/23/2013 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-10-25 12:20 | 0874-RD | Fast Track | Fast Track | Withdrawn | 5/22/2015 | Withdrawn | Withdrawn | LAKE | REDBUD SUB | Solar PV | 1.85 | 11/13/2013 | 12/2/2013 | Fail Screens: I, J, K, M | 1/9/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-10-29 10:51 | 0875-RD | Detailed Study | Detailed Study | Withdrawn | 3/16/2015 | Withdrawn | Withdrawn | MONTEREY | PRUNEDALE SUB | Other | 0.55 | 11/15/2013 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-10-29 19:42 | 0876-WD | Fast Track | Fast Track | Withdrawn | 11/17/2014 | Withdrawn | Withdrawn | YOLO | ZAMORA SUB | Solar PV | 0.058 | 11/15/2013 | 12/3/2013 | Fail Screens: 2, 4, 10 | 1/15/2014 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-11-07 05:41 | 0877-RD | Fast Track | Fast Track | In Service | 1/17/2014 | 5/15/2016 |  | SAN MATEO | BELMONT SUB | Engine | 4.49 | 11/20/2013 | 12/11/2013 | Fail | 2/13/2014 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-11-14 14:41 | 0878-RD | Fast Track | Fast Track | Withdrawn | 12/31/2016 | Withdrawn | Withdrawn | SOLANO | GRAND ISLAND SUB | Wind | 9.6 | 11/26/2013 | 12/12/2013 | Fail Screens: I, J, K, M | 1/27/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-10-15 12:24 | 0879-RD | Fast Track | Fast Track | Withdrawn | 1/30/2015 | Withdrawn | Withdrawn | MERCED | DOS PALOS SUB | Solar PV | 4.66 | 11/26/2013 | 12/9/2013 | Fail | 1/14/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | R21 Transition to WDT SGIA
2013-11-14 15:07 | 0880-WD | Fast Track | Independent Study | Withdrawn | 3/20/2014 | Withdrawn | Withdrawn | SHASTA | JESSUP SUB | Other | 2 | 11/26/2013 | 12/17/2013 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-11-18 15:49 | 0881-RD | Fast Track | Fast Track | In Service | 1/29/2014 | In Service | 1/15/2014 | EL DORADO | DIAMOND SPRINGS SUB | Storage | 3 | 11/26/2013 | 12/2/2013 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-11-21 15:38 | 0882-RD | Fast Track | Fast Track | Withdrawn | 1/15/2014 | Withdrawn | Withdrawn | TULARE | DINUBA SUB | Solar PV | 3.2 | 12/17/2013 | 1/8/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-12-12 11:23 | 0883-WD | Fast Track | Fast Track | Withdrawn | 9/1/2015 | Withdrawn | Withdrawn | SHASTA | JESSUP SUB | Solar PV | 0.21 | 12/24/2013 | 1/23/2014 | Fail Screens: 2, 10 | 3/5/2014 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-12-12 09:09 | 0884-RD | Fast Track | Fast Track | In Service | 2/27/2014 | 11/25/2014 | 11/25/2014 | TULARE | DINUBA SUB | Solar PV | 0.21 | 12/24/2013 | 2/20/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-12-23 20:30 | 0885-WD | Fast Track | Fast Track | In Service | 7/18/2014 | 12/31/2016 | 5/11/2017 | MARIN | STAFFORD SUB | Solar PV | 0.21 | 1/7/2014 | 1/27/2014 | Fail Screens: 2, 10 | 3/3/2014 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2013-12-23 20:43 | 0886-WD | Fast Track | Fast Track | Withdrawn | 7/18/2014 | Withdrawn | Withdrawn | MARIN | STAFFORD SUB | Solar PV | 0.21 | 1/7/2014 | 1/27/2014 | Fail Screens: 2, 10 | 3/3/2014 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2013-12-24 11:34 | 0887-WD | Fast Track | Independent Study | In Service | 2/20/2014 | 7/30/2014 | 6/23/2014 | SOLANO | VACA DIXON SUB | Storage | 2.4 | 1/15/2014 | 1/23/2014 | Fail | N/A | N/A (Independent Study) | Pass | 4/16/2014 | N/A | Executed | No former queue position
2014-01-07 17:17 | 0888-WD | Fast Track | Independent Study | In Service | 2/20/2014 | 9/22/2014 | 9/1/2014 | SANTA CLARA | SWIFT SUB | Storage | 4.8 | 1/15/2014 | 1/23/2014 | Fail | N/A | N/A (Independent Study) | Pass | 4/23/2014 | N/A | Executed | No former queue position
2014-01-02 15:08 | 0889-RD | Fast Track | Fast Track | In Service | 3/25/2014 | 3/7/2014 | 3/24/2014 | SANTA CRUZ | ROB ROY SUB | Storage | 0.21 | 1/15/2014 | 1/24/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-01-02 18:19 | 0890-RD | Fast Track | Fast Track | In Service | 3/18/2014 | In Service | 3/6/2014 | SANTA CLARA | EDENVALE SUB | Storage | 0.21 | 1/15/2014 | 1/17/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-01-04 19:21 | 0891-WD | Fast Track | Fast Track | Withdrawn | 6/1/2015 | Withdrawn | Withdrawn | ALAMEDA | HERDLYN SUB | Solar PV | 2 | 1/15/2014 | 1/30/2014 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-01-09 15:45 | 0892-RD | Fast Track | Fast Track | Withdrawn | 8/18/2014 | Withdrawn | Withdrawn | KERN | TUPMAN SUB | Solar PV | 0.21 | 1/22/2014 | 1/31/2014 | Fail Screens: F, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-01-14 12:07 | 0893-RD | Fast Track | Fast Track | In Service | 3/27/2014 |  |  | SAN FRANCISCO | SAN FRAN A (POTRERO PP) SUB | Solar PV | 0.8 | 1/22/2014 | 1/30/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-01-02 15:57 | 0894-RD | Fast Track | Fast Track | Withdrawn | 8/18/2014 | Withdrawn | Withdrawn | YOLO | WOODLAND SUB | Solar PV | 0.5 | 1/22/2014 | 2/6/2014 | Fail Screens: I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-01-08 07:28 | 0895-RD | Fast Track | Fast Track | Withdrawn | 12/31/2015 | Withdrawn | Withdrawn | SOLANO | PEABODY SUB | Wind | 2.5 | 1/22/2014 | 2/10/2014 | Fail Screens: F, G, I, J, K, M | 4/15/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-01-14 13:34 | 0896-RD | Fast Track | Fast Track | In Service | 3/26/2014 | In Service | 5/15/2014 | SANTA CLARA | SAN JOSE B SUB | Storage | 0.054 | 1/29/2014 | 2/19/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-01-13 11:04 | 0897-RD | Fast Track | Fast Track | Withdrawn | 8/18/2014 | Withdrawn | Withdrawn | YOLO | DAVIS SUB | Solar PV | 1 | 2/5/2014 | 2/21/2014 | Fail Screens: F, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-01-31 12:37 | 0898-RD | Fast Track | Fast Track | In Service | 4/24/2014 |  |  | EL DORADO | PLACERVILLE SUB | Solar PV | 0.03977 | 2/5/2014 | 2/6/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-01-13 13:27 | 0899-RD | Fast Track | Fast Track | Withdrawn | 3/30/2015 | Withdrawn | Withdrawn | KERN | TAFT SUB | Solar PV | 0.75 | 2/12/2014 | 3/4/2014 | Fail Screens: I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-01-13 13:38 | 0900-RD | Fast Track | Detailed Study | Withdrawn | 3/16/2015 | Withdrawn | Withdrawn | TEHAMA | LOS MOLINOS SUB | Solar PV | 0.5 | 2/12/2014 | 3/3/2014 | Fail Screens: I, J, K, M | 4/18/2014 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-02-12 09:59 | 0901-RD | Fast Track | Fast Track | In Service | 4/23/2014 |  |  | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Solar PV | 0.01 | 2/19/2014 | 3/19/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-02-14 10:07 | 0902-RD | Fast Track | Fast Track | In Service | 4/22/2014 |  |  | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Solar PV | 0.2 | 2/19/2014 | 3/19/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-02-05 18:23 | 0903-RD | Fast Track | Fast Track | In Service | 8/6/2014 | 10/15/2014 | 9/18/2014 | SANTA CLARA | SAN JOSE A SUB | Engine | 0.32 | 2/26/2014 | 3/19/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-02-18 16:50 | 0904-RD | Fast Track | Fast Track | In Service | 4/24/2014 | In Service | 5/15/2014 | EL DORADO | PLACERVILLE SUB | Solar PV | 0.42 | 2/26/2014 | 4/8/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-02-17 14:29 | 0905-RD | Fast Track | Fast Track | Withdrawn | 9/1/2014 | Withdrawn | Withdrawn | FRESNO | AUBERRY SUB | Solar PV | 0.6 | 2/26/2014 | 3/18/2014 | Fail Screens: J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-02-12 11:42 | 0906-RD | Fast Track | Fast Track | Withdrawn | 4/24/2014 | Withdrawn | Withdrawn | ALAMEDA | OAKLAND X SUB | Other | 1 | 2/26/2014 | 3/31/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-02-07 12:00 | 0907-RD | Fast Track | Fast Track | Withdrawn | 2/13/2015 | Withdrawn | Withdrawn | MARIN | NOVATO SUB | Solar PV | 0.03 | 3/5/2014 | 3/25/2014 | Fail Screens: I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-02-07 13:45 | 0908-RD | Fast Track | Fast Track | Withdrawn | 2/13/2015 | Withdrawn | Withdrawn | MARIN | NOVATO SUB | Solar PV | 0.72 | 3/5/2014 | 3/25/2014 | Fail Screens: I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-02-28 14:00 | 0909-RD | Fast Track | Fast Track | In Service | 5/21/2014 |  |  | COLUSA | COLUSA SUB | Solar PV, Turbine | 7.602 | 3/5/2014 | 3/21/2014 | Fail |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-02-17 17:38 | 0910-RD | Fast Track | Fast Track | In Service | 4/23/2014 |  |  | SAN MATEO | BELMONT SUB | Engine | 0.75 | 3/12/2014 | 4/3/2014 | Fail | 6/2/2014 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-02-24 11:27 | 0911-WD | Independent Study | Independent Study | Withdrawn | 5/1/2014 | Withdrawn | Withdrawn | SHASTA | JESSUP SUB | Biomass | 6.8 | 3/12/2014 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-02-28 12:28 | 0912-RD | Fast Track | Fast Track | In Service | 5/28/2014 |  |  | PLACER | PLEASANT GROVE SUB | Engine | 21.8 | 3/12/2014 | 3/14/2014 | Fail | 5/5/2014 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-03-04 21:44 | 0913-WD | Fast Track | Independent Study | In Service | 8/1/2014 | 4/22/2016 | 10/5/2016 | CONTRA COSTA | RICHMOND R SUB | Solar PV | 2.0657 | 3/19/2014 | 4/22/2014 | Fail Screens: 2, 4, 10 | 6/26/2014 | Fail | Pass | 2014-09-03 | 06/23/2015 | Executed | No former queue position
2014-03-11 09:19 | 0914-RD | Fast Track | Fast Track | Withdrawn | 3/1/2016 | Withdrawn | Withdrawn | MERCED | WRIGHT SUB | Solar PV | 1.5 | 3/26/2014 | 4/8/2014 | Fail Screens: F, I, J, K, M | 5/13/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-03-21 15:30 | 0915-WD | Fast Track | Fast Track | In Service | 4/1/2015 | 11/30/2015 | 4/8/2016 | KINGS | HENRIETTA SUB | Solar PV | 2 | 4/9/2014 | 4/17/2014 | Fail Screens: 2, 5, 10 | 6/9/2014 | Complete | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-03-13 14:23 | 0916-RD | Fast Track | Fast Track | Withdrawn | 5/22/2014 | Withdrawn | Withdrawn | ALAMEDA | MT EDEN SUB | Storage | 0.42 | 4/9/2014 | 6/10/2014 | Fail | 7/30/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-03-26 17:40 | 0917-RD | Fast Track | Fast Track | Withdrawn | 9/1/2015 | Withdrawn | Withdrawn | YUBA | BROWNS VALLEY SUB | Other | 0.6 | 4/9/2014 | 5/22/2014 | Fail Screens: B, C, F, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-03-17 10:43 | 0918-RD | Independent Study | Independent Study | Withdrawn | 10/1/2015 | Withdrawn | Withdrawn | BUTTE | SYCAMORE CREEK SUB | Solar PV | 1 | 4/16/2014 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | R21 Transition to WDT SGIA
2014-03-25 14:30 | 0919-RD | Fast Track | Fast Track | Withdrawn | 1/29/2016 | Withdrawn | Withdrawn | LAKE | REDBUD SUB | Solar PV | 0.03 | 4/16/2014 | 5/1/2014 | Fail Screens: B, F, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-03-28 16:45 | 0920-WD | Cluster | Cluster | Withdrawn | 3/25/2016 | Withdrawn | Withdrawn | KERN | LAKEVIEW SUB | Solar PV | 18 | 4/16/2014 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-04-07 16:36 | 0921-RD | Fast Track | Fast Track | In Service | 6/26/2014 |  |  | SAN FRANCISCO | SAN FRAN Z (EMBARCADERO) SUB | Storage | 0.054 | 4/16/2014 | 5/6/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-03-27 10:49 | 0922-RD | Detailed Study | Detailed Study | Withdrawn | 6/25/2014 | Withdrawn | Withdrawn | ALAMEDA | NEWARK SUB | Storage | 2 | 4/16/2014 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-04-01 16:25 | 0923-WD | Fast Track | Fast Track | Withdrawn | 10/20/2014 | Withdrawn | Withdrawn | MARIN | GREENBRAE SUB | Solar PV | 0.3 | 4/23/2014 | 5/14/2014 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-04-07 15:24 | 0924-WD | Fast Track | Fast Track | Withdrawn | 4/1/2015 | Withdrawn | Withdrawn | SAN JOAQUIN | MANTECA SUB | Solar PV | 0.432 | 4/23/2014 | 7/1/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-04-17 15:10 | 0925-RD | Fast Track | Fast Track | In Service | 6/19/2014 | 8/1/2014 | 8/27/2014 | SAN FRANCISCO | SAN FRAN A (POTRERO PP) SUB | Storage | 0.108 | 4/29/2014 | 5/13/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-03-06 09:03 | 0926-RD | Fast Track | Fast Track | Withdrawn | 7/18/2014 | Withdrawn | Withdrawn | SANTA CLARA | SAN JOSE B SUB | Other | 2 | 5/7/2014 | 6/10/2014 | Fail Screens: B, F, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-04-18 10:23 | 0927-RD | Fast Track | Fast Track | In Service | 6/25/2014 | 8/28/2014 | 8/28/2014 | SAN MATEO | BELMONT SUB | Storage | 0.02895 | 5/7/2014 | 5/12/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-04-18 11:10 | 0928-RD | Fast Track | Fast Track | In Service | 6/25/2014 | 7/30/2014 | 7/30/2014 | SAN MATEO | REDWOOD CITY SUB | Storage | 0.02895 | 5/7/2014 | 5/13/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-04-10 12:47 | 0929-RD | Fast Track | Fast Track | In Service | 6/26/2014 |  |  | TULARE | DINUBA SUB | Solar PV | 0.69651 | 5/7/2014 | 5/15/2014 | Fail | 7/1/2014 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-04-25 12:35 | 0930-RD | Fast Track | Fast Track | In Service | 7/23/2014 |  |  | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Storage | 0.03564 | 5/7/2014 | 5/12/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-04-28 09:53 | 0931-RD | Fast Track | Fast Track | Withdrawn | 11/3/2014 | Withdrawn | Withdrawn | SHASTA | BURNEY SUB | Other | 3 | 5/7/2014 | 5/20/2014 | Fail Screens: B, F, I, J, K, M | 7/10/2014 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-04-23 12:46 | 0932-RD | Fast Track | Fast Track | Withdrawn | 3/18/2016 | Withdrawn | Withdrawn | KERN | COPUS SUB | Solar PV | 3 | 5/14/2014 | 6/5/2014 | Fail Screens: F, I, J, K, M | 7/29/2014 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-05-08 10:32 | 0933-RD | Fast Track | Fast Track | In Service | 7/24/2014 |  |  | FRESNO | MANCHESTER SUB | Solar PV | 0.03993 | 5/14/2014 | 6/5/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-04-24 14:48 | 0934-RD | Fast Track | Fast Track | Withdrawn | 8/18/2014 | Withdrawn | Withdrawn | SANTA CLARA | COYOTE SW STA | Other | 2 | 5/28/2014 | 6/23/2014 | Fail Screens: B, F, H, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-05-21 14:32 | 0935-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SOLANO | PEABODY SUB | Solar PV | 0.19624 | 5/28/2014 | 6/4/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-05-14 12:05 | 0936-RD | Fast Track | Detailed Study | Withdrawn | 12/1/2015 | Withdrawn | Withdrawn | YOLO | GRAND ISLAND SUB | Turbine | 1.85 | 5/28/2014 | 6/11/2014 | Fail Screens: B, F, G, I, J, K, M | 7/15/2014 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-05-09 07:35 | 0937-RD | Fast Track | Fast Track | In Service | 7/29/2014 | In Service | 9/29/2015 | ALAMEDA | NEWARK SUB | Storage | 2 | 5/28/2014 | 7/25/2014 | Fail Screens: I | 11/3/2014 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-05-09 07:58 | 0938-RD | Detailed Study | Detailed Study | In Service | 7/30/2014 | In Service | 11/6/2014 | MONTEREY | LOS COCHES SUB | Storage | 1.1907 | 5/28/2014 | N/A | N/A | N/A | N/A | Pass | 7/29/2014 | N/A | Executed | No former queue position
2014-05-10 08:38 | 0939-RD | Fast Track | Fast Track | In Service | 7/29/2014 | In Service | 8/29/2014 | NAPA | PUEBLO SUB | Storage | 0.19845 | 5/28/2014 | 7/9/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-05-10 08:57 | 0940-RD | Fast Track | Fast Track | In Service | 7/29/2014 | In Service | 8/15/2014 | SONOMA | GEYSERVILLE SUB | Storage | 0.19845 | 5/28/2014 | 7/10/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-05-10 09:14 | 0941-RD | Fast Track | Fast Track | In Service | 7/29/2014 | In Service | 10/20/2014 | SONOMA | FULTON SUB | Storage | 0.59535 | 5/28/2014 | 7/10/2014 | Fail | 9/11/2014 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-05-11 10:06 | 0942-RD | Fast Track | Fast Track | In Service | 7/24/2014 | In Service | 11/6/2014 | SONOMA | GEYSERVILLE SUB | Storage | 0.19845 | 5/28/2014 | 7/11/2014 | Fail | 9/11/2014 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-05-12 07:35 | 0943-RD | Fast Track | Fast Track | Withdrawn | 7/29/2014 | Withdrawn | Withdrawn | SONOMA | SANTA ROSA A SUB | Storage | 0.6 | 5/28/2014 | 6/16/2014 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-05-12 07:46 | 0944-RD | Fast Track | Fast Track | Withdrawn | 7/29/2014 | Withdrawn | Withdrawn | SONOMA | SANTA ROSA A SUB | Storage | 1 | 5/28/2014 | 6/16/2014 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-05-20 10:48 | 0945-RD | Fast Track | Fast Track | In Service | 7/30/2014 | In Service | 9/11/2014 | SANTA CLARA | PIERCY SUB | Storage | 0.03 | 5/28/2014 | 6/17/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-05-19 18:55 | 0946-WD | Fast Track | Independent Study | Withdrawn | 2/12/2015 | Withdrawn | Withdrawn | KERN | SMYRNA SUB | Solar PV | 2 | 6/4/2014 | 6/17/2014 | Fail Screens: 2, 10 | 7/31/2014 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-05-22 10:08 | 0947-RD | Fast Track | Fast Track | Withdrawn | 3/1/2016 | Withdrawn | Withdrawn | TEHAMA | CORNING SUB | Solar PV | 1.365 | 6/4/2014 | 6/20/2014 | Fail Screens: F, J, K, M | 8/12/2014 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-05-17 14:33 | 0948-RD | Fast Track | Fast Track | Withdrawn | 7/24/2014 | Withdrawn | Withdrawn | YUBA | OLIVEHURST SUB | Solar PV | 1.203 | 6/4/2014 | 6/12/2014 | Fail Screens: D, F, H, J, K, M | 8/1/2014 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-05-20 13:36 | 0949-RD | Fast Track | Detailed Study | In Service | 7/31/2014 | In Service | 7/7/2017 | SANTA CLARA | DIXON LANDING SUB | Engine, Fuel Cell | 13.25 | 6/4/2014 | 9/24/2014 | Fail Screens: B, I, J, K | 12/8/2014 | Fail | Pass | 7/9/2015 | N/A | Executed | No former queue position
2014-05-23 11:27 | 0950-WD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | MARIN | GREENBRAE SUB | Solar PV | 0.286 | 6/11/2014 | 7/2/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-05-22 10:25 | 0951-RD | Fast Track | Fast Track | Withdrawn | 3/1/2016 | Withdrawn | Withdrawn | BUTTE | WYANDOTTE SUB | Solar PV | 1.5 | 6/11/2014 | 6/25/2014 | Fail Screens: F, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-04-29 11:38 | 0952-WD | Independent Study | Independent Study | In Service | 10/26/2015 | 12/5/2016 | 2/16/2017 | MARIN | NOVATO SUB | Engine | 3.9328 | 6/18/2014 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 10/31/2014 | N/A | Executed | No former queue position
2014-05-02 17:32 | 0953-RD | Detailed Study | Detailed Study | Withdrawn | 7/15/2015 | Withdrawn | Withdrawn | BUTTE | WYANDOTTE SUB | Solar PV | 0.749 | 6/18/2014 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-05-02 18:03 | 0954-RD | Detailed Study | Detailed Study | Withdrawn | 7/15/2015 | Withdrawn | Withdrawn | SHASTA | RED BLUFF SUB | Solar PV | 0.749 | 6/18/2014 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-05-02 18:51 | 0955-RD | Detailed Study | Detailed Study | Withdrawn | 7/15/2015 | Withdrawn | Withdrawn | TEHAMA | RED BLUFF SUB | Solar PV | 0.499 | 6/18/2014 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-05-02 21:37 | 0956-RD | Detailed Study | Detailed Study | Withdrawn | 7/15/2015 | Withdrawn | Withdrawn | BUTTE | HONCUT SUB | Solar PV | 0.749 | 6/18/2014 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-05-20 11:41 | 0957-RD | Fast Track | Fast Track | Withdrawn | 7/23/2014 | Withdrawn | Withdrawn | SAN LUIS OBISPO | OCEANO SUB | Solar PV | 0.48775 | 2014-07-10 | 2014-07-30 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-05-20 14:12 | 0958-RD | Fast Track | Fast Track | In Service | 7/31/2014 |  |  | SAN LUIS OBISPO | MESA SUB | Solar PV | 0.4831 | 6/18/2014 | 7/8/2014 | Fail | 8/26/2014 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-05-23 13:16 | 0959-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | OAKLAND C (OAKLAND PP) SUB | Storage | 0.03 | 6/25/2014 | 7/30/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-05-30 14:57 | 0960-RD | Fast Track | Fast Track | In Service | 8/27/2014 |  |  | ALAMEDA | BERKELEY F SUB | Storage | 0.018 | 6/25/2014 | 7/14/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-06-02 12:21 | 0961-RD | Fast Track | Fast Track | In Service | 8/27/2014 |  |  | MARIN | SAN RAFAEL SUB | Storage | 0.03 | 6/25/2014 | 7/2/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-06-02 15:13 | 0962-RD | Fast Track | Fast Track | In Service | 8/27/2014 |  |  | SAN JOAQUIN | STAGG SUB | Storage | 0.03 | 6/25/2014 | 7/2/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-06-16 10:31 | 0963-WD | Fast Track | Independent Study | Withdrawn | 10/15/2015 | Withdrawn | Withdrawn | MARIN | NOVATO SUB | Solar PV | 0.03 | 6/25/2014 | 7/15/2014 | Fail Screens: 2, 4, 10 | 9/22/2014 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-06-06 16:21 | 0964-RD | Fast Track | Fast Track | In Service | 10/16/2015 | 11/13/2015 | 9/23/2015 | FRESNO | KERMAN SUB | Solar PV | 0.2 | 7/1/2014 | 7/10/2014 | Fail | 7/30/2014 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | R21 Transition to WDT SGIA
2014-06-06 16:26 | 0965-RD | Fast Track | Fast Track | Withdrawn | 10/16/2015 | Withdrawn | Withdrawn | FRESNO | SAN JOAQUIN SUB | Solar PV | 0.018 | 7/1/2014 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-05-23 10:12 | 0966-RD | Fast Track | Fast Track | Withdrawn | 9/24/2014 | Withdrawn | Withdrawn | KERN | LAMONT SUB | Solar PV | 0.001 | 7/1/2014 | 7/24/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-05-23 10:19 | 0967-RD | Fast Track | Fast Track | Withdrawn | 9/24/2014 | Withdrawn | Withdrawn | KERN | LAMONT SUB | Solar PV | 0.2 | 7/1/2014 | 7/24/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-05-23 10:20 | 0968-RD | Fast Track | Fast Track | Withdrawn | 9/24/2014 | Withdrawn | Withdrawn | KERN | LAMONT SUB | Solar PV | 0.1 | 7/1/2014 | 7/24/2014 | Fail Screens: I, J, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-06-17 14:28 | 0969-RD | Fast Track | Fast Track | In Service | 11/2/2015 | 12/15/2017 | 4/25/2019 | SONOMA | CLOVERDALE SUB | Solar PV | 1 | 7/1/2014 | 7/22/2014 | Fail Screens: 10 | 9/2/2014 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | R21 Transition to WDT SGIA
2014-06-18 12:40 | 0970-RD | Fast Track | Fast Track | Withdrawn | 8/27/2014 | Withdrawn | Withdrawn | SANTA CLARA | MONTAGUE SUB | Solar PV | 1.8492 | 7/1/2014 | 7/17/2014 | Fail | 8/14/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-06-18 13:07 | 0971-RD | Fast Track | Fast Track | In Service | 9/30/2015 |  |  | SANTA CLARA | EVERGREEN SUB | Solar PV | 2.1895 | 7/1/2014 | 7/10/2014 | Fail Screens: D, F, G, H, J, K, M | 8/6/2014 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-06-18 13:38 | 0972-RD | Fast Track | Fast Track | In Service | 8/27/2014 |  |  | SANTA CLARA | EDENVALE SUB | Solar PV | 3.1278 | 7/1/2014 | 7/21/2014 | Fail | 9/2/2014 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-06-18 13:56 | 0973-RD | Fast Track | Fast Track | Withdrawn | 8/28/2014 | Withdrawn | Withdrawn | SANTA CLARA | EDENVALE SUB | Solar PV | 1.7112 | 7/1/2014 | 7/21/2014 | Fail | 8/18/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-06-19 09:02 | 0974-RD | Fast Track | Fast Track | Withdrawn | 8/26/2014 | Withdrawn | Withdrawn | SANTA CLARA | MORGAN HILL SUB | Solar PV | 3 | 7/1/2014 | 7/22/2014 | Fail Screens: G, H, I, J, K, M | 9/2/2014 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-06-25 08:08 | 0975-RD | Fast Track | Fast Track | Withdrawn | 9/23/2014 | Withdrawn | Withdrawn | SANTA CLARA | SWIFT SUB | Solar PV | 2.7048 | 7/1/2014 | 7/10/2014 | Fail Screens: D, F, H, J, K | 8/7/2014 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-06-25 08:17 | 0976-RD | Fast Track | Fast Track | Withdrawn | 9/25/2014 | Withdrawn | Withdrawn | SANTA CLARA | SWIFT SUB | Solar PV | 2.0424 | 7/1/2014 | 7/10/2014 | Fail | 8/8/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-06-17 11:02 | 0977-RD | Fast Track | Fast Track | Withdrawn | 8/15/2014 | Withdrawn | Withdrawn | KERN | WASCO SUB | Solar PV | 0.192 | 7/9/2014 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-06-23 18:17 | 0978-RD | Fast Track | Fast Track | In Service | 9/24/2014 |  |  | ALAMEDA | DIXON LANDING SUB | Storage | 0.054 | 7/9/2014 | 7/31/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-06-13 16:35 | 0979-WD | Fast Track | Independent Study | Withdrawn | 3/31/2016 | Withdrawn | Withdrawn | EL DORADO | CLARKSVILLE SUB | Other | 3 | 7/9/2014 | 8/22/2014 | Fail Screens: 2, 5, 9, 10 | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-06-13 16:37 | 0980-WD | Fast Track | Independent Study | Withdrawn | 3/31/2016 | Withdrawn | Withdrawn | EL DORADO | CLARKSVILLE SUB | Other | 2.656 | 7/9/2014 | 8/22/2014 | Fail Screens: 2, 9, 10 | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-06-13 16:42 | 0981-WD | Fast Track | Independent Study | Withdrawn | 3/31/2016 | Withdrawn | Withdrawn | EL DORADO | CLARKSVILLE SUB | Other | 3 | 7/9/2014 | 8/22/2014 | Fail Screens: 2, 9, 10 | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-06-13 16:45 | 0982-WD | Fast Track | Fast Track | Withdrawn | 3/31/2016 | Withdrawn | Withdrawn | EL DORADO | CLARKSVILLE SUB | Other | 3 | 7/9/2014 | 8/26/2014 | Fail Screens: 2, 9, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-06-13 16:49 | 0983-WD | Fast Track | Fast Track | Withdrawn | 3/31/2016 | Withdrawn | Withdrawn | EL DORADO | CLARKSVILLE SUB | Other | 3 | 7/9/2014 | 8/26/2014 | Fail Screens: 2, 5, 9, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-06-12 07:53 | 0984-WD | Fast Track | Fast Track | Withdrawn | 3/31/2016 | Withdrawn | Withdrawn | FRESNO | ORO LOMA SUB | Solar PV | 3 | 7/16/2014 | 8/15/2014 | Fail Screens: 2, 10 | 9/29/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-06-29 17:12 | 0985-RD | Fast Track | Fast Track | Withdrawn | 8/15/2014 | Withdrawn | Withdrawn | FRESNO | HAMMONDS SUB | Solar PV | 1 | 7/16/2014 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-07-01 18:05 | 0986-WD | Fast Track | Fast Track | Withdrawn | 6/11/2015 | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV | 1.5 | 7/23/2014 | 8/12/2014 | Fail Screens: 2, 4, 5, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-07-01 18:04 | 0987-WD | Fast Track | Fast Track | Withdrawn | 6/11/2015 | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV | 1.5 | 7/23/2014 | 8/12/2014 | Fail Screens: 2, 4, 5, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-06-20 14:48 | 0988-WD | Fast Track | Fast Track | Withdrawn | 4/15/2016 | Withdrawn | Withdrawn | FRESNO | CAMDEN SUB | Solar PV | 2 | 7/30/2014 | 8/14/2014 | Fail Screens: 2, 5, 10 | 9/22/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-07-07 07:59 | 0989-RD | Fast Track | Fast Track | Withdrawn | 9/17/2014 | Withdrawn | Withdrawn | SANTA CLARA | MORGAN HILL SUB | Solar PV | 1.5 | 7/30/2014 | 8/19/2014 | Fail Screens: D, F, H, J, K | 9/23/2014 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-07-16 10:49 | 0990-RD | Fast Track | Fast Track | In Service | 9/24/2014 | In Service | 4/9/2015 | SAN MATEO | EAST GRAND SUB | Storage | 0.036 | 7/30/2014 | 8/7/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-07-16 13:49 | 0991-RD | Fast Track | Fast Track | In Service | 9/30/2014 | In Service | 7/30/2015 | SANTA CLARA | DIXON LANDING SUB | Storage | 0.054 | 7/30/2014 | 8/6/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-07-17 11:16 | 0992-WD | Fast Track | Independent Study | Withdrawn | 1/31/2015 | Withdrawn | Withdrawn | MARIN | NOVATO SUB | Solar PV | 1 | 7/30/2014 | 8/20/2014 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2012-02-01 18:03 | 0993-RD | Detailed Study | Detailed Study | In Service | 9/30/2014 |  |  | SANTA BARBARA | SANTA MARIA SUB | Engine | 2.852 | 7/30/2014 | N/A | N/A | N/A | N/A | Pass | 11/18/2014 | N/A | Executed | No former queue position
2014-07-25 08:52 | 0994-WD | Independent Study | Independent Study | Withdrawn | 6/11/2015 | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV | 1.5 | 8/13/2014 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-07-25 08:56 | 0995-WD | Independent Study | Independent Study | Withdrawn | 6/11/2015 | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV | 1.5 | 8/13/2014 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-07-21 16:22 | 0996-RD | Fast Track | Fast Track | In Service | 9/30/2015 | 8/11/2017 | 4/23/2018 | SONOMA | LAKEVILLE SUB | Solar PV | 1 | 8/13/2014 | 9/3/2014 | Fail Screens: 10 | 10/7/2014 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | R21 Transition to WDT SGIA
2014-07-30 12:09 | 0997-WD | Fast Track | Fast Track | In Service | 12/30/2014 | 10/12/2015 | 1/28/2016 | TULARE | OROSI SUB | Solar PV | 0.1 | 8/20/2014 | 8/29/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-07-30 12:16 | 0998-WD | Fast Track | Fast Track | Withdrawn | 4/15/2015 | Withdrawn | Withdrawn | MERCED | WILSON SUB | Solar PV | 0.1 | 8/20/2014 | 9/16/2014 | Fail Screens: 2, 5, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-08-05 12:32 | 0999-WD | Fast Track | Fast Track | Withdrawn | 10/30/2015 | Withdrawn | Withdrawn | SAN JOAQUIN | MANTECA SUB | Solar PV | 0.36 | 8/20/2014 | 9/9/2014 | Fail Screens: 5, 10 | 11/3/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-08-07 13:00 | 1000-RD | Fast Track | Fast Track | In Service | 10/29/2014 | In Service | 12/17/2015 | SAN MATEO | MILLBRAE SUB | Storage | 0.054 | 8/20/2014 | 9/8/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-08-16 08:30 | 1001-RD | Fast Track | Fast Track | In Service | 10/31/2014 | In Service | 11/6/2014 | MARIN | SAN RAFAEL SUB | Storage | 0.19845 | 8/27/2014 | 10/3/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-08-08 08:58 | 1002-RD | Fast Track | Fast Track | In Service | 10/30/2014 |  |  | SANTA CLARA | TRIMBLE SUB | Storage | 0.018 | 8/27/2014 | 9/12/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-08-11 15:32 | 1003-WD | Fast Track | Fast Track | Withdrawn | 1/1/2015 | Withdrawn | Withdrawn | SAN FRANCISCO | JUDAH SUB | Other | 0.048 | 8/27/2014 | 12/29/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-08-11 15:50 | 1004-WD | Fast Track | Fast Track | Withdrawn | 1/1/2015 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN E SUB | Other | 0.048 | 8/27/2014 | 11/21/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-08-11 16:07 | 1005-WD | Fast Track | Fast Track | Withdrawn | 1/1/2015 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN L SUB | Other | 0.048 | 8/27/2014 | 12/17/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-08-11 16:29 | 1006-WD | Fast Track | Fast Track | Withdrawn | 1/1/2015 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN A (POTRERO PP) SUB | Other | 0.048 | 8/27/2014 | 11/6/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-08-11 16:40 | 1007-WD | Fast Track | Fast Track | Withdrawn | 1/1/2015 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN Z (EMBARCADERO) SUB | Other | 0.048 | 8/27/2014 | 12/29/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-08-11 16:50 | 1008-WD | Fast Track | Fast Track | Withdrawn | 1/1/2015 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Other | 0.048 | 8/27/2014 | 11/6/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-08-11 17:00 | 1009-WD | Fast Track | Fast Track | Withdrawn | 1/1/2015 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN E SUB | Other | 0.048 | 8/27/2014 | 12/15/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-08-11 17:17 | 1010-WD | Fast Track | Fast Track | Withdrawn | 1/1/2015 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Other | 0.048 | 8/27/2014 | 11/6/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-08-12 05:56 | 1011-RD | Fast Track | Fast Track | Withdrawn | 10/31/2014 | Withdrawn | Withdrawn | HUMBOLDT | BLUE LAKE SUB | Other | 0.17 | 8/27/2014 | 9/16/2014 | Fail Screens: B, I, J | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-08-18 16:16 | 1012-WD | Fast Track | Independent Study | In Service | 6/11/2015 | 2/1/2016 | 12/16/2015 | KINGS | HENRIETTA SUB | Solar PV | 1.5 | 8/27/2014 | 9/15/2014 | Fail Screens: 2, 4, 10 | N/A | N/A (Independent Study) | Pass | 1/27/2015 | N/A | Executed | No former queue position
2014-08-18 16:26 | 1013-WD | Fast Track | Independent Study | Withdrawn | 6/11/2015 | Withdrawn | Withdrawn | KINGS | HENRIETTA SUB | Solar PV | 1.5 | 8/27/2014 | 9/15/2014 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-08-22 14:15 | 1014-WD | Independent Study | Independent Study | In Service | 12/1/2015 | 8/31/2017 | 12/1/2017 | KERN | MAGUNDEN SUB | Solar PV | 5.25 | 9/3/2014 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 2015-01-12 | N/A | Executed | No former queue position
2014-08-21 12:44 | 1015-RD | Fast Track | Fast Track | Withdrawn | 10/15/2015 | Withdrawn | Withdrawn | SHASTA | BURNEY SUB | Solar PV | 0.333 | 9/3/2014 | 9/23/2014 | Fail Screens: F, I, J, K, M | 11/3/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-08-25 22:38 | 1016-RD | Fast Track | Fast Track | In Service | 11/26/2014 |  |  | SANTA BARBARA | SANTA YNEZ SUB | Storage | 0.03 | 9/10/2014 | 10/14/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-08-25 22:55 | 1017-RD | Fast Track | Fast Track | In Service | 11/28/2014 | In Service | 12/4/2014 | BUTTE | BUTTE SUB | Storage | 0.03 | 9/10/2014 | 10/24/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-09-01 13:51 | 1018-WD | Fast Track | Fast Track | Withdrawn | 1/15/2015 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN G SUB | Other | 0.2 | 9/17/2014 | 3/2/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-01 14:01 | 1019-WD | Fast Track | Fast Track | Withdrawn | 1/2/2015 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Other | 0.018 | 9/17/2014 | 2016-04-06 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-01 16:32 | 1020-WD | Fast Track | Fast Track | Withdrawn | 1/2/2015 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Other | 0.001 | 9/17/2014 | 3/20/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-01 16:42 | 1021-WD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN F (MARINA) SUB | Other | 0.2 | 9/17/2014 | 3/30/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-01 16:49 | 1022-WD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN F (MARINA) SUB | Other | 1.85 | 9/17/2014 | 3/30/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-02 08:11 | 1023-WD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Other | 1.85 | 9/17/2014 | 3/20/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-02 08:21 | 1024-WD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Other | 0.55 | 9/17/2014 | 12/22/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-02 09:12 | 1025-WD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Other | 0.048 | 9/17/2014 | 3/20/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-02 10:41 | 1026-WD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN F (MARINA) SUB | Other | 0.048 | 9/17/2014 | 4/23/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-02 10:52 | 1027-WD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN F (MARINA) SUB | Other | 0.048 | 9/17/2014 | 11/21/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-02 10:58 | 1028-WD | Fast Track | Fast Track | Withdrawn | 1/15/2015 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Other | 0.048 | 9/17/2014 | 12/22/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-02 11:04 | 1029-WD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Other | 0.048 | 9/17/2014 | 3/31/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-02 11:23 | 1030-WD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN J SUB | Other | 0.048 | 9/17/2014 | 3/30/2015 | Fail Screens: 7, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-02 11:29 | 1031-WD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN F (MARINA) SUB | Other | 0.048 | 9/17/2014 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-02 12:17 | 1032-WD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN G SUB | Other | 0.048 | 9/17/2014 | 4/23/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-02 12:26 | 1033-WD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN H (MARTIN) SUB | Other | 0.048 | 9/17/2014 | 12/23/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-02 12:32 | 1034-WD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN E SUB | Other | 0.048 | 9/17/2014 | 12/23/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-02 12:36 | 1035-WD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN J SUB | Other | 0.048 | 9/17/2014 | 12/23/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-02 12:42 | 1036-WD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN G SUB | Other | 0.048 | 9/17/2014 | 12/22/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-03 17:50 | 1037-WD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN F (MARINA) SUB | Other | 0.048 | 9/17/2014 | 12/23/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-03 17:56 | 1038-WD | Fast Track | Fast Track | Withdrawn | 1/15/2015 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Other | 0.048 | 9/17/2014 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-03 18:10 | 1039-WD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN G SUB | Other | 0.048 | 9/17/2014 | 4/23/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-03 18:15 | 1040-WD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Other | 0.048 | 9/17/2014 | 12/22/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-03 18:21 | 1041-WD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Other | 0.048 | 9/17/2014 | 3/13/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-03 19:59 | 1042-WD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Other | 0.048 | 9/17/2014 | 8/5/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-08-05 10:51 | 1043-WD | Independent Study | Independent Study | Withdrawn | 3/25/2016 | Withdrawn | Withdrawn | KERN | LAKEVIEW SUB | Solar PV | 10 | 9/17/2014 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-05 12:15 | 1044-WD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Other | 0.048 | 9/17/2014 | 12/23/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-05 12:21 | 1045-WD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN N SUB | Other | 0.048 | 9/17/2014 | 7/2/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-05 12:28 | 1046-WD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SAN FRANCISCO | SIXTH AVE SUB | Other | 0.048 | 9/17/2014 | 4/23/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-05 13:16 | 1047-WD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Other | 0.048 | 9/17/2014 | 12/23/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-05 13:27 | 1048-WD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Other | 0.048 | 9/17/2014 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-05 14:11 | 1049-WD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SAN FRANCISCO | CASTRO SUB | Other | 0.048 | 9/17/2014 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-08-25 08:50 | 1050-RD | Fast Track | Fast Track | In Service | 11/27/2014 |  |  | CONTRA COSTA | ROSSMOOR SUB | Storage | 0.036 | 9/17/2014 | 9/29/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-09-01 08:30 | 1051-RD | Fast Track | Fast Track | In Service | 11/28/2014 |  |  | SONOMA | SANTA ROSA A SUB | Storage | 0.99225 | 9/17/2014 | 11/13/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-09-03 07:28 | 1052-RD | Fast Track | Fast Track | In Service | 11/27/2014 |  |  | SONOMA | SANTA ROSA A SUB | Storage | 0.59535 | 9/17/2014 | 11/13/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-09-03 08:23 | 1053-RD | Fast Track | Fast Track | In Service | 11/28/2014 | In Service | 1/13/2015 | SANTA CLARA | LLAGAS SUB | Storage | 0.19845 | 9/17/2014 | 10/21/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-09-14 09:33 | 1054-RD | Fast Track | Fast Track | In Service | 12/30/2014 |  |  | SONOMA | MOLINO SUB | Storage | 0.19845 | 9/24/2014 | 10/23/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-09-14 10:48 | 1055-RD | Fast Track | Fast Track | In Service | 12/30/2014 |  |  | NAPA | HIGHWAY SUB | Storage | 0.1 | 9/24/2014 | 10/23/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-09-14 10:27 | 1056-RD | Fast Track | Fast Track | In Service | 12/31/2014 |  |  | NAPA | HIGHWAY SUB | Storage | 0.1 | 9/24/2014 | 10/23/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-09-10 00:51 | 1057-WD | Fast Track | Fast Track | Withdrawn | 7/31/2015 | Withdrawn | Withdrawn | CONTRA COSTA | POINT PINOLE SUB | Solar PV | 1 | 9/24/2014 | 10/10/2014 | Fail Screens: 2, 10 | 1/27/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-01 16:55 | 1058-WD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Other | 0.048 | 9/24/2014 | 4/23/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-15 14:21 | 1059-RD | Fast Track | Fast Track | In Service | 12/30/2014 |  |  | SANTA CLARA | SAN JOSE B SUB | Solar PV | 1.6361 | 10/1/2014 | 10/20/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-09-15 14:37 | 1060-RD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SANTA CLARA | ALMADEN SUB | Solar PV | 1.7112 | 10/1/2014 | 10/14/2014 | Fail | 11/13/2014 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-08-26 13:43 | 1061-RD | Fast Track | Fast Track | Withdrawn | 11/26/2014 | Withdrawn | Withdrawn | PLUMAS | BIG MEADOWS SUB | Solar PV | 0.12101 | 10/1/2014 | 10/27/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-18 12:18 | 1062-RD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | SANTA CLARA | SWIFT SUB | Solar PV | 2.7767 | 10/1/2014 | 10/13/2014 | Fail Screens: D, F, J, K, M | 11/13/2014 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-09-25 17:05 | 1063-RD | Fast Track | Fast Track | In Service | 12/30/2014 |  |  | SAN FRANCISCO | SAN FRAN P(HUNTERS POINT) SUB | Solar PV | 0.07181 | 10/1/2014 | 10/21/2014 | Fail | 12/18/2014 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-09-26 16:40 | 1064-RD | Fast Track | Fast Track | In Service | 12/24/2014 |  |  | SAN FRANCISCO | SAN FRAN P(HUNTERS POINT) SUB | Solar PV | 0.07446 | 10/1/2014 | 11/13/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-09-23 14:52 | 1065-WD | Fast Track | Fast Track | In Service | 4/15/2015 | 11/16/2015 | 10/22/2015 | MERCED | WILSON SUB | Solar PV | 0.00924 | 10/8/2014 | 10/23/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-10-07 15:42 | 1066-RD | Fast Track | Fast Track | Withdrawn | 1/28/2015 | Withdrawn | Withdrawn | BUTTE | BUTTE SUB | Storage | 0.54 | 10/22/2014 | 11/20/2014 | Fail Screens: B, D, F, H, J, K | 1/21/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-10-07 16:07 | 1067-RD | Fast Track | Fast Track | In Service | 12/21/2015 | 10/12/2017 | 4/20/2018 | SONOMA | PETALUMA C SUB | Solar PV | 1 | 10/22/2014 | 11/12/2014 | Fail Screens: 10 | 1/9/2015 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | R21 Transition to WDT SGIA
2014-10-07 16:13 | 1068-RD | Fast Track | Fast Track | Withdrawn | 12/21/2015 | Withdrawn | Withdrawn | SONOMA | PETALUMA C SUB | Solar PV | 0.999 | 10/22/2014 | 11/13/2014 | Fail Screens: G, I, J, K, M | 1/9/2015 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-08-29 15:11 | 1069-WD | Fast Track | Fast Track | Withdrawn | 8/2/2015 | Withdrawn | Withdrawn | FRESNO | ORO LOMA SUB | Solar PV | 2 | 10/22/2014 | 11/12/2014 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-10-10 14:05 | 1070-RD | Fast Track | Fast Track | In Service | 12/31/2014 |  |  | SANTA CLARA | MORGAN HILL SUB | Solar PV | 0.94127 | 10/22/2014 | 11/5/2014 | Fail Screens: D, H, J, K | 12/10/2014 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-10-11 08:55 | 1071-RD | Fast Track | Fast Track | Withdrawn | 6/1/2016 | Withdrawn | Withdrawn | CALAVERAS | WEST POINT PH | Other | 3 | 10/22/2014 | 11/13/2014 | Fail Screens: B, F, G, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-10-12 16:53 | 1072-RD | Fast Track | Fast Track | Withdrawn | 12/31/2014 | Withdrawn | Withdrawn | COLUSA | CORTINA SUB | Steam Turbine | 5 | 10/22/2014 | 11/13/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-10-14 06:57 | 1073-RD | Fast Track | Fast Track | Withdrawn | 1/28/2015 | Withdrawn | Withdrawn | MERCED | SANTA NELLA SUB | Steam Turbine | 2 | 10/29/2014 | 11/13/2014 | Fail | 12/22/2014 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-10-14 14:30 | 1074-WD | Fast Track | Fast Track | In Service | 2/2/2015 | 8/21/2015 | 8/15/2016 | MARIN | GREENBRAE SUB | Solar PV | 0.2335 | 10/29/2014 | 11/14/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-10-26 10:20 | 1075-RD | Fast Track | Fast Track | In Service | 1/30/2015 | In Service | 7/16/2015 | ALAMEDA | MT EDEN SUB | Storage | 2.3814 | 11/5/2014 | 1/13/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-11-08 12:56 | 1076-RD | Fast Track | Fast Track | In Service | 1/28/2015 |  |  | MARIN | NOVATO SUB | Solar PV | 0.98533 | 11/5/2014 | 12/12/2014 | Fail Screens: D, H, J, K, M | 1/13/2015 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-10-29 08:57 | 1077-RD | Fast Track | Fast Track | Withdrawn | 7/1/2016 | Withdrawn | Withdrawn | MADERA | SAN JOAQUIN #3 PH | Other | 2 | 11/12/2014 | 12/3/2014 | Fail Screens: B, F, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-10-29 10:17 | 1078-WD | Fast Track | Fast Track | Withdrawn | 3/25/2016 | Withdrawn | Withdrawn | LAKE | CLEAR LAKE SUB | Solar PV | 2.4 | 11/12/2014 | 12/2/2014 | Fail Screens: 2, 10 | 2/3/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-10-26 15:15 | 1079-WD | Fast Track | Fast Track | Withdrawn | 1/29/2016 | Withdrawn | Withdrawn | SAN JOAQUIN | FRENCH CAMP SUB | Solar PV | 3 | 11/12/2014 | 11/21/2014 | Fail Screens: 2, 5, 10 | 12/31/2014 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-10-29 18:29 | 1080-WD | Fast Track | Fast Track | Withdrawn | 12/30/2015 | Withdrawn | Withdrawn | CONTRA COSTA | KIRKER SUB | Other | 1.5 | 11/12/2014 | 12/2/2014 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-10-31 16:54 | 1081-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MARIN | SAN RAFAEL SUB | Storage | 0.018 | 11/12/2014 | 11/17/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-10-20 14:11 | 1082-RD | Fast Track | Fast Track | In Service | 1/30/2015 |  |  | SAN JOAQUIN | ROUGH & READY SUB | Turbine | 5 | 11/19/2014 | 12/10/2014 | Fail Screens: B, D, F, I, J, K | 2/6/2015 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-10-31 16:21 | 1083-RD | Fast Track | Fast Track | In Service | 1/30/2015 | In Service | 5/8/2015 | SANTA CLARA | BRITTON SUB | Storage | 0.054 | 11/19/2014 | 11/26/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-11-04 09:03 | 1084-WD | Fast Track | Fast Track | Withdrawn | 2/12/2016 | Withdrawn | Withdrawn | SAN JOAQUIN | FRENCH CAMP SUB | Solar PV | 2 | 11/19/2014 | 12/12/2014 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-11-14 11:29 | 1085-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | WHISMAN SUB | Storage | 0.2 | 11/25/2014 | 12/16/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-11-14 12:03 | 1086-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | NAPA | TULUCAY SUB | Storage | 0.1995 | 11/25/2014 | 12/18/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-11-03 11:46 | 1087-RD | Fast Track | Fast Track | In Service | 1/30/2015 |  |  | FRESNO | WOODWARD SUB | Engine | 2.362 | 11/25/2014 | 12/16/2014 | Fail | 1/29/2015 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-11-18 15:44 | 1088-RD | Fast Track | Fast Track | In Service | 1/30/2015 |  |  | SAN MATEO | EAST GRAND SUB | Storage | 0.018 | 12/3/2014 | 12/4/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-11-19 16:10 | 1089-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SONOMA | FULTON SUB | Storage | 0.8 | 12/3/2014 | 12/15/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-11-19 16:49 | 1090-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SONOMA | FULTON SUB | Storage | 0.2 | 12/3/2014 | 12/15/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-11-25 16:33 | 1091-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | FRESNO | WEST FRESNO SUB | Storage | 0.018 | 12/10/2014 | 12/29/2014 | Fail | 1/23/2015 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-02 14:40 | 1092-RD | Fast Track | Fast Track | Withdrawn | 2/27/2015 | Withdrawn | Withdrawn | BUTTE | BUTTE SUB | Solar PV | 0.001 | 12/10/2014 | 1/30/2015 | Fail Screens: I, J, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-12-01 07:17 | 1093-RD | Fast Track | Fast Track | In Service | 2/27/2015 |  |  | SOLANO | CORDELIA SUB | Storage | 0.2 | 12/10/2014 | 12/10/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-01 07:28 | 1094-RD | Fast Track | Fast Track | In Service | 2/27/2015 |  |  | SANTA CLARA | EDENVALE SUB | Storage | 1.85 | 12/10/2014 | 12/18/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-01 07:38 | 1095-RD | Fast Track | Fast Track | In Service | 2/27/2015 |  |  | SANTA CLARA | MORGAN HILL SUB | Storage | 1.85 | 12/10/2014 | 12/15/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-01 07:48 | 1096-RD | Fast Track | Fast Track | In Service | 2/27/2015 |  |  | SANTA CLARA | NORTECH SUB | Storage | 0.55 | 12/10/2014 | 12/18/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-01 14:34 | 1097-RD | Fast Track | Fast Track | In Service | 2/27/2015 |  |  | SONOMA | SANTA ROSA A SUB | Storage | 0.018 | 12/10/2014 | 12/12/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-01 14:51 | 1098-RD | Fast Track | Fast Track | In Service | 2/27/2015 |  |  | SOLANO | VACA DIXON SUB | Storage | 0.036 | 12/10/2014 | 12/12/2014 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-10 15:50 | 1099-RD | Fast Track | Fast Track | In Service | 2/27/2015 |  |  | SAN FRANCISCO | SAN FRAN A (POTRERO PP) SUB | Solar PV | 0.04009 | 12/18/2014 | 1/9/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-03 15:32 | 1100-RD | Fast Track | Fast Track | Withdrawn | 6/1/2016 | Withdrawn | Withdrawn | FRESNO | MCMULLIN SUB | Solar PV | 1.5 | 12/18/2014 | 1/12/2015 | Fail Screens: I, J, K, M | 2015-04-30 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-11-10 14:40 | 1101-RD | Fast Track | Fast Track | In Service | 1/30/2015 |  |  | SUTTER | PEASE SUB | Solar PV | 0.60376 | 12/17/2014 | 1/9/2015 | Fail | 3/10/2015 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-11 15:03 | 1102-RD | Fast Track | Fast Track | In Service | 2/27/2015 |  |  | SANTA CLARA | MCKEE SUB | Solar PV | 0.94127 | 12/17/2014 | 1/13/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-02 07:00 | 1103-RD | Fast Track | Fast Track | In Service | 2/27/2015 |  |  | CONTRA COSTA | MEADOW LANE SUB | Storage | 0.018 | 12/23/2014 | 1/8/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-02 07:13 | 1104-RD | Fast Track | Fast Track | In Service | 2/27/2015 |  |  | ALAMEDA | NEWARK SUB | Storage | 0.018 | 12/23/2014 | 1/8/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-02 07:43 | 1105-RD | Fast Track | Fast Track | In Service | 2/27/2015 |  |  | CONTRA COSTA | SAN RAMON RESEARCH CTR | Storage | 0.018 | 12/23/2014 | 1/8/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-02 08:08 | 1106-RD | Fast Track | Fast Track | In Service | 2/27/2015 |  |  | ALAMEDA | OAKLAND D SUB | Storage | 0.018 | 12/23/2014 | 1/5/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-02 08:31 | 1107-RD | Fast Track | Fast Track | In Service | 2/27/2015 | In Service | 5/7/2015 | CONTRA COSTA | SAN PABLO SUB | Storage | 0.018 | 12/23/2014 | 1/5/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-02 08:43 | 1108-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | EDENVALE SUB | Storage | 0.018 | 12/23/2014 | 1/7/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-02 09:22 | 1109-RD | Fast Track | Fast Track | In Service | 2/27/2015 |  |  | SAN JOAQUIN | LAMMERS SUB | Storage | 0.018 | 12/23/2014 | 1/5/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-09 18:32 | 1110-RD | Fast Track | Fast Track | In Service | 2/27/2015 |  |  | KERN | WESTPARK SUB | Storage | 0.018 | 12/23/2014 | 1/9/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-10-31 15:40 | 1111-WD | Independent Study | Independent Study | In Service | 4/29/2016 | 12/15/2017 | 12/6/2017 | KERN | OLD RIVER SUB | Engine | 1 | 12/23/2014 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 11/20/2015 | N/A | Executed | No former queue position
2014-11-01 12:02 | 1112-WD | Independent Study | Independent Study | In Service | 4/29/2016 | 12/15/2017 | 1/4/2018 | KERN | GANSO SUB | Engine | 1 | 12/23/2014 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 11/20/2015 | N/A | Executed | No former queue position
2014-12-10 14:13 | 1113-RD | Fast Track | Fast Track | In Service | 2/27/2015 | In Service | 5/12/2015 | KERN | MAGUNDEN SUB | Storage | 0.019 | 12/31/2014 | 1/28/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-15 17:20 | 1114-RD | Fast Track | Fast Track | In Service | 2/27/2015 |  |  | SAN MATEO | BAY MEADOWS SUB | Storage | 0.018 | 12/31/2014 | 1/20/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-16 18:57 | 1115-WD | Fast Track | Fast Track | Withdrawn | 6/15/2015 | Withdrawn | Withdrawn | MARIN | STAFFORD SUB | Solar PV | 0.45 | 1/7/2015 | 1/26/2015 | Fail Screens: 2, 4, 10 | 3/4/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-12-19 12:02 | 1116-RD | Fast Track | Fast Track | In Service | 2/27/2015 |  |  | SAN JOAQUIN | STAGG SUB | Storage | 0.036 | 1/7/2015 | 1/15/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-19 13:09 | 1117-RD | Fast Track | Fast Track | In Service | 2/27/2015 |  |  | ALAMEDA | CAYETANO SUB | Storage | 0.036 | 1/7/2015 | 1/16/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-01-05 10:11 | 1118-RD | Fast Track | Fast Track | Withdrawn | 3/31/2015 | Withdrawn | Withdrawn | KERN | POSO MTN SUB | Solar PV | 5 | 1/14/2015 | 1/28/2015 | Fail Screens: F, J, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-01-05 11:18 | 1119-RD | Fast Track | Fast Track | Withdrawn | 3/31/2015 | Withdrawn | Withdrawn | KERN | BAKERSFIELD SUB | Solar PV | 3 | 1/14/2015 | 1/28/2015 | Fail Screens: F, G, J, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-12-10 14:24 | 1120-RD | Fast Track | Detailed Study | In Service | 2/27/2015 |  |  | TEHAMA | CORNING SUB | Solar PV | 0.30316 | 1/14/2015 | 1/30/2015 | Fail | 3/17/2015 | Fail | Pass | 7/20/2015 | N/A | Executed | No former queue position
2015-01-09 16:57 | 1121-WD | Fast Track | Fast Track | Withdrawn | 6/1/2016 | Withdrawn | Withdrawn | EL DORADO | SHINGLE SPRINGS SUB | Other | 4 | 1/21/2015 | 2/12/2015 | Fail Screens: 2, 6, 9, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-12-10 17:39 | 1122-WD | Fast Track | Fast Track | In Service | 7/1/2016 | 11/30/2017 | 11/20/2017 | CONTRA COSTA | RICHMOND R SUB | Solar PV | 2 | 1/21/2015 | 2/5/2015 | Fail Screens: 2, 10 | 12/06/2016 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-24 11:47 | 1123-RD | Fast Track | Fast Track | In Service | 3/31/2015 |  |  | SAN MATEO | BELMONT SUB | Storage | 0.036 | 1/21/2015 | 2/17/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-29 12:26 | 1124-RD | Fast Track | Fast Track | Withdrawn | 3/31/2015 | Withdrawn | Withdrawn | SAN LUIS OBISPO | OCEANO SUB | Storage | 0.018 | 1/21/2015 | 2/26/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-12-29 13:49 | 1125-RD | Fast Track | Fast Track | Withdrawn | 3/31/2015 | Withdrawn | Withdrawn | SAN LUIS OBISPO | TEMPLETON SUB | Storage | 0.018 | 1/21/2015 | 2/25/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-12-29 14:23 | 1126-RD | Fast Track | Fast Track | Withdrawn | 3/31/2015 | Withdrawn | Withdrawn | ALAMEDA | OAKLAND C (OAKLAND PP) SUB | Storage | 0.018 | 1/21/2015 | 2/18/2015 | Fail Screens: D, J | 4/27/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2014-12-29 15:04 | 1127-RD | Fast Track | Fast Track | In Service | 3/31/2015 |  |  | SANTA CLARA | MOUNTAIN VIEW SUB | Storage | 0.018 | 1/21/2015 | 2/4/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-29 15:18 | 1128-RD | Fast Track | Fast Track | In Service | 3/31/2015 |  |  | ALAMEDA | NORTH DUBLIN SUB | Storage | 0.018 | 1/21/2015 | 2/4/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-29 15:34 | 1129-RD | Fast Track | Fast Track | In Service | 3/30/2015 |  |  | SONOMA | MONROE SUB | Storage | 0.018 | 1/21/2015 | 1/21/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-30 14:48 | 1130-RD | Fast Track | Fast Track | In Service | 3/31/2015 |  |  | SANTA CLARA | MORGAN HILL SUB | Storage | 0.054 | 1/21/2015 | 1/26/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-30 15:43 | 1131-RD | Fast Track | Fast Track | In Service | 3/31/2015 |  |  | SANTA CLARA | MOUNTAIN VIEW SUB | Storage | 0.018 | 1/21/2015 | 2/9/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-30 16:19 | 1132-RD | Fast Track | Fast Track | In Service | 3/31/2015 |  |  | ALAMEDA | NEWARK SUB | Storage | 0.018 | 1/21/2015 | 1/26/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-30 16:44 | 1133-RD | Fast Track | Fast Track | In Service | 3/31/2015 |  |  | ALAMEDA | NEWARK SUB | Storage | 0.018 | 1/21/2015 | 1/21/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2014-12-30 17:07 | 1134-RD | Fast Track | Fast Track | In Service | 3/31/2015 |  |  | SANTA CLARA | MONTAGUE SUB | Storage | 0.018 | 1/21/2015 | 1/21/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-01-05 11:55 | 1135-RD | Fast Track | Fast Track | In Service | 3/31/2015 |  |  | FRESNO | PINEDALE SUB | Storage | 0.018 | 1/28/2015 | 2/6/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-01-06 09:40 | 1136-RD | Fast Track | Fast Track | In Service | 3/31/2015 |  |  | SANTA CLARA | MILPITAS SUB | Storage | 0.018 | 1/28/2015 | 2/8/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-01-09 11:25 | 1137-RD | Fast Track | Fast Track | In Service | 3/31/2015 |  |  | FRESNO | FIGARDEN SUB | Storage | 0.018 | 1/28/2015 | 2/9/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-01-18 15:39 | 1138-WD | Fast Track | Fast Track | Withdrawn | 8/1/2015 | Withdrawn | Withdrawn | GLENN | HAMILTON A SUB | Solar PV | 1 | 1/28/2015 | 2/19/2015 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-01-23 11:59 | 1139-WD | Independent Study | Independent Study | Withdrawn | 7/24/2015 | Withdrawn | Withdrawn | KINGS | HENRIETTA SUB | Solar PV | 1.5 | 2/4/2015 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-01-13 15:46 | 1140-RD | Fast Track | Fast Track | In Service | 3/31/2015 |  |  | COLUSA | COLUSA PP | Engine | 1.69 | 2/4/2015 | 2/25/2015 | Fail | 4/15/2015 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-01-21 12:32 | 1141-RD | Fast Track | Fast Track | Withdrawn | 3/31/2015 | Withdrawn | Withdrawn | SONOMA | SONOMA A SUB | Solar PV | 0.99048 | 2/4/2015 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-01-23 09:51 | 1142-RD | Detailed Study | Detailed Study | Withdrawn | 5/1/2017 | Withdrawn | Withdrawn | EL DORADO | SHINGLE SPRINGS SUB | Other | 4 | 2/4/2015 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-01-23 10:59 | 1143-RD | Fast Track | Fast Track | Withdrawn | 5/1/2017 | Withdrawn | Withdrawn | EL DORADO | SHINGLE SPRINGS SUB | Other | 3 | 2/4/2015 | 2/26/2015 | Fail Screens: B, F, H, I, J, K, L | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-01-23 12:05 | 1144-RD | Fast Track | Fast Track | Withdrawn | 5/1/2017 | Withdrawn | Withdrawn | EL DORADO | SHINGLE SPRINGS SUB | Other | 3 | 2/4/2015 | 2/26/2015 | Fail Screens: B, H, I, J, K, L | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-01-23 12:13 | 1145-RD | Fast Track | Fast Track | Withdrawn | 5/1/2017 | Withdrawn | Withdrawn | EL DORADO | SHINGLE SPRINGS SUB | Other | 3 | 2/4/2015 | 2/26/2015 | Fail Screens: B, H, I, J, K, L | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-01-12 10:18 | 1146-RD | Detailed Study | Detailed Study | Withdrawn | 3/31/2015 | Withdrawn | Withdrawn | SAN MATEO | EAST GRAND SUB | Turbine | 7.2 | 2/11/2015 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-01-21 09:28 | 1147-RD | Fast Track | Fast Track | In Service | 3/31/2015 |  |  | SAN JOAQUIN | VIERRA SUB | Solar PV | 0.34278 | 2/11/2015 | 3/3/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-01-26 14:51 | 1148-RD | Detailed Study | Detailed Study | Withdrawn | 6/1/2016 | Withdrawn | Withdrawn | CALAVERAS | WEST POINT PH | Biomass | 3 | 2/11/2015 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-01-23 11:32 | 1149-WD | Fast Track | Fast Track | Withdrawn | 8/7/2015 | Withdrawn | Withdrawn | SONOMA | BASALT SUB | Solar PV | 2 | 2/11/2015 | 3/4/2015 | Fail Screens: 2, 4, 10 | 5/11/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-01-23 11:38 | 1150-WD | Fast Track | Fast Track | Withdrawn | 8/7/2015 | Withdrawn | Withdrawn | SONOMA | SONOMA A SUB | Solar PV | 2 | 2/11/2015 | 3/4/2015 | Fail Screens: 2, 4, 10 | 5/11/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-01-26 14:43 | 1151-RD | Detailed Study | Detailed Study | Withdrawn | 7/1/2016 | Withdrawn | Withdrawn | MADERA | SAN JOAQUIN #3 PH | Biomass | 2 | 2/11/2015 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-01-29 14:26 | 1152-RD | Fast Track | Fast Track | Withdrawn | 12/30/2016 | Withdrawn | Withdrawn | TEHAMA | TYLER SUB | Solar PV | 1 | 2/18/2015 | 3/9/2015 | Fail Screens: F, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-02-04 15:14 | 1153-RD | Fast Track | Fast Track | Active | 4/30/2015 |  |  | NAPA | PUEBLO SUB | Micro Turbine | 0.13 | 2/18/2015 | 3/9/2015 | Fail Screens: H, J, M | 4/16/2015 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-01-15 16:25 | 1154-RD | Fast Track | Fast Track | In Service | 3/31/2015 |  |  | KERN | WESTPARK SUB | Storage | 0.018 | 2/18/2015 | 3/10/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-01-21 17:47 | 1155-RD | Fast Track | Fast Track | In Service | 3/31/2015 |  |  | SACRAMENTO | WEST SACRAMENTO SUB | Storage | 0.036 | 2/18/2015 | 3/17/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-01-30 13:09 | 1156-WD | Fast Track | Fast Track | Withdrawn | 12/31/2018 | Withdrawn | Withdrawn | EL DORADO | SHINGLE SPRINGS SUB | Other | 4 | 2/25/2015 | 3/17/2015 | Fail Screens: 2, 4, 9, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-01-23 17:23 | 1157-WD | Independent Study | Independent Study | In Service | 6/1/2016 | 11/30/2017 | 11/15/2017 | CONTRA COSTA | RICHMOND R SUB | Solar PV | 8.5 | 2/25/2015 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 7/10/2015 | 11/13/2015 | Executed | No former queue position
2015-02-10 09:14 | 1158-WD | Fast Track | Fast Track | Withdrawn | 7/31/2015 | Withdrawn | Withdrawn | SONOMA | SONOMA A SUB | Solar PV | 0.1 | 3/4/2015 | 3/23/2015 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-02-12 15:34 | 1159-RD | Fast Track | Fast Track | In Service | 4/30/2015 |  |  | MARIN | LAS GALLINAS A SUB | Storage | 0.03 | 3/4/2015 | 3/26/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-02-17 12:25 | 1160-RD | Fast Track | Fast Track | Withdrawn | 4/11/2016 | Withdrawn | Withdrawn | KINGS | GUERNSEY SUB | Solar PV | 3 | 3/4/2015 | 3/23/2015 | Fail Screens: F, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-01-23 11:27 | 1161-WD | Independent Study | Independent Study | Withdrawn | 8/3/2015 | Withdrawn | Withdrawn | SONOMA | FULTON SUB | Solar PV | 7 | 3/4/2015 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-02-12 10:15 | 1162-WD | Independent Study | Independent Study | Withdrawn | 4/1/2019 | Withdrawn | Withdrawn | MADERA | WEST FRESNO SUB | Other | 15.3 | 3/11/2015 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-02-12 17:04 | 1163-RD | Fast Track | Fast Track | In Service | 4/30/2015 |  |  | SANTA CLARA | MONTAGUE SUB | Storage | 0.018 | 3/11/2015 | 3/26/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-02-27 16:12 | 1164-RD | Fast Track | Fast Track | Withdrawn | 5/28/2015 | Withdrawn | Withdrawn | KERN | POSO MTN SUB | Solar PV | 8 | 3/11/2015 | 3/30/2015 | Fail | 5/15/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-03-06 15:45 | 1165-RD | Fast Track | Fast Track | In Service | 5/27/2015 |  |  | NEVADA | BRUNSWICK SUB | Solar PV | 0.621 | 3/18/2015 | 4/8/2015 | Fail | 5/26/2015 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-03-13 13:41 | 1166-RD | Fast Track | Fast Track | Withdrawn | 5/28/2015 | Withdrawn | Withdrawn | SAN JOAQUIN | MOSHER SUB | Solar PV | 0.001 | 3/18/2015 | 3/25/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-03-05 09:14 | 1167-WD | Independent Study | Independent Study | In Service | 1/6/2017 | 12/14/2018 | 8/13/2020 | EL DORADO | APPLE HILL SUB | Hydro | 2.6802 | 3/18/2015 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 8/5/2015 | 12/30/2015 | Executed | No former queue position
2015-03-05 12:13 | 1168-WD | Fast Track | Fast Track | Withdrawn | 3/31/2016 | Withdrawn | Withdrawn | TULARE | OROSI SUB | Solar PV | 1.4 | 3/25/2015 | 4/2/2015 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-03-05 12:21 | 1169-WD | Fast Track | Fast Track | Withdrawn | 3/31/2016 | Withdrawn | Withdrawn | MERCED | WILSON SUB | Solar PV | 1.49 | 3/25/2015 | 4/7/2015 | Fail Screens: 2, 4, 5, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-03-09 14:32 | 1170-RD | Fast Track | Fast Track | In Service | 5/21/2015 |  |  | YOLO | MADISON SUB | Solar PV | 0.0309 | 3/25/2015 | 3/26/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-03-06 12:46 | 1171-RD | Fast Track | Fast Track | Withdrawn | 11/27/2015 | Withdrawn | Withdrawn | TEHAMA | RED BLUFF SUB | Solar PV,Storage | 0.95 | 3/25/2015 | 5/22/2015 | Fail | 9/1/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | R21 Transition to WDT SGIA
2015-02-06 14:58 | 1172-RD | Fast Track | Fast Track | Withdrawn | 4/30/2015 | Withdrawn | Withdrawn | SANTA CLARA | TRIMBLE SUB | Storage | 0.018 | 4/1/2015 | 4/10/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-02-06 16:07 | 1173-RD | Fast Track | Fast Track | Withdrawn | 4/30/2015 | Withdrawn | Withdrawn | SANTA CLARA | TRIMBLE SUB | Storage | 0.036 | 4/1/2015 | 4/10/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-02-16 11:47 | 1174-WD | Fast Track | Fast Track | Withdrawn | 12/31/2017 | Withdrawn | Withdrawn | SANTA CLARA | MORGAN HILL SUB | Other | 3 | 4/1/2015 | 4/15/2015 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-03-17 11:03 | 1175-WD | Cluster | Cluster | Withdrawn | 4/1/2019 | Withdrawn | Withdrawn | MADERA | WEST FRESNO SUB | Other | 15.3 | 4/1/2015 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-03-25 10:20 | 1176-RD | Fast Track | Fast Track | In Service | 6/30/2015 |  |  | NAPA | TULUCAY SUB | Storage | 0.99225 | 4/1/2015 | 4/28/2015 | Fail | 6/8/2015 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-03-30 11:19 | 1177-RD | Fast Track | Fast Track | Withdrawn | 6/30/2015 | Withdrawn | Withdrawn | SAN JOAQUIN | LODI SUB | Solar PV | 0.00128 | 4/8/2015 | 4/9/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-03-30 15:39 | 1178-RD | Fast Track | Fast Track | Withdrawn | 6/30/2015 | Withdrawn | Withdrawn | SANTA CLARA | LAWRENCE SUB | Solar PV | 0.00129 | 4/8/2015 | 4/15/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-03-30 16:45 | 1179-RD | Fast Track | Fast Track | Withdrawn | 6/30/2015 | Withdrawn | Withdrawn | CONTRA COSTA | CLAYTON SUB | Solar PV | 0.00151 | 4/8/2015 | 4/15/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-03-30 17:09 | 1180-RD | Fast Track | Fast Track | Withdrawn | 6/30/2015 | Withdrawn | Withdrawn | SANTA CLARA | BELLE HAVEN SUB | Solar PV | 0.001 | 4/8/2015 | 4/15/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-03-30 17:43 | 1181-RD | Fast Track | Fast Track | Withdrawn | 6/30/2015 | Withdrawn | Withdrawn | STANISLAUS | RIVERBANK SUB | Solar PV | 0.00213 | 4/8/2015 | 4/15/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-03-19 17:01 | 1182-WD | Fast Track | Fast Track | Withdrawn | 6/30/2016 | Withdrawn | Withdrawn | MADERA | DAIRYLAND SUB | Solar PV | 1.5 | 4/8/2015 | 4/29/2015 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-03-23 12:42 | 1183-RD | Fast Track | Fast Track | In Service | 5/28/2015 |  |  | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Engine | 9 | 4/8/2015 | 4/16/2015 | Fail Screens: D, E, F, J, K | 6/30/2015 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-02-06 16:55 | 1184-RD | Fast Track | Fast Track | Withdrawn | 4/30/2015 | Withdrawn | Withdrawn | SANTA CLARA | TRIMBLE SUB | Storage | 0.018 | 4/8/2015 | 5/13/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-02-13 16:00 | 1185-RD | Fast Track | Fast Track | In Service | 4/30/2015 |  |  | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Storage | 0.018 | 4/8/2015 | 5/19/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-03-15 19:44 | 1186-WD | Independent Study | Independent Study | Withdrawn | 1/31/2017 | Withdrawn | Withdrawn | SAN LUIS OBISPO | TEMPLETON SUB | Other | 4 | 4/8/2015 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-02-26 16:57 | 1187-RD | Fast Track | Fast Track | In Service | 5/28/2015 |  |  | SANTA CLARA | MONTAGUE SUB | Storage | 0.018 | 4/8/2015 | 4/22/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-02-26 17:01 | 1188-RD | Fast Track | Fast Track | In Service | 5/28/2015 |  |  | SANTA CLARA | MONTAGUE SUB | Storage | 0.018 | 4/8/2015 | 4/22/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-02-26 17:09 | 1189-RD | Fast Track | Fast Track | In Service | 5/26/2015 |  |  | SANTA CLARA | LAWRENCE SUB | Storage | 0.018 | 4/8/2015 | 4/14/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-02-26 17:13 | 1190-RD | Fast Track | Fast Track | In Service | 5/20/2015 |  |  | SANTA CLARA | LAWRENCE SUB | Storage | 0.018 | 4/8/2015 | 4/14/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-02-26 17:16 | 1191-RD | Fast Track | Fast Track | In Service | 5/27/2015 |  |  | SANTA CLARA | LAWRENCE SUB | Storage | 0.018 | 4/8/2015 | 4/14/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-03-02 10:35 | 1192-RD | Fast Track | Fast Track | In Service | 5/21/2015 |  |  | CONTRA COSTA | RICHMOND R SUB | Storage | 0.018 | 4/8/2015 | 5/19/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-03-15 10:34 | 1193-RD | Fast Track | Fast Track | Withdrawn | 9/1/2015 | Withdrawn | Withdrawn | SONOMA | LOWER LAKE SUB | Solar PV | 3 | 4/8/2015 | 4/29/2015 | Fail Screens: B, F, I, J, K, M | 7/13/2015 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-03-16 11:52 | 1194-RD | Fast Track | Fast Track | In Service | 5/29/2015 | In Service | 11/12/2015 | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Storage | 0.018 | 2015-04-08 | 4/24/2015 | Fail | 5/19/2015 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-03-16 12:25 | 1195-RD | Fast Track | Fast Track | In Service | 5/29/2015 | In Service | 9/30/2015 | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Storage | 0.036 | 4/8/2015 | 5/5/2015 | Fail | 5/19/2015 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-03-16 12:36 | 1196-RD | Fast Track | Fast Track | In Service | 5/29/2015 | In Service | 11/12/2015 | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Storage | 0.036 | 4/8/2015 | 4/24/2015 | Fail | 5/19/2015 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-03-23 17:17 | 1197-RD | Fast Track | Fast Track | In Service | 6/30/2015 |  |  | ALAMEDA | JARVIS SUB | Storage | 0.054 | 4/8/2015 | 4/10/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-03-23 17:34 | 1198-RD | Fast Track | Fast Track | In Service | 6/30/2015 |  |  | ALAMEDA | MT EDEN SUB | Storage | 0.036 | 4/8/2015 | 4/10/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-04-02 20:33 | 1199-RD | Fast Track | Fast Track | In Service | 6/30/2015 |  |  | MARIN | SAN RAFAEL SUB | Storage | 0.99225 | 4/15/2015 | 5/12/2015 | Fail | 6/8/2015 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-03-26 08:59 | 1200-RD | Fast Track | Fast Track | Withdrawn | 6/24/2015 | Withdrawn | Withdrawn | SAN JOAQUIN | TRACY SUB | Steam Turbine | 6.5 | 4/15/2015 | 5/7/2015 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-03-30 14:57 | 1201-RD | Fast Track | Fast Track | In Service | 6/30/2015 | In Service | 6/7/2016 | ALAMEDA | OAKLAND X SUB | Engine | 0.0044 | 4/15/2015 | 4/22/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-03-30 15:23 | 1202-WD | Cluster | Cluster | Withdrawn | 3/31/2018 | Withdrawn | Withdrawn | KERN | ARCO SUB | Solar PV | 20 | 4/15/2015 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-03-30 15:29 | 1203-WD | Cluster | Cluster | Withdrawn | 3/31/2018 | Withdrawn | Withdrawn | KERN | ARCO SUB | Solar PV | 20 | 4/15/2015 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-03-30 15:32 | 1204-WD | Cluster | Cluster | Withdrawn | 3/31/2018 | Withdrawn | Withdrawn | KINGS | ARCO SUB | Solar PV | 20 | 4/15/2015 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-03-17 15:16 | 1205-WD | Independent Study | Independent Study | In Service | 8/31/2016 | 3/16/2018 | 12/6/2017 | KERN | OLD RIVER SUB | Engine | 1 | 4/15/2015 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 1/8/2016 | N/A | Executed | No former queue position
2015-04-10 11:24 | 1206-WD | Independent Study | Independent Study | In Service | 3/31/2016 | 8/26/2016 | 11/17/2016 | TULARE | OROSI SUB | Solar PV | 1.5 | 4/22/2015 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 7/10/2015 | 12/1/2015 | Executed | No former queue position
2015-04-12 10:45 | 1207-WD | Fast Track | Independent Study | In Service | 11/30/2016 | 8/31/2017 | 12/5/2017 | KERN | MAGUNDEN SUB | Solar PV | 1 | 4/22/2015 | 4/27/2015 | Fail Screens: 2, 5, 6, 10 | 6/30/2015 | Fail | Pass | 1/20/2016 | N/A | Executed | No former queue position
2015-04-12 11:06 | 1208-WD | Fast Track | Fast Track | Withdrawn | 11/30/2016 | Withdrawn | Withdrawn | KERN | BAKERSFIELD SUB | Solar PV | 1 | 4/22/2015 | 4/27/2015 | Fail Screens: 2, 5, 10 | 6/16/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-04-13 15:09 | 1209-WD | Fast Track | Fast Track | In Service | 11/30/2016 | 8/31/2017 | 12/15/2017 | SAN JOAQUIN | MANTECA SUB | Solar PV | 1 | 4/22/2015 | 4/30/2015 | Fail Screens: 2, 10 | 6/4/2015 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-04-20 16:50 | 1210-RD | Fast Track | Fast Track | In Service | 6/30/2015 |  |  | BUTTE | BUTTE SUB | Solar PV | 0.15437 | 4/29/2015 | 5/20/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-03-15 16:07 | 1211-WD | Independent Study | Independent Study | Withdrawn | 11/29/2016 | Withdrawn | Withdrawn | SAN LUIS OBISPO | TEMPLETON SUB | Other | 4 | 4/29/2015 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-04-09 17:42 | 1212-RD | Fast Track | Fast Track | In Service | 6/25/2015 |  |  | SAN FRANCISCO | SAN FRAN Z (EMBARCADERO) SUB | Storage | 0.036 | 4/29/2015 | 5/1/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-04-22 14:58 | 1213-RD | Fast Track | Fast Track | In Service | 6/24/2015 |  |  | ALAMEDA | SAN RAMON SUB | Storage | 0.19845 | 4/29/2015 | 5/19/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-03-27 06:12 | 1214-RD | Fast Track | Fast Track | Withdrawn | 7/2/2015 | Withdrawn | Withdrawn | CONTRA COSTA | POINT PINOLE SUB | Solar PV | 1.2 | 4/29/2015 | 6/4/2015 | Fail Screens: I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-04-15 10:24 | 1215-WD | Fast Track | Fast Track | In Service | 11/30/2016 | 8/31/2017 | 10/3/2017 | KERN | SMYRNA SUB | Solar PV | 1 | 4/29/2015 | 5/28/2015 | Pass | 7/16/2015 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-04-15 15:24 | 1216-RD | Fast Track | Fast Track | Withdrawn | 6/30/2015 | Withdrawn | Withdrawn | SONOMA | CORONA SUB | Cogeneration | 0.13 | 4/29/2015 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-04-15 15:47 | 1217-RD | Fast Track | Fast Track | In Service | 6/30/2015 |  |  | KERN | FELLOWS SUB | Solar PV | 2.5 | 4/29/2015 | 5/12/2015 | Fail | 10/01/2015 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-04-17 12:35 | 1218-WD | Independent Study | Independent Study | Withdrawn | 12/31/2016 | Withdrawn | Withdrawn | KERN | LAMONT SUB | Solar PV | 4.5 | 4/29/2015 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-03-18 15:26 | 1219-WD | Independent Study | Independent Study | Withdrawn | 8/9/2016 | Withdrawn | Withdrawn | MONTEREY | SAN MIGUEL SUB | Other | 2 | 5/6/2015 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-03-24 14:22 | 1220-WD | Independent Study | Independent Study | Withdrawn | 8/9/2016 | Withdrawn | Withdrawn | MONTEREY | OIL FIELDS SUB | Solar PV | 5 | 5/6/2015 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-03-13 16:03 | 1221-WD | Fast Track | Fast Track | Withdrawn | 12/18/2015 | Withdrawn | Withdrawn | MARIN | NOVATO SUB | Solar PV | 1 | 5/6/2015 | 6/4/2015 | Fail Screens: 2, 4, 10 | 9/8/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-05-06 17:26 | 1222-RD | Fast Track | Fast Track | In Service | 7/30/2015 |  |  | SANTA CRUZ | PAUL SWEET SUB | Storage | 0.09 | 5/20/2015 | 6/12/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-05-07 15:03 | 1223-RD | Fast Track | Detailed Study | Withdrawn | 5/15/2016 | Withdrawn | Withdrawn | LAKE | HIGHLANDS SUB | Hydro | 2.9 | 5/20/2015 | 6/10/2015 | Fail Screens: B, F, I, J, K, M | 8/5/2015 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-04-30 13:12 | 1224-WD | Independent Study | Independent Study | Withdrawn | 5/1/2020 | Withdrawn | Withdrawn | EL DORADO | SHINGLE SPRINGS SUB | Other | 6 | 5/20/2015 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-04-02 21:16 | 1225-RD | Fast Track | Fast Track | In Service | 6/30/2015 |  |  | MARIN | IGNACIO SUB | Engine, Storage | 0.64335 | 5/20/2015 | 7/24/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-04-24 17:16 | 1226-RD | Fast Track | Fast Track | In Service | 7/29/2015 |  |  | NAPA | BASALT SUB | Storage | 0.036 | 5/20/2015 | 6/8/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-05-14 13:53 | 1227-WD | Fast Track | Fast Track | Withdrawn | 5/2/2016 | Withdrawn | Withdrawn | CONTRA COSTA | KIRKER SUB | Other | 1.5 | 6/3/2015 | 7/1/2015 | Fail Screens: 2, 10 | 10/8/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-04-24 17:07 | 1228-RD | Fast Track | Fast Track | In Service | 7/29/2015 |  |  | NAPA | BASALT SUB | Storage | 0.036 | 6/10/2015 | 6/30/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-05-28 17:48 | 1229-RD | Fast Track | Fast Track | In Service | 8/27/2015 |  |  | TEHAMA | CORNING SUB | Solar PV | 0.56372 | 6/10/2015 | 7/1/2015 | Fail | 8/19/2015 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-06-19 14:34 | 1230-RD | Fast Track | Fast Track | In Service | 8/28/2015 |  |  | ALAMEDA | BERKELEY F SUB | Solar PV | 0.10342 | 6/24/2015 | 9/1/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-06-09 16:44 | 1231-RD | Fast Track | Fast Track | In Service | 8/28/2015 |  |  | MONTEREY | SALINAS SUB | Solar PV | 0.7283 | 7/1/2015 | 7/21/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-06-11 09:41 | 1232-RD | Fast Track | Fast Track | In Service | 8/27/2015 |  |  | SANTA CLARA | AMES DIST SUB | Storage | 0.2 | 7/1/2015 | 7/16/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-06-25 10:25 | 1233-RD | Fast Track | Fast Track | In Service | 9/30/2015 |  |  | SANTA BARBARA | SANTA MARIA SUB | Engine | 0.633 | 7/1/2015 | 7/23/2015 | Fail | 9/2/2015 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-06-11 18:13 | 1234-RD | Fast Track | Fast Track | Withdrawn | 8/28/2015 | Withdrawn | Withdrawn | MERCED | ATWATER SUB | Cogeneration | 1 | 7/1/2015 | 7/17/2015 | Fail Screens: H | 8/27/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-07-01 17:11 | 1235-RD | Fast Track | Fast Track | In Service | 9/30/2015 |  |  | FRESNO | AIRWAYS SUB | Storage | 0.9975 | 7/15/2015 | 9/24/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-06-29 14:07 | 1236-WD | Fast Track | Fast Track | In Service | 4/29/2016 | 7/29/2016 | 9/8/2016 | MERCED | WILSON SUB | Solar PV | 0.75 | 7/15/2015 | 8/5/2015 | Fail Screens: 2, 5, 10 | 10/8/2015 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-07-02 14:21 | 1237-RD | Fast Track | Detailed Study | In Service | 3/15/2016 | 7/24/2017 | 3/28/2019 | KINGS | GUERNSEY SUB | Engine | 1 | 7/15/2015 | 8/10/2015 | Fail Screens: B, D, F, I, J, K, M | 9/17/2015 | Fail | Pass | 12/14/2015 | N/A | Executed | No former queue position
2015-07-06 09:46 | 1238-RD | Fast Track | Fast Track | Withdrawn | 6/16/2016 | Withdrawn | Withdrawn | KINGS | CORCORAN SUB | Reciprocating Engine | 1.028 | 7/15/2015 | 8/10/2015 | Fail Screens: B, D, F, G, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-07-06 18:43 | 1239-RD | Fast Track | Fast Track | In Service | 9/29/2015 |  |  | MONTEREY | VIEJO SUB | Engine | 0.75 | 7/15/2015 | 8/12/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-07-08 15:38 | 1240-RD | Fast Track | Fast Track | In Service | 9/29/2015 |  |  | SAN JOAQUIN | WEBER SUB | Turbine | 9.7 | 7/22/2015 | 9/1/2015 | Fail | 11/12/2015 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-07-15 09:16 | 1241-RD | Fast Track | Fast Track | In Service | 9/30/2015 |  |  | SANTA CLARA | AMES DIST SUB | Storage | 0.1 | 7/22/2015 | 8/13/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-07-10 15:16 | 1242-RD | Fast Track | Fast Track | Withdrawn | 9/23/2015 | Withdrawn | Withdrawn | FRESNO | BULLARD SUB | Engine | 7 | 7/22/2015 | 8/10/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-07-17 16:40 | 1243-WD | Fast Track | Fast Track | In Service | 9/30/2016 | 12/9/2016 | 12/15/2017 | MADERA | DAIRYLAND SUB | Solar PV | 1.5 | 7/29/2015 | 8/19/2015 | Fail Screens: 4, 5, 6, 7, 9, 10 | 10/22/2015 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-07-21 16:41 | 1244-WD | Fast Track | Fast Track | Withdrawn | 9/30/2016 | Withdrawn | Withdrawn | MADERA | DAIRYLAND SUB | Solar PV | 1 | 7/29/2015 | 8/19/2015 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-06-30 12:41 | 1245-RD | Fast Track | Fast Track | Withdrawn | 9/30/2015 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Solar PV | 0.03 | 8/5/2015 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-07-22 13:49 | 1246-RD | Fast Track | Fast Track | In Service | 9/30/2015 |  |  | SANTA CLARA | WHISMAN SUB | Storage | 0.15 | 8/5/2015 | 8/25/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-07-27 16:28 | 1247-WD | Fast Track | Independent Study | Withdrawn | 12/7/2016 | Withdrawn | Withdrawn | FRESNO | REEDLEY SUB | Solar PV | 0.75 | 8/5/2015 | 8/12/2015 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-08-14 14:26 | 1248-RD | Fast Track | Fast Track | In Service | 10/30/2015 |  |  | SAN LUIS OBISPO | SAN LUIS OBISPO SUB | Solar PV | 0.00463 | 8/19/2015 | 9/9/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-08-21 19:15 | 1249-RD | Fast Track | Fast Track | In Service | 10/29/2015 |  |  | SAN JOAQUIN | VIERRA SUB | Storage | 1.9 | 8/26/2015 | 9/17/2015 | Fail Screens: H | 11/4/2015 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-08-17 13:20 | 1250-RD | Fast Track | Fast Track | In Service | 10/30/2015 |  |  | MONTEREY | LOS OSITOS SUB | Solar PV | 0.196 | 9/2/2015 | 9/22/2015 | Fail Screens: D, F, J, M | 10/28/2015 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-08-24 16:31 | 1251-RD | Fast Track | Fast Track | In Service | 11/25/2015 |  |  | SAN FRANCISCO | SAN FRAN A (POTRERO PP) SUB | Solar PV | 0.0456 | 9/2/2015 | 9/28/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-08-20 15:18 | 1252-WD | Fast Track | Fast Track | Withdrawn | 3/18/2016 | Withdrawn | Withdrawn | SONOMA | SONOMA A SUB | Solar PV | 2 | 9/2/2015 | 9/24/2015 | Fail Screens: 2, 4, 5, 9, 10 | 1/20/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-08-28 17:37 | 1253-RD | Fast Track | Fast Track | In Service | 11/20/2015 |  |  | YUBA | OLIVEHURST SUB | Solar PV | 1.2902 | 9/9/2015 | 9/23/2015 | Fail | 10/27/2015 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-08-30 18:18 | 1254-RD | Fast Track | Fast Track | In Service | 11/26/2015 |  |  | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Micro Turbine | 0.13 | 9/9/2015 | 9/11/2015 | Fail | 11/5/2015 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-08-19 17:23 | 1255-RD | Fast Track | Detailed Study | Withdrawn | 3/1/2016 | Withdrawn | Withdrawn | MERCED | EL CAPITAN SUB | Gas Turbine | 3 | 9/9/2015 | 9/29/2015 | Fail Screens: B, F, I, J, K, M | 11/12/2015 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-08-26 08:16 | 1256-RD | Fast Track | Fast Track | In Service | 11/26/2015 |  |  | ALAMEDA | OAKLAND D SUB | Engine | 4 | 9/16/2015 | 10/8/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-09-04 12:28 | 1257-RD | Fast Track | Detailed Study | In Service | 11/26/2015 |  |  | SANTA BARBARA | DIVIDE SUB | Solar PV | 25.35 | 9/16/2015 | 10/6/2015 | Fail Screens: D, F, H, J, K | 10/20/2015 | Fail | Pass | 1/15/2016 | N/A | Executed | No former queue position
2015-08-26 04:13 | 1258-RD | Fast Track | Detailed Study | Withdrawn | 11/26/2015 | Withdrawn | Withdrawn | MONTEREY | LOS OSITOS SUB | Wind | 1.85 | 9/23/2015 | 10/15/2015 | Fail Screens: B, J, K, M | 12/1/2015 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-08-26 04:40 | 1259-RD | Fast Track | Fast Track | Withdrawn | 11/30/2015 | Withdrawn | Withdrawn | MONTEREY | SOLEDAD SUB | Wind | 1.85 | 9/23/2015 | 10/8/2015 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-09-11 07:55 | 1260-WD | Independent Study | Independent Study | Withdrawn | 4/3/2017 | Withdrawn | Withdrawn | PLUMAS | CHESTER SUB | Biomass | 0.55 | 9/23/2015 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-09-09 12:18 | 1261-RD | Fast Track | Fast Track | In Service | 11/26/2015 |  |  | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Storage | 0.018 | 9/30/2015 | 10/15/2015 | Fail | 12/7/2015 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-09-21 10:36 | 1262-WD | Fast Track | Fast Track | Withdrawn | 5/5/2016 | Withdrawn | Withdrawn | MARIN | STAFFORD SUB | Solar PV | 0.45 | 9/30/2015 | 10/28/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-09-22 14:37 | 1263-RD | Fast Track | Fast Track | Withdrawn | 9/1/2016 | Withdrawn | Withdrawn | YOLO | WOODLAND SUB | Other | 0.441 | 9/30/2015 | 10/20/2015 | Fail Screens: B, I, J, K, M | 12/11/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-09-16 11:09 | 1264-RD | Fast Track | Fast Track | In Service | 11/26/2015 |  |  | SANTA CLARA | LOCKHEED #1 SUB | Storage | 0.1 | 10/7/2015 | 10/9/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-09-02 12:13 | 1265-RD | Fast Track | Fast Track | Withdrawn | 2/1/2017 | Withdrawn | Withdrawn | KERN | CUYAMA SUB | Solar PV | 3 | 10/7/2015 | 10/28/2015 | Fail Screens: F | 1/29/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-09-29 10:01 | 1266-RD | Fast Track | Fast Track | In Service | 12/30/2015 |  |  | KINGS | KETTLEMAN HILLS SUB | Micro Turbine | 0.325 | 10/7/2015 | 10/16/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-09-21 12:30 | 1267-WD | Fast Track | Fast Track | Withdrawn | 10/1/2016 | Withdrawn | Withdrawn | FRESNO | CAMDEN SUB | Solar PV | 2 | 10/7/2015 | 10/20/2015 | Fail Screens: 2, 10 | 11/23/2015 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-09-18 12:43 | 1268-RD | Detailed Study | Detailed Study | Withdrawn | 6/16/2016 | Withdrawn | Withdrawn | KINGS | CORCORAN SUB | Reciprocating Engine | 1.028 | 10/7/2015 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-09-25 15:01 | 1269-RD | Fast Track | Detailed Study | In Service | 12/30/2015 |  |  | KINGS | CORCORAN SUB | Solar PV | 1.9269 | 10/14/2015 | 11/3/2015 | Fail Screens: D, J, K, M | 12/21/2015 | Fail | Pass | 6/22/2016 | N/A | Executed | No former queue position
2015-09-27 22:35 | 1270-RD | Fast Track | Fast Track | Withdrawn | 1/2/2017 | Withdrawn | Withdrawn | SHASTA | BURNEY SUB | Biomass | 2.88 | 10/21/2015 | 11/18/2015 | Fail Screens: B, F, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-10-06 07:24 | 1271-RD | Fast Track | Fast Track | Withdrawn | 12/31/2015 | Withdrawn | Withdrawn | KERN | COPUS SUB | Micro Turbine | 0.55 | 10/28/2015 | 3/3/2016 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-10-07 15:58 | 1272-WD | Independent Study | Independent Study | Withdrawn | 8/31/2017 | Withdrawn | Withdrawn | MONTEREY | CASTROVILLE SUB | Other | 5 | 10/28/2015 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-10-20 13:24 | 1273-RD | Fast Track | Fast Track | In Service | 12/31/2015 |  |  | SANTA CLARA | AMES DIST SUB | Storage | 0.25 | 10/28/2015 | 11/13/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-11-04 10:22 | 1274-WD | Fast Track | Fast Track | Withdrawn | 5/2/2016 | Withdrawn | Withdrawn | CONTRA COSTA | KIRKER SUB | Other | 0.5 | 11/10/2015 | 12/2/2015 | Fail Screens: 2, 10 | 1/20/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-11-06 13:38 | 1275-RD | Fast Track | Fast Track | Withdrawn | 1/29/2016 | Withdrawn | Withdrawn | FRESNO | MENDOTA SUB | Solar PV | 0.84 | 11/18/2015 | 12/9/2015 | Fail Screens: D, E, F, H, J, K | 1/21/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-11-09 16:22 | 1276-RD | Fast Track | Fast Track | In Service | 1/29/2016 |  |  | ALAMEDA | VINEYARD SUB | Solar PV | 0.9 | 11/18/2015 | 12/2/2015 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-11-09 16:16 | 1277-RD | Fast Track | Fast Track | In Service | 1/29/2016 |  |  | KERN | FELLOWS SUB | Engine | 9.6 | 11/18/2015 | 12/7/2015 | Fail Screens: D, F, H, J, K, M | 1/29/2016 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-11-17 15:56 | 1278-RD | Fast Track | Fast Track | In Service | 1/29/2016 |  |  | FRESNO | SAN JOAQUIN SUB | Solar PV | 1.5 | 12/9/2015 | 12/28/2015 | Fail Screens: B, D, F, I, J, K, L, M, S5 | 2/2/2016 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-11-23 17:45 | 1279-RD | Fast Track | Fast Track | Withdrawn | 2/29/2016 | Withdrawn | Withdrawn | CONTRA COSTA | KIRKER SUB | Solar PV | 1.1799 | 12/9/2015 | 12/29/2015 | Fail Screens: H, I, J, K, M | 2/16/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-12-03 07:28 | 1280-RD | Fast Track | Independent Study | Withdrawn | 10/31/2016 | Withdrawn | Withdrawn | ALAMEDA | CAYETANO SUB | Solar PV | 3 | 12/9/2015 | 12/29/2015 | Fail Screens: 10 | 1/29/2016 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | R21 Transition to WDT SGIA
2015-11-09 16:29 | 1281-WD | Independent Study | Independent Study | Withdrawn | 3/31/2017 | Withdrawn | Withdrawn | KERN | OLD RIVER SUB | Other | 1 | 12/16/2015 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-12-09 11:38 | 1282-RD | Detailed Study | Detailed Study | Withdrawn | 1/2/2017 | Withdrawn | Withdrawn | SHASTA | BURNEY SUB | Other | 2.881 | 12/16/2015 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-11-30 16:25 | 1283-RD | Fast Track | Fast Track | Withdrawn | 2/25/2016 | Withdrawn | Withdrawn | CONTRA COSTA | KIRKER SUB | Solar PV | 2.04 | 12/16/2015 | 1/4/2016 | Fail Screens: H, I, J, K, M | 2/16/2016 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-12-11 14:31 | 1284-RD | Fast Track | Fast Track | Withdrawn | 8/1/2016 | Withdrawn | Withdrawn | BUTTE | BANGOR SUB | Solar PV | 1.97 | 12/23/2015 | 1/12/2016 | Fail Screens: F, I, J, K, M | 2/23/2016 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-12-16 14:48 | 1285-WD | Fast Track | Fast Track | Withdrawn | 7/15/2016 | Withdrawn | Withdrawn | SAN LUIS OBISPO | SAN LUIS OBISPO SUB | Reciprocating Engine | 0.8 | 12/30/2015 | 1/25/2016 | Fail Screens: 2, 4, 5, 7, 9, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-12-22 12:39 | 1286-RD | Fast Track | Fast Track | Withdrawn | 2/26/2016 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN P(HUNTERS POINT) SUB | Solar PV | 0.133 | 12/30/2015 | 1/20/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-11-24 13:03 | 1287-RD | Fast Track | Fast Track | In Service | 2/26/2016 |  |  | SAN FRANCISCO | SAN FRAN A (POTRERO PP) SUB | Solar PV, Storage | 0.03564 | 12/30/2015 | 1/20/2016 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2015-12-17 08:56 | 1288-WD | Fast Track | Fast Track | Withdrawn | 7/1/2016 | Withdrawn | Withdrawn | SONOMA | BELLEVUE SUB | Solar PV | 1 | 1/6/2016 | 1/25/2016 | Fail Screens: 2, 6, 10 | 4/25/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2015-12-18 11:45 | 1289-WD | Fast Track | Independent Study | In Service | 11/30/2016 | 12/27/2018 | 11/12/2019 | KERN | ELK HILLS SUB | Solar PV | 3 | 1/13/2016 | 2/3/2016 | Fail Screens: 2, 4, 9, 10 | 3/18/2016 | Fail | Pass | 2016-09-20 | N/A | Executed | No former queue position
2015-12-28 15:45 | 1290-WD | Independent Study | Independent Study | Withdrawn | 12/31/2020 | Withdrawn | Withdrawn | ALAMEDA | OAKLAND J SUB | Other | 12.5 | 1/20/2016 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-01-13 15:46 | 1291-RD | Fast Track | Fast Track | In Service | 3/31/2016 |  |  | SAN FRANCISCO | SAN FRAN Z (EMBARCADERO) SUB | Solar PV | 0.05526 | 1/20/2016 | 1/22/2016 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-01-13 21:10 | 1292-RD | Detailed Study | Detailed Study | In Service | 3/31/2016 |  |  | SAN JOAQUIN | CORRAL SUB | Solar PV | 3.625 | 1/27/2016 | N/A | N/A | N/A | N/A | Pass | 2019-01-03 | N/A | Executed | No former queue position
2016-01-12 14:05 | 1293-RD | Fast Track | Fast Track | In Service | 3/31/2016 | In Service | 6/29/2016 | SANTA CLARA | MOUNTAIN VIEW SUB | Storage | 0.00426 | 2/2/2016 | 2/3/2016 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-01-25 16:03 | 1294-RD | Fast Track | Fast Track | In Service | 4/29/2016 |  |  | KERN | TUPMAN SUB | Storage | 0.1995 | 2/2/2016 | 3/2/2016 | Fail | 3/30/2016 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-02-09 13:39 | 1295-RD | Fast Track | Fast Track | In Service | 4/29/2016 |  |  | ALAMEDA | CASTRO VALLEY SUB | Solar PV | 0.11874 | 2/17/2016 | 3/3/2016 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-01-27 13:12 | 1296-WD | Independent Study | Independent Study | In Service | 5/1/2020 | 3/1/2020 | 3/11/2021 | KINGS | HENRIETTA SUB | Storage | 10 | 2/17/2016 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 9/6/2016 | 04/11/2017 | Executed | No former queue position
2016-02-18 17:00 | 1297-RD | Fast Track | Fast Track | In Service | 4/29/2016 |  |  | ALAMEDA | DIXON SUB | Storage | 0.015 | 2/24/2016 | 3/16/2016 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-02-26 17:33 | 1298-RD | Fast Track | Fast Track | Withdrawn | 5/26/2016 | Withdrawn | Withdrawn | SAN MATEO | EAST GRAND SUB | Solar PV | 0.26579 | 3/2/2016 | 6/7/2016 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-02-24 16:04 | 1299-RD | Fast Track | Fast Track | Withdrawn | 6/30/2016 | Withdrawn | Withdrawn | TEHAMA | CORNING SUB | Solar PV | 2 | 3/9/2016 | 3/21/2016 | Fail Screens: C, F, G, I, J, K, L, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-02-25 10:55 | 1300-RD | Fast Track | Fast Track | Withdrawn | 6/1/2017 | Withdrawn | Withdrawn | MADERA | DAIRYLAND SUB | Reciprocating Engine | 0.8 | 3/9/2016 | 3/31/2016 | Fail Screens: B, D, F, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-02-29 21:27 | 1301-RD | Fast Track | Fast Track | Withdrawn | 5/31/2016 | Withdrawn | Withdrawn | ALAMEDA | TESLA MOBILE STORAGE | Engine | 0.522 | 3/9/2016 | 4/26/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-02-25 13:43 | 1302-WD | Independent Study | Independent Study | Withdrawn | 10/31/2017 | Withdrawn | Withdrawn | FRESNO | BIOLA SUB | Other | 1.95 | 3/16/2016 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-03-14 16:32 | 1303-RD | Fast Track | Fast Track | Active | 5/31/2016 |  |  | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Solar PV | 0.05 | 3/23/2016 | 4/12/2016 | Fail | 5/4/2016 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-03-07 13:35 | 1304-RD | Fast Track | Fast Track | Withdrawn | 5/31/2016 | Withdrawn | Withdrawn | MERCED | EL CAPITAN SUB | Solar PV | 0.864 | 3/23/2016 | 4/12/2016 | Fail Screens: D, F, H, J, K | 5/19/2016 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-03-16 13:18 | 1305-RD | Fast Track | Fast Track | In Service | 5/31/2016 |  |  | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Solar PV | 0.058 | 3/23/2016 | 4/4/2016 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-03-17 12:29 | 1306-RD | Fast Track | Fast Track | Withdrawn | 5/26/2016 | Withdrawn | Withdrawn | ALAMEDA | OAKLAND C (OAKLAND PP) SUB | Solar PV | 0.0035 | 3/23/2016 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-03-14 10:50 | 1307-RD | Fast Track | Fast Track | Withdrawn | 8/1/2018 | Withdrawn | Withdrawn | PLUMAS | CRESCENT MILLS SUB | Biomass | 3 | 3/29/2016 | 4/15/2016 | Fail Screens: B, F, H, I, L, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-03-15 17:25 | 1308-RD | Fast Track | Fast Track | Withdrawn | 5/31/2016 | Withdrawn | Withdrawn | CONTRA COSTA | WILLOW PASS SUB | Solar PV | 1.7 | 3/29/2016 | 4/18/2016 | Fail Screens: D, F, H, J, K, M | 5/16/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-03-17 18:00 | 1309-RD | Fast Track | Fast Track | Withdrawn | 5/31/2016 | Withdrawn | Withdrawn | CONTRA COSTA | CONTRA COSTA SUB | Solar PV | 1.7 | 3/29/2016 | 4/18/2016 | Fail Screens: D, F, H, J, K, M | 5/17/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-03-17 11:05 | 1310-RD | Fast Track | Fast Track | In Service | 5/31/2016 |  |  | KERN | WEEDPATCH SUB | Solar PV | 0.54 | 3/29/2016 | 4/19/2016 | Fail Screens: F, H, J, K, M | 5/9/2016 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-03-16 11:55 | 1311-WD | Cluster | Cluster | Withdrawn | 12/31/2019 | Withdrawn | Withdrawn | KERN | GOOSE LAKE SUB | Solar PV | 10 | 4/6/2016 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-03-22 10:54 | 1312-WD | Independent Study | Independent Study | Withdrawn | 6/1/2018 | Withdrawn | Withdrawn | SAN JOAQUIN | RIPON SUB | Gas Turbine | 63.9 | 4/13/2016 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-02-12 11:18 | 1313-RD | Fast Track | Detailed Study | Withdrawn | 7/8/2016 | Withdrawn | Withdrawn | MONTEREY | SOLEDAD SUB | Wind | 3 | 4/13/2016 | 4/29/2016 | Fail Screens: B, C, F, G, H, I, J, K, M | 6/28/2016 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-04-07 15:01 | 1314-RD | Fast Track | Fast Track | In Service | 6/30/2016 |  |  | ALAMEDA | BERKELEY F SUB | Solar PV | 0.18519 | 4/13/2016 | 5/9/2016 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-04-01 12:24 | 1315-RD | Fast Track | Fast Track | In Service | 6/29/2016 |  |  | COLUSA | COLUSA SUB | Engine, Solar PV | 9.3236 | 4/13/2016 | 4/29/2016 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-04-02 14:48 | 1316-RD | Fast Track | Detailed Study | In Service | 6/1/2017 | 9/30/2017 | 3/26/2019 | FRESNO | SCHINDLER SUB | Engine | 0.8 | 4/13/2016 | 4/29/2016 | Fail Screens: B, D, F, I, J, K, M | 5/25/2016 | Fail | Pass | 8/15/2016 | N/A | Executed | No former queue position
2016-04-02 15:26 | 1317-RD | Detailed Study | Detailed Study | In Service | 9/1/2017 | 9/15/2017 | 3/28/2019 | KINGS | GUERNSEY SUB | Engine | 1.028 | 4/13/2016 | N/A | N/A | N/A | N/A | Pass | 8/17/2016 | N/A | Executed | No former queue position
2016-04-04 17:11 | 1318-RD | Detailed Study | Detailed Study | In Service | 8/1/2017 | 11/30/2017 | 10/31/2018 | MADERA | DAIRYLAND SUB | Engine | 0.8 | 4/13/2016 | N/A | N/A | N/A | N/A | Pass | 7/29/2016 | N/A | Executed | No former queue position
2016-03-30 14:26 | 1319-WD | Independent Study | Independent Study | In Service | 7/29/2016 | 8/18/2017 | 8/8/2017 | YUBA | WHEATLAND SUB | Engine, Turbine | 3.8 | 4/20/2016 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 2017-03-08 | N/A | Executed | No former queue position
2016-03-31 13:25 | 1320-WD | Independent Study | Independent Study | In Service | 3/30/2018 | 3/1/2019 |  | SANTA BARBARA | CABRILLO SUB | Wind | 99 | 4/20/2016 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 10/28/2016 | 11/19/2018 | Executed | No former queue position
2016-04-18 12:21 | 1321-RD | Fast Track | Fast Track | In Service | 6/29/2016 |  |  | SANTA CLARA | MCKEE SUB | Solar PV | 0.20512 | 4/20/2016 | 5/27/2016 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-04-18 16:25 | 1322-RD | Fast Track | Fast Track | In Service | 6/29/2016 |  |  | SANTA CLARA | HICKS SUB | Solar PV | 0.20514 | 4/20/2016 | 5/27/2016 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-04-12 12:22 | 1323-RD | Fast Track | Fast Track | Withdrawn | 6/29/2016 | Withdrawn | Withdrawn | SAN MATEO | BURLINGAME SUB | Other | 0.005 | 4/27/2016 | 5/24/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-04-12 17:40 | 1324-RD | Detailed Study | Detailed Study | Withdrawn | 11/1/2017 | Withdrawn | Withdrawn | FRESNO | SCHINDLER SUB | Engine | 0.8 | 4/27/2016 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-04-15 16:16 | 1325-RD | Fast Track | Fast Track | Withdrawn | 11/1/2017 | Withdrawn | Withdrawn | FRESNO | MCMULLIN SUB | Reciprocating Engine | 1.028 | 5/4/2016 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-04-19 17:03 | 1326-RD | Fast Track | Fast Track | Withdrawn | 7/27/2016 | Withdrawn | Withdrawn | MADERA | MADERA SUB | Solar PV | 5 | 5/4/2016 | 5/24/2016 | Fail Screens: D, F, H, J, K | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-04-24 09:40 | 1327-RD | Fast Track | Fast Track | Withdrawn | 7/28/2016 | Withdrawn | Withdrawn | MADERA | CHOWCHILLA SUB | Solar PV | 0.4461 | 5/4/2016 | 5/24/2016 | Fail Screens: D, F, H, J, M | 7/6/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-04-22 10:16 | 1328-RD | Fast Track | Fast Track | In Service | 7/27/2016 |  |  | SANTA CLARA | COOLEY LANDING SUB | Solar PV, Steam Turbine, Turbine | 4.49 | 5/4/2016 | 5/18/2016 | Fail | 7/18/2016 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-04-22 13:49 | 1329-RD | Fast Track | Fast Track | Withdrawn | 2/16/2018 | Withdrawn | Withdrawn | NEVADA | BRUNSWICK SUB | Hydro | 1.44 | 5/11/2016 | 5/31/2016 | Fail Screens: B, D, G, I, J, K, L, M, V1, V2, S5, A1 | 8/1/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-04-06 12:44 | 1330-WD | Fast Track | Fast Track | Withdrawn | 4/7/2017 | Withdrawn | Withdrawn | SAN JOAQUIN | STOCKTON A SUB | Solar PV | 1.98 | 5/11/2016 | 6/2/2016 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-04-06 13:41 | 1331-WD | Fast Track | Fast Track | In Service | 4/21/2017 | 3/3/2019 | 7/20/2018 | CONTRA COSTA | CONTRA COSTA SUB | Solar PV | 0.9 | 5/11/2016 | 6/1/2016 | Fail Screens: 2, 7, 9, 10 | 7/13/2016 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-04-19 14:44 | 1332-WD | Independent Study | Independent Study | Withdrawn | 1/20/2017 | Withdrawn | Withdrawn | SAN LUIS OBISPO | SAN LUIS OBISPO SUB | Reciprocating Engine | 1.062 | 5/18/2016 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-05-03 12:16 | 1333-WD | Independent Study | Independent Study | Withdrawn | 12/31/2017 | Withdrawn | Withdrawn | KERN | LAMONT SUB | Solar PV | 2.25 | 5/18/2016 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-05-06 09:12 | 1334-RD | Fast Track | Fast Track | Withdrawn | 5/31/2018 | Withdrawn | Withdrawn | FRESNO | KINGSBURG SUB | Solar PV | 1.215 | 5/18/2016 | 6/2/2016 | Fail Screens: G, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-05-11 10:26 | 1335-RD | Fast Track | Fast Track | Withdrawn | 12/15/2017 | Withdrawn | Withdrawn | LAKE | CLEAR LAKE SUB | Solar PV | 2 | 5/25/2016 | 6/15/2016 | Fail | 7/27/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | R21 Transition to WDT SGIA
2016-05-10 11:49 | 1336-RD | Fast Track | Fast Track | In Service | 2/24/2017 |  |  | SOLANO | VACA DIXON SUB | Solar PV | 3.75 | 5/25/2016 | 6/15/2016 | Fail | 8/2/2016 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-05-10 12:06 | 1337-RD | Fast Track | Fast Track | In Service | 2/24/2017 |  |  | SOLANO | VACA DIXON SUB | Solar PV | 3.1378 | 5/25/2016 | 6/15/2016 | Fail | 8/2/2016 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-05-10 15:34 | 1338-WD | Independent Study | Independent Study | Withdrawn | 5/31/2018 | Withdrawn | Withdrawn | FRESNO | COALINGA #1 SUB | Other | 15 | 5/25/2016 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-05-12 11:24 | 1339-RD | Fast Track | Fast Track | In Service | 7/1/2016 |  |  | ALAMEDA | GRANT SUB | Storage | 0.03 | 5/25/2016 | 6/29/2016 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-05-20 16:11 | 1340-RD | Fast Track | Fast Track | In Service | 5/20/2016 |  |  | ALAMEDA | Hillslide115 | Solar PV | 0.0691 | 5/25/2016 | 7/15/2016 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-04-25 16:35 | 1341-RD | Fast Track | Fast Track | In Service | 7/29/2016 |  |  | EL DORADO | DIAMOND SPRINGS SUB | Hydro | 0.4849 | 6/1/2016 | 6/22/2016 | Fail Screens: H | 8/17/2016 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-05-19 14:34 | 1342-RD | Fast Track | Fast Track | Withdrawn | 11/15/2016 | Withdrawn | Withdrawn | MERCED | EL CAPITAN SUB | Solar PV | 0.864 | 6/1/2016 | 6/21/2016 | Fail Screens: D, F, H, J, K | 8/1/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-05-06 15:09 | 1343-RD | Detailed Study | Detailed Study | Withdrawn | 11/1/2017 | Withdrawn | Withdrawn | FRESNO | MCMULLIN SUB | Engine | 1 | 6/8/2016 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-05-20 09:02 | 1344-RD | Fast Track | Fast Track | Withdrawn | 5/1/2017 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN Z (EMBARCADERO) SUB | Micro Turbine | 0.065 | 6/8/2016 | 7/1/2016 | Fail Screens: F, H, J | 9/20/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-05-26 15:15 | 1345-RD | Fast Track | Fast Track | In Service | 6/1/2017 |  |  | AMADOR | CLAY SUB | Hydro | 0.4476 | 6/8/2016 | 6/28/2016 | Fail Screens: B, C, D, F, G, I, J, L, M, V1, S5, A1 | 8/8/2016 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-06-08 13:49 | 1346-RD | Fast Track | Fast Track | Withdrawn | 6/8/2016 | Withdrawn | Withdrawn | SAN JOAQUIN | WEBER SUB | Solar PV | 0.35438 | 6/14/2016 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-05-27 14:42 | 1347-RD | Fast Track | Fast Track | Withdrawn | 8/5/2016 | Withdrawn | Withdrawn | MONTEREY | SOLEDAD SUB | Solar PV | 0.04974 | 6/22/2016 | 7/13/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-06-10 06:59 | 1348-RD | Fast Track | Fast Track | Withdrawn | 6/9/2017 | Withdrawn | Withdrawn | MONTEREY | PRUNEDALE SUB | Solar PV | 2.9807 | 6/22/2016 | 7/13/2016 | Fail Screens: D, F, H, J, K, M | 9/2/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-05-28 12:17 | 1349-RD | Fast Track | Detailed Study | Withdrawn | 9/30/2016 | Withdrawn | Withdrawn | SONOMA | FULTON SUB | Solar PV | 0.999 | 6/29/2016 | 7/6/2016 | Fail Screens: D, F, H, J, K, M | 8/23/2016 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-06-22 14:37 | 1350-RD | Fast Track | Fast Track | In Service | 8/1/2016 |  |  | SAN FRANCISCO | YOSEMITE SUB | Solar PV | 0.11808 | 6/29/2016 | 7/6/2016 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-06-02 16:15 | 1351-WD | Fast Track | Fast Track | Withdrawn | 12/1/2016 | Withdrawn | Withdrawn | SAN MATEO | BELLE HAVEN SUB | Other | 0.1 | 6/29/2016 | 8/31/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-06-06 12:47 | 1352-RD | Fast Track | Fast Track | In Service | 9/30/2016 |  |  | SANTA CLARA | SAN JOSE B SUB | Storage | 0.036 | 6/29/2016 | 8/29/2016 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-06-06 09:14 | 1353-WD | Fast Track | Fast Track | Withdrawn | 1/4/2017 | Withdrawn | Withdrawn | PLACER | SMARTVILLE SUB | Solar PV | 3.991 | 6/29/2016 | 7/20/2016 | Fail Screens: 2, 4, 5, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-06-23 16:58 | 1354-WD | Fast Track | Fast Track | Withdrawn | 8/31/2018 | Withdrawn | Withdrawn | BUTTE | OROVILLE SUB | Solar PV | 1.9925 | 7/6/2016 | 7/21/2016 | Fail Screens: 2, 5, 6, 10 | 8/31/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-06-23 17:21 | 1355-WD | Fast Track | Fast Track | Withdrawn | 8/31/2018 | Withdrawn | Withdrawn | EL DORADO | DIAMOND SPRINGS SUB | Solar PV | 1.8 | 7/6/2016 | 7/27/2016 | Fail Screens: 2, 4, 5, 10 | 9/16/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-06-23 17:54 | 1356-WD | Fast Track | Fast Track | Withdrawn | 8/31/2018 | Withdrawn | Withdrawn | CONTRA COSTA | BRENTWOOD SUB | Solar PV | 1.4 | 7/6/2016 | 7/19/2016 | Fail Screens: 2, 5, 10 | 9/29/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-06-23 18:24 | 1357-WD | Fast Track | Independent Study | Withdrawn | 8/31/2018 | Withdrawn | Withdrawn | STANISLAUS | RIVERBANK SUB | Solar PV | 2.8 | 7/6/2016 | 7/27/2016 | Fail Screens: 2, 5, 10 | 9/23/2016 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-06-24 12:53 | 1358-WD | Fast Track | Fast Track | Withdrawn | 8/31/2018 | Withdrawn | Withdrawn | BUTTE | WYANDOTTE SUB | Solar PV | 1 | 7/6/2016 | 7/18/2016 | Fail Screens: 2, 5, 6, 10 | 8/31/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-06-21 16:39 | 1359-RD | Detailed Study | Detailed Study | Withdrawn | 11/1/2018 | Withdrawn | Withdrawn | PLUMAS | CRESCENT MILLS SUB | Biomass | 3 | 7/6/2016 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-07-01 14:50 | 1360-RD | Fast Track | Fast Track | Withdrawn | 7/1/2018 | Withdrawn | Withdrawn | NAPA | HIGHWAY SUB | Biomass | 1 | 7/6/2016 | 7/27/2016 | Fail Screens: B, D, F, G, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-06-07 14:04 | 1361-RD | Fast Track | Fast Track | Withdrawn | 6/7/2017 | Withdrawn | Withdrawn | BUTTE | SYCAMORE CREEK SUB | Solar PV | 1.25 | 7/13/2016 | 7/15/2016 | Fail Screens: F, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-06-07 14:19 | 1362-RD | Fast Track | Fast Track | Withdrawn | 6/7/2017 | Withdrawn | Withdrawn | SHASTA | ANDERSON SUB | Solar PV | 0.36 | 7/13/2016 | 7/19/2016 | Fail Screens: I, J, K, M | 9/19/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-06-27 07:10 | 1363-RD | Fast Track | Fast Track | Withdrawn | 5/2/2018 | Withdrawn | Withdrawn | SANTA CLARA | VASONA SUB | Cogeneration | 2 | 7/20/2016 | 8/3/2016 | Fail Screens: F, H, J, K, M | 8/30/2016 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-06-30 09:58 | 1364-RD | Fast Track | Fast Track | Withdrawn | 10/1/2017 | Withdrawn | Withdrawn | MADERA | STOREY SUB | Solar PV | 0.588 | 7/20/2016 | 8/10/2016 | Fail Screens: D, F, H, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-07-13 16:59 | 1365-RD | Fast Track | Fast Track | Withdrawn | 8/1/2017 | Withdrawn | Withdrawn | CONTRA COSTA | KIRKER SUB | Solar PV | 0.6 | 7/20/2016 | 8/1/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-06-09 10:42 | 1366-RD | Detailed Study | Detailed Study | In Service | 12/31/2020 |  |  | SAN LUIS OBISPO | GOLDTREE SUB | Solar PV | 4.5 | 7/27/2016 | N/A | N/A | N/A | N/A | Pass | 12/15/2016 | N/A | Executed | No former queue position
2016-07-25 12:00 | 1367-RD | Fast Track | Fast Track | In Service | 1/25/2017 |  |  | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Storage | 0.036 | 8/10/2016 | 8/30/2016 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-07-26 21:38 | 1368-RD | Detailed Study | Detailed Study | Withdrawn | 3/3/2018 | Withdrawn | Withdrawn | HUMBOLDT | JANES CREEK SUB | Biomass | 1 | 8/17/2016 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-08-05 13:46 | 1369-RD | Fast Track | Fast Track | Withdrawn | 4/17/2017 | Withdrawn | Withdrawn | ALAMEDA | NEWARK SUB | Cogeneration | 0.45 | 8/17/2016 | 9/7/2016 | Fail Screens: B | 10/24/2016 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-08-17 09:07 | 1370-WD | Independent Study | Independent Study | Withdrawn | 5/1/2020 | Withdrawn | Withdrawn | SANTA CLARA | LLAGAS SUB | Storage | 20 | 8/24/2016 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position.
2016-08-18 18:37 | 1371-RD | Fast Track | Fast Track | In Service | 12/1/2017 |  |  | SANTA CLARA | WOLFE SUB | Solar PV | 0.72 | 8/24/2016 | 9/28/2016 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-08-12 14:17 | 1372-WD | Fast Track | Independent Study | Withdrawn | 8/31/2018 | Withdrawn | Withdrawn | BUTTE | OROVILLE SUB | Solar PV | 1.5 | 8/24/2016 | 9/13/2016 | Fail Screens: 2, 4, 5, 6, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-08-18 14:40 | 1373-RD | Detailed Study | Detailed Study | Withdrawn | 7/1/2018 | Withdrawn | Withdrawn | NAPA | HIGHWAY SUB | Other | 1.172 | 8/24/2016 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-08-04 10:34 | 1374-RD | Fast Track | Fast Track | In Service | 12/31/2017 | In Service | 5/31/2018 | MADERA | CHOWCHILLA SUB | Solar PV | 0.80973 | 8/31/2016 | 9/21/2016 | Fail Screens: D, F, H, J, K | 11/21/2016 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-07-14 08:34 | 1375-RD | Detailed Study | Detailed Study | Withdrawn | 7/3/2018 | Withdrawn | Withdrawn | YUBA | PIKE CITY SUB | Steam Turbine | 3 | 9/7/2016 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-08-26 14:31 | 1376-RD | Fast Track | Fast Track | Withdrawn | 3/22/2017 | Withdrawn | Withdrawn | GLENN | JACINTO SUB | Biomass | 0.45 | 9/7/2016 | 10/7/2016 | Fail Screens: B, F, G, L, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-08-29 17:46 | 1377-WD | Fast Track | Fast Track | Withdrawn | 8/31/2018 | Withdrawn | Withdrawn | CALAVERAS | CALAVERAS CEMENT SUB | Solar PV | 1.4 | 9/7/2016 | 9/27/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-08-17 12:16 | 1378-RD | Fast Track | Fast Track | Withdrawn | 5/15/2018 | Withdrawn | Withdrawn | KERN | PASO ROBLES SUB | Solar PV | 24.497 | 9/7/2016 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-09-01 16:15 | 1379-RD | Fast Track | Fast Track | Withdrawn | 1/2/2017 | Withdrawn | Withdrawn | CALAVERAS | STANISLAUS PH | Hydro | 3 | 9/14/2016 | 10/10/2016 | Fail Screens: B, F, G, I, J, K, M | 11/14/2016 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-08-30 07:26 | 1380-RD | Fast Track | Fast Track | In Service | 12/30/2016 |  |  | YOLO | WOODLAND SUB | Solar PV | 1.9248 | 9/14/2016 | 10/5/2016 | Fail Screens: D, J, K, M | 12/7/2016 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-08-30 08:02 | 1381-RD | Fast Track | Detailed Study | In Service | 12/30/2016 | In Service | 2/19/2010 | KERN | 7TH STANDARD SUB | Solar PV | 1.588 | 9/14/2016 | 10/3/2016 | Fail Screens: D, H, J, K, M | 11/30/2016 | Fail | Pass | 5/16/2017 | N/A | Executed | No former queue position
2016-09-08 10:55 | 1382-WD | Fast Track | Fast Track | Withdrawn | 9/14/2017 | Withdrawn | Withdrawn | SONOMA | PENNGROVE SUB | Solar PV | 1 | 9/21/2016 | 10/11/2016 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-09-08 11:13 | 1383-WD | Fast Track | Fast Track | Withdrawn | 9/14/2017 | Withdrawn | Withdrawn | SONOMA | PENNGROVE SUB | Solar PV | 1 | 9/21/2016 | 10/11/2016 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-09-21 10:29 | 1384-WD | Fast Track | Fast Track | In Service | 3/31/2017 | 3/1/2018 | 3/13/2019 | MARIN | SAN RAFAEL SUB | Cogeneration | 0.75 | 10/5/2016 | 10/27/2016 | Fail Screens: 2, 4, 9, 10 | 1/11/2017 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-09-16 17:05 | 1385-RD | Fast Track | Fast Track | Withdrawn | 11/22/2016 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Storage | 0.036 | 10/12/2016 | 10/27/2016 | Fail Screens: A | 12/18/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-09-30 14:39 | 1386-WD | Independent Study | Independent Study | Withdrawn | 2/28/2019 | Withdrawn | Withdrawn | EL DORADO | APPLE HILL SUB | Other | 10 | 10/12/2016 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-09-30 14:54 | 1387-WD | Independent Study | Independent Study | Withdrawn | 2/28/2019 | Withdrawn | Withdrawn | EL DORADO | APPLE HILL SUB | Other | 10 | 10/12/2016 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-08-26 16:22 | 1388-RD | Detailed Study | Detailed Study | Withdrawn | 6/7/2017 | Withdrawn | Withdrawn | BUTTE | SYCAMORE CREEK SUB | Solar PV | 1.25 | 10/19/2016 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-09-15 06:38 | 1389-RD | Fast Track | Detailed Study | In Service | 5/1/2017 |  |  | KERN | RENFRO SUB | Solar PV | 1.3828 | 10/19/2016 | 11/9/2016 | Fail Screens: D, E, F, H, J, K, M | 12/28/2016 | Fail | Pass | 5/19/2017 | N/A | Executed | No former queue position
2016-09-15 07:07 | 1390-RD | Fast Track | Detailed Study | In Service | 5/5/2017 |  |  | KERN | TEVIS SUB | Solar PV | 1.3982 | 10/19/2016 | 11/9/2016 | Fail Screens: D, E, F, H, J, K, M | 12/28/2016 | Fail | Pass | 5/19/2017 | N/A | Executed | No former queue position
2016-09-23 13:59 | 1391-RD | Detailed Study | Detailed Study | In Service | 12/30/2016 |  |  | SAN BENITO | SAN BENITO SUB | Engine | 2 | 10/19/2016 | N/A | N/A | N/A | N/A | Pass | 10/20/2017 | N/A | Executed | No former queue position
2016-09-29 10:37 | 1392-RD | Fast Track | Fast Track | Withdrawn | 12/30/2016 | Withdrawn | Withdrawn | MONTEREY | SOLEDAD SUB | Solar PV | 0.04814 | 10/26/2016 | 11/15/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-10-05 17:41 | 1393-WD | Fast Track | Fast Track | Withdrawn | 10/14/2017 | Withdrawn | Withdrawn | YOLO | WOODLAND SUB | Reciprocating Engine | 0.65 | 10/26/2016 | 11/17/2016 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-10-07 14:52 | 1394-WD | Independent Study | Independent Study | Withdrawn | 12/31/2019 | Withdrawn | Withdrawn | KERN | GOOSE LAKE SUB | Solar PV | 5 | 10/26/2016 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-10-13 09:07 | 1395-RD | Fast Track | Fast Track | In Service | 3/1/2017 |  |  | ALAMEDA | OAKLAND J SUB | Solar PV | 2.004 | 10/26/2016 | 11/29/2016 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-10-17 21:58 | 1396-WD | Fast Track | Fast Track | Withdrawn | 3/31/2017 | Withdrawn | Withdrawn | MARIN | STAFFORD SUB | Solar PV | 0.45 | 10/26/2016 | 11/18/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-10-12 14:02 | 1397-RD | Fast Track | Fast Track | In Service | 8/9/2017 |  |  | FRESNO | NEW KEARNEY SUB | Solar PV | 0.72 | 10/26/2016 | 11/14/2016 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-10-13 16:40 | 1398-WD | Fast Track | Fast Track | In Service | 12/5/2017 | 12/1/2018 | 12/4/2020 | SONOMA | PETALUMA C SUB | Solar PV | 1 | 11/2/2016 | 12/2/2016 | Fail Screens: 2, 4, 5, 9, 10 | 1/9/2017 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-10-13 16:52 | 1399-WD | Fast Track | Fast Track | In Service | 12/5/2017 | 12/1/2018 | 11/12/2020 | SONOMA | PETALUMA C SUB | Solar PV | 1 | 11/2/2016 | 12/2/2016 | Fail Screens: 2, 4, 5, 7, 9, 10 | 1/9/2017 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-10-18 15:31 | 1400-RD | Detailed Study | Detailed Study | In Service | 12/31/2017 |  |  | MADERA | BORDEN SUB | Solar PV | 3.66 | 11/2/2016 | N/A | N/A | N/A | N/A | Fail | 6/1/2017 | N/A | Executed | No former queue position
2016-10-26 17:51 | 1401-WD | Fast Track | Fast Track | Withdrawn | 12/11/2017 | Withdrawn | Withdrawn | SAN LUIS OBISPO | SAN LUIS OBISPO SUB | Solar PV | 1.2 | 11/9/2016 | 12/2/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-10-26 18:35 | 1402-RD | Fast Track | Detailed Study | Withdrawn | 8/1/2017 | Withdrawn | Withdrawn | BUTTE | BANGOR SUB | Solar PV | 2 | 11/9/2016 | 2017-04-28 | Fail Screens: F, G, H, L, M | 7/13/2017 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-10-17 11:56 | 1403-RD | Detailed Study | Detailed Study | Withdrawn | 1/1/2018 | Withdrawn | Withdrawn | SAN JOAQUIN | AVENA SUB | Reciprocating Engine | 2.282 | 11/9/2016 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-10-25 09:12 | 1404-RD | Fast Track | Fast Track | Withdrawn | 7/3/2017 | Withdrawn | Withdrawn | SAN JOAQUIN | LAMMERS SUB | Biomass | 2.8 | 11/9/2016 | 12/2/2016 | Fail Screens: B, F, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-10-25 15:54 | 1405-WD | Fast Track | Fast Track | Withdrawn | 11/3/2016 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN F (MARINA) SUB | Other | 0.038 | 11/9/2016 | 2017-01-12 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-10-25 16:13 | 1406-WD | Fast Track | Fast Track | Withdrawn | 11/3/2016 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN F (MARINA) SUB | Other | 0.038 | 11/9/2016 | 2017-01-12 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-10-25 16:37 | 1407-WD | Fast Track | Fast Track | Withdrawn | 11/3/2016 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Other | 0.038 | 11/9/2016 | 2017-01-12 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-10-25 16:50 | 1408-WD | Fast Track | Fast Track | Withdrawn | 11/3/2016 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Other | 0.038 | 11/9/2016 | 2017-01-12 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-10-25 16:54 | 1409-WD | Fast Track | Fast Track | Withdrawn | 11/3/2016 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN F (MARINA) SUB | Other | 0.038 | 11/9/2016 | 2017-01-12 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-10-26 11:32 | 1410-RD | Fast Track | Fast Track | Withdrawn | 1/31/2017 | Withdrawn | Withdrawn | HUMBOLDT | HARRIS SUB | Solar PV | 0.9 | 11/9/2016 | 12/2/2016 | Fail Screens: D, F, H, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-11-02 09:03 | 1411-RD | Fast Track | Fast Track | In Service | 2/20/2017 |  |  | FRESNO | WAHTOKE SUB | Solar PV | 1.0688 | 11/9/2016 | 11/17/2016 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-10-26 15:41 | 1412-RD | Fast Track | Fast Track | Withdrawn | 1/31/2017 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Solar PV | 0.06393 | 11/9/2016 | 11/28/2016 | Fail | 12/22/2016 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-11-02 14:54 | 1413-WD | Fast Track | Fast Track | Withdrawn | 8/30/2017 | Withdrawn | Withdrawn | SONOMA | SONOMA A SUB | Solar PV | 2 | 11/23/2016 | 12/15/2016 | Fail Screens: 2, 4, 5, 10 | 2/1/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-11-02 15:16 | 1414-WD | Independent Study | Independent Study | Withdrawn | 8/30/2017 | Withdrawn | Withdrawn | SONOMA | SONOMA A SUB | Solar PV | 7 | 11/23/2016 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-11-08 12:06 | 1415-RD | Detailed Study | Detailed Study | Withdrawn | 11/1/2017 | Withdrawn | Withdrawn | KINGS | KETTLEMAN HILLS SUB | Solar PV | 4.05 | 11/23/2016 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-11-11 14:20 | 1416-RD | Fast Track | Fast Track | Withdrawn | 1/31/2017 | Withdrawn | Withdrawn | MONTEREY | PRUNEDALE SUB | Solar PV | 0.84 | 11/23/2016 | 12/16/2016 | Fail Screens: D, F, H, J, K | 1/26/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-11-08 14:39 | 1417-RD | Fast Track | Fast Track | Withdrawn | 1/31/2017 | Withdrawn | Withdrawn | SANTA CLARA | SARATOGA SUB | Micro Turbine | 0.8 | 11/30/2016 | 1/5/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-11-14 10:00 | 1418-RD | Fast Track | Fast Track | In Service | 12/1/2017 |  |  | KINGS | TULARE LAKE SUB | Solar PV | 1.92 | 11/30/2016 | 12/15/2016 | Fail Screens: D, J, K, M | 1/12/2017 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-11-14 10:39 | 1419-RD | Fast Track | Detailed Study | In Service | 10/27/2017 |  |  | KERN | GOOSE LAKE SUB | Solar PV | 1.92 | 11/30/2016 | 1/27/2017 | Fail Screens: B, D, F, G, H, I, J, K, L, M | 5/11/2017 | Fail | Pass | 9/5/2017 | N/A | Executed | No former queue position
2016-11-04 14:55 | 1420-RD | Fast Track | Fast Track | In Service | 1/31/2017 |  |  | FRESNO | KERMAN SUB | Solar PV | 0.42876 | 11/30/2016 | 12/20/2016 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-11-10 12:46 | 1421-RD | Detailed Study | Detailed Study | Withdrawn | 5/1/2019 | Withdrawn | Withdrawn | KERN | TEJON SUB | Solar PV | 2.97 | 12/7/2016 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-11-22 13:29 | 1422-RD | Fast Track | Fast Track | In Service | 4/3/2017 |  |  | FRESNO | CARUTHERS SUB | Solar PV | 0.15574 | 12/7/2016 | 12/21/2016 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-11-17 14:17 | 1423-WD | Independent Study | Independent Study | Withdrawn | 8/6/2018 | Withdrawn | Withdrawn | MENDOCINO | COVELO SUB | Reciprocating Engine | 2.881 | 12/14/2016 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-12-02 17:32 | 1424-WD | Fast Track | Fast Track | Withdrawn | 5/1/2017 | Withdrawn | Withdrawn | CONTRA COSTA | RICHMOND R SUB | Solar PV | 0.3 | 12/14/2016 | 1/6/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-11-15 10:54 | 1425-RD | Detailed Study | Detailed Study | In Service | 2/15/2018 | 1/21/2019 | 6/20/2019 | KINGS | HARDWICK SUB | Engine | 1 | 12/21/2016 | N/A | N/A | N/A | N/A | Pass | 6/16/2017 | N/A | Executed | No former queue position
2016-12-14 09:13 | 1426-RD | Fast Track | Fast Track | Withdrawn | 1/31/2017 | Withdrawn | Withdrawn | MADERA | STOREY SUB | Solar PV | 0.01139 | 12/21/2016 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-12-01 11:22 | 1427-RD | Fast Track | Fast Track | In Service | 3/10/2017 |  |  | SAN MATEO | BELLE HAVEN SUB | Storage | 0.09 | 1/4/2017 | 3/9/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-12-01 15:48 | 1428-RD | Fast Track | Fast Track | In Service | 2/10/2017 |  |  | SAN FRANCISCO | SAN FRAN Z (EMBARCADERO) SUB | Storage | 0.018 | 1/4/2017 | 1/6/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-12-01 16:19 | 1429-RD | Fast Track | Fast Track | In Service | 3/1/2017 |  |  | SAN FRANCISCO | SAN FRAN Z (EMBARCADERO) SUB | Storage | 0.018 | 1/4/2017 | 1/6/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-12-05 14:21 | 1430-RD | Fast Track | Fast Track | In Service | 2/28/2017 |  |  | NEVADA | BRUNSWICK SUB | Solar PV | 1.1048 | 1/4/2017 | 1/26/2017 | Fail Screens: D, F, H, J, K | 2/27/2017 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2016-12-28 13:50 | 1431-RD | Fast Track | Fast Track | Withdrawn | 3/30/2017 | Withdrawn | Withdrawn | KERN | FRUITVALE SUB | Solar PV | 0.03888 | 1/11/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-01-04 14:21 | 1432-RD | Fast Track | Detailed Study | In Service | 3/30/2017 |  |  | KERN | GANSO SUB | Solar PV | 1.956 | 1/11/2017 | 3/30/2017 | Fail Screens: D, F, H, J, K, M | 5/18/2017 | Fail | Pass | 10/18/2017 | N/A | Executed | No former queue position
2016-12-19 14:32 | 1433-RD | Fast Track | Detailed Study | In Service | 3/30/2017 |  |  | MERCED | DOS PALOS SUB | Solar PV | 1.65 | 1/18/2017 | 4/11/2017 | Fail Screens: I, J, K, M | 5/19/2017 | Fail | Pass | 10/11/2017 | N/A | Executed | No former queue position
2017-01-03 15:20 | 1434-RD | Fast Track | Fast Track | In Service | 3/30/2017 |  |  | SAN FRANCISCO | SAN FRAN A (POTRERO PP) SUB | Storage | 0.2 | 1/18/2017 | 1/23/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-01-03 16:17 | 1435-RD | Fast Track | Fast Track | In Service | 3/30/2017 |  |  | SOLANO | VACA DIXON SUB | Storage | 0.018 | 1/18/2017 | 2/14/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-01-03 16:40 | 1436-RD | Fast Track | Fast Track | In Service | 3/30/2017 |  |  | SOLANO | VACA DIXON SUB | Storage | 0.036 | 1/18/2017 | 2/13/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-01-06 15:52 | 1437-RD | Fast Track | Fast Track | Withdrawn | 3/30/2017 | Withdrawn | Withdrawn | SANTA CLARA | MILPITAS SUB | Storage | 0.19 | 1/25/2017 | 2/27/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-12-15 14:35 | 1438-RD | Fast Track | Fast Track | Withdrawn | 2/28/2017 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN A (POTRERO PP) SUB | Cogeneration | 1.5 | 1/25/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-12-23 10:59 | 1439-WD | Independent Study | Independent Study | In Service | 6/4/2018 | 3/15/2019 | 9/5/2018 | SAN LUIS OBISPO | SAN LUIS OBISPO SUB | Engine | 0.853 | 1/25/2017 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 4/17/2017 | N/A | Executed | No former queue position
2017-01-09 13:33 | 1440-WD | Independent Study | Independent Study | Withdrawn | 12/31/2019 | Withdrawn | Withdrawn | MONTEREY | CASTROVILLE SUB | Other | 5 | 1/25/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-01-09 19:52 | 1441-WD | Independent Study | Independent Study | Withdrawn | 12/31/2019 | Withdrawn | Withdrawn | SAN LUIS OBISPO | TEMPLETON SUB | Other | 4 | 1/25/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-01-12 10:43 | 1442-RD | Fast Track | Fast Track | In Service | 3/30/2017 |  |  | SAN MATEO | BAY MEADOWS SUB | Storage | 0.2425 | 1/25/2017 | 2/15/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-01-05 07:22 | 1443-RD | Fast Track | Fast Track | Withdrawn | 3/30/2017 | Withdrawn | Withdrawn | PLUMAS | CHESTER SUB | Cogeneration | 12 | 1/25/2017 | 2/16/2017 | Fail Screens: B, I | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-01-13 16:51 | 1444-WD | Fast Track | Independent Study | Withdrawn | 6/30/2018 | Withdrawn | Withdrawn | SANTA BARBARA | CUYAMA SUB | Solar PV | 1.8 | 2/1/2017 | 2/21/2017 | Fail Screens: 2, 4, 10 | 3/24/2017 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-01-12 16:58 | 1445-RD | Fast Track | Fast Track | Withdrawn | 4/28/2017 | Withdrawn | Withdrawn | SANTA CLARA | MOUNTAIN VIEW SUB | Solar PV,Other | 0.4 | 2/1/2017 | 2/23/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2016-12-23 12:54 | 1446-RD | Detailed Study | Detailed Study | In Service | 3/30/2017 |  |  | SANTA CLARA | AMES DIST SUB | Solar PV | 2.4571 | 2/1/2017 | N/A | N/A | N/A | N/A | Pass | 7/21/2017 | N/A | Executed | No former queue position
2017-12-10 11:07 | 1447-RD | Fast Track | Fast Track | Withdrawn | 9/15/2017 | Withdrawn | Withdrawn | MONTEREY | SALINAS SUB | Solar PV | 1.056 | 2/1/2017 | 3/10/2017 | Fail Screens: G, K, L, M | 5/26/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-01-20 14:03 | 1448-RD | Fast Track | Fast Track | In Service | 4/27/2017 |  |  | SAN LUIS OBISPO | MORRO BAY DIST SUB | Solar PV | 0.01525 | 2/1/2017 | 2/13/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-01-20 18:39 | 1449-RD | Detailed Study | Detailed Study | Withdrawn | 4/28/2017 | Withdrawn | Withdrawn | FRESNO | CAMDEN SUB | Solar PV | 2 | 2/15/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-01-23 19:18 | 1450-RD | Fast Track | Fast Track | In Service | 4/28/2017 |  |  | SAN FRANCISCO | SAN FRAN Z (EMBARCADERO) SUB | Micro Turbine | 0.065 | 2/15/2017 | 3/6/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-01-27 11:34 | 1451-WD | Fast Track | Fast Track | In Service | 12/31/2017 | 5/1/2018 | 10/3/2018 | MERCED | WILSON SUB | Solar PV | 0.25 | 2/15/2017 | 3/3/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-01-31 07:55 | 1452-WD | Fast Track | Independent Study | Withdrawn | 7/31/2019 | Withdrawn | Withdrawn | MADERA | LE GRAND SUB | Solar PV | 3 | 2/15/2017 | 3/6/2017 | Fail Screens: 2, 4, 9, 10 | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-02-02 10:49 | 1453-WD | Fast Track | Independent Study | Withdrawn | 12/28/2018 | Withdrawn | Withdrawn | KINGS | LOST HILLS SUB | Solar PV | 3 | 2/15/2017 | 3/14/2017 | Fail Screens: 2, 4, 9, 10 | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-01-25 17:31 | 1454-RD | Fast Track | Fast Track | In Service | 4/24/2017 |  |  | CONTRA COSTA | KIRKER SUB | Solar PV | 0.48 | 2/22/2017 | 3/21/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-01-27 16:25 | 1455-RD | Fast Track | Fast Track | In Service | 4/25/2017 |  |  | AMADOR | MARTELL SUB | Solar PV | 0.48241 | 2/22/2017 | 3/10/2017 | Fail Screens: D, F, G, J, M | 4/20/2017 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-01-29 14:37 | 1456-RD | Fast Track | Detailed Study | In Service | 4/25/2017 |  |  | MERCED | EL NIDO SUB | Solar PV | 0.95964 | 2/22/2017 | 3/10/2017 | Fail Screens: D, F, H, J, K | 4/13/2017 | Fail | Pass | 7/18/2017 | N/A | Executed | No former queue position
2017-02-01 15:35 | 1457-RD | Fast Track | Fast Track | In Service | 4/28/2017 |  |  | SAN LUIS OBISPO | MORRO BAY DIST SUB | Solar PV | 0.00733 | 2/22/2017 | 3/14/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A | Executed | No former queue position
2017-01-31 23:54 | 1458-RD | Fast Track | Detailed Study | In Service | 4/24/2017 |  |  | FRESNO | WOODWARD SUB | Solar PV | 1.2832 | 2/22/2017 | 4/11/2017 | Fail Screens: D, H, J, K, M | 6/1/2017 | Fail | Pass | 9/28/2017 | N/A | Executed | No former queue position
2017-02-08 16:20 | 1459-RD | Fast Track | Fast Track | Withdrawn | 8/1/2018 | Withdrawn | Withdrawn | YUBA | BANGOR SUB | Hydro | 0.4 | 2/22/2017 | 3/15/2017 | Fail Screens: B, F, G, I, J, K, M | 5/10/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-01-31 20:05 | 1460-RD | Fast Track | Fast Track | In Service | 4/24/2017 |  |  | SANTA CLARA | SWIFT SUB | Storage | 0.12 | 2/22/2017 | 3/14/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-02-02 15:03 | 1461-RD | Fast Track | Fast Track | In Service | 4/28/2017 |  |  | SANTA CLARA | SWIFT SUB | Storage | 0.12 | 2/22/2017 | 3/14/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-02-14 17:54 | 1462-RD | Detailed Study | Detailed Study | In Service | 4/27/2017 |  |  | MONTEREY | LOS OSITOS SUB | Wind | 1.85 | 3/1/2017 | N/A | N/A | N/A | N/A | Pass | 5/16/2017 | N/A | Executed | No former queue position
2017-01-23 08:23 | 1463-RD | Detailed Study | Detailed Study | Withdrawn | 7/3/2017 | Withdrawn | Withdrawn | SAN JOAQUIN | LAMMERS SUB | Biomass | 2.8 | 3/1/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-01-31 16:22 | 1464-RD | Detailed Study | Detailed Study | In Service | 5/30/2017 |  |  | MERCED | EL CAPITAN SUB | Solar PV, Storage | 5.0221 | 3/1/2017 | N/A | N/A | N/A | N/A | Pass | 6/21/2017 | N/A | Executed | No former queue position
2017-01-27 13:55 | 1465-RD | Fast Track | Fast Track | In Service | 4/24/2017 |  |  | SAN LUIS OBISPO | MORRO BAY DIST SUB | Solar PV | 0.02706 | 3/1/2017 | 3/10/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-01-27 15:50 | 1466-RD | Fast Track | Fast Track | In Service | 4/24/2017 |  |  | SAN LUIS OBISPO | MORRO BAY DIST SUB | Solar PV | 0.00453 | 3/1/2017 | 3/6/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-01-31 14:56 | 1467-RD | Fast Track | Fast Track | In Service | 4/24/2017 |  |  | SAN LUIS OBISPO | MORRO BAY DIST SUB | Solar PV | 0.03208 | 3/1/2017 | 3/10/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-01-31 21:44 | 1468-RD | Fast Track | Fast Track | Withdrawn | 4/24/2017 | Withdrawn | Withdrawn | FRESNO | MCMULLIN SUB | Solar PV | 1.5 | 3/1/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-02-07 17:00 | 1469-RD | Fast Track | Detailed Study | Withdrawn | 4/28/2017 | Withdrawn | Withdrawn | KERN | MCKITTRICK SUB | Solar PV | 2 | 3/1/2017 | 6/21/2017 | Fail Screens: D, E, F, H, J, K | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-02-21 11:58 | 1470-RD | Fast Track | Fast Track | In Service | 5/30/2017 |  |  | SANTA CLARA | WHISMAN SUB | Storage | 0.25 | 3/1/2017 | 3/20/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-01-31 22:35 | 1471-RD | Fast Track | Fast Track | In Service | 4/24/2017 | In Service | 12/10/2018 | FRESNO | WAHTOKE SUB | Solar PV | 2.4066 | 3/8/2017 | 3/21/2017 | Fail Screens: D, E, J, K, M | 5/16/2017 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-01-31 22:50 | 1472-RD | Fast Track | Fast Track | In Service | 4/21/2017 | In Service | 7/30/2018 | FRESNO | ASHLAN AVE SUB | Solar PV | 2.1118 | 3/8/2017 | 3/15/2017 | Fail Screens: D, H, J, K, M | 5/10/2017 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-02-07 08:30 | 1473-RD | Fast Track | Fast Track | Withdrawn | 4/27/2017 | Withdrawn | Withdrawn | FRESNO | MANCHESTER SUB | Solar PV | 2.3253 | 3/8/2017 | 4/3/2017 | Fail Screens: J, K, M | 5/2/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-02-16 14:42 | 1474-RD | Fast Track | Fast Track | In Service | 4/27/2017 |  |  | SAN LUIS OBISPO | MORRO BAY DIST SUB | Solar PV | 0.01525 | 3/8/2017 | 3/13/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-02-27 19:03 | 1475-RD | Fast Track | Fast Track | Withdrawn | 5/31/2017 | Withdrawn | Withdrawn | AMADOR | OLETA SUB | Storage | 0.25 | 3/15/2017 | 4/4/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-01-12 00:56 | 1476-RD | Detailed Study | Detailed Study | Withdrawn | 3/30/2017 | Withdrawn | Withdrawn | MONTEREY | SOLEDAD SUB | Wind | 9.6 | 3/15/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-01-31 16:30 | 1477-RD | Fast Track | Fast Track | Withdrawn | 4/24/2017 | Withdrawn | Withdrawn | KERN | MARICOPA SUB | Micro Turbine, Solar PV | 4.66 | 3/15/2017 | 5/11/2017 | Fail Screens: D, E, H, J, K, M | 6/27/2017 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-01-30 12:55 | 1478-RD | Fast Track | Fast Track | Withdrawn | 4/24/2017 | Withdrawn | Withdrawn | SANTA CLARA | LLAGAS SUB | Solar PV | 2 | 3/15/2017 | 3/28/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-02-13 14:06 | 1479-RD | Fast Track | Fast Track | Withdrawn | 4/28/2017 | Withdrawn | Withdrawn | SONOMA | SANTA ROSA A SUB | Engine, Solar PV | 3 | 3/15/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-03-02 14:37 | 1480-RD | Fast Track | Fast Track | Withdrawn | 3/1/2019 | Withdrawn | Withdrawn | KERN | CARNERAS SUB | Solar PV | 3.2 | 3/15/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-03-07 12:07 | 1481-RD | Detailed Study | Detailed Study | In Service | 5/31/2017 |  |  | MERCED | EL CAPITAN SUB | Solar PV, Storage | 0.21 | 3/15/2017 | N/A | N/A | N/A | N/A | Pass | 6/21/2017 | N/A | Executed | No former queue position
2017-03-02 12:00 | 1482-RD | Fast Track | Fast Track | Withdrawn | 5/31/2017 | Withdrawn | Withdrawn | KINGS | KETTLEMAN HILLS SUB | Cogeneration | 0.21 | 3/22/2017 | 4/11/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-03-07 11:05 | 1483-RD | Fast Track | Detailed Study | Active | 5/31/2017 |  |  | FRESNO | DINUBA SUB | Solar PV | 0.21 | 3/22/2017 | 5/1/2017 | Fail Screens: F, I, J, K, M | 6/2/2017 | Fail | Pass | 10/18/2017 | N/A | Executed | No former queue position
2017-03-16 13:26 | 1484-WD | Fast Track | Fast Track | Withdrawn | 4/1/2020 | Withdrawn | Withdrawn | KERN | CARNERAS SUB | Solar PV | 0.21 | 3/22/2017 | 4/12/2017 | Fail Screens: 2, 5, 10 | 5/25/2017 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-03-13 11:05 | 1485-RD | Fast Track | Fast Track | Withdrawn | 5/31/2017 | Withdrawn | Withdrawn | GLENN | ORLAND B SUB | Solar PV | 0.23532 | 3/22/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-03-02 15:06 | 1486-RD | Fast Track | Fast Track | In Service | 5/31/2017 |  |  | HUMBOLDT | FAIRHAVEN SUB | Solar PV | 0.588 | 3/29/2017 | 5/1/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-02-27 11:53 | 1487-RD | Fast Track | Detailed Study | In Service | 5/31/2017 |  |  | MADERA | DAIRYLAND SUB | Solar PV | 0.93 | 3/29/2017 | 4/13/2017 | Fail Screens: D, E, H, J, K, M | 6/20/2017 | Fail | Pass | 3/2/2018 | N/A | Executed | No former queue position
2017-03-22 07:34 | 1488-WD | Fast Track | Fast Track | Withdrawn | 4/1/2020 | Withdrawn | Withdrawn | KERN | BLACKWELL SUB | Solar PV | 2.4 | 3/29/2017 | 4/20/2017 | Fail Screens: 2, 9, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-02-06 15:39 | 1489-RD | Detailed Study | Detailed Study | Withdrawn | 4/28/2017 | Withdrawn | Withdrawn | KERN | BOSWELL SUB | Solar PV | 8 | 4/5/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-02-07 17:22 | 1490-RD | Detailed Study | Detailed Study | Withdrawn | 4/25/2017 | Withdrawn | Withdrawn | KERN | MCKITTRICK SUB | Solar PV | 4.158 | 4/5/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-03-13 17:38 | 1491-RD | Fast Track | Fast Track | Withdrawn | 5/30/2017 | Withdrawn | Withdrawn | SAN JOAQUIN | COUNTRY CLUB SUB | Solar PV | 1.67 | 4/5/2017 | 5/18/2017 | Fail Screens: D, J, K, M | 6/28/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-03-15 18:30 | 1492-RD | Fast Track | Fast Track | Withdrawn | 5/31/2017 | Withdrawn | Withdrawn | PLACER | LINCOLN SUB | Micro Turbine | 0.065 | 4/5/2017 | 5/3/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-03-23 09:31 | 1493-RD | Fast Track | Fast Track | In Service | 5/31/2017 |  |  | SANTA CLARA | STELLING SUB | Storage | 0.0555 | 4/5/2017 | 4/17/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-03-23 09:44 | 1494-RD | Fast Track | Fast Track | In Service | 5/31/2017 |  |  | SANTA CLARA | LOS ALTOS SUB | Storage | 0.08325 | 4/5/2017 | 4/17/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-03-17 16:33 | 1495-RD | Fast Track | Fast Track | Withdrawn | 6/29/2017 | Withdrawn | Withdrawn | SANTA CRUZ | PAUL SWEET SUB | Solar PV | 2.9457 | 4/12/2017 | 4/27/2017 | Fail Screens: D, E, H, J, K, M | 11/7/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-04-06 12:05 | 1496-RD | Fast Track | Fast Track | In Service | 6/28/2017 |  |  | SAN FRANCISCO | SAN FRAN A (POTRERO PP) SUB | Engine, Solar PV | 8.3748 | 4/12/2017 | 5/22/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-04-04 09:51 | 1497-RD | Detailed Study | Detailed Study | Withdrawn | 9/5/2018 | Withdrawn | Withdrawn | KINGS | GUERNSEY SUB | Reciprocating Engine | 1.6 | 4/19/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-04-10 17:39 | 1498-WD | Fast Track | Fast Track | Withdrawn | 3/30/2018 | Withdrawn | Withdrawn | KINGS | CORCORAN SUB | Solar PV | 0.5 | 4/19/2017 | 5/3/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-03-28 07:42 | 1499-WD | Fast Track | Fast Track | Withdrawn | 4/1/2020 | Withdrawn | Withdrawn | KERN | MARICOPA SUB | Solar PV | 1.632 | 4/19/2017 | 5/9/2017 | Fail Screens: 2, 5, 10 | 7/31/2017 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-03-31 11:35 | 1500-WD | Fast Track | Fast Track | Withdrawn | 4/1/2020 | Withdrawn | Withdrawn | KERN | FELLOWS SUB | Solar PV | 1.296 | 4/19/2017 | 5/10/2017 | Fail Screens: 2, 10 | 7/18/2017 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-03-31 11:35 | 1501-WD | Detailed Study | Detailed Study | In Service | 12/1/2018 | 11/8/2019 |  | KERN | TWISSELMAN SUB | Solar PV | 31.3955 | 9/13/2017 | N/A | N/A | N/A | N/A | Pass | 1/25/2018 | N/A | Executed | WDT transition to R21 GIA
2017-03-24 17:36 | 1502-RD | Fast Track | Fast Track | Withdrawn | 6/29/2017 | Withdrawn | Withdrawn | CONTRA COSTA | RICHMOND Q SUB | Storage | 0.216 | 4/26/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-03-27 12:53 | 1503-RD | Fast Track | Fast Track | In Service | 6/29/2017 |  |  | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Storage | 0.036 | 4/26/2017 | 6/26/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-03-30 17:19 | 1504-RD | Detailed Study | Detailed Study | In Service | 6/29/2017 |  |  | SOLANO | PARKWAY SUB | Solar PV | 6.237 | 4/26/2017 | N/A | N/A | N/A | N/A | Pass | 12/13/2017 | N/A | Executed | No former queue position
2017-04-03 16:22 | 1505-WD | Independent Study | Independent Study | Withdrawn | 7/5/2017 | Withdrawn | Withdrawn | MONTEREY | OIL FIELDS SUB | Hydro | 0.601 | 4/26/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-04-10 16:11 | 1506-RD | Fast Track | Fast Track | In Service | 6/28/2017 |  |  | FRESNO | BULLARD SUB | Storage | 0.108 | 4/26/2017 | 6/2/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-03-31 10:19 | 1507-WD | Detailed Study | Detailed Study | Withdrawn | 10/1/2018 | Withdrawn | Withdrawn | KINGS | KETTLEMAN HILLS SUB | Solar PV | 4.05 | 5/3/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | WDT transition to R21 GIA
2017-04-10 13:49 | 1508-RD | Detailed Study | Detailed Study | Withdrawn | 7/14/2017 | Withdrawn | Withdrawn | MONTEREY | KING CITY SUB | Combustion Engine | 2.205 | 5/3/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-04-26 09:46 | 1509-RD | Fast Track | Fast Track | Withdrawn | 7/26/2017 | Withdrawn | Withdrawn | FRESNO | MCMULLIN SUB | Solar PV | 1.6008 | 5/3/2017 | 5/10/2017 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-04-16 15:08 | 1510-WD | Fast Track | Fast Track | Withdrawn | 3/30/2018 | Withdrawn | Withdrawn | CONTRA COSTA | LAKEWOOD SUB | Solar PV | 1.15 | 5/10/2017 | 5/31/2017 | Fail Screens: 2, 5, 7, 9, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-04-18 17:22 | 1511-RD | Detailed Study | Detailed Study | Active | 7/28/2017 |  |  | KERN | LAMONT SUB | Turbine | 5.005 | 5/10/2017 | N/A | N/A | N/A | N/A | Pass | 10/9/2017 | N/A | Executed | No former queue position
2017-04-19 13:16 | 1512-RD | Fast Track | Fast Track | In Service | 7/27/2017 |  |  | SANTA CLARA | SWIFT SUB | Storage | 0.036 | 5/10/2017 | 6/9/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-04-20 11:30 | 1513-RD | Fast Track | Detailed Study | In Service | 7/27/2017 | In Service | 8/24/2018 | KINGS | TULARE LAKE SUB | Solar PV | 1.3768 | 5/10/2017 | 5/30/2017 | Fail Screens: J, K, M | 6/23/2017 | Fail | Pass | 9/20/2017 | N/A | Executed | No former queue position
2017-04-27 09:26 | 1514-RD | Fast Track | Detailed Study | Withdrawn | 7/27/2017 | Withdrawn | Withdrawn | KINGS | GUERNSEY SUB | Solar PV | 2.2 | 5/10/2017 | 10/9/2017 | Fail Screens: H | 10/26/2017 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-04-27 14:07 | 1515-RD | Detailed Study | Detailed Study | In Service | 7/27/2017 |  |  | YOLO | MADISON SUB | Engine, Fuel Cell | 15 | 5/10/2017 | N/A | N/A | N/A | N/A | Pass | 10/13/2017 | N/A | Executed | No former queue position
2017-04-28 16:28 | 1516-RD | Fast Track | Fast Track | Withdrawn | 7/27/2017 | Withdrawn | Withdrawn | FRESNO | KINGSBURG SUB | Solar PV | 1.53 | 5/17/2017 | 6/5/2017 | Fail Screens: J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-05-03 23:39 | 1517-RD | Fast Track | Fast Track | Withdrawn | 7/26/2017 | Withdrawn | Withdrawn | SANTA BARBARA | CUYAMA SUB | Turbine | 0.3 | 5/24/2017 | 6/12/2017 | Fail Screens: D, F, H, J | 10/3/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-04-19 09:07 | 1518-RD | Fast Track | Fast Track | Withdrawn | 7/27/2017 | Withdrawn | Withdrawn | CONTRA COSTA | SOBRANTE SUB | Solar PV | 5.6437 | 5/31/2017 | 6/29/2017 | Fail Screens: D, F, H, J, K | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-04-19 11:39 | 1519-RD | Fast Track | Fast Track | Withdrawn | 7/27/2017 | Withdrawn | Withdrawn | CONTRA COSTA | SOBRANTE SUB | Solar PV | 5.2507 | 5/31/2017 | 7/6/2017 | Fail Screens: D, F, H, J, K | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-05-24 18:12 | 1520-RD | Fast Track | Fast Track | In Service | 8/24/2017 |  |  | SAN FRANCISCO | DALY CITY SUB | Solar PV | 0.24 | 5/31/2017 | 6/14/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-05-22 11:06 | 1521-WD | Fast Track | Independent Study | Withdrawn | 12/28/2018 | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV | 3 | 5/31/2017 | 6/15/2017 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-05-09 10:39 | 1522-RD | Fast Track | Fast Track | In Service | 7/27/2017 |  |  | KERN | Customer Owned | Solar PV | 3.7805 | 6/7/2017 | 8/7/2017 | Fail Screens: D, F, J, K | 9/27/2017 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-05-09 11:32 | 1523-RD | Fast Track | Fast Track | Active | 7/27/2017 |  |  | FRESNO | Customer Owned SE20T | Solar PV | 2.04 | 6/7/2017 | 8/28/2017 | Fail Screens: D, F, J, K | 9/27/2017 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-05-11 15:35 | 1524-RD | Fast Track | Fast Track | In Service | 7/27/2017 |  |  | ALAMEDA | SAN RAMON SUB | Fuel Cell, Solar PV | 0.95788 | 6/7/2017 | 6/26/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-05-16 09:53 | 1525-RD | Fast Track | Fast Track | In Service | 7/27/2017 |  |  | SANTA CLARA | SAN JOSE B SUB | Engine | 0.075 | 6/7/2017 | 6/27/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-05-19 09:38 | 1526-RD | Detailed Study | Detailed Study | In Service | 8/30/2017 |  |  | KERN | WASCO SUB | Solar PV | 1.35 | 6/14/2017 | N/A | N/A | N/A | N/A | Pass | 9/15/2017 | N/A | Executed | No former queue position
2017-06-02 09:09 | 1527-WD | Fast Track | Fast Track | Withdrawn | 1/26/2018 | Withdrawn | Withdrawn | MENDOCINO | COVELO SUB | Solar PV | 0.999 | 6/14/2017 | 7/3/2017 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-05-17 12:26 | 1528-RD | Fast Track | Fast Track | In Service | 8/30/2017 | In Service | 10/18/2018 | SANTA CLARA | MOUNTAIN VIEW SUB | Solar PV, Storage | 1.3291 | 6/21/2017 | 7/10/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-05-31 12:13 | 1529-RD | Fast Track | Detailed Study | Active | 8/31/2017 |  |  | SAN LUIS OBISPO | PASO ROBLES SUB | Solar PV | 3.1894 | 6/21/2017 | 6/29/2017 | Fail Screens: D, F, H, J, K | 8/24/2017 | Fail | Pass | 12/18/2017 | N/A | Executed | No former queue position
2017-05-25 15:14 | 1530-RD | Detailed Study | Detailed Study | Withdrawn | 9/1/2019 | Withdrawn | Withdrawn | MARIPOSA | MARIPOSA SUB | Biomass | 2.4 | 6/21/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-05-04 16:41 | 1531-RD | Fast Track | Fast Track | In Service | 7/28/2017 |  |  | ALAMEDA | LAS POSITAS SUB | Solar PV | 1.2667 | 6/28/2017 | 9/6/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-06-05 18:40 | 1532-WD | Fast Track | Fast Track | Withdrawn | 12/3/2018 | Withdrawn | Withdrawn | FRESNO | MCCALL SUB | Solar PV | 1.6549 | 7/5/2017 | 8/3/2017 | Fail Screens: 2, 10 | 10/11/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-06-15 09:33 | 1533-WD | Independent Study | Independent Study | Withdrawn | 1/1/2020 | Withdrawn | Withdrawn | HUMBOLDT | BLUE LAKE SUB | Cogeneration | 5 | 7/5/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-06-15 14:06 | 1534-RD | Fast Track | Fast Track | Withdrawn | 9/27/2017 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN Z (EMBARCADERO) SUB | Storage | 0.52 | 7/5/2017 | 7/5/2017 | Fail Screens: D, H, J | 8/21/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-06-13 10:16 | 1535-RD | Fast Track | Detailed Study | Withdrawn | 9/27/2017 | Withdrawn | Withdrawn | SONOMA | GEYSERVILLE SUB | Solar PV | 1 | 7/12/2017 | 8/11/2017 | Fail Screens: B, D, F, H, J, K, M | 10/4/2017 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-06-23 15:40 | 1536-RD | Fast Track | Detailed Study | In Service | 12/1/2018 | 6/30/2019 | 5/14/2021 | MADERA | DAIRYLAND SUB | Turbine | 2 | 7/12/2017 | 7/31/2017 | Fail Screens: B, F, I, J, K, M | 9/25/2017 | Fail | Pass | 2/16/2018 | N/A | Executed | No former queue position
2017-06-27 12:24 | 1537-RD | Fast Track | Fast Track | In Service | 9/28/2017 | In Service | 2/26/2020 | SONOMA | FITCH MTN SUB | Solar PV | 1.2027 | 7/12/2017 | 8/2/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-06-20 15:24 | 1538-RD | Fast Track | Detailed Study | In Service | 9/27/2017 |  |  | FRESNO | KINGSBURG SUB | Solar PV, Storage | 2.4879 | 7/12/2017 | 7/28/2017 | Fail Screens: D, J, K, M | 9/1/2017 | Fail | Pass | 12/8/2017 | N/A | Executed | No former queue position
2017-06-26 12:57 | 1539-RD | Fast Track | Fast Track | In Service | 9/27/2017 |  |  | SAN FRANCISCO | SAN FRAN Z (EMBARCADERO) SUB | Storage | 0.1 | 7/19/2017 | 8/4/2017 | Fail Screens: D, H | 9/21/2017 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-06-28 03:58 | 1540-RD | Fast Track | Fast Track | Withdrawn | 9/27/2017 | Withdrawn | Withdrawn | SHASTA | OREGON TRAIL SUB | Storage | 0.0015 | 7/26/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-06-21 12:22 | 1541-RD | Fast Track | Fast Track | In Service | 9/27/2017 |  |  | SONOMA | CORONA SUB | Solar PV | 1.1637 | 7/26/2017 | 10/12/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-07-12 12:08 | 1542-RD | Fast Track | Fast Track | Withdrawn | 9/28/2017 | Withdrawn | Withdrawn | KERN | POSO MTN SUB | Solar PV | 8.1 | 7/26/2017 | 8/1/2017 | Fail Screens: D, F, J, K, M | 8/31/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-07-15 15:24 | 1543-WD | Fast Track | Fast Track | Withdrawn | 7/31/2018 | Withdrawn | Withdrawn | CONTRA COSTA | LAKEWOOD SUB | Solar PV | 0.97515 | 7/26/2017 | 8/15/2017 | Fail Screens: 2, 10 | 11/2/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-07-03 16:14 | 1544-RD | Detailed Study | Detailed Study | In Service | 9/27/2017 |  |  | MONTEREY | BUENA VISTA SUB | Solar PV, Storage | 2.212 | 7/26/2017 | N/A | N/A | N/A | N/A | Pass | 2/12/2018 | N/A | Executed | No former queue position
2017-07-13 14:25 | 1545-RD | Fast Track | Detailed Study | In Service | 9/28/2017 |  |  | MERCED | MERCED SUB | Solar PV | 0.816 | 8/9/2017 | 2/12/2018 | Fail Screens: B, D, F, G, H, I, J, K, M | 4/5/2018 | Fail | Pass | 10/12/2018 | N/A | Executed | No former queue position
2017-07-13 17:09 | 1546-RD | Fast Track | Fast Track | In Service | 9/28/2017 | 9/28/2018 |  | SUTTER | BOGUE SUB | Micro Turbine, Solar PV | 1.45 | 8/9/2017 | 9/15/2017 | Fail Screens: B, D, F, H, J, K, M | 11/22/2017 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-07-14 13:50 | 1547-RD | Fast Track | Detailed Study | In Service | Not Provided |  |  | MONTEREY | GONZALES SUB | Wind | 1.85 | 8/9/2017 | 9/8/2017 | Fail Screens: D, F, H, J, K | 10/13/2017 | Fail | Pass | 2/20/2018 | N/A | Executed | No former queue position
2017-07-27 02:12 | 1548-RD | Fast Track | Fast Track | In Service | 9/29/2017 |  |  | FRESNO | STROUD SUB | Solar PV | 0.868 | 8/9/2017 | 2017-01-09 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-07-05 14:29 | 1549-RD | Fast Track | Fast Track | In Service | 9/27/2017 |  |  | SAN LUIS OBISPO | SAN LUIS OBISPO SUB | Storage | 0.018 | 2017-08-09 | 2017-08-23 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-07-16 16:40 | 1550-RD | Fast Track | Fast Track | Withdrawn | 10/29/2018 | Withdrawn | Withdrawn | SAN JOAQUIN | LAMMERS SUB | Biomass | 2.8 | 8/9/2017 | 8/30/2017 | Fail Screens: B, F, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-07-17 15:35 | 1551-RD | Detailed Study | Detailed Study | Withdrawn | 2/1/2019 | Withdrawn | Withdrawn | KERN | SMYRNA SUB | Reciprocating Engine | 0.995 | 8/9/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-07-17 17:09 | 1552-RD | Fast Track | Fast Track | In Service | 9/28/2017 |  |  | ALAMEDA | DUMBARTON SUB | Storage | 0.03 | 8/9/2017 | 10/3/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-06-14 13:37 | 1553-WD | Fast Track | Fast Track | Withdrawn | 1/26/2018 | Withdrawn | Withdrawn | MENDOCINO | WILLITS A SUB | Solar PV | 0.999 | 8/16/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-07-08 08:29 | 1554-WD | Fast Track | Fast Track | In Service | 10/16/2017 | 5/11/2018 | 10/1/2018 | MARIN | SAN RAFAEL SUB | Solar PV | 0.05999 | 8/16/2017 | 8/30/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-07-28 09:38 | 1555-WD | Independent Study | Independent Study | Withdrawn | 8/30/2018 | Withdrawn | Withdrawn | SONOMA | SONOMA A SUB | Solar PV | 3.5 | 8/16/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-06-26 11:47 | 1556-RD | Fast Track | Fast Track | Withdrawn | 9/27/2017 | Withdrawn | Withdrawn | SOLANO | PEABODY SUB | Solar PV | 1.56 | 8/16/2017 | 9/14/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-07-26 12:24 | 1557-RD | Detailed Study | Detailed Study | Active | 10/27/2017 |  |  | CONTRA COSTA | SOBRANTE SUB | Solar PV | 5 | 8/16/2017 | N/A | N/A | N/A | N/A | Pass | 2/22/2018 | N/A | Executed | No former queue position
2017-08-02 16:11 | 1558-RD | Fast Track | Fast Track | Active | 10/25/2017 |  |  | SAN JOAQUIN | HERDLYN SUB | Solar PV | 1.3242 | 8/16/2017 | 10/10/2017 | Fail Screens: B, F, I, J, K, L, M, S5 | 11/14/2017 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-08-02 16:54 | 1559-RD | Fast Track | Detailed Study | Active | 10/26/2017 |  |  | SAN JOAQUIN | LAMMERS SUB | Solar PV | 1.1587 | 8/16/2017 | 10/10/2017 | Fail Screens: J, K, M | 11/28/2017 | Fail | Pass | 4/14/2018 | N/A | Executed | No former queue position
2017-08-04 12:35 | 1560-RD | Fast Track | Fast Track | In Service | 10/31/2017 |  |  | SANTA CLARA | LLAGAS SUB | Solar PV | 1.2702 | 8/16/2017 | 9/6/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-08-06 09:20 | 1561-WD | Fast Track | Fast Track | In Service | 12/14/2018 | 4/19/2019 | 9/9/2019 | NAPA | HIGHWAY SUB | Solar PV | 0.98304 | 8/23/2017 | 9/13/2017 | Fail Screens: 2, 10 | 11/8/2017 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-08-06 09:23 | 1562-WD | Fast Track | Fast Track | In Service | 12/14/2018 | 4/19/2019 | 9/10/2019 | NAPA | HIGHWAY SUB | Solar PV | 0.99 | 8/23/2017 | 9/13/2017 | Fail Screens: 2, 10 | 11/8/2017 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-08-06 09:25 | 1563-WD | Fast Track | Fast Track | In Service | 12/14/2018 | 4/19/2019 | 9/10/2019 | NAPA | HIGHWAY SUB | Solar PV | 0.99455 | 8/23/2017 | 9/13/2017 | Fail Screens: 2, 10 | 11/8/2017 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-08-08 16:36 | 1564-WD | Fast Track | Fast Track | Withdrawn | 12/15/2018 | Withdrawn | Withdrawn | NAPA | HIGHWAY SUB | Solar PV | 1 | 8/23/2017 | 9/13/2017 | Fail Screens: 2, 5, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-07-26 10:08 | 1565-WD | Fast Track | Independent Study | Withdrawn | 6/1/2018 | Withdrawn | Withdrawn | KERN | SMYRNA SUB | Solar PV | 1 | Complete | 9/12/2017 | Fail Screens: 2, 10 | 11/3/2017 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-08-02 20:35 | 1566-WD | Fast Track | Fast Track | Withdrawn | 4/9/2019 | Withdrawn | Withdrawn | KERN | CARNERAS SUB | Solar PV | 3 | 8/23/2017 | 9/15/2017 | Fail Screens: 2, 9, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-08-07 14:02 | 1567-RD | Fast Track | Fast Track | In Service | 10/25/2017 |  |  | SANTA CLARA | MILPITAS SUB | Storage | 0.2 | 8/23/2017 | 9/8/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-08-08 22:20 | 1568-RD | Fast Track | Fast Track | Withdrawn | 10/25/2017 | Withdrawn | Withdrawn | MARIN | SAN RAFAEL SUB | Cogeneration | 0.01 | 8/23/2017 | 9/13/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-07-26 15:10 | 1569-RD | Fast Track | Detailed Study | In Service | 10/25/2017 |  |  | MADERA | SHARON SUB | Gas Turbine | 2.304 | 8/30/2017 | 9/12/2017 | Fail Screens: D, F, H, J, K | 11/1/2017 | Fail | Pass | 4/13/2018 | N/A | Executed | No former queue position
2017-07-31 14:07 | 1570-RD | Detailed Study | Detailed Study | In Service | 10/25/2017 |  |  | SAN LUIS OBISPO | SAN LUIS OBISPO SUB | Gas Turbine | 2.16 | 8/30/2017 | N/A | N/A | N/A | N/A | Pass | 05/25/2021 | N/A | Executed | No former queue position
2017-08-22 12:26 | 1571-WD | Fast Track | Fast Track | In Service | 6/29/2018 | 6/3/2019 | 10/18/2019 | MENDOCINO | WILLITS A SUB | Gas Turbine | 0.989 | 8/30/2017 | 9/21/2017 | Fail Screens: 2, 9, 10 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-08-10 11:51 | 1572-WD | Fast Track | Fast Track | Withdrawn | 12/14/2018 | Withdrawn | Withdrawn | NAPA | PUEBLO SUB | Gas Turbine | 1 | 8/30/2017 | 9/21/2017 | Fail Screens: 2, 10 | 11/17/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-08-10 11:58 | 1573-WD | Fast Track | Fast Track | Withdrawn | 12/14/2018 | Withdrawn | Withdrawn | NAPA | PUEBLO SUB | Gas Turbine | 1 | 8/30/2017 | 9/21/2017 | Fail Screens: 2, 10 | 11/17/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-08-18 07:56 | 1574-WD | Independent Study | Independent Study | Withdrawn | 12/31/2019 | Withdrawn | Withdrawn | SAN JOAQUIN | TESLA SUB | Solar PV | 20 | 8/30/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-08-14 11:12 | 1575-RD | Fast Track | Fast Track | Withdrawn | 11/29/2017 | Withdrawn | Withdrawn | SANTA BARBARA | DIVIDE SUB | Solar PV | 2.9491 | 9/6/2017 | 9/12/2017 | Fail Screens: D, J, K, M | 10/16/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-08-22 11:22 | 1576-WD | Fast Track | Fast Track | Withdrawn | 6/29/2018 | Withdrawn | Withdrawn | MENDOCINO | COVELO SUB | Solar PV | 0.98304 | 9/6/2017 | 10/4/2017 | Fail Screens: 2, 10 | 12/15/2017 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-08-15 12:06 | 1577-RD | Fast Track | Fast Track | In Service | 11/29/2017 |  |  | SAN MATEO | BAY MEADOWS SUB | Storage | 0.2425 | 9/6/2017 | 9/13/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-08-16 10:05 | 1578-WD | Fast Track | Fast Track | Withdrawn | 11/30/2018 | Withdrawn | Withdrawn | MERCED | DOS PALOS SUB | Solar PV | 1.5 | 9/6/2017 | 9/12/2017 | Fail Screens: 2, 5 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-08-21 15:28 | 1579-RD | Fast Track | Fast Track | In Service | 11/29/2017 |  |  | KINGS | KETTLEMAN HILLS SUB | Micro Turbine | 2 | 9/6/2017 | 9/22/2017 | Fail Screens: D, H, J, K, M | 11/17/2017 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-08-24 15:18 | 1580-WD | Fast Track | Fast Track | Withdrawn | 6/29/2018 | Withdrawn | Withdrawn | SONOMA | LAKEVILLE SUB | Solar PV | 0.98304 | 9/6/2017 | 10/4/2017 | Fail Screens: 2, 5, 10 | 12/18/2017 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-08-24 15:24 | 1581-WD | Fast Track | Fast Track | Withdrawn | 6/29/2018 | Withdrawn | Withdrawn | SONOMA | LAKEVILLE SUB | Solar PV | 0.98304 | 9/6/2017 | 10/4/2017 | Fail Screens: 2, 5, 10 | 12/18/2017 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-08-24 15:31 | 1582-WD | Fast Track | Fast Track | Withdrawn | 6/29/2018 | Withdrawn | Withdrawn | SONOMA | LAKEVILLE SUB | Solar PV | 0.98304 | 9/6/2017 | 10/4/2017 | Fail Screens: 2, 5, 10 | 12/18/2017 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-08-25 10:44 | 1583-RD | Fast Track | Fast Track | In Service | 11/29/2017 |  |  | SONOMA | FULTON SUB | Solar PV | 1.5 | 9/6/2017 | 10/11/2017 | Fail Screens: F, H, J, K, M | 12/5/2017 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-07-31 16:58 | 1584-WD | Fast Track | Independent Study | Withdrawn | 2/28/2019 | Withdrawn | Withdrawn | KERN | DEVILS DEN SUB | Solar PV | 0.991 | 9/13/2017 | 10/4/2017 | Fail Screens: 2, 10 | 12/21/2017 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-07-31 17:02 | 1585-WD | Independent Study | Independent Study | Withdrawn | 2/28/2019 | Withdrawn | Withdrawn | FRESNO | GATES SUB | Solar PV | 4.5518 | 9/13/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-07-31 17:04 | 1586-WD | Fast Track | Independent Study | Withdrawn | 2/28/2019 | Withdrawn | Withdrawn | FRESNO | COALINGA #1 SUB | Solar PV | 1.62 | 9/13/2017 | 10/4/2017 | Fail Screens: 2, 4, 10 | 12/11/2017 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-08-01 10:06 | 1587-WD | Fast Track | Independent Study | Withdrawn | 2/28/2019 | Withdrawn | Withdrawn | FRESNO | COALINGA #2 SUB | Solar PV | 1.8965 | 9/13/2017 | 10/4/2017 | Fail Screens: 2, 4, 10 | 12/11/2017 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-08-04 14:00 | 1588-WD | Independent Study | Independent Study | Withdrawn | 2/28/2019 | Withdrawn | Withdrawn | KERN | COALINGA #2 SUB | Solar PV | 4.5518 | 9/13/2017 | N/A | N/A (Independent Study) | Withdrawn | Withdrawn | Pass | 2018-08-30 | Withdrawn | Withdrawn | No former queue position
2017-08-16 14:55 | 1589-WD | Fast Track | Independent Study | Withdrawn | 2/28/2019 | Withdrawn | Withdrawn | KERN | BLACKWELL SUB | Solar PV | 2.5838 | 9/13/2017 | 10/4/2017 | Pass | 12/11/2017 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-08-23 14:04 | 1590-WD | Fast Track | Fast Track | Withdrawn | 12/20/2017 | Withdrawn | Withdrawn | MARIN | STAFFORD SUB | Solar PV | 0.45 | 9/13/2017 | 10/9/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-09-07 16:17 | 1591-RD | Fast Track | Fast Track | Active | 11/28/2017 |  |  | ALAMEDA | OAKLAND L SUB | Solar PV | 0.01445 | 9/13/2017 | 9/28/2017 | Fail Screens: A | 12/6/2017 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-08-25 15:10 | 1592-RD | Fast Track | Fast Track | In Service | 11/29/2017 | In Service | 9/25/2019 | SAN JOAQUIN | CHANNEL SUB | Fuel Cell, Solar PV | 1.24 | 9/13/2017 | 10/2/2017 | Fail Screens: J, K, M | 12/13/2017 | Fail | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-08-31 16:37 | 1593-RD | Fast Track | Detailed Study | In Service | 11/28/2017 |  |  | KERN | LAKEVIEW SUB | Solar PV | 1.375 | 9/20/2017 | 10/9/2017 | Fail Screens: D, F, H, J, K, M | 11/14/2017 | Fail | Pass | 3/27/2018 | N/A | Executed | No former queue position
2017-08-11 21:29 | 1594-RD | Fast Track | Fast Track | In Service | 11/29/2017 |  |  | SONOMA | SANTA ROSA A SUB | Engine, Solar PV, Storage | 3.5188 | 9/20/2017 | 3/9/2018 | Pass | 4/23/2018 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-09-05 13:46 | 1595-RD | Fast Track | Fast Track | In Service | 11/29/2017 |  |  | ALAMEDA | NEWARK SUB | Storage | 0.2425 | 9/20/2017 | 10/10/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-09-01 12:00 | 1596-RD | Fast Track | Detailed Study | Withdrawn | 11/29/2017 | Withdrawn | Withdrawn | SAN LUIS OBISPO | TEMPLETON SUB | Solar PV | 1.68 | 9/20/2017 | 11/8/2017 | Fail Screens: D, F, H, J, K | 12/21/2017 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-09-07 17:24 | 1597-WD | Fast Track | Fast Track | In Service | 7/29/2018 | 5/17/2019 | 6/17/2020 | MARIN | LAS GALLINAS A SUB | Solar PV | 0.972 | 9/20/2017 | 10/18/2017 | Fail Screens: 2, 5, 9, 10 | 1/5/2018 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-08-18 16:42 | 1598-RD | Fast Track | Fast Track | In Service | 11/29/2017 |  |  | SAN JOAQUIN | MANTECA SUB | Storage | 0.036 | 9/27/2017 | 10/13/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-08-18 17:04 | 1599-RD | Fast Track | Fast Track | In Service | 11/29/2017 |  |  | CONTRA COSTA | LONE TREE SUB | Storage | 0.036 | 9/27/2017 | 12/8/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-08-21 18:16 | 1600-RD | Fast Track | Fast Track | In Service | 11/29/2017 |  |  | SANTA CLARA | NORTECH SUB | Storage | 0.036 | 9/27/2017 | 10/11/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-08-22 13:02 | 1601-RD | Fast Track | Fast Track | In Service | 11/29/2017 |  |  | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Storage | 0.054 | 9/27/2017 | 10/3/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-08-22 13:20 | 1602-RD | Fast Track | Fast Track | In Service | 11/29/2017 |  |  | SAN FRANCISCO | SAN FRAN P(HUNTERS POINT) SUB | Storage | 0.018 | 9/27/2017 | 10/10/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-08-22 13:28 | 1603-RD | Fast Track | Fast Track | Withdrawn | 11/29/2017 | Withdrawn | Withdrawn | SANTA CLARA | MOUNTAIN VIEW SUB | Storage | 0.216 | 9/27/2017 | 10/16/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-08-22 13:35 | 1604-RD | Fast Track | Fast Track | In Service | 11/29/2017 |  |  | SOLANO | DIXON SUB | Storage | 0.108 | 9/27/2017 | 10/17/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-08-22 13:52 | 1605-RD | Fast Track | Fast Track | Withdrawn | 11/29/2017 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Storage | 0.018 | 9/27/2017 | 10/17/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-09-06 18:18 | 1606-RD | Fast Track | Fast Track | In Service | 11/28/2017 |  |  | SAN JOAQUIN | FRENCH CAMP SUB | Storage | 0.036 | 9/27/2017 | 10/6/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-09-06 22:35 | 1607-RD | Fast Track | Fast Track | In Service | 11/29/2017 |  |  | SAN JOAQUIN | FRENCH CAMP SUB | Storage | 0.108 | 9/27/2017 | 10/6/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-09-06 22:45 | 1608-RD | Fast Track | Fast Track | In Service | 11/29/2017 |  |  | FRESNO | BARTON SUB | Storage | 0.018 | 9/27/2017 | 10/30/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-09-06 22:54 | 1609-RD | Fast Track | Fast Track | In Service | 11/29/2017 |  |  | FRESNO | BARTON SUB | Storage | 0.018 | 9/27/2017 | 10/30/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-09-08 11:43 | 1610-RD | Fast Track | Fast Track | In Service | 11/29/2017 |  |  | SANTA CLARA | NORTECH SUB | Storage | 0.054 | 9/27/2017 | 10/11/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-09-14 11:45 | 1611-RD | Fast Track | Detailed Study | Withdrawn | 11/29/2017 | Withdrawn | Withdrawn | TULARE | DINUBA SUB | Solar PV | 1.55 | 9/27/2017 | 2/2/2018 | Fail Screens: F, I, J, K, M | 3/6/2018 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-09-14 16:24 | 1612-WD | Fast Track | Independent Study | Withdrawn | 6/30/2019 | Withdrawn | Withdrawn | SAN LUIS OBISPO | TEMPLETON SUB | Solar PV | 0.5 | 9/27/2017 | 10/16/2017 | Fail Screens: 2, 5, 6, 10 | 11/14/2017 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-09-21 16:31 | 1613-RD | Fast Track | Fast Track | Withdrawn | 11/22/2017 | Withdrawn | Withdrawn | ALAMEDA | OAKLAND L SUB | Solar PV | 0.00993 | 9/27/2017 | 10/19/2017 | Fail Screens: D | 1/4/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-08-21 11:03 | 1614-RD | Detailed Study | Detailed Study | Active | 11/29/2017 |  |  | SAN FRANCISCO | SAN FRAN H (MARTIN) SUB | Engine | 1.899 | 9/27/2017 | N/A | N/A | N/A | N/A | Pass | 1/12/2018 | N/A | Executed | No former queue position
2017-09-13 13:36 | 1615-RD | Fast Track | Fast Track | In Service | 11/29/2017 |  |  | MARIN | SAN RAFAEL SUB | Solar PV | 1.0345 | 9/27/2017 | 10/23/2017 | Fail Screens: D, H, J, K, M | 1/2/2018 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-08-03 16:07 | 1616-RD | Detailed Study | Detailed Study | Withdrawn | 10/25/2017 | Withdrawn | Withdrawn | CONTRA COSTA | SOBRANTE SUB | Solar PV | 5 | 9/27/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-08-17 07:01 | 1617-RD | Detailed Study | Detailed Study | Withdrawn | 6/12/2019 | Withdrawn | Withdrawn | SHASTA | PIT #1 PH | Other | 10 | 9/27/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-08-30 14:08 | 1618-RD | Fast Track | Fast Track | Withdrawn | 11/29/2017 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Micro Turbine | 0.075 | 9/27/2017 | 10/16/2017 | Fail Screens: H | 12/14/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-09-11 11:28 | 1619-WD | Fast Track | Fast Track | Withdrawn | 4/30/2018 | Withdrawn | Withdrawn | SONOMA | MOLINO SUB | Solar PV | 1 | 9/27/2017 | 11/17/2017 | Fail Screens: 2, 4, 5, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-09-08 11:40 | 1620-WD | Fast Track | Independent Study | Active | 12/31/2018 | 8/21/2020 |  | KERN | ELK HILLS SUB | Solar PV | 3 | 10/4/2017 | 10/23/2017 | Fail Screens: 2, 4, 10 | 12/19/2017 | Fail | Pass | 5/22/2018 | 8/24/2018 | Executed | No former queue position
2017-09-20 16:03 | 1621-RD | Fast Track | Fast Track | Withdrawn | 11/22/2017 | Withdrawn | Withdrawn | YOLO | PLAINFIELD SUB | Solar PV | 1.116 | 10/4/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-09-07 18:17 | 1622-WD | Independent Study | Independent Study | Withdrawn | 12/31/2019 | Withdrawn | Withdrawn | KINGS | JOLON SUB | Solar PV | 20.496 | 10/11/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-09-19 09:02 | 1623-RD | Detailed Study | Detailed Study | Withdrawn | 4/17/2019 | Withdrawn | Withdrawn | KINGS | GUERNSEY SUB | Cogeneration | 0.995 | 10/11/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-09-25 15:41 | 1624-WD | Fast Track | Independent Study | Withdrawn | 6/29/2018 | Withdrawn | Withdrawn | ALAMEDA | CAYETANO SUB | Solar PV | 3 | 10/11/2017 | 11/7/2017 | Fail Screens: 2, 4, 9, 10 | 1/31/2018 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-09-25 16:04 | 1625-WD | Fast Track | Fast Track | Withdrawn | 6/29/2018 | Withdrawn | Withdrawn | ALAMEDA | HERDLYN SUB | Solar PV | 1 | 10/11/2017 | 10/31/2017 | Fail Screens: 2, 4, 10 | 2/6/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-09-26 15:44 | 1626-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | SANTA CLARA | LAWRENCE SUB | Storage | 0.00426 | 10/11/2017 | 10/31/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-09-19 12:49 | 1627-RD | Fast Track | Detailed Study | Withdrawn | 5/9/2018 | Withdrawn | Withdrawn | COLUSA | COLUSA JUNCTION | Other | 3.044 | 10/11/2017 | 10/30/2017 | Fail Screens: B, F, I, J, K, M | 12/29/2017 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-09-21 18:20 | 1628-RD | Fast Track | Detailed Study | Withdrawn | 5/7/2018 | Withdrawn | Withdrawn | GLENN | JACINTO SUB | Turbine | 0.99 | 10/11/2017 | 10/19/2017 | Fail Screens: B, I, J, K, M | 12/18/2017 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-09-29 17:34 | 1629-RD | Fast Track | Detailed Study | Withdrawn | 12/28/2017 | Withdrawn | Withdrawn | KERN | FELLOWS SUB | Solar PV | 0.8325 | 10/18/2017 | 11/8/2017 | Fail Screens: D, F, H, J, K, M | 12/11/2017 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-09-27 13:16 | 1630-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | SAN MATEO | SAN CARLOS SUB | Storage | 0.01 | 10/18/2017 | 11/7/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-09-27 13:30 | 1631-RD | Fast Track | Fast Track | In Service | 12/27/2017 |  |  | SANTA CLARA | STELLING SUB | Storage | 0.005 | 10/18/2017 | 11/27/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-09-27 14:53 | 1632-RD | Detailed Study | Detailed Study | Withdrawn | 12/28/2017 | Withdrawn | Withdrawn | KINGS | AVENAL SUB | Solar PV | 2.0029 | 10/18/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-09-28 12:14 | 1633-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | SANTA CLARA | MORGAN HILL SUB | Storage | 0.01 | 10/25/2017 | 11/6/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-12 12:53 | 1634-WD | Fast Track | Fast Track | Withdrawn | 4/2/2018 | Withdrawn | Withdrawn | TULARE | SMYRNA SUB | Other | 2 | 10/25/2017 | 11/15/2017 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-10-06 18:37 | 1635-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | CONTRA COSTA | SAN RAMON SUB | Storage | 0.005 | 11/1/2017 | 11/9/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-06 19:11 | 1636-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | SANTA CLARA | LOYOLA SUB | Storage | 0.005 | 11/1/2017 | 11/13/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-09 15:57 | 1637-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | CONTRA COSTA | BRYANT SUB | Storage | 0.005 | 11/1/2017 | 11/27/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 12:55 | 1638-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | SANTA CLARA | MENLO SUB | Storage | 0.01 | 11/1/2017 | 11/17/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 13:15 | 1639-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | CONTRA COSTA | TASSAJARA SUB | Storage | 0.005 | 11/1/2017 | 11/27/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 16:20 | 1640-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | ALAMEDA | CASTRO VALLEY SUB | Storage | 0.01 | 11/1/2017 | 11/13/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 16:46 | 1641-RD | Fast Track | Fast Track | Withdrawn | 12/28/2017 | Withdrawn | Withdrawn | MONTEREY | BUENA VISTA SUB | Storage | 0.01 | 11/1/2017 | 12/5/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-10-20 15:21 | 1642-WD | Fast Track | Independent Study | Active | 6/30/2018 | 11/15/2019 |  | SANTA BARBARA | CUYAMA SUB | Solar PV | 3 | 11/1/2017 | 11/20/2017 | Fail Screens: 2, 10 | N/A | N/A (Independent Study) | Pass | 3/20/2018 | N/A | Executed | No former queue position
2017-10-10 09:41 | 1643-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | CONTRA COSTA | TASSAJARA SUB | Storage | 0.015 | 11/1/2017 | 11/17/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 10:02 | 1644-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | SAN MATEO | SERRAMONTE SUB | Storage | 0.01 | 11/1/2017 | 11/8/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 11:04 | 1645-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | MARIN | WOODACRE SUB | Storage | 0.02 | 11/1/2017 | 11/17/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 11:06 | 1646-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | NAPA | PUEBLO SUB | Storage | 0.01 | 11/1/2017 | 12/1/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 11:08 | 1647-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | ALAMEDA | EL CERRITO G SUB | Storage | 0.005 | 11/1/2017 | 11/6/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 11:36 | 1648-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | MARIN | COTATI SUB | Storage | 0.005 | 11/1/2017 | 12/1/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 13:02 | 1649-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | MARIN | GREENBRAE SUB | Storage | 0.02 | 11/1/2017 | 11/27/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 16:26 | 1650-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | ALAMEDA | CASTRO VALLEY SUB | Storage | 0.01 | 11/1/2017 | 11/22/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-12 14:18 | 1651-RD | Fast Track | Fast Track | Withdrawn | 12/28/2017 | Withdrawn | Withdrawn | ALAMEDA | DUMBARTON SUB | Storage | 0.005 | 11/1/2017 | 11/17/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-10-10 11:23 | 1652-RD | Fast Track | Fast Track | Withdrawn | 12/28/2017 | Withdrawn | Withdrawn | ALAMEDA | VINEYARD SUB | Storage | 0.015 | 11/8/2017 | 11/22/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-10-10 11:36 | 1653-RD | Fast Track | Fast Track | Withdrawn | 12/28/2017 | Withdrawn | Withdrawn | ALAMEDA | CASTRO VALLEY SUB | Storage | 0.01 | 11/8/2017 | 11/22/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-10-16 09:56 | 1654-RD | Fast Track | Fast Track | In Service | 1/30/2018 |  |  | MARIN | SAN RAFAEL SUB | Storage | 0.005 | 11/8/2017 | 11/30/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-18 11:56 | 1655-RD | Fast Track | Fast Track | In Service | 1/30/2018 |  |  | BUTTE | BUTTE SUB | Storage | 0.005 | 11/8/2017 | 11/9/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-18 13:34 | 1656-RD | Fast Track | Fast Track | In Service | 1/30/2018 |  |  | SANTA CLARA | SARATOGA SUB | Storage | 0.005 | 11/8/2017 | 11/20/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-09-26 08:12 | 1657-RD | Fast Track | Fast Track | Withdrawn | 3/3/2018 | Withdrawn | Withdrawn | SONOMA | SONOMA A SUB | Solar PV | 0.018 | 11/8/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-09-27 13:44 | 1658-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Storage | 0.01 | 11/8/2017 | 11/9/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 09:29 | 1659-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | SAN MATEO | MENLO SUB | Storage | 0.005 | 11/8/2017 | 11/9/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 09:43 | 1660-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | ALAMEDA | CASTRO VALLEY SUB | Storage | 0.01 | 11/8/2017 | 11/27/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 10:05 | 1661-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | CONTRA COSTA | TASSAJARA SUB | Storage | 0.015 | 11/8/2017 | 12/26/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 10:12 | 1662-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | SAN LUIS OBISPO | SAN LUIS OBISPO SUB | Storage | 0.005 | 11/8/2017 | 11/10/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 10:17 | 1663-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | SAN MATEO | WOODSIDE SUB | Storage | 0.01 | 11/8/2017 | 1/29/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 10:29 | 1664-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | TUOLUMNE | MI-WUK SUB | Storage | 0.01 | 11/8/2017 | 11/27/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 10:35 | 1665-RD | Fast Track | Fast Track | Withdrawn | 12/28/2017 | Withdrawn | Withdrawn | NAPA | PUEBLO SUB | Storage | 0.005 | 11/8/2017 | 11/27/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-10-10 10:37 | 1666-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | SAN MATEO | SNEATH LANE SUB | Storage | 0.02 | 11/8/2017 | 12/7/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 10:42 | 1667-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | MONTEREY | DEL MONTE SUB | Storage | 0.01 | 11/8/2017 | 11/29/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 11:53 | 1668-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | CONTRA COSTA | TASSAJARA SUB | Storage | 0.005 | 11/8/2017 | 11/27/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 11:36 | 1669-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | SANTA CLARA | SARATOGA SUB | Storage | 0.005 | 11/8/2017 | 11/27/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 12:12 | 1670-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | ALAMEDA | LIVERMORE SUB | Storage | 0.01 | 11/8/2017 | 11/27/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 12:29 | 1671-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | SANTA CRUZ | LOS GATOS SUB | Storage | 0.01 | 11/8/2017 | 11/27/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 13:20 | 1672-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | SANTA CLARA | MORGAN HILL SUB | Storage | 0.005 | 11/8/2017 | 11/27/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 13:48 | 1673-RD | Fast Track | Fast Track | In Service | 12/27/2017 |  |  | SAN FRANCISCO | DALY CITY SUB | Storage | 0.01 | 11/8/2017 | 12/4/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 13:59 | 1674-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | EL DORADO | CLARKSVILLE SUB | Storage | 0.01 | 11/8/2017 | 12/7/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 14:07 | 1675-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | SANTA CRUZ | BIG BASIN SUB | Storage | 0.01 | 11/8/2017 | 12/27/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 14:17 | 1676-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | MARIN | SAUSALITO SUB | Storage | 0.015 | 11/8/2017 | 12/26/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 15:06 | 1677-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | SANTA CLARA | LOYOLA SUB | Storage | 0.01 | 11/8/2017 | 12/26/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 16:48 | 1678-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | SAN MATEO | GLENWOOD SUB | Storage | 0.01 | 11/8/2017 | 12/13/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-11 14:24 | 1679-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | SANTA CLARA | FOOTHILL SUB | Storage | 0.005 | 11/8/2017 | 12/20/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-11 15:57 | 1680-RD | Fast Track | Fast Track | Withdrawn | 12/28/2017 | Withdrawn | Withdrawn | SANTA CLARA | MCKEE SUB | Storage | 0.01 | 11/8/2017 | 12/19/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-10-10 10:09 | 1681-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | MARIN | WOODACRE SUB | Storage | 0.005 | 11/8/2017 | 1/3/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-13 08:41 | 1682-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | SANTA CLARA | HICKS SUB | Storage | 0.01 | 11/8/2017 | 12/19/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-17 16:51 | 1683-WD | Fast Track | Fast Track | Withdrawn | 11/30/2018 | Withdrawn | Withdrawn | MERCED | DOS PALOS SUB | Solar PV | 2 | 11/8/2017 | 2/21/2018 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-10-10 12:38 | 1684-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | SANTA CLARA | STELLING SUB | Storage | 0.005 | 11/15/2017 | 12/27/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 17:15 | 1685-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | SANTA CLARA | EL PATIO SUB | Storage | 0.005 | 11/15/2017 | 12/27/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-11 15:37 | 1686-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | TEHAMA | RED BLUFF SUB | Storage | 0.005 | 11/15/2017 | 12/12/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-18 13:21 | 1687-RD | Fast Track | Fast Track | In Service | 1/31/2018 |  |  | SANTA BARBARA | SANTA MARIA SUB | Engine | 2.852 | 11/15/2017 | 11/29/2017 | Fail Screens: D, J, K, M | 2/23/2018 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-20 15:45 | 1688-RD | Fast Track | Fast Track | Withdrawn | 1/30/2018 | Withdrawn | Withdrawn | ALAMEDA | CASTRO VALLEY SUB | Storage | 0.01 | 11/15/2017 | 12/27/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-10-20 16:06 | 1689-RD | Fast Track | Fast Track | In Service | 1/30/2018 |  |  | MONTEREY | VIEJO SUB | Storage | 0.01 | 11/15/2017 | 11/29/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-25 16:58 | 1690-RD | Fast Track | Fast Track | Withdrawn | 1/31/2018 | Withdrawn | Withdrawn | SAN LUIS OBISPO | MESA SUB | Solar PV | 0.54 | 11/15/2017 | 12/8/2017 | Fail Screens: D, F, G, I, J, K, M | 1/31/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-10-23 21:07 | 1691-RD | Fast Track | Fast Track | Withdrawn | 4/30/2018 | Withdrawn | Withdrawn | YOLO | MADISON SUB | Hydro | 0.037 | 11/15/2017 | 12/5/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-10-18 09:42 | 1692-RD | Fast Track | Fast Track | In Service | 1/30/2018 |  |  | SAN MATEO | BAY MEADOWS SUB | Storage | 0.01 | 11/15/2017 | 12/4/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-20 15:52 | 1693-RD | Fast Track | Fast Track | In Service | 1/30/2018 |  |  | SAN FRANCISCO | SAN FRAN E SUB | Storage | 0.005 | 11/15/2017 | 11/28/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-24 16:02 | 1694-RD | Fast Track | Fast Track | Withdrawn | 1/30/2018 | Withdrawn | Withdrawn | SANTA CLARA | HICKS SUB | Storage | 0.03 | 11/15/2017 | 12/4/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-10-26 10:35 | 1695-RD | Fast Track | Fast Track | In Service | 1/31/2018 |  |  | MARIN | OLEMA SUB | Storage | 0.005 | 11/15/2017 | 12/26/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-11-01 17:38 | 1696-RD | Fast Track | Fast Track | In Service | 1/24/2018 |  |  | MONTEREY | RESERVATION ROAD | Storage | 0.01 | 11/15/2017 | 12/5/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-11-03 10:17 | 1697-RD | Fast Track | Fast Track | In Service | 1/31/2018 |  |  | NAPA | CALISTOGA SUB | Storage | 0.015 | 11/15/2017 | 12/7/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 12:32 | 1698-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | SAN MATEO | HALF MOON BAY SUB | Storage | 0.005 | 11/22/2017 | 11/28/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-11 14:56 | 1699-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | SAN FRANCISCO | SAN FRAN M SUB | Storage | 0.005 | 11/22/2017 | 12/12/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-18 11:26 | 1700-RD | Fast Track | Fast Track | In Service | 1/30/2018 |  |  | MONTEREY | VIEJO SUB | Storage | 0.01 | 11/22/2017 | 3/14/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-19 10:02 | 1701-RD | Fast Track | Fast Track | In Service | 1/30/2018 |  |  | SANTA CLARA | LLAGAS SUB | Storage | 0.133 | 11/22/2017 | 1/4/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-19 17:37 | 1702-RD | Fast Track | Fast Track | In Service | 1/30/2018 |  |  | SANTA CLARA | LLAGAS SUB | Storage | 0.133 | 11/22/2017 | 1/4/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-20 16:28 | 1703-RD | Fast Track | Fast Track | Withdrawn | 1/30/2018 | Withdrawn | Withdrawn | SANTA CLARA | SARATOGA SUB | Storage | 0.01 | 11/22/2017 | 12/27/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-10-10 14:23 | 1704-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | NAPA | PUEBLO SUB | Storage | 0.01 | 11/22/2017 | 11/28/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-12 14:06 | 1705-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | MONTEREY | VIEJO SUB | Storage | 0.01 | 11/22/2017 | 12/14/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-12 15:06 | 1706-RD | Fast Track | Fast Track | Withdrawn | 12/28/2017 | Withdrawn | Withdrawn | SAN MATEO | OTTER SUB | Storage | 0.01 | 11/22/2017 | 12/20/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-10-11 10:07 | 1707-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | SANTA CLARA | CAMP EVERS SUB | Storage | 0.01 | 11/22/2017 | 12/11/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-25 14:23 | 1708-RD | Fast Track | Fast Track | In Service | 1/31/2018 |  |  | ALAMEDA | OAKLAND D SUB | Storage | 0.005 | 11/22/2017 | 12/19/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-31 06:21 | 1709-RD | Detailed Study | Detailed Study | Withdrawn | 1/30/2018 | Withdrawn | Withdrawn | SOLANO | BRIDGEVILLE SUB | Solar PV | 2.55 | 11/22/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-11-06 20:10 | 1710-RD | Fast Track | Fast Track | Withdrawn | 5/1/2019 | Withdrawn | Withdrawn | MONTEREY | SOLEDAD SUB | Wind | 2.5 | 11/22/2017 | 12/14/2017 | Fail Screens: B, F, G, H, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-11-13 17:04 | 1711-RD | Detailed Study | Detailed Study | Withdrawn | 6/3/2019 | Withdrawn | Withdrawn | BUTTE | PEACHTON SUB | Engine | 3.6 | 11/22/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-10-18 10:37 | 1712-RD | Fast Track | Fast Track | In Service | 1/30/2018 |  |  | CONTRA COSTA | ROSSMOOR SUB | Storage | 0.01 | 11/29/2017 | 1/2/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-18 13:51 | 1713-RD | Fast Track | Fast Track | In Service | 1/30/2018 |  |  | SAN FRANCISCO | SAN FRAN H (MARTIN) SUB | Storage | 0.005 | 11/29/2017 | 12/19/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-11-01 21:23 | 1714-WD | Fast Track | Fast Track | Withdrawn | 3/5/2018 | Withdrawn | Withdrawn | SONOMA | SONOMA A SUB | Other | 0.5 | 11/29/2017 | 12/20/2017 | Fail Screens: 2, 7, 10 | 3/13/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-11-07 10:15 | 1715-RD | Fast Track | Fast Track | Withdrawn | 1/30/2018 | Withdrawn | Withdrawn | CONTRA COSTA | WALDO SUB | Storage | 0.005 | 11/29/2017 | 12/19/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-11-07 10:40 | 1716-RD | Fast Track | Fast Track | In Service | 1/30/2018 |  |  | SANTA CLARA | LLAGAS SUB | Storage | 0.015 | 11/29/2017 | 12/12/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-11-07 15:11 | 1717-RD | Fast Track | Fast Track | In Service | 1/30/2018 |  |  | SANTA CLARA | LOS GATOS SUB | Storage | 0.01 | 11/29/2017 | 1/3/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-11-09 08:44 | 1718-RD | Fast Track | Fast Track | In Service | 1/30/2018 |  |  | MONTEREY | MONTEREY SUB | Storage | 0.01 | 11/29/2017 | 12/13/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-11-20 16:09 | 1719-RD | Fast Track | Fast Track | In Service | 2/27/2018 |  |  | ALAMEDA | BERKELEY F SUB | Solar PV | 0.06848 | 11/29/2017 | 2/26/2018 | Fail Screens: D, F, H, J |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-11-13 15:09 | 1720-RD | Fast Track | Fast Track | In Service | 1/31/2018 |  |  | SANTA CLARA | VASONA SUB | Storage | 0.015 | 12/6/2017 | 12/22/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-11-15 10:38 | 1721-RD | Fast Track | Fast Track | In Service | 1/31/2018 |  |  | SOLANO | BAHIA SUB | Storage | 0.01 | 12/6/2017 | 1/3/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-10 13:45 | 1722-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | CONTRA COSTA | MORAGA SUB | Storage | 0.005 | 12/6/2017 | 12/26/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-11-14 10:59 | 1723-RD | Fast Track | Fast Track | In Service | 1/30/2018 |  |  | SAN FRANCISCO | SAN FRAN H (MARTIN) SUB | Storage | 0.005 | 12/6/2017 | 12/13/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-11-16 11:12 | 1724-RD | Fast Track | Fast Track | Withdrawn | 2/27/2018 | Withdrawn | Withdrawn | SAN LUIS OBISPO | SAN LUIS OBISPO SUB | Storage | 0.005 | 12/6/2017 | 12/14/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-11-21 07:28 | 1725-RD | Fast Track | Fast Track | In Service | 2/28/2018 |  |  | SAN LUIS OBISPO | CAYUCOS SUB | Solar PV | 0.01139 | 12/6/2017 | 1/3/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-11-27 10:40 | 1726-WD | Independent Study | Independent Study | Active | 2/28/2019 | 6/1/2020 |  | KERN | TWISSELMAN SUB | Solar PV | 5.1675 | 12/6/2017 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 5/9/2018 | N/A | Executed | No former queue position
2017-11-28 15:14 | 1727-RD | Fast Track | Fast Track | In Service | 2/27/2018 |  |  | FRESNO | WAHTOKE SUB | Storage | 0.13 | 12/6/2017 | 12/19/2017 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-11-15 12:52 | 1728-RD | Detailed Study | Detailed Study | Withdrawn | 8/10/2018 | Withdrawn | Withdrawn | SUTTER | LIVE OAK SUB | Engine | 3.3632 | 12/13/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-10-11 07:36 | 1729-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | MARIN | WOODACRE SUB | Storage | 0.01 | 12/13/2017 | 1/3/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-10-11 10:26 | 1730-RD | Fast Track | Fast Track | In Service | 12/28/2017 |  |  | SAN MATEO | HALF MOON BAY SUB | Storage | 0.015 | 12/13/2017 | 1/3/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-11-01 11:27 | 1731-WD | Fast Track | Fast Track | Withdrawn | 5/2/2018 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN H (MARTIN) SUB | Solar PV | 0.142 | 12/13/2017 | 12/27/2017 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-11-07 09:56 | 1732-RD | Fast Track | Fast Track | In Service | 1/31/2018 |  |  | SANTA CRUZ | BIG BASIN SUB | Storage | 0.01 | 12/13/2017 | 1/24/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-11-16 11:38 | 1733-RD | Fast Track | Fast Track | In Service | 2/27/2018 |  |  | SANTA CRUZ | BIG BASIN SUB | Storage | 0.005 | 12/13/2017 | 1/24/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-11-17 17:55 | 1734-RD | Fast Track | Fast Track | In Service | 2/27/2018 |  |  | CONTRA COSTA | SOBRANTE SUB | Storage | 0.005 | 12/13/2017 | 1/9/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-11-22 16:18 | 1735-RD | Fast Track | Fast Track | Withdrawn | 2/27/2018 | Withdrawn | Withdrawn | MONTEREY | DOLAN RD SUB | Solar PV | 2.75 | 12/13/2017 | 1/3/2018 | Fail Screens: D, H | 3/12/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-11-28 11:33 | 1736-RD | Fast Track | Fast Track | Withdrawn | 2/27/2018 | Withdrawn | Withdrawn | SAN MATEO | REDWOOD CITY SUB | Storage | 0.01 | 12/20/2017 | 2/23/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-05 18:25 | 1737-RD | Fast Track | Fast Track | In Service | 2/27/2018 |  |  | KERN | DERRICK SUB | Solar PV | 1.816 | 12/20/2017 | 1/26/2018 | Fail Screens: D, F, H, J, K | 3/9/2018 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-06 16:12 | 1738-RD | Fast Track | Fast Track | Withdrawn | 2/27/2018 | Withdrawn | Withdrawn | MADERA | CHARCA SUB | Solar PV | 2.58 | 12/20/2017 | 1/26/2018 | Fail Screens: D, F, H, J, K | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-11 12:13 | 1739-RD | Detailed Study | Detailed Study | In Service | 3/28/2018 |  |  | STANISLAUS | COTTLE SUB | Solar PV | 1.8613 | 12/20/2017 | N/A | N/A | N/A | N/A | Pass | 5/14/2018 | N/A | Executed | No former queue position
2017-11-28 13:11 | 1740-RD | Fast Track | Fast Track | Withdrawn | 2/27/2018 | Withdrawn | Withdrawn | SAN LUIS OBISPO | SAN LUIS OBISPO SUB | Storage | 0.005 | 12/20/2017 | 2018-03-17 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-11-27 11:19 | 1741-RD | Fast Track | Fast Track | In Service | 2/27/2018 |  |  | SANTA CLARA | SARATOGA SUB | Storage | 0.02 | 12/20/2017 | 2018-03-28 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-11-28 13:40 | 1742-RD | Fast Track | Fast Track | In Service | 2/27/2018 |  |  | SAN MATEO | WOODSIDE SUB | Storage | 0.01 | 12/20/2017 | 1/3/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-11-28 14:35 | 1743-RD | Fast Track | Fast Track | In Service | 2/27/2018 |  |  | SAN MATEO | MENLO SUB | Storage | 0.01 | 12/20/2017 | 2/23/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-07 10:29 | 1744-RD | Fast Track | Fast Track | In Service | 2/27/2018 |  |  | SANTA CRUZ | ROY ROY SUB | Storage | 0.005 | 12/20/2017 | 1/29/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-12 09:39 | 1745-RD | Fast Track | Fast Track | In Service | 2/27/2018 |  |  | SANTA CLARA | LLAGAS SUB | Storage | 0.01 | 12/20/2017 | 2/7/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-12 09:45 | 1746-RD | Fast Track | Fast Track | In Service | 2/27/2018 |  |  | LAKE | MIDDLETOWN SUB | Storage | 0.01 | 12/20/2017 | 1/30/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-12 17:17 | 1747-RD | Detailed Study | Detailed Study | In Service | 2/27/2018 |  |  | MONTEREY | KING CITY SUB | Solar PV | 4.2068 | 12/20/2017 | N/A | N/A | N/A | N/A | Pass | 6/21/2018 | N/A | Executed | No former queue position
2017-11-22 15:50 | 1748-RD | Detailed Study | Detailed Study | Withdrawn | 8/1/2019 | Withdrawn | Withdrawn | KINGS | GUERNSEY SUB | Engine | 0.864 | 12/27/2017 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-11-06 12:46 | 1749-RD | Fast Track | Fast Track | In Service | 1/31/2018 |  |  | SAN JOAQUIN | WEBER SUB | Solar PV | 0.746 | 12/27/2017 | 2/23/2018 | Fail Screens: D, F, G, J, K, M | 6/20/2018 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-08 17:35 | 1750-RD | Fast Track | Fast Track | In Service | 2/27/2018 |  |  | SAN MATEO | MILLBRAE SUB | Storage | 0.315 | 12/27/2017 | 2018-03-17 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-13 10:48 | 1751-RD | Detailed Study | Detailed Study | In Service | 2/27/2018 |  |  | PLACER | LINCOLN SUB | Solar PV | 3 | 12/27/2017 | N/A | N/A | N/A | N/A | Pass | 9/6/2018 | N/A | Executed | No former queue position
2017-11-29 15:19 | 1752-RD | Fast Track | Fast Track | Withdrawn | 2/27/2018 | Withdrawn | Withdrawn | CONTRA COSTA | MEADOW LANE SUB | Storage | 0.2 | 12/27/2017 | 2/23/2018 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-11 17:38 | 1753-RD | Fast Track | Detailed Study | Active | 2/27/2018 |  |  | SHASTA | OREGON TRAIL SUB | Solar PV, Storage | 1.927 | 1/3/2018 | 2/5/2018 | Fail Screens: F, M, A3 | 3/23/2018 | Fail | Fail | 2/25/2019 | N/A | Executed | No former queue position
2017-12-18 14:45 | 1754-WD | Independent Study | Independent Study | Withdrawn | 10/31/2019 | Withdrawn | Withdrawn | FRESNO | BIOLA SUB | Engine | 2 | 1/3/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-11-29 16:26 | 1755-RD | Fast Track | Fast Track | Withdrawn | 2/27/2018 | Withdrawn | Withdrawn | MONTEREY | VIEJO SUB | Storage | 0.4 | 1/3/2018 | 2018-03-04 | Fail Screens: B, F, G, H, I, J | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-13 13:28 | 1756-RD | Fast Track | Fast Track | In Service | 2/27/2018 |  |  | EL DORADO | SHINGLE SPRINGS SUB | Solar PV | 1.375 | 1/3/2018 | 3/17/2018 | Fail Screens: B, F, G, H, I, J, K, L, M, V1, V2, S5 | 6/4/2018 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-10 21:12 | 1757-RD | Fast Track | Fast Track | In Service | 3/28/2018 |  |  | MONTEREY | SALINAS SUB | Solar PV, Storage | 1.4978 | 1/3/2018 | 4/2/2018 | Fail Screens: B, F, G, H, I, J, K, L, M | 5/30/2018 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-13 09:21 | 1758-WD | Fast Track | Fast Track | Withdrawn | 12/14/2018 | Withdrawn | Withdrawn | NAPA | PUEBLO SUB | Solar PV | 0.999 | 1/3/2018 | 1/17/2018 | Pass | 3/20/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-13 14:50 | 1759-RD | Fast Track | Fast Track | Withdrawn | 2/27/2018 | Withdrawn | Withdrawn | KINGS | LEMOORE SUB | Solar PV | 1.25 | 1/3/2018 | 2/2/2018 | Fail Screens: I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-12 08:05 | 1760-RD | Fast Track | Fast Track | Withdrawn | 2/27/2018 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Micro Turbine | 0.13 | 1/10/2018 | 2019-05-13 | Fail Screens: B, D, F, G, I, J, L, M, V1, S5, A1 | 7/16/2019 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-13 15:14 | 1761-RD | Fast Track | Fast Track | Withdrawn | 3/28/2018 | Withdrawn | Withdrawn | MONTEREY | PRUNEDALE SUB | Solar PV | 0.78 | 1/10/2018 | 2/14/2018 | Fail Screens: G, I, J, K, M | 4/12/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-21 14:23 | 1762-RD | Fast Track | Fast Track | In Service | 3/28/2018 |  |  | SAN JOAQUIN | HAMMER SUB | Solar PV | 0.9 | 1/10/2018 | 3/17/2018 | Fail Screens: B, D, G, H, I, J, K, M | 7/2/2018 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-13 12:59 | 1763-RD | Fast Track | Fast Track | Withdrawn | 12/15/2019 | Withdrawn | Withdrawn | MENDOCINO | WILLITS A SUB | Biomass | 3 | 1/10/2018 | 1/30/2018 | Fail Screens: B, F, G, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-22 12:38 | 1764-RD | Fast Track | Fast Track | Withdrawn | 3/28/2018 | Withdrawn | Withdrawn | CONTRA COSTA | FAIRVIEW SUB | Engine, Solar PV | 1.3067 | 1/10/2018 | 7/26/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-22 14:25 | 1765-RD | Fast Track | Fast Track | Withdrawn | 3/28/2018 | Withdrawn | Withdrawn | NAPA | HIGHWAY SUB | Solar PV | 1.7413 | 1/10/2018 | 1/29/2018 | Fail Screens: I, J, K, M | 3/26/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-26 08:51 | 1766-RD | Fast Track | Fast Track | Withdrawn | 3/28/2018 | Withdrawn | Withdrawn | NAPA | BASALT SUB | Solar PV | 1.8119 | 1/10/2018 | 1/29/2018 | Fail Screens: F, I, J, K, M | 3/27/2018 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-11-20 10:50 | 1767-RD | Detailed Study | Detailed Study | Withdrawn | 2/28/2018 | Withdrawn | Withdrawn | ALAMEDA | CASTRO VALLEY SUB | Solar PV | 5 | 1/17/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-13 12:56 | 1768-RD | Fast Track | Fast Track | Withdrawn | 12/1/2019 | Withdrawn | Withdrawn | CONTRA COSTA | KIRKER SUB | Biomass | 3 | 1/17/2018 | 2/1/2018 | Pass | 4/5/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-20 12:20 | 1769-RD | Fast Track | Detailed Study | Withdrawn | 3/28/2018 | Withdrawn | Withdrawn | KERN | MAGUNDEN SUB | Solar PV | 2.0529 | 1/17/2018 | 2/12/2018 | Fail Screens: F, G, H, J, K, M | 5/15/2018 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-22 13:19 | 1770-RD | Fast Track | Detailed Study | Withdrawn | 3/28/2018 | Withdrawn | Withdrawn | PLACER | LINCOLN SUB | Solar PV | 1.8625 | 1/17/2018 | 2/1/2018 | Fail Screens: F, I, J, K, M, V1, V2, S1, S2, S5, A1 | 5/3/2018 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-22 13:22 | 1771-RD | Fast Track | Detailed Study | In Service | 3/28/2018 |  |  | KERN | LERDO SUB | Solar PV | 2.2595 | 1/17/2018 | 2/12/2018 | Fail Screens: B, D, F, G, H, I, J, K, L, M, V1, V2, S5, A1 | 5/15/2018 | Fail | Pass | 3/13/2019 | N/A | Executed | No former queue position
2017-12-29 12:46 | 1772-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | CONTRA COSTA | TASSAJARA SUB | Solar PV | 1.28 | 1/17/2018 | 2/21/2018 | Fail Screens: D, H, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-22 09:09 | 1773-WD | Independent Study | Independent Study | Withdrawn | 10/31/2019 | Withdrawn | Withdrawn | MERCED | EL NIDO SUB | Reciprocating Engine | 1.95 | 1/17/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-27 15:35 | 1774-RD | Fast Track | Fast Track | Withdrawn | 3/27/2018 | Withdrawn | Withdrawn | ALAMEDA | OAKLAND J SUB | Solar PV | 0.54054 | 1/17/2018 | 2/13/2018 | Fail Screens: F, I, J, K, M | 7/3/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-28 14:03 | 1775-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | OAKLAND C (OAKLAND PP) SUB | Solar PV | 0.636 | 1/17/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-22 14:04 | 1776-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN LUIS OBISPO | SAN LUIS OBISPO SUB | Solar PV | 0.95727 | 1/17/2018 | 1/31/2018 | Fail Screens: D, G, I, J, K, M | 6/15/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-19 12:19 | 1777-RD | Fast Track | Fast Track | Withdrawn | 3/28/2018 | Withdrawn | Withdrawn | MADERA | OAKHURST SUB | Solar PV | 0.31278 | 1/24/2018 | 3/6/2018 | Fail Screens: F, G, H, I, J, M, V2, S2 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-20 12:13 | 1778-RD | Fast Track | Fast Track | In Service | 3/27/2018 |  |  | NAPA | SILVERADO SUB | Storage | 0.005 | 1/24/2018 | 2/18/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-20 12:36 | 1779-RD | Fast Track | Fast Track | In Service | 3/27/2018 |  |  | SONOMA | SONOMA A SUB | Storage | 0.01 | 1/24/2018 | 2/18/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-21 12:54 | 1780-RD | Fast Track | Detailed Study | Withdrawn | 3/27/2018 | Withdrawn | Withdrawn | YUBA | BANGOR SUB | Solar PV | 1.306 | 1/24/2018 | 2/21/2018 | Fail Screens: G, I, J, K, L, M | 5/10/2018 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-22 10:28 | 1781-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SONOMA | MOLINO SUB | Storage | 0.005 | 1/24/2018 | 2/18/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-22 13:20 | 1782-RD | Fast Track | Detailed Study | In Service | 9/29/2018 |  |  | EL DORADO | DIAMOND SPRINGS SUB | Solar PV | 0.72 | 1/24/2018 | 2/14/2018 | Fail Screens: D, F, G, I, J, K, M | 6/1/2018 | Fail | Pass | 1/30/2019 | N/A | Executed | No former queue position
2017-12-22 14:52 | 1783-WD | Fast Track | Independent Study | Active | 5/31/2019 | 2/15/2021 |  | KERN | LAMONT SUB | Solar PV | 1.9661 | 1/24/2018 | 2/13/2018 | Fail Screens: 2, 4, 5, 10 | 4/10/2018 | Fail | Pass | 10/10/2018 | N/A | Executed | No former queue position
2017-12-22 15:09 | 1784-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | SAN FRAN A (POTRERO PP) SUB | Storage | 0.01 | 1/24/2018 | 2/17/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-22 17:02 | 1785-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | AMADOR | IONE SUB | Solar PV | 1.958 | 1/24/2018 | 2/26/2018 | Fail Screens: I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-22 18:47 | 1786-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | SAN LUIS OBISPO | BAYWOOD SUB | Solar PV | 1.212 | 1/24/2018 | 2/15/2018 | Fail Screens: J, K, M | 4/23/2018 | Fail | Pass | 9/10/2018 | N/A | Executed | No former queue position
2017-12-28 14:36 | 1787-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | CONTRA COSTA | TASSAJARA SUB | Storage | 0.01 | 1/24/2018 | 2/18/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-29 17:08 | 1788-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | FRESNO | MALAGA SUB | Solar PV | 2.75 | 1/24/2018 | 3/5/2018 | Fail Screens: I, J, K, M | 4/24/2018 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-30 12:54 | 1789-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CLARA | FMC SUB | Solar PV | 2.9082 | 1/24/2018 | 3/21/2018 | Fail Screens: J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-01-02 12:08 | 1790-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN JOAQUIN | WEBER SUB | Solar PV | 1.32 | 1/24/2018 | 2/20/2018 | Fail Screens: I, J, K, M | 4/4/2018 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-01-02 12:54 | 1791-RD | Fast Track | Detailed Study | In Service | Not Provided |  |  | SAN JOAQUIN | WEBER SUB | Solar PV | 1.26 | 1/24/2018 | 2/20/2018 | Fail Screens: D, I, J, K, M | 4/4/2018 | Fail | Pass | 7/3/2018 | N/A | Executed | No former queue position
2018-01-03 18:44 | 1792-RD | Detailed Study | Detailed Study | In Service | Not Provided | In Service | 3/1/2019 | FRESNO | MALAGA SUB | Solar PV | 4.56 | 1/24/2018 | N/A | N/A | N/A | N/A | Pass | 6/4/2018 | N/A | Executed | No former queue position
2017-12-18 08:52 | 1793-RD | Fast Track | Fast Track | In Service | 3/27/2018 |  |  | SAN MATEO | WOODSIDE SUB | Storage | 0.01 | 1/24/2018 | 2/7/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-18 13:45 | 1794-RD | Fast Track | Fast Track | Withdrawn | 3/28/2018 | Withdrawn | Withdrawn | AMADOR | WEST POINT PH | Storage | 0.005 | 1/24/2018 | 2/15/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-22 17:53 | 1795-RD | Fast Track | Fast Track | In Service | 9/29/2018 |  |  | NAPA | BASALT SUB | Solar PV | 0.996 | 1/24/2018 | 2/15/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-28 18:25 | 1796-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MARIN | ALTO SUB | Solar PV | 0.6 | 1/24/2018 | 2/12/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-21 15:20 | 1797-RD | Fast Track | Detailed Study | In Service | Not Provided |  |  | EL DORADO | CLARKSVILLE SUB | Solar PV | 1.625 | 1/24/2018 | 3/29/2018 | Fail Screens: D, F, I, J, K, M | 6/13/2018 | Fail | Pass | 2019-02-04 | N/A | Executed | No former queue position
2017-12-22 13:23 | 1798-RD | Detailed Study | Detailed Study | In Service | 6/30/2018 |  |  | KERN | LERDO SUB | Solar PV | 2.0529 | 1/24/2018 | N/A | N/A | N/A | N/A | Fail | 5/30/2019 | N/A | Executed | No former queue position
2017-12-27 11:38 | 1799-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | EL DORADO | DIAMOND SPRINGS SUB | Solar PV | 1.5 | 1/24/2018 | 2/16/2018 | Fail Screens: F, G, H, I, J, K, M | 5/18/2018 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-28 14:37 | 1800-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | WOODWARD SUB | Solar PV | 2.3995 | 1/24/2018 | 2/12/2018 | Fail Screens: I, J, K, L, M | 4/2/2018 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-28 14:56 | 1801-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | OLD KEARNEY SUB | Solar PV | 2.3995 | 1/24/2018 | 2/12/2018 | Fail Screens: J, K, M | 3/21/2018 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-28 15:28 | 1802-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | OLD KEARNEY SUB | Solar PV | 2.3995 | 1/24/2018 | 2/12/2018 | Fail Screens: I, J, K, M | 3/21/2018 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-28 17:41 | 1803-RD | Fast Track | Fast Track | In Service | 9/29/2018 |  |  | YUBA | MARYSVILLE SUB | Solar PV, Storage | 2.1148 | 1/24/2018 | 2/14/2018 | Fail Screens: H, I, J, K, M | 4/17/2018 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-28 19:51 | 1804-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | OLD KEARNEY SUB | Solar PV | 2.3995 | 1/24/2018 | 2/12/2018 | Fail Screens: I, J, K, M | 3/21/2018 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-28 20:21 | 1805-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | OLD KEARNEY SUB | Solar PV | 2.3995 | 1/24/2018 | 2/12/2018 | Fail Screens: F, I, J, K, M | 3/21/2018 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-29 06:54 | 1806-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | WEST FRESNO SUB | Solar PV | 2.3995 | 1/24/2018 | 2/8/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-29 07:03 | 1807-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | OLD KEARNEY SUB | Solar PV | 2.3995 | 1/24/2018 | 2/12/2018 | Fail Screens: I, J, K, M | 3/28/2018 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-03 23:54 | 1808-WD | Fast Track | Fast Track | Withdrawn | 3/28/2018 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Storage | 0.25 | 1/24/2018 | 2/14/2018 | Fail Screens: 2, 7, 10 | 4/25/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-04 00:08 | 1809-WD | Fast Track | Fast Track | Withdrawn | 3/28/2018 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Storage | 0.5 | 1/24/2018 | 2/14/2018 | Fail Screens: 2, 7, 10 | 2018-06-21 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-09 11:50 | 1810-WD | Fast Track | Fast Track | In Service | 3/28/2018 | 7/2/2018 | 1/8/2019 | MARIN | STAFFORD SUB | Solar PV | 0.0885 | 1/24/2018 | 2/12/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-28 19:50 | 1811-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | DUMBARTON SUB | Solar PV | 1.0713 | 1/24/2018 | 2/20/2018 | Fail Screens: F, G, H, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-29 15:39 | 1812-WD | Fast Track | Fast Track | Withdrawn | 2/20/2019 | Withdrawn | Withdrawn | SAN JOAQUIN | LOCKEFORD SUB | Solar PV | 3 | 1/24/2018 | 2/14/2018 | Fail Screens: 2, 6, 10 | 5/3/2018 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-29 17:06 | 1813-WD | Fast Track | Fast Track | Withdrawn | 2/20/2019 | Withdrawn | Withdrawn | MENDOCINO | WILLITS A SUB | Solar PV | 1.9661 | 1/24/2018 | 2/21/2018 | Fail Screens: 2, 5, 10 | 5/9/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-27 16:52 | 1814-RD | Fast Track | Fast Track | Active | Not Provided |  |  | CONTRA COSTA | MEADOW LANE SUB | Solar PV, Storage | 0.98288 | 1/31/2018 | 2/21/2018 | Fail Screens: B, D, F, G, H, I, J, K, L, M, V1, S5, A1 | 4/25/2018 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-27 15:08 | 1815-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | SANTA CLARA | SARATOGA SUB | Solar PV, Storage | 3.5119 | 1/31/2018 | N/A | N/A | N/A | N/A | Pass | 2019-04-19 | N/A | Executed | No former queue position
2017-12-30 17:40 | 1816-RD | Detailed Study | Detailed Study | In Service | 11/30/2018 |  |  | MADERA | SHARON SUB | Solar PV | 1.9829 | 1/31/2018 | N/A | N/A | N/A | N/A | Pass | 8/22/2018 | N/A | Executed | No former queue position
2018-01-03 09:40 | 1817-RD | Fast Track | Fast Track | In Service | 3/31/2018 |  |  | SANTA CLARA | LOS GATOS SUB | Storage | 0.005 | 1/31/2018 | 3/3/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-01-03 10:10 | 1818-WD | Independent Study | Independent Study | Active | 5/31/2019 | 7/15/2020 |  | KERN | WASCO SUB | Solar PV | 4.6128 | 1/31/2018 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 6/26/2018 | N/A | Executed | No former queue position
2018-01-08 12:26 | 1819-WD | Independent Study | Independent Study | Withdrawn | 5/31/2019 | Withdrawn | Withdrawn | ALAMEDA | CAYETANO SUB | Solar PV | 4 | 1/31/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-01-24 10:33 | 1820-RD | Fast Track | Fast Track | In Service | 6/30/2018 |  |  | SAN FRANCISCO | SAN FRAN P(HUNTERS POINT) SUB | Solar PV | 0.1002 | 1/31/2018 | 2/14/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-22 09:05 | 1821-WD | Independent Study | Independent Study | Withdrawn | 10/31/2019 | Withdrawn | Withdrawn | FRESNO | STROUD SUB | Engine | 1 | 1/31/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-30 14:36 | 1822-RD | Fast Track | Fast Track | Withdrawn | 11/30/2018 | Withdrawn | Withdrawn | KERN | Withdrawn | Solar PV | 0.86 | 1/31/2018 | 2/13/2018 | Fail Screens: G, H, J, K, L, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-19 09:05 | 1823-RD | Fast Track | Fast Track | In Service | 3/27/2018 |  |  | ALAMEDA | MT EDEN SUB | Solar PV | 0.6 | 1/31/2018 | 2/26/2018 | Fail Screens: A, B, C, F, G, H, I, J, K, L, M | 4/23/2018 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-01-02 16:02 | 1824-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN JOAQUIN | FRENCH CAMP SUB | Storage | 0.325 | 1/31/2018 | 2/20/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-01-03 12:02 | 1825-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN MATEO | EAST GRAND SUB | Storage | 0.264 | 1/31/2018 | 2/20/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-01-03 17:35 | 1826-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN Z (EMBARCADERO) SUB | Storage | 0.132 | 1/31/2018 | 2/20/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-30 20:41 | 1827-RD | Fast Track | Detailed Study | Active | 2/1/2019 | 8/1/2020 |  | FRESNO | MALAGA SUB | Engine | 5 | 2/7/2018 | 2/16/2018 | Fail Screens: B, F, I, J, K, M | 3/14/2018 | Fail | Pass | 7/25/2018 | N/A | Executed | No former queue position
2017-12-29 10:57 | 1828-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | FRESNO | FIGARDEN SUB | Solar PV, Storage | 1.192 | 2/7/2018 | 3/17/2018 | Fail Screens: H, I, J, K, M | 8/10/2018 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-29 12:19 | 1829-RD | Fast Track | Detailed Study | In Service | Not Provided |  |  | FRESNO | MALAGA SUB | Solar PV, Storage | 1.8032 | 2/7/2018 | 3/29/2018 | Fail Screens: B, G, I, J, K, M | 8/27/2018 | Fail | Pass | 2/22/2019 | N/A | Executed | No former queue position
2017-12-29 12:51 | 1830-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | FRESNO | BULLARD SUB | Solar PV, Storage | 1.4782 | 2/7/2018 | 4/2/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-29 14:48 | 1831-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | FRESNO | ASHLAN AVE SUB | Solar PV, Storage | 1.619 | 2/7/2018 | 4/2/2018 | Fail Screens: H, J, K, M | 8/31/2018 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-29 18:14 | 1832-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | STAGG SUB | Solar PV | 2.76 | 2/7/2018 | 2/16/2018 | Fail Screens: J, K, M, S1 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-30 10:22 | 1833-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CRUZ | GREEN VALLEY SUB | Solar PV | 2.5809 | 2/7/2018 | 3/2/2018 | Fail Screens: D, F, G, I, J, K, M | 5/11/2018 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-30 17:42 | 1834-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | MONTEREY | CAMPHORA SUB | Solar PV | 1.75 | 2/7/2018 | N/A | N/A | N/A | N/A | Fail | 7/24/2018 | N/A | Executed | No former queue position
2017-12-30 23:34 | 1835-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN LUIS OBISPO | GOLDTREE SUB | Solar PV | 0.99105 | 2018-07-26 | 8/8/2018 | Fail Screens: D, H, I, J, K, M | 11/16/2018 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-01-03 09:57 | 1836-WD | Independent Study | Independent Study | Active | 5/31/2019 | 3/31/2022 |  | KERN | CHARCA SUB | Solar PV | 4.66 | 2/7/2018 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 7/3/2018 | N/A | Executed | No former queue position
2018-01-03 11:01 | 1837-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | SAN FRAN L SUB | Storage | 0.005 | 2/7/2018 | 3/23/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-01-09 11:16 | 1838-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN LUIS OBISPO | TEMPLETON SUB | Solar PV | 1.026 | 2/7/2018 | 2/26/2018 | Fail Screens: B, D, F, G, H, I, J, K, L, M, V1, S5, A1 | 4/24/2018 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-01-16 16:30 | 1839-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | AVENA SUB | Gas Turbine | 2.302 | 2/7/2018 | 2/21/2018 | Fail Screens: B, D, F, G, H, I, J, K, L, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-01-19 15:25 | 1840-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | VALLEY HOME SUB | Gas Turbine | 2.302 | 2/7/2018 | 2/26/2018 | Fail Screens: B, D, G, H, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-02-01 14:08 | 1841-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | PORTOLA SUB | Gas Turbine | 0.28119 | 2/7/2018 | 4/2/2018 | Fail Screens: J, M, A3 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-01-09 16:20 | 1842-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | YOLO | WOODLAND SUB | Gas Turbine | 2.565 | 2/7/2018 | 2/28/2018 | Fail Screens: B, F, G, M | 4/27/2018 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-01-10 15:43 | 1843-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | BOWLES SUB | Gas Turbine | 1.79 | 2/7/2018 | 3/19/2018 | Fail Screens: D, F, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-01-10 16:05 | 1844-RD | Fast Track | Detailed Study | In Service | Not Provided |  |  | FRESNO | SANGER SUB | Solar PV | 1.0333 | 2/7/2018 | 2018-04-18 | Fail Screens: D, J, K, M | N/A | N/A | Pass | 8/2/2018 | N/A | Executed | No former queue position
2018-01-09 12:46 | 1845-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN A (POTRERO PP) SUB | Storage | 0.396 | 2/14/2018 | 3/23/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-01-30 13:09 | 1846-WD | Independent Study | Independent Study | Withdrawn | 8/2/2018 | Withdrawn | Withdrawn | TULARE | ALPAUGH SUB | Other | 2 | 2/14/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-01-09 15:59 | 1847-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | SAN FRAN L SUB | Storage | 0.005 | 2/14/2018 | 3/23/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-01-16 12:21 | 1848-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CLARA | WOLFE SUB | Storage | 0.005 | 2/14/2018 | 6/6/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-01-16 13:07 | 1849-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN MATEO | CAROLANDS SUB | Storage | 0.01 | 2/14/2018 | 3/23/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-01-16 13:27 | 1850-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | NAPA | SILVERADO SUB | Storage | 0.01 | 2/14/2018 | 3/27/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-01-16 14:50 | 1851-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | SARATOGA SUB | Storage | 0.01 | 2/14/2018 | 6/6/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-01-18 10:40 | 1852-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | SAN FRAN P(HUNTERS POINT) SUB | Storage | 0.01 | 2/14/2018 | 2018-03-30 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-19 10:30 | 1853-RD | Detailed Study | Detailed Study | Withdrawn | 3/1/2018 | Withdrawn | Withdrawn | KERN | MIDSUN SW STA | Cogeneration | 10 | 2/14/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-01-16 16:28 | 1854-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SOLANO | PEABODY SUB | Storage | 0.325 | 2/21/2018 | 3/21/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-01-19 16:34 | 1855-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MONTEREY | SALINAS SUB | Storage | 0.32123 | 2/21/2018 | 7/18/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-01-19 16:58 | 1856-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN JOAQUIN | TRACY SUB | Storage | 0.32123 | 2/21/2018 | 2018-07-19 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-01-22 11:58 | 1857-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | FRESNO | WOODWARD SUB | Engine | 2 | 2/21/2018 | 6/5/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-30 17:45 | 1858-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | MONTEREY | CAMPHORA SUB | Solar PV, Wind | 6.8283 | 2/21/2018 | N/A | N/A | N/A | N/A | Pass | 8/13/2018 | N/A | Executed | No former queue position
2018-02-01 15:43 | 1859-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | CONTRA COSTA | KIRKER SUB | Gas Turbine | 4.8 | 2/21/2018 | 3/2/2018 | Fail Screens: B, D, G, H, I, J, K, L, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-01-03 12:54 | 1860-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | LOS GATOS SUB | Gas Turbine | 0.02 | 2/28/2018 | 4/4/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-01-23 12:08 | 1861-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | VASONA SUB | Gas Turbine | 0.005 | 2/28/2018 | 3/27/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-01-23 13:17 | 1862-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CRUZ | CAMP EVERS SUB | Solar PV | 0.01 | 2/28/2018 | 3/14/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-01-30 15:50 | 1863-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MARIN | COTATI SUB | Storage | 0.01 | 2/28/2018 | 3/5/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-02-05 14:20 | 1864-WD | Fast Track | Fast Track | In Service | 10/21/2019 | 3/15/2020 |  | FRESNO | CARUTHERS SUB | Other | 0.5504 | 2/28/2018 | 3/6/2018 | Fail Screens: 2, 4, 7, 9, 10 | 2018-08-03 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-02-05 14:47 | 1865-WD | Fast Track | Independent Study | Withdrawn | 12/13/2019 | Withdrawn | Withdrawn | MADERA | STOREY SUB | Solar PV | 2 | 2/28/2018 | 3/5/2018 | Pass | 5/8/2018 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-02-07 16:22 | 1866-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | AMADOR | IONE SUB | Solar PV | 0.24 | 2/28/2018 | 3/5/2018 | Fail Screens: I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-01-24 11:47 | 1867-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Storage | 0.005 | 2/28/2018 | 3/23/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-02-12 09:59 | 1868-WD | Fast Track | Independent Study | In Service | 6/30/2019 | 7/16/2020 | 12/3/2020 | MARIN | NOVATO SUB | Solar PV | 0.99 | 2/28/2018 | 3/16/2018 | Fail Screens: 2, 4, 5, 10 | 5/15/2018 | Fail | Pass | 10/2/2018 | N/A | Executed | No former queue position
2018-02-12 10:06 | 1869-WD | Fast Track | Independent Study | In Service | 6/30/2019 | 7/16/2020 | 2/3/2021 | MARIN | NOVATO SUB | Solar PV | 0.99 | 2/28/2018 | 3/16/2018 | Fail Screens: 2, 4, 5, 10 | 5/15/2018 | Fail | Pass | 2/11/2019 | N/A | Executed | No former queue position
2018-02-12 10:17 | 1870-WD | Fast Track | Independent Study | In Service | 6/30/2019 | 7/16/2020 | 12/3/2020 | MARIN | NOVATO SUB | Solar PV | 0.99 | 2/28/2018 | 3/16/2018 | Fail Screens: 2, 4, 5, 10 | 5/15/2018 | Fail | Pass | 2/11/2019 | N/A | Executed | No former queue position
2018-02-12 10:29 | 1871-WD | Fast Track | Fast Track | Withdrawn | 6/30/2019 | Withdrawn | Withdrawn | MARIN | NOVATO SUB | Solar PV | 1.62 | 2/28/2018 | 3/16/2018 | Fail Screens: 2, 4, 5, 10 | 5/15/2018 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-02-23 08:33 | 1872-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Solar PV | 0.02347 | 2/28/2018 | 3/8/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-02-07 12:08 | 1873-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | CONTRA COSTA | EL CERRITO G SUB | Storage | 0.264 | 2/28/2018 | 4/18/2018 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-02-14 15:36 | 1874-WD | Fast Track | Fast Track | Withdrawn | 5/16/2019 | Withdrawn | Withdrawn | SONOMA | MOLINO SUB | Storage | 0.216 | 3/7/2018 | 3/28/2018 | Fail Screens: 2, 5, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-02-15 17:09 | 1875-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | YOLO | UC DAVIS MTR STA | Storage | 0.005 | 3/7/2018 | 3/30/2018 | Fail Screens: B, H, I, L | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-02-16 14:10 | 1876-WD | Independent Study | Independent Study | Withdrawn | 3/1/2022 | Withdrawn | Withdrawn | SANTA CLARA | MORGAN HILL SUB | Battery | 20 | 3/7/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-02-20 16:21 | 1877-WD | Independent Study | Independent Study | Withdrawn | 11/1/2019 | Withdrawn | Withdrawn | SUTTER | HARTER SUB | Other | 50.5 | 3/7/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-01-30 09:42 | 1878-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN MATEO | BURLINGAME SUB | Storage | 0.015 | 3/7/2018 | 3/22/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-02-07 11:49 | 1879-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN MATEO | Customer Owned | Solar PV | 1.1745 | 3/7/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-02-09 12:29 | 1880-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN MATEO | WOODSIDE SUB | Storage | 0.02 | 3/7/2018 | 3/29/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-02-12 08:30 | 1881-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN L SUB | Storage | 0.01 | 3/7/2018 | 3/23/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-02-12 17:02 | 1882-RD | Detailed Study | Detailed Study | In Service | 1/7/2019 |  |  | SAN MATEO | BELMONT SUB | Engine, Storage | 2.29 | 3/7/2018 | N/A | N/A | N/A | N/A | Pass | 10/23/2018 | N/A | Executed | No former queue position
2018-02-20 13:43 | 1883-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | MENLO SUB | Storage | 0.01 | 3/14/2018 | 3/26/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-02-16 09:58 | 1884-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SONOMA | SALMON CREEK SUB | Storage | 0.01 | 3/14/2018 | 3/27/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-02-20 09:01 | 1885-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SONOMA | KONOCTI SUB | Storage | 0.01 | 3/14/2018 | 3/27/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-02-22 14:21 | 1886-WD | Fast Track | Independent Study | Active | 5/31/2019 | 3/2/2021 |  | KERN | WEEDPATCH SUB | Solar PV | 2.5838 | 3/14/2018 | 4/3/2018 | Fail Screens: 2, 4, 5, 10 | 5/17/2018 | Fail | Pass | 10/5/2018 | N/A | Executed | No former queue position
2018-02-22 15:00 | 1887-WD | Fast Track | Independent Study | Active | 5/31/2019 | 2/19/2021 |  | KERN | SHAFTER SUB | Solar PV | 2.5838 | 3/14/2018 | 4/3/2018 | Fail Screens: 2, 4, 5, 10 | 5/16/2018 | Fail | Pass | 10/30/2018 | N/A | Executed | No former queue position
2018-02-22 15:37 | 1888-WD | Fast Track | Independent Study | Active | 5/31/2019 | 2/15/2021 |  | KERN | ELK HILLS SUB | Solar PV | 2.4171 | 3/14/2018 | 4/9/2018 | Fail Screens: 2, 4, 9, 10 | 5/25/2018 | Fail | Pass | 11/9/2018 | N/A | Executed | No former queue position
2018-02-28 10:14 | 1889-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | PINEDALE SUB | Storage | 0.01 | 3/14/2018 | 4/3/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-02-28 16:26 | 1890-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | MABURY SUB | Storage | 0.005 | 3/14/2018 | 3/21/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-03-06 11:30 | 1891-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SOLANO | CORDELIA SUB | Storage | 0.264 | 3/14/2018 | 4/11/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-30 20:18 | 1892-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN MATEO | WOODSIDE SUB | Solar PV | 1.5865 | 3/21/2018 | 5/23/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-03-05 17:28 | 1893-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CLARA | LOYOLA SUB | Storage | 0.005 | 3/21/2018 | 3/27/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-30 14:56 | 1894-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | SANTA CRUZ | PAUL SWEET SUB | Engine, Solar PV | 6.6075 | 3/21/2018 | N/A | N/A | N/A | N/A | Pass | 9/28/2018 | N/A | Executed | No former queue position
2017-12-27 17:22 | 1895-RD | Fast Track | Fast Track | Active | Not Provided |  |  | CONTRA COSTA | KIRKER SUB | Solar PV | 1.002 | 3/28/2018 | 8/27/2018 | Fail Screens: G, H, I, J, K, M | 11/14/2018 | Fail | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-29 16:57 | 1896-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | TULARE | DINUBA SUB | Engine, Solar PV | 0.87249 | 3/28/2018 | 4/24/2018 | Fail Screens: B, F, G, I, J, K, L, M, S5 | 8/6/2018 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-03-09 13:04 | 1897-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CLARA | MORGAN HILL SUB | Storage | 0.01 | 3/28/2018 | 6/21/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-03-13 10:01 | 1898-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MARIN | SAN RAFAEL SUB | Storage | 0.01 | 3/28/2018 | 6/22/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-28 14:36 | 1899-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | Withdrawn | Solar PV | 21.3556 | 3/28/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-03-15 12:47 | 1900-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SONOMA | DUNBAR SUB | Storage | 0.01 | 3/28/2018 | 6/12/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-03-09 17:52 | 1901-WD | Independent Study | Independent Study | Withdrawn | 3/31/2020 | Withdrawn | Withdrawn | PLACER | LINCOLN SUB | Solar PV | 6.35 | 4/4/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-03-21 19:58 | 1902-WD | Independent Study | Independent Study | In Service | 6/1/2020 | 9/18/2020 |  | SUTTER | PEASE SUB | Storage | 5 | 4/4/2018 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 10/26/2018 | N/A | Executed | No former queue position
2017-12-31 18:58 | 1903-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN MATEO | RALSTON SUB | Solar PV | 2.6956 | 4/4/2018 | 4/21/2018 | Fail Screens: I, J, K, M | 6/19/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-03-20 10:42 | 1904-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CRUZ | LOS GATOS SUB | Storage | 0.01 | 4/4/2018 | 7/26/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-03-23 15:47 | 1905-RD | Fast Track | Detailed Study | In Service | Not Provided |  |  | SOLANO | DIXON SUB | Solar PV | 1.1344 | 4/11/2018 | 7/21/2018 | Fail Screens: G, I, J, K, M | 9/5/2018 | Fail | Pass | 3/6/2019 | N/A | Executed | No former queue position
2018-03-26 16:31 | 1906-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | ORO LOMA SUB | Solar PV | 2.52 | 4/11/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-03-29 09:36 | 1907-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | SAN LEANDRO U SUB | Storage | 0.455 | 4/11/2018 | 7/19/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2017-12-30 13:13 | 1908-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CLARA | Customer Owned Zanker Road 115KV | Engine, Fuel Cell, Solar PV | 15.5847 | 4/11/2018 | 5/17/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-03-09 14:00 | 1909-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | FRESNO | CALIFORNIA AVE SUB | Solar PV | 1.1434 | 4/11/2018 | 4/27/2018 | Fail Screens: D, J, K, M | 7/5/2018 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-03-12 10:31 | 1910-RD | Detailed Study | Detailed Study | In Service | Not Provided | In Service | 2/5/2021 | KERN | TEMBLOR SUB | Solar PV | 5 | 4/11/2018 | N/A | N/A | N/A | N/A | Pass | 12/27/2018 | N/A | Executed | No former queue position
2018-03-20 15:22 | 1911-RD | Fast Track | DGSP | Active | Not Provided |  |  | AMADOR | IONE SUB | Solar PV, Storage | 2.18 | 4/11/2018 | 5/9/2018 | Pass | N/A | N/A | Pass | 2018-09-17 | N/A | Executed | No former queue position
2018-03-21 11:39 | 1912-RD | Fast Track | DGSP | Active | Not Provided |  |  | AMADOR | IONE SUB | Solar PV | 0.24 | 4/11/2018 | 4/25/2018 | Fail Screens: D, J, K, M | N/A | N/A | Pass | 2018-09-17 | N/A | Executed | No former queue position
2018-03-29 11:41 | 1913-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MONTEREY | DEL MONTE SUB | Solar PV | 3 | 4/11/2018 | 5/9/2018 | Fail Screens: B, F, G, H, I, J, K, L, M | 6/13/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-30 19:48 | 1914-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN MATEO | SNEATH LANE SUB | Solar PV | 2.259 | 4/11/2018 | 4/27/2018 | Fail Screens: I, J, K, M | 6/19/2018 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-03-14 13:16 | 1915-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | CASTRO VALLEY SUB | Storage | 0.015 | 4/11/2018 | 4/23/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-03-27 11:22 | 1916-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | MOUNTAIN VIEW SUB | Storage | 0.015 | 4/11/2018 | 4/23/2018 | Fail Screens: B, D, H, I, L, M |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-03-30 10:06 | 1917-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | HICKS SUB | Storage | 0.005 | 4/11/2018 | 4/25/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-03-28 09:45 | 1918-WD | Fast Track | Fast Track | Withdrawn | 5/30/2019 | Withdrawn | Withdrawn | SUTTER | HARTER SUB | Other | 2 | 4/18/2018 | 5/10/2018 | Fail Screens: 2, 5, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-03-29 16:39 | 1919-WD | Cluster | Cluster | Withdrawn | 6/30/2020 | Withdrawn | Withdrawn | SUTTER | HARTER SUB | Other | 5 | 4/18/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-30 19:15 | 1920-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SHASTA | DESCHUTES SUB | Solar PV | 0.91046 | 4/18/2018 | 6/11/2018 | Fail Screens: D, G, J, K, M | 8/14/2018 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-03-20 23:51 | 1921-WD | Fast Track | Fast Track | Withdrawn | 4/22/2019 | Withdrawn | Withdrawn | SONOMA | COTATI SUB | Solar PV | 0.96 | 4/18/2018 | 5/16/2018 | Fail Screens: 2, 4, 10 | 7/16/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-04-13 15:38 | 1922-WD | Independent Study | Independent Study | Withdrawn | 12/1/2020 | Withdrawn | Withdrawn | SUTTER | MARYSVILLE SUB | Other | 47.6 | 4/25/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2017-12-21 22:13 | 1923-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SOLANO | CORDELIA SUB | Solar PV, Storage | 1.1835 | 4/25/2018 | 7/23/2018 | Fail Screens: B, F, J, K, M | 10/10/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-04-06 13:47 | 1924-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | AVENA SUB | Gas Turbine | 2.302 | 5/2/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-03-26 12:36 | 1925-WD | Fast Track | Independent Study | Withdrawn | 12/30/2019 | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Gas Turbine | 3 | 5/2/2018 | 5/21/2018 | Fail Screens: 4, 5, 6, 10 | 7/23/2018 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-03-30 15:27 | 1926-WD | Independent Study | Independent Study | In Service | 12/27/2019 | 9/1/2021 |  | YOLO | PUTAH CREEK SUB | Solar PV | 3.465 | 5/2/2018 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | Withdrawn | N/A | Executed | No former queue position
2018-04-20 12:42 | 1927-WD | Fast Track | Fast Track | Withdrawn | 9/20/2018 | Withdrawn | Withdrawn | CALAVERAS | NORTH BRANCH SUB | Solar PV | 3 | 5/2/2018 | 5/22/2018 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-04-09 16:35 | 1928-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | FRESNO | WAHTOKE SUB | Solar PV | 1.468 | 5/2/2018 | N/A | N/A | N/A | N/A | Pass | 2018-07-25 | N/A | Executed | No former queue position
2018-04-23 13:55 | 1929-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN MATEO | EAST GRAND SUB | Storage | 0.1 | 5/2/2018 | 5/29/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-04-13 11:36 | 1930-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN W (BAYSHORE) SUB | Other | 4.6 | 5/9/2018 | 5/25/2018 | Fail Screens: B | 8/13/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-04-25 20:32 | 1931-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN MATEO | REDWOOD CITY SUB | Storage | 0.315 | 5/9/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-04-27 09:00 | 1932-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Storage | 0.132 | 5/9/2018 | 6/6/2018 | Fail Screens: A | 2018-09-12 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-04-30 09:10 | 1933-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | DIXON LANDING SUB | Storage | 0.475 | 5/9/2018 | 6/15/2018 | Fail |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-04-30 14:26 | 1934-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | FRESNO | NEWHALL SUB | Solar PV | 5 | 5/9/2018 | N/A | N/A | N/A | N/A | Pass | 2018-12-04 | N/A | Executed | No former queue position
2018-04-20 13:30 | 1935-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | NAPA | SILVERADO SUB | Storage, Turbine | 3.072 | 5/16/2018 | 6/7/2018 | Fail Screens: B, F, G, H, I, J, K, M | 8/2/2018 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-04-26 13:40 | 1936-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CRUZ | CAMP EVERS SUB | Storage | 0.01 | 5/16/2018 | 2018-08-09 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-04-27 16:35 | 1937-WD | Fast Track | Fast Track | Withdrawn | 12/31/2020 | Withdrawn | Withdrawn | SONOMA | RINCON SUB | Other | 3 | 5/16/2018 | 5/31/2018 | Fail Screens: 2, 5, 10 | 7/5/2018 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-04-30 11:05 | 1938-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN Z (EMBARCADERO) SUB | Storage | 0.132 | 5/16/2018 | 6/14/2018 | Fail Screens: A, L | 10/8/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-04-30 11:14 | 1939-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | OAKLAND D SUB | Storage | 0.01764 | 5/16/2018 | 5/30/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-04-27 18:05 | 1940-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | NORTECH SUB | Storage | 0.029 | 5/16/2018 | 2018-07-24 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-04-27 16:56 | 1941-WD | Fast Track | Fast Track | Withdrawn | 12/31/2020 | Withdrawn | Withdrawn | SONOMA | PETALUMA C SUB | Other | 3 | 5/16/2018 | 6/5/2018 | Fail Screens: 2, 5, 10 | 7/11/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-05-01 09:55 | 1942-WD | Fast Track | Fast Track | Withdrawn | 12/31/2020 | Withdrawn | Withdrawn | SONOMA | PETALUMA C SUB | Other | 3 | 5/16/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-05-02 12:47 | 1943-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | NAPA | HIGHWAY SUB | Storage | 0.132 | 5/23/2018 | 7/13/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-04-25 09:15 | 1944-RD | Fast Track | Fast Track | In Service | 1/31/2019 |  |  | TRINITY | HUMBOLDT SUB | Hydro | 2 | 5/23/2018 | 6/6/2018 | Fail Screens: B, F, G, I, J, K, M | 7/2/2018 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-05-08 06:57 | 1945-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN FRANCISCO | SAN FRAN A (POTRERO PP) SUB | Engine | 0.035 | 5/23/2018 | 10/03/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-05-09 09:26 | 1946-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN MATEO | EAST GRAND SUB | Storage | 0.132 | 5/23/2018 | 6/14/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-05-09 09:33 | 1947-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN MATEO | EAST GRAND SUB | Storage | 0.132 | 5/23/2018 | 6/14/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-05-09 10:18 | 1948-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN A (POTRERO PP) SUB | Storage | 0.066 | 5/23/2018 | 6/14/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-05-09 10:22 | 1949-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN A (POTRERO PP) SUB | Storage | 0.132 | 5/23/2018 | 6/20/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-05-09 10:29 | 1950-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Storage | 0.036 | 5/23/2018 | 2018-06-20 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-05-09 10:39 | 1951-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN A (POTRERO PP) SUB | Storage | 0.264 | 5/23/2018 | 6/20/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-05-09 10:46 | 1952-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN A (POTRERO PP) SUB | Storage | 0.198 | 5/23/2018 | 6/20/2018 | Fail Screens: J | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-05-09 11:59 | 1953-RD | Fast Track | Fast Track | Active | Not Provided |  |  | CONTRA COSTA | ROSSMOOR SUB | Storage | 0.036 | 5/23/2018 | 8/31/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-05-09 12:06 | 1954-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN FRANCISCO | SAN FRAN Z (EMBARCADERO) SUB | Storage | 0.072 | 5/23/2018 | 7/19/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-05-09 12:16 | 1955-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CRUZ | PAUL SWEET SUB | Storage | 0.036 | 5/23/2018 | 6/13/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-05-09 12:27 | 1956-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA CLARA | VASONA SUB | Storage | 0.036 | 5/23/2018 | 8/16/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-05-09 12:33 | 1957-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN FRANCISCO | SAN FRAN E SUB | Storage | 0.018 | 5/23/2018 | 8/20/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-05-09 12:37 | 1958-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MARIN | NOVATO SUB | Storage | 0.036 | 5/23/2018 | 9/4/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-05-09 12:49 | 1959-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN L SUB | Storage | 0.036 | 5/23/2018 | 11/2/2018 | Fail Screens: J | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-05-09 12:54 | 1960-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SONOMA | PETALUMA C SUB | Storage | 0.036 | 5/23/2018 | 9/4/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-05-09 13:01 | 1961-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN FRANCISCO | SAN FRAN A (POTRERO PP) SUB | Storage | 0.036 | 5/23/2018 | 8/1/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-05-09 14:25 | 1962-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN MATEO | BAY MEADOWS SUB | Storage | 0.036 | 5/23/2018 | 6/11/2018 | Fail |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-05-09 15:11 | 1963-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MARIN | SAN RAFAEL SUB | Storage | 0.036 | 5/23/2018 | 8/1/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-05-09 15:17 | 1964-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | CONTRA COSTA | SAN RAMON SUB | Storage | 0.036 | 5/23/2018 | 2018-09-27 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-05-09 15:23 | 1965-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SONOMA | MOLINO SUB | Storage | 0.018 | 5/23/2018 | 7/25/2018 | Fail Screens: B, H, I, L, M |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-03-15 14:42 | 1966-RD | Fast Track | Fast Track | Withdrawn | 12/18/2018 | Withdrawn | Withdrawn | FREMONT | DIXON LANDING SUB | Other | 2.1 | 5/23/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-04-25 11:57 | 1967-WD | Independent Study | Independent Study | Withdrawn | 12/21/2020 | Withdrawn | Withdrawn | MERCED | LOS BANOS SUB | Wind | 120.96 | 5/23/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-05-07 10:37 | 1968-RD | Fast Track | Detailed Study | Withdrawn | 5/1/2020 | Withdrawn | Withdrawn | CONTRA COSTA | KIRKER SUB | Engine | 3.2 | 5/23/2018 | 7/3/2018 | Fail Screens: B, D, F, G, I, J, K, M | 8/10/2018 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-05-02 15:02 | 1969-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | CASTRO VALLEY SUB | Storage | 0.01 | 5/30/2018 | 6/26/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-05-15 16:18 | 1970-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | OAKLAND X SUB | Storage | 0.036 | 5/30/2018 | 6/25/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-05-22 17:35 | 1971-WD | Cluster | Independent Study | Active | 12/1/2020 |  |  | SANTA CLARA | LOS ESTEROS SUB | Other | 28 | 5/30/2018 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 2022-01-10 | 2019-12-20 | Tendered | No former queue position
2018-05-23 10:26 | 1972-WD | Independent Study | Independent Study | Withdrawn | 12/1/2020 | Withdrawn | Withdrawn | SUTTER | BOGUE SUB | Other | 47.6 | 5/30/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-05-11 10:09 | 1973-WD | Independent Study | Independent Study | Withdrawn | 12/1/2021 | Withdrawn | Withdrawn | LASSEN | MCARTHUR SUB | Other | 60.8 | 6/6/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-05-24 20:50 | 1974-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SUTTER | PEASE SUB | Solar PV | 0.09001 | 6/6/2018 | 6/26/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-05-17 09:58 | 1975-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | STANISLAUS | VALLEY HOME SUB | Gas Turbine | 1.151 | 6/6/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-05-25 15:08 | 1976-WD | Fast Track | Independent Study | Withdrawn | 12/16/2019 | Withdrawn | Withdrawn | MONTEREY | JOLON SUB | Solar PV | 4.66 | 6/6/2018 | 6/27/2018 | Fail Screens: 2, 10 | 7/30/2018 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-05-16 09:50 | 1977-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SONOMA | PENNGROVE SUB | Storage | 2 | 6/6/2018 | 8/6/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-05-30 12:21 | 1978-WD | Fast Track | Independent Study | Withdrawn | 12/15/2019 | Withdrawn | Withdrawn | MONTEREY | SAN ARDO SUB | Solar PV | 3 | 6/6/2018 | 6/27/2018 | Fail Screens: 2, 10 | 8/2/2018 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-05-17 12:58 | 1979-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | VINEYARD SUB | Solar PV | 3.2 | 6/13/2018 | 7/26/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-05-24 16:12 | 1980-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | BOWLES SUB | Solar PV | 0.21 | 6/13/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-05-18 15:50 | 1981-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN Z (EMBARCADERO) SUB | Storage | 0.21 | 6/20/2018 | 7/11/2018 | Fail Screens: A | 8/29/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-05-18 16:48 | 1982-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN Z (EMBARCADERO) SUB | Storage | 0.21 | 6/20/2018 | 8/2/2018 | Fail Screens: A | 10/1/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-05-21 15:54 | 1983-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Storage | 0.21 | 6/20/2018 | 10/1/2018 | Fail Screens: F, J, M | 12/13/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-05-21 22:22 | 1984-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN Z (EMBARCADERO) SUB | Storage | 0.036 | 6/20/2018 | 8/2/2018 | Fail Screens: A | 9/7/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-06-07 09:12 | 1985-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | MENDOTA SUB | Solar PV | 2.804 | 6/20/2018 | 7/19/2018 | Fail Screens: F, G, H, J, K, M | 9/5/2018 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-06-06 14:55 | 1986-RD | Detailed Study | Detailed Study | In Service | 2/1/2019 | 11/26/2021 |  | COLUSA | WILLIAMS SUB | Turbine | 3.6 | 6/20/2018 | N/A | N/A | N/A | N/A | Pass | 11/28/2018 | 4/22/2019 | Executed | No former queue position
2018-06-07 18:33 | 1987-RD | Detailed Study | Detailed Study | Withdrawn | 2/1/2019 | Withdrawn | Withdrawn | GLENN | LOGAN CREEK SUB | Turbine | 3.6 | 6/20/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-06-08 09:46 | 1988-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | NEWARK SUB | Storage | 1.12 | 6/20/2018 | 10/23/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-06-08 11:59 | 1989-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN MATEO | MILLBRAE SUB | Storage | 0.132 | 6/20/2018 | 7/27/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-06-07 10:52 | 1990-RD | Detailed Study | Detailed Study | Active | 8/1/2018 |  |  | KERN | MIDSUN SW STA | Engine | 9.6 | 6/20/2018 | N/A | N/A | N/A | N/A | Pass | 12/20/2019 | N/A | Executed | No former queue position
2018-06-06 10:08 | 1991-RD | Detailed Study | Detailed Study | Active | 6/25/2020 | 6/25/2020 |  | NAPA | HIGHWAY SUB | Engine | 2.344 | 6/27/2018 | N/A | N/A | N/A | N/A | Pass | 10/29/2018 | N/A | Executed | No former queue position
2018-06-12 17:04 | 1992-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | AMADOR | IONE SUB | Solar PV | 1.918 | 6/27/2018 | 8/1/2018 | Fail | 2019-02-05 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-06-12 13:05 | 1993-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | FRESNO | AIRWAYS SUB | Solar PV | 2.4204 | 6/27/2018 | N/A | N/A | N/A | N/A | Pass | 10/17/2018 | N/A | Executed | No former queue position
2018-05-01 12:38 | 1994-RD | Detailed Study | Detailed Study | Withdrawn | 4/15/2019 | Withdrawn | Withdrawn | SAN JOAQUIN | RIPON SUB | Engine | 3.0442 | 6/27/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-06-19 09:11 | 1995-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Storage | 0.01 | 7/3/2018 | 7/26/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-06-21 09:27 | 1996-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MENDOCINO | UKIAH SUB | Solar PV | 0.70328 | 7/3/2018 | 7/30/2018 | Fail Screens: I, J, K, M | 9/6/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-06-15 16:44 | 1997-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | LAKE | LUCERNE SUB | Solar PV | 1.32 | 7/3/2018 | 4/3/2019 | Fail Screens: F, G, I, J, K, M | 5/15/2019 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-06-05 12:27 | 1998-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | NEWARK SUB | Storage | 0.6174 | 7/3/2018 | 9/25/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-06-19 05:51 | 1999-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SONOMA | FULTON SUB | Solar PV | 1.34 | 7/3/2018 | 8/22/2018 | Fail Screens: I, J, K, M | 9/27/2018 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-06-11 16:50 | 2000-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | TEJON SUB | Micro Turbine | 1 | 7/11/2018 | 12/6/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-06-13 13:25 | 2001-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | COPUS SUB | Micro Turbine | 1 | 7/11/2018 | 12/6/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-06-13 13:43 | 2002-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | COPUS SUB | Solar PV | 1 | 7/11/2018 | 12/6/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-06-26 16:43 | 2003-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SHASTA | OREGON TRAIL SUB | Solar PV | 0.58 | 7/11/2018 | 7/18/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-06-28 18:16 | 2004-WD | Independent Study | Independent Study | Withdrawn | 5/1/2021 | Withdrawn | Withdrawn | CONTRA COSTA | HERDLYN SUB | Solar PV, Storage | 21.1985 | 7/11/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-07-05 10:28 | 2005-WD | Independent Study | Independent Study | Active | 12/31/2021 | 3/31/2022 |  | SONOMA | SALMON CREEK SUB | Storage | 6 | 7/11/2018 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 11/16/2018 | N/A | Executed | No former queue position
2018-07-02 10:15 | 2006-WD | Independent Study | Independent Study | Withdrawn | 12/13/2019 | Withdrawn | Withdrawn | MADERA | STOREY SUB | Solar PV | 3.332 | 7/17/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-07-09 09:55 | 2007-RD | Detailed Study | Detailed Study | Active | 6/3/2019 | 12/31/2020 |  | MADERA | SAN JOAQUIN #3 PH | Turbine | 2.344 | 7/17/2018 | N/A | N/A | N/A | N/A | Pass | 12/7/2018 | N/A | Executed | No former queue position
2018-07-09 16:05 | 2008-RD | Detailed Study | Detailed Study | Active | 12/31/2019 |  |  | CALAVERAS | WEST POINT PH | Turbine | 3.88 | 7/17/2018 | N/A | N/A | N/A | N/A | Pass | 10/25/2018 | N/A | Executed | No former queue position
2018-06-11 11:51 | 2009-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN Z (EMBARCADERO) SUB | Storage | 0.264 | 7/17/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-06-22 10:40 | 2010-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN Z (EMBARCADERO) SUB | Storage | 0.132 | 7/17/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-06-22 11:06 | 2011-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN Z (EMBARCADERO) SUB | Storage | 0.792 | 7/17/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-06-25 11:06 | 2012-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | TEHAMA | RAWSON SUB | Storage | 0.06 | 7/17/2018 | 8/21/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-06-25 11:32 | 2013-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | KERN | TEJON SUB | Storage | 0.0582 | 7/17/2018 | 8/20/2018 | Fail Screens: J, M |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-06-29 15:48 | 2014-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN MATEO | EAST GRAND SUB | Storage | 0.315 | 7/17/2018 | 11/2/2018 | Fail Screens: J, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-06-27 07:05 | 2015-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | OAKLAND L SUB | Storage | 0.01 | 7/17/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-07-02 16:22 | 2016-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN JOAQUIN | WEBER SUB | Solar PV | 0.96 | 7/17/2018 | 8/1/2018 | Fail Screens: B, F, G, H, I, J, K, M | 8/30/2018 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-06-29 12:08 | 2017-WD | Fast Track | Fast Track | Withdrawn | 12/10/2019 | Withdrawn | Withdrawn | ALAMEDA | JARVIS SUB | Solar PV | 1 | 7/25/2018 | 8/22/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-06-29 12:20 | 2018-WD | Fast Track | Fast Track | Withdrawn | 12/10/2019 | Withdrawn | Withdrawn | ALAMEDA | DUMBARTON SUB | Solar PV | 3 | 7/25/2018 | 8/23/2018 | Fail Screens: 2, 4, 5, 6, 7, 9, 10 | 12/12/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-05-17 14:11 | 2019-WD | Fast Track | Fast Track | Withdrawn | 3/1/2019 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Solar PV | 3.2 | 7/25/2018 | 8/15/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-06-06 16:35 | 2020-WD | Fast Track | Fast Track | Withdrawn | 1/11/2019 | Withdrawn | Withdrawn | ALAMEDA | MT EDEN SUB | Solar PV | 0.21 | 7/25/2018 | 8/24/2018 | Fail Screens: 2, 9, 10 | 11/21/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-07-11 12:41 | 2021-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN JOAQUIN | LAMMERS SUB | Solar PV | 0.21 | 7/25/2018 | 8/9/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-07-10 14:38 | 2022-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | AMADOR | OLETA SUB | Storage | 0.21 | 8/1/2018 | 9/10/2018 | Fail Screens: B, F, H, I, J, M |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-07-10 09:54 | 2023-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CLARA | STONE SUB | Storage | 0.21 | 8/1/2018 | 8/21/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-07-12 15:10 | 2024-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN E SUB | Storage | 0.01 | 8/1/2018 | 8/21/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-07-17 13:13 | 2025-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | CHOWCHILLA SUB | Solar PV | 0.9332 | 8/1/2018 | 4/3/2019 | Fail Screens: B, D, G, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-07-18 09:44 | 2026-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | NEWARK SUB | Storage | 1.56 | 8/8/2018 | 9/11/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-07-25 13:31 | 2027-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN MATEO | GLENWOOD SUB | Storage | 0.01 | 8/15/2018 | 8/28/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-07-26 14:41 | 2028-RD | Fast Track | DGSP | In Service | Not Provided |  |  | KERN | LERDO SUB | Solar PV | 2.875 | 8/15/2018 | 11/16/2018 | Fail Screens: B, D, F, G, H, I, J, K, M | 1/7/2019 | Fail | Fail | 2019-08-27 | N/A | Executed | No former queue position
2018-07-10 14:39 | 2029-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN MATEO | WOODSIDE SUB | Storage | 0.02 | 8/15/2018 | 8/28/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-07-30 22:16 | 2030-WD | Fast Track | Fast Track | Withdrawn | 12/14/2019 | Withdrawn | Withdrawn | SANTA CRUZ | GREEN VALLEY SUB | Solar PV | 2 | 8/15/2018 | 9/19/2018 | Fail Screens: 2, 4, 5, 6, 9, 10 | 11/21/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-07-30 22:29 | 2031-WD | Fast Track | Fast Track | Withdrawn | 12/14/2019 | Withdrawn | Withdrawn | SANTA CRUZ | GREEN VALLEY SUB | Solar PV | 3 | 8/15/2018 | 9/19/2018 | Fail Screens: 2, 4, 5, 6, 9, 10 | 11/21/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-07-02 08:44 | 2032-WD | Fast Track | Fast Track | Withdrawn | 12/16/2019 | Withdrawn | Withdrawn | ALAMEDA | HERDLYN SUB | Solar PV | 1.85 | 8/15/2018 | 8/28/2018 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-07-30 15:20 | 2033-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | MADERA | OAKHURST SUB | Solar PV | 0.3218 | 8/15/2018 | N/A | N/A | N/A | N/A | Pass | 12/4/2018 | N/A | Executed | No former queue position
2018-06-28 08:07 | 2034-WD | Independent Study | Independent Study | Withdrawn | 6/28/2019 | Withdrawn | Withdrawn | SAN JOAQUIN | LAMMERS SUB | Solar PV | 5 | 8/22/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-07-10 13:45 | 2035-RD | Detailed Study | Detailed Study | Withdrawn | 6/15/2020 | Withdrawn | Withdrawn | SHASTA | BURNEY SUB | Turbine | 3.6 | 8/22/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-08-09 09:50 | 2036-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MONTEREY | PRUNEDALE SUB | Storage | 0.325 | 8/22/2018 | 9/19/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-07-02 13:51 | 2037-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CLARA | TRANSMISSION | Solar PV | 3.5804 | 8/22/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-07-23 18:18 | 2038-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | MERCED SUB | Solar PV | 1.25 | 8/22/2018 | 9/12/2018 | Fail Screens: F, G, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-08-13 15:31 | 2039-RD | Fast Track | Detailed Study | In Service | 3/1/2020 |  |  | SAN LUIS OBISPO | TEMPLETON SUB | Solar PV | 1.375 | 8/22/2018 | 11/28/2018 | Fail Screens: D, F, I, J, K, M | 1/14/2019 | Fail | Fail | 5/16/2019 | N/A | Executed | No former queue position
2018-08-09 11:50 | 2040-WD | Fast Track | Independent Study | Active | 12/15/2019 | 12/3/2021 |  | KERN | TAFT SUB | Solar PV | 2.2 | 8/29/2018 | 9/19/2018 | Pass | 12/12/2018 | Fail | Pass | 7/11/2019 | N/A | Executed | No former queue position
2018-08-14 13:22 | 2041-WD | Fast Track | Fast Track | Active | 12/15/2019 |  |  | SANTA BARBARA | CUYAMA SUB | Solar PV | 3 | 8/29/2018 | 9/20/2018 | Pass | 2019-01-25 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-08-02 10:04 | 2042-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | TEHAMA | TYLER SUB | Solar PV | 8.1808 | 8/29/2018 | N/A | N/A | N/A | N/A | Pass | 2/15/2019 | N/A | Executed | No former queue position
2018-07-28 14:40 | 2043-RD | Fast Track | Fast Track | Withdrawn | 9/23/2019 | Withdrawn | Withdrawn | FRESNO | MCMULLIN SUB | Turbine | 3.4368 | 8/29/2018 | 9/12/2018 | Fail Screens: B, F, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-07-28 15:28 | 2044-RD | Fast Track | Fast Track | Withdrawn | 9/30/2019 | Withdrawn | Withdrawn | KINGS | ALPAUGH SUB | Turbine | 1.145 | 8/29/2018 | 9/13/2018 | Fail Screens: B, F, I, J, K, M | 10/17/2018 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-08-02 16:28 | 2045-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | LAKE | Customer Owned | Storage | 0.65 | 8/29/2018 | 4/12/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-08-03 14:32 | 2046-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | PINEDALE SUB | Storage | 0.5 | 8/29/2018 | 9/19/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-08-22 10:32 | 2047-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | LAS POSITAS SUB | Solar PV | 0.00244 | 8/29/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-08-08 08:06 | 2048-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SONOMA | SONOMA A SUB | Micro Turbine, Solar PV, Storage | 0.48649 | 9/5/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-08-15 14:44 | 2049-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | FRESNO | CALIFORNIA AVE SUB | Engine, Solar PV, Storage | 5.7715 | 9/5/2018 | N/A | N/A | N/A | N/A | Pass | 4/11/2019 | N/A | Executed | No former queue position
2018-08-03 09:27 | 2050-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | PLUMAS | HAMILTON BRANCH SUB | Storage | 0.01 | 9/5/2018 | 9/13/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-07-26 14:21 | 2051-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | STOREY SUB | Solar PV | 2 | 9/19/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-07-27 22:24 | 2052-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SOLANO | PEABODY SUB | Solar PV | 4.4464 | 9/19/2018 | N/A | N/A | N/A | N/A | Pass | 3/14/2019 | N/A | Executed | No former queue position
2018-08-09 15:15 | 2053-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | HICKS SUB | Storage | 0.005 | 9/19/2018 | 10/9/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-08-24 12:17 | 2054-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN LUIS OBISPO | TRANSMISSION | Solar PV | 0.81612 | 9/19/2018 | 2/7/2019 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-08-28 20:00 | 2055-RD | Fast Track | Fast Track | Withdrawn | 9/28/2019 | Withdrawn | Withdrawn | KINGS | GUERNSEY SUB | Engine | 1.538 | 9/19/2018 | 9/28/2018 | Fail Screens: B, F, G, H, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-08-17 12:59 | 2056-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA BARBARA | BUELLTON SUB | Storage | 0.35 | 9/26/2018 | 1/30/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-08-17 13:06 | 2057-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | VINEYARD SUB | Storage | 0.455 | 9/26/2018 | 10/30/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-08-30 13:35 | 2058-WD | Fast Track | Independent Study | Withdrawn | 10/1/2019 | Withdrawn | Withdrawn | LAKE | CLEAR LAKE SUB | Solar PV | 2 | 9/26/2018 | 10/11/2018 | Fail Screens: 2, 5, 10 | 12/17/2018 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-09-05 16:05 | 2059-WD | Fast Track | Fast Track | Withdrawn | 12/31/2019 | Withdrawn | Withdrawn | FRESNO | CALIFORNIA AVE SUB | Solar PV | 1.0928 | 9/26/2018 | 10/17/2018 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-09-05 16:17 | 2060-WD | Fast Track | Fast Track | Withdrawn | 12/31/2019 | Withdrawn | Withdrawn | KERN | LERDO SUB | Solar PV | 1.5118 | 9/26/2018 | 10/30/2018 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-09-05 16:38 | 2061-WD | Fast Track | Fast Track | Withdrawn | 12/31/2019 | Withdrawn | Withdrawn | KERN | CASTROVILLE SUB | Solar PV | 2.0737 | 9/26/2018 | 11/5/2018 | Fail Screens: 2, 4, 5, 6, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-09-06 16:28 | 2062-WD | Fast Track | Fast Track | Withdrawn | 12/31/2019 | Withdrawn | Withdrawn | MERCED | EL CAPITAN SUB | Solar PV | 1.11 | 9/26/2018 | 10/24/2018 | Fail Screens: 2, 5, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-09-06 17:32 | 2063-WD | Fast Track | Fast Track | Withdrawn | 12/31/2019 | Withdrawn | Withdrawn | KINGS | ANGIOLA SUB | Solar PV | 1.13 | 9/26/2018 | 10/17/2018 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-09-06 17:48 | 2064-WD | Fast Track | Fast Track | Withdrawn | 12/31/2019 | Withdrawn | Withdrawn | MERCED | EL CAPITAN SUB | Solar PV | 1.367 | 9/26/2018 | 10/17/2018 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-09-13 14:19 | 2065-WD | Fast Track | Independent Study | Withdrawn | 10/31/2019 | Withdrawn | Withdrawn | HUMBOLDT | BLUE LAKE SUB | Solar PV | 1 | 9/27/2018 | 10/12/2018 | Fail Screens: 2, 5, 10 | 12/18/2018 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-09-14 15:16 | 2066-WD | Fast Track | Fast Track | Withdrawn | 5/13/2019 | Withdrawn | Withdrawn | NAPA | HIGHWAY SUB | Solar PV | 0.996 | 10/3/2018 | 10/24/2018 | Fail Screens: 2, 4, 5, 10 | 12/5/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-08-28 11:22 | 2067-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | FRESNO | PINEDALE SUB | Storage | 0.01 | 10/3/2018 | 10/18/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-09-07 09:58 | 2068-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | MT EDEN SUB | Storage | 0.1 | 10/3/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-09-05 15:20 | 2069-RD | Detailed Study | Detailed Study | Withdrawn | 10/1/2019 | Withdrawn | Withdrawn | KERN | MARICOPA SUB | Cogeneration | 19 | 10/3/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-08-27 13:50 | 2070-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | STUART SUB | Storage | 0.00488 | 10/10/2018 | 10/25/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-09-05 16:48 | 2071-WD | Fast Track | Fast Track | Withdrawn | 12/31/2019 | Withdrawn | Withdrawn | KERN | LERDO SUB | Solar PV | 2.1084 | 10/10/2018 | 10/25/2018 | Fail Screens: 2, 5, 9, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-09-06 15:48 | 2072-WD | Fast Track | Fast Track | Withdrawn | 12/31/2019 | Withdrawn | Withdrawn | KERN | MCFARLAND SUB | Solar PV | 1.3091 | 10/10/2018 | 10/30/2018 | Fail Screens: 2, 5, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-09-14 04:15 | 2073-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | KERN | TEMBLOR SUB | Solar PV | 5 | 10/10/2018 | N/A | N/A | N/A | N/A | Pass | 8/16/2019 | N/A | Executed | No former queue position
2018-09-19 17:02 | 2074-WD | Fast Track | Fast Track | Withdrawn | 12/31/2019 | Withdrawn | Withdrawn | KINGS | ANGIOLA SUB | Other | 2.2 | 10/10/2018 | 10/24/2018 | Fail Screens: 2, 4, 10 | 12/13/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-09-20 14:46 | 2075-WD | Fast Track | Fast Track | Withdrawn | 12/15/2019 | Withdrawn | Withdrawn | MERCED | DOS PALOS SUB | Solar PV | 1 | 10/10/2018 | 11/05/2018 | Fail Screens: 2, 5, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-09-27 17:38 | 2076-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MONTEREY | GREEN VALLEY SUB | Solar PV | 1 | 10/10/2018 | 11/2/2018 | Fail Screens: D, F, G, H, J, K, L, M | 3/5/2019 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-08-30 16:45 | 2077-WD | Fast Track | Fast Track | Withdrawn | 5/20/2019 | Withdrawn | Withdrawn | CALAVERAS | FROGTOWN SUB | Hydro | 0.0896 | 10/17/2018 | 11/8/2018 | Fail Screens: 4, 5, 6, 7, 10 | 12/20/2018 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-09-07 09:10 | 2078-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | ALMADEN SUB | Storage | 0.006 | 10/17/2018 | 11/1/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-09-24 06:57 | 2079-WD | Independent Study | Independent Study | Withdrawn | 6/1/2020 | Withdrawn | Withdrawn | SUTTER | PEASE SUB | Other | 3.5 | 10/24/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-10-05 12:49 | 2080-WD | Fast Track | Fast Track | Active | 5/31/2020 | 12/17/2021 |  | FRESNO | REEDLEY SUB | Solar PV | 1.7203 | 10/24/2018 | 11/9/2018 | Fail Screens: 2, 10 | 12/24/2018 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-10-12 10:52 | 2081-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | OAKLAND X SUB | Storage | 0.036 | 10/24/2018 | 11/15/2018 | Fail Screens: J, M |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-10-05 12:51 | 2082-WD | Fast Track | Independent Study | Withdrawn | 5/31/2020 | Withdrawn | Withdrawn | MARIN | WESTLANDS SUB | Solar PV | 1.625 | 10/24/2018 | 11/20/2018 | Fail Screens: 2, 10 | 2/12/2019 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-10-03 15:17 | 2083-WD | Fast Track | Independent Study | Withdrawn | 10/24/2019 | Withdrawn | Withdrawn | SONOMA | NOVATO SUB | Solar PV | 0.98304 | 10/31/2018 | 11/21/2018 | Fail Screens: 2, 4, 5, 10 | 1/15/2019 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-10-03 15:26 | 2084-WD | Fast Track | Independent Study | Withdrawn | 10/24/2019 | Withdrawn | Withdrawn | SONOMA | NOVATO SUB | Solar PV | 1 | 10/31/2018 | 11/21/2018 | Fail Screens: 2, 4, 5, 10 | 1/15/2019 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-10-11 15:46 | 2085-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN MATEO | BELLE HAVEN SUB | Storage | 0.03 | 10/31/2018 | 3/29/2019 | Fail Screens: J, M |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-10-16 15:36 | 2086-WD | Independent Study | Independent Study | Withdrawn | 12/15/2019 | Withdrawn | Withdrawn | KINGS | TWISSELMAN SUB | Solar PV, Storage | 3.2 | 10/31/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-10-08 14:27 | 2087-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | WEST FRESNO SUB | Engine | 0.21 | 10/31/2018 | 12/4/2018 | Fail Screens: B, F, G | 2/21/2019 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-10-09 15:32 | 2088-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | LOYOLA SUB | Solar PV, Storage | 0.21 | 11/7/2018 | 1/24/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-10-05 12:50 | 2089-WD | Independent Study | Independent Study | Withdrawn | 5/31/2020 | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV | 0.21 | 11/7/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-10-05 12:54 | 2090-WD | Independent Study | Independent Study | Withdrawn | 5/31/2020 | Withdrawn | Withdrawn | FRESNO | WESTLANDS SUB | Solar PV | 0.21 | 11/7/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-09-19 15:20 | 2091-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | DIXON LANDING SUB | Storage | 0.195 | 11/7/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-10-05 09:56 | 2092-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | KERN | WASCO SUB | Solar PV | 17.1 | 11/7/2018 | N/A | N/A | N/A | N/A | Fail | 10/9/2019 | N/A | Executed | No former queue position
2018-10-25 07:07 | 2093-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SONOMA | CLOVERDALE SUB | Storage | 0.01 | 11/7/2018 | 11/16/2018 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-10-25 16:14 | 2094-RD | Detailed Study | Detailed Study | Withdrawn | 1/1/2021 | Withdrawn | Withdrawn | KERN | KERN OIL SUB | Solar PV | 3.875 | 11/7/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-10-17 14:38 | 2095-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SANTA CLARA | NEWARK SUB | Engine | 26.04 | 11/7/2018 | N/A | N/A | N/A | N/A | Pass | 5/2/2019 | 8/15/2019 | Executed | No former queue position
2018-10-09 12:40 | 2096-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | TWISSELMAN SUB | Solar PV | 1.6812 | 11/14/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-10-16 09:55 | 2097-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | TRANSMISSION | Solar PV | 4.2061 | 11/14/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-11-02 14:57 | 2098-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SONOMA | Customer Owned | Solar PV | 2.3142 | 11/21/2018 | 1/24/2019 | Fail Screens: J, K |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-11-09 14:59 | 2099-WD | Fast Track | Fast Track | Withdrawn | 12/15/2019 | Withdrawn | Withdrawn | KERN | TWISSELMAN SUB | Solar PV | 1.3009 | 11/21/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-10-22 14:21 | 2100-RD | Detailed Study | Detailed Study | Withdrawn | 6/3/2019 | Withdrawn | Withdrawn | MERCED | EL CAPITAN SUB | Turbine | 3.2 | 11/21/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-10-30 16:33 | 2101-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN MATEO | MILLBRAE SUB | Other | 0.5 | 11/21/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-11-08 16:32 | 2102-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | YOLO | WEST SACRAMENTO SUB | Solar PV, Storage | 1.052 | 12/5/2018 | 4/16/2020 | Fail Screens: B, K, M, S5 | 5/13/2020 | Fail | Pass | 9/2/2020 | N/A | Executed | No former queue position
2018-11-12 14:37 | 2103-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | OAKLAND D SUB | Solar PV, Storage | 0.3 | 12/5/2018 | 7/17/2020 | Fail Screens: I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-10-30 14:32 | 2104-WD | Fast Track | Fast Track | Withdrawn | 12/31/2019 | Withdrawn | Withdrawn | KINGS | ANGIOLA SUB | Solar PV | 2.2 | 12/5/2018 | 12/17/2018 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-11-01 12:49 | 2105-WD | Fast Track | Independent Study | Active | 12/15/2019 | 12/3/2021 |  | KERN | TAFT SUB | Solar PV | 2 | 12/5/2018 | 1/3/2019 | Fail Screens: 2, 4, 7, 9, 10 | 2/28/2019 | Fail | Pass | 8/16/2019 | N/A | Executed | No former queue position
2018-11-06 12:04 | 2106-WD | Fast Track | Fast Track | Withdrawn | 12/15/2019 | Withdrawn | Withdrawn | MERCED | ORTIGA SUB | Solar PV | 1.2714 | 12/5/2018 | 12/26/2018 | Fail Screens: 2, 4 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-11-12 20:31 | 2107-RD | Fast Track | Fast Track | Withdrawn | 12/31/2019 | Withdrawn | Withdrawn | CONTRA COSTA | HERDLYN SUB | Solar PV | 3.15 | 12/5/2018 | 1/4/2019 | Fail Screens: F, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-11-12 20:32 | 2108-RD | Fast Track | Fast Track | Withdrawn | 12/31/2019 | Withdrawn | Withdrawn | CONTRA COSTA | TIDEWATER SUB | Solar PV | 3.15 | 12/5/2018 | 1/22/2019 | Fail Screens: H, I, J, K, M | 4/8/2019 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-11-14 14:57 | 2109-WD | Fast Track | Fast Track | Withdrawn | 12/31/2019 | Withdrawn | Withdrawn | KINGS | ANGIOLA SUB | Solar PV | 0.0015 | 12/5/2018 | 12/17/2018 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-11-19 14:59 | 2110-RD | Fast Track | Fast Track | In Service | Not Provided | 4/14/2020 |  | KERN | TRANSMISSION | Solar PV | 18 | 12/5/2018 | 3/5/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-11-07 10:04 | 2111-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | KERN | SMYRNA SUB | Solar PV | 1.0413 | 12/5/2018 | 7/12/2019 | Fail Screens: B, D, I, J, K, L, M, S5 | 11/08/2019 | Fail | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-11-12 12:42 | 2112-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN MATEO | BELLE HAVEN SUB | Solar PV, Storage | 0.98 | 12/5/2018 | 7/20/2020 | Fail Screens: G, I, J, K, M | 9/23/2020 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-11-16 08:43 | 2113-WD | Fast Track | Fast Track | Withdrawn | 5/30/2020 | Withdrawn | Withdrawn | ALAMEDA | ARLINGTON SUB | Solar PV | 2.1624 | 12/5/2018 | 12/26/2018 | Fail Screens: 2, 4, 6, 9, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-11-28 16:17 | 2114-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | GUSTINE SUB | Turbine | 6.96 | 12/5/2018 | 12/26/2018 | Fail Screens: B, D, G, H, I, J, K, L, M | 3/7/2019 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-11-06 14:15 | 2115-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | SAN BENITO | Customer Owned | Solar PV | 4.36 | 12/12/2018 | N/A | N/A | N/A | N/A | Pass | 5/13/2019 | N/A | Executed | No former queue position
2018-12-04 12:49 | 2116-RD | Fast Track | Fast Track | In Service | Not Provided | In Service | 8/23/2019 | SAN FRANCISCO | SAN FRAN A (POTRERO PP) SUB | Solar PV | 0.02981 | 12/12/2018 | 1/2/2019 | Fail Screens: J, M |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-10-16 13:31 | 2117-RD | Fast Track | Fast Track | Withdrawn | 12/31/2019 | Withdrawn | Withdrawn | CONTRA COSTA | CLAYTON SUB | Solar PV | 3.15 | 12/19/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-12-05 14:27 | 2118-WD | Fast Track | Independent Study | Withdrawn | 12/15/2019 | Withdrawn | Withdrawn | KERN | TWISSELMAN SUB | Solar PV | 1.9913 | 12/19/2018 | 1/14/2019 | Fail Screens: 2, 4, 10 | 4/3/2019 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-12-10 12:56 | 2119-WD | Fast Track | Fast Track | Withdrawn | 7/1/2019 | Withdrawn | Withdrawn | SOLANO | PEABODY SUB | Wind | 0.28 | 12/19/2018 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-12-10 16:45 | 2120-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | SAN JOAQUIN | CHANNEL SUB | Engine | 0.375 | 12/19/2018 | 1/11/2019 | Fail Screens: B, F, J, K, M | 2/13/2019 | Fail | Pass | 8/22/2019 | N/A | Executed | No former queue position
2018-12-11 10:39 | 2121-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | CALAVERAS | CALAVERAS CEMENT SUB | Solar PV | 0.03605 | 12/19/2018 | 1/31/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-12-07 10:34 | 2122-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN MATEO | BELLE HAVEN SUB | Solar PV | 1.1647 | 12/19/2018 | 1/31/2019 | Fail Screens: I, J, K | 4/17/2019 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2018-11-27 13:46 | 2123-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | SAN JOAQUIN | TRACY SUB | Solar PV | 3.6 | 12/26/2018 | N/A | N/A | N/A | N/A | Pass | 5/1/2019 | N/A | Executed | No former queue position
2018-12-13 12:29 | 2124-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | FRESNO | MCCALL SUB | Solar PV | 1.4653 | 1/2/2019 | N/A | N/A | N/A | N/A | Pass | 5/2/2019 | N/A | Executed | No former queue position
2018-12-13 12:42 | 2125-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | FRESNO | MCCALL SUB | Solar PV | 1.45 | 1/2/2019 | N/A | N/A | N/A | N/A | Fail | 7/16/2019 | N/A | Executed | No former queue position
2018-12-12 10:13 | 2126-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | KERN OIL SUB | Solar PV | 1.7525 | 1/2/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-12-19 10:41 | 2127-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | WEBER SUB | Solar PV | 2.5036 | 1/2/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-12-20 15:20 | 2128-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA BARBARA | CUYAMA SUB | Solar PV | 2.5036 | 1/9/2019 | 3/5/2019 | Fail Screens: B, D, F, I, J, K, L, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-12-14 13:30 | 2129-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | VIERRA SUB | Solar PV | 2.64 | 1/16/2019 | 2/4/2019 | Fail Screens: J, K, M | 3/19/2019 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2018-12-11 16:30 | 2130-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | KERN OIL SUB | Solar PV | 1.7525 | 1/16/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-01-03 09:34 | 2131-WD | Independent Study | Independent Study | Withdrawn | 12/31/2022 | Withdrawn | Withdrawn | KERN | TEVIS SUB | Storage | 20 | 1/16/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-01-03 09:44 | 2132-WD | Independent Study | Independent Study | Withdrawn | 12/31/2022 | Withdrawn | Withdrawn | MERCED | MERCED SUB | Storage | 20 | 1/16/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-01-14 12:44 | 2133-RD | Fast Track | Fast Track | In Service | Not Provided | In Service | 2/28/2019 | ALAMEDA | VINEYARD SUB | Engine | 0.8 | 1/23/2019 | 2/6/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-01-11 13:11 | 2134-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | BIOLA SUB | Solar PV | 1.2 | 1/23/2019 | 1/30/2019 | Fail Screens: F, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-01-07 16:29 | 2135-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | TEVIS SUB | Solar PV | 2.012 | 1/30/2019 | 2/20/2019 | Fail Screens: B, D, F, G, H, I, J, K, L, M | 4/4/2019 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-01-10 10:19 | 2136-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | NAPA | PUEBLO SUB | Storage | 0.015 | 1/30/2019 | 2/6/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-01-10 14:53 | 2137-WD | Fast Track | Fast Track | Withdrawn | 12/16/2020 | Withdrawn | Withdrawn | SAN LUIS OBISPO | CARRIZO PLAINS SUB | Solar PV | 0.57118 | 1/30/2019 | 3/9/2019 | Fail Screens: 2, 4, 10 | 9/18/2019 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-01-10 18:43 | 2138-WD | Independent Study | Independent Study | In Service | 7/15/2020 | 12/15/2020 | 7/15/2021 | SOLANO | BAHIA SUB | Solar PV | 5 | 1/30/2019 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 5/21/2019 | N/A | Executed | No former queue position
2019-01-18 15:07 | 2139-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | YOLO | DAVIS SUB | Solar PV | 1.0759 | 1/30/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-01-18 15:26 | 2140-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | YOLO | DAVIS SUB | Solar PV | 1.0759 | 1/30/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-01-18 12:44 | 2141-WD | Fast Track | Fast Track | Withdrawn | 12/20/2019 | Withdrawn | Withdrawn | SONOMA | PETALUMA C SUB | Solar PV | 0.98304 | 2/6/2019 | 3/9/2019 | Fail Screens: 2, 4, 5, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-01-18 15:43 | 2142-WD | Fast Track | Independent Study | Active | 12/30/2019 | 6/3/2021 |  | MERCED | ORTIGA SUB | Fuel Cell, Solar PV | 1.675 | 2/6/2019 | 3/16/2019 | Fail Screens: 2, 4, 5, 10 | 6/5/2019 | Fail | Pass | 11/21/2019 | N/A | Executed | No former queue position
2019-01-11 14:13 | 2143-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | LAS POSITAS SUB | Engine | 2 | 2/6/2019 | 2/25/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-01-22 15:20 | 2144-WD | Fast Track | Fast Track | Withdrawn | 9/1/2019 | Withdrawn | Withdrawn | SONOMA | SILVERADO SUB | Solar PV | 3 | 2/6/2019 | 5/3/2019 | Fail Screens: 2, 4, 5, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-01-28 15:52 | 2145-RD | Fast Track | Fast Track | In Service | Not Provided | In Service | 7/9/2019 | SAN FRANCISCO | Customer Owned | Solar PV | 0.01967 | 2/13/2019 | 2/20/2019 | Fail Screens: A | 3/25/2019 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-02-07 17:11 | 2146-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN FRANCISCO | SAN FRAN A (POTRERO PP) SUB | Engine | 1.875 | 2/21/2019 | 4/15/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-02-05 10:47 | 2147-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SOLANO | PEABODY SUB | Solar PV | 0.934 | 2/21/2019 | 3/26/2019 | Fail Screens: F, G, H, J, K, L, M | 4/29/2019 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-02-05 16:00 | 2148-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | WASCO SUB | Solar PV | 0.52901 | 2/21/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-02-12 09:52 | 2149-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | KERMAN SUB | Solar PV | 0.936 | 2/27/2019 | 7/16/2019 | Fail Screens: J, K, M, S5 | 8/8/2019 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-02-12 15:45 | 2150-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | KERN | STOCKDALE SUB | Solar PV | 1.712 | 2/27/2019 | 7/25/2019 | Fail Screens: A, B, C, D, F, G, H, I, J, K, L, M, V1, S5, A1 | 8/26/2019 | Fail | Pass | 12/17/2019 | N/A | Executed | No former queue position
2019-02-13 14:16 | 2151-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | TEHAMA | TYLER SUB | Solar PV | 0.834 | 2/27/2019 | 3/20/2019 | Fail Screens: J, K, L, M, S5 | 4/22/2019 | Fail | Fail | 9/4/2019 | N/A | Executed | No former queue position
2019-02-05 10:12 | 2152-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN MATEO | SAN CARLOS SUB | Storage | 0.005 | 2/27/2019 | 3/18/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-01-28 13:05 | 2153-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | SAN FRAN H (MARTIN) SUB | Solar PV | 0.12977 | 2/27/2019 | 3/25/2019 | Fail Screens: I, J |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-02-19 18:52 | 2154-WD | Fast Track | Independent Study | In Service | 6/30/2020 | 8/20/2021 |  | CONTRA COSTA | BRENTWOOD SUB | Solar PV | 0.98304 | 3/6/2019 | 3/25/2019 | Fail Screens: 2, 4, 10 | 5/10/2019 | Fail | Pass | 11/16/2019 | N/A | Executed | No former queue position
2019-02-14 13:27 | 2155-WD | Independent Study | Independent Study | Withdrawn | 7/31/2020 | Withdrawn | Withdrawn | MARIN | PETALUMA C SUB | Solar PV | 2.5036 | 3/6/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-02-25 12:31 | 2156-WD | Fast Track | Fast Track | Withdrawn | 3/31/2020 | Withdrawn | Withdrawn | MARIN | PETALUMA C SUB | Solar PV | 0.98304 | 3/6/2019 | 3/25/2019 | Fail Screens: 2, 4, 5, 10 | 5/13/2019 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-02-04 10:50 | 2157-RD | Fast Track | Fast Track | In Service | 4/1/2020 |  |  | SANTA CLARA | MILPITAS SUB | Other | 0.2325 | 3/6/2019 | 3/17/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-02-07 11:21 | 2158-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | SAN LEANDRO U SUB | Fuel Cell | 0.245 | 3/6/2019 | 3/25/2019 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-02-19 18:34 | 2159-WD | Fast Track | Fast Track | Withdrawn | 3/31/2020 | Withdrawn | Withdrawn | NAPA | TULUCAY SUB | Solar PV | 0.98304 | 3/6/2019 | 3/25/2019 | Pass | 5/10/2019 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-02-19 18:44 | 2160-WD | Fast Track | Fast Track | Withdrawn | 3/31/2020 | Withdrawn | Withdrawn | NAPA | TULUCAY SUB | Solar PV | 0.98304 | 3/6/2019 | 3/25/2019 | Fail Screens: 2, 10 | 5/10/2019 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-02-25 21:25 | 2161-WD | Independent Study | Independent Study | Withdrawn | 10/1/2020 | Withdrawn | Withdrawn | KERN | KERN PP DIST SUB | Solar PV | 2 | 3/6/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-02-26 10:42 | 2162-RD | Fast Track | Fast Track | Withdrawn | 12/15/2020 | Withdrawn | Withdrawn | SONOMA | BELLEVUE SUB | Solar PV | 1 | 3/6/2019 | 4/4/2019 | Fail Screens: B, G, I, J, K, M | 6/12/2019 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-01-23 05:53 | 2163-WD | Fast Track | Fast Track | Withdrawn | 12/10/2020 | Withdrawn | Withdrawn | ALAMEDA | DUMBARTON SUB | Solar PV | 3 | 3/13/2019 | 4/3/2019 | Pass | 2019-08-23 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-02-04 13:28 | 2164-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | FREMONT SUB | Solar PV | 0.24625 | 3/13/2019 | 3/16/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2019-02-15 15:49 | 2165-WD | Independent Study | Independent Study | Withdrawn | 6/1/2021 | Withdrawn | Withdrawn | SUTTER | MERIDIAN SUB | Storage | 11.3795 | 3/13/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-02-18 08:16 | 2166-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN Z (EMBARCADERO) SUB | Storage | 0.88561 | 3/13/2019 | 4/5/2019 | Fail Screens: A | 7/1/2019 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-02-20 08:16 | 2167-WD | Independent Study | Independent Study | Withdrawn | 2/1/2022 | Withdrawn | Withdrawn | ALAMEDA | OAKLAND C (OAKLAND PP) SUB | Storage | 5.0974 | 3/13/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-02-11 15:25 | 2168-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | VINEYARD SUB | Storage | 0.475 | 3/20/2019 | 4/9/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-02-20 15:40 | 2169-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | MT EDEN SUB | Storage | 0.35 | 3/20/2019 | 4/18/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-02-21 11:32 | 2170-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN MATEO | EAST GRAND SUB | Storage | 0.28 | 3/20/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-02-06 17:30 | 2171-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | SAN JOAQUIN | TRANSMISSION-Customer Owned | Solar PV, Storage | 5.1351 | 3/20/2019 | N/A | N/A | N/A | N/A | Pass | 8/30/2019 | N/A | Executed | No former queue position
2019-03-06 08:55 | 2172-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | EL DORADO | APPLE HILL SUB | Storage | 0.005 | 3/20/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-02-07 11:34 | 2173-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | SAN FRAN Z (EMBARCADERO) SUB | Solar PV | 0.0345 | 3/27/2019 | 4/16/2019 | Fail Screens: J |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-03-05 13:01 | 2174-WD | Fast Track | Independent Study | Active | 4/1/2020 | 12/3/2021 |  | KERN | TAFT SUB | Solar PV | 2.1624 | 3/27/2019 | 4/26/2019 | Fail Screens: 2, 4, 5, 7, 9, 10 | 7/17/2019 | Fail | Pass | 10/31/2019 | N/A | Executed | No former queue position
2019-03-05 13:05 | 2175-WD | Fast Track | Independent Study | Active | 4/1/2020 | 12/3/2021 |  | KERN | TAFT SUB | Solar PV | 2.1624 | 3/27/2019 | 4/26/2019 | Fail Screens: 2, 4, 5, 7, 9, 10 | 7/18/2019 | Fail | Pass | 10/31/2019 | N/A | Executed | No former queue position
2019-03-14 14:23 | 2176-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Solar PV | 0.08652 | 3/27/2019 | 4/22/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-03-12 14:18 | 2177-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN MATEO | MENLO SUB | Storage | 0.02 | 3/27/2019 | 4/11/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-03-05 09:24 | 2178-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | MORGAN HILL SUB | Storage | 0.01 | 4/2/2019 | 4/22/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-03-13 15:24 | 2179-WD | Independent Study | Independent Study | In Service | 1/29/2021 | 11/6/2020 | 7/30/2021 | HUMBOLDT | JANES CREEK SUB | Solar PV | 2.1991 | 4/2/2019 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 7/25/2019 | 11/27/2019 | Executed | No former queue position
2019-03-22 10:32 | 2180-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | SAN FRAN F (MARINA) SUB | Storage | 0.015 | 4/2/2019 | 4/25/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-03-27 07:31 | 2181-WD | Independent Study | Independent Study | Active | 10/1/2023 |  |  | SANTA CLARA | MORGAN HILL SUB | Storage | 20 | 4/2/2019 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 10/11/2019 | N/A | Executed | No former queue position
2019-03-26 09:28 | 2182-WD | Fast Track | Fast Track | Withdrawn | 5/30/2021 | Withdrawn | Withdrawn | FRESNO | HURON SUB | Storage | 4.7077 | 4/2/2019 | 5/3/2019 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-03-27 16:17 | 2183-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA BARBARA | CUYAMA SUB | Solar PV | 2.5 | 4/2/2019 | 5/3/2019 | Fail Screens: B, D, F, G, I, J, K, L, M, V1, V2, S5, A1 | 7/31/2019 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-03-26 14:22 | 2184-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | KINGS | CORCORAN SUB | Solar PV | 4.125 | 4/10/2019 | N/A | N/A | N/A | N/A | Pass | 8/5/2019 | N/A | Executed | No former queue position
2019-03-20 12:47 | 2185-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SONOMA | MONROE SUB | Storage | 0.34278 | 4/10/2019 | 5/6/2019 | Pass | 6/17/2019 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-03-22 16:12 | 2186-RD | Fast Track | Fast Track | Withdrawn | 12/31/2020 | Withdrawn | Withdrawn | CONTRA COSTA | SAN RAMON SUB | Solar PV | 1.5 | 4/10/2019 | 5/16/2019 | Fail Screens: B, D, F, G, H, I, J, K, L, M, V1, V2, S5, A1 | 6/19/2019 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-03-27 13:15 | 2187-RD | Fast Track | Detailed Study | Active | 3/10/2020 |  |  | SAN JOAQUIN | TRACY SUB | Steam Turbine | 3 | 4/17/2019 | 6/19/2019 | Pass | 7/18/2019 | Fail | Pass | 4/2/2020 | N/A | Executed | No former queue position
2019-03-20 16:01 | 2188-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CLARA | HICKS SUB | Storage | 0.01 | 4/17/2019 | 5/8/2019 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-04-02 12:43 | 2189-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | Customer Owned | Solar PV | 3.875 | 4/17/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-04-10 15:20 | 2190-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | KINGSBURG SUB | Solar PV | 1.788 | 4/17/2019 | 5/29/2019 | Fail Screens: D, F, I, J, K, M, S5 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-03-07 10:47 | 2191-WD | Fast Track | Fast Track | Withdrawn | 7/31/2020 | Withdrawn | Withdrawn | SONOMA | LAKEVILLE SUB | Solar PV | 0.98304 | 4/24/2019 | 6/8/2019 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-04-05 14:24 | 2192-WD | Independent Study | Independent Study | In Service | 10/31/2019 | 7/29/2020 |  | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Solar PV | 0.11218 | 4/24/2019 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 11/5/2019 | N/A | Executed | No former queue position
2019-04-05 14:34 | 2193-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | KERN | BERRENDA A SUB | Solar PV | 5.85 | 4/24/2019 | N/A | N/A | N/A | N/A | Fail | 9/24/2019 | N/A | Executed | No former queue position
2019-04-04 10:22 | 2194-WD | Fast Track | Independent Study | Withdrawn | 7/15/2020 | Withdrawn | Withdrawn | CONTRA COSTA | HERDLYN SUB | Solar PV | 3.2012 | 4/24/2019 | 5/29/2019 | Fail Screens: 2, 5, 9, 10 | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-04-11 16:39 | 2195-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN MATEO | BAY MEADOWS SUB | Solar PV | 0.68703 | 4/24/2019 | 5/22/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-04-09 14:33 | 2196-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN MATEO | SAN CARLOS SUB | Other | 0.25 | 5/1/2019 | 6/14/2019 | Fail Screens: J | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-04-12 16:40 | 2197-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | GLENN | CAPAY SUB | Solar PV | 0.9875 | 5/1/2019 | N/A | N/A | N/A | N/A | Fail | 8/14/2019 | N/A | Executed | No former queue position
2019-04-25 12:33 | 2198-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | MONTEREY | SOLEDAD SUB | Wind | 5.64 | 5/1/2019 | N/A | N/A | N/A | N/A | Pass | 10/11/2019 | N/A | Executed | No former queue position
2019-03-19 15:05 | 2199-RD | Fast Track | Detailed Study | Withdrawn | 7/31/2021 | Withdrawn | Withdrawn | MONTEREY | GONZALES SUB | Storage | 1.02 | 5/8/2019 | 6/12/2019 | Fail Screens: B, D, F, G, H, I, J, K, L, M, V1, V2, S5, A1 | 7/8/2019 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-03-19 15:10 | 2200-RD | Fast Track | Detailed Study | Withdrawn | 6/1/2021 | Withdrawn | Withdrawn | MONTEREY | GONZALES SUB | Storage | 1.8 | 5/8/2019 | 6/12/2019 | Fail Screens: B, D, F, G, H, I, J, K, L, M, V1, V2, S5, A1 | 7/30/2019 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-03-26 15:41 | 2201-WD | Independent Study | Independent Study | Withdrawn | 2/1/2022 | Withdrawn | Withdrawn | ALAMEDA | OAKLAND L SUB | Storage | 6.8961 | 5/8/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-04-22 16:40 | 2202-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | CONTRA COSTA | MEADOW LANE SUB | Solar PV | 1 | 2019-05-13 | 6/3/2019 | Fail Screens: G, H, J, K, M, S5 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-04-22 16:41 | 2203-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | CONTRA COSTA | MEADOW LANE SUB | Solar PV | 1 | 2019-05-13 | 6/3/2019 | Fail Screens: D, G, H, J, K, L, M, S5 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-04-22 16:42 | 2204-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | CONTRA COSTA | MEADOW LANE SUB | Solar PV | 1 | 5/8/2019 | 5/23/2019 | Fail Screens: G, H, I, J, K, M, V1, S5 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-04-12 09:40 | 2205-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | STROUD SUB | Solar PV | 2.333 | 5/8/2019 | 5/31/2019 | Fail Screens: I, J, K, M, V1, V2, S5, A1 | 8/6/2019 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-04-18 17:33 | 2206-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | OAKLAND K (CLAREMONT) SUB | Storage | 0.01 | 5/8/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-04-26 17:51 | 2207-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | MCKEE SUB | Storage | 0.01 | 5/8/2019 | 5/17/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-04-30 10:13 | 2208-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MONTEREY | DEL MONTE SUB | Storage | 0.01 | 5/8/2019 | 6/13/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-04-30 16:35 | 2209-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA BARBARA | SANTA MARIA SUB | Solar PV | 2.25 | 5/15/2019 | 5/23/2019 | Fail Screens: F, I, J, K, M | 7/2/2019 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-04-24 16:01 | 2210-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN MATEO | LAS PULGAS SUB | Storage | 0.005 | 5/22/2019 | 6/18/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-03-29 15:47 | 2211-WD | Fast Track | Fast Track | Withdrawn | 11/29/2019 | Withdrawn | Withdrawn | KERN | SMYRNA SUB | Fuel Cell | 1.75 | 5/22/2019 | 6/6/2019 | Fail Screens: 2, 4, 10 | 8/6/2019 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-03-29 16:44 | 2212-WD | Independent Study | Independent Study | Withdrawn | 2/26/2021 | Withdrawn | Withdrawn | MADERA | NEWHALL SUB | Fuel Cell | 3.5 | 5/22/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-04-06 14:47 | 2213-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MONTEREY | PACIFIC GROVE SUB | Storage | 0.01 | 5/22/2019 | 6/18/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-05-01 08:10 | 2214-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | CONTRA COSTA | MEADOW LANE SUB | Storage | 0.005 | 5/22/2019 | 6/19/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-05-15 13:15 | 2215-RD | Fast Track | Fast Track | In Service | Not Provided | In Service | 7/12/2019 | SAN FRANCISCO | SAN FRAN Z (EMBARCADERO) SUB | Solar PV | 0.06599 | 5/22/2019 | 6/13/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-05-15 13:29 | 2216-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Solar PV | 0.03199 | 5/22/2019 | 5/23/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-05-07 13:04 | 2217-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | SAN FRAN M SUB | Storage | 0.01 | 5/22/2019 | 6/18/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-05-09 03:06 | 2218-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | YOLO | DUNNIGAN SUB | Storage | 0.21 | 5/22/2019 | 6/25/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-05-10 05:00 | 2219-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SHASTA | ANDERSON SUB | Storage | 0.21 | 5/22/2019 | 6/26/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-05-10 05:07 | 2220-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | EDENVALE SUB | Storage | 0.21 | 5/22/2019 | 6/25/2019 | Fail Screens: D |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-05-10 22:16 | 2221-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MARIN | NOVATO SUB | Storage | 0.21 | 5/22/2019 | 6/25/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-05-16 08:22 | 2222-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN MATEO | SAN MATEO SUB | Solar PV, Storage | 1.5659 | 5/29/2019 | 6/19/2019 | Fail Screens: I, J, K, M | 8/28/2019 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-05-17 09:44 | 2223-WD | Independent Study | Independent Study | Withdrawn | 2/1/2021 | Withdrawn | Withdrawn | FRESNO | HURON SUB | Storage | 6.37 | 5/29/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-05-21 13:53 | 2224-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CLARA | HICKS SUB | Other, Solar PV | 0.98658 | 5/29/2019 | 6/25/2019 | Fail Screens: D | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-05-01 09:03 | 2225-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | CASTRO VALLEY SUB | Storage | 0.02 | 6/4/2019 | 6/6/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-04-17 17:37 | 2226-WD | Independent Study | Independent Study | Active | 5/1/2020 |  |  | FRESNO | PANOCHE SUB | Solar PV | 4.4 | 6/4/2019 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 4/3/2020 | N/A | Executed | No former queue position
2019-04-01 17:25 | 2227-RD | Detailed Study | Detailed Study | Withdrawn | 1/1/2022 | Withdrawn | Withdrawn | LASSEN | MCARTHUR SUB | Engine | 3.6 | 6/11/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-05-29 12:01 | 2228-RD | Fast Track | Detailed Study | In Service | Not Provided |  |  | KERN | LAMONT SUB | Solar PV | 0.8257 | 2019-06-24 | 10/24/2019 | Fail Screens: D, I, J, K, M, V1, V2, S5, A1 | 11/12/2019 | Fail | Fail | 2/4/2020 | N/A | Executed | No former queue position
2019-05-15 08:51 | 2229-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | PLACER | RIO DEL MAR SUB | Storage | 0.21 | 6/11/2019 | 8/20/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-05-22 14:21 | 2230-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | FRESNO | ORO LOMA SUB | Solar PV | 2 | 6/11/2019 | N/A | N/A | N/A | N/A | Pass | 2020-02-07 | N/A | Executed | No former queue position
2019-05-24 06:48 | 2231-RD | Fast Track | Fast Track | Withdrawn | 2/17/2020 | Withdrawn | Withdrawn | LAKE | KONOCTI SUB | Other | 0.2754 | 6/11/2019 | 6/27/2019 | Fail Screens: B, F, G, I, J, M | 8/30/2019 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-05-28 11:42 | 2232-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | SAN FRAN A (POTRERO PP) SUB | Engine | 1 | 6/19/2019 | 7/18/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-05-30 16:08 | 2233-WD | Fast Track | Fast Track | In Service | 3/31/2020 | 7/10/2020 | 12/4/2020 | NAPA | TULUCAY SUB | Solar PV | 0.99 | 6/19/2019 | 7/10/2019 | Fail Screens: 2, 10 | 8/14/2019 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-05-30 16:12 | 2234-WD | Fast Track | Fast Track | In Service | 3/31/2020 | 7/10/2020 | 12/7/2020 | NAPA | TULUCAY SUB | Solar PV | 0.99 | 6/19/2019 | 7/10/2019 | Fail Screens: 2, 10 | 8/14/2019 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-05-21 17:52 | 2235-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | CONTRA COSTA | EL CERRITO G SUB | Storage | 0.02799 | 6/19/2019 | 9/3/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-06-03 10:28 | 2236-RD | Fast Track | Detailed Study | In Service | Not Provided |  |  | ALAMEDA | LAS POSITAS SUB | Solar PV, Storage | 1.4775 | 6/19/2019 | 7/12/2019 | Fail Screens: D, F, K, L, M | 9/12/2019 | Fail | Pass | 6/9/2020 | N/A | Executed | No former queue position
2019-06-07 15:18 | 2237-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | NEWARK SUB | Storage | 0.2316 | 6/19/2019 | 9/3/2019 | Fail Screens: G, I, J, V1, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-06-14 08:52 | 2238-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Solar PV | 0.04022 | 6/19/2019 | 7/11/2019 | Fail Screens: A | 9/12/2019 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-06-14 08:59 | 2239-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Solar PV | 0.01651 | 6/19/2019 | 7/11/2019 | Fail Screens: A | 9/12/2019 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-05-23 12:37 | 2240-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SOLANO | CORDELIA SUB | Solar PV | 1.2321 | 6/26/2019 | 2/26/2020 | Fail Screens: I, L, M, S5 | 3/31/2020 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-06-07 13:27 | 2241-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN JOAQUIN | LAMMERS SUB | Storage | 0.49 | 7/2/2019 | 7/31/2019 | Fail Screens: B, F, I, J, K, L, M, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-06-28 08:16 | 2242-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Solar PV | 0.02902 | 7/2/2019 | 7/17/2019 | Fail Screens: A | 8/20/2019 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-06-10 15:14 | 2243-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | BONITA SUB | Solar PV | 1.9817 | 7/10/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-05-22 14:45 | 2244-WD | Independent Study | Independent Study | Withdrawn | 4/27/2020 | Withdrawn | Withdrawn | SONOMA | SONOMA A SUB | Other | 0.71 | 7/17/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-06-19 13:12 | 2245-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SONOMA | RINCON SUB | Storage | 0.01 | 7/17/2019 | 7/22/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-06-25 07:44 | 2246-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | DAIRYLAND SUB | Solar PV | 0.975 | 2019-08-13 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-06-25 15:42 | 2247-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | NORTECH SUB | Storage | 0.11021 | 2019-09-24 | 10/16/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-06-28 09:55 | 2248-WD | Independent Study | Independent Study | Withdrawn | 4/1/2021 | Withdrawn | Withdrawn | FRESNO | HURON SUB | Storage | 12.48 | 7/17/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-07-08 18:03 | 2249-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | METCALF SUB | Turbine | 50 | 7/24/2019 | 8/9/2019 | Fail Screens: B, I, J, K | 11/22/2019 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-06-23 12:15 | 2250-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MARIN | ALTO SUB | Engine | 1.6 | 7/24/2019 | 10/3/2019 | Fail Screens: B, D, J, M, V2, S5, A1 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-07-10 12:14 | 2251-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | OAKLAND X SUB | Storage | 0.21 | 7/24/2019 | 8/19/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-07-10 12:19 | 2252-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | CONTRA COSTA | CLAYTON SUB | Storage | 0.21 | 7/24/2019 | 8/19/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-07-10 19:54 | 2253-WD | Fast Track | DGSP | Withdrawn | 6/30/2020 | Withdrawn | Withdrawn | HUMBOLDT | BLUE LAKE SUB | Solar PV | 0.98304 | 7/24/2019 | 8/14/2019 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-07-10 19:59 | 2254-WD | Fast Track | DGSP | Withdrawn | 6/30/2020 | Withdrawn | Withdrawn | HUMBOLDT | BLUE LAKE SUB | Solar PV | 0.98304 | 7/24/2019 | 8/14/2019 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-06-07 15:46 | 2255-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | EL CAPITAN SUB | Micro Turbine | 3.2 | 7/31/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-06-07 15:47 | 2256-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | WILSON SUB | Micro Turbine | 3.2 | 7/31/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-07-10 09:59 | 2257-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SOLANO | VACAVILLE SUB | Storage | 0.21 | 7/31/2019 | 8/19/2019 | Fail Screens: S5, A1 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-07-10 11:36 | 2258-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | VINEYARD SUB | Storage | 0.21 | 7/31/2019 | 8/28/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-07-10 11:53 | 2259-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | LLAGAS SUB | Storage | 0.21 | 7/31/2019 | 8/26/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-07-10 11:57 | 2260-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MADERA | STOREY SUB | Storage | 0.21 | 7/31/2019 | 10/4/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-07-10 12:02 | 2261-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MENDOCINO | WILLITS A SUB | Storage | 0.21 | 7/31/2019 | 10/2/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-07-10 12:09 | 2262-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | FRESNO | MCCALL SUB | Storage | 0.21 | 7/31/2019 | 9/12/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-07-10 12:25 | 2263-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN LUIS OBISPO | OCEANO SUB | Storage | 0.21 | 7/31/2019 | 9/4/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-07-10 12:28 | 2264-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | KERN | WESTPARK SUB | Storage | 0.21 | 7/31/2019 | 9/4/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-07-02 19:00 | 2265-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MONTEREY | HATTON SUB | Storage | 0.01 | 7/31/2019 | 8/21/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-07-10 12:34 | 2266-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | FRESNO | PANOCHE SUB | Storage | 0.21 | 7/31/2019 | 9/4/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-07-10 12:46 | 2267-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | NORCO SUB | Storage | 0.21 | 7/31/2019 | 9/4/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-07-10 12:49 | 2268-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MONTEREY | PRUNEDALE SUB | Storage | 0.21 | 7/31/2019 | 9/4/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-07-10 13:13 | 2269-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | NORTH DUBLIN SUB | Storage | 0.21 | 7/31/2019 | 9/4/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-07-03 11:08 | 2270-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | SARATOGA SUB | Storage | 0.015 | 8/7/2019 | 8/23/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-07-17 10:11 | 2271-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | Withdrawn | Engine | 1.5 | 8/14/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-07-20 14:30 | 2272-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN LUIS OBISPO | GOLDTREE SUB | Storage | 0.01 | 8/14/2019 | 9/4/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-07-30 03:54 | 2273-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | CONTRA COSTA | LAKEWOOD SUB | Storage | 0.21 | 8/14/2019 | 8/28/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-07-28 22:54 | 2274-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN LUIS OBISPO | PASO ROBLES SUB | Storage | 0.21 | 8/14/2019 | 9/3/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-07-29 14:52 | 2275-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | SANTA CLARA | EVERGREEN SUB | Solar PV | 1.17 | 8/14/2019 | N/A | N/A | N/A | N/A | Pass | 2/28/2020 | N/A | Executed | No former queue position
2019-07-22 16:04 | 2276-WD | Fast Track | Fast Track | Withdrawn | 9/30/2020 | Withdrawn | Withdrawn | MERCED | ORTIGA SUB | Storage | 2.94 | 8/21/2019 | 9/20/2019 | Fail Screens: 2, 4, 5, 7, 9, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-07-24 14:38 | 2277-RD | Fast Track | Fast Track | Active | Not Provided |  |  | MONTEREY | CASTROVILLE SUB | Engine | 3 | 8/21/2019 | 9/25/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-07-30 04:22 | 2278-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | GLENN | WILLOWS A SUB | Storage | 0.21 | 8/21/2019 | 8/29/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-07-30 04:25 | 2279-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | LAS POSITAS SUB | Storage | 0.21 | 8/21/2019 | 9/11/2019 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-07-30 04:28 | 2280-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | OAKLAND D SUB | Storage | 0.21 | 8/21/2019 | 9/10/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-07-30 04:33 | 2281-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN JOAQUIN | LAMMERS SUB | Storage | 0.21 | 8/21/2019 | 9/27/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-07-30 04:17 | 2282-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | LOS GATOS SUB | Storage | 0.21 | 8/21/2019 | 9/18/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-07-30 22:08 | 2283-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN MATEO | HALF MOON BAY SUB | Storage | 0.21 | 8/21/2019 | 9/12/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-07-31 21:47 | 2284-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Storage | 0.21 | 8/21/2019 | 9/12/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-08-01 23:39 | 2285-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN JOAQUIN | EIGHT MILE SUB | Storage | 0.21 | 8/21/2019 | 10/1/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-08-01 23:46 | 2286-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | CASTRO VALLEY SUB | Storage | 0.21 | 8/21/2019 | 9/25/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-07-12 08:36 | 2287-WD | Fast Track | Fast Track | In Service | 7/1/2020 | 1/19/2022 |  | NAPA | TULUCAY SUB | Solar PV | 0.6582 | 8/28/2019 | 9/24/2019 | Fail Screens: 2, 7, 10 | 11/5/2019 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-07-23 11:06 | 2288-WD | Fast Track | Fast Track | Withdrawn | 2/28/2020 | Withdrawn | Withdrawn | KINGS | AVENAL SUB | Storage | 4.158 | 8/28/2019 | 10/10/2019 | Fail Screens: 2, 4, 10 | 1/27/2020 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-08-01 23:50 | 2289-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | FRESNO | MALAGA SUB | Storage | 0.21 | 8/28/2019 | 9/17/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-08-01 13:50 | 2290-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | TRANSMISSION | Solar PV | 10.11 | 8/28/2019 | N/A | N/A | N/A | N/A | Fail | 4/2/2020 | N/A | Executed | No former queue position
2019-08-05 13:31 | 2291-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | COPUS SUB | Solar PV | 2.53 | 8/28/2019 | 10/23/2019 | Fail Screens: B, D, I, J, K, L, M, V1, V2, S5, A1 | 12/2/2019 | Fail | Fail | 7/31/2020 | Withdrawn | Withdrawn | No former queue position
2019-08-06 17:17 | 2292-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CLARA | TRANSMISSION | Solar PV | 3.6091 | 9/4/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-08-09 11:16 | 2293-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | WEST FRESNO SUB | Solar PV | 2.125 | 9/4/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-08-09 11:43 | 2294-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | TULARE | KINGSBURG SUB | Solar PV | 3.875 | 9/4/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-08-12 14:23 | 2295-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | YOLO | WOODLAND SUB | Solar PV | 0.9875 | 9/4/2019 | N/A | N/A | N/A | N/A | Pass | 1/13/2020 | N/A | Executed | No former queue position
2019-08-14 18:33 | 2296-WD | Independent Study | DGSP | In Service | 12/30/2020 | 11/30/2021 |  | CONTRA COSTA | BRENTWOOD SUB | Solar PV | 4.9152 | 9/4/2019 | N/A | N/A | N/A | N/A | Fail | 2020-02-25 | N/A | Executed | No former queue position
2019-08-05 16:51 | 2297-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN JOAQUIN | STOCKTON A SUB | Other, Storage | 0.99 | 9/4/2019 | 1/21/2020 | Fail Screens: B, G, I, J, M, V1, V2, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-08-12 18:29 | 2298-RD | Fast Track | Fast Track | Withdrawn | 3/15/2021 | Withdrawn | Withdrawn | MARIN | COTATI SUB | Solar PV | 0.96 | 9/4/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-07-12 10:46 | 2299-WD | Fast Track | Independent Study | Withdrawn | 8/28/2020 | Withdrawn | Withdrawn | LAKE | HARTLEY SUB | Storage | 2.475 | 9/4/2019 | 10/10/2019 | Fail Screens: 2, 4, 5, 9, 10 | 2/20/2020 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-08-12 11:19 | 2300-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | KERN | COPUS SUB | Solar PV | 2.7964 | 9/4/2019 | 11/8/2019 | Fail Screens: B, D, F, I, J, K, L, M, V1, V2, S5, A1 | 12/30/2019 | Fail | Fail | 5/27/2020 | N/A | Executed | No former queue position
2019-08-12 21:30 | 2301-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | CARNERAS SUB | Solar PV, Storage | 1.6088 | 9/4/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-08-12 23:48 | 2302-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | JARVIS SUB | Storage | 0.21 | 9/4/2019 | 10/1/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-08-07 07:29 | 2303-WD | Fast Track | Fast Track | Withdrawn | 4/27/2020 | Withdrawn | Withdrawn | SONOMA | SONOMA A SUB | Storage | 0.71 | 9/11/2019 | 10/1/2019 | Fail Screens: 2, 4, 5, 10 | 11/27/2019 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-08-01 12:46 | 2304-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | PLACER | PLEASANT GROVE SUB | Solar PV | 0.58853 | 9/11/2019 | 11/4/2019 | Fail Screens: D, H, I, J, K, L | 1/22/2020 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-08-02 12:48 | 2305-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | LOS GATOS SUB | Storage | 0.01 | 9/11/2019 | 9/25/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-08-20 10:24 | 2306-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | SHAFTER SUB | Solar PV | 0.9 | 9/11/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-08-06 18:17 | 2307-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN MATEO | MENLO SUB | Storage | 0.015 | 9/11/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-08-20 11:49 | 2308-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | TRANSMISSION | Solar PV | 4.98 | 9/18/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-08-21 09:48 | 2309-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | SAN FRAN J SUB | Storage | 0.005 | 9/18/2019 | 10/1/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-08-27 07:24 | 2310-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MARIN | ALTO SUB | Storage | 0.015 | 9/18/2019 | 11/18/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-08-29 13:32 | 2311-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SONOMA | BELLEVUE SUB | Storage | 0.03026 | 9/18/2019 | 10/2/2019 | Fail Screens: D, I, J, M, V1, S5 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-08-18 15:28 | 2312-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MARIN | IGNACIO SUB | Storage | 0.025 | 9/25/2019 | 10/9/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-07-12 10:44 | 2313-WD | Fast Track | Independent Study | Withdrawn | 8/28/2020 | Withdrawn | Withdrawn | YUBA | PLUMAS SUB | Storage | 3.9731 | 9/25/2019 | 10/14/2019 | Fail Screens: 2, 4, 5, 6, 7, 9, 10 | 2/4/2020 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-08-20 14:46 | 2314-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SONOMA | CORONA SUB | Storage | 0.03026 | 9/25/2019 | 11/7/2019 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-08-27 08:15 | 2315-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MARIN | ALTO SUB | Storage | 0.01 | 9/25/2019 | 10/9/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-08-29 17:26 | 2316-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MARIN | LAS GALLINAS A SUB | Battery | 0.02 | 9/25/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-08-10 11:41 | 2317-WD | Fast Track | Fast Track | Withdrawn | 12/30/2021 | Withdrawn | Withdrawn | SAN MATEO | EAST GRAND SUB | Solar PV | 2.341 | 9/25/2019 | 10/24/2019 | Fail Screens: 2, 10 | 2/7/2020 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-08-30 13:15 | 2318-WD | Fast Track | Fast Track | Withdrawn | 12/15/2020 | Withdrawn | Withdrawn | SONOMA | BELLEVUE SUB | Solar PV | 0.91245 | 9/25/2019 | 10/16/2019 | Fail Screens: 2, 5, 10 | 12/10/2019 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-07-22 14:58 | 2319-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | TRANSMISSION | Solar PV, Storage | 4.9 | 9/25/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-08-30 11:49 | 2320-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SONOMA | RINCON SUB | Storage | 0.015 | 9/25/2019 | 10/16/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-09-03 15:15 | 2321-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | LOYOLA SUB | Storage | 0.015 | 9/25/2019 | 10/16/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-08-28 11:39 | 2322-WD | Independent Study | Independent Study | Withdrawn | 12/31/2021 | Withdrawn | Withdrawn | SAN JOAQUIN | CHEROKEE SUB | Storage | 9.95 | 10/1/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-09-09 18:34 | 2323-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MONTEREY | CARMEL SUB | Storage | 0.015 | 10/1/2019 | 10/2/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-09-13 13:45 | 2324-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MERCED | SANTA NELLA SUB | Engine | 6.387 | 10/1/2019 | 12/4/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-10-01 14:17 | 2325-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Solar PV | 0.05 | 10/9/2019 | 10/28/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-09-24 16:14 | 2326-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | FRESNO | MCCALL SUB | Solar PV | 0.24971 | 10/9/2019 | 10/16/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-09-11 16:11 | 2327-WD | Fast Track | Fast Track | Active | 10/1/2020 | 4/9/2021 |  | MADERA | STOREY SUB | Solar PV | 1.5 | 10/9/2019 | 10/28/2019 | Pass | 12/23/2019 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-08-30 12:47 | 2328-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN LUIS OBISPO | SAN LUIS OBISPO SUB | Storage | 0.715 | 10/16/2019 | 12/9/2019 | Fail Screens: G, I, J, K, M | 2/21/2020 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-09-13 17:21 | 2329-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | SAN RAMON SUB | Storage | 0.66124 | 10/16/2019 | 3/3/2021 | Fail Screens: I, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-09-16 11:25 | 2330-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | PLACER | DEL MAR SUB | Solar PV, Storage | 0.43734 | 10/16/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-09-11 16:42 | 2331-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | ATWATER SUB | Solar PV, Storage | 1.4 | 10/16/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-09-27 16:30 | 2332-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SONOMA | DUNBAR SUB | Storage | 0.02 | 10/23/2019 | 11/14/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-09-30 07:44 | 2333-WD | Fast Track | Fast Track | In Service | 3/20/2020 | 10/8/2021 |  | CONTRA COSTA | CONTRA COSTA SUB | Solar PV | 0.9375 | 10/23/2019 | 11/18/2019 | Fail Screens: 2, 5, 10 | 1/6/2020 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-10-01 16:15 | 2334-WD | Fast Track | Fast Track | Withdrawn | 9/29/2020 | Withdrawn | Withdrawn | KINGS | HENRIETTA SUB | Solar PV | 3 | 10/23/2019 | 10/31/2019 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-10-01 16:26 | 2335-WD | Fast Track | Fast Track | Withdrawn | 9/29/2020 | Withdrawn | Withdrawn | KERN | WELLFIELD SUB | Solar PV | 3 | 10/23/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-10-02 12:04 | 2336-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MONTEREY | KING CITY SUB | Micro Turbine | 3 | 10/23/2019 | 11/25/2019 | Fail Screens: B, D, G, H, I, J, K, L, M, S5 | 1/16/2020 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-10-02 16:11 | 2337-WD | Fast Track | Fast Track | Withdrawn | 9/29/2020 | Withdrawn | Withdrawn | FRESNO | CARUTHERS SUB | Solar PV | 0.8 | 10/23/2019 | 11/5/2019 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-10-02 16:21 | 2338-WD | Independent Study | Independent Study | Withdrawn | 9/29/2020 | Withdrawn | Withdrawn | MERCED | ORTIGA SUB | Storage | 4.48 | 10/23/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-10-03 09:38 | 2339-WD | Fast Track | Fast Track | Withdrawn | 9/29/2020 | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV | 3 | 10/23/2019 | 11/5/2019 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-10-03 09:46 | 2340-WD | Fast Track | Fast Track | Withdrawn | 9/29/2020 | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV | 3 | 10/23/2019 | 11/6/2019 | Fail Screens: 2, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-08-21 12:31 | 2341-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | KERN | KERN OIL SUB | Solar PV, Storage | 5.8767 | 10/30/2019 | N/A | N/A | N/A | N/A | Pass | 2/13/2020 | N/A | Executed | No former queue position
2019-10-02 11:54 | 2342-WD | Fast Track | Independent Study | Withdrawn | 11/2/2020 | Withdrawn | Withdrawn | LAKE | UPPER LAKE SUB | Storage | 2.475 | 10/30/2019 | 11/26/2019 | Fail Screens: 2, 4, 5, 10 | 2/19/2020 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-10-02 11:56 | 2343-WD | Fast Track | Independent Study | Withdrawn | 11/2/2020 | Withdrawn | Withdrawn | MENDOCINO | HOPLAND SUB | Storage | 2.475 | 10/30/2019 | 11/26/2019 | Fail Screens: 2, 4, 5, 10 | 2/19/2020 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-10-02 12:02 | 2344-WD | Fast Track | Fast Track | Withdrawn | 11/2/2020 | Withdrawn | Withdrawn | MENDOCINO | WILLITS A SUB | Storage | 2.475 | 10/30/2019 | 11/26/2019 | Fail Screens: 2, 10 | 2/19/2020 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-10-02 12:05 | 2345-WD | Fast Track | Fast Track | Withdrawn | 11/2/2020 | Withdrawn | Withdrawn | SONOMA | MOLINO SUB | Storage | 2.475 | 10/30/2019 | 11/26/2019 | Fail Screens: 2, 4, 5, 10 | 2/19/2020 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-10-03 09:51 | 2346-WD | Fast Track | Fast Track | Withdrawn | 10/1/2020 | Withdrawn | Withdrawn | KINGS | TWISSELMAN SUB | Solar PV, Storage | 3.95 | 10/30/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-10-03 09:51 | 2347-WD | Fast Track | Fast Track | Withdrawn | 10/1/2020 | Withdrawn | Withdrawn | KINGS | TWISSELMAN SUB | Solar PV, Storage | 4.274 | 10/30/2019 | 11/27/2019 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-10-04 16:29 | 2348-WD | Fast Track | Fast Track | Withdrawn | 11/1/2020 | Withdrawn | Withdrawn | KINGS | ANGIOLA SUB | Solar PV | 2.2 | 10/30/2019 | 11/22/2019 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-10-04 16:29 | 2349-WD | Fast Track | Fast Track | Withdrawn | 11/2/2020 | Withdrawn | Withdrawn | KINGS | ANGIOLA SUB | Solar PV | 2.2 | 10/30/2019 | 11/22/2019 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-10-14 14:59 | 2350-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | FRESNO | KERMAN SUB | Solar PV | 0.65635 | 10/30/2019 | 12/9/2019 | Fail Screens: B, D, F, I, J, K, L, M, S5 | 1/8/2020 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-10-01 16:43 | 2351-WD | Independent Study | Independent Study | Withdrawn | 9/29/2020 | Withdrawn | Withdrawn | MERCED | CANAL SUB | Storage | 9.4096 | 10/30/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-10-18 10:34 | 2352-WD | Fast Track | Fast Track | Withdrawn | 12/30/2021 | Withdrawn | Withdrawn | SAN MATEO | DALY CITY SUB | Storage | 2.52 | 11/6/2019 | 11/27/2019 | Fail Screens: 2, 10 | 3/5/2020 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-10-18 17:03 | 2353-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | SAN JOAQUIN | WEBER SUB | Solar PV | 2.6416 | 11/6/2019 | N/A | N/A | N/A | N/A | Fail | 4/23/2020 | N/A | Executed | No former queue position
2019-10-15 14:08 | 2354-WD | Fast Track | Independent Study | Withdrawn | 12/14/2020 | Withdrawn | Withdrawn | SONOMA | COTATI SUB | Storage | 2.25 | 11/13/2019 | 11/27/2019 | Fail Screens: 2, 10 | 2/19/2020 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-10-17 09:54 | 2355-WD | Fast Track | Fast Track | Withdrawn | 9/30/2020 | Withdrawn | Withdrawn | KINGS | ALPAUGH SUB | Solar PV | 3 | 11/13/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-10-15 14:22 | 2356-WD | Fast Track | Independent Study | Withdrawn | 12/14/2020 | Withdrawn | Withdrawn | YUBA | EAST MARYSVILLE SUB | Storage | 2.25 | 11/13/2019 | 11/27/2019 | Fail Screens: 2, 4, 5, 10 | 3/3/2020 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-10-21 10:58 | 2357-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | MOSHER SUB | Solar PV | 2.686 | 11/13/2019 | 12/9/2019 | Fail Screens: D, G, H, J, K, L, M, V1, S5, A1 | 2/7/2020 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-10-25 11:03 | 2358-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | CONTRA COSTA | MORAGA SUB | Storage | 0.01 | 11/13/2019 | 12/3/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-09-27 09:42 | 2359-RD | Detailed Study | Detailed Study | Withdrawn | 7/1/2021 | Withdrawn | Withdrawn | KERN | TWISSELMAN SUB | Engine | 4.0842 | 11/20/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-10-04 11:01 | 2360-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MONTEREY | CARMEL SUB | Storage | 0.005 | 11/20/2019 | 12/3/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-10-17 09:16 | 2361-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | HICKS SUB | Storage | 0.01 | 11/20/2019 | 12/13/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-10-22 13:17 | 2362-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | BUTTE | OROVILLE SUB | Solar PV | 0.3125 | 11/20/2019 | 1/16/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-10-22 16:56 | 2363-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN JOAQUIN | TRANSMISSION-Customer Owned | Solar PV, Storage | 2.6326 | 11/20/2019 | 12/12/2019 | Fail Screens: D, F, G, I, J, K, L, M, S5 | 3/20/2020 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-11-01 14:39 | 2364-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | KERN | TEMBLOR SUB | Solar PV | 1.1216 | 11/20/2019 | N/A | N/A | N/A | N/A | Fail | 6/17/2020 | N/A | Executed | No former queue position
2019-10-16 14:48 | 2365-WD | Fast Track | Fast Track | Active | 3/15/2021 | 8/29/2021 |  | MARIN | COTATI SUB | Solar PV | 0.96 | 11/20/2019 | 12/18/2019 | Fail Screens: 2, 4, 10 | 3/2/2020 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-10-30 07:25 | 2366-WD | Fast Track | Fast Track | Withdrawn | 12/30/2021 | Withdrawn | Withdrawn | SAN MATEO | EAST GRAND SUB | Storage | 2.52 | 11/26/2019 | 1/24/2020 | Fail Screens: 2, 4, 10 | 3/5/2020 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-11-06 22:11 | 2367-RD | Fast Track | Fast Track | In Service | Not Provided | 4/24/2020 |  | MARIN | ALTO SUB | Storage | 0.21 | 11/26/2019 | 1/2/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-11-06 22:11 | 2368-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | SAN JOSE A SUB | Storage | 0.21 | 11/26/2019 | 1/3/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-11-09 12:08 | 2369-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN MATEO | MENLO SUB | Storage | 0.005 | 11/26/2019 | 12/9/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-11-13 20:06 | 2370-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | HICKS SUB | Solar PV | 0.998 | 11/26/2019 | 12/12/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-11-14 10:13 | 2371-RD | Fast Track | Fast Track | Active | 6/8/2020 | 1/29/2021 |  | LAKE | KONOCTI SUB | Engine | 0.2992 | 11/26/2019 | 12/11/2019 | Pass | 1/10/2020 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-11-12 08:42 | 2372-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | LOYOLA SUB | Storage | 0.015 | 12/4/2019 | 1/6/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-10-29 15:47 | 2373-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | SARATOGA SUB | Storage | 0.01 | 12/4/2019 | 12/23/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-11-07 18:31 | 2374-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | YOLO | WOODLAND SUB | Storage | 0.03 | 12/4/2019 | 1/27/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-11-11 23:11 | 2375-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | NEWARK SUB | Storage | 0.21 | 12/4/2019 | 1/17/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-11-04 13:33 | 2376-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MONTEREY | CARMEL SUB | Storage | 0.21 | 12/11/2019 | 12/20/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-11-09 12:50 | 2377-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | SAN FRAN P(HUNTERS POINT) SUB | Storage | 0.005 | 12/11/2019 | 12/17/2019 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-11-05 12:30 | 2378-WD | Independent Study | Independent Study | Withdrawn | 12/31/2020 | Withdrawn | Withdrawn | SOLANO | PEABODY SUB | Solar PV | 6.6 | 12/10/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-11-20 15:55 | 2379-WD | Independent Study | Independent Study | Withdrawn | 9/29/2020 | Withdrawn | Withdrawn | FRESNO | CARUTHERS SUB | Solar PV | 0.8 | 12/18/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-11-20 16:10 | 2380-WD | Independent Study | Independent Study | Withdrawn | 9/29/2020 | Withdrawn | Withdrawn | KINGS | HENRIETTA SUB | Solar PV | 3 | 12/18/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-11-19 08:51 | 2381-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | TWISSELMAN SUB | Solar PV, Storage | 31.4053 | 12/18/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-11-07 17:50 | 2382-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | GLENN | ORLAND B SUB | Storage | 0.02805 | 12/24/2019 | 02/26/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-11-21 07:38 | 2383-WD | Independent Study | Independent Study | Withdrawn | 9/29/2020 | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV | 3 | 12/24/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-11-21 07:48 | 2384-WD | Independent Study | Independent Study | Withdrawn | 9/29/2020 | Withdrawn | Withdrawn | KERN | WELLFIELD SUB | Solar PV | 3 | 12/24/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-11-21 07:54 | 2385-WD | Independent Study | Independent Study | Withdrawn | 9/30/2020 | Withdrawn | Withdrawn | KINGS | ALPAUGH SUB | Solar PV | 3 | 12/24/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-11-21 07:57 | 2386-WD | Independent Study | Independent Study | Withdrawn | 9/29/2020 | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV | 3 | 12/24/2019 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-12-02 18:25 | 2387-RD | Fast Track | Detailed Study | In Service | Not Provided |  |  | KERN | 7TH STANDARD SUB | Solar PV | 1.3172 | 12/24/2019 | 1/23/2020 | Fail Screens: I, J, K, M, V1, V2, S5 | 3/3/2020 | Fail | Fail | 8/10/2020 | N/A | Executed | No former queue position
2019-12-23 16:03 | 2388-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | SAN FRAN F (MARINA) SUB | Solar PV | 0.05 | 12/24/2019 | 08/05/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-12-13 12:08 | 2389-WD | Independent Study | Independent Study | Active | 6/1/2023 |  |  | SAN JOAQUIN | STAGG SUB | Storage | 20 | 12/31/2019 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 12/4/2020 | N/A | Executed | No former queue position
2019-12-13 12:10 | 2390-WD | Independent Study | Independent Study | Active | 6/1/2023 |  |  | MENDOCINO | MENDOCINO SUB | Storage | 5 | 12/31/2019 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 2020-11-24 | N/A | Executed | No former queue position
2019-11-30 18:27 | 2391-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | LOS ALTOS SUB | Storage | 0.025 | 12/31/2019 | 1/23/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-11-12 16:37 | 2392-WD | Independent Study | Independent Study | Active | 9/1/2021 | 9/2/2022 |  | FRESNO | NEW KEARNEY SUB | Solar PV | 9.9751 | 12/31/2019 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 4/9/2020 | N/A | Executed | No former queue position
2019-12-04 11:19 | 2393-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | BUTTE | BUTTE SUB | Solar PV, Steam Turbine | 1.0808 | 12/31/2019 | 1/21/2020 | Fail Screens: B, F, G, J, K, L, M, S5 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-12-04 14:15 | 2394-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | MONTAGUE SUB | Storage | 0.3345 | 12/31/2019 | 4/3/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-12-05 15:17 | 2395-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN MATEO | SNEATH LANE SUB | Storage | 1.26 | 1/8/2020 | 1/31/2020 | Fail Screens: H, I, J, K, M | 4/1/2020 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-12-12 14:51 | 2396-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | EL DORADO | DIAMOND SPRINGS SUB | Storage | 0.7 | 1/8/2020 | 1/29/2020 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-12-13 13:12 | 2397-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | AMADOR | MARTELL SUB | Storage | 0.5005 | 1/8/2020 | 2/10/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-11-08 18:19 | 2398-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | MT EDEN SUB | Storage | 0.25 | 1/8/2020 | 3/26/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-11-27 15:08 | 2399-WD | Fast Track | Fast Track | Active | 11/30/2021 | 12/30/2021 |  | HUMBOLDT | NEWBURG SUB | Solar PV | 1 | 1/8/2020 | 1/24/2020 | Fail Screens: 2, 10 | 3/9/2020 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-11-27 15:10 | 2400-WD | Fast Track | Independent Study | Active | 11/30/2021 | 3/2/2022 |  | HUMBOLDT | NEWBURG SUB | Solar PV | 1 | 1/8/2020 | 1/27/2020 | Fail Screens: 2, 4, 10 | 3/12/2020 | Fail | Pass | 8/3/2020 | N/A | Executed | No former queue position
2019-11-27 17:40 | 2401-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | YOLO | PLAINFIELD SUB | Solar PV | 0.8 | 1/8/2020 | 4/6/2020 | Fail Screens: F, J, K, L, M, S5, R1 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-12-04 14:27 | 2402-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | LOYOLA SUB | Storage | 0.02 | 1/8/2020 | 1/27/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-12-11 15:49 | 2403-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | WEST FRESNO SUB | Engine | 2.1504 | 1/8/2020 | 2/14/2020 | Fail Screens: B, D, F, G, I, J, K, L, M, V1, V2, S5, A1 | 4/20/2020 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-12-13 13:29 | 2404-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | SAN JOAQUIN | HERDLYN SUB | Solar PV | 1.7 | 1/8/2020 | 1/30/2020 | Fail Screens: D, F, G, J, K, L, M, S5 | 4/1/2020 | Fail | Pass | 11/6/2020 | N/A | Executed | No former queue position
2019-11-19 12:57 | 2405-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | TULARE | KINGSBURG SUB | Solar PV, Storage | 1.326 | 1/15/2020 | 2/5/2020 | Fail Screens: B, F, J, K, M, V1, S5, A1 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-12-18 17:57 | 2406-WD | Fast Track | Fast Track | Withdrawn | 12/30/2020 | Withdrawn | Withdrawn | HUMBOLDT | NEWBURG SUB | Solar PV | 1 | 1/15/2020 | 2/10/2020 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-12-18 18:03 | 2407-WD | Fast Track | Fast Track | Withdrawn | 6/30/2021 | Withdrawn | Withdrawn | HUMBOLDT | BLUE LAKE SUB | Solar PV | 1 | 1/15/2020 | 2/4/2020 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-12-18 18:13 | 2408-WD | Fast Track | Fast Track | Withdrawn | 6/30/2021 | Withdrawn | Withdrawn | HUMBOLDT | NEWBURG SUB | Solar PV | 1 | 1/15/2020 | 2/4/2020 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-12-19 15:57 | 2409-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN MATEO | PACIFICA SUB | Storage | 1.26 | 1/15/2020 | 2/3/2020 | Fail Screens: F, I, J, K, M | 3/31/2020 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-12-23 08:53 | 2410-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | YOLO | DAVIS SUB | Solar PV | 1.0759 | 1/15/2020 | 3/30/2020 | Fail Screens: D, F, G, I, L, M, S5 | 5/29/2020 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-12-23 08:58 | 2411-RD | Fast Track | DGSP | In Service | Not Provided |  |  | YOLO | DAVIS SUB | Solar PV | 1.0759 | 1/15/2020 | 3/30/2020 | Fail Screens: D, F, G, I, L, M, V1, S5 | 5/27/2020 | Fail | Pass | 11/18/2020 | N/A | Executed | No former queue position
2019-12-23 14:29 | 2412-RD | Fast Track | Fast Track | In Service | Not Provided | 5/3/2003 |  | HUMBOLDT | JANES CREEK SUB | Engine | 2 | 1/15/2020 | 2/19/2020 | Fail Screens: B, I, J, M | 7/21/2020 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-12-17 16:03 | 2413-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | CONTRA COSTA | SAN RAMON SUB | Storage | 0.005 | 1/22/2020 | 2/12/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-12-17 16:09 | 2414-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Storage | 0.005 | 1/22/2020 | 2/7/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-12-20 12:29 | 2415-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | GANSO SUB | Solar PV | 1.5 | 1/22/2020 | N/A | N/A | N/A | N/A | Fail | 6/18/2020 | N/A | Executed | No former queue position
2020-01-03 19:29 | 2416-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | LINDEN SUB | Solar PV | 0.9375 | 1/22/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-01-06 14:06 | 2417-WD | Fast Track | Fast Track | Withdrawn | 3/31/2020 | Withdrawn | Withdrawn | SAN BENITO | SAN JUSTO SUB | Engine | 2 | 1/22/2020 | 2/6/2020 | Fail Screens: 2, 4, 5, 10 | 4/9/2020 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-11-14 10:45 | 2418-WD | Cluster | Cluster | Withdrawn | 11/30/2023 | Withdrawn | Withdrawn | FRESNO | DERRICK SUB | Solar PV, Storage | 63.9 | 1/22/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-11-30 05:00 | 2419-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | NAPA | CALISTOGA SUB | Storage | 0.01 | 1/22/2020 | 2/10/2020 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-12-09 14:54 | 2420-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | FRESNO | TRANSMISSION | Solar PV | 4.2 | 1/22/2020 | N/A | N/A | N/A | N/A | Pass | 7/30/2020 | N/A | Executed | No former queue position
2019-12-12 14:23 | 2421-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | KERN | TWISSELMAN SUB | Solar PV | 2.7 | 1/22/2020 | N/A | N/A | N/A | N/A | Pass | 5/11/2020 | N/A | Executed | No former queue position
2019-12-19 17:14 | 2422-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | ATWATER SUB | Solar PV | 1.44 | 1/22/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-12-24 09:57 | 2423-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | KINGS | GUERNSEY SUB | Solar PV | 2.5382 | 06/11/2020 | N/A | N/A | N/A | N/A | Pass | 8/28/2020 | N/A | Executed | No former queue position
2019-12-27 12:58 | 2424-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | LOYOLA SUB | Storage | 0.03 | 1/22/2020 | 2/12/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-01-07 10:43 | 2425-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MARIN | SAN RAFAEL SUB | Storage | 0.02 | 1/22/2020 | 2/12/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-01-08 11:13 | 2426-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | LAKE | MIDDLETOWN SUB | Storage | 0.005 | 1/22/2020 | 2/10/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-12-04 16:03 | 2427-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN LUIS OBISPO | OCEANO SUB | Storage | 0.01 | 1/22/2020 | 2/10/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2019-12-30 13:47 | 2428-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN LUIS OBISPO | CAYUCOS SUB | Solar PV, Storage | 0.01 | 1/22/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-01-13 15:16 | 2429-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SONOMA | GUALALA SUB | Storage | 0.005 | 1/22/2020 | 2/10/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-01-14 23:23 | 2430-WD | Fast Track | Fast Track | Withdrawn | 12/30/2021 | Withdrawn | Withdrawn | SAN MATEO | DALY CITY SUB | Storage | 2 | 1/22/2020 | 2/10/2020 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-01-14 15:38 | 2431-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | NAPA | PUEBLO SUB | Solar PV, Storage | 0.01 | 1/29/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-01-15 17:03 | 2432-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | TULARE | KINGSBURG SUB | Solar PV | 1.625 | 03/30/2020 | 4/14/2020 | Fail Screens: D, F, J, K, M, S5 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2019-12-30 11:13 | 2433-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN MATEO | MENLO SUB | Storage | 0.015 | 2/4/2020 | 5/18/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-01-16 14:41 | 2434-WD | Fast Track | Independent Study | Withdrawn | 12/31/2022 | Withdrawn | Withdrawn | KINGS | TWISSELMAN SUB | Solar PV | 2 | 2/4/2020 | 2/28/2020 | Fail Screens: 2, 4, 7, 9, 10 | 5/13/2020 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-01-16 14:42 | 2435-WD | Fast Track | Fast Track | Withdrawn | 12/30/2022 | Withdrawn | Withdrawn | KINGS | TWISSELMAN SUB | Solar PV | 2 | 2/4/2020 | 2/28/2020 | Fail Screens: 2, 4, 7, 9, 10 | 5/13/2020 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-01-28 11:55 | 2436-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SONOMA | CLOVERDALE SUB | Storage | 0.005 | 2/12/2020 | 3/30/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-01-28 10:53 | 2437-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | TEHAMA | CORNING SUB | Storage | 0.00055 | 2/12/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-01-28 12:08 | 2438-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | YOLO | WEST SACRAMENTO SUB | Solar PV, Storage | 1.216 | 2/12/2020 | 5/12/2020 | Fail Screens: I, J, K, M, S5 | 6/9/2020 | Fail | Pass | 12/14/2020 | N/A | Executed | No former queue position
2020-01-30 12:25 | 2439-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | OAKLAND K (CLAREMONT) SUB | Storage | 0.015 | 2/12/2020 | 3/4/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-01-15 00:15 | 2440-WD | Fast Track | Fast Track | Withdrawn | 8/28/2020 | Withdrawn | Withdrawn | LAKE | CLEAR LAKE SUB | Solar PV | 3 | 2/19/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-01-24 09:16 | 2441-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | ANTELOPE SUB | Solar PV | 2.5 | 2/19/2020 | 3/17/2020 | Fail Screens: D, J, K, L, M, V1, V2, S5, A1 | 4/17/2020 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-01-30 12:38 | 2442-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN MATEO | SAN CARLOS SUB | Other | 0.25 | 2/19/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-01-27 23:06 | 2443-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | HUMBOLDT | GARBERVILLE SUB | Storage | 0.21 | 2/19/2020 | 3/24/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-01-19 12:59 | 2444-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | LOYOLA SUB | Storage | 0.01 | 2/19/2020 | 5/26/2020 | Fail Screens: I, L, M, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-01-31 09:04 | 2445-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | ARLINGTON SUB | Storage | 0.015 | 2/26/2020 | 3/15/2020 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-02-03 12:28 | 2446-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | E20T Customer Owned | Solar PV | 18.9 | 2/26/2020 | N/A | N/A | N/A | N/A | Pass | 12/14/2020 | N/A | Executed | No former queue position
2020-02-04 15:23 | 2447-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | SAN FRAN L SUB | Micro Turbine | 0.065 | 2/26/2020 | 3/19/2020 | Fail Screens: I, J, V1 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-02-06 11:08 | 2448-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SONOMA | CORONA SUB | Storage | 0.03026 | 2/26/2020 | 3/18/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-02-06 12:00 | 2449-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SONOMA | BELLEVUE SUB | Storage | 0.03026 | 2/26/2020 | 5/28/2020 | Fail Screens: D, J, M, V1, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-02-12 16:15 | 2450-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | Withdrawn | Other | 0.5 | 2/26/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-02-12 17:22 | 2451-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | Withdrawn | Other | 0.5 | 2/26/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-02-12 17:46 | 2452-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | Withdrawn | Other | 0.5 | 2/26/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-01-31 06:43 | 2453-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA BARBARA | PURISIMA SUB | Micro Turbine | 4.56 | 2/26/2020 | 3/19/2020 | Fail Screens: B, F, J, K, M | 5/18/2020 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-01-31 09:43 | 2454-RD | Fast Track | Fast Track | Withdrawn | 7/31/2020 | Withdrawn | Withdrawn | MARIN | SAN RAFAEL SUB | Cogeneration | 0.995 | 2/26/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-02-11 14:24 | 2455-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | DIXON LANDING SUB | Storage | 0.585 | 2/26/2020 | 5/5/2020 | Fail Screens: B, D, G, I, J, V1, S5, A1, B1 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-02-03 10:43 | 2456-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN MATEO | TRANSMISSION | Solar PV | 1.693 | 2/26/2020 | 4/22/2020 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-02-10 12:19 | 2457-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Storage | 0.005 | 2/26/2020 | 3/15/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-02-14 08:08 | 2458-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | PLACER | PENRYN SUB | Storage | 0.01 | 3/4/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-01-27 14:06 | 2459-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | PLACER | FORESTHILL SUB | Solar PV, Storage | 0.01 | 3/4/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-02-07 08:55 | 2460-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | SAN RAMON SUB | Solar PV, Storage | 0.8304 | 3/4/2020 | 6/29/2020 | Fail Screens: J, K, M, S5 | 8/28/2020 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-02-07 10:50 | 2461-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | PINEDALE SUB | Solar PV, Storage | 1.5744 | 3/4/2020 | 4/30/2020 | Fail Screens: B, I, J, K, M, S5, R1 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-02-19 20:54 | 2462-RD | Fast Track | Detailed Study | In Service | Not Provided |  |  | KERN | FELLOWS SUB | Solar PV | 0.96 | 3/4/2020 | 3/20/2020 | Fail Screens: B, D, F, I, J, K, L, M, V1, S5, A1 | 5/18/2020 | Fail | Pass | 10/15/2020 | N/A | Executed | No former queue position
2020-02-04 14:50 | 2463-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | BONITA SUB | Solar PV | 0.84 | 3/4/2020 | 5/15/2020 | Fail Screens: D, F, J, K, L, M, S5 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-02-17 10:32 | 2464-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN MATEO | EAST GRAND SUB | Fuel Cell | 0.2325 | 3/4/2020 | 9/10/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-02-19 18:28 | 2465-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | MADERA | MADERA SUB | Solar PV, Storage | 3.7865 | 3/11/2020 | N/A | N/A | N/A | N/A | Pass | 7/30/2020 | N/A | Executed | No former queue position
2020-02-14 09:20 | 2466-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | KERN | CARNERAS SUB | Solar PV | 1.9112 | 3/11/2020 | N/A | N/A | N/A | N/A | Pass | 7/1/2020 | N/A | Executed | No former queue position
2020-02-21 12:49 | 2467-RD | Fast Track | Fast Track | Withdrawn | 10/5/2020 | Withdrawn | Withdrawn | FRESNO | BULLARD SUB | Solar PV | 0.06015 | 3/11/2020 | 4/27/2020 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | R21 Transition to WDT SGIA
2020-02-06 10:03 | 2468-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | SOLANO | VACA DIXON SUB | Solar PV, Storage | 5.3849 | 3/18/2020 | N/A | N/A | N/A | N/A | Pass | 10/6/2020 | N/A | Executed | No former queue position
2020-03-05 00:45 | 2469-WD | Fast Track | Independent Study | Withdrawn | 5/31/2021 | Withdrawn | Withdrawn | LAKE | CLEAR LAKE SUB | Storage | 3.2175 | 3/18/2020 | 4/9/2020 | Fail Screens: 2, 4, 10 | 6/3/2020 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-02-14 07:28 | 2470-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SONOMA | LAKEVILLE SUB | Storage | 0.005 | 3/18/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-03-04 15:53 | 2471-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | MADERA | EL PECO SUB | Solar PV | 1.8 | 3/18/2020 | N/A | N/A | N/A | N/A | Pass | 7/31/2020 | N/A | Executed | No former queue position
2020-01-27 10:14 | 2472-WD | Fast Track | Fast Track | Withdrawn | 12/31/2022 | Withdrawn | Withdrawn | SOLANO | GRAND ISLAND SUB | Other | 4.158 | 3/18/2020 | 4/29/2020 | Fail Screens: 2, 4, 5, 6, 7, 9, 10 | 6/16/2020 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-03-04 15:57 | 2473-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | NEWARK SUB | Engine | 0.625 | 3/25/2020 | 6/19/2020 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-03-02 09:59 | 2474-WD | Fast Track | Fast Track | In Service | 7/31/2020 | 1/11/2022 |  | MARIN | SAN RAFAEL SUB | Engine | 0.995 | 3/26/2020 | 5/14/2020 | Fail Screens: 2, 7, 10 | 6/23/2020 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-03-05 12:55 | 2475-RD | Fast Track | Fast Track | In Service | Not Provided | In Service | 8/6/2013 | TEHAMA | TYLER SUB | Wind | 1.0296 | 3/25/2020 | 4/7/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-03-06 17:35 | 2476-RD | Fast Track | Detailed Study | In Service | Not Provided |  |  | KERN | WHEELER RIDGE SUB | Solar PV | 2.16 | 3/25/2020 | 4/27/2020 | Fail Screens: D, F, J, K, M, V1, S5, A1 | 6/26/2020 | Fail | Pass | 11/9/2020 | N/A | Executed | No former queue position
2020-03-09 21:18 | 2477-WD | Fast Track | Fast Track | Withdrawn | 10/30/2020 | Withdrawn | Withdrawn | HUMBOLDT | NEWBURG SUB | Solar PV | 2 | 3/25/2020 | 4/13/2020 | Fail Screens: 2, 4, 10 | 5/21/2020 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-02-12 15:22 | 2478-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SHASTA | DESCHUTES SUB | Storage | 0.01 | 4/1/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-03-14 20:43 | 2479-WD | Independent Study | DGSP | Withdrawn | 6/30/2021 | Withdrawn | Withdrawn | HUMBOLDT | BLUE LAKE SUB | Solar PV | 1 | 4/1/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-02-25 15:14 | 2480-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | WOODWARD SUB | Solar PV | 1.5107 | 4/1/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-02-27 09:44 | 2481-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN A (POTRERO PP) SUB | Engine | 0.75 | 4/1/2020 | 4/15/2020 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-03-18 15:01 | 2482-WD | Fast Track | Fast Track | Withdrawn | 6/30/2020 | Withdrawn | Withdrawn | KERN | TUPMAN SUB | Fuel Cell, Steam Turbine | 0.6 | 4/8/2020 | 5/1/2020 | Fail Screens: 4, 5, 7, 9, 10 | 6/26/2020 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-02-27 15:41 | 2483-WD | Independent Study | Independent Study | Withdrawn | 6/15/2022 | Withdrawn | Withdrawn | SUTTER | MERIDIAN SUB | Storage | 8.36 | 4/8/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-03-06 15:21 | 2484-WD | Independent Study | Independent Study | Active | 12/15/2021 | 7/6/2023 |  | KINGS | AVENAL SUB | Storage | 9.8805 | 4/8/2020 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 02/01/2021 | N/A | Executed | No former queue position
2020-03-18 17:35 | 2485-WD | Independent Study | DGSP | Withdrawn | 6/30/2021 | Withdrawn | Withdrawn | HUMBOLDT | BLUE LAKE SUB | Solar PV | 0.98304 | 4/8/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-03-15 13:56 | 2486-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Storage | 0.01 | 4/8/2020 | 4/20/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-03-06 09:34 | 2487-WD | Independent Study | Independent Study | Withdrawn | 1/3/2022 | Withdrawn | Withdrawn | KINGS | CORCORAN SUB | Storage | 0.84 | 4/8/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-03-19 16:26 | 2488-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN JOAQUIN | FRENCH CAMP SUB | Storage | 0.24 | 4/8/2020 | 5/15/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-03-24 11:43 | 2489-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MONTEREY | GREEN VALLEY SUB | Solar PV, Storage | 2.5385 | 4/15/2020 | 9/4/2020 | Fail Screens: D, H, I, J, K, M, S5 | 10/29/2020 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-03-28 12:30 | 2490-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | BUTTE | CHICO B SUB | Solar PV | 1.0103 | 4/23/2020 | 7/8/2020 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-03-26 16:36 | 2491-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | YOLO | WILKINS SLOUGH SUB | Solar PV | 1.375 | 4/23/2020 | 5/8/2020 | Fail Screens: J, K, L, M, A1 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-03-27 14:57 | 2492-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | YOLO | KNIGHTS LANDING SUB | Solar PV | 0.96 | 4/23/2020 | 5/8/2020 | Fail Screens: D, F, G, J, K, L, M, S5 | 10/2/2020 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-03-17 13:58 | 2493-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | NEVADA | BRUNSWICK SUB | Solar PV, Storage | 1.7308 | 4/22/2020 | 8/28/2020 | Fail Screens: D, F, G, I, J, K, L, M, S5 | 10/9/2020 | Fail | Pass | 4/26/2021 | N/A | Executed | No former queue position
2020-03-20 09:02 | 2494-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | MCKEE SUB | Storage | 0.02 | 4/22/2020 | 4/30/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-03-30 07:50 | 2495-WD | Independent Study | Independent Study | Active | 3/29/2022 | 2/24/2024 |  | SAN BENITO | HOLLISTER SUB | Storage | 13.0625 | 4/23/2020 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | N/A | 9/11/2020 | 2022-01-11 | Executed | No former queue position
2020-03-31 15:26 | 2496-WD | Independent Study | Independent Study | Withdrawn | 6/2/2021 | Withdrawn | Withdrawn | KINGS | AVENAL SUB | Storage | 60 | 4/29/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-03-31 17:10 | 2497-WD | Independent Study | Independent Study | Withdrawn | 11/30/2021 | Withdrawn | Withdrawn | CONTRA COSTA | BRENTWOOD SUB | Solar PV, Storage | 7 | 4/29/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-04-03 15:45 | 2498-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MARIN | SAN RAFAEL SUB | Storage | 0.01 | 4/29/2020 | 3/3/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-03-23 16:14 | 2499-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CRUZ | GREEN VALLEY SUB | Storage | 0.005 | 4/29/2020 | 5/1/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-04-06 17:23 | 2500-RD | Fast Track | Fast Track | Active | Not Provided |  |  | HUMBOLDT | HARRIS SUB | Engine | 0.624 | 4/29/2020 | 5/12/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-04-10 07:42 | 2501-RD | Fast Track | Fast Track | Active | Not Provided |  |  | NAPA | BASALT SUB | Engine | 0.624 | 4/29/2020 | 5/12/2020 | Fail Screens: B, I, J, M, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-04-10 07:57 | 2502-RD | Fast Track | Fast Track | Active | Not Provided |  |  | PLACER | BELL SUB | Engine | 0.625 | 4/29/2020 | 5/26/2020 | Fail Screens: B, F, I, J, K, L, M, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-04-10 08:11 | 2503-RD | Fast Track | Fast Track | Active | Not Provided |  |  | MARIN | SAN RAFAEL SUB | Engine | 0.6248 | 4/29/2020 | 5/12/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-04-10 11:35 | 2504-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | FRESNO | CALFLAX SUB | Solar PV | 0.892 | 4/29/2020 | 5/13/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-03-17 16:38 | 2505-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | MENDOTA SUB | Solar PV | 66 | 5/6/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-03-19 08:49 | 2506-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | YOLO | DAVIS SUB | Solar PV, Storage | 1.2404 | 5/6/2020 | 7/28/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-04-07 14:47 | 2507-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | MERCED | ORTIGA SUB | Solar PV | 0.4 | 5/6/2020 | N/A | N/A | N/A | N/A | Pass | 11/19/2020 | N/A | Executed | No former queue position
2020-04-08 16:00 | 2508-WD | Independent Study | Independent Study | Withdrawn | 3/1/2021 | Withdrawn | Withdrawn | CONTRA COSTA | HERDLYN SUB | Solar PV | 5 | 5/6/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-03-31 14:09 | 2509-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | CONTRA COSTA | Customer Owned | Solar PV, Steam Turbine | 39.4634 | 5/6/2020 | N/A | N/A | N/A | N/A | Pass | 11/30/2021 | N/A | Executed | No former queue position
2020-04-13 21:54 | 2510-WD | Independent Study | Independent Study | Withdrawn | 12/1/2021 | Withdrawn | Withdrawn | SOLANO | CORDELIA SUB | Solar PV, Storage | 7.8 | 5/6/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-04-20 09:58 | 2511-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | FRESNO | WOODWARD SUB | Solar PV, Storage | 2.063 | 5/6/2020 | 11/30/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-04-21 11:05 | 2512-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SANTA CRUZ | PAUL SWEET SUB | Solar PV, Storage | 3.5543 | 5/13/2020 | N/A | N/A | N/A | N/A | Pass | 10/13/2020 | N/A | Executed | No former queue position
2020-04-22 09:49 | 2513-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MENDOCINO | HOPLAND SUB | Solar PV | 0.6 | 5/13/2020 | 7/2/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-04-27 15:19 | 2514-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | COLUMBUS SUB | Solar PV, Storage | 3.3032 | 5/27/2020 | N/A | N/A | N/A | N/A | Pass | 2/16/2021 | N/A | Executed | No former queue position
2020-05-01 12:35 | 2515-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | STANISLAUS | RIVERBANK SUB | Combustion Engine | 0.99 | 5/13/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-03-30 18:18 | 2516-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN MATEO | MILLBRAE SUB | Storage | 0.01 | 5/13/2020 | 6/3/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-03-31 15:22 | 2517-WD | Fast Track | Fast Track | Withdrawn | 11/2/2020 | Withdrawn | Withdrawn | KINGS | AVENAL SUB | Storage | 6 | 5/13/2020 | 6/4/2020 | Fail Screens: 2, 4, 10 | 8/14/2020 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-04-21 09:21 | 2518-WD | Independent Study | Independent Study | Withdrawn | 4/16/2022 | Withdrawn | Withdrawn | SANTA CRUZ | ROB ROY SUB | Storage | 109.994 | 5/13/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-04-30 14:23 | 2519-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MARIN | ALTO SUB | Storage | 0.02 | 5/20/2020 | 5/22/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-05-04 11:11 | 2520-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | CONTRA COSTA | TASSAJARA SUB | Storage | 0.01 | 5/20/2020 | 6/8/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-05-11 18:35 | 2521-RD | Fast Track | Detailed Study | Withdrawn | 3/29/2021 | Withdrawn | Withdrawn | FRESNO | PARLIER SUB | Steam Turbine | 3.3 | 5/20/2020 | 6/4/2020 | Fail Screens: B, D, F, I, J, K, M, V1, V2, S5, A1 | 7/8/2020 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-04-14 11:05 | 2522-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | YOLO | PLAINFIELD SUB | Solar PV | 0.8 | 5/20/2020 | N/A | N/A | N/A | N/A | Pass | 9/23/2020 | N/A | Executed | No former queue position
2020-05-11 17:33 | 2523-RD | Fast Track | Fast Track | Withdrawn | 3/29/2021 | Withdrawn | Withdrawn | MADERA | MADERA SUB | Steam Turbine | 0.00371 | 5/20/2020 | 6/10/2020 | Fail Screens: B, D, I, L, M, V1, V2, S5, A1 | 8/4/2020 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-04-16 13:54 | 2524-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | JARVIS SUB | Solar PV | 0.84 | 5/20/2020 | 8/7/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-04-20 09:56 | 2525-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | FREMONT SUB | Solar PV | 1.98 | 5/20/2020 | 6/19/2020 | Fail Screens: D, H, J, K, M, S5 | 8/7/2020 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-04-20 09:57 | 2526-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | JARVIS SUB | Solar PV | 2.52 | 5/20/2020 | 6/19/2020 | Fail Screens: G, M, S5 | 8/13/2020 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-04-20 10:06 | 2527-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | FREMONT SUB | Solar PV | 0.35 | 5/20/2020 | 7/21/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-04-20 10:14 | 2528-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | DIXON LANDING SUB | Solar PV | 0.9 | 5/20/2020 | 8/7/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-05-09 14:24 | 2529-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MARIN | IGNACIO SUB | Solar PV | 0.008 | 5/20/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-05-13 11:23 | 2530-WD | Independent Study | Independent Study | Withdrawn | 8/30/2021 | Withdrawn | Withdrawn | PLACER | LINCOLN SUB | Storage, Turbine | 10.863 | 5/20/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-05-13 16:16 | 2531-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | MILPITAS SUB | Storage | 0.015 | 5/20/2020 | 6/8/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-05-14 10:22 | 2532-WD | Independent Study | Independent Study | Withdrawn | 8/30/2021 | Withdrawn | Withdrawn | PLACER | LINCOLN SUB | Storage, Turbine | 10.863 | 5/20/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-05-14 10:30 | 2533-WD | Independent Study | Independent Study | Active | 8/30/2021 | 9/26/2023 |  | YUBA | PLUMAS SUB | Storage | 4.092 | 5/20/2020 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 2/17/2021 | N/A | Executed | No former queue position
2020-05-11 20:33 | 2534-RD | Fast Track | Detailed Study | Withdrawn | 3/29/2021 | Withdrawn | Withdrawn | FRESNO | MCCALL SUB | Engine | 3.3 | 5/27/2020 | 6/10/2020 | Fail Screens: B, D, I, L, M, V1, V2, S5, A1 | 7/17/2020 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-05-11 17:31 | 2535-WD | Fast Track | Fast Track | Withdrawn | 12/11/2020 | Withdrawn | Withdrawn | FRESNO | BIOLA SUB | Fuel Cell | 0.9995 | 5/27/2020 | 6/16/2020 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-04-15 10:40 | 2536-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | NAPA | SILVERADO SUB | Storage | 0.015 | 5/27/2020 | 6/3/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-05-12 10:33 | 2537-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN MATEO | WOODSIDE SUB | Storage | 0.01 | 5/27/2020 | 6/9/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-04-22 14:39 | 2538-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | TEHAMA | LOS MOLINOS SUB | Solar PV | 0.32 | 5/27/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-05-07 10:33 | 2539-RD | Detailed Study | DGSP | In Service | Not Provided |  |  | FRESNO | SANGER SUB | Fuel Cell, Solar PV | 1.8 | 5/27/2020 | N/A | N/A | N/A | N/A | Pass | 9/14/2020 | N/A | Executed | No former queue position
2020-05-07 12:47 | 2540-RD | Detailed Study | DGSP | Active | Not Provided |  |  | FRESNO | SANGER SUB | Fuel Cell, Solar PV | 1.5 | 5/27/2020 | N/A | N/A | N/A | N/A | Fail | 2021-02-20 | N/A | Executed | No former queue position
2020-05-07 13:07 | 2541-RD | Detailed Study | DGSP | Active | Not Provided |  |  | FRESNO | MCCALL SUB | Fuel Cell, Solar PV | 1.5 | 5/27/2020 | N/A | N/A | N/A | N/A | Fail | 2021-02-20 | N/A | Executed | No former queue position
2020-05-07 15:33 | 2542-RD | Detailed Study | DGSP | Active | Not Provided |  |  | FRESNO | SANGER SUB | Solar PV | 2.1 | 5/27/2020 | N/A | N/A | N/A | N/A | Fail | 2021-02-20 | N/A | Executed | No former queue position
2020-05-12 19:36 | 2543-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | TULARE | KINGSBURG SUB | Solar PV | 1.0726 | 5/27/2020 | N/A | N/A | N/A | N/A | Pass | 10/8/2020 | N/A | Executed | No former queue position
2020-05-18 09:32 | 2544-WD | Fast Track | Fast Track | Withdrawn | 10/15/2021 | Withdrawn | Withdrawn | HUMBOLDT | GARBERVILLE SUB | Solar PV | 0.50039 | 5/27/2020 | 6/16/2020 | Fail Screens: 2, 4, 7, 10 | 8/17/2020 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-04-08 12:03 | 2545-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | CONTRA COSTA | SAN RAMON SUB | Storage | 0.005 | 6/3/2020 | 6/8/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-05-15 16:55 | 2546-RD | Fast Track | Detailed Study | Withdrawn | 3/30/2022 | Withdrawn | Withdrawn | COLUSA | ARBUCKLE SUB | Steam Turbine | 5 | 6/3/2020 | 6/30/2020 | Fail Screens: B, D, F, G, I, J, K, L, M, V1, V2, S5, A1 | 9/4/2020 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-05-26 16:20 | 2547-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | TEHAMA | LOS MOLINOS SUB | Solar PV | 1.5 | 6/3/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-05-15 16:49 | 2548-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MARIN | ALTO SUB | Storage | 0.005 | 6/3/2020 | 6/18/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-05-14 22:04 | 2549-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | SARATOGA SUB | Storage | 0.21 | 6/10/2020 | 7/28/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-05-26 14:18 | 2550-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | GRANT SUB | Engine, Solar PV, Storage | 0.8 | 6/10/2020 | 2/2/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-05-20 16:48 | 2551-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MARIN | ALTO SUB | Storage | 0.5 | 6/17/2020 | 7/1/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-05-27 11:09 | 2552-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | FRESNO | BIOLA SUB | Fuel Cell | 0.999 | 6/17/2020 | N/A | N/A | N/A | N/A | Pass | 3/4/2021 | N/A | Executed | No former queue position
2020-05-19 12:20 | 2553-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | PINEDALE SUB | Solar PV, Storage | 1.5288 | 6/17/2020 | 7/1/2020 | Fail Screens: B, D, I, J, K, M, S5 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-06-09 15:25 | 2554-WD | Independent Study | Independent Study | Active | 12/1/2021 | 5/27/2023 |  | KINGS | TULARE LAKE SUB | Solar PV | 3.75 | 6/17/2020 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 9/14/2020 | N/A | Executed | No former queue position
2020-05-21 13:36 | 2555-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | NEWARK SUB | Storage | 0.11194 | 6/17/2020 | 6/18/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-06-14 21:51 | 2556-WD | Fast Track | Fast Track | Withdrawn | 6/30/2021 | Withdrawn | Withdrawn | HUMBOLDT | BLUE LAKE SUB | Solar PV | 1 | 6/24/2020 | 7/16/2020 | Fail Screens: 5, 9, 10 | 9/21/2020 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-06-04 15:36 | 2557-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN MATEO | SNEATH LANE SUB | Storage | 0.9295 | 6/24/2020 | 8/11/2020 | Fail Screens: I, J, M | 11/10/2020 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-06-04 16:47 | 2558-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | TULARE | KINGSBURG SUB | Storage | 0.9295 | 6/24/2020 | 8/11/2020 | Fail Screens: F, I, J, K, M, V1, S5, A1 | 2/5/2021 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-06-05 09:05 | 2559-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | FRESNO | PANOCHE SUB | Storage | 0.9295 | 6/24/2020 | 10/21/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-06-03 22:49 | 2560-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | TUOLUMNE | CURTIS SUB | Solar PV | 3.6 | 6/24/2020 | N/A | N/A | N/A | N/A | Pass | 12/1/2020 | N/A | Executed | No former queue position
2020-06-11 13:47 | 2561-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN MATEO | BELLE HAVEN SUB | Solar PV | 0.6 | 7/1/2020 | 7/21/2020 | Fail Screens: A, J, K | 9/21/2020 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-06-05 14:47 | 2562-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | MERCED | ATWATER SUB | Solar PV | 1.5046 | 7/8/2020 | N/A | N/A | N/A | N/A | Pass | 10/21/2020 | N/A | Executed | No former queue position
2020-06-10 17:33 | 2563-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | MADERA | EL PECO SUB | Solar PV | 0.84255 | 7/8/2020 | N/A | N/A | N/A | N/A | Pass | 10/5/2020 | N/A | Executed | No former queue position
2020-06-19 14:02 | 2564-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA BARBARA | SANTA MARIA SUB | Solar PV, Storage | 1.7775 | 7/9/2020 | 7/30/2020 | Fail Screens: F, I, J, K, M | 9/1/2020 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-05-22 12:30 | 2565-WD | Independent Study | Independent Study | Withdrawn | 11/30/2021 | Withdrawn | Withdrawn | YOLO | WOODLAND SUB | Solar PV | 4 | 7/8/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-06-18 14:17 | 2566-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | MADERA | E20T TRANSMISSION | Solar PV | 10 | 7/15/2020 | N/A | N/A | N/A | N/A | Pass | 12/15/2020 | N/A | Executed | No former queue position
2020-07-02 13:48 | 2567-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | CONTRA COSTA | SAN RAMON SUB | Solar PV, Storage | 1.82 | 7/15/2020 | 03/23/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-07-01 13:31 | 2568-WD | Independent Study | Independent Study | Withdrawn | 12/1/2021 | Withdrawn | Withdrawn | SOLANO | GRAND ISLAND SUB | Solar PV, Storage | 6.4 | 7/15/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-07-02 16:03 | 2569-WD | Independent Study | Independent Study | Active | 12/1/2021 | 7/14/2023 |  | MERCED | ORTIGA SUB | Storage | 0.0032 | 7/15/2020 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 11/24/2020 | N/A | Executed | No former queue position
2020-05-22 12:20 | 2570-WD | Independent Study | Independent Study | Withdrawn | 11/30/2021 | Withdrawn | Withdrawn | YOLO | WOODLAND SUB | Solar PV | 4.2068 | 7/22/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-07-07 15:34 | 2571-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | KINGS | TRANSMISSION-Customer Owned | Solar PV | 7.875 | 7/22/2020 | N/A | N/A | N/A | N/A | Pass | 12/9/2020 | N/A | Executed | No former queue position
2020-07-07 17:47 | 2572-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | OAKLAND C (OAKLAND PP) SUB | Storage | 1.56 | 7/22/2020 | 12/16/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-07-09 13:49 | 2573-RD | Fast Track | Fast Track | Active | Not Provided | 4/16/2022 |  | MADERA | BORDEN SUB | Solar PV | 0.44815 | 7/22/2020 | 8/11/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-07-09 15:11 | 2574-WD | Independent Study | Independent Study | Withdrawn | 3/1/2023 | Withdrawn | Withdrawn | KERN | KERN OIL SUB | Solar PV, Storage | 4.9993 | 7/29/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-07-09 15:17 | 2575-WD | Independent Study | Independent Study | Withdrawn | 3/1/2023 | Withdrawn | Withdrawn | KERN | KERN OIL SUB | Solar PV, Storage | 5.004 | 7/29/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-07-10 14:03 | 2576-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | FRESNO | REEDLEY SUB | Solar PV | 0.75 | 7/29/2020 | 8/12/2020 | Fail Screens: F, I, J, K, M, S5 | 9/2/2020 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-06-18 21:48 | 2577-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | FRESNO | CLOVIS SUB | Storage | 0.21 | 7/29/2020 | 8/11/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-06-30 09:48 | 2578-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | HUMBOLDT | EUREKA A SUB | Storage | 0.21 | 7/29/2020 | 9/1/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-07-17 20:24 | 2579-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | CONTRA COSTA | MEADOW LANE SUB | Storage | 0.9295 | 7/29/2020 | 9/4/2020 | Fail Screens: I, J, M, V1, S5, A1 | 10/19/2020 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-07-16 19:49 | 2580-WD | Independent Study | Independent Study | Withdrawn | 10/14/2021 | Withdrawn | Withdrawn | YOLO | ZAMORA SUB | Solar PV | 5 | 8/5/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-07-22 16:06 | 2581-RD | Fast Track | Fast Track | Active | Not Provided |  |  | YOLO | WOODLAND SUB | Solar PV, Storage | 1.49 | 8/5/2020 | 8/31/2020 | Fail Screens: D, I, J, K, L, M, S5 | 10/6/2020 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-07-22 16:05 | 2582-RD | Fast Track | Fast Track | Active | Not Provided |  |  | YOLO | WOODLAND SUB | Solar PV, Storage | 1.56 | 8/5/2020 | 8/31/2020 | Fail Screens: D, I, J, K, L, M, S5 | 10/6/2020 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-07-28 17:37 | 2583-WD | Independent Study | Independent Study | Withdrawn | 7/1/2022 | Withdrawn | Withdrawn | YOLO | MADISON SUB | Solar PV | 25 | 8/5/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-07-31 15:03 | 2584-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | AIRWAYS SUB | Solar PV, Storage | 3.4 | 8/12/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-07-31 16:16 | 2585-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | FRESNO | Customer Owned E20T | Solar PV, Storage | 16.5164 | 8/12/2020 | N/A | N/A | N/A | N/A | Pass | 12/22/2020 | N/A | Executed | No former queue position
2020-08-05 13:56 | 2586-WD | Independent Study | Independent Study | Withdrawn | 3/1/2023 | Withdrawn | Withdrawn | KERN | KERN OIL SUB | Storage | 5 | 8/19/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-08-05 14:11 | 2587-WD | Independent Study | Independent Study | Withdrawn | 3/1/2023 | Withdrawn | Withdrawn | KERN | KERN OIL SUB | Storage | 5 | 8/19/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-08-14 09:48 | 2588-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | GUERNSEY SUB | Solar PV | 2.46 | 8/26/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-08-11 17:13 | 2589-WD | Independent Study | Independent Study | Withdrawn | 9/30/2021 | Withdrawn | Withdrawn | ALAMEDA | HERDLYN SUB | Solar PV | 2.128 | 8/26/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-07-15 18:17 | 2590-WD | Fast Track | Independent Study | Withdrawn | 11/30/2021 | Withdrawn | Withdrawn | YOLO | PUTAH CREEK SUB | Solar PV | 2.475 | 8/26/2020 | 9/22/2020 | Fail Screens: 2, 4, 9, 10 | 11/10/2020 | Fail | Pass | 6/23/2021 | Withdrawn | Withdrawn | No former queue position
2020-08-17 17:03 | 2591-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | GRANT SUB | Solar PV, Storage | 1.52 | 9/2/2020 | 1/15/2021 | Fail Screens: D, I, M, S5 | 7/2/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-07-01 12:17 | 2592-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | YOLO | KNIGHTS LANDING SUB | Solar PV | 2.1 | 9/2/2020 | 9/24/2020 | Fail Screens: D, F, G, I, J, K, L, M, S5 | 12/1/2020 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-08-04 13:48 | 2593-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SONOMA | FITCH MTN SUB | Solar PV, Storage | 2.4659 | 9/9/2020 | 11/3/2020 | Fail Screens: B, D, F, G, I, J, K, L, M, V1, S5, A1 | 12/21/2020 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-08-31 15:33 | 2594-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Engine | 1 | 9/9/2020 | 10/7/2020 | Fail Screens: B |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-08-17 18:36 | 2595-WD | Independent Study | Independent Study | Active | 7/1/2022 |  |  | YOLO | MADISON SUB | Other | 14.4 | 9/9/2020 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 2022-04-22 | 2022-09-21 | Executed | No former queue position
2020-09-01 12:05 | 2596-WD | Independent Study | Independent Study | Active | 6/1/2023 | 7/27/2023 |  | MERCED | DOS PALOS SUB | Solar PV | 2.1035 | 9/16/2020 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 2/18/2021 | N/A | Executed | No former queue position
2020-08-25 13:59 | 2597-WD | Fast Track | Fast Track | Active | 11/30/2021 | 6/9/2023 |  | CONTRA COSTA | BRENTWOOD SUB | Solar PV | 2.5 | 9/23/2020 | 10/20/2020 | Fail Screens: 2, 5, 6, 10 | 12/7/2020 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-08-25 15:02 | 2598-WD | Fast Track | Fast Track | Active | 11/30/2021 | 8/26/2022 |  | CONTRA COSTA | BRENTWOOD SUB | Solar PV | 3 | 9/23/2020 | 10/20/2020 | Fail Screens: 2, 6, 10 | 12/21/2020 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-09-03 15:13 | 2599-WD | Independent Study | Independent Study | Withdrawn | 7/1/2022 | Withdrawn | Withdrawn | YOLO | ZAMORA SUB | Solar PV | 3.6 | 9/23/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-09-02 11:48 | 2600-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | CALAVERAS | FROGTOWN SUB | Storage | 0.14 | 9/23/2020 | 10/15/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-09-14 22:11 | 2601-WD | Independent Study | Independent Study | Withdrawn | 5/1/2021 | Withdrawn | Withdrawn | CONTRA COSTA | HERDLYN SUB | Solar PV, Storage | 7 | 9/23/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-09-09 13:32 | 2602-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | NAPA | CALISTOGA SUB | Solar PV, Storage | 0.625 | 9/23/2020 | 10/13/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-09-02 13:24 | 2603-WD | Fast Track | Independent Study | Withdrawn | 11/30/2021 | Withdrawn | Withdrawn | CONTRA COSTA | BRENTWOOD SUB | Solar PV | 3.0602 | 9/30/2020 | 11/17/2020 | Fail Screens: 2, 6, 10 | 2/18/2021 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-09-21 12:34 | 2604-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | SAN RAMON SUB | Solar PV | 1.4166 | 9/30/2020 | 10/26/2020 | Fail Screens: M, S5 | 12/14/2020 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-09-01 10:38 | 2605-WD | Fast Track | Fast Track | Withdrawn | 11/30/2021 | Withdrawn | Withdrawn | BUTTE | ESQUON SUB | Solar PV | 2 | 9/30/2020 | 11/10/2020 | Fail Screens: 2, 4, 10 | 2/1/2021 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-09-01 14:12 | 2606-WD | Fast Track | Fast Track | Active | 2/27/2021 | 11/12/2021 |  | SONOMA | SONOMA A SUB | Storage | 0.25 | 10/7/2020 | 10/20/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-09-22 15:19 | 2607-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | CONTRA COSTA | Withdrawn | Other | 0.001 | 10/7/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-09-28 15:17 | 2608-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | SAN FRAN H (MARTIN) SUB | Solar PV | 0.08878 | 10/7/2020 | 11/13/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-09-02 09:49 | 2609-WD | Fast Track | Independent Study | Withdrawn | 11/30/2021 | Withdrawn | Withdrawn | HUMBOLDT | CARLOTTA SUB | Wind | 3 | 10/7/2020 | 10/26/2020 | Fail Screens: 2, 4, 10 | 12/21/2020 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-09-04 11:19 | 2610-RD | Fast Track | Detailed Study | Withdrawn | 9/30/2021 | Withdrawn | Withdrawn | KERN | FAMOSO SUB | Engine | 3.5984 | 10/14/2020 | 11/4/2020 | Fail Screens: B, C, D, I, J, K, L, V1, S5, A1 | 1/8/2021 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-10-08 00:17 | 2611-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Engine | 0.075 | 10/21/2020 | 11/5/2020 | Fail Screens: A | 12/16/2020 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-10-07 15:48 | 2612-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | FRESNO | TRANSMISSION E20T | Solar PV, Storage | 7.05 | 10/28/2020 | N/A | N/A | N/A | N/A | Pass | 2/23/2021 | N/A | Executed | No former queue position
2020-10-18 10:55 | 2613-WD | Independent Study | Independent Study | Withdrawn | 8/31/2021 | Withdrawn | Withdrawn | KERN | WELLFIELD SUB | Solar PV | 3 | 10/28/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-10-18 10:57 | 2614-WD | Independent Study | Independent Study | Active | 8/31/2021 | 11/18/2022 |  | KINGS | ALPAUGH SUB | Solar PV | 3 | 10/28/2020 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 2/23/2021 | N/A | Executed | No former queue position
2020-10-18 10:59 | 2615-WD | Independent Study | Independent Study | Withdrawn | 8/31/2021 | Withdrawn | Withdrawn | KINGS | HENRIETTA SUB | Solar PV | 3 | 10/28/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-10-18 12:52 | 2616-WD | Independent Study | Independent Study | Withdrawn | 8/31/2021 | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV | 4.25 | 10/28/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-10-12 15:48 | 2617-RD | Fast Track | Fast Track | Active | Not Provided |  |  | EL DORADO | PLACERVILLE SUB | Storage | 0.07 | 11/4/2020 | 12/3/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-10-23 12:48 | 2618-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SANTA CLARA | DIXON LANDING SUB | Solar PV | 0.96 | 11/4/2020 | N/A | N/A | N/A | N/A | Pass | 4/8/2021 | N/A | Executed | No former queue position
2020-10-26 12:47 | 2619-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | CALIFORNIA AVE SUB | Solar PV | 1.4998 | 11/4/2020 | 12/7/2020 | Fail Screens: J, K, M, V1, S5, A1 | 1/6/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-10-08 16:04 | 2620-RD | Fast Track | Fast Track | Active | Not Provided |  |  | CONTRA COSTA | FAIRVIEW SUB | Solar PV | 1.75 | 11/4/2020 | 11/23/2020 | Fail Screens: D, F, G, H, I, J, K, M | 1/6/2021 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-10-20 11:35 | 2621-WD | Fast Track | Fast Track | Withdrawn | 11/30/2021 | Withdrawn | Withdrawn | BUTTE | OROVILLE SUB | Solar PV | 2 | 11/4/2020 | 11/24/2020 | Fail Screens: 2, 4, 5 | 1/28/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-10-20 12:05 | 2622-WD | Fast Track | Independent Study | Active | 11/30/2021 | 11/13/2023 |  | HUMBOLDT | ARCATA SUB | Solar PV | 3 | 11/4/2020 | 12/1/2020 | Fail Screens: 2, 4, 5, 10 | 2/27/2021 | Fail | Pass | 10/19/2021 | N/A | Executed | No former queue position
2020-10-23 18:17 | 2623-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | MONTEREY | JOLON SUB | Solar PV, Storage | 6.263 | 11/10/2020 | N/A | N/A | N/A | N/A | Pass | 5/21/2021 | N/A | Executed | No former queue position
2020-10-22 10:20 | 2624-WD | Independent Study | Independent Study | Withdrawn | 9/15/2022 | Withdrawn | Withdrawn | PLACER | LINCOLN SUB | Solar PV, Storage | 5.0003 | 11/10/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-09-29 15:35 | 2625-RD | Fast Track | Fast Track | Withdrawn | 5/31/2021 | Withdrawn | Withdrawn | MARIN | COTATI SUB | Solar PV, Storage | 1.8133 | 11/10/2020 | 12/21/2020 | Fail | 06/03/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | R21 Transition to WDT SGIA
2020-10-19 16:32 | 2626-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | POSO MTN SUB | Solar PV | 3.8585 | 11/10/2020 | 12/9/2020 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-10-27 10:47 | 2627-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | NEVADA | NARROWS SUB | Storage | 0.14 | 11/10/2020 | 12/9/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-10-28 23:18 | 2628-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | SAN LEANDRO U SUB | Storage | 0.21 | 11/10/2020 | 2/3/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-10-13 10:36 | 2629-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | YOLO | MADISON SUB | Storage | 0.28 | 11/18/2020 | 2/3/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-10-13 11:04 | 2630-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | YOLO | MADISON SUB | Storage | 0.7 | 11/18/2020 | 2/3/2021 | Fail Screens: I, M, S5, A1 | 4/14/2021 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-11-05 07:30 | 2631-WD | Fast Track | Fast Track | Withdrawn | 2/1/2022 | Withdrawn | Withdrawn | FRESNO | BULLARD SUB | Solar PV | 0.06015 | 11/18/2020 | 12/4/2020 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-10-27 18:17 | 2632-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | HUMBOLDT | EUREKA E SUB | Storage | 0.21 | 11/18/2020 | 2/20/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-10-19 12:51 | 2633-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN JOAQUIN | WEBER SUB | Solar PV | 1.3 | 11/18/2020 | 1/8/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-11-04 10:49 | 2634-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | HUMBOLDT | RIO DELL SUB | Other, Storage | 0.88 | 11/24/2020 | 2/5/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-11-09 10:19 | 2635-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MENDOCINO | UKIAH SUB | Solar PV | 1.0159 | 11/24/2020 | 3/8/2021 | Fail Screens: D, G, J, K, L, M, S5 | 5/18/2021 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-11-05 10:49 | 2636-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | HUMBOLDT | NEWBURG SUB | Storage | 0.28 | 11/24/2020 | 4/23/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-10-09 10:37 | 2637-WD | Fast Track | Independent Study | Withdrawn | 11/30/2021 | Withdrawn | Withdrawn | BUTTE | BUTTE SUB | Solar PV | 2 | 11/24/2020 | 12/18/2020 | Fail Screens: 2, 4, 5, 10 | 2/27/2021 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-10-27 14:18 | 2638-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SONOMA | PENNGROVE SUB | Solar PV | 0.72 | 11/24/2020 | 12/17/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-11-17 11:34 | 2639-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SANTA BARBARA | FAIRWAY SUB | Solar PV, Storage | 3.4613 | 12/2/2020 | N/A | N/A | N/A | N/A | Pass | 5/18/2021 | N/A | Executed | No former queue position
2020-11-11 13:55 | 2640-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | KINGS | KINGSBURG SUB | Solar PV | 1.08 | 12/2/2020 | 12/23/2020 | Fail Screens: D, F, G, J, K, M, S5 | 1/20/2021 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-11-20 16:07 | 2641-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | GUERNSEY SUB | Solar PV | 2.58 | 12/2/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-11-17 12:03 | 2642-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | KERN | BAKERSFIELD SUB | Solar PV | 0.9 | 12/2/2020 | 3/11/2021 | Fail Screens: F, G, H, J, K, L, M, S5 | 4/26/2021 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-11-06 09:32 | 2643-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | HUMBOLDT | ARCATA SUB | Storage | 0.14 | 12/9/2020 | 2/2/2021 | Fail Screens: I, J, M, V1, S5 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-11-09 09:19 | 2644-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | TUOLUMNE | CURTIS SUB | Storage | 0.07 | 12/9/2020 | 12/30/2020 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-11-06 18:18 | 2645-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CLARA | LAWRENCE SUB | Storage | 0.73317 | 12/9/2020 | 10/19/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-12-01 10:19 | 2646-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | GUERNSEY SUB | Solar PV | 1.32 | 12/9/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-11-30 17:32 | 2647-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | OLD RIVER SUB | Solar PV | 2.0029 | 12/9/2020 | N/A | N/A | N/A | N/A | Pass | 6/9/2021 | N/A | Executed | No former queue position
2020-11-16 08:34 | 2648-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | KERN | MARICOPA SUB | Solar PV | 1.4936 | 12/9/2020 | 12/29/2020 | Fail Screens: D, F, G, I, J, K, L, M, V1, V2, S5, A1 | 2/22/2021 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-11-09 11:06 | 2649-WD | Fast Track | Independent Study | Active | 11/30/2021 | 11/13/2023 |  | MERCED | DOS PALOS SUB | Solar PV | 3 | 12/16/2020 | 1/16/2021 | Fail Screens: 2, 4, 5, 7, 9, 10 | 3/29/2021 | Fail | Pass | 10/18/2021 | N/A | Executed | No former queue position
2020-11-13 09:18 | 2650-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN MATEO | WOODSIDE SUB | Storage | 0.05 | 12/16/2020 | 2/10/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-11-19 13:19 | 2651-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | HUMBOLDT | EUREKA A SUB | Storage | 0.21 | 12/16/2020 | 1/11/2021 | Fail Screens: I, J, V1, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-11-20 12:48 | 2652-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | HUMBOLDT | GARBERVILLE SUB | Storage | 0.14 | 12/16/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-11-20 13:16 | 2653-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | LAKE | HARTLEY SUB | Storage | 0.14 | 12/16/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-11-20 14:49 | 2654-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | HUMBOLDT | HARRIS SUB | Storage | 0.14 | 12/16/2020 | 1/14/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-11-24 08:03 | 2655-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | LAKE | LUCERNE SUB | Storage | 0.21 | 12/16/2020 | 1/7/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-11-04 16:18 | 2656-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SONOMA | SANTA ROSA A SUB | Storage | 1.8786 | 12/23/2020 | 11/1/2021 | Fail Screens: B, D, I, J, K, L, M, V1, S5, A1 | 1/4/2022 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-12-07 21:47 | 2657-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | PLACER | HIGGINS SUB | Storage | 0.21 | 12/23/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-12-07 22:03 | 2658-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | NEVADA | BRUNSWICK SUB | Storage | 0.6435 | 12/23/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-12-07 22:17 | 2659-RD | Fast Track | Fast Track | Active | Not Provided |  |  | NEVADA | BRUNSWICK SUB | Storage | 0.14 | 12/23/2020 | 3/5/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-12-07 22:32 | 2660-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | NEVADA | BRUNSWICK SUB | Storage | 0.14 | 12/23/2020 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-12-07 22:47 | 2661-RD | Fast Track | Fast Track | Active | Not Provided |  |  | NEVADA | BRUNSWICK SUB | Storage | 0.14 | 12/23/2020 | 3/31/2021 | Fail Screens: L |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-12-07 23:32 | 2662-RD | Fast Track | Fast Track | Active | Not Provided |  |  | NEVADA | HIGGINS SUB | Storage | 0.14 | 12/23/2020 | 3/4/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-12-09 10:34 | 2663-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SONOMA | SONOMA A SUB | Engine | 0.42 | 12/23/2020 | N/A | N/A | N/A | N/A | Pass | 4/14/2021 | N/A | Executed | No former queue position
2020-11-18 14:18 | 2664-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | NEVADA | BRUNSWICK SUB | Storage | 0.14 | 12/30/2020 | 1/21/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-12-01 17:47 | 2665-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | EL DORADO | APPLE HILL SUB | Storage | 0.21 | 12/30/2020 | 1/21/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-12-02 10:18 | 2666-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SONOMA | CLOVERDALE SUB | Storage | 0.28 | 12/30/2020 | 6/4/2021 | Fail Screens: D, G, I, J, V1, S5 | 8/6/2021 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-12-02 14:35 | 2667-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | LAKE | HIGHLANDS SUB | Storage | 0.21 | 12/30/2020 | 1/26/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-12-07 14:48 | 2668-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SONOMA | CLOVERDALE SUB | Storage | 0.14 | 12/30/2020 | 4/12/2021 | Fail Screens: G, I, J, M, V1, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-12-10 10:21 | 2669-RD | Fast Track | Detailed Study | In Service | Not Provided |  |  | MENDOCINO | HOPLAND SUB | Solar PV, Storage | 2.4665 | 12/30/2020 | 2/8/2021 | Fail Screens: F, M, V1 | 5/25/2021 | Fail | Pass | 10/26/2021 | N/A | Executed | No former queue position
2020-12-10 10:16 | 2670-WD | Fast Track | Fast Track | Withdrawn | 11/30/2021 | Withdrawn | Withdrawn | MERCED | LIVINGSTON SUB | Solar PV | 2 | 12/30/2020 | 2/3/2021 | Fail Screens: 2, 4, 5, 7, 9, 10 | 3/31/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-12-01 05:00 | 2671-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | RIO BRAVO SUB | Engine | 5.625 | 12/30/2020 | 2/23/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-12-10 16:09 | 2672-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | HUMBOLDT | JANES CREEK SUB | Storage | 0.35 | 1/6/2021 | 6/1/2021 | Fail Screens: D, F, I, J, M, V1, S5 | 7/29/2021 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-12-11 12:39 | 2673-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | NEVADA | BRUNSWICK SUB | Storage | 0.14 | 1/6/2021 | 1/21/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-12-11 15:04 | 2674-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | HUMBOLDT | GARBERVILLE SUB | Storage | 0.21 | 1/6/2021 | 3/15/2021 | Fail Screens: D, F, I, J, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-12-11 15:37 | 2675-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | HUMBOLDT | NEWBURG SUB | Storage | 0.28 | 1/6/2021 | 4/5/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-12-09 09:47 | 2676-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | FRESNO | WOODWARD SUB | Solar PV, Storage | 2.185 | 1/6/2021 | N/A | N/A | N/A | N/A | Pass | 7/30/2021 | N/A | Executed | No former queue position
2020-12-16 19:55 | 2677-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | GATES SUB | Solar PV | 3.192 | 1/6/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-12-31 11:00 | 2678-WD | Independent Study | Independent Study | Withdrawn | 3/11/2022 | Withdrawn | Withdrawn | CONTRA COSTA | BRENTWOOD SUB | Solar PV | 5 | 1/13/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-12-29 17:01 | 2679-RD | Detailed Study | DGSP | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | GUERNSEY SUB | Solar PV | 1.32 | 1/13/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-11-24 15:04 | 2680-RD | Detailed Study | Detailed Study | Withdrawn | 6/1/2022 | Withdrawn | Withdrawn | MERCED | SANTA NELLA SUB | Turbine | 7.2 | 1/13/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-12-22 13:16 | 2681-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SHASTA | JESSUP SUB | Storage | 0.21 | 1/13/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-12-23 11:32 | 2682-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | HUMBOLDT | GARBERVILLE SUB | Storage | 0.28 | 1/13/2021 | 8/9/2021 | Fail Screens: F, I, J, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-12-23 12:46 | 2683-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | LAKE | HIGHLANDS SUB | Storage | 0.14 | 1/13/2021 | 4/27/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-01-07 18:26 | 2684-WD | Independent Study | DGSP | Withdrawn | 3/11/2022 | Withdrawn | Withdrawn | YOLO | MADISON SUB | Solar PV | 5 | 1/13/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2020-12-15 18:14 | 2685-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | HUMBOLDT | WILLOW CREEK SUB | Storage | 0.21 | 1/13/2021 | 4/15/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-12-15 18:35 | 2686-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | HUMBOLDT | WILLOW CREEK SUB | Storage | 0.14 | 1/13/2021 | 6/9/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-01-06 13:31 | 2687-RD | Fast Track | Detailed Study | In Service | Not Provided |  |  | KINGS | GUERNSEY SUB | Solar PV | 1.625 | 1/20/2021 | 3/2/2021 | Fail Screens: F, J, K, M, V1, V2, S5, A1 | 4/1/2021 | Fail | Pass | 8/10/2021 | N/A | Executed | No former queue position
2020-12-11 15:19 | 2688-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | LAKE | HARTLEY SUB | Storage | 0.14 | 1/27/2021 | 3/24/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-12-16 12:12 | 2689-RD | Detailed Study | Detailed Study | Active | 5/2/2022 |  |  | MADERA | BORDEN SUB | Steam Turbine | 5 | 1/27/2021 | N/A | N/A | N/A | N/A | Pass | 8/18/2021 | N/A | Executed | No former queue position
2020-12-30 08:47 | 2690-RD | Fast Track | Fast Track | Active | Not Provided |  |  | HUMBOLDT | NEWBURG SUB | Storage | 0.3575 | 1/27/2021 | 5/12/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-12-30 15:18 | 2691-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | HUMBOLDT | EEL RIVER SUB | Storage | 0.14 | 1/27/2021 | 3/2/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-12-30 16:16 | 2692-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | HUMBOLDT | ARCATA SUB | Storage | 0.14 | 1/27/2021 | 7/28/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-01-05 10:48 | 2693-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | HUMBOLDT | ARCATA SUB | Storage | 0.07 | 1/27/2021 | 3/9/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-01-05 12:25 | 2694-WD | Independent Study | Independent Study | In Service | 11/5/2021 |  |  | SUTTER | PEASE SUB | Storage | 6 | 1/27/2021 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 11/5/2021 | N/A | Executed | No former queue position
2021-01-06 08:32 | 2695-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | KERN | CHARCA SUB | Solar PV, Storage | 2.7435 | 1/27/2021 | N/A | N/A | N/A | N/A | Pass | 6/21/2021 | N/A | Executed | No former queue position
2021-01-12 23:30 | 2696-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN JOAQUIN | TRACY SUB | Engine, Solar PV | 0.7666 | 1/27/2021 | 3/1/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-01-04 15:49 | 2697-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | HUMBOLDT | HARRIS SUB | Storage | 0.98 | 2/3/2021 | 7/20/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-01-08 12:18 | 2698-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | HUMBOLDT | JANES CREEK SUB | Storage | 0.35 | 2/3/2021 | 4/30/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-01-08 16:32 | 2699-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | HUMBOLDT | HARRIS SUB | Storage | 0.14 | 2/3/2021 | 3/30/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-01-12 10:03 | 2700-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | MONTEREY | OIL FIELDS SUB | Solar PV, Turbine | 13.9532 | 2/3/2021 | N/A | N/A | N/A | N/A | Pass | 05/26/2022 | N/A | Executed | No former queue position
2021-01-11 14:52 | 2701-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | HUMBOLDT | ARCATA SUB | Storage | 0.28 | 2/3/2021 | 3/1/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2020-12-16 19:39 | 2702-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | LAKE | CLEAR LAKE SUB | Storage | 0.42 | 2/3/2021 | 4/27/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-01-13 12:32 | 2703-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | TEHAMA | RAWSON SUB | Storage | 0.35 | 2/3/2021 | 5/27/2021 | Fail Screens: S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-01-15 13:31 | 2704-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | BUTTE | PARADISE SUB | Storage | 0.21 | 2/3/2021 | 3/11/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-01-15 15:48 | 2705-RD | Fast Track | Fast Track | Active | Not Provided |  |  | NEVADA | BRUNSWICK SUB | Storage | 0.21 | 2/3/2021 | 6/10/2021 | Fail Screens: F, L, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-01-22 14:20 | 2706-WD | Independent Study | DGSP | Active | 8/30/2022 |  |  | PLACER | WHEATLAND SUB | Storage | 5.1 | 2/3/2021 | N/A | N/A | N/A | N/A | Fail | 2021-09-16 | N/A | Executed | No former queue position
2020-12-29 08:10 | 2707-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | TEMBLOR SUB | Solar PV, Turbine | 107.64 | 2/10/2021 | N/A | N/A | N/A | N/A | Pass | 2022-07-21 | N/A | Executed | No former queue position
2021-01-29 09:47 | 2708-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | CONTRA COSTA | SAN RAMON SUB | Solar PV, Storage | 1.447 | 2/10/2021 | 4/8/2021 | Fail Screens: M, S5 | 6/22/2021 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-02-03 16:46 | 2709-RD | Fast Track | Fast Track | Active | Not Provided |  |  | CONTRA COSTA | SAN RAMON SUB | Solar PV, Storage | 1.547 | 2/10/2021 | 4/8/2021 | Fail Screens: D, H, M, S5 | 6/22/2021 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-02-03 16:47 | 2710-RD | Fast Track | Fast Track | Active | Not Provided |  |  | CONTRA COSTA | SAN RAMON SUB | Solar PV, Storage | 1.572 | 2/10/2021 | 4/16/2021 | Fail Screens: D, H, M, S5 | 6/22/2021 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-01-29 15:46 | 2711-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SOLANO | PEABODY SUB | Engine, Solar PV, Storage | 4.2574 | 2/17/2021 | N/A | N/A | N/A | N/A | Pass | 8/31/2021 | N/A | Executed | No former queue position
2021-02-03 17:02 | 2712-RD | Fast Track | Fast Track | Active | Not Provided |  |  | CONTRA COSTA | SAN RAMON SUB | Solar PV, Storage | 1.5428 | 2/17/2021 | 4/20/2021 | Fail Screens: D, M, S5 | 6/23/2021 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-02-03 17:02 | 2713-RD | Fast Track | Fast Track | Active | Not Provided |  |  | CONTRA COSTA | SAN RAMON SUB | Solar PV, Storage | 1.872 | 2/17/2021 | 4/20/2021 | Fail Screens: D, M, S5 | 6/24/2021 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-01-28 22:06 | 2714-WD | Independent Study | Independent Study | Withdrawn | 9/1/2021 | Withdrawn | Withdrawn | KERN | LAMONT SUB | Engine, Solar PV, Storage | 4.95 | 2/17/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-02-08 17:15 | 2715-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | DUMBARTON SUB | Storage – EV | 0.1536 | 2/24/2021 | 3/1/2021 | Fail Screens: B, J, V1, S5, A1 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-02-16 12:33 | 2716-RD | Detailed Study | DGSP | Active | Not Provided |  |  | KERN | FAMOSO SUB | Solar PV | 2.3875 | 2/24/2021 | N/A | N/A | N/A | N/A | Fail | 2021-08-12 | N/A | Executed | No former queue position
2021-02-19 12:17 | 2717-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Solar PV | 0.625 | 2/24/2021 | 3/15/2021 | Fail Screens: I, J, K | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-01-21 15:01 | 2718-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | LAKE | HIGHLANDS SUB | Storage | 0.21 | 3/3/2021 | 3/22/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-02-09 14:17 | 2719-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | EL DORADO | EL DORADO PH | Storage | 0.35 | 3/3/2021 | 4/19/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-02-09 16:32 | 2720-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | EL DORADO | APPLE HILL SUB | Storage | 0.35 | 3/3/2021 | 6/23/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-02-09 17:31 | 2721-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MENDOCINO | HOPLAND SUB | Storage | 0.14 | 3/3/2021 | 4/20/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-02-10 14:31 | 2722-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MENDOCINO | HOPLAND SUB | Storage | 0.14 | 3/3/2021 | 5/19/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-02-11 08:46 | 2723-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | CONTRA COSTA | SAN RAMON SUB | Fuel Cell, Solar PV, Storage | 2.9928 | 3/3/2021 | N/A | N/A | N/A | N/A | Fail | 1/4/2022 | N/A | Executed | No former queue position
2021-02-16 09:32 | 2724-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | POSO MTN SUB | Solar PV | 3.8585 | 3/3/2021 | N/A | N/A | N/A | N/A | Pass | 7/12/2021 | N/A | Executed | No former queue position
2021-02-08 08:37 | 2725-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SONOMA | SONOMA A SUB | Storage | 0.21 | 3/3/2021 | 4/6/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-02-11 09:47 | 2726-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALPINE | SALT SPRINGS PH | Storage | 0.21 | 3/3/2021 | 6/23/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-02-17 00:02 | 2727-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MONTEREY | VIEJO SUB | Storage | 0.21 | 3/3/2021 | 4/20/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-02-17 03:31 | 2728-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MADERA | OAKHURST SUB | Storage | 0.21 | 3/3/2021 | 4/13/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-02-17 00:17 | 2729-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN MATEO | BELMONT SUB | Storage | 0.21 | 3/3/2021 | 4/19/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-02-17 00:17 | 2730-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MONTEREY | SOLEDAD SUB | Storage | 0.21 | 3/3/2021 | 4/23/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-02-17 23:01 | 2731-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SONOMA | CORONA SUB | Storage | 0.21 | 3/3/2021 | 4/7/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-02-18 16:16 | 2732-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN MATEO | BAIR SUB | Storage | 0.715 | 3/3/2021 | 4/13/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-02-18 21:16 | 2733-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | FRESNO | WEST FRESNO SUB | Storage | 0.21 | 3/3/2021 | 3/25/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-02-20 16:46 | 2734-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | TRANSMISSION E20T | Storage | 1.287 | 3/3/2021 | 3/24/2021 | Fail Screens: J, K, L, M | 5/5/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-02-20 17:01 | 2735-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | RAINBOW SUB | Storage | 1.287 | 3/3/2021 | 3/24/2021 | Fail Screens: J, K, M, V1, S5, A1 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-02-17 17:16 | 2736-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | EL DORADO | APPLE HILL SUB | Storage | 0.42 | 3/10/2021 | 4/14/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-02-08 12:01 | 2737-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | FRESNO | WOODWARD SUB | Solar PV | 0.64773 | 3/10/2021 | 3/31/2021 | Fail Screens: H, I, J, K, M, V1, S5, A1 | 5/3/2021 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-02-23 14:01 | 2738-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MENDOCINO | HOPLAND SUB | Storage | 0.14 | 3/10/2021 | 4/15/2021 | Fail Screens: F, I, J, M, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-02-25 11:31 | 2739-WD | Fast Track | Fast Track | Withdrawn | 11/30/2023 | Withdrawn | Withdrawn | PLACER | LINCOLN SUB | Other | 2.04 | 3/17/2021 | 6/15/2021 | Fail Screens: 2, 4, 5, 9, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-02-22 17:46 | 2740-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | YOLO | MADISON SUB | Engine, Solar PV | 21.9442 | 3/17/2021 | 4/15/2021 | Fail Screens: F, G | 6/4/2021 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-02-26 16:16 | 2741-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | HUMBOLDT | NEWBURG SUB | Storage | 0.14 | 3/24/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-03-03 16:16 | 2742-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | EL DORADO | DIAMOND SPRINGS SUB | Storage | 0.14 | 3/24/2021 | 5/7/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-03-04 13:46 | 2743-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SONOMA | BELLEVUE SUB | Solar PV | 1.7 | 3/24/2021 | 4/12/2021 | Fail Screens: D, G, H, J, K, L, M, V1, S5, A1 | 6/8/2021 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-03-02 21:16 | 2744-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | SAN MATEO | EAST GRAND SUB | Engine | 3.5 | 3/24/2021 | N/A | N/A | N/A | N/A | Pass |  |  | Executed | No former queue position
2021-03-08 12:47 | 2745-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | PLACER | PLEASANT GROE | Solar PV | 2.7827 | 3/24/2021 | 4/13/2021 | Fail Screens: F, H, I, J, K, L, M, S5 | 7/1/2021 | Fail | Pass | 11/15/2021 | N/A | Executed | No former queue position
2021-03-12 19:16 | 2746-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | CONTRA COSTA | EL CERRITO G SUB | Solar PV | 1.125 | 3/31/2021 | 4/16/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-03-03 12:18 | 2747-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | SAN JOAQUIN | WEBER SUB | Solar PV, Storage | 1.6 | 3/31/2021 | 6/4/2021 | Fail Screens: D, J, K, L, M, V1, S5, A1 | 7/12/2021 | Fail | Pass | 2022-03-10 | N/A | Executed | No former queue position
2021-03-11 20:05 | 2748-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | FRESNO | BULLARD SUB | Storage | 0.21 | 3/31/2021 | 4/26/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-03-22 14:49 | 2749-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CLARA | TRANSMISSION | Storage | 3 | 3/31/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-03-04 12:06 | 2750-WD | Independent Study | Independent Study | Withdrawn | 3/11/2022 | Withdrawn | Withdrawn | CONTRA COSTA | BRENTWOOD SUB | Solar PV, Storage | 7 | 3/31/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-03-11 17:16 | 2751-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | FRESNO | COALINGA #2 SUB | Solar PV | 1.25 | 3/31/2021 | N/A | N/A | N/A | N/A | Pass | 6/23/2021 | N/A | Executed | No former queue position
2021-03-25 10:19 | 2752-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | COPUS SUB | Solar PV | 4.5 | 3/31/2021 | N/A | N/A | N/A | N/A | Pass | 09/17/2021 | N/A | Executed | No former queue position
2021-03-04 18:01 | 2753-RD | Fast Track | Fast Track | Active | Not Provided |  |  | CONTRA COSTA | KIRKER SUB | Engine, Turbine | 0.8 | 4/7/2021 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2021-03-10 12:22 | 2754-RD | Fast Track | Fast Track | Withdrawn | 8/31/2022 | Withdrawn | Withdrawn | MERCED | EL CAPITAN SUB | Storage | 0.5 | 4/7/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-03-23 01:16 | 2755-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA CLARA | LOS ALTOS SUB | Storage | 0.21 | 4/7/2021 | 6/23/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-03-26 08:12 | 2756-WD | Independent Study | Independent Study | Withdrawn | 12/15/2025 | Withdrawn | Withdrawn | SAN BENITO | HOLLISTER SUB | Solar PV, Storage | 149.992 | 4/7/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-03-24 11:47 | 2757-WD | Independent Study | Independent Study | Withdrawn | 12/1/2023 | Withdrawn | Withdrawn | KERN | TAFT SUB | Solar PV, Storage | 41.58 | 4/7/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-03-26 10:22 | 2758-WD | Independent Study | Independent Study | Active | 4/30/2023 |  |  | ALAMEDA | OAKLAND J SUB | Storage | 12.48 | 4/7/2021 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 2023-01-14 | In Progress |  | No former queue position
2021-03-29 14:03 | 2759-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | FRESNO | MENDOTA SUB | Solar PV | 1.9375 | 4/7/2021 | 5/28/2021 | Fail Screens: M, S5, A1 | 7/8/2021 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-03-31 08:07 | 2760-WD | Cluster | Cluster | Withdrawn | 6/30/2024 | Withdrawn | Withdrawn | KERN | POSO MTN SUB | Storage | 137.56 | 4/7/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-03-29 17:04 | 2761-WD | Independent Study | Independent Study | Withdrawn | 6/14/2022 | Withdrawn | Withdrawn | NAPA | HIGHWAY SUB | Storage | 5 | 4/7/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-03-29 19:12 | 2762-WD | Independent Study | Independent Study | Active | 6/14/2022 |  |  | NAPA | TULUCAY SUB | Storage | 5 | 4/7/2021 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 02/04/2022 | N/A | Executed | No former queue position
2021-03-29 19:34 | 2763-WD | Independent Study | Independent Study | Withdrawn | 6/14/2022 | Withdrawn | Withdrawn | SOLANO | BAHIA SUB | Storage | 4.9 | 4/7/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | 12/28/2021 | Withdrawn | Withdrawn | No former queue position
2021-03-31 15:21 | 2764-WD | Independent Study | Independent Study | Active | 6/14/2022 |  |  | SANTA BARBARA | FAIRWAY SUB | Storage | 10 | 4/7/2021 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 12/8/2021 | 2022-04-06 | Executed | No former queue position
2021-04-02 10:19 | 2765-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | SMYRNA SUB | Solar PV | 1.56 | 4/14/2021 | 5/20/2021 | Fail Screens: D, F, G, J, K, L, M, V1, S5 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-03-25 17:38 | 2766-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | EL DORADO | APPLE HILL SUB | Storage | 0.715 | 4/14/2021 | 5/20/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-04-05 17:03 | 2767-WD | Fast Track | Fast Track | Withdrawn | 5/16/2022 | Withdrawn | Withdrawn | HUMBOLT | BRIDGEVILLE SUB | Solar PV | 0.99 | 4/14/2021 | 07/06/2021 | Fail Screens: 2, 7, 9, 10 | 9/17/2021 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-04-05 17:14 | 2768-WD | Fast Track | Fast Track | Withdrawn | 5/16/2022 | Withdrawn | Withdrawn | HUMBOLT | BRIDGEVILLE SUB | Solar PV | 0.99 | 4/14/2021 | 6/17/2021 | Fail Screens: 2, 7, 9, 10 | 9/17/2021 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-04-05 17:20 | 2769-WD | Fast Track | Fast Track | Withdrawn | 5/16/2022 | Withdrawn | Withdrawn | HUMBOLT | BRIDGEVILLE SUB | Solar PV | 0.99 | 4/14/2021 | 7/6/2021 | Fail Screens: 2, 4, 7, 9, 10 | 9/17/2021 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-04-05 18:04 | 2770-WD | Fast Track | Fast Track | Withdrawn | 5/16/2022 | Withdrawn | Withdrawn | FRESNO | HAMMONDS SUB | Solar PV | 2 | 4/14/2021 | 5/11/2021 | Fail Screens: 2, 4, 7, 9, 10 | 7/7/2021 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-03-30 16:01 | 2771-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | FRESNO | SAN JOAQUIN SUB | Solar PV | 3.5 | 4/21/2021 | N/A | N/A | N/A | N/A | Pass | 10/20/2021 | N/A | Executed | No former queue position
2021-04-01 14:48 | 2772-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | NEVADA | BRUNSWICK SUB | Storage | 0.14 | 4/21/2021 | 6/11/2021 | Fail Screens: L, M, V1, S5 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-04-02 15:40 | 2773-RD | Detailed Study | Detailed Study | Withdrawn | 2/2/2023 | Withdrawn | Withdrawn | FRESNO | MCCALL SUB | Steam Turbine | 5 | 4/21/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-04-09 14:16 | 2774-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | BUTTE | PARADISE SUB | Storage | 0.49 | 4/21/2021 | 6/15/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-04-09 15:13 | 2775-WD | Independent Study | Independent Study | Withdrawn | 12/1/2022 | Withdrawn | Withdrawn | KERN | COPUS SUB | Solar PV | 0.003 | 4/21/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-04-13 15:58 | 2776-WD | Fast Track | Fast Track | Withdrawn | 4/1/2022 | Withdrawn | Withdrawn | NAPA | HIGHWAY SUB | Solar PV | 0.98304 | 4/21/2021 | 5/20/2021 | Fail Screens: 2, 4, 5, 7, 9, 10 | 7/8/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-04-14 17:01 | 2777-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | GUERNSEY SUB | Solar PV | 2.76 | 4/21/2021 | 6/16/2021 | Fail Screens: F, J, K, M, V1, S5, A1 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-04-15 16:01 | 2778-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | STOREY SUB | Engine | 4.5 | 4/21/2021 | 5/24/2021 | Fail Screens: B, F, J, K, M, S5 | 8/17/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-04-08 12:31 | 2779-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | HUMBOLDT | HUMBOLDT BAY PP | Solar PV, Storage | 1.93 | 4/28/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-04-16 04:32 | 2780-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | NAPA | NAPA SUB | Storage | 0.21 | 4/28/2021 | 7/2/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-04-15 15:46 | 2781-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | WEBER SUB | Solar PV, Storage | 2.0431 | 5/5/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-04-19 12:11 | 2782-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | WEBER SUB | Solar PV, Storage | 2.0121 | 5/5/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-04-19 23:12 | 2783-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SONOMA | BELLEVUE SUB | Storage | 0.21 | 5/5/2021 | 7/6/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-04-05 15:01 | 2784-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | STANISLAUS | NEWMAN SUB | Solar PV | 1.875 | 5/12/2021 | 6/11/2021 | Fail Screens: D, F, J, K, M | 8/3/2021 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-04-06 11:46 | 2785-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | HUMBOLDT | EUREKA A SUB | Storage | 0.42 | 5/12/2021 | 10/12/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-04-14 17:16 | 2786-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | HUMBOLDT | EUREKA A SUB | Storage | 0.14 | 5/12/2021 | 7/15/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-04-15 17:30 | 2787-WD | Fast Track | Independent Study | Withdrawn | 5/16/2022 | Withdrawn | Withdrawn | MERCED | WRIGHT SUB | Solar PV | 3 | 5/12/2021 | 6/2/2021 | Fail Screens: 2, 4, 5, 7, 9, 10 | 7/7/2021 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-05-02 17:31 | 2788-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | SAN FRAN A (POTRERO PP) SUB | Solar PV | 0.0657 | 5/12/2021 | 5/13/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-04-05 11:03 | 2789-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | NAPA | CALISTOGA SUB | Storage | 0.429 | 5/12/2021 | 8/23/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-04-23 16:42 | 2790-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | YOLO | DAVIS SUB | Storage | 0.21 | 5/12/2021 | 7/12/2021 | Fail Screens: I, J, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-04-25 15:01 | 2791-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CLARA | MCKEE SUB | Storage | 0.21 | 5/12/2021 | 7/2/2021 | Fail Screens: S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-04-22 16:57 | 2792-WD | Independent Study | Independent Study | Withdrawn | 12/1/2022 | Withdrawn | Withdrawn | KERN | ELK HILLS SUB | Solar PV | 3 | 5/12/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-04-22 08:33 | 2793-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN LUIS OBISPO | SAN LUIS OBISPO SUB | Storage | 0.42 | 5/19/2021 | 6/18/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-04-22 16:32 | 2794-RD | Fast Track | Fast Track | Active | Not Provided |  |  | HUMBOLDT | RIO DELL SUB | Storage | 0.572 | 5/19/2021 | 9/10/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-04-23 12:42 | 2795-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | TEHAMA | TYLER SUB | Storage | 0.14 | 5/19/2021 | 6/17/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-04-26 15:54 | 2796-WD | Independent Study | Independent Study | Active | 2/28/2023 |  |  | KINGS | HENRIETTA SUB | Solar PV | 3 | 5/19/2021 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 2022-02-22 | N/A | Executed | No former queue position
2021-04-26 15:58 | 2797-WD | Independent Study | DGSP | Withdrawn | 2/28/2023 | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV | 4.25 | 5/19/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-05-07 12:52 | 2798-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | TEJON SUB | Solar PV, Storage | 1.1875 | 5/19/2021 | 6/30/2021 | Fail Screens: B, D, I, J, K, L, M, S5 | 8/27/2021 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-05-12 18:28 | 2799-WD | Fast Track | Independent Study | Active | 6/15/2022 |  |  | MERCED | EL NIDO SUB | Solar PV | 3 | 5/19/2021 | 6/10/2021 | Fail Screens: 2, 4, 7, 9, 10 | 7/14/2021 | Fail | Pass | 11/23/2021 | N/A | Executed | No former queue position
2021-04-26 16:42 | 2800-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | BERKELEY F SUB | Solar PV, Storage | 2.1198 | 5/26/2021 | 7/1/2021 | Fail | 8/25/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-05-06 17:31 | 2801-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | FRESNO | BULLARD SUB | Storage | 0.21 | 5/26/2021 | 7/27/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-04-28 13:52 | 2802-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | EL DORADO | PLACERVILLE SUB | Storage | 0.21 | 5/26/2021 | 6/30/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-04-28 15:04 | 2803-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | SAN LUIS OBISPO | TEMPLETON SUB | Storage | 0.9 | 5/26/2021 | 6/17/2021 | Fail Screens: F, H, M | 8/20/2021 | Fail | Pass | 11/15/2021 | N/A | Executed | No former queue position
2021-05-04 12:32 | 2804-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | HUMBOLDT | JANES CREEK SUB | Storage | 0.14 | 5/26/2021 | 6/21/2021 | Fail Screens: F, G, I, J, V1, S5 | 8/19/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-05-04 14:52 | 2805-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | EL DORADO | PLACERVILLE SUB | Storage | 0.42 | 5/26/2021 | 07/20/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-05-14 12:02 | 2806-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | BAKERSFIELD SUB | Storage | 0.985 | 5/26/2021 | 8/2/2021 | Fail Screens: D, F, G, I, J, V1, S5, A1 | 9/17/2021 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-05-14 13:11 | 2807-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | FRESNO | TRANSMISSION | Solar PV, Storage | 4.4117 | 5/26/2021 | N/A | N/A | N/A | N/A | Pass | 11/2/2021 | N/A | Executed | No former queue position
2021-04-28 16:12 | 2808-RD | Fast Track | Fast Track | Active | Not Provided |  |  | MONTEREY | SALINAS SUB | Solar PV, Storage | 2.0715 | 5/26/2021 | 12/10/2021 | Fail Screens: G, I, J, K, M, S5 | 2022-03-07 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-05-07 10:43 | 2809-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | BUTTE | PARADISE SUB | Storage | 0.49 | 5/26/2021 | 6/25/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-05-11 15:22 | 2810-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | STOCKDALE SUB | Solar PV, Storage | 6.032 | 5/26/2021 | N/A | N/A | N/A | N/A | Pass | 03/22/2022 | N/A | Executed | No former queue position
2021-05-11 17:32 | 2811-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | MAGUNDEN SUB | Solar PV, Storage | 2.537 | 5/26/2021 | N/A | N/A | N/A | N/A | Pass | 05/13/2022 | N/A | Executed | No former queue position
2021-05-02 07:28 | 2812-WD | Independent Study | Independent Study | Withdrawn | 9/30/2022 | Withdrawn | Withdrawn | MERCED | EL CAPITAN SUB | Storage | 4.998 | 6/2/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-05-14 12:02 | 2813-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | CALAVERAS | PEORIA SUB | Solar PV | 0.04466 | 6/2/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-05-21 15:24 | 2814-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN H (MARTIN) SUB | Solar PV | 0.27128 | 6/2/2021 | 7/14/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-05-12 16:52 | 2815-RD | Fast Track | Fast Track | Active | Not Provided |  |  | LAKE | CLEAR LAKE SUB | Storage | 0.42 | 6/2/2021 | 09/09/2021 | Fail Screens: D, I, J, M, V1, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-05-24 17:12 | 2816-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | SMYRNA SUB | Solar PV | 1.56 | 6/2/2021 | 7/26/2021 | Fail Screens: D, F, G, J, K, L, M, S5 | 9/10/2021 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-05-25 09:41 | 2817-WD | Fast Track | Fast Track | Withdrawn | 7/5/2022 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Storage | 0.2475 | 6/2/2021 | 7/6/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-05-19 17:48 | 2818-RD | Fast Track | Detailed Study | Active | 5/31/2022 |  |  | CONTRA COSTA | RICHMOND R SUB | Solar PV | 2.25 | 6/2/2021 | 8/24/2021 | Fail Screens: G, I, J, K, M | 9/24/2021 | Fail | Pass | 1/26/2022 | N/A | Executed | No former queue position
2021-05-21 08:55 | 2819-WD | Independent Study | Cluster | Withdrawn | 11/30/2024 | Withdrawn | Withdrawn | KERN | GANSO SUB | Solar PV, Storage | 102.9 | 6/2/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-04-23 16:04 | 2820-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN LUIS OBISPO | SAN MIGUEL SUB | Solar PV, Storage | 1.8049 | 6/9/2021 | 10/18/2021 | Fail Screens: D, J, K, M | 12/30/2021 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-05-13 11:32 | 2821-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | WESTPARK SUB | Solar PV | 1.212 | 6/9/2021 | N/A | N/A | N/A | N/A | Pass | 10/28/2021 | N/A | Executed | No former queue position
2021-05-26 01:52 | 2822-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | NEWARK SUB | Storage | 0.21 | 6/9/2021 | 7/28/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-06-02 15:01 | 2823-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KINGS | CORCORAN SUB | Solar PV | 3.125 | 6/16/2021 | N/A | N/A | N/A | N/A | Pass | 10/5/2021 | N/A | Executed | No former queue position
2021-05-25 22:11 | 2824-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | OLD RIVER SUB | Storage | 0.05626 | 6/16/2021 | 2022-02-18 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-06-07 11:20 | 2825-WD | Fast Track | Fast Track | Withdrawn | 12/2/2022 | Withdrawn | Withdrawn | AMADOR | PINE GROVE SUB | Storage | 3.6975 | 6/16/2021 | 7/9/2021 | Fail Screens: 2, 4, 5, 7, 9, 10 | 8/26/2021 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-05-20 13:53 | 2826-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | EDES SUB | Storage | 0.63 | 6/16/2021 | 10/26/2021 | Fail Screens: G, J, M |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-06-09 17:34 | 2827-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | CARUTHERS SUB | Solar PV | 1.68 | 6/16/2021 | 07/26/2021 | Fail Screens: F, I, J, K, M, V1, S5, A1 | 9/9/2021 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-05-12 16:41 | 2828-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | OLD RIVER SUB | Solar PV | 0.9 | 6/23/2021 | N/A | N/A | N/A | N/A | Pass | 12/28/2021 | N/A | Executed | No former queue position
2021-05-27 09:33 | 2829-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN LUIS OBISPO | SAN LUIS OBISPO SUB | Engine, Storage | 0.29 | 6/23/2021 | 8/10/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-06-04 11:02 | 2830-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SHASTA | BURNEY SUB | Storage | 0.14 | 06/30/2021 | 7/20/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-05-19 23:01 | 2831-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | CONTRA COSTA | LONE TREE SUB | Storage | 0.9295 | 6/23/2021 | 7/26/2021 | Fail Screens: H, I, J, K, L, M, S5 | 8/27/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-05-26 12:53 | 2832-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SIERRA | ALLEGHANY SUB | Storage | 0.14 | 6/23/2021 | 7/15/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-06-08 15:27 | 2833-WD | Fast Track | Fast Track | Withdrawn | 7/15/2022 | Withdrawn | Withdrawn | MERCED | SANTA NELLA SUB | Solar PV | 2 | 6/23/2021 | 7/15/2021 | Fail Screens: 2, 4, 5, 7, 9, 10 | 9/7/2021 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-06-14 18:29 | 2834-WD | Fast Track | Fast Track | Withdrawn | 7/15/2022 | Withdrawn | Withdrawn | HUMBOLDT | EEL RIVER SUB | Solar PV | 0.99 | 6/23/2021 | 7/9/2021 | Fail Screens: 2, 4, 7, 9, 10 | 8/30/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-06-14 18:36 | 2835-WD | Fast Track | Fast Track | Withdrawn | 7/15/2022 | Withdrawn | Withdrawn | HUMBOLDT | EEL RIVER SUB | Solar PV | 0.99 | 6/23/2021 | 7/9/2021 | Fail Screens: 2, 4, 5, 7, 9, 10 | 8/30/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-06-14 18:41 | 2836-WD | Fast Track | Fast Track | Withdrawn | 7/15/2022 | Withdrawn | Withdrawn | HUMBOLDT | EEL RIVER SUB | Solar PV | 0.99 | 6/23/2021 | 7/9/2021 | Fail Screens: 2, 4, 5, 7, 9, 10 | 8/30/2021 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-06-10 16:53 | 2837-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SONOMA | COTATI SUB | Solar PV, Storage | 8.2483 | 6/23/2021 | N/A | N/A | N/A | N/A | Pass | 12/10/2021 | N/A | Executed | No former queue position
2021-06-07 14:18 | 2838-WD | Fast Track | Independent Study | Withdrawn | 12/1/2022 | Withdrawn | Withdrawn | KERN | GOOSE LAKE SUB | Solar PV | 3 | 6/30/2021 | 7/22/2021 | Fail Screens: 2, 7, 9, 10 | 9/13/2021 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-06-23 11:11 | 2839-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | MANTECA SUB | Solar PV | 0.42 | 6/30/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-06-17 12:13 | 2840-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | ANTELOPE SUB | Solar PV | 3 | 6/30/2021 | N/A | N/A | N/A | N/A | Pass | 11/23/2021 | N/A | Executed | No former queue position
2021-05-26 16:11 | 2841-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | HUMBOLDT | NEWBURG SUB | Storage | 0.63 | 6/30/2021 | 09/17/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-05-28 13:21 | 2842-WD | Independent Study | Independent Study | Withdrawn | 7/7/2021 | Withdrawn | Withdrawn | ALAMEDA | ALTAMONT SUB | Engine | 6 | 6/30/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-06-04 07:32 | 2843-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN LUIS OBISPO | SAN LUIS OBISPO SUB | Storage | 0.14 | 6/30/2021 | 08/25/2021 | Fail Screens: J, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-06-15 15:16 | 2844-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | MADERA | MADERA SUB | Solar PV | 1.192 | 7/7/2021 | N/A | N/A | N/A | N/A | Pass | 11/17/2021 | N/A | Executed | No former queue position
2021-06-22 15:13 | 2845-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | BUTTE | ESQUON SUB | Engine, Micro Turbine | 0.13 | 7/7/2021 | 9/21/2021 | Fail Screens: S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-06-16 13:26 | 2846-WD | Fast Track | Independent Study | Withdrawn | 6/15/2023 | Withdrawn | Withdrawn | SAN FRANCISCO | PORTOLA SUB | Solar PV | 1.125 | 7/7/2021 | 7/14/2021 | Fail Screens: 2, 4, 10 | 10/4/2021 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-06-16 13:40 | 2847-WD | Fast Track | Fast Track | Withdrawn | 6/15/2023 | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN A (POTRERO PP) SUB | Solar PV, Storage | 2.79 | 7/7/2021 | 7/26/2021 | Fail Screens: 2, 10 | 10/15/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-06-16 13:51 | 2848-WD | Independent Study | DGSP | Active | 6/15/2023 |  |  | SAN FRANCISCO | SAN FRAN A (POTRERO PP) SUB | Solar PV | 2.85 | 7/7/2021 | N/A | N/A | N/A | N/A | Fail | 2021-12-24 | N/A | Executed | No former queue position
2021-06-16 14:06 | 2849-WD | Independent Study | Independent Study | Active | 6/15/2023 |  |  | SAN FRANCISCO | SAN FRAN H (MARTIN) SUB | Solar PV, Storage | 9.12 | 7/7/2021 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 1/31/2022 | N/A | Executed | No former queue position
2021-06-17 17:00 | 2850-WD | Independent Study | Independent Study | Active | 4/1/2026 |  |  | SANTA BARBARA | CABRILLO SUB | Wind | 60 | 7/7/2021 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 2022-10-28 | 2024-01-23 |  | No former queue position
2021-05-18 09:22 | 2851-WD | Fast Track | Fast Track | Active | 10/28/2022 | 11/4/2022 |  | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Solar PV | 0.625 | 7/14/2021 | 8/4/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-06-21 14:24 | 2852-WD | Fast Track | Fast Track | Withdrawn | 9/1/2023 | Withdrawn | Withdrawn | KERN | TWISSELMAN SUB | Solar PV | 2.125 | 7/14/2021 | 8/26/2021 | Fail Screens: 2, 4, 7, 9, 10 | 10/1/2021 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-06-21 14:42 | 2853-WD | Fast Track | Fast Track | Withdrawn | 9/1/2023 | Withdrawn | Withdrawn | KERN | TWISSELMAN SUB | Storage | 2.125 | 7/14/2021 | 8/25/2021 | Fail Screens: 2, 4, 7, 9, 10 | 10/1/2021 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-06-22 16:13 | 2854-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MENDOCINO | WILLITS A SUB | Engine, Storage | 0.83 | 7/14/2021 | 11/15/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-06-18 13:12 | 2855-RD | Detailed Study | Detailed Study | Withdrawn | 9/1/2022 | Withdrawn | Withdrawn | SHASTA | BURNEY SUB | Engine | 5 | 7/14/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-07-07 21:12 | 2856-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Solar PV | 0.0666 | 7/14/2021 | 9/27/2021 | Fail Screens: I, J, M, V1 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-06-17 11:12 | 2857-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | TULARE | DINUBA SUB | Solar PV, Storage | 0.4233 | 7/21/2021 | N/A | N/A | N/A | N/A | Pass | 2022-04-01 | N/A | Executed | No former queue position
2021-06-22 14:12 | 2858-WD | Independent Study | Independent Study | Withdrawn | 5/27/2022 | Withdrawn | Withdrawn | MADERA | DAIRYLAND SUB | Storage | 13.25 | 7/21/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-06-24 12:52 | 2859-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SHASTA | ANDERSON SUB | Engine, Storage | 0.17 | 7/21/2021 | 9/17/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-06-25 15:05 | 2860-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | HUMBOLDT | HARRIS SUB | Storage | 0.49 | 7/21/2021 | 12/3/2021 | Fail Screens: M | 2022-02-16 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-07-09 12:04 | 2861-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | CAMDEN SUB | Solar PV | 1.56 | 7/21/2021 | 8/13/2021 | Fail Screens: F, J, K, M, S5 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-07-08 10:44 | 2862-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | AMADOR | ELECTRA PH | Engine | 0.17 | 7/21/2021 | 8/25/2021 | Fail Screens: B, J, L, M | 11/3/2021 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-07-01 08:31 | 2863-WD | Independent Study | Independent Study | Withdrawn | 9/30/2022 | Withdrawn | Withdrawn | MENDOCINO | WILLITS A SUB | Other | 6.703 | 7/21/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-07-01 10:48 | 2864-WD | Fast Track | Independent Study | Active | 11/30/2022 |  |  | MERCED | LIVINGSTON SUB | Solar PV | 2 | 7/21/2021 | 8/24/2021 | Fail Screens: 2, 4, 5, 7, 9, 10 | 10/19/2021 | Fail | Pass | 2022-04-29 | N/A | Executed | No former queue position
2021-07-01 12:37 | 2865-WD | Fast Track | Fast Track | Withdrawn | 11/30/2022 | Withdrawn | Withdrawn | CONTRA COSTA | BRENTWOOD SUB | Solar PV | 3.0602 | 7/21/2021 | 10/4/2021 | Fail Screens: 2, 4, 6, 9, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-07-01 12:52 | 2866-WD | Fast Track | Fast Track | Withdrawn | 11/30/2022 | Withdrawn | Withdrawn | CONTRA COSTA | BRENTWOOD SUB | Solar PV | 2 | 7/21/2021 | 8/26/2021 | Fail Screens: 2, 4, 5, 6, 7, 9, 10 | 10/11/2021 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-07-14 16:16 | 2867-WD | Independent Study | Independent Study | Withdrawn | 10/14/2022 | Withdrawn | Withdrawn | MENDOCINO | CALPELLA SUB | Solar PV, Storage | 2.365 | 7/21/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-07-14 18:09 | 2868-WD | Fast Track | Independent Study | Withdrawn | 2/7/2022 | Withdrawn | Withdrawn | LAKE | CLEAR LAKE SUB | Solar PV | 3 | 7/21/2021 | 8/12/2021 | Fail Screens: 2, 4, 5, 7, 9, 10 | 10/22/2021 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-07-01 11:02 | 2869-WD | Independent Study | Independent Study | Withdrawn | 9/30/2022 | Withdrawn | Withdrawn | MENDOCINO | COVELO SUB | Storage | 7.2 | 7/21/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-07-06 14:33 | 2870-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN LUIS OBISPO | GOLDTREE SUB | Storage | 0.6435 | 7/28/2021 | 9/30/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-07-12 14:14 | 2871-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | HUMBOLDT | HARRIS SUB | Storage | 0.35 | 7/28/2021 | 8/18/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-07-12 14:42 | 2872-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | HUMBOLDT | EUREKA A SUB | Storage | 0.56 | 7/28/2021 | 8/23/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-07-16 11:04 | 2873-WD | Independent Study | Independent Study | Withdrawn | 10/14/2022 | Withdrawn | Withdrawn | SONOMA | PETALUMA C SUB | Solar PV, Storage | 10 | 7/28/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-07-15 11:21 | 2874-WD | Fast Track | Fast Track | Withdrawn | 5/31/2022 | Withdrawn | Withdrawn | BUTTE | WYANDOTTE SUB | Solar PV | 0.50526 | 7/28/2021 | 9/16/2021 | Fail Screens: 2, 4 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-07-15 14:38 | 2875-WD | Fast Track | Fast Track | Withdrawn | 5/31/2022 | Withdrawn | Withdrawn | BUTTE | HONCUT SUB | Solar PV | 0.744 | 7/28/2021 | 9/17/2021 | Fail Screens: 2, 4, 7, 9, 10 | 1/14/2022 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-06-28 22:11 | 2876-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | MERCED | CANAL SUB | Storage | 0.21 | 7/28/2021 | 9/2/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-06-30 23:21 | 2877-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | GOOSE LAKE SUB | Storage | 0.21 | 7/28/2021 | 8/26/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-07-21 09:32 | 2878-WD | Fast Track | Independent Study | Withdrawn | 4/4/2023 | Withdrawn | Withdrawn | NAPA | CALISTOGA SUB | Steam Turbine | 1.1672 | 7/28/2021 | 8/17/2021 | Fail Screens: 2, 4, 7, 9, 10 | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-07-09 17:38 | 2879-WD | Fast Track | Independent Study | Withdrawn | 11/30/2022 | Withdrawn | Withdrawn | HUMBOLDT | JANES CREEK SUB | Solar PV | 1.02 | 7/28/2021 | 9/8/2021 | Fail Screens: 2, 5, 7, 9, 10 | 11/17/2021 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-07-15 08:06 | 2880-WD | Independent Study | Independent Study | Withdrawn | 9/30/2022 | Withdrawn | Withdrawn | NEVADA | GRASS VALLEY SUB | Storage | 13 | 7/28/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-07-01 14:12 | 2881-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | LAS PALMAS SUB | Engine | 1.429 | 8/4/2021 | 10/22/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-06-09 12:42 | 2882-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | BANTA SUB | Solar PV | 1.2 | 8/4/2021 | 10/14/2021 | Fail Screens: G, J, K, L, M, S5 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-07-19 16:21 | 2883-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KINGS | GUERNSEY SUB | Solar PV | 3.95 | 09/16/2021 | N/A | N/A | N/A | N/A | Pass | 2022-02-11 | N/A | Executed | No former queue position
2021-05-26 11:12 | 2884-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | MANTECA SUB | Solar PV | 1.4666 | 8/4/2021 | 9/8/2021 | Fail Screens: D, F, G, J, K, L, M, V1, S5, A1 | 10/25/2021 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-07-19 10:32 | 2885-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | KERN | PANAMA SUB | Solar PV | 1.2401 | 8/4/2021 | 9/14/2021 | Fail | 11/5/2021 | Fail | Pass | 2022-05-06 | N/A | Executed | No former queue position
2021-07-26 09:18 | 2886-WD | Fast Track | Independent Study | Withdrawn | 11/30/2022 | Withdrawn | Withdrawn | BUTTE | OROVILLE SUB | Solar PV | 2 | 8/4/2021 | 8/17/2021 | Fail Screens: 2, 4 | 9/29/2021 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-07-27 12:42 | 2887-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | CONTRA COSTA | SAN PABLO SUB | Storage | 0.21 | 8/11/2021 | 9/8/2021 | Fail Screens: J, M |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-07-14 14:13 | 2888-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | HUMBOLDT | EUREKA A SUB | Storage | 0.42 | 8/11/2021 | 10/8/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-07-23 10:02 | 2889-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | HUMBOLDT | JANES CREEK SUB | Storage | 0.28 | 8/11/2021 | 9/8/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-07-23 13:03 | 2890-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MONTEREY | OIL FIELDS SUB | Storage | 0.9295 | 8/11/2021 | 10/19/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-07-22 15:33 | 2891-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | NEWARK SUB | Solar PV | 1 | 8/11/2021 | 9/9/2021 | Fail Screens: D, M | 10/12/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-07-30 17:52 | 2892-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | SAN LUIS OBISPO | TEMPLETON SUB | Engine | 1.2648 | 8/18/2021 | 9/16/2021 | Fail Screens: B, F, I, J, K, M, S5, A1 | 12/10/2021 | Fail | Pass | 2022-07-19 | N/A | Executed | No former queue position
2021-07-27 09:21 | 2893-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | PLACER | ROCKLIN SUB | Solar PV, Storage | 2.5811 | 8/25/2021 | N/A | N/A | N/A | N/A | Pass | 1/20/2022 | N/A | Executed | No former queue position
2021-08-13 13:06 | 2894-WD | Fast Track | Fast Track | Withdrawn | 11/30/2022 | Withdrawn | Withdrawn | EL DORADO | EL DORADO PH | Storage | 3.6975 | 8/25/2021 | 9/17/2021 | Fail Screens: 2, 4, 10 | 11/8/2021 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-08-13 13:21 | 2895-WD | Fast Track | Fast Track | Withdrawn | 11/30/2022 | Withdrawn | Withdrawn | EL DORADO | EL DORADO PH | Storage | 3.6975 | 8/25/2021 | 9/17/2021 | Fail Screens: 2, 4, 10 | 11/8/2021 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-07-29 12:02 | 2896-RD | Detailed Study | Detailed Study | In Service | Not Provided |  |  | SANTA CLARA | LOCKHEED #1 SUB | Solar PV | 3.8912 | 9/1/2021 | N/A | N/A | N/A | N/A | Pass | 1/11/2022 | N/A | Executed | No former queue position
2021-08-11 12:34 | 2897-RD | Fast Track | Fast Track | Active | Not Provided |  |  | HUMBOLDT | EUREKA A SUB | Storage | 0.35 | 9/1/2021 | 11/15/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-08-04 11:02 | 2898-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | BULLARD SUB | Solar PV | 3.5 | 9/1/2021 | 9/23/2021 | Fail Screens: I, J, K, M, V1, V2, S5, A1 | 11/30/2021 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-08-16 14:04 | 2899-RD | Fast Track | Detailed Study | In Service | Not Provided |  |  | TUOLUMNE | CURTIS SUB | Storage | 0.21 | 9/8/2021 | 10/11/2021 | Fail Screens: J, L, M, S5 | 12/20/2021 | Fail | Pass | 2022-05-19 | N/A | Executed | No former queue position
2021-08-17 14:46 | 2900-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | HUMBOLDT | EUREKA A SUB | Storage | 0.42 | 9/8/2021 | 12/10/2021 | Fail Screens: M | 2022-02-09 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-08-25 12:52 | 2901-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | LERDO SUB | Solar PV | 2.5 | 9/8/2021 | N/A | N/A | N/A | N/A | Pass | 05/26/2022 | N/A | Executed | No former queue position
2021-08-27 15:32 | 2902-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | 7TH STANDARD SUB | Solar PV | 2.5 | 9/8/2021 | N/A | N/A | N/A | N/A | Pass | 07/19/2022 | N/A | Executed | No former queue position
2021-08-09 13:42 | 2903-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | EL DORADO | APPLE HILL SUB | Storage | 0.21 | 9/8/2021 | 9/29/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-08-30 17:10 | 2904-WD | Independent Study | Independent Study | Active | 12/15/2022 |  |  | BUTTE | SYCAMORE CREEK SUB | Solar PV | 3 | 9/8/2021 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 1/3/2022 | 2022-04-01 | Executed | No former queue position
2021-08-31 13:09 | 2905-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | FRESNO | CAMDEN SUB | Solar PV | 1.56 | 10/21/2021 | N/A | N/A | N/A | N/A | Pass | 2022-03-31 | N/A | Executed | No former queue position
2021-08-04 16:24 | 2906-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | Customer Owned | Solar PV | 18.1503 | 9/9/2021 | N/A | N/A | N/A | N/A | Pass | 2024-01-30 |  |  | No former queue position
2021-08-20 10:25 | 2907-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SOLANO | Customer Owned | Storage | 9.0294 | 9/9/2021 | 12/1/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-08-25 12:12 | 2908-WD | Independent Study | Independent Study | Active | 4/1/2024 |  |  | SONOMA | CLOVERDALE SUB | Other | 15 | 9/9/2021 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 2023-10-06 | 2024-01-31 |  | No former queue position
2021-08-25 09:23 | 2909-WD | Independent Study | Independent Study | Active | 12/31/2025 |  |  | LAKE | EAGLE ROCK SUB | Wind | 131.2 | 9/15/2021 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 2023-08-30 | 2024-01-31 |  | No former queue position
2021-08-26 18:21 | 2910-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SUTTER | BARRY SUB | Solar PV | 0.10637 | 9/15/2021 | 10/5/2021 | Fail Screens: L, M, S5 | 11/22/2021 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-09-09 10:14 | 2911-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SONOMA | WINDSOR SUB | Solar PV | 1.2 | 12/10/2021 | 12/31/2021 | Fail Screens: D, F, G, J, K, M, V1, S5, A1 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-09-09 10:38 | 2912-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Engine | 0.06 | 9/22/2021 | 10/5/2021 | Fail Screens: J, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-08-27 15:43 | 2913-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | TEJON SUB | Solar PV | 5 | 9/22/2021 | N/A | N/A | N/A | N/A | Pass | 2022-03-08 | N/A | Executed | No former queue position
2021-09-14 10:46 | 2914-WD | Independent Study | Independent Study | Withdrawn | 11/30/2022 | Withdrawn | Withdrawn | AMADOR | PINE GROVE SUB | Storage | 5.187 | 9/29/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-09-17 11:33 | 2915-WD | Independent Study | Independent Study | Active | 12/30/2022 |  |  | MADERA | CHOWCHILLA SUB | Solar PV | 3 | 9/29/2021 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 2022-02-04 | N/A | Executed | No former queue position
2021-09-09 14:59 | 2916-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | HUMBOLDT | NEWBURG SUB | Storage | 0.63 | 9/29/2021 | 11/16/2021 | Fail | 1/5/2022 | Fail | Pass | 2022-05-26 | N/A | Executed | No former queue position
2021-08-27 15:12 | 2917-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | VINEYARD SUB | Solar PV, Storage | 3.0842 | 10/6/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-09-21 11:45 | 2918-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | FRESNO | CARUTHERS SUB | Solar PV | 1.68 | 10/6/2021 | N/A | N/A | N/A | N/A | Pass | 2022-03-09 | N/A | Executed | No former queue position
2021-09-30 13:28 | 2919-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | SUNOL SUB | Solar PV | 0.05771 | 10/6/2021 | 11/19/2021 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-09-23 08:52 | 2920-WD | Independent Study | Independent Study | Withdrawn | 10/31/2023 | Withdrawn | Withdrawn | FRESNO | HURON SUB | Solar PV | 5 | 10/13/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-09-23 17:31 | 2921-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | HUMBOLDT | JANES CREEK SUB | Storage | 0.42 | 10/13/2021 | 11/16/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-10-01 10:44 | 2922-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | TEJON SUB | Solar PV | 1.25 | 10/13/2021 | N/A | N/A | N/A | N/A | Pass | 2022-07-11 | N/A | Executed | No former queue position
2021-10-01 13:25 | 2923-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | SAN JOAQUIN SUB | Solar PV | 0.98842 | 10/13/2021 | 11/1/2021 | Fail Screens: F, J, K, M, V1, V2, S5, A1 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-10-06 15:12 | 2924-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | LAMONT SUB | Solar PV | 1.2 | 10/13/2021 | N/A | N/A | N/A | N/A | Pass | 2022-02-11 | N/A | Executed | No former queue position
2021-10-07 10:14 | 2925-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | MADERA | DAIRYLAND SUB | Solar PV | 4.9542 | 10/13/2021 | N/A | N/A | N/A | N/A | Pass | 2022-05-11 | N/A | Executed | No former queue position
2021-09-30 18:30 | 2926-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA CLARA | FREMONT SUB | Engine, Solar PV | 0.482 | 10/20/2021 | 2022-02-25 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-10-06 14:32 | 2927-WD | Independent Study | Independent Study | Active | 11/30/2022 |  |  | EL DORADO | APPLE HILL SUB | Storage | 5 | 10/20/2021 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 2022-05-17 | N/A | Executed | No former queue position
2021-09-17 10:47 | 2928-RD | Detailed Study | DGSP | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | GUERNSEY SUB | Solar PV | 2.125 | 10/20/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-10-08 13:52 | 2929-RD | Detailed Study | DGSP | Active | Not Provided |  |  | FRESNO | CARUTHERS SUB | Solar PV | 2 | 10/20/2021 | N/A | N/A | N/A | N/A | Fail | 2022-09-07 | N/A | Executed | No former queue position
2021-10-08 16:07 | 2930-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | MERCED | MERCED SUB | Solar PV | 4.125 | 10/20/2021 | N/A | N/A | N/A | N/A | Pass | 2022-03-11 | N/A | Executed | No former queue position
2021-09-30 09:22 | 2931-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | MERCED | ATWATER SUB | Engine, Solar PV, Storage | 8.1643 | 10/20/2021 | N/A | N/A | N/A | N/A | Pass | 2022-05-24 | N/A | Executed | No former queue position
2021-10-05 17:22 | 2932-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | STANISLAUS | VALLEY HOME SUB | Solar PV | 1.3923 | 10/20/2021 | 11/16/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-10-15 16:20 | 2933-WD | Independent Study | Independent Study | Withdrawn | 5/16/2022 | Withdrawn | Withdrawn | MERCED | WRIGHT SUB | Solar PV | 3 | 10/27/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-10-06 10:11 | 2934-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SONOMA | PENNGROVE SUB | Solar PV, Storage | 6.025 | 10/27/2021 | N/A | N/A | N/A | N/A | Pass | 2022-03-21 | N/A | Executed | No former queue position
2021-10-15 12:44 | 2935-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | GOOSE LAKE SUB | Solar PV | 0.74771 | 10/27/2021 | 12/8/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-10-01 13:17 | 2936-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | CONTRA COSTA | RICHMOND R SUB | Solar PV | 2.34 | 10/27/2021 | N/A | N/A | N/A | N/A | Pass | 2023-09-06 | N/A | Executed | No former queue position
2021-10-06 15:22 | 2937-RD | Fast Track | Detailed Study | In Service | Not Provided |  |  | SAN JOAQUIN | CARBONA SUB | Storage | 0.28 | 11/3/2021 | 11/24/2021 | Fail Screens: L, M | 1/12/2022 | Fail | Pass | 2022-07-13 | N/A | Executed | No former queue position
2021-10-19 12:20 | 2938-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | COLUSA | WILLIAMS SUB | Solar PV | 1.4863 | 11/3/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-10-21 13:42 | 2939-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KINGS | ANGIOLA SUB | Solar PV | 1.92 | 11/3/2021 | N/A | N/A | N/A | N/A | Pass | 2022-06-06 | N/A | Executed | No former queue position
2021-10-18 10:38 | 2940-WD | Independent Study | Independent Study | Withdrawn | 12/1/2023 | Withdrawn | Withdrawn | KERN | GANSO SUB | Solar PV | 3 | 11/3/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-09-26 22:49 | 2941-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | FREMONT SUB | Storage | 0.14065 | 11/3/2021 | 1/5/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-09-17 16:50 | 2942-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SAN JOAQUIN | MANTECA SUB | Solar PV | 1.5 | 11/10/2021 | N/A | N/A | N/A | N/A | Pass | 2022-04-07 | N/A | Executed | No former queue position
2021-10-27 09:05 | 2943-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | ALAMEDA | NEWARK SUB | Solar PV | 0.9875 | 11/10/2021 | 12/20/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-10-12 14:23 | 2944-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | BANTA SUB | Solar PV, Storage | 1.3048 | 11/10/2021 | 12/31/2021 | Fail Screens: G, I, J, K, L, M, S5 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-10-28 11:22 | 2945-WD | Independent Study | Independent Study | Withdrawn | 11/30/2022 | Withdrawn | Withdrawn | KINGS | LOST HILLS SUB | Solar PV, Storage | 10.25 | 11/10/2021 | N/A | N/A (Independent Study) | Withdrawn | Withdrawn | Pass | 2022-10-21 | Withdrawn | Withdrawn | No former queue position
2021-10-15 11:25 | 2946-WD | Fast Track | Fast Track | Withdrawn | 3/15/2023 | Withdrawn | Withdrawn | KINGS | DEVILS DEN SUB | Solar PV | 2.0029 | 11/10/2021 | 12/6/2021 | Fail Screens: 2, 4, 10 | 1/12/2022 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-10-22 10:28 | 2947-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | BUTTE | PARADISE SUB | Storage | 0.49 | 11/10/2021 | 12/20/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-10-22 10:41 | 2948-RD | Fast Track | Fast Track | Active | Not Provided |  |  | BUTTE | PARADISE SUB | Storage | 0.49 | 11/10/2021 | 12/20/2021 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-10-14 09:26 | 2949-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SAN JOAQUIN | EAST STOCKTON SUB | Solar PV, Storage | 2.08 | 11/17/2021 | N/A | N/A | N/A | N/A | Pass | 2022-05-25 | N/A | Executed | No former queue position
2021-10-19 12:57 | 2950-RD | Fast Track | DGSP | Active | Not Provided |  |  | MERCED | ATWATER SUB | Solar PV | 0.78237 | 11/17/2021 | 12/16/2021 | Fail Screens: M, S5 | 2022-02-15 | Fail | Fail | 2023-02-08 | N/A | Executed | No former queue position
2021-11-05 15:23 | 2951-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN JOAQUIN | STOCKTON A SUB | Solar PV | 1.1 | 11/24/2021 | 1/11/2022 | Fail Screens: D, G, J, K, M, V1, S5, A1 | 2022-02-28 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-10-13 01:24 | 2952-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | CONTRA COSTA | SAN RAMON SUB | Storage | 0.9295 | 11/24/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-10-14 23:38 | 2953-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | SANTA NELLA SUB | Storage | 0.858 | 11/24/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-11-09 18:06 | 2954-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | SAN LEANDRO U SUB | Solar PV | 1.25 | 12/1/2021 | 2022-02-09 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-11-10 13:16 | 2955-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CLARA | LLAGAS SUB | Solar PV, Storage | 2.026 | 12/1/2021 | 1/14/2022 | Fail Screens: D, I, J, K, M, S5 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-11-04 11:59 | 2956-RD | Detailed Study | DGSP | Active | Not Provided |  |  | KINGS | GUERNSEY SUB | Solar PV | 3.625 | 12/1/2021 | N/A | N/A | N/A | N/A | Fail | 2022-09-01 | N/A | Executed | No former queue position
2021-11-10 11:52 | 2957-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | SAN LEANDRO U SUB | Solar PV, Storage | 2.6311 | 12/1/2021 | 2022-06-13 | Fail Screens: D, G, I, J, K, L, M, M1, V1, S5. A1, J, K, M | 2022-08-08 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-11-15 10:10 | 2958-WD | Independent Study | Independent Study | Active | 11/30/2022 |  |  | EL DORADO | EL DORADO PH | Storage | 5.187 | 12/1/2021 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 2022-07-06 | N/A | Tendered | No former queue position
2021-11-23 19:03 | 2959-WD | Independent Study | Independent Study | Withdrawn | 3/15/2023 | Withdrawn | Withdrawn | KINGS | TULARE LAKE SUB | Solar PV | 3 | 12/8/2021 | N/A | N/A (Independent Study) | Withdrawn | Withdrawn | Pass | 2022-07-21 | Withdrawn | Withdrawn | No former queue position
2021-11-17 05:27 | 2960-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | BANTA SUB | Solar PV | 1.2 | 12/8/2021 | 12/29/2021 | Fail Screens: G, J, K, L, M, S5 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-11-18 15:51 | 2961-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | SCHINDLER SUB | Solar PV | 1.9072 | 12/8/2021 | 12/27/2021 | Fail Screens: F, J, K, M, S5 | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-11-10 10:57 | 2962-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MONTEREY | SPENCE SUB | Solar PV, Storage | 2.6615 | 12/8/2021 | 1/27/2022 | Fail Screens: F, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-11-10 10:59 | 2963-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MONTEREY | SPENCE SUB | Solar PV, Storage | 2.1615 | 12/8/2021 | 2022-02-15 | Fail Screens: D, F, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-11-21 08:22 | 2964-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | GANSO SUB | Storage | 0.858 | 12/8/2021 | 2022-06-15 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-11-29 12:02 | 2965-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | ASHLAN AVE SUB | Solar PV | 0.01656 | 12/15/2021 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-11-04 13:30 | 2966-WD | Fast Track | Independent Study | Withdrawn | 3/30/2023 | Withdrawn | Withdrawn | CONTRA COSTA | KIRKER SUB | Solar PV | 3.6501 | 12/15/2021 | 1/19/2022 | Fail Screens: 2, 4, 6, 7, 9, 10 | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-11-12 12:21 | 2967-WD | Independent Study | Independent Study | Active | 3/30/2023 |  |  | SOLANO | GRAND ISLAND SUB | Solar PV | 2.7306 | 12/15/2021 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 2022-05-10 | N/A | Executed | No former queue position
2021-10-12 11:53 | 2968-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA CRUZ | CAMP EVERS SUB | Storage | 0.98 | 12/15/2021 | 1/27/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-10-19 01:56 | 2969-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | NEWARK SUB | Solar PV, Storage | 1.7989 | 12/15/2021 | 2022-04-07 | Fail | 2022-05-23 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-10-21 14:01 | 2970-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | FRESNO | BARTON SUB | Solar PV, Storage | 1.329 | 12/15/2021 | N/A | N/A | N/A | N/A | Pass | 2022-07-12 | N/A | Executed | No former queue position
2021-10-26 15:28 | 2971-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | FRESNO | BARTON SUB | Solar PV, Storage | 3.218 | 12/15/2021 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2021-12-01 11:02 | 2972-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN LUIS OBISPO | SAN LUIS OBISPO SUB | Engine, Storage | 1.53 | 12/15/2021 | 1/27/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-12-11 12:30 | 2973-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CLARA | SARATOGA SUB | Solar PV | 0.03465 | 12/15/2021 | 2022-02-08 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-11-23 16:51 | 2974-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | FRUITVALE SUB | Solar PV | 1.2462 | 12/15/2021 | 1/19/2022 | Fail Screens: D, G, I, J, V1, V2, S5, A1 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-11-29 15:05 | 2975-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | KERN OIL SUB | Solar PV | 0.99694 | 12/15/2021 | 1/14/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-12-06 15:53 | 2976-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | FRESNO | SAN JOAQUIN SUB | Solar PV | 0.9 | 12/22/2021 | N/A | N/A | N/A | N/A | Pass | 07/27/2022 | N/A | Executed | No former queue position
2021-12-09 13:02 | 2977-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | FRESNO | RANCHERS COTTON SUB | Solar PV | 1.5 | 02/24/2022 | 2022-03-11 | Fail Screens: F, J, K, M, V1, S5, A1 | 2022-04-26 | Fail | Pass | 2022-09-09 | N/A | Executed | No former queue position
2021-12-07 15:41 | 2978-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA CRUZ | PAUL SWEET SUB | Fuel Cell, Other, Solar PV | 0.39096 | 12/22/2021 | 2022-03-15 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-11-30 12:59 | 2979-WD | Independent Study | Independent Study | Withdrawn | 3/15/2023 | Withdrawn | Withdrawn | BUTTE | BANGOR SUB | Solar PV | 3 | 12/22/2021 | N/A | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-11-04 11:12 | 2980-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SAN MATEO | MILLBRAE SUB | Solar PV, Storage | 3.7248 | 12/29/2021 | N/A | N/A | N/A | N/A | Pass | 2022-06-16 | N/A | Executed | No former queue position
2021-12-02 14:48 | 2981-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | EL DORADO | SHINGLE SPRINGS SUB | Storage | 0.6435 | 12/29/2021 | 1/19/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-12-22 13:56 | 2982-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | NEWARK SUB | Solar PV | 0.1332 | 12/29/2021 | 2022-03-14 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-12-08 11:13 | 2983-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | FRESNO | WAHTOKE SUB | Engine, Solar PV, Storage | 2.7445 | 12/29/2021 | N/A | N/A | N/A | N/A | Pass | 2022-05-02 | N/A | Executed | No former queue position
2021-12-16 14:31 | 2984-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | BUTTE | WYANDOTTE SUB | Solar PV | 3.6916 | 12/29/2021 | N/A | N/A | N/A | N/A | Pass | 2022-05-20 | N/A | Executed | No former queue position
2021-12-16 05:58 | 2985-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | TEHAMA | VINA SUB | Solar PV | 1.1455 | 1/5/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-12-16 19:07 | 2986-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | TEHAMA | VINA SUB | Solar PV | 1.6546 | 1/5/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-12-10 15:44 | 2987-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | MONTEREY | LOS COCHES SUB | Wind | 2.8 | 1/5/2022 | N/A | N/A | N/A | N/A | Pass | 2022-11-07 |  |  | No former queue position
2021-12-30 14:24 | 2988-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | FRESNO | PANOCHE SUB | Solar PV | 0.75 | 1/12/2022 | 2022-03-03 | Fail Screens: D, F, G, J, K, L, M, M1, A1 | 2022-03-29 | Fail | Pass | 09/13/2022 | N/A | Executed | No former queue position
2021-12-30 14:36 | 2989-RD | Fast Track | DGSP | Active | Not Provided |  |  | FRESNO | PANOCHE SUB | Solar PV | 0.75 | 1/12/2022 | 2022-03-03 | Fail Screens: D, F, G, J, K, L, M, M1, S5 | 2022-03-29 | Fail | Fail | 2023-02-02 | N/A | Executed | No former queue position
2021-12-18 15:10 | 2990-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SANTA CLARA | EDENVALE SUB | Solar PV, Storage | 2.724 | 1/12/2022 | N/A | N/A | N/A | N/A | Pass | 2022-05-23 | N/A | Executed | No former queue position
2021-12-23 10:47 | 2991-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CLARA | LLAGAS SUB | Solar PV | 1.325 | 1/12/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-12-31 13:58 | 2992-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | CONTRA COSTA | LAKEWOOD SUB | Solar PV | 0.18519 | 1/12/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-12-13 16:08 | 2993-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SOLANO | CORDELIA SUB | Engine | 1.2 | 1/12/2022 | 2022-04-18 | Fail Screens: B, F, G, I, J, K, M, S5, A1 | 2022-12-27 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2021-12-22 21:50 | 2994-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SAN JOAQUIN | VIERRA SUB | Solar PV, Storage | 2.5391 | 03/01/2022 | N/A | N/A | N/A | N/A | Pass | 2022-08-02 | N/A | Executed | No former queue position
2022-01-06 11:18 | 2995-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | KERN | CELERON HILL SUB | Solar PV | 1.494 | 1/19/2022 | 2022-02-09 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-01-07 17:41 | 2996-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | SAN JOAQUIN | TRACY SUB | Solar PV | 1.92 | 1/19/2022 | 2022-02-25 | Fail Screens: D, F, G, J, K, L, M, M1, S5 | 2022-03-28 | Fail | Pass | 2022-07-07 | N/A | Executed | No former queue position
2021-12-02 10:19 | 2997-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | Customer Owned | Solar PV | 28.65 | 1/19/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-11-21 08:29 | 2998-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | TEJON SUB | Storage | 0.9295 | 1/19/2022 | 2022-05-10 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-11-22 08:32 | 2999-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | TEJON SUB | Storage | 0.9295 | 1/19/2022 | 2022-05-10 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-12-13 13:44 | 3000-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | MT EDEN SUB | Solar PV, Storage | 3.125 | 1/19/2022 | 2022-05-25 | Fail Screens: D, G, I, J, K, L, M, M1, V1, V2, S5, A1 | 2022-07-27 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-01-04 07:02 | 3001-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA BARBARA | PURISIMA SUB | Micro Turbine | 4.56 | 1/19/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-12-18 14:24 | 3002-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SANTA CLARA | TRIMBLE SUB | Solar PV, Storage | 2.5255 | 1/26/2022 | N/A | N/A | N/A | N/A | Pass | 2022-05-17 | N/A | Executed | No former queue position
2022-01-14 08:18 | 3003-WD | Independent Study | Independent Study | Active | 12/31/2023 |  |  | MERCED | ORO LOMA SUB | Solar PV | 2.5998 | 1/26/2022 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 2022-06-08 | N/A | Tendered | No former queue position
2021-12-22 16:28 | 3004-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | TRANSMISSION | Solar PV | 317.4142 | 1/26/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-12-29 13:01 | 3005-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CLARA | RIVER OAKS SUB | Solar PV, Storage | 1.3875 | 1/26/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-12-31 14:19 | 3006-RD | Fast Track | Fast Track | Active | Not Provided |  |  | NAPA | SILVERADO SUB | Solar PV | 0.94118 | 2/2/2022 | 6/13/2022 | Fail Screens: D, M | 7/22/2022 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-01-12 15:58 | 3007-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | SAN BENITO | SAN BENITO SUB | Engine, Fuel Cell, Solar PV | 9.58 | 2/2/2022 | 4/6/2022 | Fail Screens: I, J, K, M, S5 | 5/20/2022 | Fail | Pass | 10/6/2022 | N/A | Executed | No former queue position
2022-01-14 16:02 | 3008-RD | Detailed Study | Detailed Study | Withdrawn | 1/2/2023 | Withdrawn | Withdrawn | KINGS | GUERNSEY SUB | Engine | 2.852 | 2/9/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-01-21 11:53 | 3009-WD | Fast Track | Fast Track | Withdrawn | 12/30/2023 | Withdrawn | Withdrawn | KERN | ALPAUGH SUB | Solar PV | 3 | 2/9/2022 | 3/1/2022 | Fail Screens: 2, 7, 9, 10 | 5/12/2022 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-01-21 12:11 | 3010-WD | Fast Track | Fast Track | Withdrawn | 12/30/2023 | Withdrawn | Withdrawn | KERN | ALPAUGH SUB | Solar PV | 3 | 2/9/2022 | 3/1/2022 | Fail Screens: 2, 4, 7, 9, 10 | 5/12/2022 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-01-21 12:28 | 3011-WD | Fast Track | Fast Track | Withdrawn | 12/30/2023 | Withdrawn | Withdrawn | KERN | ALPAUGH SUB | Solar PV | 3 | 2/9/2022 | 3/1/2022 | Fail Screens: 2, 4, 7, 9, 10 | 5/12/2022 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-01-21 16:59 | 3012-RD | Detailed Study | DGSP | Active | Not Provided |  |  | ALAMEDA | VINEYARD SUB | Solar PV, Storage | 2.7287 | 2/9/2022 | N/A | N/A | N/A | N/A | Fail | 2022-08-17 | N/A | Executed | No former queue position
2022-01-25 10:47 | 3013-RD | Fast Track | DGSP | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | LAMMERS SUB | Solar PV | 1.875 | 2/9/2022 | 3/4/2022 | Fail Screens: D, F, J, K, L, M, S5 | 4/21/2022 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-01-25 10:53 | 3014-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | LAMMERS SUB | Solar PV | 1.875 | 2/9/2022 | 3/4/2022 | Fail Screens: D, F, J, K, L, M, S5 | 4/21/2022 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-01-26 10:37 | 3015-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | SMYRNA SUB | Solar PV | 3.125 | 03/02/2022 | N/A | N/A | N/A | N/A | Pass | 6/21/2022 | N/A | Executed | No former queue position
2022-01-25 08:26 | 3016-WD | Independent Study | Independent Study | Withdrawn | 12/29/2023 | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV | 4.25 | 2/9/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-01-27 10:21 | 3017-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | MENDOTA SUB | Solar PV | 1.5 | 2/9/2022 | 4/18/2022 | Pass | 5/19/2022 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-01-28 15:11 | 3018-WD | Independent Study | Independent Study | Withdrawn | 6/15/2023 | Withdrawn | Withdrawn | FRESNO | ORO LOMA SUB | Solar PV | 5 | 2/9/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-01-17 18:58 | 3019-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | FRESNO | MCCALL SUB | Solar PV | 5.76 | 2/9/2022 | N/A | N/A | N/A | N/A | Pass | 8/31/2022 | N/A | Executed | No former queue position
2022-01-10 15:41 | 3020-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SAN JOAQUIN | WEBER SUB | Solar PV, Storage | 1.6522 | 2/16/2022 | 4/13/2022 | Fail Screens: F, J, K, M | N/A | N/A | Pass | 9/12/2022 |  |  | No former queue position
2022-01-14 15:00 | 3021-RD | Detailed Study | DGSP | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | BANTA SUB | Solar PV, Storage | 1.9918 | 2/16/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-01-25 08:31 | 3022-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA BARBARA | Withdrawn | Solar PV | 0.05 | 2/16/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-01-27 23:37 | 3023-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | SONOMA | SONOMA A SUB | Solar PV | 1.577 | 2/16/2022 | 6/22/2022 | Fail Screens: B, J, M, S5 | 8/18/2022 | Fail | Pass | 6/5/2023 | N/A | Executed | No former queue position
2022-01-19 11:46 | 3024-RD | Detailed Study | DGSP | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV | 7.431 | 2/16/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-12-10 13:31 | 3025-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CRUZ | GREEN VALLEY SUB | Solar PV | 0.995 | 2/16/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2021-12-13 09:37 | 3026-RD | Detailed Study | Detailed Study | Active | 6/1/2023 |  |  | CONTRA COSTA | BRENTWOOD SUB | Solar PV | 5 | 2/16/2022 | N/A | N/A | N/A | N/A | Pass | 4/13/2023 |  |  | No former queue position
2022-01-21 12:40 | 3027-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | TULARE | DINUBA SUB | Solar PV | 1.625 | 2/16/2022 | 6/16/2022 | Fail Screens: B, F, I, J, K, M, S5 | 8/18/2022 | Fail | Pass | 4/20/2023 | N/A | Tendered | No former queue position
2021-12-22 11:09 | 3028-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | TRANSMISSION | Solar PV | 2.241 | 2/23/2022 | 4/4/2022 | Fail | 5/26/2022 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-01-12 13:19 | 3029-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | LAS POSITAS SUB | Solar PV | 1.4 | 2/23/2022 | 5/25/2022 | Fail Screens: D, F, H, I, J, K, L, M, V1, V2, S5 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-01-14 15:40 | 3030-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | ALAMEDA | Transmission Customer | Solar PV | 9.533 | 2/23/2022 | N/A | N/A | N/A | N/A | Pass | 2023-10-26 | N/A | Executed | No former queue position
2022-01-19 13:24 | 3031-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SONOMA | SONOMA A SUB | Solar PV | 0.13 | 2/23/2022 | 5/4/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2022-01-28 09:11 | 3032-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SANTA BARBARA | PALMER SUB | Solar PV | 5 | 2/23/2022 | N/A | N/A | N/A | N/A | Pass | 12/2/2022 | N/A | Executed | No former queue position
2022-02-03 11:26 | 3033-WD | Fast Track | Fast Track | Withdrawn | 5/1/2022 | Withdrawn | Withdrawn | SAN JOAQUIN | MANTECA SUB | Inverter | 2.5 | 2/23/2022 | 3/23/2022 | Fail Screens: 2, 9 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-02-10 09:37 | 3034-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN MATEO | MENLO SUB | Solar PV | 0.928 | 2/23/2022 | 7/7/2022 | Fail Screens: F, I, J, M, V1 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2022-01-27 16:50 | 3035-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | TRANSMISSION | Solar PV | 4.14 | 3/2/2022 | N/A | N/A | N/A | N/A | Pass | 6/30/2022 | N/A | Executed | No former queue position
2022-01-28 17:07 | 3036-RD | Fast Track | Fast Track | Active | Not Provided |  |  | YOLO | WOODLAND SUB | Solar PV | 1.542 | 3/2/2022 | 7/11/2022 | Fail Screens: I, J, K, M, S5, A1 | 9/8/2022 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-02-16 15:33 | 3037-WD | Independent Study | Independent Study | Active | 12/30/2022 | 1/31/2024 |  | MADERA | CHOWCHILLA SUB | Solar PV | 5 | 3/2/2022 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 10/28/2022 | N/A | Executed | No former queue position
2022-02-15 11:16 | 3038-WD | Fast Track | Fast Track | Withdrawn | 12/30/2023 | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV | 3 | 3/2/2022 | 3/22/2022 | Fail Screens: 2, 4, 10 | 6/16/2022 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-02-16 07:22 | 3039-WD | Fast Track | Fast Track | Withdrawn | 12/30/2023 | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV | 3 | 3/2/2022 | 3/22/2022 | Fail Screens: 2, 10 | 6/16/2022 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-02-25 12:18 | 3040-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | OAKLAND C (OAKLAND PP) SUB | Solar PV | 43.2 | 3/2/2022 | 4/19/2022 | Fail Screens: A | 5/17/2022 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-02-10 10:59 | 3041-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | NEVADA | BRUNSWICK SUB | Solar PV | 0.42 | 3/2/2022 | 4/7/2022 | Pass | N/A | N/A | N/A |  | N/A | Executed | No former queue position
2022-02-18 17:54 | 3042-WD | Independent Study | Independent Study | Active | 4/28/2023 |  |  | MERCED | WRIGHT SUB | Solar PV | 5 | 3/2/2022 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 6/28/2022 | N/A | Executed | No former queue position
2022-01-24 15:51 | 3043-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SAN JOAQUIN | TRANSMISSION | Solar PV | 3.075 | 3/9/2022 | N/A | N/A | N/A | N/A | Pass | 8/24/2022 | N/A | Executed | No former queue position
2022-03-02 12:22 | 3044-RD | Fast Track | DGSP | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | GUERNSEY SUB | Solar PV | 1.476 | 3/16/2022 | 4/4/2022 | Fail Screens: F, J, K, M, V1, S5, A1 | 5/24/2022 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-02-16 12:08 | 3045-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | OAKLAND J SUB | Solar PV | 2.254 | 3/16/2022 | 6/13/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-02-08 14:28 | 3046-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SAN MATEO | MILLBRAE SUB | Solar PV | 2.431 | 3/16/2022 | N/A | N/A | N/A | N/A | Pass | 10/31/2022 | N/A | Executed | No former queue position
2022-03-07 17:30 | 3047-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MENDOCINO | LAYTONVILLE SUB | Solar PV | 4.95 | 3/16/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-02-08 08:43 | 3048-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA BARBARA | ZACA SUB | Solar PV | 1.5 | 3/16/2022 | 6/10/2022 | Fail Screens: D, F, I, J, K, M | 8/11/2022 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-02-01 11:43 | 3049-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KINGS | TULARE LAKE SUB | Solar PV | 0.929 | 3/23/2022 | 4/29/2022 | Fail Screens: J, K, M, S5 | 7/15/2022 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-02-23 11:39 | 3050-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | LERDO SUB | Solar PV+Synchronous | 38 | 3/23/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-03-03 15:21 | 3051-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SONOMA | CLOVERDALE SUB | Solar PV | 0.065 | 3/23/2022 | 8/5/2022 | Fail Screens: V1, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-03-03 15:25 | 3052-RD | Fast Track | Fast Track | Active | Not Provided |  |  | MENDOCINO | WILLITS A SUB | Solar PV | 0.065 | 3/23/2022 | 5/18/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-03-03 15:34 | 3053-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SONOMA | RINCON SUB | Solar PV | 0.13 | 3/23/2022 | 8/12/2022 | Fail Screens: I, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-03-04 11:38 | 3054-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SONOMA | BELLEVUE SUB | Solar PV | 1.92 | 3/23/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-02-11 07:58 | 3055-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | SAN LEANDRO U SUB | Solar PV | 1.904 | 3/23/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-03-10 13:09 | 3056-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | MARICOPA SUB | Solar PV | 2 | 3/23/2022 | 4/21/2022 | Fail Screens: 2, 4, 10 | 6/28/2022 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-03-10 16:12 | 3057-WD | Fast Track | DGSP | Active | Not Provided | 10/22/2024 |  | FRESNO | PANOCHE SUB | Solar PV | 0.25 | 3/23/2022 | 4/12/2022 | Fail | 5/24/2022 | Fail | Fail | 2023-01-05 | N/A | Executed | No former queue position
2022-02-23 11:36 | 3058-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN MATEO | BAY MEADOWS SUB | Solar PV+Synchronous | 0.035 | 3/23/2022 | 4/13/2022 | Fail Screens: I, J |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-03-04 10:53 | 3059-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN LUIS OBISPO | Transmission-Customer Owned | Solar PV | 0.363 | 3/30/2022 | 5/23/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-03-04 12:24 | 3060-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN LUIS OBISPO | Transmission-Customer Owned | Solar PV | 0.233 | 3/30/2022 | 7/27/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-01-24 16:56 | 3061-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | SHAFTER SUB | Solar PV | 2.495 | 3/30/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-02-23 16:26 | 3062-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN MATEO | BELMONT SUB | Solar PV | 1.23 | 3/30/2022 | 4/21/2022 | Fail Screens: I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-02-08 10:57 | 3063-WD | Fast Track | Fast Track | In Service | 7/1/2022 | 2/12/2024 | 2/17/2023 | ALAMEDA | SOLANO SUB | Solar PV | 0.071 | 3/30/2022 | 6/3/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-02-08 15:58 | 3064-WD | Fast Track | Fast Track | In Service | 7/7/2022 | 10/15/2023 | 12/1/2022 | SAN FRANCISCO | SAN FRAN P(HUNTERS POINT) SUB | Solar PV | 0.062 | 3/30/2022 | 4/19/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-02-17 15:41 | 3065-RD | Detailed Study | DGSP | Active | Not Provided |  |  | SANTA CLARA | MOUNTAIN VIEW SUB | Solar PV | 1.02 | 3/30/2022 | N/A | N/A | N/A | N/A | Pass | 2023-06-28 |  |  | No former queue position
2022-02-18 12:12 | 3066-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CRUZ | GREEN VALLEY SUB | Solar PV | 1 | 3/30/2022 | 5/20/2022 | Fail Screens: J, K, M, S5 | 8/25/2022 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-03-03 15:45 | 3067-RD | Detailed Study | DGSP | Active | Not Provided |  |  | SAN JOAQUIN | BANTA SUB | Solar PV | 1.2 | 3/30/2022 | N/A | N/A | N/A | N/A | Fail | 2023-03-06 | N/A | Executed | No former queue position
2022-03-09 06:40 | 3068-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | CONTRA COSTA | FRANKLIN SUB | Solar PV | 1.5 | 05/13/2022 | 6/1/2022 | Fail Screens: D, F, G, H, J, K, M, V1, V2, S5, A1 | 8/26/2022 | Fail | Pass | 4/17/2023 | N/A | Tendered | No former queue position
2022-03-17 12:23 | 3069-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | TAFT SUB | Solar PV | 2 | 4/6/2022 | 5/3/2022 | Fail Screens: 2, 10 | 6/17/2022 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-03-18 14:09 | 3070-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SONOMA | LAKEVILLE SUB | Solar PV | 4 | 05/24/2022 | N/A | N/A | N/A | N/A | Pass | 9/20/2022 | N/A | Executed | No former queue position
2022-02-24 12:04 | 3071-RD | Fast Track | Detailed Study | In Service | Not Provided |  |  | YOLO | DAVIS SUB | Solar PV | 1.43 | 4/6/2022 | 4/25/2022 | Fail Screens: J, K, M, S5 | 6/6/2022 | Fail | Pass | 11/2/2022 | N/A | Executed | No former queue position
2022-03-21 17:34 | 3072-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | LERDO SUB | Solar PV | 3.36 | 4/6/2022 | 04/28/2022 | Fail Screens: F, J, K, M, V1, V2, S5, A1 | 6/7/2022 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-02-16 11:48 | 3073-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | PANAMA SUB | Solar PV | 0.93 | 4/6/2022 | 5/18/2022 | Fail Screens: D, F, G, H, I, J, V1, S5, A1 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-03-17 15:14 | 3074-WD | Independent Study | Independent Study | Active | Not Provided |  |  | KERN | TAFT SUB | Solar PV | 6.81 | 4/13/2022 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 9/1/2022 | N/A | Executed | No former queue position
2022-02-11 11:47 | 3075-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | FRESNO | MALAGA SUB | Solar PV | 2.088 | 4/13/2022 | N/A | N/A | N/A | N/A | Pass | 9/14/2022 | N/A | Executed | No former queue position
2022-03-07 17:37 | 3076-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | LOST HILLS SUB | Solar PV | 2.875 | 4/13/2022 | 6/9/2022 | Fail Screens: D, F, G, J, K, M, V1, V2, S5, A1 | 9/26/2022 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-03-23 07:59 | 3077-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SONOMA | SONOMA A SUB | Solar PV | 8.146 | 4/13/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-03-04 13:51 | 3078-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | FRESNO | LAS PALMAS SUB | Solar PV | 9.247 | 4/13/2022 | N/A | N/A | N/A | N/A | Pass | 2/8/2023 | N/A | Executed | No former queue position
2022-03-07 06:56 | 3079-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN MATEO | SAN FRAN H (MARTIN) SUB | Solar PV | 0.937 | 4/20/2022 | 8/25/2022 | Fail Screens: D, F, I, J, K, M |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-03-14 17:28 | 3080-RD | Fast Track | Fast Track | Active | Not Provided |  |  | YOLO | UC DAVIS MTR STA | Solar PV | 14.35 | 4/20/2022 | 5/27/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-03-04 07:35 | 3081-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | TRANSMISSION | Solar PV | 1.375 | 4/27/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-03-14 12:45 | 3082-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | MAGUNDEN SUB | Solar PV | 1.98 | 4/27/2022 | 5/18/2022 | Fail Screens: D, F, J, K, M, V1, S5, A1 | 8/26/2022 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-03-30 14:39 | 3083-RD | Fast Track | Fast Track | Active | Not Provided |  |  | EL DORADO | PLACERVILLE SUB | Solar PV | 0.93 | 4/27/2022 | 6/9/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-03-29 11:43 | 3084-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SOLANO | GRAND ISLAND SUB | Solar PV | 1.25 | 4/27/2022 | 5/25/2022 | Fail Screens: 2, 4, 5, 6, 7, 9, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-04-17 18:40 | 3085-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | TULARE LAKE SUB | Solar PV | 2 | 4/27/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-04-21 16:38 | 3086-WD | Independent Study | Independent Study | Active | Not Provided | 9/30/2024 |  | MENDOCINO | CALPELLA SUB | Solar PV | 4 | 5/4/2022 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 10/28/2022 | N/A | Executed | No former queue position
2022-03-10 14:11 | 3087-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | MENDOCINO | HOPLAND SUB | Solar PV | 0.72 | 5/4/2022 | 7/12/2022 | Fail Screens: F, I, M, S5 | 9/30/2022 | Fail | Pass | 2/2/2023 | N/A | Executed | No former queue position
2022-04-06 15:39 | 3088-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | SAN RAMON SUB | Solar PV | 0.923 | 5/4/2022 | 7/29/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-04-29 10:10 | 3089-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | KERN OIL SUB | Solar PV | 4.4 | 5/4/2022 | 5/31/2022 | Fail Screens: B, D, F, G, I, J, K, L, M, V1, V2, S5, A1 | 7/15/2022 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-02-16 06:06 | 3090-RD | Detailed Study | Detailed Study | Active | 6/24/2022 |  |  | MADERA | BORDEN SUB | Solar PV | 4.026 | 5/11/2022 | N/A | N/A | N/A | N/A | Pass | 11/1/2022 | N/A | Executed | No former queue position
2022-04-19 23:03 | 3091-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | COALINGA #2 SUB | Solar PV | 0.929 | 5/11/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-04-19 23:07 | 3092-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | COALINGA #2 SUB | Solar PV | 0.929 | 5/11/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-05-06 18:33 | 3093-RD | Fast Track | Fast Track | Active | Not Provided |  |  | NEVADA | BRUNSWICK SUB | Solar PV | 0.21 | 5/18/2022 | 7/12/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-04-01 09:39 | 3094-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN JOAQUIN | VIERRA SUB | Solar PV | 0.146 | 5/18/2022 | 6/6/2022 | Fail Screens: D, F, G, I, J, L, M, V1, S5, A1 | 7/12/2022 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-05-04 11:55 | 3095-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN JOAQUIN | MOSHER SUB | Solar PV | 0.996 | 5/18/2022 | 6/9/2022 | Fail Screens: H, J, K, L, M, S5 | 7/20/2022 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-04-01 08:51 | 3096-RD | Detailed Study | Fast Track | Active | Not Provided |  |  | YOLO | PUTAH CREEK SUB | Solar PV | 4.375 | 5/25/2022 | N/A | N/A | N/A | N/A | Pass | 2023-02-28 | N/A | Executed | No former queue position
2022-04-21 18:27 | 3097-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | MALAGA SUB | Solar PV | 2.75 | 5/25/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-05-13 12:19 | 3098-WD | Independent Study | Independent Study | Active | Not Provided | 6/30/2025 |  | SAN JOAQUIN | RIPON SUB | Solar PV | 2.631 | 5/25/2022 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 10/18/2022 | N/A | Executed | No former queue position
2022-04-24 11:14 | 3099-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | SAN RAMON SUB | Solar PV | 0.125 | 5/25/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-05-09 15:02 | 3100-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | BUTTE | BUTTE SUB | Solar PV | 0.672 | 5/25/2022 | 6/15/2022 | Fail Screens: F, G, I, J, K, M, S5, A1 | 9/15/2022 | Fail | Pass | 3/23/2023 | N/A | Executed | No former queue position
2022-05-11 19:15 | 3101-RD | Fast Track | Fast Track | Active | Not Provided |  |  | MARIN | SAN RAFAEL SUB | Solar PV | 0.787 | 5/25/2022 | 6/24/2022 | Fail Screens: I, J, K, L, M, S5 | 7/28/2022 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-05-12 10:19 | 3102-WD | Fast Track | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | COPUS SUB | Solar PV | 15.25 | 5/25/2022 | 6/22/2022 | Pass | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-05-12 15:06 | 3103-WD | Fast Track | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | SMYRNA SUB | Solar PV | 13.125 | 5/25/2022 | 6/23/2022 | Fail Screens: 2, 4, 5, 7, 9, 10 | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-05-17 02:16 | 3104-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SANTA CRUZ | GREEN VALLEY SUB | Solar PV | 0.21 | 6/1/2022 | 7/27/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-05-11 03:05 | 3105-RD | Fast Track | Fast Track | Active | Not Provided |  |  | COLUSA | MAXWELL SUB | Solar PV | 0.2 | 6/8/2022 | 7/5/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-05-23 13:45 | 3106-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | SONOMA | WINDSOR SUB | Solar PV | 2.054 | 6/8/2022 | 8/10/2022 | Fail Screens: F, G, M, S5 | 9/28/2022 | Fail | Pass | 3/1/2023 | N/A | Executed | No former queue position
2022-05-09 12:33 | 3107-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MONTEREY | WATSONVILLE SUB | Solar PV | 2.2 | 6/8/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-05-10 15:33 | 3108-RD | Fast Track | Fast Track | Active | Not Provided |  |  | MARIN | SAN RAFAEL SUB | Solar PV | 1 | 6/8/2022 | 9/13/2022 | Fail Screens: F | 12/12/2022 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-05-20 15:18 | 3109-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | TEHAMA | RED BLUFF SUB | Solar PV | 0.75 | 6/8/2022 | 6/29/2022 | Fail Screens: 2, 4, 5, 7, 9, 10 | 9/30/2022 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-05-26 16:12 | 3110-RD | Detailed Study | DGSP | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | GUERNSEY SUB | Machine-Synchronous | 3.75 | 6/15/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-06-06 00:19 | 3111-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | FRUITVALE SUB | Solar PV | 0.991 | 6/15/2022 | 7/8/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-06-02 17:08 | 3112-WD | DGSP | DGSP | Active | Not Provided |  |  | KERN | LAMONT SUB | Solar PV,Cogeneration | 1.404 | 6/22/2022 | N/A | N/A | N/A | N/A | Fail | 2023-02-16 | N/A | Executed | No former queue position
2022-06-08 10:58 | 3113-WD | Fast Track | Independent Study | Active | Not Provided |  |  | MONTEREY | OIL FIELDS SUB | Solar PV | 3 | 6/22/2022 | 8/1/2022 | Fail Screens: 2, 4, 10 | 9/29/2022 | Fail | Pass | 5/26/2023 | N/A | Executed | No former queue position
2022-06-10 12:19 | 3114-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | MADERA | WOODWARD SUB | Solar PV | 0.572 | 6/22/2022 | 9/7/2022 | Fail Screens: F, J, K, M, V1, V2, S5, A1 | 10/25/2022 | Fail | Pass | 4/10/2023 | N/A | Executed | No former queue position
2022-05-30 22:30 | 3115-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA CLARA | MONTAGUE SUB | Solar PV | 0.21 | 6/29/2022 | 8/3/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2022-05-30 23:14 | 3116-RD | Fast Track | Fast Track | Active | Not Provided |  |  | CONTRA COSTA | RICHMOND R SUB | Solar PV | 0.21 | 6/29/2022 | 10/5/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-06-14 14:55 | 3117-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CLARA | MILPITAS SUB | Solar PV | 0.25 | 6/29/2022 | 7/20/2022 | Fail Screens: 2, 4, 10 | 9/23/2022 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-06-13 17:35 | 3118-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | LAS POSITAS SUB | Solar PV | 1.3 | 6/29/2022 | 8/5/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-06-07 14:47 | 3119-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | DIXON LANDING SUB | Solar PV | 1.02 | 7/6/2022 | 6/1/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2022-06-27 18:37 | 3120-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SOLANO | VACA DIXON SUB | Solar PV | 1.444 | 7/6/2022 | N/A | N/A | N/A | N/A | Pass | 1/25/2023 | N/A | Executed | No former queue position
2022-06-16 14:37 | 3121-WD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CLARA | SWIFT SUB | Solar PV | 0.5 | 7/13/2022 | 8/2/2022 | Fail Screens: 2, 10 | 10/5/2022 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-06-20 10:53 | 3122-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | HUMBOLDT | JANES CREEK SUB | Solar PV | 2 | 7/13/2022 | 9/12/2022 | Fail Screens: I, J, K, L, M, V1, S5 | 11/23/2022 | Fail | Pass | 6/20/2023 | N/A | Executed | No former queue position
2022-06-16 18:01 | 3123-WD | Independent Study | Independent Study | Active | Not Provided | 11/14/2024 |  | KERN | CARNERAS SUB | Solar PV | 4.8453 | 7/13/2022 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 12/15/2022 | N/A | Executed | No former queue position
2022-07-07 16:36 | 3124-RD | Detailed Study | DGSP | Active | Not Provided |  |  | KINGS | GUERNSEY SUB | Solar PV | 2.125 | 7/13/2022 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2022-07-05 17:46 | 3125-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | FAMOSO SUB | Solar PV | 5 | 7/20/2022 | N/A | N/A | N/A | N/A | Pass | 12/6/2022 | N/A | Executed | No former queue position
2022-07-08 08:16 | 3126-RD | Detailed Study | Detailed Study | Active | Not Provided | 6/28/2024 |  | SHASTA | BURNEY SUB | Biomass | 3.6 | 7/20/2022 | N/A | N/A | N/A | N/A | Pass | 11/23/2022 | N/A | Executed | No former queue position
2022-07-09 12:48 | 3127-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | TULARE LAKE SUB | Solar PV | 2.5 | 7/20/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-07-08 06:48 | 3128-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SOLANO | Customer-Owned Substation | Solar PV | 9.499 | 7/20/2022 | 10/7/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-06-20 17:32 | 3129-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | EL CAPITAN SUB | Solar PV | 0.976 | 7/27/2022 | 8/23/2022 | Fail Screens: D, F, J, K, M, S5 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-07-08 14:36 | 3130-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | DIXON LANDING SUB | Solar PV | 0.5 | 8/3/2022 | 9/30/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-07-12 14:49 | 3131-WD | Independent Study | Independent Study | Active | Not Provided | 12/20/2024 |  | KERN | MARICOPA SUB | Solar PV | 3 | 8/3/2022 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 12/22/2022 | N/A | Executed | No former queue position
2022-07-15 16:54 | 3132-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN MATEO | DALY CITY SUB | Gas Turbine | 0.787 | 8/3/2022 | 9/12/2022 | Fail Screens: H, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-07-20 02:36 | 3133-RD | Fast Track | Fast Track | Active | Not Provided |  |  | COLUSA | MAXWELL SUB | Solar PV | 0.45 | 8/3/2022 | 8/24/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-07-12 15:08 | 3134-WD | Independent Study | Independent Study | Active | Not Provided | 10/31/2024 |  | KERN | TAFT SUB | Solar PV | 5 | 8/3/2022 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 12/22/2022 | N/A | Executed | No former queue position
2022-07-20 07:22 | 3135-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA BARBARA | FAIRWAY SUB | Solar PV | 1.4 | 8/3/2022 | 8/24/2022 | Fail Screens: I, J, K, M, S5, A1 | 10/25/2022 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-07-22 17:56 | 3136-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | LERDO SUB | Solar PV | 3.375 | 8/3/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-07-01 13:37 | 3137-RD | Fast Track | Fast Track | Active | Not Provided |  |  | CONTRA COSTA | RICHMOND R SUB | Cogeneration | 0.331 | 8/3/2022 | 9/14/2022 | Fail Screens: B, J, M | 2/24/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-07-13 09:03 | 3138-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN JOAQUIN | FRENCH CAMP SUB | Solar PV | 0.35 | 8/10/2022 | 9/6/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-08-03 11:20 | 3139-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | NEWARK SUB | Solar PV | 1.046 | 8/17/2022 | 10/4/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2022-07-21 09:23 | 3140-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | NEWARK SUB | Gas Turbine | 0.085 | 8/24/2022 | 10/31/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-07-21 09:39 | 3141-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SONOMA | BELLEVUE SUB | Gas Turbine | 0.085 | 8/24/2022 | 11/18/2022 | Fail Screens: I, J, M |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-07-21 09:41 | 3142-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | SAN LEANDRO U SUB | Gas Turbine | 0.125 | 8/24/2022 | 10/31/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-07-21 09:26 | 3143-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN MATEO | EAST GRAND SUB | Solar PV | 0.085 | 8/24/2022 | 10/11/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-07-21 09:37 | 3144-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SONOMA | Customer-Owned Substation | Gas Turbine | 0.085 | 8/24/2022 | 2/23/2023 | Fail Screens: S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-07-22 11:21 | 3145-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | SAN JOAQUIN | MOSHER SUB | Cogeneration,Solar PV | 1.573 | 8/24/2022 | 9/14/2022 | Fail Screens: F, I, J, K, M, V1, S5, A1 | 10/28/2022 | Fail | Pass | 2024-03-11 |  | Tendered | No former queue position
2022-08-11 11:55 | 3146-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Solar PV | 0.089 | 8/24/2022 | 9/14/2022 | Fail Screens: V1 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-08-10 09:58 | 3147-RD | Fast Track | Fast Track | In Service | Not Provided |  |  | EL DORADO | DIAMOND SPRINGS SUB | Solar PV | 0.5 | 8/24/2022 | 10/21/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-02-16 13:58 | 3148-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | CONTRA COSTA | RICHMOND R SUB | Solar PV | 0.7 | 8/31/2022 | 10/13/2022 | Fail Screens: F, I, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-07-21 09:31 | 3149-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SONOMA | SANTA ROSA A SUB | Gas Turbine | 0.085 | 8/31/2022 | 1/27/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-08-03 14:04 | 3150-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MARIN | SAN RAFAEL SUB | Cogeneration | 2.35 | 8/31/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-08-08 10:59 | 3151-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | BUTTE | OROVILLE SUB | Solar PV | 2 | 8/31/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-08-01 15:29 | 3152-WD | Independent Study | Independent Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | KERN OIL SUB | Gas Turbine | 21.97 | 8/31/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-08-10 11:13 | 3153-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MONTEREY | Withdrawn | Solar PV+AES+Synchronous | 1.976 | 9/7/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-08-12 13:32 | 3154-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | SAN RAMON SUB | Solar PV | 1 | 9/7/2022 | 9/22/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-08-17 16:00 | 3155-RD | Fast Track | DGSP | Active | Not Provided |  |  | FRESNO | GATES SUB | Solar PV | 5.25 | 9/7/2022 | N/A | N/A | N/A | N/A | Pass | 2023-09-28 | N/A | Executed | No former queue position
2022-08-24 08:36 | 3156-RD | Fast Track | DGSP | Active | Not Provided |  |  | MONTEREY | OIL FIELDS SUB | Solar PV | 0.95 | 9/7/2022 | 10/4/2022 | Fail Screens: F, J, S5 | 12/14/2022 | Fail | Pass | 2023-12-20 |  | Tendered | No former queue position
2022-08-30 11:16 | 3157-RD | Fast Track | Fast Track | Active | Not Provided |  |  | TULARE | CORCORAN SUB | Solar PV | 0.96 | 9/7/2022 | 11/3/2022 | Fail Screens: F, J, K, M, V1, S5, A1 | 12/21/2022 | Fail | Pass | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-08-30 07:21 | 3158-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | MERCED | ATWATER SUB | Solar PV | 0.21 | 9/14/2022 | 10/5/2022 | Fail Screens: F, G, I, J, L, M, S5 | 11/18/2022 | Fail | Pass | 4/21/2023 | N/A | Executed | No former queue position
2022-08-17 15:53 | 3159-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | SAN LUIS OBISPO | TEMPLETON SUB | Solar PV | 2.375 | 9/21/2022 | 12/1/2022 | Fail Screens: D, F, G, H, J, K, L, M, V1, V2, S5 | 2/3/2023 | Fail | Pass | In Progress |  |  | No former queue position
2022-08-22 13:11 | 3160-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA CLARA | LOCKHEED #1 SUB | Solar PV | 1.66 | 9/21/2022 | 12/7/2022 | Fail Screens: J, K, M, S5 | 2/17/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-08-23 17:27 | 3161-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | HUMBOLDT | HUMBOLDT BAY PP | Solar PV | 1.93 | 9/21/2022 | N/A | N/A | N/A | N/A | Pass | 4/24/2023 | N/A | Executed | No former queue position
2022-08-26 09:41 | 3162-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CRUZ | GREEN VALLEY SUB | Solar PV | 0.8 | 9/21/2022 | 12/5/2022 | Fail Screens: B, F, I, J, S5 | 2/27/2023 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-09-02 19:26 | 3163-RD | Fast Track | Fast Track | Active | Not Provided |  |  | CONTRA COSTA | SAN RAMON SUB | Solar PV | 0.9 | 9/21/2022 | 10/17/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-09-06 19:29 | 3164-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | CONTRA COSTA | LONE TREE SUB | Solar PV | 0.9 | 9/21/2022 | 10/24/2022 | Fail Screens: F, J, K, M, S5 | 12/5/2022 | Fail | Pass | 4/19/2023 | N/A | Executed | No former queue position
2022-08-02 10:15 | 3165-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN FRANCISCO | SAN FRAN G SUB | Solar PV | 0.13 | 9/28/2022 | 1/24/2023 | Fail Screens: J, M |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-08-30 17:25 | 3166-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Solar PV | 0.13 | 9/28/2022 | 1/24/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-08-25 16:37 | 3167-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | OAKLAND C (OAKLAND PP) SUB | Solar PV | 2.24 | 9/28/2022 | 5/26/2023 | Fail Screens: D, I, J, K, M | 8/7/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2022-08-19 14:31 | 3168-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SOLANO | VACAVILLE SUB | Solar PV | 0.3 | 10/5/2022 | 10/26/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-09-02 09:50 | 3169-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SOLANO | SUISUN SUB | Solar PV | 0.653 | 10/5/2022 | 11/30/2022 | Fail Screens: B, D, I, J, K, M, S5 | 2/7/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-09-15 10:24 | 3170-WD | Independent Study | DGSP | Active | Not Provided | 8/15/2025 |  | FRESNO | ORO LOMA SUB | Solar PV | 5 | 10/5/2022 | N/A | N/A | N/A | N/A | Fail | 2023-04-11 | N/A | Executed | No former queue position
2022-09-26 15:59 | 3171-WD | Independent Study | Independent Study | Withdrawn | 7/31/2024 | Withdrawn | Withdrawn | KERN | SMYRNA SUB | Solar PV | 3 | 10/5/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-09-26 16:09 | 3172-WD | Independent Study | DGSP | Withdrawn | 7/31/2024 | Withdrawn | Withdrawn | KERN | SMYRNA SUB | Solar PV | 5 | 10/5/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-09-30 13:41 | 3173-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | SAN JOAQUIN | CARBONA SUB | Solar PV | 0.983 | 10/12/2022 | 11/1/2022 | Fail Screens: D, J, K, M | 12/20/2022 | Fail | Pass | 6/26/2023 | N/A | Executed | No former queue position
2022-09-16 14:52 | 3174-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | BUTTE | JACINTO SUB | Solar PV | 0.96 | 11/23/2022 | 12/23/2022 | Fail Screens: D, F, G, J, K, M, S5 | 3/14/2023 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-09-22 19:35 | 3175-RD | Fast Track | Fast Track | Active | Not Provided |  |  | CONTRA COSTA | MEADOW LANE SUB | Solar PV | 0.715 | 10/12/2022 | 11/21/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-09-26 16:24 | 3176-WD | Independent Study | Independent Study | Withdrawn | 7/31/2024 | Withdrawn | Withdrawn | KERN | COPUS SUB | Solar PV | 3 | 10/12/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-09-26 16:32 | 3177-WD | Independent Study | Independent Study | Withdrawn | 7/31/2024 | Withdrawn | Withdrawn | KERN | COPUS SUB | Solar PV | 5 | 10/12/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-08-19 12:00 | 3178-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | SAN LEANDRO U SUB | Solar PV | 1.12 | 10/12/2022 | 2/21/2023 | Fail Screens: F, I, J, K, M | 6/1/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2022-09-15 11:44 | 3179-WD | DGSP | DGSP | Active | Not Provided | 8/31/2025 |  | FRESNO | ORO LOMA SUB | Solar PV | 3.875 | 10/12/2022 | N/A | N/A | N/A | N/A | Pass | 2023-04-11 | N/A | Executed | No former queue position
2022-09-23 16:42 | 3180-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SOLANO | VACA DIXON SUB | Solar PV | 1.47 | 10/12/2022 | 1/10/2023 | Pass | N/A | N/A | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2022-10-04 10:18 | 3181-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | SONOMA | FITCH MTN SUB | Solar PV | 0.987 | 10/12/2022 | 11/9/2022 | Fail Screens: F, I, J, K, L, M | 12/30/2022 | Fail | Pass | 6/2/2023 | N/A | Executed | No former queue position
2022-10-03 06:56 | 3182-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MONTEREY | SOLEDAD SUB | Solar PV | 0.966 | 10/19/2022 | 2/13/2023 | Fail Screens: I, J, K, M, S5, R1 | 3/28/2023 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-10-04 19:44 | 3183-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | CALIFORNIA AVE SUB | Solar PV | 1.57 | 10/19/2022 | 4/10/2023 | Fail Screens: D, F, J, K, M, S5 | 5/30/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2022-10-04 19:53 | 3184-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | CALIFORNIA AVE SUB | Solar PV | 1.208 | 10/19/2022 | 11/8/2022 | Fail Screens: D, J, K, M, S5 | 1/18/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2022-10-05 11:26 | 3185-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SOLANO | JAMESON SUB | Solar PV | 2.212 | 10/26/2022 | N/A | N/A | N/A | N/A | Pass | 5/22/2023 | N/A | Executed | No former queue position
2022-10-07 01:06 | 3186-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN MATEO | DALY CITY SUB | Solar PV | 0.787 | 11/2/2022 | 12/8/2022 | Fail Screens: D, G, I, J, V1, S5, A1 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-10-19 12:04 | 3187-RD | Fast Track | Fast Track | Active | Not Provided | 6/15/2024 |  | CONTRA COSTA | KIRKER SUB | Solar PV | 2.9 | 11/2/2022 | 12/1/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-09-29 13:18 | 3188-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | YOLO | DAVIS SUB | Solar PV | 0.5 | 11/2/2022 | 12/22/2022 | Fail Screens: F, I, J, K, M | 2/17/2023 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-10-07 15:59 | 3189-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA CLARA | LLAGAS SUB | Solar PV | 0.5 | 11/2/2022 | 12/7/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2022-09-02 12:06 | 3190-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SANTA BARBARA | Transmission Customer | Solar PV | 14.745 | 11/2/2022 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2022-10-28 11:46 | 3191-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN FRANCISCO | SAN FRAN P(HUNTERS POINT) SUB | Solar PV | 0.36 | 11/2/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-10-25 15:20 | 3192-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | SAN BERNARD SUB | Solar PV | 0.25 | 11/9/2022 | 12/7/2022 | Fail Screens: D, F, I, J, K, M, V1, V2, S5, A1 | 1/18/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-10-28 13:22 | 3193-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA CLARA | FMC SUB | Solar PV | 0.195 | 11/9/2022 | 12/5/2022 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-10-11 15:08 | 3194-WD | Independent Study | Independent Study | Active | 12/31/2025 | 12/14/2026 |  | KERN | TAFT SUB | Solar PV | 5 | 11/9/2022 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 5/3/2023 | N/A | Executed | No former queue position
2022-10-17 17:04 | 3195-WD | Independent Study | Independent Study | Active | 6/3/2024 | 12/31/2024 |  | KINGS | TULARE LAKE SUB | Solar PV | 5 | 11/9/2022 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 8/8/2023 | N/A | Executed | No former queue position
2022-10-17 17:50 | 3196-WD | Independent Study | DGSP | Active | 6/3/2024 |  |  | KINGS | TULARE LAKE SUB | Solar PV | 5 | 11/9/2022 | N/A | N/A | N/A | N/A | Pass | 2024-01-30 |  | Tendered | No former queue position
2022-11-02 14:50 | 3197-WD | Independent Study | Independent Study | Active | 5/31/2024 | 5/21/2024 |  | KERN | LAKEVIEW SUB | Solar PV | 1.2 | 11/9/2022 | 11/30/2022 | Fail Screens: 2, 7, 9, 10 | 1/12/2023 | Fail | Pass | 7/31/2023 | N/A | Executed | No former queue position
2022-11-03 14:47 | 3198-WD | Independent Study | Independent Study | Active | 12/31/2024 | 12/14/2026 |  | KERN | TWISSELMAN SUB | Solar PV | 3 | 11/16/2022 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 4/25/2023 | N/A | Executed | No former queue position
2022-09-26 09:46 | 3199-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Solar PV,Leroy Sommer Synchronous Engine | 0.13 | 11/16/2022 | 2023-04-21 | Fail Screens: F, G, I, J, K, M | 2023-09-01 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2022-10-28 12:19 | 3200-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | MONTEREY | WATSONVILLE SUB | Solar PV | 1.2 | 11/23/2022 | N/A | N/A | N/A | N/A | Pass | 2023-11-09 |  | Tendered | No former queue position
2022-11-11 15:27 | 3201-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN FRANCISCO | DALY CITY SUB | Solar PV | 0.036 | 11/23/2022 | 2023-04-11 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-11-11 11:13 | 3202-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | SCHINDLER SUB | Solar PV | 0.84 | 11/30/2022 | 2023-01-23 | Fail Screens: D, J, K, M, M1, S5 | 2023-03-06 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-10-26 10:17 | 3203-RD | Fast Track | Fast Track | Active | Not Provided |  |  | YOLO | DAVIS SUB | Solar PV | 0.966 | 2022-12-07 | 2023-02-22 | Pass | N/A | N/A | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-11-04 16:20 | 3204-WD | Fast Track | Fast Track | Active | 6/5/2023 | 3/31/2025 |  | SAN JOAQUIN | WEBER SUB | Solar PV | 1 | 12/7/2022 | 1/11/2023 | Fail Screens: 2, 4, 5, 7, 9, 10 | 3/17/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-11-04 16:31 | 3205-WD | Fast Track | Independent Study | Withdrawn | 6/5/2023 | Withdrawn | Withdrawn | SAN JOAQUIN | WEBER SUB | Solar PV | 1 | 12/7/2022 | 1/11/2023 | Fail Screens: 2, 4, 5, 7, 9, 10 | 3/13/2023 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-11-04 16:38 | 3206-WD | Fast Track | Fast Track | Active | 6/5/2023 | 3/31/2025 |  | SAN JOAQUIN | WEBER SUB | Solar PV | 1 | 12/7/2022 | 1/11/2023 | Fail Screens: 2, 7, 10 | 3/16/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-11-09 15:47 | 3207-WD | Fast Track | Fast Track | Withdrawn | 6/8/2023 | Withdrawn | Withdrawn | ALAMEDA | EDES SUB | Solar PV | 1.006 | 12/7/2022 | 02/09/2023 | Fail Screens: 2, 5, 7, 10 | 3/6/2023 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-11-09 15:51 | 3208-WD | Fast Track | Independent Study | Withdrawn | 6/8/2023 | Withdrawn | Withdrawn | SAN JOAQUIN | WEBER SUB | Solar PV | 1.006 | 12/7/2022 | 1/6/2023 | Fail Screens: 2, 4, 5, 7, 9, 10 | 3/15/2023 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-11-09 16:14 | 3209-WD | Fast Track | Fast Track | Active | 6/8/2023 | 3/31/2025 |  | ALAMEDA | EDES SUB | Solar PV | 1.006 | 12/7/2022 | 1/19/2023 | Fail Screens: 2, 10 | 3/6/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-11-09 16:20 | 3210-WD | Fast Track | Independent Study | Withdrawn | 6/8/2023 | Withdrawn | Withdrawn | SAN JOAQUIN | WEBER SUB | Solar PV | 1.006 | 12/7/2022 | 1/6/2023 | Fail Screens: 2, 4, 5, 7, 9, 10 | 3/15/2023 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-11-09 16:33 | 3211-WD | Fast Track | Fast Track | Withdrawn | 6/8/2023 | Withdrawn | Withdrawn | ALAMEDA | EDES SUB | Solar PV | 1.006 | 12/7/2022 | 12/28/2022 | Fail Screens: 2, 10 | 2/16/2023 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-11-09 16:40 | 3212-WD | Fast Track | Fast Track | Active | 6/8/2023 | 3/31/2025 |  | SAN JOAQUIN | WEBER SUB | Solar PV | 1.006 | 12/7/2022 | 1/9/2023 | Fail Screens: 2, 7, 10 | 3/17/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-11-09 16:44 | 3213-WD | Fast Track | Independent Study | Withdrawn | 6/8/2023 | Withdrawn | Withdrawn | SAN JOAQUIN | WEBER SUB | Solar PV | 1.006 | 12/7/2022 | 1/6/2023 | Fail Screens: 2, 4, 5, 7, 9, 10 | 3/15/2023 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-11-09 16:53 | 3214-WD | Fast Track | Fast Track | Active | 6/8/2023 | 3/31/2025 |  | SAN JOAQUIN | VIERRA SUB | Solar PV | 1.006 | 12/7/2022 | 1/9/2023 | Fail Screens: 2, 4, 5, 7, 9, 10 | 3/24/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-11-17 09:38 | 3215-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | FAMOSO SUB | Solar PV | 1.125 | 12/7/2022 | N/A | N/A | N/A | N/A | Pass | 5/8/2023 | N/A | Executed | No former queue position
2022-11-17 09:44 | 3216-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | MCFARLAND SUB | Solar PV | 1 | 12/7/2022 | N/A | N/A | N/A | N/A | Pass | 5/8/2023 | N/A | Tendered | No former queue position
2022-11-17 10:05 | 3217-RD | Detailed Study | DGSP | Active | Not Provided |  |  | KINGS | CORCORAN SUB | Solar PV | 2.75 | 12/7/2022 | N/A | N/A | N/A | N/A | Fail | 2023-10-03 | N/A | Executed | No former queue position
2022-11-17 10:55 | 3218-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | SMYRNA SUB | Solar PV | 1.75 | 12/7/2022 | N/A | N/A | N/A | N/A | Pass | 7/19/2023 | N/A | Executed | No former queue position
2022-11-17 11:00 | 3219-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | LERDO SUB | Solar PV | 1.25 | 12/7/2022 | N/A | N/A | N/A | N/A | Pass | 8/11/2023 | N/A | Executed | No former queue position
2022-11-17 11:03 | 3220-RD | Detailed Study | DGSP | Active | Not Provided |  |  | KERN | LERDO SUB | Solar PV | 2 | 12/7/2022 | N/A | N/A | N/A | N/A | Fail | 2023-11-08 | N/A | Executed | No former queue position
2022-11-17 11:21 | 3221-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | TUPMAN SUB | Solar PV | 1.8 | 12/7/2022 | N/A | N/A | N/A | N/A | Fail | 8/4/2023 | N/A | Executed | No former queue position
2022-11-17 11:27 | 3222-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | SMYRNA SUB | Solar PV | 1.5 | 12/7/2022 | N/A | N/A | N/A | N/A | Pass | 8/4/2023 | N/A | Executed | No former queue position
2022-11-17 15:36 | 3223-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | LERDO SUB | Solar PV | 3 | 12/7/2022 | N/A | N/A | N/A | N/A | Pass | 7/19/2023 | N/A | Executed | No former queue position
2022-11-23 12:10 | 3224-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MARIPOSA | MARIPOSA SUB | Biomass | 3.6 | 12/7/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-11-04 15:28 | 3225-WD | Independent Study | Cluster | Active | 10/30/2024 |  |  | SANTA BARBARA | CUYAMA SUB | Solar PV | 5 | 12/7/2022 | N/A | N/A (Cluster) | N/A | N/A (Cluster) | Fail | In Progress |  |  | No former queue position
2022-11-08 08:14 | 3226-WD | Detailed Study | Detailed Study | Active | Not Provided | 4/18/2025 |  | KERN | ANTELOPE SUB | Solar PV | 5.5 | 12/7/2022 | N/A | N/A | N/A | N/A | Pass | 5/18/2023 | N/A | Executed | No former queue position
2022-11-14 15:21 | 3227-WD | Cluster | Cluster | Active | 12/13/2024 |  |  | MERCED | LIVINGSTON SW STA | Solar PV, Storage | 10.5126 | 12/7/2022 | N/A | N/A (Cluster) | N/A | N/A (Cluster) | N/A (Cluster) |  |  |  | No former queue position
2022-11-23 08:59 | 3228-RD | Fast Track | Fast Track | Active | Not Provided |  |  | AMADOR | CLAYTON SUB | Solar PV | 1 | 12/7/2022 | 2/21/2023 | Fail Screens: D, F, J, K, M, V1, S5 | 3/31/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-11-29 23:18 | 3229-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SUTTER | TUDOR SUB | Solar PV | 0.504 | 12/14/2022 | 4/18/2023 | Fail Screens: G, I, L, M, S5 | 10/12/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2022-11-17 11:23 | 3230-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | SEMITROPIC SUB | Solar PV | 2.53 | 12/14/2022 | N/A | N/A | N/A | N/A | Pass | 7/24/2023 | N/A | Executed | No former queue position
2022-11-02 15:36 | 3231-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | MALAGA SUB | Solar PV | 2.406 | 12/14/2022 | 3/1/2023 | Fail Screens: F, I, J, K, M, V2, S5, A1 | 4/12/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-12-07 16:18 | 3232-WD | Independent Study | Independent Study | Withdrawn | 3/29/2024 | Withdrawn | Withdrawn | SONOMA | PETALUMA C SUB | Solar PV | 2.5 | 12/21/2022 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-12-02 16:52 | 3233-WD | Independent Study | Independent Study | Active | 3/29/2024 |  |  | TEHAMA | VOLTA #1 PH | Solar PV | 3 | 12/21/2022 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 7/20/2023 | 2/22/2024 | Tendered | No former queue position
2022-11-04 16:08 | 3234-WD | Fast Track | Fast Track | Withdrawn | 6/5/2023 | 3/31/2025 | Withdrawn | SAN MATEO | EAST GRAND SUB | Solar PV | 1.006 | 12/28/2022 | 1/19/2023 | Fail Screens: 2, 10 | 4/3/2023 | Pass | Withdrawn | Withdrawn | Withdrawn | Executed | No former queue position
2022-12-14 17:43 | 3235-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SOLANO | SUISUN SUB | Solar PV | 1.25 | 1/4/2023 | 2/27/2023 | Fail Screens: D, F, I, J, K, S5, A1 | 4/19/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-12-11 08:53 | 3236-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | AMADOR | ELECTRA SUB | LEP Generator | 0.17 | 1/4/2023 | 2/2/2023 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-11-17 09:41 | 3237-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | LERDO SUB | Solar PV | 1 | 03/23/2023 | N/A | N/A | N/A | N/A | Pass | 9/7/2023 | N/A | Executed | No former queue position
2022-12-21 15:14 | 3238-RD | Fast Track | Detailed Study | Active | Not Provided | 3/28/2025 |  | SAN JOAQUIN | VIERRA SUB | Solar PV | 3 | 1/11/2023 | 2/2/2023 | Fail Screens: J, K, L, M | 3/2/2023 | Fail | Fail | 8/25/2023 | N/A | Executed | No former queue position
2022-11-09 16:27 | 3239-WD | Fast Track | Fast Track | Active | 6/8/2023 | 3/31/2025 |  | ALAMEDA | OAKLAND C (OAKLAND PP) SUB | Solar PV | 1.006 | 1/11/2023 | 1/24/2023 | Fail Screens: 2, 10 | 3/13/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-12-15 13:39 | 3240-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | KERN | FELLOWS SUB | Solar PV | 2.916 | 1/18/2023 | 2/7/2023 | Fail Screens: D, F, J, K, L, M, V1, S5, A1 | 5/19/2023 | Fail | Pass | In Progress |  |  | No former queue position
2022-12-13 12:22 | 3241-WD | Independent Study | Independent Study | Active | 2/1/2024 |  |  | LAKE | HARTLEY SUB | Solar PV | 12 | 1/18/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | In Progress |  |  | No former queue position
2022-12-27 11:31 | 3242-WD | Fast Track | Fast Track | Withdrawn | 4/30/2024 | Withdrawn | Withdrawn | SANTA CRUZ | PAUL SWEET SUB | Solar PV | 2.522 | 1/25/2023 | 2/8/2023 | Fail Screens: 2, 6, 10 | 4/11/2023 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-12-27 11:33 | 3243-WD | Fast Track | Fast Track | Withdrawn | 4/30/2024 | Withdrawn | Withdrawn | SANTA CRUZ | CAMP EVERS SUB | Solar PV | 2.522 | 1/25/2023 | 2/8/2023 | Fail Screens: 2, 6, 10 | 4/3/2023 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-12-23 15:37 | 3244-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN BENITO | TRES PINOS SUB | Solar PV | 0.375 | 1/25/2023 | 2/14/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-01-03 10:00 | 3245-WD | Fast Track | Fast Track | Withdrawn | 4/30/2024 | Withdrawn | Withdrawn | SAN BENITO | HOLLISTER SUB | Solar PV | 2.522 | 1/25/2023 | 2/9/2023 | Fail Screens: 2, 4, 6, 10 | 4/11/2023 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-01-06 16:54 | 3246-WD | Independent Study | Independent Study | Active | 4/30/2024 |  |  | EL DORADO | SHINGLE SPRINGS SUB | Solar PV | 4.99 | 1/25/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 7/21/2023 | 3/7/2024 |  | No former queue position
2023-01-12 06:46 | 3247-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | DUMBARTON SUB | Solar PV | 0.966 | 1/25/2023 | 3/2/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-01-17 14:13 | 3248-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | VASCO SUB | Solar PV | 0.2 | 1/25/2023 | 5/23/2023 | Fail Screens: D, F, I, J, K, L, M | 10/9/2023 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-12-19 09:15 | 3249-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA BARBARA | SANTA MARIA SUB | Solar PV | 1.95 | 1/25/2023 | 3/3/2023 | Fail Screens: F, J, K, M | 5/30/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-12-22 18:02 | 3250-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | CALIFORNIA AVE SUB | Solar PV | 1.066 | 1/25/2023 | 3/9/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-01-12 16:37 | 3251-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | KERN | FAMOSO SUB | Solar PV | 0.546 | 1/25/2023 | 3/15/2023 | Fail Screens: D, F, I, J, K, M, V1, V2, S5, A1 | 4/19/2023 | Fail | Pass | 11/14/2023 | N/A | Executed | No former queue position
2022-12-13 14:47 | 3252-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SOLANO | PEABODY SUB | Solar PV,Cogeneration | 0.326 | 2/1/2023 | 4/11/2023 | Fail Screens: S5, A1 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-01-05 07:18 | 3253-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | RIO BRAVO SUB | Solar PV | 2.75 | 02/22/2023 | N/A | N/A | N/A | N/A | Pass | 9/5/2023 | N/A | Executed | No former queue position
2023-01-20 16:13 | 3254-RD | Fast Track | Fast Track | Active | Not Provided |  |  | MONTEREY | DOLAN RD SUB | Solar PV | 0.975 | 2/1/2023 | 2/21/2023 | Fail Screens: M | 3/20/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-12-29 09:22 | 3255-WD | Independent Study | Independent Study | Active | 9/30/2024 |  |  | KERN | SHAFTER SUB | Solar PV | 6.134 | 2/1/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 11/21/2023 | N/A | Tendered | No former queue position
2022-12-27 11:35 | 3256-WD | Fast Track | Fast Track | Withdrawn | 4/30/2024 | Withdrawn | Withdrawn | SANTA CRUZ | GREEN VALLEY SUB | Solar PV | 2.522 | 2/1/2023 | 2/23/2023 | Fail Screens: 2, 4, 6, 10 | 4/6/2023 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-01-10 13:34 | 3257-WD | Independent Study | Independent Study | Withdrawn | 12/31/2024 | Withdrawn | Withdrawn | HUMBOLDT | JANES CREEK SUB | Solar PV | 1.234 | 2/1/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-01-10 14:11 | 3258-WD | Independent Study | Independent Study | Active | 12/29/2023 | 12/31/2024 |  | HUMBOLDT | ARCATA SUB | Solar PV | 4 | 2/1/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 9/25/2023 | N/A | Executed | No former queue position
2023-01-18 14:30 | 3259-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA CRUZ | GREEN VALLEY SUB | Gas Turbine | 0.494 | 2/8/2023 | 7/31/2023 | Fail Screens: F, G, H, I, J, L, M, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-01-23 12:00 | 3260-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | SCHINDLER SUB | Solar PV | 0.84 | 09/22/2023 | 10/13/2023 | Fail Screens: F, J, K, M, V1, S5, A1 | 1/2/2024 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-02-01 15:19 | 3261-WD | Independent Study | Independent Study | Withdrawn | 4/1/2025 | Withdrawn | Withdrawn | FRESNO | SAN JOAQUIN SUB | Solar PV | 3.75 | 2/15/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-01-26 13:47 | 3262-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | NORCO SUB | Cogeneration | 0.8 | 2/15/2023 | 5/16/2023 | Fail Screens: B, D, F, G, I, J, M, V1, S5, A1 | 9/18/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-02-06 16:41 | 3263-RD | Fast Track | Fast Track | Active | Not Provided |  |  | CONTRA COSTA | LAKEWOOD SUB | Solar PV | 1.041 | 2/15/2023 | 4/24/2023 | Fail Screens: D, G, H, J, K, M, V1, S5, A1 | 5/22/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2022-12-28 15:49 | 3264-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CLARA | AMES DIST SUB | Solar PV | 3 | 2/15/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-01-26 13:45 | 3265-WD | Fast Track | Fast Track | Withdrawn | 10/2/2023 | Withdrawn | Withdrawn | ALAMEDA | OAKLAND J SUB | Storage | 0.243 | 2/15/2023 | 3/13/2023 | Fail Screens: 2, 4, 6, 10 | 5/24/2023 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-01-26 13:45 | 3266-WD | Fast Track | Fast Track | Withdrawn | 4/30/2024 | Withdrawn | Withdrawn | SANTA CRUZ | GREEN VALLEY SUB | Solar PV | 3.783 | 2/15/2023 | 3/1/2023 | Fail Screens: 2, 6, 10 | 4/3/2023 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-02-06 17:11 | 3267-WD | Independent Study | DGSP | Active | 11/1/2024 |  |  | MERCED | MERCED SUB | Gas Turbine | 0.999 | 2/15/2023 | N/A | N/A | N/A | N/A | Pass | 2024-02-02 |  |  | No former queue position
2023-02-06 10:03 | 3268-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CRUZ | GREEN VALLEY SUB | Solar PV,Gas Turbine | 0.5 | 2/22/2023 | 6/28/2023 | Fail Screens: B, F, G, H, I, J, K, L, M, S5 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-02-08 14:57 | 3269-WD | Fast Track | Fast Track | Withdrawn | 4/1/2025 | Withdrawn | Withdrawn | FRESNO | HELM SUB | Solar PV | 1.4 | 3/1/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-01-23 15:59 | 3270-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA CLARA | WHISMAN SUB | Solar PV | 1.31 | 3/1/2023 | 3/22/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-02-10 11:50 | 3271-WD | Fast Track | Fast Track | Withdrawn | 12/16/2024 | Withdrawn | Withdrawn | SAN JOAQUIN | MORMON SUB | Solar PV | 2.214 | 3/1/2023 | 4/20/2023 | Fail Screens: 2, 4, 9, 10 | 7/27/2023 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-02-13 14:12 | 3272-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KINGS | CORCORAN SUB | Linear Generator | 0.988 | 3/1/2023 | 4/21/2023 | Fail Screens: B, D, F, G, I, J, K, L, M, V1, S5, A1 | 7/31/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-02-06 15:11 | 3273-WD | Independent Study | Independent Study | Active | 11/1/2024 |  |  | MERCED | WILSON SUB | Biomass | 0.999 | 3/8/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 9/11/2023 | N/A | Tendered | No former queue position
2023-02-15 16:05 | 3274-WD | Fast Track | Fast Track | Withdrawn | 4/19/2024 | Withdrawn | Withdrawn | ALAMEDA | NEWARK SUB | Solar PV | 1.1347 | 3/8/2023 | 8/30/2023 | Fail Screens: 2, 4, 10 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-02-16 08:06 | 3275-WD | Fast Track | Fast Track | Withdrawn | 4/19/2024 | Withdrawn | Withdrawn | ALAMEDA | GRANT SUB | Solar PV, Storage | 1.135 | 3/8/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-02-16 08:38 | 3276-WD | Fast Track | Fast Track | Withdrawn | 4/19/2024 | Withdrawn | Withdrawn | ALAMEDA | EDES SUB | Solar PV | 1.578 | 3/8/2023 | 3/27/2023 | Fail Screens: 2, 10 | 5/8/2023 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-02-16 11:27 | 3277-WD | Fast Track | Fast Track | Withdrawn | 4/19/2024 | Withdrawn | Withdrawn | ALAMEDA | EDES SUB | Solar PV | 1.459 | 3/8/2023 | 3/27/2023 | Fail Screens: 2, 10 | 6/7/2023 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-02-07 14:05 | 3278-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SAN JOAQUIN | WEBER SUB | Solar PV | 5.52 | 3/8/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-02-16 13:19 | 3279-WD | Fast Track | Independent Study | Withdrawn | 4/19/2024 | Withdrawn | Withdrawn | SAN JOAQUIN | BANTA SUB | Linear Generator | 2.503 | 3/8/2023 | 4/13/2023 | Fail Screens: 2, 4, 10 | 6/8/2023 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-02-16 07:52 | 3280-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV, Storage | 9.85 | 3/15/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-02-17 10:15 | 3281-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | MERCED | CANAL SUB | Cogeneration | 1.998 | 3/15/2023 | N/A | N/A | N/A | N/A | Pass | 8/15/2023 | N/A | Executed | No former queue position
2023-02-17 13:21 | 3282-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | GUERNSEY SUB | Gas Turbine | 2.997 | 3/15/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-02-17 17:07 | 3283-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | MERCED | SANTA RITA SUB | Engine | 0.999 | 3/15/2023 | N/A | N/A | N/A | N/A | Pass | 8/24/2023 | N/A | Tendered | No former queue position
2023-02-27 15:01 | 3284-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | SCHINDLER SUB | Solar PV | 1.32 | 3/15/2023 | 4/11/2023 | Fail Screens: F, J, K, M, V1, S5, A1 | 5/16/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-01-07 16:40 | 3285-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | DUNLAP SUB | Solar PV | 0.05 | 3/15/2023 | 4/4/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-02-13 14:03 | 3286-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | COLUSA | WILLIAMS SUB | Solar PV | 2.503 | 3/22/2023 | 4/12/2023 | Fail Screens: D, I, J, K, M, V1, V2, S5, A1 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-03-02 16:29 | 3287-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | EL CERRITO G SUB | Engine, Solar PV | 6.065 | 3/22/2023 | 8/4/2023 | Fail Screens: B, F, I, J, K, L, M | 12/4/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-01-20 15:09 | 3288-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | CALIFORNIA AVE SUB | Solar PV | 2.385 | 3/22/2023 | 5/5/2023 | Fail Screens: F, J, K, M, S5 | 7/7/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-02-24 10:26 | 3289-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN LUIS OBISPO | CARRIZO PLAINS SUB | Solar PV | 4.9 | 3/22/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-02-24 10:50 | 3290-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SOLANO | VACA DIXON SUB | Solar PV | 2.999 | 3/22/2023 | 4/21/2023 | Fail Screens: B, D, F, I, J, K, M, S5, A1 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-02-27 10:55 | 3291-WD | Independent Study | Independent Study | Withdrawn | 9/27/2024 | Withdrawn | Withdrawn | EL DORADO | DIAMOND SPRINGS SUB | Solar PV | 4.99 | 3/22/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-02-27 12:00 | 3292-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | WEEDPATCH SUB | Solar PV, Storage | 9.7 | 3/22/2023 | N/A | N/A | N/A | N/A | Pass | 12/26/2023 |  |  | No former queue position
2023-02-27 13:08 | 3293-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | SAN BERNARD SUB | Solar PV, Storage | 9.7 | 3/22/2023 | N/A | N/A | N/A | N/A | Fail | 2/8/2024 |  |  | No former queue position
2023-02-27 14:41 | 3294-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | WHEELER RIDGE SUB | Solar PV, Storage | 9.7 | 3/22/2023 | N/A | N/A | N/A | N/A | Pass | 2/22/2024 |  |  | No former queue position
2023-02-27 15:37 | 3295-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | CHOWCHILLA SUB | Solar PV, Storage | 9.7 | 3/22/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-02-27 17:00 | 3296-WD | Fast Track | Fast Track | Withdrawn | 9/27/2024 | Withdrawn | Withdrawn | KINGS | GUERNSEY SUB | Solar PV | 2 | 3/22/2023 | 4/11/2023 | Fail Screens: 2, 4, 10 | 7/28/2023 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-02-28 10:04 | 3297-WD | Fast Track | Fast Track | Withdrawn | 8/11/2023 | Withdrawn | Withdrawn | SAN MATEO | EAST GRAND SUB | Solar PV | 0.494 | 3/22/2023 | 4/12/2023 | Fail Screens: 2, 7, 10 | 7/12/2023 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-02-28 11:43 | 3298-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | CHARCA SUB | Solar PV, Storage | 9.7 | 3/22/2023 | N/A | N/A | N/A | N/A | Pass | 2023-10-06 |  |  | No former queue position
2023-03-03 16:29 | 3299-WD | Independent Study | Independent Study | Withdrawn | 9/30/2024 | Withdrawn | Withdrawn | SHASTA | JESSUP SUB | Solar PV | 2.504 | 3/29/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-03-03 17:04 | 3300-WD | Independent Study | Independent Study | Withdrawn | 9/30/2024 | Withdrawn | Withdrawn | TEHAMA | RED BLUFF SUB | Solar PV | 4.99 | 3/29/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-02-21 10:42 | 3301-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SOLANO | BAHIA SUB | Solar PV | 1.28 | 3/29/2023 | N/A | N/A | N/A | N/A | Pass | 8/24/2023 | N/A | Executed | No former queue position
2023-03-09 15:46 | 3302-WD | DGSP | DGSP | Withdrawn | 4/1/2025 | Withdrawn | Withdrawn | FRESNO | HELM SUB | Solar PV | 1.25 | 3/29/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-03-03 19:16 | 3303-RD | Fast Track | Fast Track | Active | Not Provided |  |  | CONTRA COSTA | RICHMOND R SUB | Cogeneration,Solar PV | 1.71 | 3/29/2023 | 4/25/2023 | Fail Screens: B, F, I, J, K, M | 5/23/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-03-07 15:49 | 3304-RD | Fast Track | Fast Track | Active | Not Provided |  |  | PLACER | PLEASANT GROVE SUB | Solar PV | 0.12 | 3/29/2023 | 5/23/2023 | Fail Screens: F, G, I, J, K, M | 11/7/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-03-10 11:41 | 3305-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SONOMA | TYLER SUB | Solar PV | 1.004 | 3/29/2023 | 4/28/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-03-10 17:50 | 3306-WD | Independent Study | DGSP | Active | 11/28/2025 |  |  | ALAMEDA | NEWARK DIST SUB | Solar PV | 15 | 3/29/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-03-10 19:16 | 3307-WD | Independent Study | DGSP | Active | 11/28/2025 |  |  | ALAMEDA | NEWARK DIST SUB | Storage | 14.959 | 3/29/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-03-16 20:34 | 3308-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | AMADOR | ELECTRA PH | Engine, Solar PV | 0.5 | 3/29/2023 | 6/27/2023 | Fail Screens: D, I, J, L, M, S5 | 1/12/2024 | Fail | Pass | In Progress |  |  | No former queue position
2023-03-07 15:51 | 3309-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA CLARA | LLAGAS SUB | Solar PV | 1.26 | 4/5/2023 | 4/24/2023 | Fail Screens: I, J, K, M, S5 | 5/26/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-03-13 08:32 | 3310-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | WAHTOKE SUB | Solar PV | 2.25 | 4/5/2023 | 4/26/2023 | Fail Screens: F, J, K, M, V1, V2, S5, A1 | 7/18/2023 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-03-13 09:04 | 3311-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | FRESNO | WAHTOKE SUB | Solar PV | 1 | 4/5/2023 | 4/28/2023 | Fail Screens: F, J, K, M, V1, V2, S5 | 7/18/2023 | Fail | Pass | 1/25/2024 | N/A | Tendered | No former queue position
2023-03-02 05:51 | 3312-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | ALAMEDA | CASTRO VALLEY SUB | Solar PV, Storage | 2.078 | 4/5/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-03-03 22:59 | 3313-WD | Independent Study | Independent Study | Active | 4/10/2024 |  |  | CALAVERAS | VALLEY SPRINGS SUB | Storage | 12.665 | 4/5/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass |  |  |  | No former queue position
2023-03-03 23:58 | 3314-WD | Independent Study | Independent Study | Active | 4/12/2024 |  |  | TUOLUMNE | RACETRACK SUB | Solar PV | 10.976 | 4/5/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass |  |  |  | No former queue position
2023-03-04 00:49 | 3315-WD | Independent Study | Independent Study | Active | 4/9/2024 |  |  | MENDOCINO | HOPLAND SUB | Storage | 12.665 | 4/5/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass |  |  |  | No former queue position
2023-03-04 01:39 | 3316-WD | Independent Study | Independent Study | Active | 4/1/2024 |  |  | LAKE | CLEAR LAKE SUB | Storage | 11.821 | 4/5/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass |  |  |  | No former queue position
2023-03-07 05:58 | 3317-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | FRESNO | NEWHALL SUB | Solar PV, Storage | 9.7 | 4/5/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-03-13 14:07 | 3318-WD | Independent Study | Independent Study | Active | 3/31/2025 | 12/20/2024 |  | KERN | BLACKWELL SUB | Storage | 2 | 4/5/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Fail | 10/6/2023 | N/A | Executed | No former queue position
2023-03-20 12:29 | 3319-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | LERDO SUB | Solar PV, Storage | 3.639 | 4/5/2023 | 5/17/2023 | Fail Screens: B, D, H, I, J, K, L, M, V1, S5, A1 | 6/20/2023 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-03-16 12:37 | 3320-RD | Detailed Study | DGSP | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | ORTIGA SUB | Solar PV | 1.2832 | 4/5/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-03-23 13:04 | 3321-WD | Cluster | Cluster | Active | 11/1/2024 |  |  | KERN | FAMOSO SUB | Storage | 6.087 | 4/5/2023 | N/A | N/A (Cluster) | N/A | N/A (Cluster) | N/A (Cluster) | In Progress |  |  | No former queue position
2023-03-23 15:28 | 3322-WD | Cluster | Cluster | Active | 11/1/2024 |  |  | KERN | FAMOSO SUB | Storage | 6.087 | 4/5/2023 | N/A | N/A (Cluster) | N/A | N/A (Cluster) | N/A (Cluster) | In Progress |  |  | No former queue position
2023-03-04 01:24 | 3323-WD | Independent Study | Independent Study | Active | 4/12/2024 |  |  | SAN LUIS OBISPO | FOOTHILL SUB | Biomass | 10.976 | 4/5/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass |  |  |  | No former queue position
2023-03-16 11:50 | 3324-RD | Detailed Study | DGSP | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | ORTIGA SUB | Solar PV | 0.7333 | 4/5/2023 | 4/28/2023 | Fail | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-03-22 10:09 | 3325-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | COALINGA #2 SUB | Solar PV, Storage | 2.044 | 4/12/2023 | 6/23/2023 | Fail Screens: F, J, K, M, V1, S5, A1 | 8/23/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-03-15 12:46 | 3326-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | FRESNO | CANTUA SUB | Solar PV | 2.125 | 4/12/2023 | 5/15/2023 | Fail Screens: D, J, K, M | 6/30/2023 | Pass | N/A | N/A | N/A | Executed | No former queue position
2023-03-17 13:18 | 3327-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN MATEO | BELMONT SUB | Solar PV | 0.9375 | 4/12/2023 | In Progress |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-03-19 14:39 | 3328-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | LAMMERS SUB | Solar PV | 1.328 | 4/12/2023 | 5/3/2023 | Fail Screens: M, S5 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-03-13 16:16 | 3329-RD | Fast Track | Fast Track | Active | Not Provided |  |  | HUMBOLDT | EUREKA A SUB | Solar PV,Cogeneration | 0.42 | 4/12/2023 | 5/24/2023 | Fail Screens: B, I, J, M, S5 | 8/21/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2022-12-16 15:36 | 3330-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MONTEREY | GREEN VALLEY SUB | Other, Solar PV | 0.564 | 4/12/2023 | 8/3/2023 | Fail Screens: F, G, H, I, J, K, L, M, S5 | 9/20/2023 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2022-12-16 15:36 | 3331-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MONTEREY | GREEN VALLEY SUB | Other, Solar PV | 0.869 | 4/12/2023 | 5/24/2023 | Fail Screens: F, G, H, I, J, K, L, M, S5 | 8/3/2023 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-03-20 13:57 | 3332-RD | Fast Track | Fast Track | Active | Not Provided |  |  | NAPA | TULUCAY SUB | Other, Storage | 1.715 | 4/19/2023 | 8/9/2023 | Fail Screens: B, C, D, F, G, I, J, K, M, V1, S5, A1 | 1/17/2024 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-03-07 15:56 | 3333-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | OAKLAND J SUB | Storage - EVSE | 0.072 | 4/19/2023 | 5/24/2023 | Fail Screens: B, D, F, G, I, J, K, M, V1, S5, A1 | 8/7/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-03-10 15:10 | 3334-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | EL PECO SUB | Solar PV | 5 | 4/19/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-03-10 15:17 | 3335-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | WEEDPATCH SUB | Solar PV, Storage | 9.7 | 4/19/2023 | N/A | N/A | N/A | N/A | Fail | 12/26/2023 |  |  | No former queue position
2023-03-23 16:24 | 3336-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA BARBARA | DIVIDE SUB | Solar PV | 0.96 | 4/19/2023 | 8/1/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-03-24 15:00 | 3337-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SOLANO | PEABODY SUB | Solar PV | 1.044 | 4/19/2023 | 7/6/2023 | Fail Screens: D, I, J, K, M, V1, V2, S5 | 9/13/2023 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-03-24 15:13 | 3338-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | KERN | RIO BRAVO SUB | Solar PV | 1.044 | 4/19/2023 | 7/28/2023 | Fail Screens: B, D, F, G, H, I, J, K, M, V1, V2, S5, A1 | 9/14/2023 | Fail | Pass | In Progress |  |  | No former queue position
2023-03-24 16:15 | 3339-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | DUMBARTON SUB | Solar PV | 1.552 | 4/19/2023 | 8/14/2023 | Fail Screens: J, K, M, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-03-24 16:47 | 3340-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | DUMBARTON SUB | Solar PV | 2.63 | 4/19/2023 | 8/17/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-03-28 13:55 | 3341-RD | Fast Track | Fast Track | Active | Not Provided |  |  | MADERA | MADERA SUB | Solar PV | 1.562 | 4/19/2023 | 5/24/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-03-29 19:45 | 3342-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | STOCKDALE SUB | Cogeneration,Solar PV | 0.13 | 4/19/2023 | 8/25/2023 | Fail Screens: B, F, H, I, J, K, M, V2, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-03-30 08:38 | 3343-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA CLARA | NORTECH SUB | Solar PV | 1.692 | 4/19/2023 | 6/7/2023 | Fail Screens: F, G, H, J, K, L, M, S5 | 7/24/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-03-30 10:52 | 3344-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | MONTEREY | TBD | Solar PV, Wind | 5.802 | 4/19/2023 | [8 empty] | No former queue position
2023-03-30 11:18 | 3345-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA CLARA | NORTECH SUB | Solar PV | 1.043 | 4/19/2023 | 6/7/2023 | Fail Screens: D, F, G, H, J, K, L, M, S5 | 7/24/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-03-30 13:40 | 3346-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA CLARA | NORTECH SUB | Solar PV | 1.437 | 4/19/2023 | 5/23/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-03-24 16:26 | 3347-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | DUMBARTON SUB | Solar PV | 1.326 | 4/19/2023 | 8/14/2023 | Fail Screens: F, J, K, M, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-03-27 15:45 | 3348-WD | Cluster | Cluster | Active | 4/1/2024 |  |  | KINGS | GUERNSEY SUB | Solar PV | 3 | 4/19/2023 | N/A | N/A (Cluster) | N/A | N/A (Cluster) | N/A (Cluster) | In Progress |  |  | No former queue position
2023-03-29 12:39 | 3349-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KINGS | CORCORAN SUB | Solar PV | 1.055 | 4/19/2023 | 5/26/2023 | Fail Screens: D, F, G, J, K, L, M, S5 | 7/19/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-03-29 14:45 | 3350-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | SEMITROPIC SUB | Solar PV | 0.48425 | 4/19/2023 | 8/4/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-03-31 11:53 | 3351-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | BUTTE | HAMILTON A SUB | Solar PV | 2 | 4/19/2023 | 5/23/2023 | Fail Screens: F, I, J, K, M | 9/18/2023 | Fail | Pass | In Progress |  |  | No former queue position
2023-03-30 12:39 | 3352-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CLARA | NORTECH SUB | Solar PV | 1.327 | 4/19/2023 | 5/16/2023 | Fail Screens: B, F, G, H, I, J, K, L, M, S5 | 7/24/2023 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-03-30 15:27 | 3353-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA CLARA | NORTECH SUB | Solar PV | 1.181 | 4/19/2023 | 5/16/2023 | Fail Screens: D, G, H, J, K, L, M, S5 | 7/24/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-03-14 15:19 | 3354-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | TBD | Solar PV | 1 | 4/26/2023 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-03-23 11:19 | 3355-WD | DGSP | DGSP | Active | 8/1/2024 |  |  | KERN | SMYRNA SUB | Solar PV, Storage | 4.99 | 4/26/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-03-28 19:00 | 3356-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CLARA | AMES DIST SUB | Solar PV, Storage | 9.588 | 4/26/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-03-29 09:20 | 3357-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | LERDO SUB | Solar PV | 0.9 | 4/26/2023 | 6/1/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-03-30 08:07 | 3358-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN JOAQUIN | ROUGH & READY SUB | Solar PV | 1.62 | 4/26/2023 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-03-31 14:11 | 3359-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | WEST FRESNO SUB | Solar PV | 2.294 | 4/26/2023 | 8/16/2023 | Fail Screens: J, K, M, V1, S5, A1 | 11/6/2023 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-03-31 14:14 | 3360-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | FRESNO | WEST FRESNO SUB | Solar PV | 1.208 | 4/26/2023 | 8/16/2023 | Fail Screens: J, K, M, V1, S5, A1 | 11/6/2023 | Fail |  |  |  |  | No former queue position
2023-03-23 16:29 | 3361-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SOLANO | CORDELIA SUB | Solar PV | 0.6 | 4/26/2023 | 9/26/2023 | Fail Screens: D, F, I, J, K, M, S5 | 11/27/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-03-24 09:45 | 3362-WD | DGSP | DGSP | Active | 8/1/2024 |  |  | KERN | COPUS SUB | Solar PV | 5 | 4/26/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-03-29 11:26 | 3363-WD | Cluster | Cluster | Withdrawn | 12/31/2027 | Withdrawn | Withdrawn | KERN | GANSO SUB | Solar PV | 60 | 4/26/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-03-29 22:44 | 3364-WD | Cluster | Cluster | Withdrawn | 12/30/2027 | Withdrawn | Withdrawn | KERN | GANSO SUB | Storage | 100 | 4/26/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-03-30 12:26 | 3365-RD | Fast Track | Fast Track | Active | Not Provided |  |  | NEVADA | BRUNSWICK SUB | Solar PV | 1.122 | 4/26/2023 | 5/23/2023 | Fail Screens: D, F, G, J, K, L, M, S5 | 2/9/2024 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-03-28 10:45 | 3366-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN JOAQUIN | VIERRA SUB | Solar PV | 1.92 | 4/26/2023 | 7/25/2023 | Fail Screens: D, J, K, L, M, S5 | 2024-03-27 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-03-29 17:25 | 3367-WD | DGSP | DGSP | Withdrawn | 8/1/2023 | Withdrawn | Withdrawn | FRESNO | CANTUA SUB | Solar PV, Storage | 4.5 | 4/26/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-03-30 15:52 | 3368-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | SOLANO | PEABODY SUB | Solar PV | 1.125 | 4/26/2023 | 7/20/2023 | Fail Screens: I, J, K, M, V2, S5, A1 | 9/13/2023 | Fail | Pass | In Progress |  |  | No former queue position
2023-03-23 09:36 | 3369-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | EL PECO SUB | Solar PV, Storage | 9.7 | 4/26/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-03-29 09:19 | 3370-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN MATEO | SNEATH LANE SUB | Solar PV | 2.28 | 4/26/2023 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-03-21 14:52 | 3371-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | ALAMEDA | CASTRO VALLEY SUB | Solar PV | 3.809 | 4/26/2023 | 10/9/2023 | Fail Screens: D, F, I, J, K, M | 2/21/2024 | Fail | Pass |  |  |  | No former queue position
2023-03-23 09:12 | 3372-WD | DGSP | Independent Study | Active | 8/1/2024 |  |  | KERN | LAKEVIEW SUB | Solar PV, Storage | 4.99 | 4/26/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 11/22/2023 |  |  | No former queue position
2023-03-24 12:47 | 3373-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN JOAQUIN | TRACY SUB | Solar PV | 0.21 | 4/26/2023 | 5/17/2023 | Fail Screens: D, I, J, K, M, S5 | 7/26/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-04-07 07:58 | 3374-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | GUERNSEY SUB | Solar PV | 1.44 | 4/26/2023 | 5/15/2023 | Fail Screens: F, J, K, M | 6/28/2023 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-09 13:18 | 3375-RD | Fast Track | Fast Track | Active | Not Provided |  |  | MENDOCINO | CALPELLA SUB | Solar PV | 1.05 | 4/26/2023 | 5/17/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-03-30 09:42 | 3376-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | CONTRA COSTA | CONTRA COSTA SUB | Engine, Solar PV, Storage | 1.272 | 5/3/2023 | 5/24/2023 | Fail Screens: B, D, F, G, H, I, J, K, M, V1, S5, A1 | 10/19/2023 | Fail | Pass | In Progress |  |  | No former queue position
2023-03-31 11:18 | 3377-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | SAN BERNARD SUB | Solar PV, Storage | 9.7 | 5/3/2023 | N/A | N/A | N/A | N/A | Pass | 2/9/2024 |  |  | No former queue position
2023-03-31 11:22 | 3378-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | LERDO SUB | Solar PV, Storage | 9.7 | 5/3/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-03-31 11:54 | 3379-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | COALINGA #1 SUB | Solar PV, Storage | 9.7 | 5/3/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-03-31 12:42 | 3380-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | LERDO SUB | Solar PV, Storage | 9.7 | 5/3/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-03-31 13:05 | 3381-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | LERDO SUB | Solar PV, Storage | 9.7 | 5/3/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-03-31 13:44 | 3382-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | EL NIDO SUB | Solar PV, Storage | 4.6 | 5/3/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-04 12:47 | 3383-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | WEBER SUB | Solar PV | 4.38 | 5/3/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-03-31 14:18 | 3384-WD | Independent Study | Cluster | Active | 12/1/2026 |  |  | TULARE | OROSI SUB | Solar PV | 20 | 5/3/2023 | N/A | N/A (Cluster) | N/A | N/A (Cluster) | Fail |  |  |  | No former queue position
2023-03-31 14:23 | 3385-WD | Independent Study | DGSP | Active | 6/1/2026 |  |  | NEVADA | HIGGINS SUB | Solar PV | 20 | 5/3/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-03-31 14:34 | 3386-WD | Independent Study | Independent Study | Active | 6/1/2026 |  |  | NEVADA | NARROWS SUB | Solar PV | 20 | 5/3/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | In Progress |  |  | No former queue position
2023-04-03 16:35 | 3387-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SAN LUIS OBISPO | TEMPLETON SUB | Solar PV | 1.5 | 5/3/2023 | [8 empty] | No former queue position
2023-04-04 14:19 | 3388-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SONOMA | SONOMA A SUB | Solar PV | 1.62 | 5/3/2023 | N/A | N/A | N/A | N/A | Pass |  |  |  | No former queue position
2023-04-12 12:19 | 3389-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | STROUD SUB | Solar PV | 5.772 | 5/3/2023 | 7/10/2023 | Fail Screens: F, J, K, M, V1, V2, S5, A1 | 8/10/2023 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-03-09 09:20 | 3390-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | WESTPARK SUB | Solar PV | 0.586 | 5/3/2023 | 3/17/2024 | Fail Screens: D, J, K, M, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-03-30 15:26 | 3391-WD | Independent Study | Independent Study | Withdrawn | 6/14/2024 | Withdrawn | Withdrawn | MENDOCINO | LAYTONVILLE SUB | Solar PV | 5.007 | 5/3/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-06 06:07 | 3392-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN JOAQUIN | EAST STOCKTON SUB | Solar PV | 3.864 | 5/3/2023 | 7/24/2023 | Fail Screens: D, F, J, K, L, M, V1, S5, A1 | 2/22/2024 | Fail | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-03-29 10:34 | 3393-WD | Cluster | DGSP | Active | 11/1/2024 |  |  | SAN JOAQUIN | LOCKEFORD SUB | Solar PV | 14.8 | 5/3/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-04-05 08:34 | 3394-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN LUIS OBISPO | GOLDTREE SUB | Solar PV | 1 | 12/07/2023 | 3/20/2024 | Fail Screens: D, F, G, J, K, M, S5 | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-04-03 12:47 | 3395-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | RAINBOW SUB | Solar PV | 1.57 | 5/3/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-03 12:48 | 3396-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SANTA CLARA | LLAGAS SUB | Solar PV | 1.57 | 5/3/2023 | N/A | N/A | N/A | N/A | Pass | 10/5/2023 | N/A | Executed | No former queue position
2023-04-03 12:51 | 3397-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SAN JOAQUIN | LAMMERS SUB | Solar PV | 1.57 | 5/3/2023 | N/A | N/A | N/A | N/A | Pass | 3/12/2024 |  |  | No former queue position
2023-04-03 18:59 | 3398-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | GATES SUB | Solar PV | 2.9856 | 5/3/2023 | 6/27/2023 | Fail Screens: F, I, J, K, M, V1, V2, S5, A1 | 8/9/2023 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-07 16:47 | 3399-RD | Fast Track | Fast Track | Active | Not Provided |  |  | YUBA | EAST MARYSVILLE SUB | Solar PV | 1 | 5/3/2023 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-04-07 19:04 | 3400-RD | Fast Track | Fast Track | Active | Not Provided |  |  | MARIN | WOODACRE SUB | Solar PV | 0.7 | 5/3/2023 | 7/31/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-04-12 17:39 | 3401-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA CLARA | EL PATIO SUB | Solar PV | 1.208 | 5/3/2023 | 6/8/2023 | Fail Screens: D, G, J, K, M, V1, S5, A1 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-04-13 19:06 | 3402-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | MCMULLIN SUB | Solar PV | 0.938 | 5/3/2023 | 6/9/2023 | Fail Screens: F, J, K, M, V1, S5, A1 | 7/28/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-04-13 20:56 | 3403-RD | Fast Track | Fast Track | Active | Not Provided |  |  | AMADOR | CLAY SUB | Solar PV | 1.71 | 5/3/2023 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-03-16 14:55 | 3404-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA BARBARA | SANTA MARIA SUB | Solar PV,Cogeneration | 0.332 | 5/10/2023 | 11/2/2023 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-12 14:04 | 3405-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KINGS | KETTLEMAN HILLS SUB | Solar PV | 1.38 | 5/10/2023 | 7/11/2023 | Fail Screens: D, F, G, J, K, L, M, V1, S5, A1 | 8/22/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-04-13 15:00 | 3406-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | DAIRYLAND SUB | Solar PV | 6.348 | 5/10/2023 | 5/30/2023 | Fail Screens: D, F, G, I, J, K, L, M, V1, V2, S5, A1 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-13 15:35 | 3407-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | MERCED SUB | Solar PV, Storage | 6.348 | 5/10/2023 | 5/30/2023 | Fail Screens: D, F, G, I, J, K, L, M, V1, V2, S5, A1 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-05 15:03 | 3408-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | Withdrawn | Solar PV | 1 | 5/10/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-10 15:50 | 3409-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | Withdrawn | Solar PV, Storage | 6.348 | 5/10/2023 | 6/13/2023 | Fail Screens: F, J, K, M, S5, A1 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-11 14:53 | 3410-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | VINEYARD SUB | Solar PV | 1.375 | 07/27/2023 | 10/27/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-04-12 12:37 | 3411-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | WRIGHT SUB | Solar PV | 1.862 | 5/10/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-14 10:01 | 3412-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | PLACER | PLEASANT GROVE SUB | Solar PV | 0.751 | 5/10/2023 | 7/18/2023 | Fail Screens: B, F, G, H, I, J, K, M | 11/2/2023 | Fail | Pass | 3/29/2024 |  |  | No former queue position
2023-04-14 14:24 | 3413-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | SAN JOAQUIN | TRACY SUB | Solar PV | 4.468 | 5/10/2023 | 5/25/2023 | Fail Screens: D, F, G, J, K, M, V1, S5, A1 | 7/28/2023 | Fail | Pass | In Progress |  |  | No former queue position
2023-04-14 14:51 | 3414-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | SONOMA | LAKEVILLE SUB | Solar PV | 1.44 | 5/10/2023 | 5/25/2023 | Fail Screens: D, F, G, J, K, M, V1, S5, A1 | 8/9/2023 | Fail | Pass |  |  |  | No former queue position
2023-04-18 17:07 | 3415-WD | Fast Track | Fast Track | Withdrawn | 11/15/2024 | Withdrawn | Withdrawn | SAN JOAQUIN | MORMON SUB | Solar PV | 2.003 | 5/10/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-11 15:26 | 3416-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | COLUSA | ARBUCKLE SUB | Solar PV | 3.5 | 5/10/2023 | N/A | N/A | 9/22/2023 | Fail | Pass | In Progress |  |  | No former queue position
2023-04-13 09:37 | 3417-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | GUERNSEY SUB | Solar PV, Storage | 6.348 | 5/10/2023 | 6/13/2023 | Fail Screens: F, J, K, M, V2, S5, A1 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-13 10:31 | 3418-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | GUERNSEY SUB | Solar PV, Storage | 6.348 | 5/10/2023 | 6/13/2023 | Fail Screens: F, J, K, M, V1, V2, S5, A1 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-13 12:32 | 3419-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV, Storage | 6.348 | 5/10/2023 | 6/13/2023 | Fail Screens: F, I, J, K, L, M, V1, V2, S5, A1 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-13 13:47 | 3420-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV, Storage | 6.348 | 5/10/2023 | 6/13/2023 | Fail Screens: D, F, G, I, J, K, L, M, V1, V2, S5, A1 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-13 14:32 | 3421-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA CLARA | SWIFT SUB | Solar PV | 13.355 | 5/10/2023 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-04-13 17:40 | 3422-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA CLARA | SWIFT SUB | Solar PV | 4.938 | 5/10/2023 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-04-10 11:16 | 3423-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | SAN JOAQUIN | VIERRA SUB | Solar PV | 2.373 | 5/10/2023 | 6/20/2023 | Fail Screens: F, G, J, K, L, M, S5 | 8/31/2023 | Fail | Pass | In Progress |  |  | No former queue position
2023-04-13 12:54 | 3424-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | LAS POSITAS SUB | Solar PV | 2 | 5/10/2023 | 8/15/2023 | Fail Screens: F, H, I, J, K, M | 11/28/2023 | Fail | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-04-13 16:45 | 3425-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | WHEELER RIDGE SUB | Solar PV | 1.375 | 5/10/2023 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-04-13 17:07 | 3426-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | TEJON SUB | Solar PV | 2 | 5/10/2023 | In Progress |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-04-14 14:23 | 3427-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN JOAQUIN | FRENCH CAMP SUB | Solar PV | 3.466 | 5/10/2023 | 6/20/2023 | Fail Screens: I, J, K, M, S5, A1 | 8/29/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-05-05 10:22 | 3428-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN MATEO | MILLBRAE SUB | Solar PV | 0.1 | 5/10/2023 | 6/16/2023 | Fail Screens: I, J, M | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-04-07 17:40 | 3429-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN MATEO | RALSTON SUB | Solar PV | 3.7 | 5/10/2023 | 7/31/2023 | Fail Screens: F, I, J, K, L, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-10 15:01 | 3430-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | SANGER SUB | Solar PV | 0.96 | 5/10/2023 | 7/19/2023 | Fail Screens: D, F, G, J, K, M, V1, S5, A1 | 9/28/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-04-12 13:05 | 3431-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | MONTEREY | OIL FIELDS SUB | Solar PV | 2.46 | 5/10/2023 | 6/12/2023 | Fail Screens: F, J, K, M, S5, A1 | 7/25/2023 | Fail | Pass | In Progress |  |  | No former queue position
2023-04-14 14:36 | 3432-RD | Fast Track | DGSP | Active | Not Provided |  |  | CONTRA COSTA | KIRKER SUB | Solar PV | 0.9 | 5/10/2023 | 6/9/2023 | Fail Screens: F, G, H, J, K, M, S5 | 8/30/2023 | Fail | Pass |  |  |  | No former queue position
2023-04-03 11:37 | 3433-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA CLARA | LAWRENCE SUB | Cogeneration | 6.65 | 5/17/2023 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-04-13 15:27 | 3434-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN MATEO | EAST GRAND SUB | Solar PV | 1.326 | 5/17/2023 | 8/2/2023 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-13 16:54 | 3435-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KINGS | KETTLEMAN HILLS SUB | Solar PV | 2 | 5/17/2023 | 7/11/2023 | Fail Screens: B, F, I, J, M, V1, V2, S5, A1 | 8/14/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-04-13 19:41 | 3436-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | NAPA | BASALT SUB | Solar PV | 1.764 | 5/17/2023 | 7/26/2023 | Fail Screens: D, F, J, K, M, V1, S5, A1 | 8/23/2023 | Fail |  |  |  |  | No former queue position
2023-04-14 16:46 | 3437-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | MT EDEN SUB | Solar PV, Storage | 2.037 | 5/17/2023 | 8/15/2023 | Fail Screens: F, I, J, K, M | 3/6/2024 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-04-18 12:43 | 3438-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | BUTTE | CHICO B SUB | Solar PV | 1.045 | 5/17/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-21 13:50 | 3439-RD | Fast Track | Fast Track | Active | Not Provided |  |  | BUTTE | NORD SUB | Solar PV | 2.988 | 5/17/2023 | 6/7/2023 | Fail Screens: F, I, K, M | 2/1/2024 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-04-21 14:10 | 3440-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | STANISLAUS | CROWS LANDING SUB | Solar PV | 2.988 | 5/17/2023 | 6/8/2023 | Fail Screens: D, I, J, K, L, M, V1, V2, S5, A1, R1 | 8/3/2023 | Fail | Pass | 3/20/2024 |  |  | No former queue position
2023-03-31 16:11 | 3441-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | SAN LUIS OBISPO | SAN LUIS OBISPO SUB | Solar PV | 1.076 | 5/17/2023 | 9/18/2023 | Fail Screens: D, F, G, J, K, M, S5 | 11/15/2023 | Fail | Pass |  |  |  | No former queue position
2023-04-12 11:28 | 3442-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SUTTER | PEASE SUB | Solar PV | 3.2 | 5/17/2023 | 9/20/2023 | Fail Screens: F, G, K, M | 2/26/2024 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-04-13 12:52 | 3443-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | OAKLAND J SUB | Solar PV, Storage | 0.81207 | 5/17/2023 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-04-13 13:59 | 3444-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | MCCALL SUB | Solar PV | 5.85 | 5/17/2023 | 8/7/2023 | Fail Screens: F, J, K, M, V1, V2, S5, A1 | 10/9/2023 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-14 12:09 | 3445-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SOLANO | CORDELIA SUB | Solar PV | 1.52 | 5/17/2023 | 6/22/2023 | Fail Screens: I, J, K, M, S5 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-10 09:51 | 3446-RD | Fast Track | Fast Track | Active | Not Provided |  |  | BUTTE | TRES VIAS SUB | Solar PV | 0.96 | 5/17/2023 | 6/1/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-04-10 10:37 | 3447-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | CANAL SUB | Solar PV | 2.002 | 5/17/2023 | 6/8/2023 | Fail Screens: D, F, G, J, K, M, S5 | 7/24/2023 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-10 15:48 | 3448-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | BULLARD SUB | Other, Solar PV | 8.2 | 5/17/2023 | 7/24/2023 | Fail Screens: B, F, I, J, K, M, V1, V2, S5, A1 | 10/11/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-04-12 12:57 | 3449-RD | Fast Track | DGSP | Active | Not Provided |  |  | SAN JOAQUIN | WEBER SUB | Solar PV | 1.491 | 5/17/2023 | 6/16/2023 | Fail Screens: M | 7/24/2023 | Fail | Pass |  |  |  | No former queue position
2023-04-13 10:28 | 3450-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | TULARE | DINUBA SUB | Engine, Solar PV, Storage | 6.9579 | 5/17/2023 | 6/29/2023 | Fail Screens: F, I, J, K, M, V1, V2, S5, A1 | 8/25/2023 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-14 11:55 | 3451-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SOLANO | DIXON SUB | Solar PV | 1.239 | 5/17/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-14 12:52 | 3452-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA CLARA | EVERGREEN SUB | Solar PV | 0.903 | 5/17/2023 | 6/28/2023 | Fail Screens: B, D, F, G, H, I, J, K, L, M, V1, S5, A1 | 10/19/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-04-14 21:17 | 3453-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MONTEREY | SOLEDAD SUB | Solar PV | 2.3 | 5/17/2023 | 6/28/2023 | Pass | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-13 16:59 | 3454-RD | Fast Track | Fast Track | Active | Not Provided |  |  | MONTEREY | SALINAS SUB | Solar PV | 3.172 | 5/17/2023 | 6/14/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-04-14 10:08 | 3455-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | MALAGA SUB | Solar PV | 0.9 | 5/17/2023 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-04-14 14:53 | 3456-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN LUIS OBISPO | SAN LUIS OBISPO SUB | Solar PV | 1.041 | 5/17/2023 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-04-10 15:36 | 3457-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | CALIFORNIA AVE SUB | Solar PV | 1.982 | 5/17/2023 | 8/14/2023 | Fail Screens: J, K, M, V1, S5, A1 | 9/21/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-04-12 09:03 | 3458-WD | Independent Study | Independent Study | Withdrawn | 1/1/2026 | Withdrawn | Withdrawn | FRESNO | WEST FRESNO SUB | Solar PV | 5 | 5/17/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-12 09:04 | 3459-WD | Independent Study | Independent Study | Withdrawn | 1/1/2026 | Withdrawn | Withdrawn | FRESNO | FIGARDEN SUB | Solar PV | 5 | 5/17/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-14 09:25 | 3460-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | MARICOPA SUB | Solar PV | 1.357 | 5/17/2023 | 7/7/2023 | Fail Screens: D, F, I, J, K, L, M, V1, S5, A1 | 12/28/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-04-14 12:30 | 3461-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | KERMAN SUB | Solar PV, Storage | 1.46 | 5/17/2023 | 6/29/2023 | Fail Screens: F, I, J, K, M, S5 | 8/22/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-04-14 18:17 | 3462-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA CLARA | STONE SUB | Solar PV | 1.68 | 5/17/2023 | 6/15/2023 | Fail Screens: D, G, I, J, K, L, M, S5 | 9/14/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-04-27 10:32 | 3463-RD | Fast Track | Fast Track | Active | Not Provided |  |  | AMADOR | MARTELL SUB | Solar PV | 2.988 | 5/17/2023 | 6/22/2023 | Fail Screens: D, F, G, I, J, K, M, V1, V2, S5, A1, R1 | 1/4/2024 | Fail | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-04-27 10:36 | 3464-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | MCFARLAND SUB | Solar PV | 4.98 | 5/17/2023 | N/A | N/A | N/A | N/A | Fail | 1/3/2024 | N/A | Tendered | No former queue position
2023-05-05 12:10 | 3465-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | STANISLAUS | COTTLE SUB | Solar PV | 0.461 | 5/17/2023 | 6/6/2023 | Fail Screens: D, F, G, I, J, L, M, S5 | 8/16/2023 | Fail | Pass | 3/4/2024 |  |  | No former queue position
2023-04-11 08:10 | 3466-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA CRUZ | GREEN VALLEY SUB | Engine, Turbine | 0.8 | 5/24/2023 | 8/4/2023 | Fail Screens: B, F, G, I, J, K, L, M, S5 | 12/13/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-04-17 15:57 | 3467-WD | Cluster | Cluster | Withdrawn | 6/2/2025 | Withdrawn | Withdrawn | KERN | BLACKWELL SUB | Solar PV | 21.609 | 5/24/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-07 19:44 | 3468-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA BARBARA | CUYAMA SUB | Solar PV | 0.55 | 5/24/2023 | 8/1/2023 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-12 20:44 | 3469-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | TEVIS SUB | Solar PV | 2.242 | 5/24/2023 | 8/3/2023 | Fail Screens: B, D, F, H, I, J, K, M, V1, S5, A1 | 10/23/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-04-13 11:58 | 3470-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CRUZ | PAUL SWEET SUB | Solar PV | 1.268 | 5/24/2023 | 8/11/2023 | Fail Screens: F, J, K, M, V1, S5, A1 | 12/22/2023 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-14 17:38 | 3471-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | CONTRA COSTA | RICHMOND R SUB | Solar PV | 2.16 | 06/22/2023 | N/A | N/A | N/A | N/A | Pass | 11/20/2023 | N/A | Executed | No former queue position
2023-04-14 15:23 | 3472-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | CAISO Controlled Sub | Solar PV | 16 | 5/24/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-05-11 06:18 | 3473-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | ORTIGA SUB | Solar PV | 2.988 | 5/24/2023 | 6/14/2023 | Fail Screens: D, F, G, I, J, K, M, V1, V2, S5, A1, R1 | 8/17/2023 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-05-11 09:45 | 3474-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SUTTER | PEASE SUB | Solar PV | 2.988 | 5/24/2023 | 6/6/2023 | Fail Screens: F, I, K, M | 2/26/2024 | Fail | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-05-11 09:48 | 3475-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | YOLO | DEEPWATER SUB | Solar PV | 2.988 | 5/24/2023 | 6/22/2023 | Fail Screens: B, D, F, G, I, J, K, M, V1, V2, S5, A1, R1 | 9/6/2023 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-05-22 13:21 | 3476-RD | Detailed Study | Fast Track | Active | Not Provided |  |  | ALAMEDA | OAKLAND C (OAKLAND PP) SUB | Solar PV | 0.043 | 5/24/2023 | 7/6/2023 | Fail Screens: A |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-04-13 20:13 | 3477-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN LUIS OBISPO | BAYWOOD SUB | Solar PV | 0.98 | 5/31/2023 | 8/16/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-04-14 18:31 | 3478-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | GLENN | LOGAN CREEK SUB | Solar PV | 0.84 | 5/31/2023 | 6/6/2023 | Fail Screens: D, F, G, J, K, M, V1, S5, A1 | 8/24/2023 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-28 09:49 | 3479-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | COLUSA | RICE SUB | Solar PV | 0.3 | 5/31/2023 | 7/11/2023 | Fail Screens: D, G, I, J, L, M, V1, S5 | 9/15/2023 | Fail | Pass | In Progress |  |  | No former queue position
2023-05-04 18:47 | 3480-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | COLUSA | RICE SUB | Solar PV | 0.8 | 5/31/2023 | 7/11/2023 | Fail Screens: D, F, G, I, J, K, L, M, S5 | 9/15/2023 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-05-16 07:31 | 3481-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | STANISLAUS | COTTLE SUB | Solar PV | 4.98 | 5/31/2023 | N/A | N/A | N/A | N/A | Pass | 12/20/2023 | N/A | Tendered | No former queue position
2023-03-21 14:32 | 3482-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | BAKERSFIELD SUB | Solar PV | 1.1 | 08/07/2023 | 11/9/2023 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-13 15:35 | 3483-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Solar PV | 2.52 | 5/31/2023 | 6/20/2023 | Fail Screens: D, F, G, J, K, M, V1, S5, A1 | 9/7/2023 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-13 19:32 | 3484-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SOLANO | PEABODY SUB | Solar PV | 1.05 | 5/31/2023 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-04-14 22:16 | 3485-RD | Fast Track | Fast Track | Active | Not Provided |  |  | CONTRA COSTA | POINT PINOLE SUB | Solar PV | 1.3 | 5/31/2023 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-04-03 15:02 | 3486-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | COLUSA | HIGHLANDS SUB | Solar PV, Storage | 1.19 | 5/31/2023 | 7/3/2023 | Fail Screens: D, F, I, J, K, M, S5, A1 | 9/20/2023 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-04-07 07:57 | 3487-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | SAN RAMON SUB | Solar PV, Storage | 0.20725 | 6/7/2023 | 9/19/2023 | Fail Screens: B, D, F, G, H, I, J, K, M, V1, V2, S5, A1 | 3/26/2024 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-04-14 06:49 | 3488-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MONTEREY | SPENCE SUB | Solar PV, Storage | 1.675 | 6/7/2023 | 7/24/2023 | Fail Screens: B, D, F, H, I, J, K, M, V1, V2, S5 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-05-16 16:36 | 3489-WD | Independent Study | DGSP | Active | 11/15/2024 |  |  | SAN JOAQUIN | MORMON SUB | Solar PV, Storage | 2 | 6/7/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-05-17 16:43 | 3490-WD | Independent Study | Independent Study | Active | 9/30/2024 |  |  | TEHAMA | RED BLUFF SUB | Solar PV, Storage | 4.99 | 6/7/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | In Progress |  |  | No former queue position
2023-05-17 16:54 | 3491-WD | Independent Study | Independent Study | Active | 9/27/2024 |  |  | EL DORADO | DIAMOND SPRINGS SUB | Solar PV, Storage | 4.99 | 6/7/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | In Progress |  |  | No former queue position
2023-04-13 11:01 | 3492-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | Withdrawn | Solar PV | 7.47 | 6/7/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-05-17 16:27 | 3493-RD | Fast Track | Fast Track | Active | Not Provided |  |  | MADERA | Withdrawn | Other | 0.428 | 6/7/2023 | 7/12/2023 | Fail Screens: F, I, J, K, L, M, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-05-18 16:47 | 3494-WD | Independent Study | Independent Study | Active | 7/26/2024 |  |  | BUTTE | BANGOR SUB | Solar PV, Storage | 3 | 6/7/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | In Progress |  |  | No former queue position
2023-05-18 16:48 | 3495-WD | Independent Study | Independent Study | Withdrawn | 9/27/2024 | Withdrawn | Withdrawn | KINGS | GUERNSEY SUB | Solar PV, Storage | 2 | 6/7/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-05-18 16:49 | 3496-WD | Independent Study | Independent Study | Active | 9/30/2024 |  |  | SHASTA | JESSUP SUB | Solar PV, Storage | 2.4 | 6/7/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | In Progress |  |  | No former queue position
2023-05-18 11:55 | 3497-WD | Independent Study | Independent Study | Active | 8/22/2025 |  |  | KERN | GOOSE LAKE SUB | Solar PV, Storage | 3 | 6/7/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | 3/6/2024 |  |  | No former queue position
2023-04-04 14:18 | 3498-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | NAPA | SILVERADO SUB | Solar PV | 1.5 | 6/7/2023 | N/A | N/A | N/A | N/A | Pass | 2/22/2024 |  |  | No former queue position
2023-05-26 13:26 | 3499-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | BLACKWELL SUB | Solar PV | 4.98 | 6/7/2023 | 6/27/2023 | Fail Screens: F, I, J, K, L, M, V1, V2, S5, A1, R1 | 9/13/2023 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-05-26 13:36 | 3500-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | SEMITROPIC SUB | Solar PV | 4.98 | 6/7/2023 | 8/29/2023 | Fail Screens: B, D, F, G, I, J, K, L, M, V1, V2, S5, A1, R1 | 12/28/2023 | Fail | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-05-22 14:49 | 3501-RD | Fast Track | DGSP | Active | Not Provided |  |  | CONTRA COSTA | CONTRA COSTA SUB | Solar PV | 0.28 | 6/14/2023 | 7/19/2023 | Fail Screens: D, F, G, I, J, M, S5 | 10/23/2023 | Fail | Pass |  |  |  | No former queue position
2023-04-10 10:47 | 3502-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SOLANO | TBD | Solar PV | 3.912 | 6/14/2023 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-05-12 12:14 | 3503-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA CLARA | BRITTON SUB | Solar PV | 1.204 | 6/14/2023 | 10/2/2023 | Fail Screens: B, D, F, G, I, J, K, M, V1, S5, A1 | 12/5/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-05-25 10:29 | 3504-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | CARUTHERS SUB | Solar PV | 1.4 | 08/15/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-05-24 10:08 | 3505-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | LAKEVIEW SUB | Storage | 1.2045 | 6/14/2023 | 8/31/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-05-18 18:20 | 3506-WD | Independent Study | Independent Study | Withdrawn | 7/31/2024 | Withdrawn | Withdrawn | BUTTE | SYCAMORE CREEK SUB | Solar PV, Storage | 2.375 | 6/21/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-06-08 11:52 | 3507-RD | Detailed Study | DGSP | Active | Not Provided |  |  | COLUSA | ARBUCKLE SUB | Steam Turbine | 5 | 6/21/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-06-05 10:10 | 3508-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN JOAQUIN | TBD | Solar PV | 2.384 | 6/28/2023 | 7/21/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-06-10 18:01 | 3509-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | GANSO SUB | Steam Turbine | 0.5 | 6/28/2023 | 7/25/2023 | Fail Screens: B, F, G, I, J, M, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-06-10 18:45 | 3510-RD | Fast Track | Fast Track | Active | Not Provided |  |  | MERCED | SANTA NELLA SUB | Steam Turbine | 0.55 | 6/28/2023 | 7/24/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-06-16 09:05 | 3511-RD | Fast Track | Fast Track | Active | Not Provided |  |  | MERCED | GUSTINE SUB | Solar PV | 0.1 | 6/28/2023 | 9/6/2023 | Fail Screens: D, I, J, L, M, V1, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-04-10 16:30 | 3512-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | WEST FRESNO SUB | Solar PV, Storage | 2.326 | 6/28/2023 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-06-12 14:30 | 3513-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA CLARA | BRITTON SUB | Solar PV | 1.468 | 6/28/2023 | 8/7/2023 | Fail Screens: D, J, K, V1, S5, A1 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-06-02 15:54 | 3514-RD | Fast Track | Fast Track | Active | Not Provided |  |  | PLACER | PLEASANT GROVE SUB | Solar PV | 2.5 | 7/5/2023 | 7/26/2023 | Fail Screens: H, I, J, K, M | 3/19/2024 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-06-09 11:14 | 3515-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA BARBARA | DIVIDE SUB | Steam Turbine | 1 | 7/5/2023 | 10/12/2023 | Pass | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Executed | No former queue position
2023-06-19 12:42 | 3516-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | TEJON SUB | Solar PV | 0.7 | 7/5/2023 | 7/26/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-06-01 15:42 | 3517-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KINGS | JACOBS CORNER SUB | Biomass | 0.999 | 7/12/2023 | N/A | N/A | N/A | N/A | Pass | 2/13/2024 |  |  | No former queue position
2023-06-19 12:54 | 3518-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | TEJON SUB | Solar PV | 0.7 | 7/12/2023 | 8/3/2023 | Fail |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-06-29 16:36 | 3519-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | TUPMAN SUB | Solar PV | 9 | 7/12/2023 | 8/2/2023 | Pass | N/A | N/A | Pass | 2/23/2024 |  |  | No former queue position
2023-06-23 11:23 | 3520-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | KINGS | RESERVE OIL SUB | Solar PV | 3 | 7/12/2023 | 8/3/2023 | Fail Screens: F, J, K, M, V1, V2, S5, A1 | 10/9/2023 | Fail | Pass | In Progress |  |  | No former queue position
2023-07-07 16:57 | 3521-WD | Independent Study | Independent Study | Withdrawn | 10/1/2025 | Withdrawn | Withdrawn | STANISLAUS | CROWS LANDING SUB | Solar PV | 3.5 | 7/19/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-06-29 10:43 | 3522-RD | Fast Track | Fast Track | Active | Not Provided |  |  | BUTTE | WYANDOTTE SUB | Solar PV | 4.98 | 7/19/2023 | 10/30/2023 | Fail Screens: F, G, I, J, K, L, M | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-06-29 13:59 | 3523-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | BLACKWELL SUB | Solar PV | 4.98 | 7/19/2023 | 9/14/2023 | Fail Screens: B, D, F, G, I, J, K, L, M, V1, V2, S5, A1, R1 | 1/9/2024 | Fail | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-06-22 12:17 | 3524-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | LAKEVIEW SUB | Solar PV | 5 | 7/19/2023 | 8/28/2023 | Fail Screens: B, D, F, I, J, K, L, M, V1, V2, S5, A1, R1 | 11/27/2023 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-06-22 13:52 | 3525-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | LAKEVIEW SUB | Solar PV | 5.312 | 7/19/2023 | 8/28/2023 | Fail Screens: B, D, F, I, J, K, L, M, V1, V2, S5, A1, R1 | 11/27/2023 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-06-22 14:41 | 3526-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | LAKEVIEW SUB | Solar PV | 5.312 | 7/19/2023 | 8/28/2023 | Fail Screens: B, D, F, G, I, J, K, L, M, V1, V2, S5, A1, R1 | 11/27/2023 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-06-29 14:26 | 3527-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SAN LUIS OBISPO | MESA SUB | Storage | 5.684 | 7/26/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-06-22 12:09 | 3528-RD | Fast Track | Fast Track | Active | Not Provided |  |  | TULARE | DINUBA SUB | Storage | 0.85 | 7/26/2023 | 10/2/2023 | Fail Screens: B, F, I, J, K, M, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-07-12 16:33 | 3529-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | KERN | RIO BRAVO SUB | Solar PV | 5 | 7/26/2023 | 9/14/2023 | Fail Screens: B, D, F, I, J, K, M, V1, V2, S5, A1, R1 | 1/11/2024 | Fail | Pass |  |  |  | No former queue position
2023-07-13 14:50 | 3530-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | KERN | ANTELOPE SUB | Solar PV | 5 | 7/26/2023 | 9/15/2023 | Fail Screens: B, D, F, G, I, J, K, L, M, V1, V2, S5, A1, R1 | 1/12/2024 | Fail | Pass |  |  |  | No former queue position
2023-07-17 14:44 | 3531-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | TULARE | ALPAUGH SUB | Storage | 3 | 7/26/2023 | 8/11/2023 | Fail Screens: F, J, K, M, V1, V2, S5, A1 | 10/11/2023 | Fail | Fail |  |  |  | No former queue position
2023-07-19 10:46 | 3532-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | OAKLAND L SUB | Solar PV | 0.067 | 8/2/2023 | 9/1/2023 | Fail Screens: A | 11/9/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-07-27 12:49 | 3533-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN FRANCISCO | SAN FRAN Y (LARKIN) SUB | Solar PV | 0.012 | 8/2/2023 | 8/14/2023 | Fail Screens: M |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-07-27 13:55 | 3534-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN FRANCISCO | SAN FRAN E SUB | Solar PV | 0.002 | 8/2/2023 | 8/14/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-07-21 11:15 | 3535-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA CRUZ | GREEN VALLEY SUB | Cogeneration | 0.247 | 8/2/2023 | 9/26/2023 | Fail Screens: B, F, G, H, I, J, M, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-07-12 16:46 | 3536-WD | Independent Study | Cluster | Withdrawn | 4/30/2025 | Withdrawn | Withdrawn | FRESNO | ORO LOMA SUB | Solar PV | 3.875 | 8/9/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-07-24 16:00 | 3537-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | WHEELER RIDGE SUB | TBD | 7.214 | 8/9/2023 | N/A | N/A | N/A | N/A | Pass | 2/23/2024 |  |  | No former queue position
2023-07-28 17:29 | 3538-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | MERCED | GUSTINE SUB | Solar PV | 5 | 8/9/2023 | N/A | N/A | N/A | N/A | Pass | 12/28/2023 | N/A | Tendered | No former queue position
2023-07-24 13:27 | 3539-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | MARICOPA SUB | Solar PV | 6.529 | 8/16/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-07-26 06:22 | 3540-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | STOREY SUB | TBD | 4.98 | 8/16/2023 | 9/6/2023 | Fail Screens: B, D, F, G, I, J, K, M, V1, V2, S5, A1, R1 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-07-26 06:30 | 3541-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN LUIS OBISPO | TEMPLETON SUB | TBD | 1.992 | 8/16/2023 | 10/23/2023 | Fail Screens: B, D, F, G, H, I, J, K, L, M, V1, V2, S5, A1, R1 | 3/14/2024 | Fail | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-07-26 06:57 | 3542-RD | Fast Track | Fast Track | Active | Not Provided |  |  | EL DORADO | SHINGLE SPRINGS SUB | TBD | 4.98 | 8/16/2023 | 12/1/2023 | Fail Screens: F, I, K, L, M | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-07-27 13:35 | 3543-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | YOLO | MADISON SUB | TBD | 4.98 | 8/16/2023 | 9/22/2023 | Fail Screens: D, F, I, J, K, M, S5, A1, R1 | 11/17/2023 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-07-31 16:35 | 3544-WD | Independent Study | Independent Study | Withdrawn | 9/30/2025 | Withdrawn | Withdrawn | KINGS | JACOBS CORNER SUB | Solar PV | 2.4 | 8/16/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-08-03 12:04 | 3545-WD | Independent Study | Independent Study | Withdrawn | 10/27/2025 | Withdrawn | Withdrawn | KERN | 7TH STANDARD SUB | Solar PV | 4.99 | 8/16/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-08-07 07:50 | 3546-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | CONTRA COSTA | BRENTWOOD SUB | Solar PV | 3 | 8/16/2023 | 10/13/2023 | Fail Screens: D, F, I, J, K, M, S5 | 12/5/2023 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-08-02 08:53 | 3547-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | NAPA | HIGHWAY SUB | Solar PV | 1.85 | 8/16/2023 | 9/7/2023 | Fail Screens: D, F, G, I, J, K, M, V1, S5, A1 | 12/7/2023 | Fail | Pass | In Progress |  |  | No former queue position
2023-08-01 14:48 | 3548-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | KERN | RIO BRAVO SUB | Battery | 6 | 8/16/2023 | 9/18/2023 | Fail Screens: D, F, G, I, J, K, M, V1, V2, S5, A1 | 11/14/2023 | Fail | Fail |  |  |  | No former queue position
2023-08-04 13:01 | 3549-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | FAMOSO SUB | Storage | 5 | 8/16/2023 | 9/18/2023 | Pass | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-08-08 15:08 | 3550-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | ALAMEDA | BRENTWOOD SUB | Solar PV | 1.35 | 8/16/2023 | 1/17/2024 | Fail Screens: D, F, G, H, I, J, K, L, M, V1, S5, A1 | 2/16/2024 | Fail | Pass |  |  |  | No former queue position
2023-07-28 11:39 | 3551-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | DAIRYLAND SUB | Solar PV | 4.6 | 8/30/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-08-02 12:30 | 3552-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | CHEROKEE SUB | Solar PV | 1.856 | 8/30/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-08-07 10:52 | 3553-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | MCFARLAND SUB | Solar PV | 3 | 8/30/2023 | 1/5/2024 | Fail Screens: B, D, F, G, I, J, K, M, V1, V2, S5, A1 | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-08-07 13:21 | 3554-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | KERN | SEMITROPIC SUB | Solar PV | 5 | 8/30/2023 | 9/27/2023 | Fail Screens: B, D, F, G, I, J, K, L, M, V1, V2, S5, A1, R1 | 1/23/2024 | Pass | Pass |  |  |  | No former queue position
2023-08-07 15:19 | 3555-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | MADERA | BIOLA SUB | Solar PV | 3.8 | 8/30/2023 | 9/22/2023 | Fail Screens: F, J, K, M, V1, V2, S5, A1 | 11/10/2023 | Fail | Pass | In Progress |  |  | No former queue position
2023-08-07 17:18 | 3556-WD | Fast Track | Fast Track | Active | 6/21/2024 |  |  | ALAMEDA | SAN LEANDRO U SUB | Solar PV | 1.087 | 8/30/2023 | 11/30/2023 | Fail Screens: 2, 4, 5, 7, 9, 10 | 3/7/2024 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-08-08 10:07 | 3557-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | PLACER | LINCOLN SUB | Solar PV | 1.203 | 8/30/2023 | 12/4/2023 | Fail Screens: B, D, F, G, I, J, K, M, V1, V2, S5, A1 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-08-08 10:14 | 3558-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | FRESNO | MCCALL SUB | Solar PV | 0.929 | 8/30/2023 | 9/22/2023 | Fail Screens: F, J, K, M, V1, V2, S5, A1 | 10/31/2023 | Fail | Pass | In Progress |  |  | No former queue position
2023-08-08 13:30 | 3559-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | HARDWICK SUB | Solar PV | 0.928 | 8/30/2023 | 9/22/2023 | Fail Screens: B, D, F, G, I, J, K, L, M, V1, V2, S5, A1 | 11/2/2023 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-08-08 13:37 | 3560-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA BARBARA | SISQUOC SUB | Solar PV | 3 | 8/30/2023 | 10/11/2023 | Fail Screens: F, I, J, K, M, V1, V2, S5, A1 | 2/2/2024 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-08-09 07:07 | 3561-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | KERN | OLD RIVER SUB | Solar PV | 3.2 | 8/30/2023 | 9/29/2023 | Fail Screens: B, D, F, G, I, J, K, M, V1, V2, S5, A1, R1 | 1/16/2024 | Fail | Pass |  |  |  | No former queue position
2023-08-09 12:14 | 3562-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA BARBARA | CABRILLO SUB | Solar PV | 2.79 | 8/30/2023 | 9/21/2023 | Fail Screens: B, D, F, I, J, K, M, V1, V2, S5, A1 | 2/29/2024 | Fail | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-08-09 12:40 | 3563-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA BARBARA | SISQUOC SUB | Solar PV | 3 | 8/30/2023 | 9/21/2023 | Fail Screens: D, F, M, V1, V2, S5, A1 | 2/16/2024 | Fail | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-08-09 13:06 | 3564-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | BONITA SUB | Solar PV | 1.856 | 8/30/2023 | 9/21/2023 | Fail Screens: B, D, F, I, J, K, L, M, V1, V2, S5, A1 | 11/2/2023 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-08-09 13:33 | 3565-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | LE GRAND SUB | TBD | 2.79 | 8/30/2023 | 9/21/2023 | Fail Screens: B, D, F, I, J, K, L, M, V1, V2, S5, A1 | 11/8/2023 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-08-09 15:25 | 3566-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | TULARE | ALPAUGH SUB | Solar PV | 3.6 | 8/30/2023 | 9/25/2023 | Fail Screens: B, D, F, G, I, J, K, M, V1, V2, S5, A1 | 11/7/2023 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-08-10 12:13 | 3567-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | MADERA | DAIRYLAND SUB | Solar PV | 1 | 8/30/2023 | 9/21/2023 | Fail Screens: B, D, F, I, J, K, M, V1, V2, S5, A1 | 11/3/2023 | Fail | Pass | In Progress |  |  | No former queue position
2023-08-10 13:13 | 3568-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | FRESNO | HAMMONDS SUB | Solar PV | 2.4 | 8/30/2023 | 9/21/2023 | Fail Screens: B, D, F, G, I, J, K, M, V1, V2, S5, A1 | 11/3/2023 | Fail | Fail |  |  |  | No former queue position
2023-08-10 13:33 | 3569-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | SANTA BARBARA | MESA SUB | Storage | 1 | 8/30/2023 | 10/5/2023 | Fail Screens: B, D, F, G, I, J, K, L, M, V1, V2, S5, A1 | 1/3/2024 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-08-10 16:36 | 3570-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | CRESSEY SUB | Solar PV | 2.562 | 8/30/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-08-11 00:25 | 3571-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | YOLO | WOODLAND SUB | Solar PV | 5.93 | 8/30/2023 | N/A | N/A | N/A | N/A | Pass | 3/18/2024 |  |  | No former queue position
2023-08-11 15:06 | 3572-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MARIPOSA | BEAR VALLEY SUB | Solar PV | 5 | 8/30/2023 | 9/25/2023 | Fail | 12/6/2023 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-08-18 10:07 | 3573-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | MCCALL SUB | Solar PV | 3.301 | 8/30/2023 | 9/28/2023 | Fail Screens: F, J, K, M, V1, V2, S5, A1, R1 | 11/9/2023 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-08-08 11:14 | 3574-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | KERN | OLD RIVER SUB | Solar PV | 5.125 | 9/6/2023 | 9/29/2023 | Fail Screens: B, D, F, G, I, J, K, M, V1, V2, S5, A1, R1 | 1/16/2024 | Fail | Pass |  |  |  | No former queue position
2023-08-10 16:16 | 3575-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | ORTIGA SUB | Solar PV | 5.007 | 9/6/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-07-28 09:54 | 3576-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | MERCED SUB | Solar PV | 9.7 | 9/6/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-08-17 12:10 | 3577-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | GATES SUB | Solar PV | 8 | 9/6/2023 | 9/29/2023 | Fail Screens: F, J, K, M, V1, V2, S5, A1 | 11/15/2023 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-08-17 15:40 | 3578-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | HARDWICK SUB | TBD | 11.38 | 9/6/2023 | 10/4/2023 | Fail Screens: F, J, K, L, M, V1, V2, S5, A1 | 11/28/2023 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-08-18 09:50 | 3579-WD | Fast Track | Fast Track | Active | 3/3/2025 |  |  | CONTRA COSTA | TIDEWATER SUB | Solar PV | 4 | 9/6/2023 | 10/27/2023 | Fail Screens: 2, 4, 5, 6, 7, 9, 10 | 1/3/2024 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-07-21 12:59 | 3580-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | WHEELER RIDGE SUB | Solar PV | 7.214 | 9/13/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-08-07 16:44 | 3581-WD | Fast Track | Fast Track | Active | 6/21/2024 | 3/1/2026 |  | ALAMEDA | EDES SUB | Solar PV | 0.725 | 9/13/2023 | 10/3/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-08-07 17:02 | 3582-WD | Fast Track | Fast Track | Active | 6/21/2024 |  |  | ALAMEDA | GRANT SUB | Solar PV | 0.604 | 9/13/2023 | In Progress |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-08-10 10:52 | 3583-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | DEVILS DEN SUB | Solar PV | 4.005 | 9/13/2023 | 10/5/2023 | Fail Screens: F, J, K, M, V1, V2, S5, A1 | 11/27/2023 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-08-11 12:26 | 3584-WD | Independent Study | DGSP | Active | 8/12/2024 |  |  | SHASTA | JESSUP SUB | Steam Turbine | 6 | 9/13/2023 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2023-08-03 10:24 | 3585-WD | Independent Study | Independent Study | Active | 6/21/2024 |  |  | SAN JOAQUIN | TRACY SUB | Solar PV | 3 | 9/13/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | In Progress |  |  | No former queue position
2023-08-03 11:36 | 3586-WD | Fast Track | Fast Track | Active | 6/14/2024 |  |  | SAN JOAQUIN | BANTA SUB | Solar PV | 2 | 9/13/2023 | 11/9/2023 | Fail Screens: 2, 4, 5, 7, 10 | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-08-17 09:02 | 3587-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KINGS | AVENAL SUB | Solar PV | 1.41 | 9/20/2023 | 12/12/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-08-29 13:15 | 3588-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | MCFARLAND SUB | Solar PV | 2.49 | 9/20/2023 | 10/17/2023 | Fail Screens: B, D, F, G, I, J, K, M, V1, V2, S5, A1, R1 | 12/26/2023 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-08-29 14:50 | 3589-RD | Detailed Study | DGSP | Active | Not Provided |  |  | BUTTE | BANGOR SUB | Solar PV | 4.98 | 9/20/2023 | N/A | N/A | N/A | N/A | Pass |  |  |  | No former queue position
2023-08-29 15:09 | 3590-RD | Fast Track | Fast Track | Active | Not Provided |  |  | YUBA | PLUMAS SUB | Solar PV | 0.996 | 9/20/2023 | 1/9/2024 | Fail Screens: B, D, F, G, H, I, J, K, L, M, V1, V2, S5, A1, R1 | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-09-01 08:50 | 3591-WD | DGSP | DGSP | Active | 10/1/2025 |  |  | SAN JOAQUIN | RIPON SUB | Solar PV | 4.95 | 9/20/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-09-01 08:50 | 3592-WD | DGSP | DGSP | Withdrawn | 9/1/2025 | Withdrawn | Withdrawn | KERN | MAGUNDEN SUB | Solar PV | 4.99 | 9/20/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-09-01 08:51 | 3593-WD | DGSP | DGSP | Withdrawn | 10/1/2025 | Withdrawn | Withdrawn | FRESNO | CARUTHERS SUB | Storage | 2.4 | 9/20/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-09-01 08:53 | 3594-WD | DGSP | Independent Study | Active | 10/1/2025 |  |  | KERN | MCFARLAND SUB | Storage | 4.99 | 9/20/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | In Progress |  |  | No former queue position
2023-09-01 08:53 | 3595-WD | DGSP | Independent Study | Active | 10/1/2025 |  |  | KERN | WELLFIELD SUB | Solar PV | 4.95 | 9/20/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | In Progress |  |  | No former queue position
2023-09-01 08:54 | 3596-WD | DGSP | Independent Study | Active | 10/1/2025 |  |  | KERN | SEMITROPIC SUB | Solar PV | 4.95 | 9/20/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | In Progress |  |  | No former queue position
2023-09-01 08:54 | 3597-WD | DGSP | Independent Study | Active | 10/1/2025 |  |  | KERN | FAMOSO SUB | Solar PV | 4.95 | 9/20/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | In Progress |  |  | No former queue position
2023-09-01 16:59 | 3598-WD | DGSP | DGSP | Withdrawn | 10/1/2025 | Withdrawn | Withdrawn | FRESNO | SANGER SUB | Solar PV | 4.95 | 9/20/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-08-17 10:00 | 3599-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SHASTA | BURNEY SUB | Other | 5 | 9/20/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-08-24 14:00 | 3600-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | FRESNO | RAINBOW SUB | Solar PV | 0.966 | 9/20/2023 | N/A | N/A | N/A | N/A | Pass | 12/14/2023 | N/A | Executed | No former queue position
2023-09-07 21:57 | 3601-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | LERDO SUB | Solar PV | 5 | 9/20/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-09-01 08:55 | 3602-WD | DGSP | DGSP | Active | 10/1/2025 |  |  | KERN | ARVIN SUB | Storage | 2.5 | 9/27/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-09-07 17:19 | 3603-WD | DGSP | DGSP | Active | 10/1/2025 |  |  | KERN | ANTELOPE SUB | Solar PV | 4.99 | 9/27/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-09-07 18:39 | 3604-WD | Fast Track | Fast Track | Active | 4/1/2025 |  |  | SAN JOAQUIN | TRACY SUB | Solar PV | 1.932 | 9/27/2023 | 10/25/2023 | Fail Screens: 2, 4, 5, 7, 10 | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-09-08 14:43 | 3605-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SHASTA | JESSUP SUB | Solar PV | 2.988 | 9/27/2023 | 1/25/2024 | Fail Screens: F, I, K, M | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-09-08 14:47 | 3606-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SUTTER | BOGUE SUB | Solar PV | 4.98 | 9/27/2023 | 1/31/2024 | Fail Screens: F, G, I, J, K, M | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-09-11 13:18 | 3607-WD | DGSP | Independent Study | Active | 10/1/2025 |  |  | KERN | WHEELER RIDGE SUB | Storage | 4.99 | 9/27/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | In Progress |  |  | No former queue position
2023-09-11 13:38 | 3608-WD | DGSP | DGSP | Active | 10/1/2025 |  |  | KERN | TEJON SUB | Solar PV | 4.99 | 9/27/2023 | N/A | N/A | N/A | N/A | Pass | 2024-03-28 |  |  | No former queue position
2023-09-11 14:30 | 3609-WD | DGSP | DGSP | Active | 10/1/2025 |  |  | KERN | COPUS SUB | Solar PV | 4.99 | 9/27/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-09-11 14:50 | 3610-WD | DGSP | DGSP | Active | 11/3/2025 |  |  | SAN LUIS OBISPO | CHOLAME SUB | TBD | 4.99 | 9/27/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-09-11 15:10 | 3611-WD | DGSP | DGSP | Active | 10/1/2025 |  |  | KERN | TUPMAN SUB | Solar PV | 4.99 | 9/27/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-09-11 15:44 | 3612-RD | Fast Track | Fast Track | Active | Not Provided |  |  | COLUSA | COLUSA JUNCTION | Reciprocating Engine | 3 | 9/27/2023 | 11/15/2023 | Fail Screens: B, D, F, I, J, K, M, S5 | 1/11/2024 | Fail | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-09-12 15:32 | 3613-WD | DGSP | Cluster | Withdrawn | 12/31/2024 | Withdrawn | Withdrawn | MERCED | WILSON SUB | Solar PV | 2.25 | 9/27/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-08-23 12:26 | 3614-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | Transmission Customer | Solar PV | 1.204 | 10/4/2023 | 2/26/2024 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-09-07 14:35 | 3615-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | RAINBOW SUB | Solar PV | 5 | 10/4/2023 | 11/14/2023 | Fail Screens: D, F, G, I, J, K, L, M, V1, V2, S5, A1 | 12/18/2023 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-09-12 12:32 | 3616-WD | Independent Study | Cluster | Active | 3/19/2025 |  |  | MERCED | LIVINGSTON SUB | TBD | 6.014 | 10/4/2023 | N/A | N/A (Cluster) | N/A | N/A (Cluster) | Fail |  |  |  | No former queue position
2023-09-17 19:58 | 3617-WD | DGSP | DGSP | Withdrawn | 11/3/2025 | Withdrawn | Withdrawn | KERN | LAMONT SUB | Solar PV | 4.999 | 10/4/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-09-18 10:49 | 3618-WD | DGSP | DGSP | Active | 11/3/2025 |  |  | SUTTER | BARRY SUB | Solar PV | 4.999 | 10/4/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-09-18 11:03 | 3619-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN MATEO | REDWOOD CITY SUB | Other | 0.987 | 10/4/2023 | 11/16/2023 | Fail Screens: J, K, M |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-09-18 11:52 | 3620-WD | DGSP | Independent Study | Active | 10/1/2025 |  |  | SUTTER | LIVE OAK SUB | Solar PV | 9.95 | 10/4/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | In Progress |  |  | No former queue position
2023-09-18 12:16 | 3621-WD | DGSP | Independent Study | Active | 10/31/2025 |  |  | SUTTER | WHEATLAND SUB | Solar PV | 4.99 | 10/4/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | In Progress |  |  | No former queue position
2023-09-18 13:54 | 3622-WD | DGSP | DGSP | Active | 10/1/2025 |  |  | KERN | SMYRNA SUB | Solar PV | 4.99 | 10/4/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-09-18 14:32 | 3623-WD | DGSP | DGSP | Withdrawn | 10/1/2025 | Withdrawn | Withdrawn | KERN | OLD RIVER SUB | Solar PV | 4.999 | 10/4/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-08-09 01:11 | 3624-WD | Independent Study | Independent Study | Active | 12/20/2024 |  |  | KERN | TWISSELMAN SUB | Solar PV | 4.95 | 10/4/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | In Progress |  |  | No former queue position
2023-09-08 12:30 | 3625-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN JOAQUIN | TBD | Solar PV | 1.305 | 10/4/2023 | 12/14/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-09-12 06:19 | 3626-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SUTTER | MERIDIAN SUB | Solar PV | 4.98 | 10/4/2023 | 11/8/2023 | Fail Screens: B, D, F, I, J, K, L, M | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-09-14 16:58 | 3627-WD | Independent Study | Cluster | Active | 3/31/2025 |  |  | CONTRA COSTA | BRENTWOOD SUB | TBD | 4.99 | 10/4/2023 | N/A | N/A (Cluster) | N/A | N/A (Cluster) | Fail |  |  |  | No former queue position
2023-09-18 11:21 | 3628-WD | DGSP | DGSP | Active | 10/2/2023 |  |  | SAN JOAQUIN | LOCKEFORD SUB | Solar PV | 4.99 | 10/4/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-09-19 16:04 | 3629-WD | DGSP | DGSP | Withdrawn | 10/1/2025 | Withdrawn | Withdrawn | KERN | SHAFTER SUB | Storage | 4.99 | 10/4/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-09-20 11:42 | 3630-WD | DGSP | DGSP | Withdrawn | 10/1/2025 | Withdrawn | Withdrawn | MADERA | EL PECO SUB | Storage | 4.99 | 10/4/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-09-21 10:50 | 3631-WD | DGSP | DGSP | Withdrawn | 10/31/2025 | Withdrawn | Withdrawn | MADERA | EL PECO SUB | Storage | 4.99 | 10/4/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-09-21 11:23 | 3632-WD | DGSP | DGSP | Active | 11/3/2025 |  |  | SUTTER | LIVE OAK SUB | TBD | 4.99 | 10/4/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-09-21 11:39 | 3633-WD | DGSP | DGSP | Active | 10/1/2025 |  |  | SUTTER | EAST NICOLAUS SUB | Solar PV | 4.99 | 10/4/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-09-21 12:07 | 3634-WD | DGSP | Independent Study | Active | 10/1/2025 |  |  | KERN | RIO BRAVO SUB | Storage | 4.99 | 10/4/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | In Progress |  |  | No former queue position
2023-09-22 09:56 | 3635-WD | DGSP | DGSP | Withdrawn | 10/1/2025 | Withdrawn | Withdrawn | KINGS | LEMOORE SUB | Solar PV | 4.999 | 10/4/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-09-22 12:55 | 3636-WD | DGSP | DGSP | Withdrawn | 10/1/2025 | Withdrawn | Withdrawn | KERN | WESTPARK SUB | Storage | 4.999 | 10/4/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-09-22 13:09 | 3637-WD | DGSP | DGSP | Withdrawn | 10/1/2025 | Withdrawn | Withdrawn | KERN | WESTPARK SUB | Storage | 4.999 | 10/4/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-09-22 13:19 | 3638-WD | DGSP | DGSP | Withdrawn | 10/1/2025 | Withdrawn | Withdrawn | KERN | WESTPARK SUB | Storage | 4.999 | 10/4/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-09-22 13:43 | 3639-WD | DGSP | DGSP | Withdrawn | 3/3/2025 | Withdrawn | Withdrawn | KERN | WESTPARK SUB | Storage | 4.999 | 10/4/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-09-22 13:46 | 3640-WD | DGSP | DGSP | Active | 10/1/2025 |  |  | KERN | MIDWAY SUB | Solar PV | 4.99 | 10/4/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-09-11 14:39 | 3641-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | YOLO | WINTERS SUB | Solar PV | 5 | 10/4/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-09-11 14:42 | 3642-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | CARUTHERS SUB | TBD | 6.895 | 10/4/2023 | 10/31/2023 | Fail Screens: F, J, K, M | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-08-10 00:49 | 3643-WD | Independent Study | Independent Study | Active | 11/8/2024 |  |  | KERN | TUPMAN SUB | Solar PV | 6.432 | 10/11/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | In Progress |  |  | No former queue position
2023-09-07 13:19 | 3644-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | FRESNO | KINGSBURG SUB | Storage | 3.607 | 10/11/2023 | 10/27/2023 | Fail Screens: F, J, K, M, V1, V2, S5, A1 | 1/11/2024 | Fail | Fail |  |  |  | No former queue position
2023-08-09 13:41 | 3645-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN JOAQUIN | AVENA SUB | Solar PV | 2 | 10/11/2023 | 3/19/2024 | Fail Screens: F, I, J, K, L, M, V1, V2, S5, A1 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-09-11 18:31 | 3646-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | CAMDEN SUB | Solar PV | 5 | 10/11/2023 | 11/29/2023 | Fail Screens: F, J, K, M, V1, V2, S5, A1 | 1/18/2024 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-09-18 11:07 | 3647-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | CHOWCHILLA SUB | Storage | 5 | 10/11/2023 | 10/31/2023 | Fail Screens: B, D, F, G, I, J, K, M, V1, V2, S5, A1 | 12/20/2023 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-09-18 09:23 | 3648-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | FAMOSO SUB | Solar PV | 5 | 10/11/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-09-22 12:11 | 3649-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | COARSEGOLD SUB | Solar PV | 4.98 | 10/11/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-09-18 16:05 | 3650-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | GIFFEN SUB | Solar PV | 5 | 10/11/2023 | 10/30/2023 | Fail Screens: F, J, K, M, S5, A1 | 1/10/2024 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-09-18 10:21 | 3651-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | CHARCA SUB | Solar PV | 2 | 10/11/2023 | 12/24/2023 | Fail Screens: D, F, G, J, K, M, V1, S5, A1 | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-09-20 12:00 | 3652-WD | Independent Study | Cluster | Active | 7/1/2025 |  |  | FRESNO | COALINGA #2 SUB | Solar PV | 3.6 | 10/11/2023 | N/A | N/A (Cluster) | N/A | N/A (Cluster) | Fail |  |  |  | No former queue position
2023-09-20 12:17 | 3653-WD | Independent Study | Cluster | Active | 7/1/2025 |  |  | FRESNO | COALINGA #2 SUB | Storage | 3.6 | 10/11/2023 | N/A | N/A (Cluster) | N/A | N/A (Cluster) | Fail |  |  |  | No former queue position
2023-09-21 10:24 | 3654-WD | Fast Track | Independent Study | Active | 2/3/2025 |  |  | KERN | MAGUNDEN SUB | Storage | 4 | 10/18/2023 | 11/14/2023 | Fail Screens: 2, 4, 5, 6, 7, 9, 10 | 1/24/2024 | Fail |  |  |  |  | No former queue position
2023-10-04 12:26 | 3655-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | LIVINGSTON SUB | Solar PV | 2 | 10/18/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-09-18 12:01 | 3656-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | TULARE | STONE CORRAL SUB | Solar PV | 3.7 | 10/18/2023 | 11/9/2023 | Fail Screens: F, J, K, L, M, V1, V2, S5, A1 | 1/24/2024 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-09-27 07:53 | 3657-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | YUBA | OLIVEHURST SUB | Storage | 3.984 | 10/18/2023 | N/A | N/A | N/A | N/A | Pass |  |  |  | No former queue position
2023-08-28 15:54 | 3658-WD | Independent Study | Independent Study | Active | 6/3/2024 |  |  | NAPA | CALISTOGA SUB | Battery | 11.3 | 10/18/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | In Progress |  |  | No former queue position
2023-10-04 15:01 | 3659-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SACRAMENTO | COLONY SUB | Storage | 2 | 10/18/2023 | N/A | N/A | N/A | N/A | Pass |  |  |  | No former queue position
2023-10-05 08:19 | 3660-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | DAIRYLAND SUB | Solar PV | 5 | 10/25/2023 | 11/13/2023 | Fail Screens: D, F, G, I, J, K, L, M, V1, V2, S5, A1 | 1/10/2024 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-09-19 15:09 | 3661-RD | Fast Track | Fast Track | Active | Not Provided |  |  | CONTRA COSTA | EL CERRITO G SUB | Battery | 0.775 | 10/25/2023 | 12/12/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-09-27 12:36 | 3662-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | AVENAL SUB | Solar PV | 3 | 10/25/2023 | 11/21/2023 | Fail Screens: F, J, K, M, V1, V2, S5, A1 | 1/18/2024 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-10-04 15:01 | 3663-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | CRESSEY SUB | Solar PV | 4 | 10/25/2023 | 11/15/2023 | Fail Screens: B, D, F, G, I, J, K, M, V1, V2, S5, A1 | 1/18/2024 | Fail | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-09-28 08:44 | 3664-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | WEST FRESNO SUB | Solar PV | 5 | 10/25/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-09-28 10:00 | 3665-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | FIGARDEN SUB | Solar PV | 5 | 10/25/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-09-29 09:56 | 3666-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | YOLO | WEST SACRAMENTO SUB | Cogeneration | 5 | 10/25/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-09-29 10:17 | 3667-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | MERCED SUB | Cogeneration | 5 | 10/25/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-09-29 10:53 | 3668-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | MERCED SUB | Battery | 5 | 10/25/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-09-29 11:09 | 3669-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | WEST FRESNO SUB | Cogeneration | 5 | 10/25/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-09-29 11:33 | 3670-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | CHOWCHILLA SUB | Battery | 5 | 10/25/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-10-05 15:56 | 3671-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | WOODWARD SUB | Solar PV | 3.24 | 11/1/2023 | 2/22/2024 | Fail Screens: D, F, G, H, J, K, L, M, V1, S5, A1 | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-10-06 13:50 | 3672-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | SANGER SUB | TBD | 3 | 11/1/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-10-12 16:53 | 3673-WD | Independent Study | Cluster | Active | 12/31/2025 |  |  | KERN | MIDWAY SUB | Battery | 20 | 11/1/2023 | N/A | N/A (Cluster) | N/A | N/A (Cluster) | Fail |  |  |  | No former queue position
2023-10-13 13:24 | 3674-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | COARSEGOLD SUB | Storage | 5 | 11/1/2023 | 11/22/2023 | Fail Screens: B, D, F, H, I, J, K, M, V1, V2, S5, A1 | 1/18/2024 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-10-17 13:27 | 3675-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | YOLO | MADISON SUB | Solar PV | 5.511 | 11/1/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-09-29 14:09 | 3676-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | TULARE | STONE CORRAL SUB | Solar PV | 4.999 | 11/1/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-10-04 08:05 | 3677-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | LIVINGSTON SUB | TBD | 5 | 11/1/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-10-12 13:50 | 3678-RD | Fast Track | Fast Track | Active | Not Provided |  |  | MONTEREY | GREEN VALLEY SUB | Battery | 0.5 | 11/1/2023 | 12/28/2023 | Fail Screens: B, F, G, H, I, J, M, S5 | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-10-12 13:51 | 3679-RD | Fast Track | Fast Track | Active | Not Provided |  |  | MONTEREY | GREEN VALLEY SUB | Battery | 0.25 | 11/1/2023 | 1/8/2024 | Fail Screens: B, D, I, J, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2023-10-16 16:16 | 3680-WD | Independent Study | Independent Study | Active | 5/15/2025 |  |  | BUTTE | NOTRE DAME SUB | Solar PV | 4.99 | 11/1/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass |  |  |  | No former queue position
2023-10-17 20:51 | 3681-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | TEMBLOR SUB | Solar PV | 3 | 11/1/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-10-18 12:26 | 3682-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | CUYAMA SUB | Solar PV | 5.511 | 11/1/2023 | N/A | N/A | N/A | N/A | Pass |  |  |  | No former queue position
2023-09-05 11:29 | 3683-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | LERDO SUB | Solar PV | 3.26 | 11/8/2023 | 12/27/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-09-29 14:56 | 3684-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | CAMDEN SUB | Solar PV | 5 | 11/8/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-10-19 16:16 | 3685-WD | Independent Study | Independent Study | Active | 5/30/2025 |  |  | LAKE | KONOCTI SUB | Solar PV | 13.298 | 11/8/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass | In Progress |  |  | No former queue position
2023-09-25 10:54 | 3686-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | COLUSA | CORTINA SUB | Solar PV | 5 | 11/8/2023 | 12/27/2023 | Fail Screens: B, D, F, G, I, J, K, M, V1, V2, S5, A1 | 2/16/2024 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-10-12 16:06 | 3687-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | TUOLUMNE | PEORIA SUB | Solar PV | 1 | 11/8/2023 | 12/27/2023 | Fail Screens: D, F, J, K, L, M, S5 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-10-17 10:38 | 3688-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | MCMULLIN SUB | Solar PV | 5 | 11/8/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-10-18 16:46 | 3689-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KINGS | HARDWICK SUB | Solar PV | 3 | 11/8/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-10-19 08:21 | 3690-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | MCMULLIN SUB | Storage | 5 | 11/8/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-10-24 13:23 | 3691-RD | Detailed Study | DGSP | Active | Not Provided |  |  | SAN LUIS OBISPO | TEMPLETON SUB | Reciprocating Engine | 4.98 | 11/8/2023 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2023-10-24 13:34 | 3692-RD | Detailed Study | DGSP | Active | Not Provided |  |  | SAN JOAQUIN | VICTOR SUB | Storage | 4.98 | 11/8/2023 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2023-10-25 17:50 | 3693-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | GANSO SUB | Reciprocating Engine,Solar PV | 0.775 | 11/8/2023 | 1/29/2024 | Fail Screens: F, I, J, K, M | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-10-26 12:57 | 3694-WD | Fast Track | Fast Track | Active | 12/31/2025 |  |  | KERN | KERN OIL SUB | Storage | 2 | 11/8/2023 | 12/28/2023 | Fail Screens: 2, 4, 5, 7, 9, 10 | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-10-13 13:35 | 3695-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | ELK HILLS SUB | TBD | 4 | 11/8/2023 | 12/7/2023 | Fail | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-10-16 10:13 | 3696-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | OLD KEARNEY SUB | TBD | 3 | 11/8/2023 | 11/30/2023 | Fail Screens: F, J, K, M, V1, V2, S5, A1 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-10-17 21:13 | 3697-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SUTTER | TUDOR SUB | Solar PV | 1.996 | 11/8/2023 | 3/27/2024 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-10-17 23:42 | 3698-RD | Fast Track | Fast Track | Active | Not Provided |  |  | BUTTE | PEACHTON SUB | TBD | 3 | 11/8/2023 | In Progress |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-10-18 12:26 | 3699-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | CASSIDY SUB | Storage | 4.98 | 11/8/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-10-18 22:44 | 3700-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | CHOWCHILLA SUB | Storage | 3 | 11/8/2023 | 11/29/2023 | Fail Screens: D, F, G, I, J, K, L, M, V1, V2, S5, A1 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-10-19 10:10 | 3701-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | DAIRYLAND SUB | Storage | 1 | 11/8/2023 | 11/29/2023 | Fail Screens: D, F, G, I, J, K, L, M, V1, V2, S5, A1 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-10-30 13:11 | 3702-WD | Cluster | Cluster | Active | 7/1/2025 |  |  | SANTA CLARA | AMES DIST SUB | Battery | 8.7444 | 11/8/2023 | N/A | N/A (Cluster) | N/A | N/A (Cluster) | N/A (Cluster) |  |  |  | No former queue position
2023-10-16 00:18 | 3703-WD | Independent Study | Independent Study | Withdrawn | 12/20/2024 | Withdrawn | Withdrawn | FRESNO | FIREBAUGH SUB | Solar PV | 4.95 | 11/15/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-10-19 16:13 | 3704-WD | Independent Study | Independent Study | Active | 5/30/2025 |  |  | PLACER | PENRYN SUB | Storage | 8.5 | 11/15/2023 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass |  |  |  | No former queue position
2023-10-26 13:36 | 3705-RD | Detailed Study | DGSP | Active | Not Provided |  |  | MONTEREY | LOS OSITOS SUB | Storage | 2.4 | 11/15/2023 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2023-10-23 17:11 | 3706-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN JOAQUIN | TRACY SUB | Storage | 1.285 | 11/15/2023 | 1/2/2024 | Fail Screens: F, G, I, J, M, S5 | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-10-27 11:50 | 3707-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SONOMA | MONROE SUB | Solar PV | 0.9 | 11/22/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-10-23 09:40 | 3708-RD | Fast Track | Fast Track | Active | Not Provided |  |  | COLUSA | COLUSA SUB | Reciprocating Engine | 3 | 11/22/2023 | 1/5/2024 | Fail Screens: B, D, F, I, J, K, M, V1, S5, A1 | 3/21/2024 | Fail | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-10-24 12:05 | 3709-RD | Fast Track | Detailed Study | Active | Not Provided |  |  | MONTEREY | SOLEDAD SUB | Other | 1.266 | 11/22/2023 | 1/10/2024 | Fail Screens: F, G, H, I, J, K, M, S5 | 2/8/2024 | Fail | Pass |  |  |  | No former queue position
2023-10-26 19:31 | 3710-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | TEMBLOR SUB | Storage | 4 | 11/22/2023 | 12/24/2023 | Fail Screens: B, D, F, G, I, J, K, M, V1, V2, S5, A1 | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-10-26 21:27 | 3711-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | BOWLES SUB | Storage | 0.996 | 11/22/2023 | 12/26/2023 | Fail Screens: B, D, F, I, J, K, M, V1, V2, S5, A1 | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-10-30 17:46 | 3712-RD | Fast Track | Fast Track | Active | Not Provided |  |  | TEHAMA | LOS MOLINOS SUB | Storage | 0.996 | 11/22/2023 | In Progress |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-10-30 22:53 | 3713-RD | Fast Track | Fast Track | Active | Not Provided |  |  | MADERA | EL PECO SUB | Storage | 0.996 | 11/22/2023 | 12/14/2023 | Fail Screens: B, D, F, G, I, J, K, L, M, V1, V2, S5, A1 | 3/5/2024 | Fail | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-11-01 17:49 | 3714-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN JOAQUIN | VALLEY HOME SUB | Storage | 0.996 | 11/22/2023 | 12/26/2023 | Fail Screens: B, D, F, G, I, J, K, L, M, V1, V2, S5, A1 | 3/5/2024 | Fail | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-11-01 19:18 | 3715-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | SMYRNA SUB | Storage | 0.996 | 11/22/2023 | 12/19/2023 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-11-01 20:54 | 3716-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | GLENN | RICE SUB | Storage | 0.996 | 11/22/2023 | 1/9/2024 | Fail Screens: B, D, F, I, J, K, L, M, V1, V2, S5, A1 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-11-03 16:43 | 3717-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | SHAFTER SUB | Storage | 0.7 | 11/22/2023 | 12/28/2023 | Fail Screens: F, I, J, K, M | 3/11/2024 | Pass | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-11-02 16:49 | 3718-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA CLARA | EL PATIO SUB | Battery | 0.979 | 11/22/2023 | 1/31/2024 | Fail Screens: J, K, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-11-09 13:42 | 3719-WD | Cluster | Cluster | Active | 11/3/2025 |  |  | KINGS | GUERNSEY SUB | Solar PV | 2.34 | 11/29/2023 | N/A | N/A (Cluster) | N/A | N/A (Cluster) | N/A (Cluster) |  |  |  | No former queue position
2023-11-10 15:16 | 3720-WD | Cluster | Cluster | Active | 12/5/2025 |  |  | FRESNO | STROUD SUB | Solar PV | 5 | 11/29/2023 | N/A | N/A (Cluster) | N/A | N/A (Cluster) | N/A (Cluster) |  |  |  | No former queue position
2023-11-16 16:30 | 3721-RD | Fast Track | Fast Track | Active | Not Provided |  |  | LAKE | CLEAR LAKE SUB | Solar PV | 0.979 | 12/6/2023 | 1/24/2024 | Fail Screens: D, F, G, I, J, K, M, V1, V2, S5, A1 | 2/16/2024 | Fail | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-11-07 13:14 | 3722-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | MENDOCINO | BIG RIVER SUB | Solar PV | 2 | 12/6/2023 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-11-08 08:13 | 3723-RD | Fast Track | Fast Track | Active | Not Provided |  |  | ALAMEDA | CASTRO VALLEY SUB | Solar PV | 0.982 | 12/6/2023 | 1/29/2024 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-11-15 14:22 | 3724-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | YUBA | OLIVEHURST SUB | Solar PV | 5.511 | 12/6/2023 | N/A | N/A | N/A | N/A | Pass |  |  |  | No former queue position
2023-11-15 14:30 | 3725-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | AMADOR | CLAY SUB | Solar PV | 5.511 | 12/6/2023 | N/A | N/A | N/A | N/A | Pass |  |  |  | No former queue position
2023-11-14 11:17 | 3726-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | KERMAN SUB | Solar PV | 4.6 | 12/6/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-11-14 13:43 | 3727-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | EL PECO SUB | Solar PV | 4.6 | 12/6/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-11-14 15:28 | 3728-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | EL NIDO SUB | Solar PV | 4.6 | 12/6/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-11-15 08:22 | 3729-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | MADERA | DAIRYLAND SUB | Solar PV | 4.6 | 12/6/2023 | [8 empty] | No former queue position
2023-11-15 09:16 | 3730-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | MERCED | MERCED SUB | Solar PV | 4.6 | 12/6/2023 | [8 empty] | No former queue position
2023-11-15 11:16 | 3731-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KINGS | JACOBS CORNER SUB | Solar PV | 4.6 | 12/6/2023 | [8 empty] | No former queue position
2023-11-15 11:38 | 3732-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | MADERA | EL PECO SUB | Solar PV | 4.6 | 12/6/2023 | [8 empty] | No former queue position
2023-11-15 12:30 | 3733-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | FRESNO | COALINGA #1 SUB | Storage | 5 | 12/6/2023 | [8 empty] | No former queue position
2023-11-15 12:53 | 3734-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | LERDO SUB | Storage | 5 | 12/6/2023 | [8 empty] | No former queue position
2023-11-15 12:57 | 3735-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | LERDO SUB | Storage | 5 | 12/6/2023 | [8 empty] | No former queue position
2023-11-15 14:16 | 3736-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | LERDO SUB | Storage | 5 | 12/6/2023 | [8 empty] | No former queue position
2023-11-16 14:52 | 3737-WD | Independent Study | Independent Study | Withdrawn | 8/15/2025 | Withdrawn | Withdrawn | CALAVERAS | CORRAL SUB | Solar PV | 2.5 | 12/13/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-11-29 14:10 | 3738-RD | Detailed Study | DGSP | Active | Not Provided |  |  | TEHAMA | RED BLUFF SUB | Solar PV | 4.98 | 12/13/2023 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2023-11-07 16:41 | 3739-RD | Fast Track | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MERCED | CRESSEY SUB | Solar PV | 4 | 12/13/2023 | 1/5/2024 | Fail Screens: B, D, F, G, I, J, K, M, V1, V2, S5, A1 | 2/27/2024 | Fail | Pass | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-11-21 14:16 | 3740-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | CALIFORNIA AVE SUB | Battery | 1.285 | 12/13/2023 | 3/1/2024 | Fail Screens: J, V1, S5, A1 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-11-21 14:18 | 3741-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | CALIFORNIA AVE SUB | Storage | 1.285 | 12/13/2023 | 3/1/2024 | Fail Screens: D, F, G, I, J, M, V1, S5, A1 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-11-20 15:30 | 3742-RD | Fast Track | Fast Track | Active | Not Provided |  |  | MADERA | BORDEN SUB | Solar PV | 3 | 12/20/2023 | 1/12/2024 | Fail Screens: B, D, F, G, I, J, K, M, V1, V2, S5, A1 | 3/11/2024 | Fail | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-11-18 09:41 | 3743-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN MATEO | EAST GRAND SUB | Solar PV | 1.272 | 12/20/2023 | 1/12/2024 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-12-06 10:16 | 3744-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SOLANO | VACA DIXON SUB | Solar PV | 3 | 12/20/2023 | 1/26/2024 | Fail Screens: B, D, F, I, J, K, M, V1, V2, S5, A1, R1 | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-11-23 10:11 | 3745-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | GOOSE LAKE SUB | Solar PV | 18.675 | 12/20/2023 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2023-11-03 15:43 | 3746-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | GATES SUB | Solar PV | 19.936 | 12/20/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-11-03 16:00 | 3747-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | YOLO | PUTAH CREEK SUB | Solar PV | 19.936 | 12/20/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-11-07 17:02 | 3748-RD | Fast Track | Fast Track | Active | Not Provided |  |  | COLUSA | COLUSA SUB | Solar PV | 19.936 | 12/20/2023 | 1/29/2024 | Fail | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-11-09 12:29 | 3749-WD | Cluster | Cluster | Active | 12/1/2028 |  |  | KINGS | AVENAL SUB | Battery | 50.403 | 12/20/2023 | N/A | N/A (Cluster) | N/A | N/A (Cluster) | N/A (Cluster) |  |  |  | No former queue position
2023-10-23 18:00 | 3750-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN JOAQUIN | TRACY SUB | Storage | 1.285 | 12/27/2023 | 3/12/2024 | Fail Screens: F, G, I, J, M, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-11-15 13:29 | 3751-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | CHOWCHILLA SUB | Storage | 5 | 12/27/2023 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-12-08 16:25 | 3752-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN JOAQUIN | CARBONA SUB | Storage | 0.642 | 12/27/2023 | 3/19/2024 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Tendered | No former queue position
2023-12-12 12:39 | 3753-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN JOAQUIN | CARBONA SUB | Storage | 2.056 | 12/27/2023 | In Progress |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-11-03 11:26 | 3754-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | LAKE | MIDDLETOWN SUB | Solar PV | 4.98 | 1/3/2024 | N/A | N/A | N/A | N/A | Pass |  |  |  | No former queue position
2023-12-08 12:46 | 3755-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | CONTRA COSTA | BALFOUR SUB | Solar PV | 4.98 | 1/3/2024 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2023-12-11 10:09 | 3756-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | CAMDEN SUB | Solar PV | 4.99 | 1/3/2024 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-12-12 16:45 | 3757-WD | Independent Study | Independent Study | Active | 12/31/2025 |  |  | AMADOR | PINE GROVE SUB | Solar PV | 3.875 | 1/3/2024 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass |  |  |  | No former queue position
2023-12-14 19:08 | 3758-RD | Detailed Study | DGSP | Active | Not Provided |  |  | MONTEREY | SOLEDAD SUB | Solar PV | 4.98 | 1/3/2024 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2023-12-07 19:10 | 3759-RD | Fast Track | Fast Track | Active | Not Provided |  |  | TUOLUMNE | CURTIS SUB | Battery | 0.12 | 1/10/2024 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-12-06 09:46 | 3760-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | SAND CREEK SUB | Solar PV | 5 | 1/10/2024 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-12-20 12:19 | 3761-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | SHAFTER SUB | Solar PV | 5 | 1/10/2024 | 1/31/2024 | Fail Screens: B, D, F, G, I, J, K, M, V1, V2, S5, A1, R1 | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-12-20 17:14 | 3762-RD | Fast Track | Fast Track | Active | Not Provided |  |  | TUOLUMNE | RACETRACK SUB | Solar PV | 4 | 1/10/2024 | 2/2/2024 | Fail Screens: B, D, F, G, I, J, K, L, M, V1, V2, S5, A1 | 3/28/2024 | Fail | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-12-21 10:06 | 3763-RD | Fast Track | Fast Track | Active | Not Provided |  |  | STANISLAUS | COTTLE SUB | Solar PV | 5 | 1/10/2024 | 2/2/2024 | Fail Screens: B, D, F, G, I, J, K, L, M, V1, V2, S5, A1, R1 | 3/13/2024 | Fail | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-12-22 11:47 | 3764-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | COLUSA | RICE SUB | Solar PV | 5 | 1/10/2024 | N/A | N/A | N/A | N/A | Pass | In Progress |  |  | No former queue position
2023-12-14 13:50 | 3765-WD | Independent Study | Independent Study | Active | 12/20/2024 |  |  | KERN | GOOSE LAKE SUB | Solar PV | 4.95 | 1/10/2024 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Fail |  |  |  | No former queue position
2023-12-14 16:05 | 3766-WD | Independent Study | DGSP | Active | 1/19/2026 |  |  | AMADOR | CLAY SUB | Solar PV | 4.5 | 1/10/2024 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2023-12-19 12:04 | 3767-WD | Independent Study | Independent Study | Active | 1/16/2026 |  |  | LAKE | CLEAR LAKE SUB | Storage | 3 | 1/10/2024 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Fail |  |  |  | No former queue position
2023-12-14 09:59 | 3768-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | GANSO SUB | Storage | 4 | 1/10/2024 | 2/5/2024 | Fail Screens: J, K, M | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-12-20 13:22 | 3769-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | GOOSE LAKE SUB | Storage | 5 | 1/10/2024 | 2/5/2024 | Fail Screens: I, J, K, M | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-12-13 12:14 | 3770-WD | Independent Study | Independent Study | Active | 12/30/2024 |  |  | FRESNO | GATES SUB | Solar PV | 4.954 | 1/17/2024 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Fail |  |  |  | No former queue position
2023-12-22 09:11 | 3771-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | SAN JOAQUIN | VICTOR SUB | Solar PV | 6.923 | 1/17/2024 | 2/20/2024 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-12-22 11:38 | 3772-RD | Fast Track | Fast Track | Active | Not Provided |  |  | COLUSA | COLUSA JUNCTION | Storage | 5 | 1/17/2024 | 2/8/2024 | Fail Screens: B, D, F, I, J, K, L, M, V1, V2, S5, A1 | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-12-23 20:48 | 3773-RD | Fast Track | Fast Track | Active | Not Provided |  |  | GLENN | LOGAN CREEK SUB | Solar PV | 5 | 1/17/2024 | In Progress |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-12-19 12:12 | 3774-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN JOAQUIN | MANTECA SUB | Solar PV | 4.62 | 1/17/2024 | In Progress |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-12-19 17:05 | 3775-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | BOWLES SUB | Solar PV | 5 | 1/17/2024 | 2/20/2024 | Fail Screens: D, F, G, I, J, K, M, V1, V2, S5, A1 | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-12-19 17:51 | 3776-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | COALINGA #2 SUB | Solar PV | 4.25 | 1/17/2024 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-12-19 19:19 | 3777-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | MCFARLAND SUB | Solar PV | 4.98 | 1/17/2024 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2023-12-19 19:20 | 3778-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | MCFARLAND SUB | Solar PV | 4.98 | 1/17/2024 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2023-12-20 07:21 | 3779-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | MCFARLAND SUB | Storage | 4.98 | 1/17/2024 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2023-12-22 12:06 | 3780-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SANTA BARBARA | CUYAMA SUB | Storage | 5 | 1/17/2024 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2024-01-02 16:00 | 3781-WD | Independent Study | Independent Study | Active | 12/20/2024 |  |  | KERN | TEMBLOR SUB | Solar PV | 2.4 | 1/17/2024 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) |  |  |  |  | No former queue position
2024-01-02 17:02 | 3782-WD | Independent Study | Independent Study | Active | 12/20/2024 |  |  | KERN | BLACKWELL SUB | Solar PV | 2.4 | 1/17/2024 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) |  |  |  |  | No former queue position
2024-01-03 09:51 | 3783-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | CARUTHERS SUB | Solar PV | 4.99 | 1/17/2024 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-12-20 07:32 | 3784-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | MCFARLAND SUB | Storage | 4.98 | 1/17/2024 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2023-12-22 15:30 | 3785-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | MCMULLIN SUB | Battery | 0.057 | 1/24/2024 | 2/14/2024 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) | Executed | No former queue position
2024-01-09 07:50 | 3786-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | MADERA | STOREY SUB | Solar PV | 4.98 | 1/24/2024 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2024-01-09 23:59 | 3787-WD | Independent Study | Independent Study | Active | 12/31/2025 |  |  | KERN | KERN OIL SUB | Solar PV | 4.95 | 1/24/2024 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Fail |  |  |  | No former queue position
2023-12-29 11:17 | 3788-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | MARICOPA SUB | Storage | 4.98 | 1/24/2024 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2023-12-22 11:02 | 3789-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN JOAQUIN | LAMMERS SUB | Storage | 1.828 | 1/31/2024 | In Progress |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-01-04 11:15 | 3790-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | FRESNO | WAHTOKE SUB | Solar PV | 2.468 | 1/31/2024 | N/A | N/A | N/A | N/A | Pass |  |  |  | No former queue position
2024-01-08 09:37 | 3791-WD | Independent Study | Independent Study | Active | 9/16/2024 |  |  | PLACER | LINCOLN SUB | Storage | 0.996 | 1/31/2024 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Pass |  |  |  | No former queue position
2024-01-08 16:54 | 3792-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | LERDO SUB | Solar PV | 4.927 | 1/31/2024 | 2/27/2024 | Fail Screens: D, G, H, I, J, K, M, V1, V2, S5, A1 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-01-09 14:57 | 3793-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | STROUD SUB | Storage | 5 | 1/31/2024 | 3/4/2024 | Fail Screens: F, J, K, M, V1, S5, A1 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-01-09 15:06 | 3794-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA BARBARA | CUYAMA SUB | Solar PV | 5 | 1/31/2024 | 2/22/2024 | Fail | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-12-22 16:27 | 3795-RD | Fast Track | Fast Track | Active | Not Provided |  |  | MERCED | CANAL SUB | Solar PV | 1.642 | 1/31/2024 | 2/22/2024 | Fail Screens: D, F, G, J, K, M, S5 | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-01-09 08:36 | 3796-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | COPPERMINE SUB | Storage | 5 | 1/31/2024 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2024-01-09 12:19 | 3797-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | BOWLES SUB | Storage | 2.988 | 1/31/2024 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2023-12-06 05:12 | 3798-WD | Independent Study | Independent Study | Active | 5/29/2026 |  |  | FRESNO | REEDLEY SUB | Battery | 9.525 | 1/31/2024 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Fail |  |  |  | No former queue position
2024-01-05 12:27 | 3799-RD | Detailed Study | DGSP | Active | Not Provided |  |  | GLENN | LOGAN CREEK SUB | Solar PV | 4.98 | 1/31/2024 | N/A | N/A | N/A | N/A | Pass |  |  |  | No former queue position
2024-01-18 21:04 | 3800-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | GOOSE LAKE SUB | Storage | 5 | 1/31/2024 | 2/22/2024 | Fail Screens: A, C, D, F, G, I, J, K, L, M, V1, S5, A1 | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-12-05 16:00 | 3801-WD | Independent Study | Independent Study | In Service | 12/13/2023 | 5/30/2023 | 11/16/2023 | SANTA BARBARA | CUYAMA SUB | Battery | 3 | 1/31/2024 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Fail |  |  |  | No former queue position
2023-12-08 11:25 | 3802-WD | Independent Study | Independent Study | Active | 5/29/2026 |  |  | KERN | LAMONT SUB | TBD | 9.525 | 1/31/2024 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) |  |  |  |  | No former queue position
2024-01-18 15:55 | 3803-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | FRESNO | CARUTHERS SUB | Storage | 9.167 | 1/31/2024 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2023-12-28 16:13 | 3804-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | WAHTOKE SUB | Solar PV | 1 | 2/7/2024 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-12-29 17:14 | 3805-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN JOAQUIN | MORMON SUB | Solar PV | 0.966 | 2/7/2024 | 3/12/2024 | Fail Screens: D, F, G, J, K, L, M, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-01-18 15:52 | 3806-WD | Fast Track | Fast Track | Active | 4/30/2025 |  |  | HUMBOLDT | BLUE LAKE SUB | Solar PV | 1.222 | 2/7/2024 | 2/23/2024 | Fail Screens: 2, 4, 7, 9, 10 | In Progress |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-01-25 09:54 | 3807-WD | Fast Track | Fast Track | Active | 7/1/2024 |  |  | ALAMEDA | EDES SUB | Battery | 0.5 | 2/7/2024 | 3/6/2024 | Fail Screens: 2 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-01-16 01:25 | 3808-WD | Independent Study | Independent Study | Active | 12/20/2024 |  |  | SOLANO | SUISUN SUB | Solar PV | 4.95 | 2/7/2024 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Fail |  |  |  | No former queue position
2024-01-25 11:14 | 3809-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | BUTTE | CLARK RD SUB | Storage | 5 | 2/7/2024 | N/A | N/A | N/A | N/A | Pass |  |  |  | No former queue position
2024-01-22 13:25 | 3810-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | LERDO SUB | Solar PV | 4.98 | 2/7/2024 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2024-01-19 14:12 | 3811-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | WHEELER RIDGE SUB | Solar PV | 4.98 | 2/14/2024 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2023-12-19 16:10 | 3812-RD | Fast Track | Fast Track | Active | Not Provided |  |  | MERCED | ORTIGA SUB | Solar PV | 0.9 | 2/14/2024 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-01-04 17:54 | 3813-RD | Fast Track | Fast Track | Active | Not Provided |  |  | MADERA | TRANSMISSION | Solar PV | 2.772 | 2/14/2024 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-01-22 15:37 | 3814-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | MONTEREY | OIL FIELDS SUB | Storage | 5 | 2/14/2024 | N/A | N/A | N/A | N/A | Pass |  |  |  | No former queue position
2024-01-22 17:20 | 3815-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | MENDOCINO | LAYTONVILLE SUB | Storage | 5 | 2/14/2024 | N/A | N/A | N/A | N/A | Pass |  |  |  | No former queue position
2024-01-23 15:04 | 3816-WD | Independent Study | Independent Study | Active | 11/14/2025 |  |  | KERN | CARNERAS SUB | Solar PV | 4.673 | 2/14/2024 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Fail |  |  |  | No former queue position
2024-01-26 14:33 | 3817-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN JOAQUIN | VICTOR SUB | Battery | 2.988 | 2/21/2024 | 3/13/2024 | Pass |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-02-02 11:31 | 3818-RD | Fast Track | Fast Track | Active | Not Provided |  |  | CALAVERAS | CALAVERAS CEMENT SUB | Solar PV | 3 | 2/21/2024 | 3/5/2024 | Fail Screens: B, I, J, K, M, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-02-02 09:15 | 3819-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | REEDLEY SUB | Solar PV | 1.27 | 2/21/2024 | 3/27/2024 | Fail Screens: D, J, K, M, S5 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-02-03 12:30 | 3820-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | STROUD SUB | Storage | 5 | 2/21/2024 | In Progress |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-02-03 12:55 | 3821-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA BARBARA | CUYAMA SUB | Solar PV | 5 | 2/21/2024 | 3/29/2024 | Fail Screens: D, F, I, J, K, L, M, V1, S5, A1 |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2023-12-21 15:01 | 3822-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | FRESNO | CARUTHERS SUB | Storage | 5 | 2/28/2024 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2024-02-01 12:51 | 3823-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | CARNERAS SUB | Storage | 4.98 | 2/28/2024 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2024-02-01 13:13 | 3824-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | MERCED | EL CAPITAN SUB | Battery | 4.98 | 2/28/2024 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2024-02-09 08:51 | 3825-WD | Independent Study | Cluster | Active | 3/13/2026 |  |  | MADERA | CHOWCHILLA SUB | Solar PV | 4.99 | 2/28/2024 | N/A | N/A (Cluster) | N/A | N/A (Cluster) | Fail |  |  |  | No former queue position
2024-02-01 13:24 | 3826-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SAN JOAQUIN | AVENA SUB | Storage | 4.98 | 2/28/2024 | N/A | N/A | N/A | N/A | Pass |  |  |  | No former queue position
2023-12-29 12:08 | 3827-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KINGS | GUERNSEY SUB | Battery | 2.196 | 3/6/2024 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-01-09 11:55 | 3828-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SUTTER | CATLETT SUB | Solar PV | 2.988 | 3/6/2024 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2024-02-14 13:01 | 3829-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | WOODWARD SUB | Solar PV | 2.76 | 3/6/2024 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2024-02-05 16:59 | 3830-RD | Detailed Study | Detailed Study | Withdrawn | Not Provided | Withdrawn | Withdrawn | KERN | MIDWAY SUB | Solar PV | 4.98 | 3/6/2024 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Fail | Withdrawn | Withdrawn | Withdrawn | No former queue position
2024-02-12 08:36 | 3831-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | ALAMEDA | NEWARK SUB | Solar PV | 1.599 | 3/6/2024 | N/A | N/A | N/A | N/A | Pass |  |  |  | No former queue position
2024-02-16 07:49 | 3832-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | FRESNO | WEST FRESNO SUB | TBD | 4.98 | 3/6/2024 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2024-02-16 12:01 | 3833-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KERN | TBD | Storage | 4.98 | 3/6/2024 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2024-02-08 10:45 | 3834-RD | Fast Track | Fast Track | Active | Not Provided |  |  | BUTTE | ANITA SUB | Solar PV | 2.93 | 3/6/2024 | In Progress |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-02-08 16:31 | 3835-RD | Fast Track | Fast Track | Active | Not Provided |  |  | BUTTE | ANITA SUB | Solar PV | 2.36 | 3/6/2024 | In Progress |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-02-14 00:22 | 3836-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN JOAQUIN | MORMON SUB | Solar PV | 2.79 | 3/13/2024 | In Progress |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-02-16 15:18 | 3837-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SANTA CRUZ | GREEN VALLEY SUB | Storage | 3.984 | 3/13/2024 | In Progress |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-02-09 16:40 | 3838-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SHASTA | STILLWATER SUB | Solar PV | 0.4 | 3/13/2024 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-02-05 13:26 | 3839-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | MONTEREY | TBD | Solar PV | 6.3 | 3/13/2024 | [8 empty] | No former queue position
2024-02-12 14:43 | 3840-RD | Fast Track | Fast Track | Active | Not Provided |  |  | LAKE | MIDDLETOWN SUB | Solar PV | 2.28 | 3/13/2024 | In Progress |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-02-21 10:32 | 3841-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | MERCED | CRESSEY SUB | Solar PV | 4.98 | 3/13/2024 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2024-01-19 10:14 | 3842-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SAN BENITO | LOS OSITOS SUB | Solar PV | 4.98 | 3/13/2024 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2024-02-12 13:12 | 3843-RD | Fast Track | Fast Track | Active | Not Provided |  |  | SAN JOAQUIN | LAMMERS SUB | Solar PV | 5 | 3/13/2024 | In Progress |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-02-13 15:22 | 3844-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | KINGS | JACOBS CORNER SUB | Solar PV | 2.25 | 3/13/2024 | [8 empty] | No former queue position
2024-02-20 20:03 | 3845-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SAN BENITO | HOLLISTER SUB | Solar PV | 5.595 | 3/13/2024 | In Progress | [7 empty] | No former queue position
2024-02-21 14:14 | 3846-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SANTA CLARA | TBD | TBD | 4.98 | 3/13/2024 | 3/27/2024 | Fail Screens: D, F, H, I, J, K, M | N/A | N/A |  |  |  |  | No former queue position
2024-02-16 11:49 | 3847-RD | Fast Track | Fast Track | Active | Not Provided |  |  | MADERA | TBD | Solar PV | 7.5 | 3/20/2024 | In Progress |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-02-27 14:34 | 3848-RD | Fast Track | Fast Track | Withdrawn | Not Provided | Withdrawn | Withdrawn | FRESNO | BOWLES SUB | Solar PV | 4.98 | 3/20/2024 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | Withdrawn | No former queue position
2024-02-29 09:17 | 3849-WD | Independent Study | Independent Study | Active | 2/2/2026 |  |  | MERCED | CRESSEY SUB | Solar PV | 2 | 3/20/2024 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) | Fail |  |  |  | No former queue position
2024-02-14 17:06 | 3850-RD | Fast Track | Fast Track | Active | Not Provided |  |  | TUOLUMNE | TBD | Solar PV | 1.9 | 3/20/2024 | In Progress |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-02-22 08:58 | 3851-RD | Fast Track | Fast Track | Active | Not Provided |  |  | YOLO | WINTERS SUB | Solar PV | 3.75 | 3/20/2024 | In Progress |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-02-28 17:00 | 3852-RD | Fast Track | Fast Track | Active | Not Provided |  |  | CONTRA COSTA | ROSSMOOR SUB | Solar PV | 1.171 | 3/20/2024 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-03-01 | 3853-RD | Detailed Study | DGSP | Active | Not Provided |  |  | FRESNO | FIGARDEN SUB | Solar PV | 5 | 3/20/2024 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2024-03-01 | 3854-RD | Detailed Study | DGSP | Active | Not Provided |  |  | MADERA | CHOWCHILLA SUB | Battery | 5 | 3/20/2024 | N/A | N/A | N/A | N/A |  |  |  |  | No former queue position
2024-03-01 | 3855-RD | Detailed Study | DGSP | Active | Not Provided |  |  | MERCED | MERCED SUB | Solar PV | 5 | 3/20/2024 | N/A | N/A | N/A | N/A |  |  |  |  | No former queue position
2024-03-07 10:19 | 3856-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SAN JOAQUIN | VICTOR SUB | Battery | 5 | 3/27/2024 | [8 empty] | No former queue position
2024-02-27 19:01 | 3857-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | BUTTE | ANITA SUB | Solar PV | 5 | 3/27/2024 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2024-02-27 19:20 | 3858-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | SONOMA | CORONA SUB | Solar PV | 5 | 3/27/2024 | N/A | N/A | N/A | N/A | Fail |  |  |  | No former queue position
2024-02-28 19:52 | 3859-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | TEHAMA | TYLER SUB | Storage | 5 | 3/27/2024 | [8 empty] | No former queue position
2024-03-11 09:19 | 3860-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | LAKEVIEW SUB | Battery | 1.767 | 3/27/2024 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-03-11 09:25 | 3861-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | COPUS SUB | Battery | 1.044 | 3/27/2024 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-03-11 09:43 | 3862-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | LAKEVIEW SUB | Solar PV | 1.124 | 3/27/2024 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-03-11 10:21 | 3863-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | TECUYA SUB | Storage | 0.883 | 3/27/2024 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-03-11 13:30 | 3864-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | COPUS SUB | Storage | 0.803 | 3/27/2024 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-03-11 13:53 | 3865-RD | Fast Track | Fast Track | Active | Not Provided |  |  | KERN | COPUS SUB | Storage | 0.803 | 3/27/2024 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-01-04 08:26 | 3866-WD | Fast Track | Fast Track | Active | 12/31/2024 |  |  | SAN FRANCISCO | SAN FRAN X (MISSION) SUB | Solar PV | 0.083 | 3/27/2024 | In Progress |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-02-14 13:37 | 3867-RD | Fast Track | Fast Track | Active | Not Provided |  |  | MONTEREY | SOLEDAD SUB | Solar PV | 0.96 | 3/27/2024 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-02-14 14:20 | 3868-RD | Fast Track | Fast Track | Active | Not Provided |  |  | FRESNO | CANTUA SUB | Solar PV | 0.9 | 3/27/2024 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-02-23 07:29 | 3869-RD | Fast Track | Fast Track | Active | Not Provided |  |  | LAKE | REDBUD SUB | Storage | 3.912 | 3/27/2024 |  |  |  |  | N/A (Fast Track) | N/A (Fast Track) | N/A (Fast Track) |  | No former queue position
2024-03-12 10:44 | 3870-WD | Independent Study | Independent Study | Active | 12/31/2026 |  |  | EL DORADO | SHINGLE SPRINGS SUB | Solar PV | 5 | 3/27/2024 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) |  |  |  |  | No former queue position
2024-03-14 13:40 | 3871-WD | Independent Study | Independent Study | Active | 12/31/2026 |  |  | EL DORADO | SHINGLE SPRINGS SUB | Solar PV | 5 | 3/27/2024 | N/A | N/A (Independent Study) | N/A | N/A (Independent Study) |  |  |  |  | No former queue position
2024-03-04 10:33 | 3872-RD | Detailed Study | Detailed Study | Active | Not Provided |  |  | FRESNO | REEDLEY SUB | Battery | 4.99 | 3/27/2024 | [8 empty] | No former queue position