## 08J
REQUESTED DATA
Order | Short Text (description) | Circuit Name | Linear ckt ft or miles per project in 2020 | 2020 MPP Approved Budget / Projected cost | Estimated Construction Complete Date | FISD Actualized or Forecasted | 1) Region (Bay, Central Coast, Central Valley, Northern) | 2) Corrosion Zone | 3) Conductor Material | 4) Number of Splices
31132477 | RELIAIBLITY OAKLAND-REPLACE 1/0 OH | OAKLAND D 1105 | 740 | 140371.1 | 2020-01-11 | Actualized | Bay | Moderate | 1/0 Cu | Unknown
31279013 | MALAGA 1102 RECOND 1350FT 6CU | MALAGA 1102 | 1217 | 32653.1 | 2020-01-16 | Actualized | Central Valley | None | 6 Cu | 26
31262866 | HBPP 1101 LR 898396 EXCESSIVE SPLICES | HUMBOLDT BAY 1101 | 4906 | 613540 | 2020-01-29 | Actualized | Northern | Severe | 6 Cu | 49
31232282 | +SISQUOC 1104, 3502 TELEPHONE RD, SM | SISQUOC 1104 | 7350 | 79350 | 2020-01-30 | Actualized | Central Coast | Moderate | 4 ar | 26+
31308789 | RECONDUCTOR WESTLEY 1101-HAMILTON RD | WESTLEY 1101 | 13200 | 46965.9 | 2020-02-04 | Actualized | Central Valley | None | 6 Cu | Unknown
31212921 | HAMMONDS 1104 REPLACE 397AL | HAMMONDS 1104 | 7924 | 544315 | 2020-02-08 | Actualized | Central Valley | None | 397 AL | Unknown
31265331 | RAINBOW 1106 RECOND 6600FT 6CU | RAINBOW 1106 | 6600 | 800836.2 | 2020-02-10 | Actualized | Central Valley | None | 6 Cu | Unknown
31193590 | +R5 DIVIDE 1102 WD RECONDUCTORING | DIVIDE 1102 | 1080 | 20000 | 2020-02-12 | Actualized | Central Coast | Moderate | 4 Ar | 6+
31082391 | RECON 4-SPANS SULLIVAN RD | Molino 1102 | 1059 | 328969.8 | 2020-02-14 | Actualized | Northern | None | 6 Cu | 14+
31158390 | +RECOND 960 FT OF 4 ACSR ON SLO 1101 | SAN LUIS OBISPO 1101 | 994 | 277409.8 | 2020-02-14 | Actualized | Central Coast | Moderate | 4 Ar | 6+
31219804 | GRAND ISLD 2224 RECOND 800FT 6CU W2A | GRAND ISLAND 2224 | 2601 | 141196 | 2020-02-26 | Actualized | Northern | None | 4 Cu | 19+
31202926 | REMOVE SPLICES AND INSTALL FUSES | Woodside 1105 | 419 | 94504.2 | 2020-02-28 | Actualized | Bay | None | 6 Cu | 12+
31257470 | VIERRA 1707 RECOND. W. RIPON RD MANTECA | VIERRA 1707 | 5222 | 563491 | 2020-03-02 | Actualized | Central Valley | None | 6 Cu | 31+
31177369 | R5 SBWF FW 1107 & DIV 1104, HWY 1 & BLK | DIVIDE 1103 | 6872 | 149803.2 | 2020-03-06 | Actualized | Central Coast | Severe | 4 Ar | Unknown
31236820 | WOODWARD 2107-RECONDUCTORING | WOODWARD 2107 | 1456 | 222658.7 | 2020-03-06 | Actualized | Central Valley | None | 6 Cu | 34+
35123906 | RECOND 10 SPAN 2385FT 4ACSR W 2ACSR | SISQUOC 1103 | 2442 | 85639.4 | 2020-03-09 | Actualized | Central Coast | None | 4 Ar | 10+
31251131 | PALMER 1101 WO HWY 101 NO HW 135, LOS AL | PALMER 1101 | 8060 | 286172.1 | 2020-03-12 | Actualized | Central Coast | None | 4 Cu | 102
31207091 | MVWF BUENA VISTA AVE, CITY ALTO 1124 | ALTO 1124 | 2998 | 1081774.5 | 2020-03-16 | Actualized | Bay | Moderate | 6 Cu | Unknown
31082390 | R7 RECON 12-SPAN GRATON RD W/RAILROAD AV | Molino 1102 | 1865 | 768820.1 | 2020-04-24 | Actualized | Northern | None | 6 Cu | 15+
31277398 | RECONDUCTOR LIVINGSTON 1106 - WD | LIVINGSTON 1106 | 2299 | 224550.2 | 2020-05-15 | Actualized | Central Valley | None | 6 Cu | 13+
31222395 | LINDEN 1104 RECONDUCTORING(WIREDOWN) | LINDEN 1104 | 2405 | 89481.4 | 2020-06-02 | Actualized | Central Valley | None | 6 Cu | 87+
30981770 | R5 2017 TAFT 1108 RECONDUCTOR | Maricopa 1102 | 3798 | 297104 | 2020-06-05 | Actualized | Central Valley | None | 6 Cu | Unknown
35051253 | R2 RECONDUCT DOLAN RD 1101 WD#16-0065306 | DOLAN ROAD 1101 | 2751 | 321849.8 | 2020-06-12 | Actualized | Central Coast | Moderate | 6 Cu | 28 +
31224307 | +CABRILLO 1103 WD FUSE AND RECONDUCT | CABRILLO 1103 | 484 | 47000 | 2020-06-08 16:00 | Actualized | Central Coast | Moderate | 2 ar | Unknown
31236028 | TRACY 1102 RECONDUCTOR CABRILLO DR | TRACY 1102 | 1950 | 636904.5 | 2020-06-19 | Actualized | Central Valley | None | 4 ar | 55+
31142343 | R2 2017 KERMAN 1102 RECONDUCTOR WIREDOWN | KERMAN 1102 | 5485 | 400112.3 | 2020-06-22 16:00 | Actualized | Central Valley | None | 6 Cu | 9+
31193955 | +SBWF MESA 1102 NO DIVISION ST, GUADALUP | MESA 1102 | 12479 | 368012.6 | 2020-08-21 | Actualized | Central Coast | Severe | 6 Cu | Unknown
31247517 | R7 RECOND 2400' LAKEVILLE HWY, LKVL 1101 | LAKEVILLE 1101 | 2479 | 139990.6 | 2020-12-09 | Actualized | Northern | None | 6 Cu | 31+
31248666 | MIDDLE RIVER 1103 RECONDUCTOR | MIDDLE RIVER 1103 | 7414 | 563000 | 2020-07-28 | Actualized | Central Valley | None | 6 Cu | 51+
31258120 | HARTLEY 1102 RECONDUCTOR LINE BAD SP | HARTLEY 1102 | 4000 | 327832 | 2020-10-08 | Actualized | Northern | None | 6 Cu | 35+
31276194 | R5 RIO BRAVO 1101 - RECONDUCTOR 1,650' | RIO BRAVO 1101 | 1576 | 106570.2 | 2020 pushed to 2022 | Forecasted | Central Valley | None | 6 Cu | 22+
31185022 | R2 WF 1111 RECONDUCTOR - VALENTINE AVE. | WEST FRESNO 1111 | 2720 | 297154 | 2020-08-05 | Actualized | Central Valley | None | 6 Cu | 147+
35123423 | RECONDUCTOR PAST FUSE 45133 SISQUOC 1104 | SISQUOC 1104 | 526 | 61000 | 2020-09-01 | Actualized | Central Coast | Moderate | 4 Ar | 11+
35024645 | S031CC201 - RR2105 RECONDUCT NEAR SW7387 | ROB ROY 2105 | 386 | 38600 | 2020 pushed to 2021 | Forecasted | Central Coast | Severe | 4 Ar | 7+
35123429 | R2WATSNVILLE 2101 HIGH SPLICE CABLE REPL | WATSONVILLE 2101 | 1670 | 165246.9 | 2020 pushed to 2021 | Forecasted | Central Coast | Moderate | 8 Cu | 27+
31377407 | HIGGINS 1107 RECONDUCTOR | HIGGINS 1107 | 4045 | 395976.9 | 2020 pushed to 2021 | Forecasted | Northern | None | 4 Ar | 7+
31151064 | RECONDUCT ON U1112 | SAN LEANDRO U 1112 | 200 | 20000 | 2020 pushed to 2021 | Forecasted | Central Coast | None | 6 Cu | Unknown
31234874 | RELIAIBLITY 2017 - UWF VARIOUS CKTS | ARLINGTON 0401 | 6500 | 427985.1 | 2020-08-31 16:00 | Actualized | Bay | Moderate | 4 Cu | Unknown
35019447 | R2 RECONDUCTR 4268FT OF3-4ACSR WTH 3-2CU | CABRILLO 1104 | 4268 | 322839.5 | 2020 pushed to 2021 | Forecasted | Central Coast | Severe | 4 AR | unknown
30900554 | XDIX. LAND 2102 - RECONDUCTOR 900 FT | Dixon Landing 2102 | 553 | 55300 | 2020-09-11 16:00 | Actualized | Central Coast | None | 4 ar | Unknown
31219439 | +SANTA MARIA 1105 WD 15-0087677 | SANTA MARIA 1105 | 500 | 24313.3 | 2020 pushed to 2021 | Forecasted | Central Coast | Moderate | 4 AR | unknown
35020110 | 2019 08J CC SOLEDAD 1114 S060CC214 | SOLEDAD 1114 | 6896 | 202578.1 | 2020-09-26 16:00 | Actualized | Central Coast | None | 4 Cu | 20+
31262300 | EP RECONDUCTOR KNIGHTS LANDING 1102 | KNIGHTS LANDING 1102 | 1630 | 246853.2 | 2020 pushed to 2021 | Forecasted | Northern | None | 4 Ar | 10+
31249134 | REPLACE DETERIORATED CONDUCT_MABURY1103 | MABURY 1103 | 842 | 84200 | 2020 pushed to 2021 | Forecasted | Central Coast | None | 4 Ar | 11
31330242 | COLUSA 1103 RECOND 7000 FT 6C @ C/O 3557 | Colusa 1103 | 6034 | 550587 | 2020-07-24 | Actualized | Northern | None | 6 Cu | 9+
35123425 | R2 RECONDUCT SALINAS 1106 | SALINAS 1106 | 1000 | 100000 | 2020 pushed to 2021 | Forecasted | Central Coast | Moderate | 4 Ar | Unknown
35123428 | PN WIREDOWN 17-0043197 DC-1112 | DALY CITY 1112 | 1500 | 263425.2 | 2020 pushed to 2021 | Forecasted | Central Coast | Severe | 4 AR | unknown
35123430 | 2019 08J PN EG-1101 S072CC216 | EAST GRAND 1101 | 1700 | 325201.5 | 2020 pushed to 2021 | Forecasted | Central Coast | moderate | 4 AR | 10+
35076187 | E STOCKTON 402-RECOND 2,800' OF 6CU/W 2A | EAST STOCKTON 0402 | 2800 | 384683.6 | 2020 pushed to 2021 | Forecasted | Central Valley | None | 6 Cu | 16+
31276349 | 2018 OH COND RPLC: EEL RIVER 1103 | EEL RIVER 1103 | 650 | 65000 | 2020 pushed to 2021 | Forecasted | Northern | Moderate | 6 Cu | 19+
35052976 | WD-EIGHT MILE2101-CO738931-ILS 180066835 | EIGHT MILE 2101 | 3580 | 472027 | 2020 pushed to 2021 | Forecasted | Central Valley | None | 4 Cu | 22+
31212878 | RECONDUCTOR GRAND ISLAND 2223 | GRAND ISLAND 2223 | 470 | 47000 | 2020 pushed to 2021 | Forecasted | Northern | None | 6 Cu | 7+
31282951 | RECONDUCTOR SIX SPANS-GRAND ISLAND 2224 | GRAND ISLAND 2224 | 1700 | 170000 | 2020 pushed to 2021 | Forecasted | Northern | None | 6 Cu | 10+
35123907 | RECONDUCT CASTROVILLE 2104 WD#16-0083838 | CASTROVILLE 2104 | 2600 | 231865.8 | 2020 pushed to 2021 | Forecasted | Central Coast | Moderate | 6 Cu | 10+
35015933 | R2RPL OH WIRE ON DOLANRD-1104 17-0069754 | DOLAN ROAD 1104 | 1785 | 313698.9 | 2020-11-06 | Actualized | Central Coast | Moderate | 4 Ar | Unknown
35054821 | RPL OH COND.RESERVATION RD.1102 18-69362 | RESERVATION ROAD 1102 | 2842 | 467105.2 | 2020 pushed to 2021 | Forecasted | Central Coast | Moderate | 4 Ar | Unknown
35125402 | RECOND 3400FT OF 4ACSR WITH 2ACSR SOLEDA | SOLEDAD 2102 | 3400 | 567041.1 | 2020 pushed to 2021 | Forecasted | Central Coast | None | 4 Ar | 12+
31274093 | R2Z KETTLEMAN HILLS 1101 RECOND 2741FT | KETTLEMAN HILLS 1101 |  |  | Cancelled | Forecasted
35008760 | 2019 KINGBURG 1113 RECONDUCTOR | KINGSBURG 1113 | 4300 | 399216.1 | 2020 pushed to 2021 | Forecasted | Central Valley | None | 4 Cu | 30+
35125684 | R2RPL OH WIRE ON GONZALES1104 18-0003089 | GONZALES 1104 | 11121 | 58176.3 | 2020 pushed to 2021 | Forecasted | Central Coast | None | 6 Cu | 7+
35125413 | R2RPL OH WIRE ON DOLN RD-1104 17-0061463 | DOLAN ROAD 1104 | 8997 | 575610.3 | 2020 pushed to 2021 | Forecasted | Central Coast | Moderate | 4 Ar | Unknown
35018554 | RIO BRAVO 1106 - RECONDUCTOR | RIO BRAVO 1106 | 5280 | 545818 | 2020 pushed to 2021 | Forecasted | Central Valley | None | 4 Ar | 21+
35008694 | BAKERSFLD 1114 TARGETD OH RECOND | BAKERSFIELD 1114 | 4000 | 346059.4 | 2020 pushed to 2021 | Forecasted | Central Valley | None | 2 Cu | 22+
31203813 | MVWF STINSON BEACH, BOLINAS 1101 | BOLINAS 1101 | 7378 | 1263738.8 | 2020 pushed to 2021 | Forecasted | Bay | Severe | 6 Cu | Unknown
35019007 | KING CITY 1102 LR7024 REPLACE OH LINE | KING CITY 1102 | 4780 | 914334.7 | 2020 Pushed to 2022 | Forecasted | Central Coast | None | 4 Ar | 27+
35053651 | RPL OH COND. SALINAS 1107 18-0066956 | SALINAS 1107 | 3685 | 610610.3 | 2020 pushed to 2021 | Forecasted | Central Coast | Moderate | 4 Ar | Unknown
35123424 | RECON 815 FT TAP OFF LAUGHLIN CAPELLA 01 | CALPELLA 1101 | 815 | 81500 | 2020 pushed to 2021 | Forecasted | Northern | None | 6 Cu | 11+
35148810 | GRAND ISLAND 2224 RECON STATION OUTLET | GRAND ISLAND 2224 |  |  | Cancelled | Forecasted
35100323 | GRAND ISLAND 2226 RECOND 2600 FEET OF OH | GRAND ISLAND 2226 | 2600 | 277365.8 | 2020 pushed to 2021 | Forecasted | Northern | None | 4 Ar | 7+
31131283 | R2Z V2101 14-0076675 COWARD RD | Green Valley 2101 | 760 | 76000 | 2020 pushed to 2021 | Forecasted | Central Coast | Moderate | 4 Ar | Unknown
35059716 | HAMMER 1105 RECONDUCTORING - WIREDOWN | HAMMER 1105 | 1600 | 420429.4 | 2020 pushed to 2021 | Forecasted | Central Valley | None | 4 Ar | Unknown
35052329 | HIGHWAY 1105 WIRE DOWN 18-0060061 | HIGHWAY 1105 | 3150 | 330531 | 2020 pushed to 2021 | Forecasted | Bay | None | 4 Ar | 11+
31352062 | L-1102 - 48TH AVE RECONDUCTORING PROJECT | JUDAH 0402 | 2888 | 835000 | 2020-12-20 | Actualized | Bay | Severe | 4 Cu | Unknown
35000302 | RE-CONDUC 4149FT 6CU&4ACSR W2CU SM 1110 | SANTA MARIA 1110 | 4149 | 429649.4 | 2020 pushed to 2021 | Forecasted | Central Coast | Severe | 4 Ar | Unknown
35029850 | RE-CONDUCTOR 1328FT CAMBRIA 1101 | CAMBRIA 1101 | 1328 | 161827.4 | 2020 pushed to 2021 | Forecasted | Central Coast | Severe | 4 Ar | Unknown
31338877 | DUMBARTON 2111 FUSE 7809 PROJECT | DUMBARTON 2111 | 5379 | 762511.6 | 2020 pushed to 2021 | Forecasted | Central Coast | Moderate | 6 Cu | Unknown
35125691 | ELK HILLS 1104 OH SPLICE SSD1523 | ELK HILLS 1104 | 18242 | 1810885 | 2020 Pushed to 2022 | Forecasted | Central Valley | None | 4 Cu | 16+
35123908 | RECONDUCTOR - FUSE ZONE - SM1109 CKT | SANTA MARIA 1109 | 1612 | 365419.4 | 2020 pushed to 2021 | Forecasted | Central Coast | Severe | 4 Ar | 4+
31276346 | 2018 OH COND RPLC: BIG LAGOON 1101 | BIG LAGOON 1101 | 3750 | 296286.4 | 2020 pushed to 2021 | Forecasted | Northern | Severe | 6 Cu | 33+
31209286 | VIERRA 1707 RECONDUCTORING MANTECA | VIERRA 1707 | 5207 | 462234.3 | 2020 pushed to 2021 | Forecasted | Central Valley | None | 6 Cu | 196+
31082395 | RECON TWO SPANS GRATON RD | Molino 1102 | 754 | 75400 | 2020 pushed to 2021 | Forecasted | Northern | None | 6 Cu | Unknown
31264776 | PEASE 1101 RECOND LINE BAD SPLICES | PEASE 1101 | 1066 | 106600 | 2020 pushed to 2021 | Forecasted | Northern | None | 4 Ar | 6+
31182216 | RECON 11-SPANS (MADISON&MARIA) PET 1105 | PETALUMA C 1105 | 3800 | 636021.8 | 2020 pushed to 2021 | Forecasted | Northern | None | 1 Cu | 13+
35123422 | R7 PUEBLO 2102 RECOND 600 FT OF 4AR | Pueblo 2102 | 600 | 60000 | 2020 pushed to 2021 | Forecasted | Bay | None | 4 Ar | Unknown
31065400 | BH406 REPL.320FT OH LINE 5TH AVE RWC | REDWOOD CITY 0406 | 510 | 36700 | 2020-12-01 | Actualized | Central Coast | None | 1/0 Cu | 10+
35123421 | R1 WIREDOWN RECONDUCTORING H-1110 | SF H 1110 | 203 | 20300 | 2020 pushed to 2021 | Forecasted | Central Coast | Moderate | 397 AL | 11
35060583 | RECONDUCTOR STOREY 1105 | STOREY 1105 | 3163 | 446000 | 2020-06-20 | Actualized | Central Valley | None | 6 Cu | 13+
35125403 | TERMINOUS 1102 RECONDUCTOR | TERMINOUS 1102 | 3610 | 393972.6 | 2020 pushed to 2022 | Forecasted | Central Valley | None | 4 Ar | 67+
35123905 | 2019 VALLEJO B 413 HIGH SPLICE COUNT | VALLEJO B 0413 | 2350 | 283137.8 | 2020 pushed to 2021 | Forecasted | Bay | None | 4 Cu | 24+
35001862 | WATERLOO 1101 RECOND 4000' OH CONDUCTOR | WATERLOO 1101 | 4300 | 447588.1 | 2020 pushed to 2021 | Forecasted | Central Valley | None | 6 Cu | 5+
35125693 | RECOND WATSONVILLE 2101 REF# S074CC218 | WATSONVILLE 2101 | 26540 | 2654000 | 2020 pushed to 2021 | Forecasted | Central Coast | Moderate | 4 Ar | 9+
31278065 | RECONDUCTOR MERCED 2101-STRETCH RD | MERCED 2101 | 753 | 75300 | 2020 pushed to 2021 | Forecasted | Central Valley | None | 4 Cu | 13+
35029545 | DINUBA 1104 RECOND 3,240' OF 6CU/W 2ACSR | DINUBA 1104 | 3240 | 316478.3 | 2020 pushed to 2021 | Forecasted | Central Valley | None | 6 Cu | 10+
35056269 | AIRWAYS 1105-RECOND 1,520 FT OF 1/O ACSR | AIRWAYS 1105 | 1520 | 163116.3 | 2020 pushed to 2022 | Forecasted | Central Valley | None | 6 Cu | Unknown
35018622 | R2 RECON 1400 FT WITH 2CU$ 1FCO | CABRILLO 1104 | 1400 | 127243.3 | 2020 pushed to 2021 | Forecasted | Central Coast | Severe | 4 Ar | 12+
35125400 | ELK HILLS 1104 OH SPLICE FUSE 19082 | ELK HILLS 1104 | 3290 | 334279.6 | 2020 pushed to 2022 | Forecasted | Central Valley | None | 6 Cu | 11+
35125408 | BOWLES 1104 RECONDUCTOR | Bowles 1104 | 5502 | 555209.1 | 2020 pushed to 2021 | Forecasted | Central Valley | None | 4 Cu | 23+
31259546 | 2018 AIRWAYS 1101 RECOND 2800FT TO 715AL | AIRWAYS 1101 | 2800 | 290189.9 | 2020 pushed to 2021 | Forecasted | Central Valley | None | 6 Cu | 20+
35125405 | RECONDUCTOR 3,750' MESA 1101 S041CC208 | MESA 1101 | 3750 | 349748.4 | 2020 pushed to 2021 | Forecasted | Central Coast | Moderate | 1/0 AR | 12+
35089227 | BIOLA 1104 RECONDUCTOR 2,995 FT OF 6CU | BIOLA 1104 | 2015 | 279960.9 | 2020 pushed to 2021 | Forecasted | Central Valley | None | 6 Cu | 41+
35135003 | R2 EL NIDO 1101 RECOND 3700FT WITH #2AR | EL NIDO 1101 | 3700 | 292100.4 | 2020 pushed to 2022 | Forecasted | Central Valley | None | 6 Cu | 12+
31185480 | R2Z WDN 15-54205 PS2106-BAY AVE | PAUL SWEET 2106 | 627 | 75641.5 | 2020 pushed to 2021 | Forecasted | Central Coast | Severe | 4 AR | 13+
31276229 | 2018 OH COND RPLC: ARCATA 1121 | ARCATA 1121 | 5000 | 266436.1 | 2020 pushed to 2021 | Forecasted | Northern | Moderate | 6 Cu | 174+
35018563 | R2 2019 MALAGA 1103 RECONDUCTORING | MALAGA 1103 | 3000 | 283331.4 | 2020 pushed to 2021 | Forecasted | Central Valley | None | 4 Ar | 14+
35123909 | RE-COND21SPANS, ALMOST 3152 OCEANO 1106 | OCEANO 1106 | 3152 | 323875 | 2020 pushed to 2022 | Forecasted | Central Coast | Severe | 4 Ar | Unknown
35125692 | R2OLD RIVR 1102 REPLACE ANNEALD CONDUCTO | OLD RIVER 1102 | 21000 | 1847328.7 | 2020 pushed to 2021 | Forecasted | Central Valley | None | 2 Cu | 212+
35116180 | R-1123 RECONDUCTOR PAST R9229 - WHARF ST | RICHMOND R 1123 | 1900 | 190000 | 2020 pushed to 2021 | Forecasted | Bay | Severe | 4 Ar | unknown
35123901 | R1-EB- R1127- RECOND 1,850' OF 6CU | RICHMOND R 1127 | 1850 | 185000 | 2020 pushed to 2021 | Forecasted | Bay | Severe | 6 Cu | 8+
35030422 | RE-CONDUCTOR 1526 FEET SANTA MARIA 1110 | SANTA MARIA 1110 | 1526 | 172304.2 | 2020 pushed to 2022 | Forecasted | Central Coast | Severe | 4 Ar | Unknown
35125683 | R2 SISQUOC 1104_ FUSE 46147 | SISQUOC 1104 | 10649 | 1096663.7 | 2020 pushed to 2021 | Forecasted | Central Coast | Moderate | 4 Ar | 12+
35125409 | 2019 WILLOW PASS 2108 HIGH SPLICE COUNT | WILLOW PASS 2108 | 6250 | 564017.4 | 2020 pushed to 2021 | Forecasted | Bay | None | 1/0 Cu | 10+
35125682 | RECONDUCTOR KINGSBURG 1113 - AVE 368 | KINGSBURG 1113 | 10375 | 994283.6 | 2020 pushed to 2021 | Forecasted | Central Valley | None | 4 Cu | 13+
35125685 | KINGSBURG 1111 RECOND 12,000' OF 6 CU | KINGSBURG 1111 | 11900 | 1182008 | 2020 pushed to 2021 | Forecasted | Central Valley | None | 6 Cu | 21+
35029808 | R2PLOH WIRE ON CASTROVILE2104 18-0016481 | CASTROVILLE 2104 | 1974 | 222543.5 | 2020 pushed to 2021 | Forecasted | Central Coast | Moderate | 4 Ar | Unknown
35066029 | RPL OH.CON.SPENCE 1123 18-0074972 | SPENCE 1102 | 12403 | 1104428.5 | 2020 pushed to 2021 | Forecasted | Central Coast | None | 4 Ar | Unknown
35032114 | GV2102 RECONDUCTOR WD | GREEN VALLEY 2102 | 1520 | 152000 | 2020 pushed to 2021 | Forecasted | Central Coast | Moderate | 4 Ar | Unknown
35184050 | KETTLEMAN HILLS 1101 RECOND 2741FT 4AR | KETTLEMAN HILLS 1101 | 2714 | 228338 | 2020 pushed to 2021 | Forecasted | Central Valley | None | 4 ar | 13+
35123904 | R2 ATWATER 1103 RECONDUCTORING | ATWATER 1103 | 2300 | 230000 | 2021 | Forecasted | Central Valley | None | 6 Cu | 12+
35193844 | MAGUNDEN 1105 - RECONDUCTOR | MAGUNDEN 1105 | 5640 | 564000 | 2021 | Forecasted | Central Valley | None | 4 Ar | Unknown
35125414 | 2018 OH COND RPLC: EUREKA E 1104 | EUREKA E 1104 | 9200 | 920000 | 2021 | Forecasted | Northern | Moderate | 4 Ar | Unknown
35067360 | SUISUN 1105 WIRE DOWN DSC 6385 TO 6473 | SUISUN 1105 | 7996 | 1199400 | 2021 | Forecasted | Northern | None | 4 Ar | Unknown
35029546 | BIOLA 1104 6,350FT TARGET OH REPL | BIOLA 1104 | 6350 | 635000 | 2021 | Forecasted | Central Valley | None | 1/0 Cu | Unknown
35129030 | REEDLEY 1110 RECONDUCTOR 12,271FT OF 6CU | REEDLEY 1110 | 12271 | 1227100 | 2021 | Forecasted | Central Valley | None | 6 Cu | 162+
35065016 | SAN RAFAEL 1103 WIRE DOWN 18-0096220 | SAN RAFAEL 1103 | 850 | 85000 | 2021 | Forecasted | Bay | Severe | 4 Ar | Unknown
35117180 | RECOND GREEN VALLEY 2103 REF# S011CC105 | GREEN VALLEY 2103 | 12225 | 1222500 | 2021 | Forecasted | Central Coast | Severe | 4 Ar | Unknown
35125680 | 2019 PUEBLO 1104 HIGH SPLICE COUNT 1 | PUEBLO 1104 | 10085 | 1008500 | 2021 | Forecasted | Bay | None | 6 Cu | 23+
35098747 | SHEPHERD 2109 RECOND 3,780FT WITH 4/O AL | SHEPHERD 2109 | 3780 | 378000 | 2021 | Forecasted | Central Valley | None | 6 Cu | 15+
35024646 | S048CC209 - RR2105 RECONDUCT 9333 ZONE | ROB ROY 2105 | 2752 | 275300 | 2021 | Forecasted | Central Coast | Severe | 4 Ar | 5+
35125687 | 2020 FAIRHAVEN 1103 DET WIRE PHASE 1 | FAIRHAVEN 1103 | 12800 | 1280000 | 2021 | Forecasted | Northern | Severe | 4 Cu | 47+
35125412 | RECONDUCTOR DEEPWATER 1107 EXCESS SPLICE | DEEPWATER 1107 | 8648 | 864800 | 2021 | Forecasted | Northern | None | 6 Cu | Unknown
35183226 | GRAND ISLAND 2225 RECOND 2.4MI (PH1) | GRAND ISLAND 2224 | 12727 | 2227225 | 2021 | Forecasted | Northern | None | 3/0 Al | Unknown
31383064 | 2020 FORT BRAGG 1103 RECONDUCTOR OUTLET | FORT BRAGG A 1103 | 3100 | 310000 | 2021 | Forecasted | Northern | Severe | 1/0 Cu | 18+
35125690 | 16149CIRCUIT FT(52 SPANS) 4ACSR&6CU W2CU | BAYWOOD 1101 | 16149 | 1614900 | 2021 | Forecasted | Central Coast | severe | 4 Ar | unknown
35125688 | COTATI 1103 RECONDUCTOR ON MIDDLE RD | COTATI 1103 | 14256 | 1425600 | 2021 | Forecasted | Northern | Moderate | 6 Cu | unknown
35123903 | NEW HOPE 1101 2,200FT RECONDUCTOR | NEW HOPE 1101 | 2200 | 220000 | 2021 | Forecasted | Central Valley | None | 6 Cu | 5+
TBD | TBD - Small ar wire in severe and Moderate Corrosion Zones | TBD |  | 15494281 | 2022 | Forecasted | All | Severe/Moderate | Ar | Unknown
TBD | TBD - Small wire with elevated wire down | TBD |  | 15494281 | 2022 | Forecasted | All | None | TBD | Unknown
Note on A70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cancelled