## ProjectList
Order | Order Description | Category | MAT | SAP Status | Status (see 2nd tab) | Planned UG Miles | Planned OH Miles | Planned Removal Miles | Total Planned Circuit Miles | 2020 Miles Installed | 2021 Miles Installed | 2021 Remaining Miles Forecast | 2022 Forecast Miles | 2023 Forecast Miles | Division | Region | City | County | Latitude | Longitude | Old Circuit Protection Zone | Circuit Protection Zone | 2018 Risk Rank | 2021 Risk Rank | Project Type (see 3rd tab for description) | HFTD Tier
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.51326 | 0 | 0.51326 | 0 | 0 | 0.51326 | 0 | 0 | HB | Region 1 - North Coast | Fort Bragg | Mendocino | 39.5022 | -123.7717 | FORT BRAGG A 11013113 | FORT BRAGG A 11013113 | 2292 | 2140 | Pre | Tier 3
31361965 | OCGC 2300 FT - NUNS CANYON -DUNBAR 1101 | Base SH | 08W | FICL | Post-Construction | 0 | 0.4483 | 0 | 0.4483 | 0 | 0.4483 | 0 | 0 | 0 | SO | Region 1 - North Coast | Kenwood | Sonoma | 38.3919 | -122.53 | DUNBAR 110147964 | DUNBAR 110147964 | 1151 | 1794 | Pre | Tier 3
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.0038 | 0 | 1.0038 | 0 | 0 | 0 | 1.0038 | 0 | CC | Region 4 - Central Coast | Aptos | Santa Cruz | 36.9746 | -121.8838 | ROB ROY 210512474 | ROB ROY 210512474 | 2523 | 3283 | Pre | Tier 3
35026643 | DIAMOND SPRINGS 1105 - LR 2102 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.0089 | 0 | 1.0089 | 0 | 0 | 0 | 1.0089 | 0 | SI | Region 2 - North East | El Dorado | El Dorado | 0 | 0 | DIAMOND SPRINGS 11052102 | DIAMOND SPRINGS 11052102 | 787 | 666 | Top 20% MAVF CPZ | Tier 2
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Base SH | 08W | CONS | In-Construction* | 0 | 1.4733 | 0 | 1.4733 | 0 | 0 | 1.4733 | 0 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1332 | -122.1258 | BIG BASIN 110110296 | BIG BASIN 110110296 | 303 | 2456 | Pre | Tier 3
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.6297 | 0 | 1.6297 | 0 | 0 | 0 | 1.6297 | 0 | YO | Region 5 - Central Valley | Long Barn | Tuolumne | 0 | 0 | MIWUK 1701953336 | MIWUK 1701953336 | 2724 | 2267 | Pre | Tier 3
35052821 | T2/T3-CWSP - MIWUK 1701 OCB - PH 1.1 | Base SH | 08W | CONS | In-Construction* | 0 | 2.0911 | 0 | 2.0911 | 0 | 2.0911 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne | 38.0571 | -120.2065 | MIWUK 1701CB | MIWUK 1701CB | 2 | 2353 | Pre | Tier 3
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Base SH | 08W | DOCC | Post-Construction | 0 | 1.1114 | 0 | 1.1114 | 0 | 1.1114 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne | 38.0489 | -120.2345 | MIWUK 1702S2247 | MIWUK 1702S2247 | 26 | 2737 | Pre | Tier 3
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Base SH | 08W | PEND | Permitting/Dependency | 0.26193 | 1.2653 | 0 | 1.5273 | 0 | 0 | 0 | 1.5273 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7821 | -120.6094 | EL DORADO PH 210119752 | EL DORADO PH 210119752 | 12 | 1946 | PSS Approved | Tier 3
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Base SH | 08W | DOCC | Post-Construction | 0 | 2.0278 | 0 | 2.0278 | 0 | 2.0278 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mi Wuk Village | Tuolumne | 0 | 0 | MIWUK 1701CB | MIWUK 1701CB | 2 | 2353 | Pre | Tier 3
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Base SH | 08W | PEND | Permitting/Dependency | 0.59375 | 0.71572 | 0 | 1.3095 | 0 | 0 | 0 | 1.3095 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7821 | -120.6094 | EL DORADO PH 210119752 | EL DORADO PH 210119752 | 12 | 1946 | PSS Approved | Tier 3
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Base SH | 08W | CONS | In-Construction* | 2.4557 | 0 | 0 | 2.4557 | 0 | 0 | 0 | 2.4557 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7821 | -120.6094 | EL DORADO PH 210119752 | EL DORADO PH 210119752 | 12 | 1946 | PSS Approved | Tier 3
35061206 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH1.1 | Base SH | 08W | DOCC | Post-Construction | 0 | 1.7348 | 0 | 1.7348 | 0 | 1.7348 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | Nevada | 0 | 0 | BRUNSWICK 110350070 | BRUNSWICK 110350070 | 7 | 2144 | Pre | Tier 3
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Base SH | 08W | FICL | Post-Construction | 0 | 1.9985 | 0 | 1.9985 | 0 | 1.9985 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | Nevada | 39.291 | -121.0309 | BRUNSWICK 110350070 | BRUNSWICK 110350070 | 7 | 2144 | Pre | Tier 3
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Base SH | 08W | DOCC | Post-Construction | 0 | 1.4511 | 0 | 1.4511 | 1.3445 | 0.10663 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | Nevada | 39.2907 | -121.0162 | BRUNSWICK 110350070 | BRUNSWICK 110350070 | 7 | 2144 | Pre | Tier 3
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Base SH | 08W | PEND | Permitting/Dependency | 2.0513 | 0 | 0 | 2.0513 | 0 | 0 | 0 | 2.0513 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado | 0 | 0 | SHINGLE SPRINGS 21099372 | SHINGLE SPRINGS 21099372 | 472 | 227 | Top 20% MAVF CPZ | Tier 3
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Base SH | 08W | PEND | Permitting/Dependency | 1.5646 | 0 | 0 | 1.5646 | 0 | 0 | 0 | 1.5646 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado | 0 | 0 | SHINGLE SPRINGS 21099372 | SHINGLE SPRINGS 21099372 | 472 | 227 | Top 20% MAVF CPZ | Tier 3
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Base SH | 08W | ESTS | Estimating | 4.3356 | 0 | 0 | 4.3356 | 0 | 0 | 0 | 4.3356 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado | 0 | 0 | SHINGLE SPRINGS 210935598 | SHINGLE SPRINGS 210935598 | 604 | 159 | Top 20% MAVF CPZ | Tier 3
35075103 | FROGTOWN 1701 TIER 2 RECOND - FUSE L2969 | Base SH | 08W | CONS | In-Construction* | 0 | 0.63674 | 0 | 0.63674 | 0 | 0 | 0.63674 | 0 | 0 | ST | Region 5 - Central Valley | Murphys | Calaveras | 0 | 0 | FROGTOWN 17011623 | FROGTOWN 17011623 | 1165 | 721 | Top 20% MAVF CPZ | Tier 3
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.84659 | 0 | 0.84659 | 0 | 0 | 0 | 0.84659 | 0 | CC | Region 4 - Central Coast | Aptos | Santa Cruz | 36.9746 | -121.8838 | ROB ROY 210512474 | ROB ROY 210512474 | 2523 | 3283 | Pre | Tier 3
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Base SH | 08W | DOCC | Post-Construction | 0 | 1.0617 | 0 | 1.0617 | 0 | 1.0617 | 0 | 0 | 0 | HB | Region 1 - North Coast | Kelseyville | Lake | 38.9024 | -122.7519 | KONOCTI 1102532 | KONOCTI 1102532 | 153 | 1999 | Pre | Tier 3
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Base SH | 08W | PEND | Permitting/Dependency | 0.032576 | 1.7771 | 0 | 1.8097 | 0 | 0 | 0 | 1.8097 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 0 | 0 | STANISLAUS 17021804 | STANISLAUS 17021804 | 17 | 2712 | Pre | Tier 3
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | Base SH | 08W | FICL | Post-Construction | 0 | 2.49 | 0 | 2.49 | 2.3309 | 0.15909 | 0 | 0 | 0 | NV | Region 2 - North East | Shingletown | Shasta | 40.4974 | -121.8473 | VOLTA 11021502 | VOLTA 110253130 | 2292 | 2314 | Pre | Tier 3
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | Base SH | 08W | ESTS | Estimating | 0.24223 | 2.4256 | 0 | 2.6678 | 0 | 0 | 0 | 2.6678 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 0 | 0 | EL DORADO PH 210119752 | EL DORADO PH 210119752 | 12 | 1946 | PSS Approved | Tier 3
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Base SH | 08W | ESTS | Estimating | 0.31515 | 2.4574 | 0 | 2.7725 | 0 | 0 | 0 | 2.7725 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 0 | 0 | EL DORADO PH 210119752 | EL DORADO PH 210119752 | 12 | 1946 | PSS Approved | Tier 3
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 | Base SH | 08W | CLSD | Closed | 0 | 1.3269 | 0 | 1.3269 | 1.1178 | 0.20909 | 0 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7508 | -120.5676 | EL DORADO PH 210219562 | EL DORADO PH 210219562 | 48 | 3014 | Pre | Tier 3
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | Base SH | 08W | FICL | Post-Construction | 0 | 2.2267 | 0 | 2.2267 | 2.1784 | 0.048295 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Volcano | Amador | 38.4873 | -120.5755 | WEST POINT 110113444 | WEST POINT 11013444 | 59 | 2293 | Pre | Tier 3
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Base SH | 08W | FICL | Post-Construction | 0 | 0.72102 | 0 | 0.72102 | 0 | 0.72102 | 0 | 0 | 0 | DA | Region 4 - Central Coast | Los Gatos | Santa Clara | 37.1912 | -122.0324 | LOS GATOS 1106LB44 | LOS GATOS 1106LB44 | 690 | 1864 | Pre | Tier 3
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Base SH | 08W | CONS | In-Construction* | 0 | 3.2451 | 0 | 3.2451 | 0 | 0 | 2.3153 | 0.92973 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1332 | -122.1258 | BIG BASIN 110110296 | BIG BASIN 110110296 | 303 | 2456 | Pre | Tier 3
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Base SH | 08W | CONS | In-Construction* | 0 | 2.3443 | 0 | 2.3443 | 0 | 0 | 0 | 2.3443 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 0 | 0 | BIG BASIN 110110296 | BIG BASIN 110110296 | 303 | 2456 | Pre | Tier 3
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Base SH | 08W | PEND | Permitting/Dependency | 0.090341 | 1.3943 | 0 | 1.4847 | 0 | 0 | 0 | 1.4847 | 0 | ST | Region 5 - Central Valley | Kit Carson | Amador | 0 | 0 | PINE GROVE 11021222 | PINE GROVE 11021222 | 18 | 2271 | Pre | Tier 3
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Base SH | 08W | FICL | Post-Construction | 0 | 1.3352 | 0 | 1.3352 | 1.172 | 0.16326 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Kit Carson | Amador | 38.4357 | -120.5538 | PINE GROVE 11021222 | PINE GROVE 11021222 | 18 | 2271 | Pre | Tier 3
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Base SH | 08W | FICL | Post-Construction | 0 | 1.0966 | 0 | 1.0966 | 0.081061 | 1.0155 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Kit Carson | Amador | 38.4428 | -120.5433 | PINE GROVE 11021222 | PINE GROVE 11021222 | 18 | 2271 | Pre | Tier 3
35114048 | OCGC CWSP - PINE GROVE 1102 - LR1222 | Base SH | 08W | FICL | Post-Construction | 0 | 1.3909 | 0 | 1.3909 | 0 | 1.3909 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.436 | -120.5562 | PINE GROVE 11021222 | PINE GROVE 11021222 | 20 | 2271 | Pre | Tier 3
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Base SH | 08W | FICL | Post-Construction | 0 | 1.5705 | 0 | 1.5705 | 0.70663 | 0.86383 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.436 | -120.5562 | PINE GROVE 11021222 | PINE GROVE 11021222 | 18 | 2271 | Pre | Tier 3
35114051 | OCGC PINE GROVE 1102 - LR1222 - PH | Base SH | 08W | DOCC | Post-Construction | 0 | 1.4371 | 0 | 1.4371 | 0 | 1.4371 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4485 | -120.5393 | PINE GROVE 11021222 | PINE GROVE 11021222 | 2 | 2271 | Pre | Tier 3
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | Base SH | 08W | FICL | Post-Construction | 0 | 0.95076 | 0 | 0.95076 | 0 | 0.95076 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Scotts Valley | Santa Cruz | 0 | 0 | CAMP EVERS 21065020 | CAMP EVERS 21065020 | 46 | 2464 | Pre | Tier 3
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Base SH | 08W | MAPP | Post-Construction | 0 | 0.73428 | 0 | 0.73428 | 0.16004 | 0.57424 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Scotts Valley | Santa Cruz | 37.0987 | -121.9895 | CAMP EVERS 21065020 | CAMP EVERS 21065020 | 42 | 2464 | Pre | Tier 3
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Base SH | 08W | FICL | Post-Construction | 0 | 1.1294 | 0 | 1.1294 | 0 | 1.1294 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Scotts Valley | Santa Cruz | 0 | 0 | CAMP EVERS 21065020 | CAMP EVERS 21065020 | 42 | 2464 | Pre | Tier 3
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | Base SH | 08W | FICL | Post-Construction | 0 | 1.6241 | 0 | 1.6241 | 0 | 1.6241 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne | 38.0571 | -120.2065 | MIWUK 1701CB | MIWUK 1701CB | 2 | 2353 | Pre | Tier 3
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | Base SH | 08W | DOCC | Post-Construction | 0 | 1.779 | 0 | 1.779 | 0 | 1.779 | 0 | 0 | 0 | YO | Region 5 - Central Valley |  |  |  |  | MIWUK 1701CB | MIWUK 1701CB | 2 | 2353 | Pre | Tier 3
35115054 | CWSP - MIWUK 1701 - OCB - PH 2.2 | Base SH | 08W | MAPP | Post-Construction | 0 | 1.3953 | 0 | 1.3953 | 0 | 1.3953 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne | 38.0614 | -120.1982 | MIWUK 1701CB | MIWUK 1701CB | 2 | 2353 | Pre | Tier 3
35115055 | CWSP - MIWUK 1701 - OCB - PH 2.3 | Base SH | 08W | MAPP | Post-Construction | 0 | 2.1343 | 0 | 2.1343 | 0 | 2.1343 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne | 0 | 0 | MIWUK 1701CB | MIWUK 1701CB | 2 | 2353 | Pre | Tier 2
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Base SH | 08W | DOCC | Post-Construction | 0 | 2.1331 | 0 | 2.1331 | 2.0127 | 0.12045 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | Nevada | 39.2954 | -121.0218 | BRUNSWICK 110350070 | BRUNSWICK 110350070 | 7 | 2144 | Pre | Tier 3
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Base SH | 08W | FICL | Post-Construction | 0 | 1.9019 | 0 | 1.9019 | 0 | 1.9019 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | Nevada | 0 | 0 | BRUNSWICK 110350070 | BRUNSWICK 110350070 | 7 | 2144 | Pre | Tier 3
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Base SH | 08W | CONS | In-Construction* | 0 | 1.6701 | 0 | 1.6701 | 0 | 0.90985 | 0.76023 | 0 | 0 | SI | Region 2 - North East | Nevada City | Nevada | 0 | 0 | BRUNSWICK 110350070 | BRUNSWICK 110350070 | 7 | 2144 | Pre | Tier 3
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Base SH | 08W | FICL | Post-Construction | 0 | 1.7006 | 0 | 1.7006 | 0 | 1.7006 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | Nevada | 39.299 | -121.0391 | BRUNSWICK 110350070 | BRUNSWICK 110350070 | 7 | 2144 | Pre | Tier 3
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Base SH | 08W | FICL | Post-Construction | 0 | 1.6462 | 0 | 1.6462 | 0 | 1.6462 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | Nevada | 0 | 0 | BRUNSWICK 110350070 | BRUNSWICK 110350070 | 7 | 2144 | Pre | Tier 3
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | Base SH | 08W | FICL | Post-Construction | 0 | 1.2456 | 0 | 1.2456 | 1.0847 | 0.16098 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.3019 | -120.277 | SALT SPRINGS 21023142 | SALT SPRINGS 21023142 | 8 | 2659 | Pre | Tier 3
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Base SH | 08W | MAPP | Post-Construction | 0 | 1.3919 | 0 | 1.3919 | 0 | 1.3919 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne | 0 | 0 | MIWUK 1701953336 | MIWUK 1701953336 | 12 | 2267 | Pre | Tier 3
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Base SH | 08W | FICL | Post-Construction | 0 | 1.7801 | 0 | 1.7801 | 0 | 1.7801 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne | 38.0743 | -120.1731 | MIWUK 1701953336 | MIWUK 1701953336 | 12 | 2267 | Pre | Tier 3
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.5161 | 0 | 1.5161 | 0 | 0 | 0 | 1.5161 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne | 0 | 0 | MIWUK 1701953336 | MIWUK 1701953336 | 12 | 2267 | Pre | Tier 3
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Base SH | 08W | FICL | Post-Construction | 0 | 2.0902 | 0 | 2.0902 | 1.3841 | 0.70606 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne | 38.0494 | -120.261 | MIWUK 1702CB | MIWUK 1702CB | 25 | 2369 | Pre | Tier 3
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | Base SH | 08W | FICL | Post-Construction | 0 | 1.703 | 0 | 1.703 | 0 | 1.703 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne | 38.0596 | -120.2138 | MIWUK 1702CB | MIWUK 1702CB | 25 | 2369 | Pre | Tier 3
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Base SH | 08W | FICL | Post-Construction | 0 | 2.3314 | 0 | 2.3314 | 1.7888 | 0.54148 | 0.0011364 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne | 38.0486 | -120.2438 | MIWUK 170238218 | MIWUK 170238218 | 32 | 2678 | Pre | Tier 3
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Base SH | 08W | CONS | In-Construction* | 0 | 2.065 | 0 | 2.065 | 0 | 0 | 2.065 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne | 38.0486 | -120.2438 | MIWUK 170238218 | MIWUK 170238218 | 32 | 2678 | Pre | Tier 3
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | Base SH | 08W | DOCC | Post-Construction | 0 | 1.3864 | 0 | 1.3864 | 0.73996 | 0.6464 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne | 38.0441 | -120.2479 | MIWUK 1702823548 | MIWUK 1702823548 | 23 | 2411 | Pre | Tier 3
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Base SH | 08W | MAPP | Post-Construction | 0.10417 | 1.1737 | 0 | 1.2778 | 0.37008 | 0.90777 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne | 38.0441 | -120.2479 | MIWUK 1702823548 | MIWUK 1702823548 | 23 | 2411 | Pre | Tier 3
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Base SH | 08W | FICL | Post-Construction | 0 | 2.2237 | 0 | 2.2237 | 2.2167 | 0.0070076 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Twain Harte | Tuolumne | 38.0441 | -120.2479 | MIWUK 1702823548 | MIWUK 1702823548 | 23 | 2411 | Pre | Tier 3
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Base SH | 08W | MAPP | Post-Construction | 0 | 2.1347 | 0 | 2.1347 | 0 | 2.1347 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | Nevada | 0 | 0 | BRUNSWICK 110350070 | BRUNSWICK 110350070 | 7 | 2144 | Pre | Tier 3
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.84905 | 0 | 0.84905 | 0 | 0 | 0 | 0.84905 | 0 | DA | Region 4 - Central Coast | Los Gatos | Santa Clara | 0 | 0 | LOS GATOS 1106LB44 | LOS GATOS 1106LB44 | 841 | 1864 | Pre | Tier 3
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Base SH | 08W | CONS | In-Construction* | 0 | 0.39299 | 0 | 0.39299 | 0 | 0 | 0.39299 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7927 | -122.6592 | MIDDLETOWN 1101CB | MIDDLETOWN 1101CB | 351 | 86 | ECOP - Top 20% | Tier 3
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Base SH | 08W | CONS | In-Construction* | 0 | 1.3786 | 0 | 1.3786 | 0 | 0 | 1.3786 | 0 | 0 | HB | Region 1 - North Coast | Cobb | Lake | 38.7927 | -122.6592 | MIDDLETOWN 11014646 | MIDDLETOWN 11014646 | 205 | 328 | ECOP - Top 20% | Tier 3
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Base SH | 08W | CONS | In-Construction* | 0 | 1.0116 | 0 | 1.0116 | 0 | 0 | 1.0116 | 0 | 0 | HB | Region 1 - North Coast | Cobb | Lake | 38.7927 | -122.6592 | MIDDLETOWN 11014646 | MIDDLETOWN 11014646 | 205 | 328 | ECOP - Top 20% | Tier 3
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Base SH | 08W | FICL | Post-Construction | 0 | 1.5932 | 0 | 1.5932 | 0 | 1.5932 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | Nevada | 39.2906 | -120.9978 | BRUNSWICK 11032200 | BRUNSWICK 11032200 | 105 | 2521 | Pre | Tier 3
35144944 | PSPS - SNEATH LANE 1107 - LR 48338 | Base SH | 08W | PEND | Permitting/Dependency | 0.2553 | 0 | 0 | 0.2553 | 0 | 0 | 0 | 0.2553 | 0 | PN | Region 3 - Bay Area | South San Francisco | San Mateo | 37.6433 | -122.4679 | SNEATH LANE 110748338 | SNEATH LANE 110748338 | 2329 | 3550 | PSPS - Community Resiliency | Tier 2
35145001 | PSPS - CLAYTON 2215 - CB | Base SH | 08W | PEND | Permitting/Dependency | 1.8409 | 0.071023 | 0 | 1.9119 | 0 | 0 | 0 | 1.9119 | 0 | DI | Region 3 - Bay Area | Concord | Contra Costa | 0 | 0 | CLAYTON 2215184604 | CLAYTON 2215184604 | 2831 | 1739 | PSPS - Community Resiliency | Tier 2 & 3
35145003 | PSPS CWSP - MORAGA 1103 - CB | Base SH | 08W | CONS | In-Construction* | 0.24015 | 0.079545 | 0 | 0.3197 | 0 | 0 | 0 | 0.3197 | 0 | DI | Region 3 - Bay Area | Orinda | Contra Costa | 0 | 0 | MORAGA 1103CB | MORAGA 1103CB | 1846 | 2631 | PSPS - Community Resiliency | Tier 2 & 3
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | Base SH | 08W | CONS | In-Construction* | 0.58201 | 0.37216 | 0 | 0.95417 | 0 | 0 | 0.95417 | 0 | 0 | DI | Region 3 - Bay Area | Lafayette | Contra Costa | 37.8624 | -122.0862 | ROSSMOOR 1106CB | ROSSMOOR 1106CB | 1133 | 3259 | PSPS - Community Resiliency | Tier 2 & 3
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Base SH | 08W | PEND | Permitting/Dependency | 3.9451 | 0 | 0 | 3.9451 | 0 | 0 | 0 | 3.9451 | 0 | SI | Region 2 - North East | El Dorado Hills | El Dorado | 0 | 0 | CLARKSVILLE 2104CB | CLARKSVILLE 2104CB | 459 | 134 | PSPS - Community Resiliency | Tier 2
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Base SH | 08W | CONS | In-Construction* | 0.775 | 0 | 0 | 0.775 | 0 | 0.775 | 0 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4896 | -122.6662 | RINCON 1103CB | RINCON 1103CB | 532 | 1755 | PSPS - Scoped | Tier 3
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Base SH | 08W | CONS | In-Construction* | 1.1737 | 0.2 | 0 | 1.3737 | 0 | 1.3737 | 0 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.489 | -122.666 | RINCON 1104CB | RINCON 1104CB | 1257 | 3302 | PSPS - Scoped | Tier 2
35145540 | PSPS - FROGTOWN 1702 - CB | Base SH | 08W | PEND | Permitting/Dependency | 0.53902 | 0.73333 | 0 | 1.2723 | 0 | 0 | 0 | 1.2723 | 0 | ST | Region 5 - Central Valley | Angels Camp | Calaveras | 38.0453 | -120.5253 | FROGTOWN 1702CB | FROGTOWN 1702CB | 2556 | 1316 | PSPS - Scoped | Tier 3
35161152 | OCT2019 BRICEBURG FIRE REBUILD | Base SH | 08W | MAPP | Post-Construction | 0 | 0.081439 | 0 | 0.081439 | 0 | 0.081439 | 0 | 0 | 0 | YO | Region 5 - Central Valley |  |  |  |  | MARIPOSA 2101752630 | MARIPOSA 2101752630 | 2886 | 700 | Remote Grid | Tier 2 & 3
35174085 | OCGC PSPS - FROGTOWN 1702 - LR 36870 | Base SH | 08W | MAPP | Post-Construction | 0 | 0.095265 | 0 | 0.095265 | 0 | 0.095265 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Angels Camp | Calaveras | 38.0878 | -120.5693 | FROGTOWN 170236870 | FROGTOWN 170236870 | 2157 | 2139 | PSPS - Scoped | Tier 3
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Base SH | 08W | ESTS | Estimating | 1.04 | 0 | 0 | 1.04 | 0 | 0 | 0 | 1.04 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35174479 | REMG 749-MIDDLETOWN 1101,ANDERSON SPRNGS | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0 | 3.96 | 3.96 | 0 | 0 | 0 | 3.96 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Base SH | 08W | ADER | Estimating | 4.0903 | 0 | 0 | 4.0903 | 0 | 0 | 0 | 4.0903 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.3526 | -122.5226 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35175853 | REMG 650- PLACERVILLE 2106, RINGTAIL | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0.7 | 0.7 | 0 | 0 | 0 | 0.7 | 0 | SI | Region 2 - North East | Georgetown | El Dorado | 0 | 0 | PLACERVILLE 21061104 | PLACERVILLE 21061104 | 14 | 2131 | Remote Grid Pilot | Tier 3
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | Base SH | 08W | UNSC | Ready for Construction | 0 | 2.22 | 0 | 2.22 | 0 | 0 | 2.2201 | 0 | 0 | NB | Region 1 - North Coast | Saint Helena | Napa | 38.5095 | -122.386 | SILVERADO 210258626 | SILVERADO 210258626 | 218 | 663 | ECOP - Top 20% | Tier 3
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Base SH | 08W | PEND | Permitting/Dependency | 1.2816 | 0 | 0 | 1.2816 | 0 | 0 | 0 | 1.2816 | 0 | NB | Region 1 - North Coast | Nicasio | Marin | 38.046 | -122.646 | LAS GALLINAS A 110599904 | LAS GALLINAS A 110599904 | 187 | 215 | ECOP - Top 20% | Tier 3
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | Base SH | 08W | CONS | In-Construction* | 0 | 1.3337 | 0 | 1.3337 | 0 | 0 | 1.3337 | 0 | 0 | NB | Region 1 - North Coast | Saint Helena | Napa | 38.5057 | -122.401 | SILVERADO 210258626 | SILVERADO 210258626 | 218 | 663 | ECOP - Top 20% | Tier 3
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Base SH | 08W | UNSC | Ready for Construction | 0 | 1.4617 | 0 | 1.4617 | 0 | 0 | 1.4617 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.4108 | -122.4506 | PUEBLO 2102792 | PUEBLO 2102792 | 36 | 951 | ECOP | Tier 3
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | Base SH | 08W | DOCC | Post-Construction | 0 | 2.1869 | 0 | 2.1869 | 0 | 2.1869 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Fish Camp | Mariposa | 37.481 | -119.6374 | OAKHURST 11035120 | OAKHURST 11035120 | 345 | 1975 | Storm Rebuild | Tier 3
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | Base SH | 08W | ADER | Estimating | 1.34 | 0 | 0 | 1.34 | 0 | 0 | 0 | 1.34 | 0 | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.8682 | -121.8573 | CLAYTON 221296224 | CLAYTON 221296224 | 777 | 377 | ECOP - Top 20% | Tier 3
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.27008 | 0 | 0.27008 | 0 | 0 | 0 | 0.27008 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7238 | -122.6197 | MIDDLETOWN 110148212 | MIDDLETOWN 110148212 | 319 | 468 | ECOP - Top 20% | Tier 3
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Base SH | 08W | ESTS | Estimating | 2.04 | 0 | 0 | 2.04 | 0 | 0 | 0 | 2.04 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7238 | -122.6197 | MIDDLETOWN 110148212 | MIDDLETOWN 110148212 | 319 | 468 | ECOP - Top 20% | Tier 3
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | Base SH | 08W | PEND | Permitting/Dependency | 2.0701 | 0 | 0 | 2.0701 | 0 | 0 | 0 | 2.0701 | 0 | NB | Region 1 - North Coast | Pope Valley | Napa | 38.6154 | -122.4315 | SILVERADO 2104726 | SILVERADO 2104726 | 495 | 279 | ECOP - Top 20% | Tier 3
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Base SH | 08W | CONS | In-Construction* | 0 | 5.0519 | 0 | 5.0519 | 0 | 0 | 5.0519 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.739 | -120.9057 | DIAMOND SPRINGS 11071402 | DIAMOND SPRINGS 11071402 | 214 | 811 | ECOP | Tier 3
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Base SH | 08W | PEND | Permitting/Dependency | 0.70871 | 0 | 0 | 0.70871 | 0 | 0 | 0 | 0.70871 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7215 | -120.8714 | DIAMOND SPRINGS 11071402 | DIAMOND SPRINGS 11071402 | 214 | 811 | ECOP | Tier 3
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Base SH | 08W | PEND | Permitting/Dependency | 1.2701 | 0 | 0 | 1.2701 | 0 | 0 | 0 | 1.2701 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.5527 | -122.7132 | FULTON 1107604 | FULTON 1107604 | 196 | 637 | ECOP - Top 20% | Tier 3
35217267 | SH - MARIPOSA 2102 LR 241564 | Base SH | 08W | MAPP | Post-Construction | 0 | 0.93977 | 0 | 0.93977 | 0 | 0.93977 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4871 | -119.9619 | MARIPOSA 2102241564 | MARIPOSA 2102241564 | 2961 | 10 | Top 50 Miles | Tier 2 & 3
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Base SH | 08W | ESTS | Estimating | 0 | 0.42992 | 0 | 0.42992 | 0 | 0 | 0 | 0.42992 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7573 | -122.606 | MIDDLETOWN 1102302610 | MIDDLETOWN 1102302610 | 3061 | 8 | Top 50 Miles | Tier 2
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.55 | 0 | 0.55 | 0 | 0 | 0 | 0.55 | 0 | HB | Region 1 - North Coast | Kelseyville | Lake | 38.9301 | -122.7429 | KONOCTI 1102965078 | KONOCTI 1102965078 | 2774 | 9 | Top 50 Miles | Tier 3
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Base SH | 08W | ESTS | Estimating | 1.54 | 0 | 0 | 1.54 | 0 | 0 | 0 | 1.54 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7561 | -122.6052 | MIDDLETOWN 1103830 | MIDDLETOWN 1103830 | 1322 | 14 | Top 50 Miles | Tier 2 & 3
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Base SH | 08W | UNSC | Ready for Construction | 0.3 | 0 | 0 | 0.3 | 0 | 0 | 0 | 0.3 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6253 | -122.4633 | KESWICK 11011586 | KESWICK 11011586 | 1102 | 7 | Top 50 Miles | Tier 3
35217273 | SH - UPPER LAKE 1101 CB | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.08 | 0 | 1.08 | 0 | 0 | 1.08 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.353 | -122.7722 | UPPER LAKE 1101CB | UPPER LAKE 1101CB | 1534 | 6 | Top 50 Miles | Tier 2
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | Base SH | 08W | PEND | Permitting/Dependency | 1.14 | 0 | 0 | 1.14 | 0 | 0 | 0 | 1.14 | 0 | DI | Region 3 - Bay Area | Concord | Contra Costa | 37.9632 | -121.9407 | TIDEWATER 210614072 | TIDEWATER 210614072 | 2003 | 18 | Top 50 Miles | Tier 2
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | Base SH | 08W | ESTS | Estimating | 1.6701 | 0 | 0 | 1.6701 | 0 | 0 | 0 | 1.6701 | 0 | DI | Region 3 - Bay Area | Pittsburg | Contra Costa | 37.9907 | -121.896 | KIRKER 2104442850 | KIRKER 2104442850 | 1644 | 21 | Top 250 Miles | Tier 2
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | Base SH | 08W | UNSC | Ready for Construction | 0 | 2.4794 | 0 | 2.4794 | 0 | 0 | 1.9491 | 0.5303 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2276 | -119.6896 | COARSEGOLD 2104CB | COARSEGOLD 2104CB | 600 | 22 | Top 250 Miles | Tier 2
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.70265 | 0 | 0.70265 | 0 | 0 | 0.70265 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7514 | -122.6117 | MIDDLETOWN 1101118494 | MIDDLETOWN 1101118494 | 3276 | 23 | Top 250 Miles | Tier 2 & 3
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | Base SH | 08W | ESTS | Estimating | 0 | 2.7269 | 0 | 2.7269 | 0 | 0 | 0 | 2.7269 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | HIGHLANDS 1102628 | HIGHLANDS 1102628 | 496 | 27 | Top 250 Miles | Tier 2 & 3
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Base SH | 08W | CONS | In-Construction* | 0 | 0.92822 | 0.86723 | 1.7955 | 0 | 0.87803 | 0.91742 | 0 | 0 | NV | Region 2 - North East | Feather Falls | Butte | 39.4631 | -121.5149 | WYANDOTTE 110932586 | WYANDOTTE 110932586 | 712 | 29 | Top 250 Miles | Tier 2
35219266 | CWSP - MARIPOSA 2102CB PH 1 | Base SH | 08W | CONS | In-Construction* | 0 | 2.9312 | 0 | 2.9312 | 0 | 0 | 2.9312 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5061 | -120.0049 | MARIPOSA 2102CB | MARIPOSA 2102CB | 1807 | 35 | Top 250 Miles | Tier 2
35219267 | CWSP - MARIPOSA 2102440236 PH1.1 | Base SH | 08W | UNSC | Ready for Construction | 0 | 1.67 | 0 | 1.67 | 0 | 0 | 1.6701 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4858 | -119.9694 | MARIPOSA 2102440236 | MARIPOSA 2102440236 | 3110 | 50 | Top 250 Miles | Tier 2 & 3
35219268 | CWSP - MARIPOSA 210197142 PH 1 | Base SH | 08W | CONS | In-Construction* | 0 | 1.972 | 0 | 1.972 | 0 | 0 | 1.972 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5066 | -120.0082 | MARIPOSA 210197142 | MARIPOSA 210197142 | 1966 | 36 | Top 250 Miles | Tier 2
35219269 | CWSP - VACA DIXON 110540092 PH 1.1 | Base SH | 08W | ESTS | Estimating | 0 | 2.14 | 0 | 2.14 | 0 | 0 | 0 | 2.14 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4159 | -121.9706 | VACA DIXON 110540092 | VACA DIXON 110540092 | 493 | 37 | Top 250 Miles | Tier 2
35219272 | CWSP - MIDDLETOWN 1101481876 | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.92 | 0 | 0.92 | 0 | 0 | 0.92 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7628 | -122.6133 | MIDDLETOWN 1101481876 | MIDDLETOWN 1101481876 | 2766 | 38 | Top 250 Miles | Tier 2 & 3
35219273 | CWSP - VOLTA 110149742 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 3.4324 | 0 | 3.4324 | 0 | 0 | 0 | 3.4324 | 0 | NV | Region 2 - North East | Manton | Tehama | 40.4305 | -121.8716 | VOLTA 110149742 | VOLTA 110149742 | 1993 | 39 | Top 250 Miles | Tier 2
35219275 | CWSP - PUTAH CREEK 110246012 | Base SH | 08W | DOCC | Post-Construction | 0 | 1.0231 | 0 | 1.0231 | 0 | 1.0231 | 0 | 0 | 0 | SA | Region 2 - North East | Winters | Yolo-Solano | 38.4831 | -122.0253 | PUTAH CREEK 110246012 | PUTAH CREEK 110246012 | 3124 | 41 | Top 250 Miles | Tier 2
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | Base SH | 08W | ESTS | Estimating | 2.69 | 0 | 0 | 2.69 | 0 | 0 | 0 | 2.69 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3423 | -122.0077 | VACAVILLE 11046542 | VACAVILLE 11046542 | 1469 | 42 | Top 250 Miles | Tier 3
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.5871 | 0 | 1.5871 | 0 | 0 | 1.5871 | 0 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.362 | -123.1283 | POTTER VALLEY P H 110564118 | POTTER VALLEY P H 110564118 | 2515 | 43 | Top 250 Miles | Tier 2
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Base SH | 08W | PEND | Permitting/Dependency | 2.1025 | 0 | 0 | 2.1025 | 0 | 0 | 0 | 2.1025 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8983 | -120.9827 | MOUNTAIN QUARRIES 21016953 | MOUNTAIN QUARRIES 21016953 | 525 | 45 | Top 250 Miles | Tier 2
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.91 | 0 | 2.91 | 0 | 0 | 0 | 2.91 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.535 | -122.2392 | DESCHUTES 11049718 | DESCHUTES 11049718 | 1758 | 48 | Top 250 Miles | Tier 2
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6.1 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.3962 | 0 | 2.3962 | 0 | 0 | 0 | 2.3962 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6299 | -122.2445 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | Base SH | 08W | UNSE | Scoping/Scoped | 4.3544 | 0 | 0 | 4.3544 | 0 | 0 | 0 | 4.3544 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35219291 | CWSP - VACA DIXON 1101126774 | Base SH | 08W | CONS | In-Construction* | 0 | 0.39432 | 0 | 0.39432 | 0 | 0 | 0.39432 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3973 | -121.9855 | VACA DIXON 1101126774 | VACA DIXON 1101126774 | 3568 | 20 | Top 250 Miles | Tier 2
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Base SH | 08W | ESTS | Estimating | 0.13883 | 0 | 0 | 0.13883 | 0 | 0 | 0 | 0.13883 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7307 | -120.7828 | PLACERVILLE 1112CB | PLACERVILLE 1112CB | 1568 | 2123 | PSPS - Community Resiliency | Tier 2
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Base SH | 08W | ESTS | Estimating | 0.24 | 0 | 0 | 0.24 | 0 | 0 | 0 | 0.24 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7293 | -120.7998 | PLACERVILLE 1112CB | PLACERVILLE 1112CB | 1568 | 2123 | PSPS - Community Resiliency | Tier 2
35219587 | CWSP - MARIPOSA 2102440236 PH1.2 | Base SH | 08W | ESTS | Estimating | 0 | 2.03 | 0 | 2.03 | 0 | 0 | 0 | 2.0299 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4867 | -119.9603 | MARIPOSA 2102440236 | MARIPOSA 2102440236 | 3110 | 50 | Top 250 Miles | Tier 2 & 3
35219588 | CWSP - MARIPOSA 2102440236 PH1.3 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.39 | 0 | 1.39 | 0 | 0 | 0 | 1.39 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4632 | -119.9479 | MARIPOSA 2102440236 | MARIPOSA 2102440236 | 3110 | 50 | Top 250 Miles | Tier 2 & 3
35219589 | CWSP - WILDWOOD 11011454 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.5799 | 0 | 2.5799 | 0 | 0 | 0 | 2.5799 | 0 | NV | Region 2 - North East | Platina | Shasta | 40.3595 | -122.8928 | WILDWOOD 11011454 | WILDWOOD 11011454 | 2353 | 52 | Top 250 Miles | Tier 2
35219590 | CWSP - VACA DIXON 1105965390 | Base SH | 08W | CONS | In-Construction* | 0 | 1.6167 | 0 | 1.6167 | 0 | 0 | 1.6167 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4341 | -121.9915 | VACA DIXON 1105965390 | VACA DIXON 1105965390 | 3088 | 53 | Top 250 Miles | Tier 2
35219591 | CWSP - OLETA 1101754718 PH1.1 | Base SH | 08W | ESTS | Estimating | 0 | 1.2261 | 0 | 1.2261 | 0 | 0 | 0 | 1.2261 | 0 | ST | Region 5 - Central Valley | Plymouth | Amador | 38.4692 | -120.8536 | OLETA 1101754718 | OLETA 1101754718 | 3456 | 54 | Top 250 Miles | Tier 2
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Base SH | 08W | ESTS | Estimating | 1.9299 | 0 | 0 | 1.9299 | 0 | 0 | 0 | 1.9299 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7569 | -122.607 | MIDDLETOWN 1103830 | MIDDLETOWN 1103830 | 1322 | 14 | Top 50 Miles | Tier 2 & 3
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Base SH | 08W | ESTS | Estimating | 0.27992 | 0 | 0 | 0.27992 | 0 | 0 | 0 | 0.27992 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7569 | -122.607 | MIDDLETOWN 1103830 | MIDDLETOWN 1103830 | 1322 | 14 | Top 50 Miles | Tier 2 & 3
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.88996 | 0 | 0.88996 | 0 | 0 | 0.88996 | 0 | 0 | HB | Region 1 - North Coast | Pope Valley | Napa | 38.7569 | -122.607 | MIDDLETOWN 1103830 | MIDDLETOWN 1103830 | 1322 | 14 | Top 50 Miles | Tier 2 & 3
35222234 | REMG 581 - OAKHURST 1101, MIAMI MOUNTAIN | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0.56818 | 0.56818 | 0 | 0 | 0 | 0.56818 | 0 | YO | Region 5 - Central Valley | Oakhurst | Madera | 37.4203 | -119.7086 | [5 empty] | Tier 3
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 2.6 | 2.6 | 0 | 0 | 0 | 2.6 | 0 | FR | Region 5 - Central Valley | Kings Canyon National Pk | Tulare | 36.6537 | -118.986 | DUNLAP 1102778286 | DUNLAP 1102778286 | 2637 | 2738 | Remote Grid Pilot | Tier 3
35223024 | ECOP - SILVERADO 2104 - H05 - LR726 PH 2 | Base SH | 08W | PEND | Permitting/Dependency | 2.24 | 0 | 0 | 2.24 | 0 | 0 | 0 | 2.24 | 0 | NB | Region 1 - North Coast | Pope Valley | Napa | 38.6152 | -122.4293 | SILVERADO 2104726 | SILVERADO 2104726 | 495 | 279 | ECOP - Top 20% | Tier 3
35223026 | ECOP - SILVERADO 2104 - H05 - LR726 PH 3 | Base SH | 08W | PEND | Permitting/Dependency | 1.8 | 0 | 0 | 1.8 | 0 | 0 | 0 | 1.8 | 0 | NB | Region 1 - North Coast | Pope Valley | Napa | 38.6152 | -122.4293 | SILVERADO 2104726 | SILVERADO 2104726 | 495 | 279 | ECOP - Top 20% | Tier 3
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Base SH | 08W | CONS | In-Construction* | 0 | 1.6559 | 0 | 1.6559 | 0 | 0 | 1.6559 | 0 | 0 | NB | Region 1 - North Coast | Pope Valley | Napa | 38.6152 | -122.4293 | SILVERADO 2104726 | SILVERADO 2104726 | 495 | 279 | ECOP - Top 20% | Tier 3
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Base SH | 08W | CONS | In-Construction* | 0 | 1.1987 | 0 | 1.1987 | 0 | 0.29167 | 0.90701 | 0 | 0 | NB | Region 1 - North Coast | Pope Valley | Napa | 38.6152 | -122.4293 | SILVERADO 2104726 | SILVERADO 2104726 | 495 | 279 | ECOP - Top 20% | Tier 3
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Base SH | 08W | ESTS | Estimating | 0.57008 | 0 | 0 | 0.57008 | 0 | 0 | 0 | 0.57008 | 0 | NV | Region 2 - North East | Bangor | Butte | 39.3878 | -121.4038 | BANGOR 1101CB | BANGOR 1101CB | 1606 | 355 | PSPS - Community Resiliency | Tier 2
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Base SH | 08W | ADER | Estimating | 0.44 | 0 | 0 | 0.44 | 0 | 0 | 0 | 0.44 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8858 | -121.0157 | MOUNTAIN QUARRIES 2101CB | MOUNTAIN QUARRIES 2101CB | 412 | 68 | PSPS - Community Resiliency | Tier 2
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Base SH | 08W | PEND | Permitting/Dependency | 0.072159 | 0 | 0.018371 | 0.09053 | 0 | 0 | 0 | 0.09053 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.2376 | -121.0592 | BRUNSWICK 1110CB | BRUNSWICK 1110CB | 2596 | 2134 | PSPS - Community Resiliency | Tier 2
35223037 | PSPS - OAKHURST 1101 - OAKHURST | Base SH | 08W | CONS | In-Construction* | 0 | 0 | 0.0079545 | 0.0079545 | 0 | 0 | 0.0079545 | 0 | 0 | YO | Region 5 - Central Valley | Oakhurst | Madera | 37.3227 | -119.6344 | OAKHURST 1101CB | OAKHURST 1101CB | 568 | 847 | PSPS - Community Resiliency | Tier 3
35223038 | PSPS - MARTELL 1101 - SUTTER CREEK PH1.1 | Base SH | 08W | ESTS | Estimating | 0.72008 | 0 | 0 | 0.72008 | 0 | 0 | 0 | 0.72008 | 0 | ST | Region 5 - Central Valley | Sutter Creek | Amador | 38.3949 | -120.804 | MARTELL 1101CB | MARTELL 1101CB | 1971 | 999 | PSPS - Community Resiliency | Tier 2
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Base SH | 08W | APPR | Estimating | 0.77008 | 0 | 0 | 0.77008 | 0 | 0 | 0 | 0.77008 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.4738 | -121.5307 | WYANDOTTE 1109702710 | WYANDOTTE 1109702710 | 3072 | 218 | PSPS - Community Resiliency | Tier 2
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0.036553 | 0.036553 | 0 | 0 | 0 | 0.036553 | 0 | SI | Region 2 - North East | Downieville | Sierra | 39.5618 | -120.8274 | ALLEGHANY 1101VR816 | ALLEGHANY 1101VR816 | 51 | 2010 | PSPS - Community Resiliency | Tier 3
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.13125 | 0 | 0.13125 | 0 | 0 | 0.13125 | 0 | 0 | NB | Region 1 - North Coast | Calistoga | Napa | 38.5766 | -122.5839 | CALISTOGA 1102184814 | CALISTOGA 1102184814 | 2762 | 3098 | PSPS - Community Resiliency | Tier 2
35223063 | PSPS - DUNBAR 1101 - OAKMONT | Base SH | 08W | UNSE | Scoping/Scoped | 0.3197 | 0 | 0 | 0.3197 | 0 | 0 | 0 | 0.3197 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4438 | -122.602 | DUNBAR 1101CB | DUNBAR 1101CB | 1429 | 2048 | PSPS - Community Resiliency | Tier 2
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | Base SH | 08W | PEND | Permitting/Dependency | 1.5928 | 0 | 0 | 1.5928 | 0 | 0 | 0 | 1.5928 | 0 | NB | Region 1 - North Coast | San Rafael | Marin | 38.0443 | -122.6155 | LAS GALLINAS A 110599904 | LAS GALLINAS A 110599904 | 187 | 215 | ECOP - Top 20% | Tier 3
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.3299 | 0 | 2.3299 | 0 | 0 | 0 | 2.3299 | 0 | NV | Region 2 - North East | Platina | Shasta | 40.3595 | -122.8928 | WILDWOOD 11011454 | WILDWOOD 11011454 | 2353 | 52 | Top 250 Miles | Tier 2
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Base SH | 08W | PEND | Permitting/Dependency | 0.13996 | 0 | 0 | 0.13996 | 0 | 0 | 0 | 0.13996 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 0 | 0 | PLACERVILLE 21067522 | PLACERVILLE 21067522 | 959 | 1363 | PSPS - Community Resiliency | Tier 3
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | Base SH | 08W | CONS | In-Construction* | 0 | 2.8384 | 0.075947 | 2.9144 | 0 | 0 | 2.9144 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3423 | -122.0077 | VACAVILLE 11046542 | VACAVILLE 11046542 | 1469 | 42 | Top 250 Miles | Tier 3
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.88996 | 0 | 0.88996 | 0 | 0 | 0 | 0.88996 | 0 | HB | Region 1 - North Coast | Kelseyville | Lake | 38.93 | -122.7428 | KONOCTI 1102965078 | KONOCTI 1102965078 | 2774 | 9 | Top 50 Miles | Tier 3
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.8 | 0 | 0.8 | 0 | 0 | 0 | 0.8 | 0 | HB | Region 1 - North Coast | Kelseyville | Lake | 38.93 | -122.7428 | KONOCTI 1102965078 | KONOCTI 1102965078 | 2774 | 9 | Top 50 Miles | Tier 3
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.05 | 0 | 1.05 | 0 | 0 | 0 | 1.05 | 0 | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.8879 | -121.8676 | CLAYTON 221296224 | CLAYTON 221296224 | 777 | 377 | ECOP - Top 20% | Tier 3
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.83807 | 0 | 0.83807 | 0 | 0 | 0.83807 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.549 | -122.72 | FULTON 1107604 | FULTON 1107604 | 196 | 637 | ECOP - Top 20% | Tier 3
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.79356 | 0 | 0.79356 | 0 | 0 | 0.79356 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.549 | -122.72 | FULTON 1107604 | FULTON 1107604 | 196 | 637 | ECOP - Top 20% | Tier 3
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.9053 | 0 | 0.9053 | 0 | 0 | 0.9053 | 0 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.549 | -122.72 | FULTON 1107604 | FULTON 1107604 | 196 | 637 | ECOP - Top 20% | Tier 3
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | Base SH | 08W | CONS | In-Construction* | 0 | 1.5214 | 0 | 1.5214 | 0 | 1.5214 | 0 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.535 | -122.2392 | DESCHUTES 11049718 | DESCHUTES 11049718 | 1758 | 48 | Top 250 Miles | Tier 2
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.5424 | 0 | 2.5424 | 0 | 0 | 0 | 2.5424 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | Base SH | 08W | UNSE | Scoping/Scoped | 0.84564 | 0 | 0 | 0.84564 | 0 | 0 | 0 | 0.84564 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | Base SH | 08W | ESTS | Estimating | 2.5314 | 0 | 0 | 2.5314 | 0 | 0 | 0 | 2.5314 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.19 | 0 | 2.19 | 0 | 0 | 0 | 2.19 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35226240 | CWSP - MARIPOSA 210197142 PH 3 | Base SH | 08W | UNSC | Ready for Construction | 0 | 1.1701 | 0 | 1.1701 | 0 | 0 | 1.1701 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5066 | -120.0082 | MARIPOSA 210197142 | MARIPOSA 210197142 | 1966 | 36 | Top 250 Miles | Tier 2
35226241 | CWSP - MARIPOSA 210197142 PH 2 | Base SH | 08W | CONS | In-Construction* | 0 | 1.2045 | 0 | 1.2045 | 0 | 0 | 1.2045 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5066 | -120.0082 | MARIPOSA 210197142 | MARIPOSA 210197142 | 1966 | 36 | Top 250 Miles | Tier 2
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Base SH | 08W | ESTS | Estimating | 1.55 | 0 | 0 | 1.55 | 0 | 0 | 0 | 1.55 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | MIDDLETOWN 110148212 | MIDDLETOWN 110148212 | 319 | 468 | ECOP - Top 20% | Tier 3
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | Base SH | 08W | ESTS | Estimating | 0 | 0.76004 | 0 | 0.76004 | 0 | 0 | 0 | 0.76004 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | MIDDLETOWN 110148212 | MIDDLETOWN 110148212 | 319 | 468 | ECOP - Top 20% | Tier 3
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | Base SH | 08W | ESTS | Estimating | 0 | 1.15 | 0 | 1.15 | 0 | 0 | 0 | 1.15 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | MIDDLETOWN 110148212 | MIDDLETOWN 110148212 | 319 | 468 | ECOP - Top 20% | Tier 3
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.74678 | 0 | 0.74678 | 0 | 0 | 0.74678 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | MIDDLETOWN 110148212 | MIDDLETOWN 110148212 | 319 | 468 | ECOP - Top 20% | Tier 3
35226625 | FRRB - ELK CREEK 1101 LR 2106 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 8.9 | 8.9 | 0 | 0 | 0 | 8.9 | 0 | NV | Region 2 - North East | Elk Creek | Glenn | 39.6064 | -122.5416 | ELK CREEK 11012106 | ELK CREEK 11012106 | 2286 | 340 | FRRB - REMG - 2021 | Tier 2
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | Base SH | 08W | UNSC | In-Construction* | 0 | 0 | 4.15 | 4.15 | 0 | 4.15 | 0 | 0 | 0 | SO | Region 1 - North Coast | Healdsburg | Sonoma | 38.5919 | -122.9622 | FITCH MOUNTAIN 11136751 | FITCH MOUNTAIN 11136751 | 190 | 945 | FRRB - REMG - 2021 | Tier 2
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Base SH | 08W | CONS | In-Construction* | 0 | 0.31761 | 0 | 0.31761 | 0 | 0.31383 | 0.0037879 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6253 | -122.4633 | KESWICK 11011586 | KESWICK 11011586 | 1102 | 7 | Top 50 Miles | Tier 3
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Base SH | 08W | PEND | Permitting/Dependency | 0.82008 | 0 | 0 | 0.82008 | 0 | 0 | 0 | 0.82008 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6253 | -122.4633 | KESWICK 11011586 | KESWICK 11011586 | 1102 | 7 | Top 50 Miles | Tier 3
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Base SH | 08W | PEND | Permitting/Dependency | 4.5 | 0 | 0 | 4.5 | 0 | 0 | 0 | 4.5 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6253 | -122.4633 | KESWICK 11011586 | KESWICK 11011586 | 1102 | 7 | Top 50 Miles | Tier 3
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | Base SH | 08W | CONS | In-Construction* | 0 | 1.4 | 0.033523 | 1.4335 | 0 | 0 | 1.4335 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6253 | -122.4633 | KESWICK 11011586 | KESWICK 11011586 | 1102 | 7 | Top 50 Miles | Tier 3
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Base SH | 08W | CONS | In-Construction* | 0 | 1.5134 | 0 | 1.5134 | 0 | 0.33485 | 1.1786 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6253 | -122.4633 | KESWICK 11011586 | KESWICK 11011586 | 1102 | 7 | Top 50 Miles | Tier 3
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Base SH | 08W | PEND | Permitting/Dependency | 0.10606 | 0 | 0 | 0.10606 | 0 | 0 | 0 | 0.10606 | 0 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.362 | -123.1283 | POTTER VALLEY P H 110564118 | POTTER VALLEY P H 110564118 | 2515 | 43 | Top 250 Miles | Tier 2
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | Base SH | 08W | ESTS | Estimating | 0.57008 | 0 | 0 | 0.57008 | 0 | 0 | 0 | 0.57008 | 0 | NV | Region 2 - North East |  |  |  |  | WYANDOTTE 110932586 | WYANDOTTE 110932586 | 712 | 29 | Top 250 Miles | Tier 2
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Base SH | 08W | ADER | Estimating | 0 | 1.59 | 0 | 1.59 | 0 | 0 | 0 | 1.59 | 0 | NV | Region 2 - North East | Platina | Shasta | 40.3595 | -122.8928 | WILDWOOD 11011454 | WILDWOOD 11011454 | 2353 | 52 | Top 250 Miles | Tier 2
35226799 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0 | 0.19223 | 0.19223 | 0 | 0 | 0 | 0.19223 | 0 | NV | Region 2 - North East | Platina | Shasta | 40.3595 | -122.8928 | WILDWOOD 11011454 | WILDWOOD 11011454 | 2353 | 52 | Top 250 Miles | Tier 2
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | Base SH | 08W | ESTS | Estimating | 0 | 1.99 | 0 | 1.99 | 0 | 0 | 0 | 1.99 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7573 | -122.606 | MIDDLETOWN 1102302610 | MIDDLETOWN 1102302610 | 3061 | 8 | Top 50 Miles | Tier 2
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Base SH | 08W | CONS | In-Construction* | 0 | 2.2956 | 0 | 2.2956 | 0 | 1.8939 | 0.4017 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7201 | -120.861 | DIAMOND SPRINGS 11071402 | DIAMOND SPRINGS 11071402 | 214 | 811 | ECOP | Tier 3
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Base SH | 08W | CONS | In-Construction* | 0 | 1.4795 | 0 | 1.4795 | 0 | 0 | 1.4795 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado | 38.7138 | -120.9394 | SHINGLE SPRINGS 21099372 | SHINGLE SPRINGS 21099372 | 472 | 227 | Top 20% MAVF CPZ | Tier 3
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Base SH | 08W | CONS | In-Construction* | 0 | 1.2939 | 0.22462 | 1.5186 | 0 | 0 | 0 | 1.5186 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado | 38.7138 | -120.9394 | SHINGLE SPRINGS 21099372 | SHINGLE SPRINGS 21099372 | 472 | 227 | Top 20% MAVF CPZ | Tier 3
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Base SH | 08W | UNSC | Ready for Construction | 0 | 2.8341 | 0 | 2.8341 | 0 | 0 | 0 | 2.8341 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado | 38.7138 | -120.9394 | SHINGLE SPRINGS 21099372 | SHINGLE SPRINGS 21099372 | 472 | 227 | Top 20% MAVF CPZ | Tier 3
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Base SH | 08W | PEND | Permitting/Dependency | 1.7799 | 0 | 0 | 1.7799 | 0 | 0 | 0 | 1.7799 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado | 38.7138 | -120.9394 | SHINGLE SPRINGS 21099372 | SHINGLE SPRINGS 21099372 | 472 | 227 | Top 20% MAVF CPZ | Tier 3
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Base SH | 08W | CONS | In-Construction* | 0 | 1.4674 | 0 | 1.4674 | 0 | 0.18542 | 1.282 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado | 38.7138 | -120.9394 | SHINGLE SPRINGS 21099372 | SHINGLE SPRINGS 21099372 | 472 | 227 | Top 20% MAVF CPZ | Tier 3
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Base SH | 08W | CONS | In-Construction* | 0 | 2.0612 | 0 | 2.0612 | 0 | 0.079924 | 1.9812 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado | 38.7138 | -120.9394 | SHINGLE SPRINGS 21099372 | SHINGLE SPRINGS 21099372 | 472 | 227 | Top 20% MAVF CPZ | Tier 3
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.3718 | 0 | 2.3718 | 0 | 0 | 0 | 2.3718 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado | 38.7138 | -120.9394 | SHINGLE SPRINGS 210935598 | SHINGLE SPRINGS 210935598 | 604 | 159 | Top 20% MAVF CPZ | Tier 3
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Base SH | 08W | CONS | In-Construction* | 0 | 1.9174 | 0 | 1.9174 | 0 | 0 | 0 | 1.9174 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado | 38.7138 | -120.9394 | SHINGLE SPRINGS 210935598 | SHINGLE SPRINGS 210935598 | 604 | 159 | Top 20% MAVF CPZ | Tier 3
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Base SH | 08W | ESTS | Estimating | 0 | 2.0076 | 0.36364 | 2.3712 | 0 | 0 | 0 | 2.3712 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado | 38.7138 | -120.9394 | SHINGLE SPRINGS 210935598 | SHINGLE SPRINGS 210935598 | 604 | 159 | Top 20% MAVF CPZ | Tier 3
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Base SH | 08W | CONS | In-Construction* | 0 | 1.0938 | 0 | 1.0938 | 0 | 0 | 0 | 1.0938 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado | 38.7138 | -120.9394 | SHINGLE SPRINGS 210935598 | SHINGLE SPRINGS 210935598 | 604 | 159 | Top 20% MAVF CPZ | Tier 3
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Base SH | 08W | ESTS | Estimating | 0.85 | 0 | 0 | 0.85 | 0 | 0 | 0 | 0.85 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Base SH | 08W | ADER | Estimating | 0 | 0.37992 | 0 | 0.37992 | 0 | 0 | 0 | 0.37992 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Base SH | 08W | APPR | Estimating | 0 | 0.87992 | 0 | 0.87992 | 0 | 0 | 0 | 0.87992 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0 | 0.66004 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Base SH | 08W | APPR | Estimating | 0 | 0.57992 | 0 | 0.57992 | 0 | 0 | 0 | 0.57992 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | Base SH | 08W | CONS | In-Construction* | 0 | 0.52765 | 0 | 0.52765 | 0 | 0 | 0.52765 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.32652 | 0 | 0.32652 | 0 | 0 | 0 | 0.32652 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.23542 | 0 | 0.23542 | 0 | 0 | 0 | 0.23542 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.51818 | 0 | 0.51818 | 0 | 0 | 0 | 0.51818 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | Base SH | 08W | ESTS | Estimating | 0 | 0.41951 | 0 | 0.41951 | 0 | 0 | 0.41951 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | Base SH | 08W | CONS | In-Construction* | 0 | 0.079545 | 0 | 0.079545 | 0 | 0 | 0.079545 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | Base SH | 08W | CONS | In-Construction* | 0 | 0.22121 | 0 | 0.22121 | 0 | 0 | 0.22121 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | Base SH | 08W | ESTS | Estimating | 1.0394 | 0 | 0 | 1.0394 | 0 | 0 | 0 | 1.0394 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | Base SH | 08W | ESTS | Estimating | 0.58883 | 0 | 0 | 0.58883 | 0 | 0 | 0 | 0.58883 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35226900 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH4 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.6517 | 0 | 0.6517 | 0 | 0 | 0 | 0.6517 | 0 | NV | Region 2 - North East | Platina | Shasta | 40.3595 | -122.8928 | WILDWOOD 11011454 | WILDWOOD 11011454 | 2353 | 52 | Top 250 Miles | Tier 2
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | Base SH | 08W | ESTS | Estimating | 0.7214 | 0 | 0 | 0.7214 | 0 | 0 | 0 | 0.7214 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | Base SH | 08W | ESTS | Estimating | 0.43295 | 0 | 0 | 0.43295 | 0 | 0 | 0 | 0.43295 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | Base SH | 08W | ESTS | Estimating | 0.58087 | 0 | 0 | 0.58087 | 0 | 0 | 0 | 0.58087 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | Base SH | 08W | ESTS | Estimating | 0.3483 | 0 | 0 | 0.3483 | 0 | 0 | 0 | 0.3483 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Base SH | 08W | ADER | Estimating | 2.8756 | 0 | 0 | 2.8756 | 0 | 0 | 0 | 2.8756 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Base SH | 08W | ADER | Estimating | 0 | 0.15795 | 0 | 0.15795 | 0 | 0 | 0 | 0.15795 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35227013 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.4 | Base SH | 08W | ESTS | Estimating | 0 | 0.031818 | 0 | 0.031818 | 0 | 0 | 0 | 0.031818 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | Base SH | 08W | ESTS | Estimating | 0 | 0.96705 | 0 | 0.96705 | 0 | 0 | 0 | 0.96705 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Base SH | 08W | ESTS | Estimating | 0 | 1.1955 | 0 | 1.1955 | 0 | 0 | 0 | 1.1955 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Base SH | 08W | ESTS | Estimating | 0 | 0.21667 | 0 | 0.21667 | 0 | 0 | 0 | 0.21667 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Base SH | 08W | ESTS | Estimating | 0.54924 | 0 | 0 | 0.54924 | 0 | 0 | 0 | 0.54924 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.78996 | 0 | 0.78996 | 0 | 0 | 0 | 0.78996 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | MIDDLETOWN 110148212 | MIDDLETOWN 110148212 | 319 | 468 | ECOP - Top 20% | Tier 3
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.6 | 0 | 0.6 | 0 | 0 | 0.6 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | MIDDLETOWN 110148212 | MIDDLETOWN 110148212 | 319 | 468 | ECOP - Top 20% | Tier 3
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.04 | 0 | 1.04 | 0 | 0 | 1.04 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | MIDDLETOWN 110148212 | MIDDLETOWN 110148212 | 319 | 468 | ECOP - Top 20% | Tier 3
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Base SH | 08W | ESTS | Estimating | 1.3801 | 0 | 0 | 1.3801 | 0 | 0 | 0 | 1.3801 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | MIDDLETOWN 110148212 | MIDDLETOWN 110148212 | 319 | 468 | ECOP - Top 20% | Tier 3
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Base SH | 08W | ESTS | Estimating | 1.55 | 0 | 0 | 1.55 | 0 | 0 | 0 | 1.55 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | MIDDLETOWN 110148212 | MIDDLETOWN 110148212 | 319 | 468 | ECOP - Top 20% | Tier 3
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.87121 | 0 | 0.87121 | 0 | 0 | 0.87121 | 0 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.433 | -122.4021 | PUEBLO 2102792 | PUEBLO 2102792 | 36 | 951 | ECOP | Tier 3
35227033 | REMG 702, PUEBLO 2102, DRY CREEK | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 2.3299 | 2.3299 | 0 | 0 | 0 | 2.3299 | 0 | NB | Region 1 - North Coast | Napa | Napa | 38.433 | -122.4021 | PUEBLO 2102792 | PUEBLO 2102792 | 36 | 951 | ECOP | Tier 3
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Base SH | 08W | CONS | In-Construction* | 0 | 1.0898 | 0 | 1.0898 | 0 | 1.09 | -0.00018939 | 0 | 0 | YO | Region 5 - Central Valley | Fish Camp | Mariposa | 37.4809 | -119.6371 | OAKHURST 11035120 | OAKHURST 11035120 | 345 | 1975 | Storm Rebuild | Tier 3
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Base SH | 08W | UNSE | Scoping/Scoped | 1.3201 | 0 | 0 | 1.3201 | 0 | 0 | 0 | 1.3201 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7573 | -122.606 | MIDDLETOWN 1102302610 | MIDDLETOWN 1102302610 | 3061 | 8 | Top 50 Miles | Tier 2
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.73996 | 0 | 0.73996 | 0 | 0 | 0 | 0.73996 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7573 | -122.606 | MIDDLETOWN 1102302610 | MIDDLETOWN 1102302610 | 3061 | 8 | Top 50 Miles | Tier 2
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | Base SH | 08W | ESTS | Estimating | 0.32008 | 0 | 0 | 0.32008 | 0 | 0 | 0 | 0.32008 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7573 | -122.606 | MIDDLETOWN 1102302610 | MIDDLETOWN 1102302610 | 3061 | 8 | Top 50 Miles | Tier 2
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.46004 | 0 | 0.46004 | 0 | 0 | 0 | 0.46004 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7573 | -122.606 | MIDDLETOWN 1102302610 | MIDDLETOWN 1102302610 | 3061 | 8 | Top 50 Miles | Tier 2
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.9 | 0 | 0.9 | 0 | 0 | 0 | 0.9 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7573 | -122.606 | MIDDLETOWN 1102302610 | MIDDLETOWN 1102302610 | 3061 | 8 | Top 50 Miles | Tier 2
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | Base SH | 08W | ESTS | Estimating | 1.01 | 0 | 0 | 1.01 | 0 | 0 | 0 | 1.01 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7561 | -122.6052 | MIDDLETOWN 1103830 | MIDDLETOWN 1103830 | 1322 | 14 | Top 50 Miles | Tier 2 & 3
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | Base SH | 08W | ESTS | Estimating | 1.8 | 0 | 0 | 1.8 | 0 | 0 | 0 | 1.8 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7561 | -122.6052 | MIDDLETOWN 1103830 | MIDDLETOWN 1103830 | 1322 | 14 | Top 50 Miles | Tier 2 & 3
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | Base SH | 08W | ESTS | Estimating | 1.5701 | 0 | 0 | 1.5701 | 0 | 0 | 0 | 1.5701 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7561 | -122.6052 | MIDDLETOWN 1103830 | MIDDLETOWN 1103830 | 1322 | 14 | Top 50 Miles | Tier 2 & 3
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Base SH | 08W | DOCC | Post-Construction | 0 | 0.94943 | 0 | 0.94943 | 0 | 0.95 | -0.00056818 | 0 | 0 | YO | Region 5 - Central Valley | Fish Camp | Mariposa | 37.4809 | -119.6371 | OAKHURST 11035120 | OAKHURST 11035120 | 345 | 1975 | Storm Rebuild | Tier 3
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | Base SH | 08W | CONS | In-Construction* | 0 | 2.2212 | 0 | 2.2212 | 0 | 0.66515 | 1.5561 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2275 | -119.6896 | COARSEGOLD 2104CB | COARSEGOLD 210410335 | 600 | 66 | Top 250 Miles | Tier 2
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | Base SH | 08W | CONS | In-Construction* | 0 | 1.729 | 0 | 1.729 | 0 | 0 | 1.729 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2275 | -119.6896 | COARSEGOLD 2104CB | COARSEGOLD 210410335 | 600 | 66 | Top 250 Miles | Tier 2
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | Base SH | 08W | CONS | In-Construction* | 0 | 1.7341 | 0 | 1.7341 | 0 | 0 | 1.7341 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2275 | -119.6896 | COARSEGOLD 2104CB | COARSEGOLD 210410335 | 600 | 66 | Top 250 Miles | Tier 2
35227263 | CWSP - MARIPOSA 2102CB PH 2 | Base SH | 08W | CONS | In-Construction* | 0 | 2.5172 | 0 | 2.5172 | 0 | 0.093561 | 2.4237 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5061 | -120.0049 | MARIPOSA 2102CB | MARIPOSA 2102CB | 1807 | 35 | Top 250 Miles | Tier 2
35227651 | CWSP - VACAVILLE 11046542 PH 1.2 | Base SH | 08W | UNSC | Ready for Construction | 0 | 2.6951 | 0 | 2.6951 | 0 | 0 | 2.6951 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3423 | -122.0077 | VACAVILLE 11046542 | VACAVILLE 11046542 | 1469 | 42 | Top 250 Miles | Tier 3
35227652 | CWSP - VACAVILLE 11046542 PH 1.3 | Base SH | 08W | PEND | Permitting/Dependency | 0.55 | 0 | 0 | 0.55 | 0 | 0 | 0 | 0.55 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3423 | -122.0077 | VACAVILLE 11046542 | VACAVILLE 11046542 | 1469 | 42 | Top 250 Miles | Tier 3
35227653 | CWSP - VACAVILLE 11046542 PH 1.4 | Base SH | 08W | UNSC | Ready for Construction | 0 | 2.646 | 0 | 2.646 | 0 | 0 | 2.646 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3423 | -122.0077 | VACAVILLE 11046542 | VACAVILLE 11046542 | 1469 | 42 | Top 250 Miles | Tier 3
35227654 | CWSP - VACAVILLE 11046542 PH 1.5 | Base SH | 08W | ESTS | Estimating | 0 | 0 | 0.52992 | 0.52992 | 0 | 0 | 0 | 0.52992 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3423 | -122.0077 | VACAVILLE 11046542 | VACAVILLE 11046542 | 1469 | 42 | Top 250 Miles | Tier 3
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 3.2598 | 3.2598 | 0 | 0 | 0 | 3.2598 | 0 | DI | Region 3 - Bay Area | Pittsburg | Contra Costa | 37.9907 | -121.896 | KIRKER 2104442850 | KIRKER 2104442850 | 1644 | 21 | Top 250 Miles | Tier 2
35227656 | CWSP - VACAVILLE 11046542 - PH 2.3 | Base SH | 08W | ESTS | Estimating | 1.3089 | 0 | 0 | 1.3089 | 0 | 0 | 0 | 1.3089 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3423 | -122.0077 | VACAVILLE 11046542 | VACAVILLE 11046542 | 1469 | 42 | Top 250 Miles | Tier 3
35227657 | CWSP - VACAVILLE 11046542 - PH 2.4 | Base SH | 08W | CONS | In-Construction* | 0 | 0.44186 | 0 | 0.44186 | 0 | 0 | 0.44186 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3423 | -122.0077 | VACAVILLE 11046542 | VACAVILLE 11046542 | 1469 | 42 | Top 250 Miles | Tier 3
35227658 | CWSP - VACAVILLE 11046542 - PH 2.5 | Base SH | 08W | ADER | Estimating | 0 | 0.41307 | 0 | 0.41307 | 0 | 0 | 0 | 0.41307 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3423 | -122.0077 | VACAVILLE 11046542 | VACAVILLE 11046542 | 1469 | 42 | Top 250 Miles | Tier 3
35227659 | CWSP - VACAVILLE 11046542 - PH 2.6 | Base SH | 08W | CONS | In-Construction* | 0 | 0.30682 | 0 | 0.30682 | 0 | 0 | 0.30682 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3423 | -122.0077 | VACAVILLE 11046542 | VACAVILLE 11046542 | 1469 | 42 | Top 250 Miles | Tier 3
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.2 | 0 | 0.2 | 0 | 0 | 0.2 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7561 | -122.6052 | MIDDLETOWN 1103830 | MIDDLETOWN 1103830 | 1322 | 14 | Top 50 Miles | Tier 2 & 3
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.5201 | 0 | 1.5201 | 0 | 0 | 1.5201 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7561 | -122.6052 | MIDDLETOWN 1103830 | MIDDLETOWN 1103830 | 1322 | 14 | Top 50 Miles | Tier 2 & 3
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.09 | 0 | 1.09 | 0 | 0 | 1.09 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7561 | -122.6052 | MIDDLETOWN 1103830 | MIDDLETOWN 1103830 | 1322 | 14 | Top 50 Miles | Tier 2 & 3
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.78996 | 0 | 0.78996 | 0 | 0 | 0.78996 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7561 | -122.6052 | MIDDLETOWN 1103830 | MIDDLETOWN 1103830 | 1322 | 14 | Top 50 Miles | Tier 2 & 3
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Base SH | 08W | ESTS | Estimating | 0.62008 | 0 | 0 | 0.62008 | 0 | 0 | 0 | 0.62008 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7561 | -122.6052 | MIDDLETOWN 1103830 | MIDDLETOWN 1103830 | 1322 | 14 | Top 50 Miles | Tier 2 & 3
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.52008 | 0 | 0.52008 | 0 | 0 | 0.52008 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7561 | -122.6052 | MIDDLETOWN 1103830 | MIDDLETOWN 1103830 | 1322 | 14 | Top 50 Miles | Tier 2 & 3
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.97992 | 0 | 0.97992 | 0 | 0 | 0.97992 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7561 | -122.6052 | MIDDLETOWN 1103830 | MIDDLETOWN 1103830 | 1322 | 14 | Top 50 Miles | Tier 2 & 3
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | Base SH | 08W | ESTS | Estimating | 0 | 0.4 | 0 | 0.4 | 0 | 0 | 0 | 0.4 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7561 | -122.6052 | MIDDLETOWN 1103830 | MIDDLETOWN 1103830 | 1322 | 14 | Top 50 Miles | Tier 2 & 3
35227870 | CWSP - VACAVILLE 11046542 - PH 2.2 | Base SH | 08W | ESTS | Estimating | 1.4848 | 0 | 0 | 1.4848 | 0 | 0 | 0 | 1.4848 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3423 | -122.0077 | VACAVILLE 11046542 | VACAVILLE 11046542 | 1469 | 42 | Top 250 Miles | Tier 3
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Base SH | 08W | ESTS | Estimating | 1.49 | 0 | 0 | 1.49 | 0 | 0 | 0 | 1.49 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7561 | -122.6052 | MIDDLETOWN 1103830 | MIDDLETOWN 1103830 | 1322 | 14 | Top 50 Miles | Tier 2 & 3
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.62992 | 0 | 0.62992 | 0 | 0 | 0.62992 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7561 | -122.6052 | MIDDLETOWN 1103830 | MIDDLETOWN 1103830 | 1322 | 14 | Top 50 Miles | Tier 2 & 3
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 3.45 | 3.45 | 0 | 0 | 0 | 3.45 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7561 | -122.6052 | MIDDLETOWN 1103830 | MIDDLETOWN 1103830 | 1322 | 14 | Top 50 Miles | Tier 2 & 3
35228449 | RIO DELL STORM REBUILD | Base SH | 08W | UNSC | In-Construction* | 0 | 2.8061 | 0 | 2.8061 | 0 | 2.8061 | 0 | 0 | 0 | HB | Region 1 - North Coast | Myers Flat | Humboldt | 40.3679 | -124.0594 | Rio Dell 11024230 | Rio Dell 11024230 | 2536 | 585 | Storm Rebuild | Tier 2
35228774 | PSPS - DUNBAR 1101 - OAKMONT PH 2 | Base SH | 08W | UNSE | Scoping/Scoped | 1.0008 | 0 | 0 | 1.0008 | 0 | 0 | 0 | 1.0008 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4438 | -122.602 | DUNBAR 1101CB | DUNBAR 1101CB | 1429 | 2048 | PSPS - Community Resiliency | Tier 2
35228775 | PSPS - DUNBAR 1101 - OAKMONT PH 3 | Base SH | 08W | UNSE | Scoping/Scoped | 0.90341 | 0 | 0 | 0.90341 | 0 | 0 | 0 | 0.90341 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4438 | -122.602 | DUNBAR 1101CB | DUNBAR 1101CB | 1429 | 2048 | PSPS - Community Resiliency | Tier 2
35229051 | REMG 299 - CORNING 1102, TURRI ELLIS | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 2 | 0 | NV | Region 2 - North East | Flournoy | Tehama | 0 | 0 | CORNING 110253184 | CORNING 110253184 | 1844 | 413 | Remote Grid Pilot | Tier 3
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Base SH | 08W | PEND | Permitting/Dependency | 0.5858 | 0 | 0 | 0.5858 | 0 | 0 | 0 | 0.5858 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7514 | -122.6117 | MIDDLETOWN 1101118494 | MIDDLETOWN 1101118494 | 3276 | 23 | Top 250 Miles | Tier 2 & 3
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | Base SH | 08W | ESTS | Estimating | 1.3 | 0 | 0 | 1.3 | 0 | 0 | 0 | 1.3 | 0 | DI | Region 3 - Bay Area | Concord | Contra Costa | 37.9632 | -121.9407 | TIDEWATER 210614072 | TIDEWATER 210614072 | 2003 | 18 | Top 50 Miles | Tier 2
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | Base SH | 08W | MAPP | Post-Construction | 0 | 1.1009 | 0.034848 | 1.1358 | 0 | 1.1358 | 0 | 0 | 0 | DI | Region 3 - Bay Area | Concord | Contra Costa | 37.9632 | -121.9407 | TIDEWATER 210614072 | TIDEWATER 210614072 | 2003 | 18 | Top 50 Miles | Tier 2
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Base SH | 08W | CONS | In-Construction* | 0 | 1.4093 | 0 | 1.4093 | 0 | 0 | 1.4093 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado | 38.7138 | -120.9394 | SHINGLE SPRINGS 21099372 | SHINGLE SPRINGS 21099372 | 472 | 227 | Top 20% MAVF CPZ | Tier 3
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.37121 | 0 | 0.37121 | 0 | 0 | 0 | 0.37121 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado | 38.7138 | -120.9394 | SHINGLE SPRINGS 21099372 | SHINGLE SPRINGS 21099372 | 472 | 227 | Top 20% MAVF CPZ | Tier 3
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Base SH | 08W | CONS | In-Construction* | 0 | 1.7477 | 0.15758 | 1.9053 | 0 | 0 | 1.9053 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado | 38.7138 | -120.9394 | SHINGLE SPRINGS 21099372 | SHINGLE SPRINGS 21099372 | 472 | 227 | Top 20% MAVF CPZ | Tier 3
35231620 | CWSP - HIGHLANDS 1102628 PH 1.2 | Base SH | 08W | ESTS | Estimating | 2.6782 | 0 | 0 | 2.6782 | 0 | 0 | 0 | 2.6782 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | HIGHLANDS 1102628 | HIGHLANDS 1102628 | 496 | 27 | Top 250 Miles | Tier 2 & 3
35231621 | CWSP - HIGHLANDS 1102628 PH 1.3 | Base SH | 08W | ESTS | Estimating | 1.3655 | 0 | 0 | 1.3655 | 0 | 0 | 0 | 1.3655 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | HIGHLANDS 1102628 | HIGHLANDS 1102628 | 496 | 27 | Top 250 Miles | Tier 2 & 3
35231622 | CWSP - HIGHLANDS 1102628 PH 1.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0.88996 | 0.88996 | 0 | 0 | 0 | 0.88996 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | HIGHLANDS 1102628 | HIGHLANDS 1102628 | 496 | 27 | Top 250 Miles | Tier 2 & 3
35231623 | CWSP - HIGHLANDS 1102628 PH 1.5 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 1.3799 | 1.3799 | 0 | 0 | 0 | 1.3799 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | HIGHLANDS 1102628 | HIGHLANDS 1102628 | 496 | 27 | Top 250 Miles | Tier 2 & 3
35231624 | CWSP - HIGHLANDS 1102628 PH 1.6 | Base SH | 08W | ESTS | Estimating | 0 | 0 | 4.2701 | 4.2701 | 0 | 0 | 0 | 4.2701 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | HIGHLANDS 1102628 | HIGHLANDS 1102628 | 496 | 27 | Top 250 Miles | Tier 2 & 3
35231625 | CWSP - HIGHLANDS 1102628 PH 1.7 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0.8 | 0.8 | 0 | 0 | 0 | 0.8 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | HIGHLANDS 1102628 | HIGHLANDS 1102628 | 496 | 27 | Top 250 Miles | Tier 2 & 3
35231626 | CWSP - HIGHLANDS 1102628 PH 1.8 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.68314 | 0 | 0.68314 | 0 | 0 | 0 | 0.68314 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | HIGHLANDS 1102628 | HIGHLANDS 1102628 | 496 | 27 | Top 250 Miles | Tier 2 & 3
35231627 | CWSP - HIGHLANDS 1102628 PH 1.9 | Base SH | 08W | ESTS | Estimating | 0 | 0.39867 | 0 | 0.39867 | 0 | 0 | 0 | 0.39867 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | HIGHLANDS 1102628 | HIGHLANDS 1102628 | 496 | 27 | Top 250 Miles | Tier 2 & 3
35231628 | CWSP - HIGHLANDS 1102628 PH 1.10 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 1.8799 | 1.8799 | 0 | 0 | 0 | 1.8799 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | HIGHLANDS 1102628 | HIGHLANDS 1102628 | 496 | 27 | Top 250 Miles | Tier 2 & 3
35231629 | CWSP - HIGHLANDS 1102628 PH 1.11 | Base SH | 08W | ESTS | Estimating | 0 | 0 | 2.7701 | 2.7701 | 0 | 0 | 0 | 2.7701 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | HIGHLANDS 1102628 | HIGHLANDS 1102628 | 496 | 27 | Top 250 Miles | Tier 2 & 3
35231630 | CWSP - HIGHLANDS 1102628 PH 1.12 | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.36326 | 0 | 0.36326 | 0 | 0 | 0.36345 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | HIGHLANDS 1102628 | HIGHLANDS 1102628 | 496 | 27 | Top 250 Miles | Tier 2 & 3
35231631 | CWSP - HIGHLANDS 1102628 PH 1.13 | Base SH | 08W | ESTS | Estimating | 0 | 0.46686 | 0 | 0.46686 | 0 | 0 | 0 | 0.46686 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | HIGHLANDS 1102628 | HIGHLANDS 1102628 | 496 | 27 | Top 250 Miles | Tier 2 & 3
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Base SH | 08W | FICL | Post-Construction | 0 | 0.61269 | 0 | 0.61269 | 0 | 0.61269 | 0 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado | 38.7138 | -120.9394 | SHINGLE SPRINGS 21099372 | SHINGLE SPRINGS 21099372 | 472 | 227 | Top 20% MAVF CPZ | Tier 3
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 | Base SH | 08W | CONS | In-Construction* | 0 | 3.1706 | 0 | 3.1706 | 0 | 0 | 3.1706 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.535 | -122.2392 | DESCHUTES 11049718 | DESCHUTES 11049718 | 1758 | 48 | Top 250 Miles | Tier 2
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 | Base SH | 08W | MAPP | Post-Construction | 0 | 1.0093 | 0 | 1.0093 | 0 | 1.0093 | 0 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.535 | -122.2392 | DESCHUTES 11049718 | DESCHUTES 11049718 | 1758 | 48 | Top 250 Miles | Tier 2
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 | Base SH | 08W | CONS | In-Construction* | 0 | 3.4282 | 0 | 3.4282 | 0 | 0.053977 | 3.3742 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.535 | -122.2392 | DESCHUTES 11049718 | DESCHUTES 11049718 | 1758 | 48 | Top 250 Miles | Tier 2
35232445 | CWSP - DESCHUTES 11049718 PH 2.5 | Base SH | 08W | CONS | In-Construction* | 0 | 2.6036 | 0 | 2.6036 | 0 | 0.45246 | 2.1511 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.535 | -122.2392 | DESCHUTES 11049718 | DESCHUTES 11049718 | 1758 | 48 | Top 250 Miles | Tier 2
35232650 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.2 | Base SH | 08W | PEND | Permitting/Dependency | 1.3447 | 0 | 0 | 1.3447 | 0 | 0 | 0 | 1.3447 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8983 | -120.9827 | MOUNTAIN QUARRIES 21016953 | MOUNTAIN QUARRIES 21016953 | 525 | 45 | Top 250 Miles | Tier 2
35232651 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.3 | Base SH | 08W | UNSC | Ready for Construction | 0 | 1.7182 | 0 | 1.7182 | 0 | 0 | 1.7182 | 0 | 0 | SI | Region 2 - North East | Cool | El Dorado | 38.8983 | -120.9827 | MOUNTAIN QUARRIES 21016953 | MOUNTAIN QUARRIES 21016953 | 525 | 45 | Top 250 Miles | Tier 2
35232960 | CWSP - DESCHUTES 11049718 PH1.2 | Base SH | 08W | UNSC | Ready for Construction | 0 | 2.9299 | 0 | 2.9299 | 0 | 0 | 2.9299 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.535 | -122.2392 | DESCHUTES 11049718 | DESCHUTES 11049718 | 1758 | 48 | Top 250 Miles | Tier 2
35233947 | CWSP - OREGON TRAIL 110335002 PH1.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.8436 | 0 | 1.8436 | 0 | 0 | 0 | 1.8436 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35233948 | CWSP - OREGON TRAIL 110335002 PH1.3 | Base SH | 08W | UNSE | Scoping/Scoped | 2.5871 | 0 | 0 | 2.5871 | 0 | 0 | 0 | 2.5871 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35233949 | CWSP - OREGON TRAIL 110335002 PH1.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.9769 | 0 | 1.9769 | 0 | 0 | 0 | 1.9769 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35233950 | CWSP - OREGON TRAIL 110335002 PH1.5 | Base SH | 08W | UNSE | Scoping/Scoped | 2.8943 | 0 | 0 | 2.8943 | 0 | 0 | 0 | 2.8943 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35233951 | CWSP - OREGON TRAIL 110335002 PH1.6 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.5648 | 0 | 1.5648 | 0 | 0 | 0 | 1.5648 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35233952 | CWSP - OREGON TRAIL 110335002 PH2.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.1616 | 0 | 2.1616 | 0 | 0 | 0 | 2.1616 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35233953 | CWSP - OREGON TRAIL 110335002 PH2.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0.84034 | 0 | 0 | 0.84034 | 0 | 0 | 0 | 0.84034 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35233954 | CWSP - OREGON TRAIL 110335002 PH3.2 | Base SH | 08W | ESTS | Estimating | 0 | 0.21212 | 0 | 0.21212 | 0 | 0 | 0 | 0.21212 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35233955 | CWSP - OREGON TRAIL 110335002 PH2.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0.54924 | 0 | 0 | 0.54924 | 0 | 0 | 0 | 0.54924 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35233956 | CWSP - OREGON TRAIL 110335002 PH3.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.25455 | 0 | 0.25455 | 0 | 0 | 0 | 0.25455 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35233957 | CWSP - OREGON TRAIL 110335002 PH2.5 | Base SH | 08W | UNSE | Scoping/Scoped | 0.10208 | 0 | 0 | 0.10208 | 0 | 0 | 0 | 0.10208 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35233958 | CWSP - OREGON TRAIL 110335002 PH3.4 | Base SH | 08W | ESTS | Estimating | 0 | 0.20814 | 0 | 0.20814 | 0 | 0 | 0 | 0.20814 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35233959 | CWSP - OREGON TRAIL 110335002 PH2.6 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.34602 | 0 | 0.34602 | 0 | 0 | 0 | 0.34602 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35233995 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.2 | Base SH | 08W | PEND | Permitting/Dependency | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 0 | 0 | PLACERVILLE 21067522 | PLACERVILLE 21067522 | 959 | 1363 | PSPS - Community Resiliency | Tier 3
35233996 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.3 | Base SH | 08W | ESTS | Estimating | 0.71019 | 0 | 0 | 0.71019 | 0 | 0 | 0 | 0.71019 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 0 | 0 | PLACERVILLE 21067522 | PLACERVILLE 21067522 | 959 | 1363 | PSPS - Community Resiliency | Tier 3
35234284 | PSPS - MARTELL 1101 - SUTTER CREEK PH1.2 | Base SH | 08W | ESTS | Estimating | 0 | 0.32992 | 0 | 0.32992 | 0 | 0 | 0 | 0.32992 | 0 | ST | Region 5 - Central Valley | Sutter Creek | Amador | 38.3949 | -120.804 | MARTELL 1101CB | MARTELL 1101CB | 1971 | 999 | PSPS - Community Resiliency | Tier 2
35234380 | CWSP - OREGON TRAIL 110335002 PH3.5 | Base SH | 08W | ESTS | Estimating | 0 | 2.2419 | 0 | 2.2419 | 0 | 0 | 0 | 2.2419 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35234381 | CWSP - OREGON TRAIL 110335002 PH2.7 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.5468 | 0 | 1.5468 | 0 | 0 | 0 | 1.5468 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35234382 | CWSP - OREGON TRAIL 110335002 PH2.8 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.5875 | 0 | 1.5875 | 0 | 0 | 0 | 1.5875 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35234383 | CWSP - OREGON TRAIL 110335002 PH3.6 | Base SH | 08W | UNSE | Scoping/Scoped | 1.1985 | 0 | 0 | 1.1985 | 0 | 0 | 0 | 1.1985 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35234384 | CWSP - OREGON TRAIL 110335002 PH3.7 | Base SH | 08W | ESTS | Estimating | 0 | 0.058144 | 0 | 0.058144 | 0 | 0 | 0 | 0.058144 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35234385 | CWSP - OREGON TRAIL 110335002 PH3.8 | Base SH | 08W | ESTS | Estimating | 0 | 0.67443 | 0 | 0.67443 | 0 | 0 | 0 | 0.67443 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35234386 | CWSP - OREGON TRAIL 110335002 PH3.9 | Base SH | 08W | ESTS | Estimating | 0 | 0.85777 | 0 | 0.85777 | 0 | 0 | 0 | 0.85777 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35234387 | CWSP - OREGON TRAIL 110335002 PH4.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.93996 | 0 | 0.93996 | 0 | 0 | 0 | 0.93996 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35234388 | CWSP - OREGON TRAIL 110335002 PH4.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.0402 | 0 | 2.0402 | 0 | 0 | 0 | 2.0402 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35234389 | CWSP - OREGON TRAIL 110335002 PH4.4 | Base SH | 08W | ESTS | Estimating | 0 | 0.9 | 0 | 0.9 | 0 | 0 | 0 | 0.9 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35234390 | CWSP - OREGON TRAIL 110335002 PH4.5 | Base SH | 08W | ESTS | Estimating | 0 | 0.52008 | 0 | 0.52008 | 0 | 0 | 0 | 0.52008 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35234391 | CWSP - OREGON TRAIL 110335002 PH4.6 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.26 | 0 | 1.26 | 0 | 0 | 0 | 1.26 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35234392 | CWSP - OREGON TRAIL 110335002 PH4.7 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.66 | 0 | 1.66 | 0 | 0 | 0 | 1.66 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35234393 | CWSP - OREGON TRAIL 110335002 PH5.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.4201 | 0 | 2.4201 | 0 | 0 | 0 | 2.4201 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35234394 | CWSP - OREGON TRAIL 110335002 PH5.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.79 | 0 | 1.79 | 0 | 0 | 0 | 1.79 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35234395 | CWSP - OREGON TRAIL 110335002 PH5.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.71 | 0 | 2.71 | 0 | 0 | 0 | 2.71 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35234396 | CWSP - OREGON TRAIL 110335002 PH5.5 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.69 | 0 | 1.69 | 0 | 0 | 0 | 1.69 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35234397 | CWSP - OREGON TRAIL 110335002 PH5.6 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.72008 | 0 | 0.72008 | 0 | 0 | 0 | 0.72008 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35234398 | CWSP - OREGON TRAIL 110335002 PHASE 6.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.8525 | 0 | 2.8525 | 0 | 0 | 0 | 2.8525 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35234399 | CWSP - OREGON TRAIL 110335002 PHASE 6.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0.48011 | 0 | 0 | 0.48011 | 0 | 0 | 0 | 0.48011 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35234400 | CWSP - OREGON TRAIL 110335002 PHASE 6.4 | Base SH | 08W | ESTS | Estimating | 0 | 1.39 | 0 | 1.39 | 0 | 0 | 0 | 1.39 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35234401 | CWSP - OREGON TRAIL 110335002 PHASE 6.5 | Base SH | 08W | ESTS | Estimating | 0 | 1.85 | 0 | 1.85 | 0 | 0 | 0 | 1.85 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 | Top 250 Miles | Tier 2
35234526 | PSPS - MARTELL 1101 - SUTTER CREEK PH1.3 | Base SH | 08W | ESTS | Estimating | 0.58996 | 0 | 0 | 0.58996 | 0 | 0 | 0 | 0.58996 | 0 | ST | Region 5 - Central Valley | Sutter Creek | Amador | 38.3949 | -120.804 | MARTELL 1101CB | MARTELL 1101CB | 1971 | 999 | PSPS - Community Resiliency | Tier 2
35234527 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0.075947 | 0 | 0 | 0.075947 | 0 | 0 | 0 | 0.075947 | 0 | SI | Region 2 - North East | Downieville | Sierra | 39.5618 | -120.8274 | ALLEGHANY 1101VR816 | ALLEGHANY 1101VR816 | 51 | 2010 | PSPS - Community Resiliency | Tier 3
35234528 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0.035985 | 0 | 0 | 0.035985 | 0 | 0 | 0 | 0.035985 | 0 | SI | Region 2 - North East | Downieville | Sierra | 39.5618 | -120.8274 | ALLEGHANY 1101VR816 | ALLEGHANY 1101VR816 | 51 | 2010 | PSPS - Community Resiliency | Tier 3
35234529 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0.70833 | 0 | 0 | 0.70833 | 0 | 0 | 0 | 0.70833 | 0 | SI | Region 2 - North East | Downieville | Sierra | 39.5618 | -120.8274 | ALLEGHANY 1101VR816 | ALLEGHANY 1101VR816 | 51 | 2010 | PSPS - Community Resiliency | Tier 3
35234756 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.9 | Base SH | 08W | ESTS | Estimating | 2.782 | 0 | 0 | 2.782 | 0 | 0 | 0 | 2.782 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35234758 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.10 | Base SH | 08W | ESTS | Estimating | 0.58201 | 0 | 0 | 0.58201 | 0 | 0 | 0 | 0.58201 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35234862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.11 | Base SH | 08W | ESTS | Estimating | 0.079924 | 0 | 0 | 0.079924 | 0 | 0 | 0 | 0.079924 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35234865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.12 | Base SH | 08W | ESTS | Estimating | 0.64754 | 0 | 0 | 0.64754 | 0 | 0 | 0 | 0.64754 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35236437 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.7 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.37841 | 0 | 0.37841 | 0 | 0 | 0.37841 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | MIDDLETOWN 110148212 | MIDDLETOWN 110148212 | 319 | 468 | ECOP - Top 20% | Tier 3
35236438 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.8 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.5197 | 0 | 0.5197 | 0 | 0 | 0.5197 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | MIDDLETOWN 110148212 | MIDDLETOWN 110148212 | 319 | 468 | ECOP - Top 20% | Tier 3
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | Base SH | 08W | APPR | Estimating | 1.1201 | 0 | 0 | 1.1201 | 0 | 0 | 0 | 1.1201 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 | Base SH | 08W | ADER | Estimating | 0.47992 | 0 | 0 | 0.47992 | 0 | 0 | 0 | 0.47992 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 | ECOP - Top 20% | Tier 3
35236661 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.22008 | 0 | 0.22008 | 0 | 0 | 0.22008 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7561 | -122.6052 | MIDDLETOWN 1103830 | MIDDLETOWN 1103830 | 1322 | 14 | Top 50 Miles | Tier 2 & 3
35236662 | CWSP - OLETA 1101754718 PH 1.2 | Base SH | 08W | CONS | In-Construction* | 0 | 1.6246 | 0 | 1.6246 | 0 | 0 | 1.6246 | 0 | 0 | ST | Region 5 - Central Valley | Plymouth | Amador | 38.4692 | -120.8536 | OLETA 1101754718 | OLETA 1101754718 | 3456 | 54 | Top 250 Miles | Tier 2
35237258 | CWSP - VACA DIXON 110540092 PH 1.2 | Base SH | 08W | ESTS | Estimating | 0 | 2.15 | 0 | 2.15 | 0 | 0 | 0 | 2.15 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4159 | -121.9706 | VACA DIXON 110540092 | VACA DIXON 110540092 | 493 | 37 | Top 250 Miles | Tier 2
35237259 | CWSP - VACA DIXON 110540092 PH 1.3 | Base SH | 08W | ESTS | Estimating | 0 | 4.0453 | 0 | 4.0453 | 0 | 0 | 0 | 4.0453 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4159 | -121.9706 | VACA DIXON 110540092 | VACA DIXON 110540092 | 493 | 37 | Top 250 Miles | Tier 2
35237360 | CWSP - VACA DIXON 110540092 PH 1.4 | Base SH | 08W | ESTS | Estimating | 0 | 3.01 | 0 | 3.01 | 0 | 0 | 0 | 3.01 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4159 | -121.9706 | VACA DIXON 110540092 | VACA DIXON 110540092 | 493 | 37 | Top 250 Miles | Tier 2
35237361 | CWSP - VACA DIXON 110540092 PH 1.5 | Base SH | 08W | ESTS | Estimating | 0 | 2.8701 | 0 | 2.8701 | 0 | 0 | 0 | 2.8701 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4159 | -121.9706 | VACA DIXON 110540092 | VACA DIXON 110540092 | 493 | 37 | Top 250 Miles | Tier 2
35237364 | CWSP - VACA DIXON 110540092 PH 1.6 | Base SH | 08W | ESTS | Estimating | 0 | 3.0299 | 0 | 3.0299 | 0 | 0 | 0 | 3.0299 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4159 | -121.9706 | VACA DIXON 110540092 | VACA DIXON 110540092 | 493 | 37 | Top 250 Miles | Tier 2
35237365 | CWSP - VACA DIXON 110540092 PH 1.7 | Base SH | 08W | ESTS | Estimating | 0 | 2.5699 | 0 | 2.5699 | 0 | 0 | 0 | 2.5699 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4159 | -121.9706 | VACA DIXON 110540092 | VACA DIXON 110540092 | 493 | 37 | Top 250 Miles | Tier 2
35237366 | CWSP - VACA DIXON 110540092 PH 1.8 | Base SH | 08W | ESTS | Estimating | 0 | 2.2299 | 0 | 2.2299 | 0 | 0 | 0 | 2.2299 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4159 | -121.9706 | VACA DIXON 110540092 | VACA DIXON 110540092 | 493 | 37 | Top 250 Miles | Tier 2
35237368 | CWSP - VACA DIXON 110540092 PH 1.9 | Base SH | 08W | ESTS | Estimating | 0 | 4.19 | 0 | 4.19 | 0 | 0 | 0 | 4.19 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4159 | -121.9706 | VACA DIXON 110540092 | VACA DIXON 110540092 | 493 | 37 | Top 250 Miles | Tier 2
35237369 | CWSP - VACA DIXON 110540092 PH 1.10 | Base SH | 08W | ESTS | Estimating | 0 | 3.14 | 0 | 3.14 | 0 | 0 | 0 | 3.14 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4159 | -121.9706 | VACA DIXON 110540092 | VACA DIXON 110540092 | 493 | 37 | Top 250 Miles | Tier 2
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 | Base SH | 08W | ESTS | Estimating | 0 | 3.7799 | 0 | 3.7799 | 0 | 0 | 0 | 3.7799 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4159 | -121.9706 | VACA DIXON 110540092 | VACA DIXON 110540092 | 493 | 37 | Top 250 Miles | Tier 2
35237371 | CWSP - VACA DIXON 110540092 PH 1.12 | Base SH | 08W | ESTS | Estimating | 0 | 0.33996 | 0 | 0.33996 | 0 | 0 | 0 | 0.33996 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.4159 | -121.9706 | VACA DIXON 110540092 | VACA DIXON 110540092 | 493 | 37 | Top 250 Miles | Tier 2
35238088 | REMG 531 - MARIPOSA 2101,SLAUGHTER HOUSE | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4927 | -119.9656 | MARIPOSA 210135244 | MARIPOSA 210135244 | 1464 | 428 | Remote Grid Pilot | Tier 3
35238098 | ECOP - SILVERADO 2104 - H05 - LR726 PH 6 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.47936 | 0 | 0.47936 | 0 | 0 | 0 | 0.47936 | 0 | NB | Region 1 - North Coast | Pope Valley | Napa | 38.6152 | -122.4293 | SILVERADO 2104726 | SILVERADO 2104726 | 495 | 279 | ECOP - Top 20% | Tier 3
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.10436 | 0 | 0.10436 | 0 | 0 | 0.10436 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5065 | -120.0082 | MARIPOSA 210197142 | MARIPOSA 210197142 | 1966 | 36 | Top 250 Miles | Tier 2
35240160 | CWSP - COARSEGOLD 21045310 PH 1.1 | Base SH | 08W | ESTS | Estimating | 0 | 4.3841 | 0 | 4.3841 | 0 | 0 | 0 | 4.3841 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2286 | -119.7102 | COARSEGOLD 21045310 | COARSEGOLD 21045310 | 312 | 61 | CWSP 2022-2023 | Tier 2
35240162 | CWSP - COARSEGOLD 21045310 PH 2.1 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.1252 | 0 | 2.1252 | 0 | 0 | 0 | 2.1252 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2286 | -119.7102 | COARSEGOLD 21045310 | COARSEGOLD 21045310 | 312 | 61 | CWSP 2022-2023 | Tier 2
35240163 | CWSP - COARSEGOLD 21045310 PH 3.1 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.2153 | 0 | 2.2153 | 0 | 0 | 0 | 2.2153 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2286 | -119.7102 | COARSEGOLD 21045310 | COARSEGOLD 21045310 | 312 | 61 | CWSP 2022-2023 | Tier 2
35240164 | CWSP - COARSEGOLD 2104570682 PH 1 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.0979 | 0 | 2.0979 | 0 | 0 | 0 | 0 | 2.0979 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.264 | -119.7128 | COARSEGOLD 2104570682 | COARSEGOLD 2104570682 | 481 | 78 | CWSP 2022-2023 | Tier 2
35240165 | CWSP - COARSEGOLD 21046210 PH 1.1 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.8498 | 0 | 3.8498 | 0 | 0 | 0 | 0 | 3.8498 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.269 | -119.7126 | COARSEGOLD 21046210 | COARSEGOLD 21046210 | 1874 | 132 | CWSP 2022-2023 | Tier 2
35240166 | CWSP - VOLTA 1101CB PH 1.1 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.4201 | 0 | 1.4201 | 0 | 0 | 0 | 1.4201 | 0 | NV | Region 2 - North East | Manton | Tehama | 40.4595 | -121.8662 | VOLTA 1101CB | VOLTA 1101CB | 1694 | 76 | CWSP 2022-2023 | Tier 2 & 3
35240167 | CWSP - VOLTA 1101CB PH 2.1 | Base SH | 08W | UNSE | Scoping/Scoped | 0.41288 | 0.037879 | 0 | 0.45076 | 0 | 0 | 0 | 0.45076 | 0 | NV | Region 2 - North East | Manton | Tehama | 40.4595 | -121.8662 | VOLTA 1101CB | VOLTA 1101CB | 1694 | 76 | CWSP 2022-2023 | Tier 2
35240168 | CWSP - VOLTA 110153118 PH 1.1 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.5 | 0 | 1.5 | 0 | 0 | 0 | 1.5 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.4013 | -121.8752 | VOLTA 110153118 | VOLTA 110153118 | 1618 | 157 | CWSP 2022-2023 | Tier 2
35240169 | CWSP - VOLTA 11011568 PH 1.1 | Base SH | 08W | ESTS | Estimating | 0 | 1.8951 | 0 | 1.8951 | 0 | 0 | 0 | 0 | 1.8951 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.4587 | -121.867 | VOLTA 11011568 | VOLTA 11011568 | 1479 | 85 | CWSP 2022-2023 | Tier 2 & 3
35240170 | CWSP - VOLTA 11011568 PH 2.1 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.88996 | 0 | 0.88996 | 0 | 0 | 0 | 0 | 0.88996 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.4587 | -121.867 | VOLTA 11011568 | VOLTA 11011568 | 1479 | 85 | CWSP 2022-2023 | Tier 2
35240171 | CWSP - VOLTA 11011568 PH 3.1 | Base SH | 08W | ESTS | Estimating | 0 | 1.341 | 0 | 1.341 | 0 | 0 | 0 | 0 | 1.3409 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.4587 | -121.867 | VOLTA 11011568 | VOLTA 11011568 | 1479 | 85 | CWSP 2022-2023 | Tier 2
35240173 | CWSP - PUTAH CREEK 11028352 PH 1.1 | Base SH | 08W | ESTS | Estimating | 0 | 1.22 | 0 | 1.22 | 0 | 0 | 0 | 1.2201 | 0 | SA | Region 2 - North East | Winters | Yolo-Solano | 38.5035 | -122.002 | PUTAH CREEK 11028352 | PUTAH CREEK 11028352 | 2110 | 171 | CWSP 2022-2023 | Tier 2
35240174 | CWSP - PUTAH CREEK 11028352 PH 2.1 | Base SH | 08W | ADER | Estimating | 0 | 1.07 | 0 | 1.07 | 0 | 0 | 0 | 1.07 | 0 | SA | Region 2 - North East | Winters | Yolo-Solano | 38.5035 | -122.002 | PUTAH CREEK 11028352 | PUTAH CREEK 11028352 | 2110 | 171 | CWSP 2022-2023 | Tier 2
35240175 | CWSP - PUTAH CREEK 110267858 PH 1 | Base SH | 08W | ESTS | Estimating | 0 | 3.446 | 0 | 3.446 | 0 | 0 | 0 | 3.446 | 0 | SA | Region 2 - North East | Winters | Yolo-Solano | 38.481 | -122.0272 | PUTAH CREEK 110267858 | PUTAH CREEK 110267858 | 581 | 92 | CWSP 2022-2023 | Tier 2
35240176 | CWSP - PUTAH CREEK 110264044 PH 1.1 | Base SH | 08W | ESTS | Estimating | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 2.4 | 0 | SA | Region 2 - North East | Winters | Yolo-Solano | 38.4946 | -122.034 | PUTAH CREEK 110264044 | PUTAH CREEK 110264044 | 747 | 529 | CWSP 2022-2023 | Tier 2
35240177 | CWSP - PUTAH CREEK 110264044 PH 2 | Base SH | 08W | ESTS | Estimating | 0 | 3.3 | 0 | 3.3 | 0 | 0 | 0 | 3.3 | 0 | SA | Region 2 - North East | Winters | Yolo-Solano | 38.4946 | -122.034 | PUTAH CREEK 110264044 | PUTAH CREEK 110264044 | 747 | 529 | CWSP 2022-2023 | Tier 2
35240178 | CWSP - PUTAH CREEK 1102710384 PH 1.1 | Base SH | 08W | ESTS | Estimating | 0 | 3.423 | 0 | 3.423 | 0 | 0 | 0 | 3.4229 | 0 | SA | Region 2 - North East | Winters | Yolo-Solano | 38.5142 | -122.0002 | PUTAH CREEK 1102710384 | PUTAH CREEK 1102710384 | 2697 | 418 | CWSP 2022-2023 | Tier 2
35240179 | CWSP - SANTA YNEZ 1104CB | Base SH | 08W | ADER | Estimating | 0 | 0.25 | 0 | 0.25 | 0 | 0 | 0 | 0.25 | 0 | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.6254 | -120.1189 | SANTA YNEZ 1104CB | SANTA YNEZ 1104CB | 2249 | 137 | CWSP 2022-2023 | Tier 2
35240220 | CWSP - SANTA YNEZ 1104Y04 PH 1.1 | Base SH | 08W | ESTS | Estimating | 0 | 2.2701 | 0 | 2.2701 | 0 | 0 | 0 | 2.2701 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6354 | -120.0656 | SANTA YNEZ 1104Y04 | SANTA YNEZ 1104Y04 | 576 | 108 | CWSP 2022-2023 | Tier 2
35240221 | CWSP - SANTA YNEZ 1104Y04 PH 2.1 | Base SH | 08W | ESTS | Estimating | 0 | 2.93 | 0 | 2.93 | 0 | 0 | 0 | 2.93 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6354 | -120.0656 | SANTA YNEZ 1104Y04 | SANTA YNEZ 1104Y04 | 576 | 108 | CWSP 2022-2023 | Tier 2
35240222 | CWSP - SANTA YNEZ 1104Y66 PH 1.1 | Base SH | 08W | ESTS | Estimating | 0 | 2.11 | 0 | 2.11 | 0 | 0 | 0 | 0 | 2.11 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6111 | -120.0203 | SANTA YNEZ 1104Y66 | SANTA YNEZ 1104Y66 | 431 | 153 | CWSP 2022-2023 | Tier 2 & 3
35240223 | CWSP - SANTA YNEZ 1104Y66 PH 2.1 | Base SH | 08W | ESTS | Estimating | 0 | 2.61 | 0 | 2.61 | 0 | 0 | 0 | 0 | 2.61 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6111 | -120.0203 | SANTA YNEZ 1104Y66 | SANTA YNEZ 1104Y66 | 431 | 153 | CWSP 2022-2023 | Tier 2 & 3
35240224 | CWSP - SANTA YNEZ 110477098 PH 1.1 | Base SH | 08W | ESTS | Estimating | 0 | 1.87 | 0 | 1.87 | 0 | 0 | 0 | 1.8701 | 0 | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.6323 | -120.1186 | SANTA YNEZ 110477098 | SANTA YNEZ 110477098 | 589 | 308 | CWSP 2022-2023 | Tier 2
35241060 | REMG 581 - OAKHURST 1101, MIAMI MOUNTAIN | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 1.5 | 0 | YO | Region 2 - North East | Palo Cedro | Shasta | 37.364 | -119.7252 | OAKHURST 110110090 | OAKHURST 110110090 | 1021 | 421 | Remote Grid Pilot | Tier 3
35241071 | CWSP - DESCHUTES 11041582 | Base SH | 08W | ESTS | Estimating | 0 | 2.06 | 0.325 | 2.385 | 0 | 0 | 0 | 2.385 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.5725 | -122.2381 | DESCHUTES 11041582 | DESCHUTES 11041582 | 1927 | 301 | CWSP 2022-2023 | Tier 2
35241072 | CWSP - DESCHUTES 11041370 PH1.1 | Base SH | 08W | ESTS | Estimating | 0 | 3.6 | 0.21 | 3.81 | 0 | 0 | 0 | 3.81 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.573 | -122.2386 | DESCHUTES 11041370 | DESCHUTES 11041370 | 1954 | 100 | CWSP 2022-2023 | Tier 2
35241073 | CWSP - DESCHUTES 110449024 PH1.1 | Base SH | 08W | ESTS | Estimating | 0 | 3.87 | 0 | 3.87 | 0 | 0 | 0 | 3.8701 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.5929 | -122.2397 | DESCHUTES 110449024 | DESCHUTES 110449024 | 415 | 99 | CWSP 2022-2023 | Tier 2
35243440 | PSPS-OREGON TRAIL 1103 CB & 35002-PH7 | Base SH | 08W | UNSE | Scoping/Scoped | 0.42992 | 0 | 0 | 0.42992 | 0 | 0 | 0 | 0.42992 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | OREGON TRAIL 1103CB | OREGON TRAIL 1103CB | 1689 | 290 | PSPS | Tier 2
35243441 | REMG 17 - CHALLENGE 1102, PONDEROSA WAY | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 2.3233 | 2.3233 | 0 | 0 | 0 | 2.3233 | 0 | NV | Region 2 - North East | Brownsville | Yuba | 39.483 | -121.2466 | CHALLENGE 11025462 | CHALLENGE 11025462 | 199 | 1428 | REMG 2022-2023 | Tier 2 & 3
35243442 | REMG 130 - PIKE CITY 1102, TAHOE NF | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 2.319 | 2.319 | 0 | 0 | 0 | 0 | 2.319 | SI | Region 2 - North East | North San Juan | Nevada | 39.4385 | -120.9959 | PIKE CITY 1102CB | PIKE CITY 1102CB | 349 | 1308 | REMG 2022-2023 | Tier 3
35243443 | REMG 188 - TIVY VALLEY 1107 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 11.215 | 11.215 | 0 | 0 | 0 | 11.215 | 0 | FR | Region 5 - Central Valley | Sanger | Fresno | 36.8168 | -119.3407 | TIVY VALLEY 1107869946 | TIVY VALLEY 1107869946 | 507 | 491 | REMG 2022-2023 | Tier 2
35243444 | CWSP - VOLTA 11011568 PH2.3 | Base SH | 08W | ESTS | Estimating | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | NV | Region 2 - North East | Manton | Tehama | 40.4587 | -121.867 | VOLTA 11011568 | VOLTA 11011568 | 1479 | 85 | CWSP 2022-2023 | Tier 2
35243445 | REMG 49 - OLEMA 1101, HOME RANCH PRNS | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 1.92 | 1.92 | 0 | 0 | 0 | 1.92 | 0 | NB | Region 1 - North Coast | Inverness | Marin | 38.1094 | -122.8698 | OLEMA 1101602 | OLEMA 1101602 | 1633 | 2360 | REMG 2022-2023 | Tier 2
35243446 | REMG 665 - OLEMA 1101, MT VISIONS PRNS | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0.37 | 0.37 | 0 | 0 | 0 | 0.37 | 0 | NB | Region 1 - North Coast | Inverness | Marin | 38.1094 | -122.8698 | OLEMA 110150396 | OLEMA 110150396 | 306 | 2644 | REMG 2022-2023 | Tier 2
35243447 | CWSP - DESCHUTES 11041370 PH 2.1 | Base SH | 08W | ESTS | Estimating | 0 | 2.64 | 0.033 | 2.673 | 0 | 0 | 0 | 2.673 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.573 | -122.2386 | DESCHUTES 11041370 | DESCHUTES 11041370 | 1954 | 100 | CWSP 2022-2023 | Tier 2
35243448 | CWSP - DESCHUTES 110449024 PH 2.1 | Base SH | 08W | ESTS | Estimating | 0 | 3.69 | 0 | 3.69 | 0 | 0 | 0 | 3.69 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.5929 | -122.2396 | DESCHUTES 110449024 | DESCHUTES 110449024 | 415 | 99 | CWSP 2022-2023 | Tier 2
35243452 | CWSP - COARSEGOLD 210410030 - PH1.1 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 3.3625 | 0 | 3.3625 | 0 | 0 | 0 | 3.3625 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2234 | -119.7689 | COARSEGOLD 210410030 | COARSEGOLD 210410030 | 2223 | 144 | CWSP 2022-2023 | Tier 2
35243453 | CWSP - VOLTA 11011596 - PH1.1 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 1.49 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.351 | -121.7811 | VOLTA 11011596 | VOLTA 11011596 | 2583 | 966 | CWSP 2022-2023 | Tier 2
35246501 | REMG 44- FULTON 1107,PEPPERWOOD PRESERVE | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0.70985 | 0.70985 | 0 | 0 | 0 | 0.71004 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.5702 | -122.6772 | FULTON 1107604 | FULTON 1107604 | 196 | 637 | REMG 2022-2023 | Tier 3
35249871 | CWSP - COARSEGOLD 21045310 PH 1.2 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.0186 | 0 | 2.0186 | 0 | 0 | 0 | 2.0186 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2286 | -119.7102 | COARSEGOLD 21045310 | COARSEGOLD 21045310 | 312 | 61 | CWSP 2022-2023 | Tier 2
35249872 | CWSP - COARSEGOLD 21045310 PH 1.3 | Base SH | 08W | ESTS | Estimating | 0 | 2.725 | 0 | 2.725 | 0 | 0 | 0 | 2.725 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2286 | -119.7102 | COARSEGOLD 21045310 | COARSEGOLD 21045310 | 312 | 61 | CWSP 2022-2023 | Tier 2
35249873 | CWSP - COARSEGOLD 21045310 PH 3.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.8913 | 0 | 3.8913 | 0 | 0 | 0 | 3.8913 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2286 | -119.7102 | COARSEGOLD 21045310 | COARSEGOLD 21045310 | 312 | 61 | CWSP 2022-2023 | Tier 2
35249874 | CWSP - COARSEGOLD 21045310 PH 3.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.7922 | 0 | 3.7922 | 0 | 0 | 0 | 3.7922 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2286 | -119.7102 | COARSEGOLD 21045310 | COARSEGOLD 21045310 | 312 | 61 | CWSP 2022-2023 | Tier 2
35249875 | CWSP - COARSEGOLD 21046210 PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.6394 | 0 | 2.6394 | 0 | 0 | 0 | 0 | 2.6394 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.269 | -119.7126 | COARSEGOLD 21046210 | COARSEGOLD 21046210 | 1874 | 132 | CWSP 2022-2023 | Tier 2
35249876 | CWSP - COARSEGOLD 21046210 PH 1.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.6483 | 0 | 3.6483 | 0 | 0 | 0 | 0 | 3.6483 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.269 | -119.7126 | COARSEGOLD 21046210 | COARSEGOLD 21046210 | 1874 | 132 | CWSP 2022-2023 | Tier 2
35249877 | CWSP - COARSEGOLD 21046210 PH 1.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 1.0299 | 1.0299 | 0 | 0 | 0 | 1.0299 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.269 | -119.7126 | COARSEGOLD 21046210 | COARSEGOLD 21046210 | 1874 | 132 | CWSP 2022-2023 | Tier 2
35249996 | CWSP - COARSEGOLD 210410030 PH 1.2 | Base SH | 08W | ESTS | Estimating | 0 | 1.9536 | 0 | 1.9536 | 0 | 0 | 0 | 1.9536 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2234 | -119.7689 | COARSEGOLD 210410030 | COARSEGOLD 210410030 | 2223 | 144 | CWSP 2022-2023 | Tier 2
35249997 | CWSP - COARSEGOLD 210410030 PH 1.3 | Base SH | 08W | ESTS | Estimating | 0 | 2.115 | 0 | 2.115 | 0 | 0 | 0 | 2.115 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2234 | -119.7689 | COARSEGOLD 210410030 | COARSEGOLD 210410030 | 2223 | 144 | CWSP 2022-2023 | Tier 2
35249998 | CWSP - COARSEGOLD 210410030 PH 1.4 | Base SH | 08W | ESTS | Estimating | 0 | 3.6773 | 0 | 3.6773 | 0 | 0 | 0 | 3.6773 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2234 | -119.7689 | COARSEGOLD 210410030 | COARSEGOLD 210410030 | 2223 | 144 | CWSP 2022-2023 | Tier 2
35249999 | CWSP - COARSEGOLD 210410030 PH 1.5 | Base SH | 08W | ESTS | Estimating | 0 | 2.0688 | 0 | 2.0688 | 0 | 0 | 0 | 2.0688 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2234 | -119.7689 | COARSEGOLD 210410030 | COARSEGOLD 210410030 | 2223 | 144 | CWSP 2022-2023 | Tier 2
35250570 | CWSP - MARIPOSA 2101 LR 35244 PH1 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.401 | 0 | 2.401 | 0 | 0 | 0 | 0 | 2.401 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4927 | -119.9656 |  | MARIPOSA 210135244 | 1464 | 428 | CWSP 2022-2023 | Tier 2 & 3
35250571 | CWSP - MARIPOSA 2101 LR 35244 PH2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 4.595 | 0 | 4.595 | 0 | 0 | 0 | 0 | 4.595 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4927 | -119.9656 |  | MARIPOSA 210135244 | 1464 | 428 | CWSP 2022-2023 | Tier 2
35250572 | CWSP - MARIPOSA 2101 LR 309438 PH1.1 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.953 | 0 | 1.953 | 0 | 0 | 0 | 0 | 1.953 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5026 | -119.9886 |  | MARIPOSA 2101309438 | 3000 | 605 | CWSP 2022-2023 | Tier 2
35250573 | CWSP - MARIPOSA 2101 CB | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.759 | 0 | 1.759 | 0 | 0 | 0 | 0 | 1.759 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5046 | -120.0081 |  | MARIPOSA 2101CB | 2081 | 57 | CWSP 2022-2023 | Tier 2
35250574 | CWSP - HARTLEY 1101 LR 336932 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 8.0701 | 0 | 8.0701 | 0 | 0 | 0 | 0 | 8.0701 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0512 | -122.9384 |  | HARTLEY 11011306 | 1743 | 593 | CWSP 2022-2023 | Tier 2
35250575 | CWSP - HARTLEY 1101 LR 789752 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.2299 | 0 | 3.2299 | 0 | 0 | 0 | 0 | 3.2299 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0724 | -122.9571 |  | HARTLEY 1101658 | 882 | 439 | CWSP 2022-2023 | Tier 2
35250576 | CWSP - HARTLEY 1101 LR 698 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.22992 | 0 | 0.22992 | 0 | 0 | 0 | 0 | 0.22992 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0803 | -122.9513 |  | HARTLEY 1101698 | 1832 | 58 | CWSP 2022-2023 | Tier 2
35250577 | CWSP - STANISLAUS 1702 CB | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.3513 | 0 | 3.3513 | 0 | 0 | 0 | 0 | 3.3513 | YO | Region 5 - Central Valley | Mi Wuk Village | Tuolumne | 38.1377 | -120.3701 |  | STANISLAUS 1702CB | 1360 | 235 | CWSP 2022-2023 | Tier 2 & 3
35250578 | CWSP - STANISLAUS 1701 CB | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.4174 | 0 | 2.4174 | 0 | 0 | 0 | 0 | 2.4174 | YO | Region 5 - Central Valley | Mi Wuk Village | Tuolumne | 38.1376 | -120.3702 |  | STANISLAUS 1701CB | 1422 | 56 | CWSP 2022-2023 | Tier 2 & 3
35250579 | CWSP - POTTER VALLEY PH 1104 LR 95878 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 6.14 | 0 | 6.14 | 0 | 0 | 0 | 0 | 6.14 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3618 | -123.1272 |  | POTTER VALLEY P H 110495878 | 2524 | 60 | CWSP 2022-2023 | Tier 2 & 3
35250737 | CWSP - COARSEGOLD 21045310 PH 2.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.8564 | 0 | 2.8564 | 0 | 0 | 0 | 2.8564 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2286 | -119.7102 | COARSEGOLD 21045310 | COARSEGOLD 21045310 | 312 | 61 | CWSP 2022-2023 | Tier 2
35250738 | CWSP - COARSEGOLD 21045310 PH 2.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.4856 | 0 | 3.4856 | 0 | 0 | 0 | 3.4856 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.2286 | -119.7102 | COARSEGOLD 21045310 | COARSEGOLD 21045310 | 312 | 61 | CWSP 2022-2023 | Tier 2
35254067 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.0424 | 0 | 1.0424 | 0 | 0 | 0 | 0 | 1.0424 | SI | Region 2 - North East | Cool | El Dorado | 38.9139 | -121.0189 |  | MOUNTAIN QUARRIES 2101CB | 412 | 68 | CWSP 2022-2023 | Tier 2
35254068 | CWSP - MOUNTAIN QUARRIES 2101 CB PH2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.39 | 0 | 1.39 | 0 | 0 | 0 | 0 | 1.39 | SI | Region 2 - North East | Cool | El Dorado | 38.9139 | -121.0189 |  | MOUNTAIN QUARRIES 2101CB | 412 | 68 | CWSP 2022-2023 | Tier 2
35254069 | CWSP - MOUNTAIN QUARRIES 2101 CB PH3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 8.34 | 0 | 8.34 | 0 | 0 | 0 | 0 | 8.34 | SI | Region 2 - North East | Cool | El Dorado | 38.9139 | -121.0189 |  | MOUNTAIN QUARRIES 2101CB | 412 | 68 | CWSP 2022-2023 | Tier 2
35254070 | CWSP-MOUNTAIN QUARRIES 2101 LR 1350 PH1 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 10.8799 | 0 | 10.8799 | 0 | 0 | 0 | 0 | 10.8799 | SI | Region 2 - North East | Cool | El Dorado | 38.8931 | -120.9966 |  | MOUNTAIN QUARRIES 21011350 | 1328 | 169 | CWSP 2022-2023 | Tier 2
35254071 | CWSP-MOUNTAIN QUARRIES 2101 LR 1350 PH2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.2087 | 0 | 1.2087 | 0 | 0 | 0 | 0 | 1.2087 | SI | Region 2 - North East | Cool | El Dorado | 38.8931 | -120.9966 |  | MOUNTAIN QUARRIES 21011350 | 1328 | 169 | CWSP 2022-2023 | Tier 2
35254072 | CWSP - HIGHLANDS 1102 LR 623120 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 6.19 | 0 | 6.19 | 0 | 0 | 0 | 0 | 6.19 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9544 | -122.6079 |  | HIGHLANDS 1102623120 | 2966 | 74 | CWSP 2022-2023 | Tier 2
35254073 | CWSP - POTTER VALLEY PH 1105 LR 1904 PH1 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 9.9299 | 0 | 9.9299 | 0 | 0 | 0 | 0 | 9.9299 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3218 | -123.0951 |  | POTTER VALLEY P H 11051904 | 1439 | 75 | CWSP 2022-2023 | Tier 2 & 3
35254074 | CWSP - POTTER VALLEY PH 1105 LR 1904 PH2 | Base SH | 08W | UNSE | Scoping/Scoped | 0.24508 | 8.7591 | 0 | 9.0042 | 0 | 0 | 0 | 0 | 9.0042 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3218 | -123.0951 |  | POTTER VALLEY P H 11051904 | 1439 | 75 | CWSP 2022-2023 | Tier 2
35254075 | CWSP - POTTER VALLEY PH 1105 LR 1904 PH3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 9.9299 | 0 | 9.9299 | 0 | 0 | 0 | 0 | 9.9299 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3218 | -123.0951 |  | POTTER VALLEY P H 11051904 | 1439 | 75 | CWSP 2022-2023 | Tier 2
35254076 | CWSP - POTTER VALLEY PH 1105 LR 1904 PH4 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.05 | 0 | 2.05 | 0 | 0 | 0 | 0 | 2.05 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3218 | -123.0951 |  | POTTER VALLEY P H 11051904 | 1439 | 75 | CWSP 2022-2023 | Tier 2
35254077 | CWSP - POTTER VALLEY PH 1105 LR 37476 | Base SH | 08W | UNSE | Scoping/Scoped | 0.82803 | 2.0184 | 0 | 2.8464 | 0 | 0 | 0 | 0 | 2.8464 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3171 | -123.1131 |  | POTTER VALLEY P H 110537476 | 2366 | 396 | CWSP 2022-2023 | Tier 2
35254078 | CWSP - AUBERRY 1101 CB PH1 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.6199 | 0 | 2.6199 | 0 | 0 | 0 | 2.6199 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0679 | -119.4966 |  | AUBERRY 1101CB | 1431 | 63 | CWSP 2022-2023 | Tier 2
35254079 | CWSP - AUBERRY 1101 CB PH2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.4011 | 0 | 2.4011 | 0 | 0 | 0 | 2.4011 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0679 | -119.4966 |  | AUBERRY 1101CB | 1431 | 63 | CWSP 2022-2023 | Tier 2
35254177 | CWSP - PUTAH CREEK 110264044 PH 2.2 | Base SH | 08W | ESTS | Estimating | 0 | 0.31 | 0 | 0.31 | 0 | 0 | 0 | 0.31 | 0 | SA | Region 2 - North East | Winters | Yolo-Solano | 38.4946 | -122.034 | PUTAH CREEK 110264044 | PUTAH CREEK 110264044 | 747 | 529 | CWSP 2022-2023 | Tier 2
35254178 | CWSP - PUTAH CREEK 110267858 PH 1.3 | Base SH | 08W | ESTS | Estimating | 0 | 1.253 | 0 | 1.253 | 0 | 0 | 0 | 1.253 | 0 | SA | Region 2 - North East | Winters | Yolo-Solano | 38.481 | -122.0272 | PUTAH CREEK 110267858 | PUTAH CREEK 110267858 | 581 | 92 | CWSP 2022-2023 | Tier 2
35254240 | CWSP - AUBERRY 1101 LR R2839 PH1 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.1252 | 0 | 2.1252 | 0 | 0 | 0 | 0 | 2.1252 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0362 | -119.452 |  | AUBERRY 1101R2839 | 1746 | 274 | CWSP 2022-2023 | Tier 2
35254241 | CWSP - AUBERRY 1101 LR R2839 PH2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.8248 | 0 | 2.8248 | 0 | 0 | 0 | 0 | 2.8248 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0362 | -119.452 |  | AUBERRY 1101R2839 | 1746 | 274 | CWSP 2022-2023 | Tier 2
35254242 | CWSP - AUBERRY 1101 LR 49122 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.9436 | 0 | 1.9436 | 0 | 0 | 0 | 0 | 1.9436 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0812 | -119.4864 |  | AUBERRY 110149122 | 682 | 330 | CWSP 2022-2023 | Tier 2
35254243 | CWSP - AUBERRY 1101 LR R2578 PH1 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.91 | 0 | 2.91 | 0 | 0 | 0 | 0 | 2.91 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0173 | -119.427 |  | AUBERRY 1101R2578 | 1377 | 163 | CWSP 2022-2023 | Tier 2
35254244 | CWSP - AUBERRY 1101 LR R2578 PH2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.66 | 0 | 2.66 | 0 | 0 | 0 | 2.66 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0173 | -119.427 |  | AUBERRY 1101R2578 | 1377 | 163 | CWSP 2022-2023 | Tier 2
35254245 | CWSP - AUBERRY 1101 LR R2578 PH3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.958 | 0 | 2.958 | 0 | 0 | 0 | 0 | 2.958 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0173 | -119.427 |  | AUBERRY 1101R2578 | 1377 | 163 | CWSP 2022-2023 | Tier 2
35254246 | CWSP - AUBERRY 1101 LR R2578 PH4 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.62 | 0 | 2.62 | 0 | 0 | 0 | 0 | 2.62 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0173 | -119.427 |  | AUBERRY 1101R2578 | 1377 | 163 | CWSP 2022-2023 | Tier 2
35254247 | CWSP - AUBERRY 1101 LR R2578 PH5 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.95 | 0 | 1.95 | 0 | 0 | 0 | 1.95 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0173 | -119.427 |  | AUBERRY 1101R2578 | 1377 | 163 | CWSP 2022-2023 | Tier 2
35254248 | CWSP - PASO ROBLES 1103 LR N58 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.43 | 0 | 1.43 | 0 | 0 | 0 | 1.43 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6286 | -120.6955 |  | PASO ROBLES 1103N58 | 676 | 257 | CWSP 2022-2023 | Tier 2
35254249 | CWSP - PASO ROBLES 1103 LR N54 PH1 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.7 | 0 | 2.7 | 0 | 0 | 0 | 2.7 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6543 | -120.7258 |  | PASO ROBLES 1103N54 | 564 | 69 | CWSP 2022-2023 | Tier 2
35254250 | CWSP - PASO ROBLES 1103 LR N54 PH2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.11 | 0 | 1.11 | 0 | 0 | 0 | 1.11 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6543 | -120.7258 |  | PASO ROBLES 1103N54 | 564 | 69 | CWSP 2022-2023 | Tier 2
35254251 | CWSP - PASO ROBLES 1103 LR 59763 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.13 | 0 | 1.13 | 0 | 0 | 0 | 1.13 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6415 | -120.7259 |  | PASO ROBLES 110359763 | 616 | 615 | CWSP 2022-2023 | Tier 2
35254252 | CWSP - PASO ROBLES 1103 LR N52 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.49 | 0.065 | 2.555 | 0 | 0 | 0 | 0 | 2.555 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6886 | -120.7649 |  | PASO ROBLES 1103N52 | 1851 | 291 | CWSP 2022-2023 | Tier 2
35254253 | CWSP - PASO ROBLES 1103 LR N50 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0.75 | 0.75 | 0 | 0 | 0 | 0 | 0.75 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.714 | -120.8385 |  | PASO ROBLES 1103N50 | 465 | 138 | CWSP 2022-2023 | Tier 2
35254254 | CWSP - PASO ROBLES 1103 LR 2731 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.46 | 0 | 1.46 | 0 | 0 | 0 | 0 | 1.46 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6844 | -120.7299 |  | PASO ROBLES 11032731 | 1088 | 260 | CWSP 2022-2023 | Tier 2
35254258 | CWSP - VOLTA 1101CB PH 1.2 | Base SH | 08W | UNSC | Ready for Construction | 0 | 1.45 | 0 | 1.45 | 0 | 0 | 0 | 1.45 | 0 | NV | Region 2 - North East | Manton | Tehama | 40.4594 | -121.8663 | VOLTA 1101CB | VOLTA 1101CB | 1694 | 76 | CWSP 2022-2023 | Tier 2 & 3
35254259 | CWSP - VOLTA 1101CB PH 1.3 | Base SH | 08W | ESTS | Estimating | 0.85 | 0 | 0 | 0.85 | 0 | 0 | 0 | 0.85 | 0 | NV | Region 2 - North East | Manton | Tehama | 40.4594 | -121.8663 | VOLTA 1101CB | VOLTA 1101CB | 1694 | 76 | CWSP 2022-2023 | Tier 2 & 3
35254260 | CWSP - PUTAH CREEK 110267858 PH 1.6 | Base SH | 08W | ESTS | Estimating | 0.4 | 0 | 0 | 0.4 | 0 | 0 | 0 | 0.4 | 0 | SA | Region 2 - North East | Winters | Yolo-Solano | 38.481 | -122.0272 | PUTAH CREEK 110267858 | PUTAH CREEK 110267858 | 581 | 92 | CWSP 2022-2023 | Tier 2
35254261 | CWSP - PUTAH CREEK 110267858 PH 1.5 | Base SH | 08W | ESTS | Estimating | 0 | 2.802 | 0 | 2.802 | 0 | 0 | 0 | 2.802 | 0 | SA | Region 2 - North East | Winters | Yolo-Solano | 38.481 | -122.0272 | PUTAH CREEK 110267858 | PUTAH CREEK 110267858 | 581 | 92 | CWSP 2022-2023 | Tier 2
35254262 | CWSP - PUTAH CREEK 110267858 PH 1.4 | Base SH | 08W | ESTS | Estimating | 0 | 2.104 | 0 | 2.104 | 0 | 0 | 0 | 2.104 | 0 | SA | Region 2 - North East | Winters | Yolo-Solano | 38.481 | -122.0272 | PUTAH CREEK 110267858 | PUTAH CREEK 110267858 | 581 | 92 | CWSP 2022-2023 | Tier 2
35254263 | CWSP - PUTAH CREEK 1102710384 PH 1.2 | Base SH | 08W | ESTS | Estimating | 0 | 1.225 | 0 | 1.225 | 0 | 0 | 0 | 1.225 | 0 | SA | Region 2 - North East | Winters | Yolo-Solano | 38.5142 | -122.0002 | PUTAH CREEK 1102710384 | PUTAH CREEK 1102710384 | 2697 | 418 | CWSP 2022-2023 | Tier 2
35254264 | CWSP - PUTAH CREEK 11028352 PH 1.2 | Base SH | 08W | ADER | Estimating | 0 | 1.33 | 0 | 1.33 | 0 | 0 | 0 | 1.33 | 0 | SA | Region 2 - North East | Winters | Yolo-Solano | 38.5035 | -122.002 | PUTAH CREEK 11028352 | PUTAH CREEK 11028352 | 2110 | 171 | CWSP 2022-2023 | Tier 2
35254265 | CWSP - PUTAH CREEK 11028352 PH 2.2 | Base SH | 08W | ESTS | Estimating | 0 | 2.76 | 0 | 2.76 | 0 | 0 | 0 | 2.76 | 0 | SA | Region 2 - North East | Winters | Yolo-Solano | 38.5035 | -122.002 | PUTAH CREEK 11028352 | PUTAH CREEK 11028352 | 2110 | 171 | CWSP 2022-2023 | Tier 2
35254266 | CWSP - PUTAH CREEK 11028352 PH 2.3 | Base SH | 08W | ESTS | Estimating | 0 | 0.13 | 0 | 0.13 | 0 | 0 | 0 | 0.13 | 0 | SA | Region 2 - North East | Winters | Yolo-Solano | 38.5035 | -122.002 | PUTAH CREEK 11028352 | PUTAH CREEK 11028352 | 2110 | 171 | CWSP 2022-2023 | Tier 2
35254560 | CWSP - PUTAH CREEK 110267858 PH 1.2 | Base SH | 08W | ESTS | Estimating | 0 | 1.211 | 0 | 1.211 | 0 | 0 | 0 | 1.211 | 0 | SA | Region 2 - North East | Winters | Yolo-Solano | 38.481 | -122.0272 | PUTAH CREEK 110267858 | PUTAH CREEK 110267858 | 581 | 92 | CWSP 2022-2023 | Tier 2
35254640 | CWSP - VOLTA 1101CB PH 1.4 | Base SH | 08W | ESTS | Estimating | 0 | 1.45 | 0 | 1.45 | 0 | 0 | 0 | 1.45 | 0 | NV | Region 2 - North East | Manton | Tehama | 40.4594 | -121.8663 | VOLTA 1101CB | VOLTA 1101CB | 1694 | 76 | CWSP 2022-2023 | Tier 2 & 3
35254641 | CWSP - VOLTA 1101CB PH 1.5 | Base SH | 08W | UNSE | Scoping/Scoped | 0.35606 | 0.075947 | 0.67008 | 1.1021 | 0 | 0 | 0 | 1.1021 | 0 | NV | Region 2 - North East | Manton | Tehama | 40.4594 | -121.8663 | VOLTA 1101CB | VOLTA 1101CB | 1694 | 76 | CWSP 2022-2023 | Tier 2 & 3
35254642 | CWSP - VOLTA 1101CB PH 1.6 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.15 | 0 | 1.15 | 0 | 0 | 0 | 1.15 | 0 | NV | Region 2 - North East | Manton | Tehama | 40.4594 | -121.8663 | VOLTA 1101CB | VOLTA 1101CB | 1694 | 76 | CWSP 2022-2023 | Tier 2 & 3
35254643 | CWSP - VOLTA 1101CB PH 1.7 | Base SH | 08W | UNSE | Scoping/Scoped | 1.21 | 0 | 1.0979 | 2.308 | 0 | 0 | 0 | 2.308 | 0 | NV | Region 2 - North East | Manton | Tehama | 40.4594 | -121.8663 | VOLTA 1101CB | VOLTA 1101CB | 1694 | 76 | CWSP 2022-2023 | Tier 2 & 3
35254644 | CWSP - VOLTA 1101CB PH 1.8 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.41004 | 0 | 0.41004 | 0 | 0 | 0 | 0.41004 | 0 | NV | Region 2 - North East | Manton | Tehama | 40.4594 | -121.8663 | VOLTA 1101CB | VOLTA 1101CB | 1694 | 76 | CWSP 2022-2023 | Tier 2 & 3
35254645 | CWSP - VOLTA 1101CB PH 2.2 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.1165 | 0 | 1.1165 | 0 | 0 | 0 | 1.1165 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.4354 | -121.8725 | VOLTA 1101CB | VOLTA 1101CB | 1694 | 76 | CWSP 2022-2023 | Tier 2
35254646 | CWSP - VOLTA 1101CB PH 2.3 | Base SH | 08W | UNSC | Ready for Construction | 0 | 0 | 0.34394 | 0.34394 | 0 | 0 | 0 | 0.34394 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.4354 | -121.8725 | VOLTA 1101CB | VOLTA 1101CB | 1694 | 76 | CWSP 2022-2023 | Tier 2
35254647 | CWSP - VOLTA 1101CB PH 2.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0.50606 | 0 | 0 | 0.50606 | 0 | 0 | 0 | 0.50606 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.4354 | -121.8725 | VOLTA 1101CB | VOLTA 1101CB | 1694 | 76 | CWSP 2022-2023 | Tier 2
35254648 | CWSP - VOLTA 1101CB PH 2.5 | Base SH | 08W | UNSC | Ready for Construction | 0 | 0.48485 | 0 | 0.48485 | 0 | 0 | 0 | 0.48485 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.4354 | -121.8725 | VOLTA 1101CB | VOLTA 1101CB | 1694 | 76 | CWSP 2022-2023 | Tier 2
35254649 | CWSP - VOLTA 110153118 PH 1.2 | Base SH | 08W | ESTS | Estimating | 0.68996 | 0 | 0 | 0.68996 | 0 | 0 | 0 | 0.68996 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.4013 | -121.8752 | VOLTA 110153118 | VOLTA 110153118 | 1618 | 157 | CWSP 2022-2023 | Tier 2
35254650 | CWSP - VOLTA 110153118 PH 1.3 | Base SH | 08W | ESTS | Estimating | 0.36004 | 0 | 0 | 0.36004 | 0 | 0 | 0 | 0.36004 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.4013 | -121.8752 | VOLTA 110153118 | VOLTA 110153118 | 1618 | 157 | CWSP 2022-2023 | Tier 2
35254651 | CWSP - VOLTA 110153118 PH 1.4 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 2.439 | 0 | 2.439 | 0 | 0 | 0 | 2.439 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.4013 | -121.8752 | VOLTA 110153118 | VOLTA 110153118 | 1618 | 157 | CWSP 2022-2023 | Tier 2
35254652 | CWSP - VOLTA 110153118 PH 1.5 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 1.9341 | 0 | 1.9341 | 0 | 0 | 0 | 1.9341 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.4013 | -121.8752 | VOLTA 110153118 | VOLTA 110153118 | 1618 | 157 | CWSP 2022-2023 | Tier 2
35254653 | CWSP - VOLTA 110153118 PH 1.6 | Base SH | 08W | ESTS | Estimating | 0 | 2.028 | 0 | 2.028 | 0 | 0 | 0 | 2.028 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.4013 | -121.8752 | VOLTA 110153118 | VOLTA 110153118 | 1618 | 157 | CWSP 2022-2023 | Tier 2
35254654 | CWSP - VOLTA 110153118 PH 1.7 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.15095 | 0 | 0.15095 | 0 | 0 | 0 | 0 | 0.15095 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.4013 | -121.8752 | VOLTA 110153118 | VOLTA 110153118 | 1618 | 157 | CWSP 2022-2023 | Tier 2
35254655 | CWSP - VOLTA 110153118 PH 1.8 | Base SH | 08W | PEND | Permitting/Dependency | 0 | 0.57197 | 0 | 0.57197 | 0 | 0 | 0 | 0.57197 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.4013 | -121.8752 | VOLTA 110153118 | VOLTA 110153118 | 1618 | 157 | CWSP 2022-2023 | Tier 2
35254656 | CWSP - VOLTA 11011568 PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0.44205 | 0 | 0 | 0.44205 | 0 | 0 | 0 | 0 | 0.44205 | NV | Region 2 - North East | Manton | Tehama | 40.4587 | -121.867 | VOLTA 11011568 | VOLTA 11011568 | 1479 | 85 | CWSP 2022-2023 | Tier 2 & 3
35254657 | CWSP - VOLTA 11011568 PH 1.3 | Base SH | 08W | ESTS | Estimating | 0 | 0 | 0.16004 | 0.16004 | 0 | 0 | 0 | 0 | 0.16004 | NV | Region 2 - North East | Manton | Tehama | 40.4587 | -121.867 | VOLTA 11011568 | VOLTA 11011568 | 1479 | 85 | CWSP 2022-2023 | Tier 2 & 3
35254658 | CWSP - VOLTA 11011568 PH 1.4 | Base SH | 08W | ESTS | Estimating | 0 | 1.7561 | 0 | 1.7561 | 0 | 0 | 0 | 0 | 1.7561 | NV | Region 2 - North East | Manton | Tehama | 40.4587 | -121.867 | VOLTA 11011568 | VOLTA 11011568 | 1479 | 85 | CWSP 2022-2023 | Tier 2 & 3
35254659 | CWSP - VOLTA 11011568 PH 1.5 | Base SH | 08W | ESTS | Estimating | 0 | 2.6759 | 0 | 2.6759 | 0 | 0 | 0 | 0 | 2.6759 | NV | Region 2 - North East | Manton | Tehama | 40.4587 | -121.867 | VOLTA 11011568 | VOLTA 11011568 | 1479 | 85 | CWSP 2022-2023 | Tier 2 & 3
35254720 | CWSP - VOLTA 11011568 PH 1.6 | Base SH | 08W | ESTS | Estimating | 0 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0 | 0 | 1.4299 | NV | Region 2 - North East | Manton | Tehama | 40.4587 | -121.867 | VOLTA 11011568 | VOLTA 11011568 | 1479 | 85 | CWSP 2022-2023 | Tier 2 & 3
35254721 | CWSP - VOLTA 11011568 PH 1.7 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.2049 | 0 | 2.2049 | 0 | 0 | 0 | 0 | 2.2049 | NV | Region 2 - North East | Manton | Tehama | 40.4587 | -121.867 | VOLTA 11011568 | VOLTA 11011568 | 1479 | 85 | CWSP 2022-2023 | Tier 2 & 3
35254738 | CWSP - VOLTA 11011568 PH 2.2 | Base SH | 08W | ESTS | Estimating | 0 | 0 | 1.018 | 1.018 | 0 | 0 | 0 | 0 | 1.018 | NV | Region 2 - North East | Manton | Tehama | 40.4587 | -121.867 | VOLTA 11011568 | VOLTA 11011568 | 1479 | 85 | CWSP 2022-2023 | Tier 2
35254940 | CWSP - VOLTA 11011568 PH 3.2 | Base SH | 08W | ESTS | Estimating | 0 | 0 | 0.647 | 0.647 | 0 | 0 | 0 | 0 | 0.64697 | NV | Region 2 - North East | Manton | Tehama | 40.4587 | -121.867 | VOLTA 11011568 | VOLTA 11011568 | 1479 | 85 | CWSP 2022-2023 | Tier 2
35254941 | CWSP - VOLTA 11011568 PH 3.3 | Base SH | 08W | ESTS | Estimating | 0 | 2.178 | 0 | 2.178 | 0 | 0 | 0 | 0 | 2.178 | NV | Region 2 - North East | Manton | Tehama | 40.4587 | -121.867 | VOLTA 11011568 | VOLTA 11011568 | 1479 | 85 | CWSP 2022-2023 | Tier 2
35254942 | CWSP - VOLTA 11011568 PH 3.4 | Base SH | 08W | ESTS | Estimating | 0 | 1.482 | 0 | 1.482 | 0 | 0 | 0 | 0 | 1.482 | NV | Region 2 - North East | Manton | Tehama | 40.4587 | -121.867 | VOLTA 11011568 | VOLTA 11011568 | 1479 | 85 | CWSP 2022-2023 | Tier 2
35254943 | CWSP - VOLTA 11011568 PH 3.5 | Base SH | 08W | ESTS | Estimating | 0 | 0.932 | 0 | 0.932 | 0 | 0 | 0 | 0 | 0.93201 | NV | Region 2 - North East | Manton | Tehama | 40.4587 | -121.867 | VOLTA 11011568 | VOLTA 11011568 | 1479 | 85 | CWSP 2022-2023 | Tier 2
35254944 | CWSP - VOLTA 11011596 - PH1.2 | Base SH | 08W | ESTS | Estimating | 0 | 0.05 | 0.12 | 0.17 | 0 | 0 | 0 | 0.17 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.351 | -121.7811 | VOLTA 11011596 | VOLTA 11011596 | 2583 | 966 | CWSP 2022-2023 | Tier 2
35254945 | CWSP - VOLTA 11011596 - PH1.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0.51 | 0 | 0 | 0.51 | 0 | 0 | 0 | 0.51 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.351 | -121.7811 | VOLTA 11011596 | VOLTA 11011596 | 2583 | 966 | CWSP 2022-2023 | Tier 2
35254946 | CWSP - VOLTA 11011596 - PH1.4 | Base SH | 08W | ESTS | Estimating | 0 | 0.889 | 0 | 0.889 | 0 | 0 | 0 | 0.889 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.351 | -121.7811 | VOLTA 11011596 | VOLTA 11011596 | 2583 | 966 | CWSP 2022-2023 | Tier 2
35254947 | CWSP - VOLTA 11011596 - PH1.5 | Base SH | 08W | UNSE | Scoping/Scoped | 0.263 | 0 | 0 | 0.263 | 0 | 0 | 0 | 0.263 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.351 | -121.7811 | VOLTA 11011596 | VOLTA 11011596 | 2583 | 966 | CWSP 2022-2023 | Tier 2
35254948 | CWSP - VOLTA 11011596 - PH1.6 | Base SH | 08W | ESTS | Estimating | 0 | 0.979 | 0 | 0.979 | 0 | 0 | 0 | 0.979 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.351 | -121.7811 | VOLTA 11011596 | VOLTA 11011596 | 2583 | 966 | CWSP 2022-2023 | Tier 2
35256082 | CWSP - UPPER LAKE 11011276 PH 1 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.211 | 0 | 1.211 | 0 | 0 | 0 | 0 | 1.211 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1583 | -122.9898 |  | UPPER LAKE 11011276 | 1931 | 335 | CWSP 2022-2023 | Tier 2
35256083 | CWSP - UPPER LAKE 11011276 PH 2 | Base SH | 08W | UNSE | Scoping/Scoped | 5.0909 | 2.467 | 0 | 7.558 | 0 | 0 | 0 | 0 | 7.558 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1434 | -123.0023 |  | UPPER LAKE 11011276 | 1931 | 335 | CWSP 2022-2023 | Tier 2
35259511 | CWSP - DESCHUTES 11041370 PH 2.2 | Base SH | 08W | ESTS | Estimating | 0 | 2.77 | 0 | 2.77 | 0 | 0 | 0 | 2.77 | 0 | NV | Region 2 - North East | Bella Vista | Shasta | 40.6276 | -122.2347 | DESCHUTES 11041370 | DESCHUTES 11041370 | 1954 | 100 | CWSP 2022-2023 | Tier 2
35259512 | CWSP - DESCHUTES 11041370 PH 2.3 | Base SH | 08W | ESTS | Estimating | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0.15 | 0 | NV | Region 2 - North East | Bella Vista | Shasta | 40.6324 | -122.2376 | DESCHUTES 11041370 | DESCHUTES 11041370 | 1954 | 100 | CWSP 2022-2023 | Tier 2
35259513 | CWSP - DESCHUTES 1104499024 PH 2.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 4.64 | 0 | 4.64 | 0 | 0 | 0 | 4.64 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.5917 | -122.2743 | DESCHUTES 110449024 | DESCHUTES 110449024 | 415 | 99 | CWSP 2022-2023 | Tier 2
35259514 | CWSP - DESCHUTES 11041582 PH1.2 | Base SH | 08W | ESTS | Estimating | 0 | 3.61 | 0 | 3.61 | 0 | 0 | 0 | 3.61 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.5894 | -122.2244 | DESCHUTES 11041582 | DESCHUTES 11041582 | 1927 | 301 | CWSP 2022-2023 | Tier 2
35259515 | CWSP - DESCHUTES 11041370 PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.72 | 0 | 2.72 | 0 | 0 | 0 | 2.72 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.5836 | -122.2422 | DESCHUTES 11041370 | DESCHUTES 11041370 | 1954 | 100 | CWSP 2022-2023 | Tier 2
35259516 | CWSP - DESCHUTES 11041370 PH 1.3 | Base SH | 08W | ESTS | Estimating | 0.22 | 0 | 0 | 0.22 | 0 | 0 | 0 | 0.22 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.598 | -122.2382 | DESCHUTES 11041370 | DESCHUTES 11041370 | 1954 | 100 | CWSP 2022-2023 | Tier 2
35259517 | CWSP - DESCHUTES 110449024 PH1.2 | Base SH | 08W | ESTS | Estimating | 0 | 4.59 | 0 | 4.59 | 0 | 0 | 0 | 4.59 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.593 | -122.2549 | DESCHUTES 110449024 | DESCHUTES 110449024 | 415 | 99 | CWSP 2022-2023 | Tier 2
35260649 | CWSP - PASO ROBLES 1103N04 PH 1 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.62992 | 0 | 0.62992 | 0 | 0 | 0 | 0 | 0.62992 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.7334 | -120.8792 |  | PASO ROBLES 1103N04 | 398 | 510 | CWSP 2022-2023 | Tier 2
35264181 | CWSP - SANTA YNEZ 1104Y04 PH 1.2 | Base SH | 08W | ESTS | Estimating | 0 | 2.5568 | 0 | 2.5568 | 0 | 0 | 0 | 2.5568 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6365 | -120.0218 | SANTA YNEZ 1104Y04 | SANTA YNEZ 1104Y04 | 576 | 108 | CWSP 2022-2023 | Tier 2
35264182 | CWSP - SANTA YNEZ 1104Y04 PH 1.3 | Base SH | 08W | ESTS | Estimating | 0 | 2.3167 | 0 | 2.3167 | 0 | 0 | 0 | 2.3167 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6278 | -120.0209 | SANTA YNEZ 1104Y04 | SANTA YNEZ 1104Y04 | 576 | 108 | CWSP 2022-2023 | Tier 2
35264183 | CWSP - SANTA YNEZ 1104Y04 PH 2.2 | Base SH | 08W | ESTS | Estimating | 0 | 2.44 | 0 | 2.44 | 0 | 0 | 0 | 2.44 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6273 | -120.0209 | SANTA YNEZ 1104Y04 | SANTA YNEZ 1104Y04 | 576 | 108 | CWSP 2022-2023 | Tier 2
35264184 | CWSP - SANTA YNEZ 1104Y04 PH 2.3 | Base SH | 08W | ESTS | Estimating | 0 | 2.1 | 0 | 2.1 | 0 | 0 | 0 | 2.1 | 0 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.5985 | -120.0297 | SANTA YNEZ 1104Y04 | SANTA YNEZ 1104Y04 | 576 | 108 | CWSP 2022-2023 | Tier 2
35264185 | CWSP - SANTA YNEZ 1104Y66 PH 1.2 | Base SH | 08W | ESTS | Estimating | 0 | 1.52 | 0.18 | 1.7 | 0 | 0 | 0 | 0 | 1.7 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6142 | -119.9878 | SANTA YNEZ 1104Y66 | SANTA YNEZ 1104Y66 | 431 | 153 | CWSP 2022-2023 | Tier 2 & 3
35264186 | CWSP - SANTA YNEZ 1104Y66 PH 1.3 | Base SH | 08W | ESTS | Estimating | 0 | 0 | 0.43 | 0.43 | 0 | 0 | 0 | 0 | 0.43 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6119 | -119.9908 | SANTA YNEZ 1104Y66 | SANTA YNEZ 1104Y66 | 431 | 153 | CWSP 2022-2023 | Tier 2 & 3
35264187 | CWSP - SANTA YNEZ 1104Y66 PH 1.4 | Base SH | 08W | ESTS | Estimating | 0 | 2.07 | 0 | 2.07 | 0 | 0 | 0 | 0 | 2.07 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6112 | -119.9786 | SANTA YNEZ 1104Y66 | SANTA YNEZ 1104Y66 | 431 | 153 | CWSP 2022-2023 | Tier 2 & 3
35264188 | CWSP - SANTA YNEZ 1104Y66 PH 1.5 | Base SH | 08W | ESTS | Estimating | 0 | 1.14 | 0 | 1.14 | 0 | 0 | 0 | 0 | 1.14 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6065 | -119.9508 | SANTA YNEZ 1104Y66 | SANTA YNEZ 1104Y66 | 431 | 153 | CWSP 2022-2023 | Tier 2 & 3
35264189 | CWSP - SANTA YNEZ 1104Y66 PH 2.2 | Base SH | 08W | ESTS | Estimating | 0 | 2.66 | 0 | 2.66 | 0 | 0 | 0 | 0 | 2.66 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6377 | -119.9713 | SANTA YNEZ 1104Y66 | SANTA YNEZ 1104Y66 | 431 | 153 | CWSP 2022-2023 | Tier 2 & 3
35264190 | CWSP - SANTA YNEZ 1104Y66 PH 2.3 | Base SH | 08W | ESTS | Estimating | 0 | 2.37 | 0 | 2.37 | 0 | 0 | 0 | 0 | 2.37 | LP | Region 4 - Central Coast | Santa Ynez | Santa Barbara | 34.6451 | -119.9634 | SANTA YNEZ 1104Y66 | SANTA YNEZ 1104Y66 | 431 | 153 | CWSP 2022-2023 | Tier 2 & 3
35264191 | CWSP - SANTA YNEZ 110477098 PH 1.2 | Base SH | 08W | ESTS | Estimating | 0 | 2.35 | 0 | 2.35 | 0 | 0 | 0 | 2.35 | 0 | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.6323 | -120.1426 | SANTA YNEZ 110477098 | SANTA YNEZ 110477098 | 589 | 308 | CWSP 2022-2023 | Tier 2
35264192 | CWSP - SANTA YNEZ 110477098 PH 1.3 | Base SH | 08W | ESTS | Estimating | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 2.4 | 0 | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.6338 | -120.1419 | SANTA YNEZ 110477098 | SANTA YNEZ 110477098 | 589 | 308 | CWSP 2022-2023 | Tier 2
35264193 | CWSP - SANTA YNEZ 110477098 PH 1.4 | Base SH | 08W | ESTS | Estimating | 0 | 2.08 | 0 | 2.08 | 0 | 0 | 0 | 2.08 | 0 | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.6509 | -120.1422 | SANTA YNEZ 110477098 | SANTA YNEZ 110477098 | 589 | 308 | CWSP 2022-2023 | Tier 2
35264194 | CWSP - SANTA YNEZ 110477098 PH 1.5 | Base SH | 08W | ESTS | Estimating | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.647 | -120.1323 | SANTA YNEZ 110477098 | SANTA YNEZ 110477098 | 589 | 308 | CWSP 2022-2023 | Tier 2
35271002 | CWSP SANTA YNEZ 110477098 PH 1.6 | Base SH | 08W | ESTS | Estimating | 0 | 1.22 | 0 | 1.22 | 0 | 0 | 0 | 1.22 | 0 | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.66 | -120.1339 | SANTA YNEZ 110477098 | SANTA YNEZ 110477098 | 589 | 308 | CWSP 2022-2023 | Tier 2
35271455 | CWSP - VACAVILLE 11046542 PH 1.6 | Base SH | 08W | ESTS | Estimating | 0 | 0.54034 | 0 | 0.54034 | 0 | 0 | 0 | 0.54034 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3373 | -122.0168 | VACAVILLE 11046542 | VACAVILLE 11046542 | 1469 | 42 | Top 250 Miles | Tier 3
35274589 | CWSP MARIPOSA 2101 LR 35244 PH1.2 | Base SH | 08W | UNSE | Scoping/Scoped | 2.132 | 0 | 0 | 2.132 | 0 | 0 | 0 | 0 | 2.132 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5186 | -119.9402 |  | MARIPOSA 210135244 | 1464 | 428 | CWSP 2022-2023 | Tier 2 & 3
35274591 | CWSP MARIPOSA 2101 LR 35244 PH1.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.022 | 0 | 1.022 | 0 | 0 | 0 | 0 | 1.022 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5195 | -119.9397 |  | MARIPOSA 210135244 | 1464 | 428 | CWSP 2022-2023 | Tier 2 & 3
35274592 | CWSP MARIPOSA 2101 LR 35244 PH 2.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.963 | 0 | 1.963 | 0 | 0 | 0 | 0 | 1.963 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5116 | -119.9647 |  | MARIPOSA 210135244 | 1464 | 428 | CWSP 2022-2023 | Tier 2
35274593 | CWSP MARIPOSA 2101 LR 35244 PH 2.3 | Base SH | 08W | UNSE | Scoping/Scoped | 2.756 | 0 | 0 | 2.756 | 0 | 0 | 0 | 0 | 2.756 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5165 | -119.9716 |  | MARIPOSA 210135244 | 1464 | 428 | CWSP 2022-2023 | Tier 2
35274594 | CWSP MARIPOSA 2101 LR 35244 PH 2.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.078 | 0 | 3.078 | 0 | 0 | 0 | 0 | 3.078 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5353 | -119.9554 |  | MARIPOSA 210135244 | 1464 | 428 | CWSP 2022-2023 | Tier 2
35274595 | CWSP MARIPOSA 2101 LR 309438 PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0.057 | 0.057 | 0 | 0 | 0 | 0 | 0.057 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4983 | -119.9732 |  | MARIPOSA 2101309438 | 3000 | 605 | CWSP 2022-2023 | Tier 2
35274596 | CWSP MARIPOSA 2101 LR 309438 PH 1.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.214 | 0.172 | 1.386 | 0 | 0 | 0 | 0 | 1.386 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4889 | -119.9738 |  | MARIPOSA 2101309438 | 3000 | 605 | CWSP 2022-2023 | Tier 2
35274597 | CWSP MARIPOSA 2101 CB PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.633 | 0 | 0.633 | 0 | 0 | 0 | 0 | 0.633 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5054 | -120.0067 |  | MARIPOSA 2101CB | 2081 | 57 | CWSP 2022-2023 | Tier 2
35276100 | REMG - CORNING 110253184 #300 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0.77008 | 0.77008 | 0 | 0 | 0 | 0.77008 | 0 | NV | Region 2 - North East | Flournoy | Tehama | 39.9108 | -122.493 | CORNING 110253184 | CORNING 110253184 | 1844 | 413 | Remote Grid Pilot | Tier 3
35277921 | CWSP AUBERRY 1101 R2578 PH1.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.4 | 0 | 2.4 | 0 | 0 | 0 | 0 | 2.4 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0111 | -119.4175 |  | AUBERRY 1101R2578 | 1377 | 163 | CWSP 2022-2023 | Tier 2
35277922 | CWSP AUBERRY 1101 R2578 PH1.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.76 | 0 | 1.76 | 0 | 0 | 0 | 0 | 1.76 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.005 | -119.4055 |  | AUBERRY 1101R2578 | 1377 | 163 | CWSP 2022-2023 | Tier 2
35277923 | CWSP AUBERRY 1101 R2578 PH1.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.1701 | 0 | 3.1701 | 0 | 0 | 0 | 0 | 3.1701 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9916 | -119.4068 |  | AUBERRY 1101R2578 | 1377 | 163 | CWSP 2022-2023 | Tier 2
35277924 | CWSP AUBERRY 1101 R2578 PH1.5 | Base SH | 08W | UNSE | Scoping/Scoped | 0.10909 | 0 | 0.12955 | 0.23864 | 0 | 0 | 0 | 0 | 0.23864 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0071 | -119.4086 |  | AUBERRY 1101R2578 | 1377 | 163 | CWSP 2022-2023 | Tier 2
35277925 | CWSP - AUBERRY 1101CB PH1.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0.21326 | 0 | 0 | 0.21326 | 0 | 0 | 0 | 0.21326 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0746 | -119.4845 |  | AUBERRY 1101CB | 1431 | 63 | CWSP 2022-2023 | Tier 2
35277926 | CWSP - AUBERRY 1101CB PH1.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.4417 | 0 | 3.4417 | 0 | 0 | 0 | 3.4417 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0749 | -119.4852 |  | AUBERRY 1101CB | 1431 | 63 | CWSP 2022-2023 | Tier 2
35277927 | CWSP - AUBERRY 1101CB PH1.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.8672 | 0 | 2.8672 | 0 | 0 | 0 | 2.8672 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.067 | -119.4802 |  | AUBERRY 1101CB | 1431 | 63 | CWSP 2022-2023 | Tier 2
35277929 | CWSP - AUBERRY 1101CB PH2.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.4011 | 0 | 2.4011 | 0 | 0 | 0 | 2.4011 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0578 | -119.4739 |  | AUBERRY 1101CB | 1431 | 63 | CWSP 2022-2023 | Tier 2
35277930 | CWSP - AUBERRY 1101CB PH2.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.32936 | 0 | 0.32936 | 0 | 0 | 0 | 0.32936 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0528 | -119.4629 |  | AUBERRY 1101CB | 1431 | 63 | CWSP 2022-2023 | Tier 2
35277931 | CWSP - AUBERRY 1101CB PH2.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.5072 | 0 | 3.5072 | 0 | 0 | 0 | 3.5072 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0503 | -119.4639 |  | AUBERRY 1101CB | 1431 | 63 | CWSP 2022-2023 | Tier 2
35277933 | CWSP AUBERRY 1101 R2839 PH1.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.1036 | 0 | 2.1036 | 0 | 0 | 0 | 0 | 2.1036 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0335 | -119.4426 |  | AUBERRY 1101R2839 | 1746 | 274 | CWSP 2022-2023 | Tier 2
35277934 | CWSP AUBERRY 1101 R2839 PH1.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.1415 | 0 | 2.1415 | 0 | 0 | 0 | 0 | 2.1415 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0314 | -119.4428 |  | AUBERRY 1101R2839 | 1746 | 274 | CWSP 2022-2023 | Tier 2
35277935 | CWSP AUBERRY 1101 R2839 PH1.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0.093 | 0 | 0 | 0.093 | 0 | 0 | 0 | 0 | 0.092992 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0313 | -119.4396 |  | AUBERRY 1101R2839 | 1746 | 274 | CWSP 2022-2023 | Tier 2
35277936 | CWSP AUBERRY 1101 R2578 PH2.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.94 | 0 | 3.94 | 0 | 0 | 0 | 3.94 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0143 | -119.4031 |  | AUBERRY 1101R2578 | 1377 | 163 | CWSP 2022-2023 | Tier 2
35277937 | CWSP AUBERRY 1101 R2578 PH2.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.8701 | 0 | 2.8701 | 0 | 0 | 0 | 2.8701 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0129 | -119.3939 |  | AUBERRY 1101R2578 | 1377 | 163 | CWSP 2022-2023 | Tier 2
35277938 | CWSP AUBERRY 1101 R2578 PH2.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0.38996 | 0 | 0.27973 | 0.6697 | 0 | 0 | 0 | 0.6697 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0125 | -119.4038 |  | AUBERRY 1101R2578 | 1377 | 163 | CWSP 2022-2023 | Tier 2
35278090 | CWSP - AUBERRY 1101R2839 PH2.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.8492 | 0.39583 | 3.2451 | 0 | 0 | 0 | 0 | 3.2451 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0201 | -119.4294 |  | AUBERRY 1101R2839 | 1746 | 274 | CWSP 2022-2023 | Tier 2
35278091 | CWSP - AUBERRY 1101R2578 PH3.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.839 | 0 | 2.839 | 0 | 0 | 0 | 0 | 2.839 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9796 | -119.3694 |  | AUBERRY 1101R2578 | 1377 | 163 | CWSP 2022-2023 | Tier 2
35278092 | CWSP - AUBERRY 1101R2578 PH3.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.8369 | 0 | 3.8369 | 0 | 0 | 0 | 0 | 3.8369 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.978 | -119.3677 |  | AUBERRY 1101R2578 | 1377 | 163 | CWSP 2022-2023 | Tier 2
35278093 | CWSP - AUBERRY 1101R2578 PH3.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0.415 | 0 | 0 | 0.415 | 0 | 0 | 0 | 0 | 0.41496 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9797 | -119.3677 |  | AUBERRY 1101R2578 | 1377 | 163 | CWSP 2022-2023 | Tier 2
35278096 | CWSP - AUBERRY 1101R2578 PH4.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.23 | 0 | 1.23 | 0 | 0 | 0 | 0 | 1.23 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9806 | -119.3952 |  | AUBERRY 1101R2578 | 1377 | 163 | CWSP 2022-2023 | Tier 2
35278097 | CWSP - AUBERRY 1101R2578 PH4.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.2 | 0 | 1.2 | 0 | 0 | 0 | 0 | 1.2 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.98 | -119.4029 |  | AUBERRY 1101R2578 | 1377 | 163 | CWSP 2022-2023 | Tier 2
35278098 | CWSP - AUBERRY 1101R2578 PH4.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.54 | 0 | 1.54 | 0 | 0 | 0 | 0 | 1.54 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9797 | -119.4037 |  | AUBERRY 1101R2578 | 1377 | 163 | CWSP 2022-2023 | Tier 2
35278880 | CWSP - PASO ROBLES 1103 LRN54 PH1.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.09 | 0 | 2.09 | 0 | 0 | 0 | 2.09 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6698 | -120.7266 |  | PASO ROBLES 1103N54 | 564 | 69 | CWSP 2022-2023 | Tier 2
35278881 | CWSP - PASO ROBLES 1103 LRN54 PH1.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.68 | 0 | 2.68 | 0 | 0 | 0 | 2.68 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6635 | -120.7259 |  | PASO ROBLES 1103N54 | 564 | 69 | CWSP 2022-2023 | Tier 2
35278882 | CWSP - PASO ROBLES 1103 LRN54 PH1.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.01 | 0 | 2.01 | 0 | 0 | 0 | 2.01 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6747 | -120.7423 |  | PASO ROBLES 1103N54 | 564 | 69 | CWSP 2022-2023 | Tier 2
35278883 | CWSP - PASO ROBLES 1103 LRN54 PH2.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.81 | 0 | 1.81 | 0 | 0 | 0 | 1.81 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6795 | -120.745 |  | PASO ROBLES 1103N54 | 564 | 69 | CWSP 2022-2023 | Tier 2
35278884 | CWSP - PASO ROBLES 1103 LRN54 PH2.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.77 | 0 | 2.77 | 0 | 0 | 0 | 2.77 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6807 | -120.7554 |  | PASO ROBLES 1103N54 | 564 | 69 | CWSP 2022-2023 | Tier 2
35278885 | CWSP - PASO ROBLES 1103 LRN54 PH2.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.47 | 0 | 1.47 | 0 | 0 | 0 | 1.47 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6819 | -120.7391 |  | PASO ROBLES 1103N54 | 564 | 69 | CWSP 2022-2023 | Tier 2
35278886 | CWSP - PASO ROBLES 1103 LRN54 PH2.5 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 1.49 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6892 | -120.7391 |  | PASO ROBLES 1103N54 | 564 | 69 | CWSP 2022-2023 | Tier 2
35278887 | CWSP - PASO ROBLES 1103 LRN54 PH2.6 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.48 | 0 | 1.48 | 0 | 0 | 0 | 1.48 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6819 | -120.738 |  | PASO ROBLES 1103N54 | 564 | 69 | CWSP 2022-2023 | Tier 2
35278888 | CWSP - PASO ROBLES 1103 LRN54 PH2.7 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.39 | 0 | 1.39 | 0 | 0 | 0 | 1.39 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6848 | -120.73 |  | PASO ROBLES 1103N54 | 564 | 69 | CWSP 2022-2023 | Tier 2
35278889 | CWSP - AUBERRY 1101 LR49122 PH1.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.1968 | 0 | 2.1968 | 0 | 0 | 0 | 0 | 2.1968 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0894 | -119.4783 |  | AUBERRY 110149122 | 682 | 330 | CWSP 2022-2023 | Tier 2
35278890 | CWSP - AUBERRY 1101R2578 PH5.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.75 | 0 | 1.75 | 0 | 0 | 0 | 1.75 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9737 | -119.3888 |  | AUBERRY 1101R2578 | 1377 | 163 | CWSP 2022-2023 | Tier 2
35278891 | CWSP - AUBERRY 1101R2578 PH5.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9752 | -119.3882 |  | AUBERRY 1101R2578 | 1377 | 163 | CWSP 2022-2023 | Tier 2
35278892 | CWSP - AUBERRY 1101R2578 PH5.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.5299 | 0 | 2.5299 | 0 | 0 | 0 | 2.5299 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9662 | -119.3834 |  | AUBERRY 1101R2578 | 1377 | 163 | CWSP 2022-2023 | Tier 2
35278899 | CWSP - STANISLAUS 1701 CB PH1.2 | Base SH | 08W | UNSE | Scoping/Scoped | 2.9449 | 0 | 0 | 2.9449 | 0 | 0 | 0 | 0 | 2.9449 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 |  | STANISLAUS 1701CB | 1422 | 56 | CWSP 2022-2023 | Tier 2 & 3
35279120 | CWSP - STANISLAUS 1701 CB PH1.3 | Base SH | 08W | UNSE | Scoping/Scoped | 1.004 | 0 | 0 | 1.004 | 0 | 0 | 0 | 0 | 1.004 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1831 | -120.3755 |  | STANISLAUS 1701CB | 1422 | 56 | CWSP 2022-2023 | Tier 2 & 3
35279121 | CWSP - STANISLAUS 1701 CB PH1.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.77235 | 0 | 0.77235 | 0 | 0 | 0 | 0 | 0.77235 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1797 | -120.3786 |  | STANISLAUS 1701CB | 1422 | 56 | CWSP 2022-2023 | Tier 2 & 3
35279122 | CWSP - STANISLAUS 1701 CB PH1.5 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.90909 | 0 | 0.90909 | 0 | 0 | 0 | 0 | 0.90909 | YO | Region 5 - Central Valley | Mi Wuk Village | Tuolumne | 38.1379 | -120.3707 |  | STANISLAUS 1701CB | 1422 | 56 | CWSP 2022-2023 | Tier 2 & 3
35279626 | CWSP - PASO ROBLES 1103 LR 2731 PH1.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.17 | 0 | 0.17 | 0 | 0 | 0 | 0 | 0.17 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6844 | -120.73 |  | PASO ROBLES 11032731 | 1088 | 260 | CWSP 2022-2023 | Tier 2
35279627 | CWSP - PASO ROBLES 1103 LRN50 PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.47 | 0 | 1.47 | 0 | 0 | 0 | 0 | 1.47 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.7253 | -120.8701 |  | PASO ROBLES 1103N50 | 465 | 138 | CWSP 2022-2023 | Tier 2
35279628 | CWSP PASO ROBLES 1103 LRN52 PH1.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.37 | 0 | 2.37 | 0 | 0 | 0 | 0 | 2.37 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.706 | -120.8189 |  | PASO ROBLES 1103N52 | 1851 | 291 | CWSP 2022-2023 | Tier 2
35279629 | CWSP PASO ROBLES 1103 LRN52 PH1.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.71 | 0 | 1.71 | 0 | 0 | 0 | 0 | 1.71 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.7141 | -120.8386 |  | PASO ROBLES 1103N52 | 1851 | 291 | CWSP 2022-2023 | Tier 2
35279630 | CWSP - PASO ROBLES 1103 LR59763 PH1.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.69 | 0 | 1.69 | 0 | 0 | 0 | 1.69 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6401 | -120.7318 |  | PASO ROBLES 110359763 | 616 | 615 | CWSP 2022-2023 | Tier 2
35279631 | CWSP PASO ROBLES 1103 LRN58 PH1.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 3.07 | 0 | 3.07 | 0 | 0 | 0 | 3.07 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 35.6385 | -120.7157 |  | PASO ROBLES 1103N58 | 676 | 257 | CWSP 2022-2023 | Tier 2
35279985 | FRRB - BIG MEADOWS 2101 (REMG) | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 2.19 | 2.19 | 0 | 0 | 0 | 2.19 | 0 | NV | Region 2 - North East | Chester | Plumas | 40.2927 | -121.2429 |  | BIG MEADOWS 21012248 | 1922 | 916 | FRRB | Tier 2
35280362 | CWSP - MARIPOSA 2102440236 PH1.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0.1089 | 0 | 0 | 0.1089 | 0 | 0 | 0 | 0.1089 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4632 | -119.9483 | MARIPOSA 2102440236 | MARIPOSA 2102440236 | 3110 | 50 | Top 250 Miles | Tier 2 & 3
35282057 | FRRB - GANSNER 11012424 REMG PH1.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0.48 | 0.48 | 0 | 0 | 0 | 0.48 | 0 | NV | Region 2 - North East | Quincy | Plumas | 0 | 0 | GANSNER 11012424 | GANSNER 11012424 | 1231 | 1172 | FRRB | Tier 2 & 3
35283196 | CWSP HARTLEY 1101 LR698 PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.66799 | 0 | 0.66799 | 0 | 0 | 0 | 0 | 0.66799 | HB | Region 1 - North Coast | Lakeport | Lake | 39.095 | -122.9656 |  | HARTLEY 1101698 | 1832 | 58 | CWSP 2022-2023 | Tier 3
35283197 | CWSP HARTLEY 1101 LR698 PH 1.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.4381 | 0 | 2.4381 | 0 | 0 | 0 | 0 | 2.4381 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0946 | -122.9632 |  | HARTLEY 1101698 | 1832 | 58 | CWSP 2022-2023 | Tier 2
35283198 | CWSP HARTLEY 1101 LR698 PH 1.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0.27803 | 0 | 0 | 0.27803 | 0 | 0 | 0 | 0 | 0.27803 | HB | Region 1 - North Coast | Lakeport | Lake | 39.108 | -122.9558 |  | HARTLEY 1101698 | 1832 | 58 | CWSP 2022-2023 | Tier 2
35283199 | CWSP HARTLEY 1101 LR698 PH 1.5 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.2701 | 0 | 1.2701 | 0 | 0 | 0 | 0 | 1.2701 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0813 | -122.9625 |  | HARTLEY 1101698 | 1832 | 58 | CWSP 2022-2023 | Tier 2
35283340 | CWSP HARTLEY 1101 LR698 PH 1.6 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 0 | 1.49 | HB | Region 1 - North Coast | Lakeport | Lake | 39.105 | -122.9581 |  | HARTLEY 1101698 | 1832 | 58 | CWSP 2022-2023 | Tier 2
35283341 | CWSP UPPER LAKE 1101 1276 PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.07803 | 0 | 0.07803 | 0 | 0 | 0 | 0 | 0.07803 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.157 | -122.9917 |  | UPPER LAKE 11011276 | 1931 | 335 | CWSP 2022-2023 | Tier 2
35283343 | CWSP UPPER LAKE 1101 1276 PH 1.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0.85303 | 0 | 0 | 0.85303 | 0 | 0 | 0 | 0 | 0.85303 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1488 | -122.9992 |  | UPPER LAKE 11011276 | 1931 | 335 | CWSP 2022-2023 | Tier 2
35283344 | CWSP UPPER LAKE 1101 1276 PH 1.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.6561 | 0 | 1.6561 | 0 | 0 | 0 | 0 | 1.6561 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1474 | -122.9995 |  | UPPER LAKE 11011276 | 1931 | 335 | CWSP 2022-2023 | Tier 2
35283346 | CWSP UPPER LAKE 1101 1276 PH 1.5 | Base SH | 08W | UNSE | Scoping/Scoped | 0.77803 | 0 | 0 | 0.77803 | 0 | 0 | 0 | 0 | 0.77803 | HB | Region 1 - North Coast | Lakeport | Lake | 39.13 | -122.997 |  | UPPER LAKE 11011276 | 1931 | 335 | CWSP 2022-2023 | Tier 2
35283347 | CWSP UPPER LAKE 1101 1276 PH 1.6 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.478 | 0 | 1.478 | 0 | 0 | 0 | 0 | 1.478 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1253 | -122.9948 |  | UPPER LAKE 11011276 | 1931 | 335 | CWSP 2022-2023 | Tier 2
35283348 | CWSP UPPER LAKE 1101 1276 PH 1.7 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.075 | 0 | 1.075 | 0 | 0 | 0 | 0 | 1.075 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1213 | -122.9896 |  | UPPER LAKE 11011276 | 1931 | 335 | CWSP 2022-2023 | Tier 2
35283349 | CWSP UPPER LAKE 1101 1276 PH 1.8 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.0549 | 0 | 1.0549 | 0 | 0 | 0 | 0 | 1.0549 | HB | Region 1 - North Coast | Lakeport | Lake | 39.113 | -122.9818 |  | UPPER LAKE 11011276 | 1931 | 335 | CWSP 2022-2023 | Tier 2
35283938 | CWSP - WOODSIDE 1101 FS 775939 | Base SH | 08W | UNSE | Scoping/Scoped | 2.4799 | 0 | 0 | 2.4799 | 0 | 0 | 0 | 0 | 2.4799 | PN | Region 3 - Bay Area | Redwood City | San Mateo | 37.3781 | -122.2796 |  | WOODSIDE 11018974 | 55 | 1145 | CWSP 2022-2023 | Tier 3
35284364 | CWSP STANISLAUS 1702 CB PH 1.2 | Base SH | 08W | UNSE | Scoping/Scoped | 4.3498 | 0.040341 | 0 | 4.3902 | 0 | 0 | 0 | 0 | 4.3902 | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1677 | -120.3831 |  | STANISLAUS 1702CB | 1360 | 235 | CWSP 2022-2023 | Tier 2 & 3
35284365 | CWSP STANISLAUS 1702 CB PH 1.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0.19375 | 0.019508 | 0 | 0.21326 | 0 | 0 | 0 | 0 | 0.21326 | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2399 | -120.3619 |  | STANISLAUS 1702CB | 1360 | 235 | CWSP 2022-2023 | Tier 2 & 3
35284366 | CWSP STANISLAUS 1702 CB PH 1.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 0.60871 | 0.60871 | 0 | 0 | 0 | 0.60871 | 0 | YO | Region 5 - Central Valley | Mi Wuk Village | Tuolumne | 38.1446 | -120.3574 | STANISLAUS 1702CB | STANISLAUS 1702CB | 1360 | 235 | CWSP 2022-2023 | Tier 2 & 3
35285064 | CWSP POTTER VALLEY PH 1105 LR37476 PH1.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0.58636 | 0 | 0 | 0.58636 | 0 | 0 | 0 | 0 | 0.58636 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3076 | -123.1132 |  | POTTER VALLEY P H 110537476 | 2366 | 396 | CWSP 2022-2023 | Tier 2
35285065 | CWSP POTTER VALLEY PH 1105 LR37476 PH1.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0.24167 | 0.012311 | 0 | 0.25398 | 0 | 0 | 0 | 0 | 0.25398 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.2968 | -123.1087 |  | POTTER VALLEY P H 110537476 | 2366 | 396 | CWSP 2022-2023 | Tier 2
35285245 | CWSP POTTER VALLEY PH 1105 LR37476 PH1.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.40398 | 0 | 0.40398 | 0 | 0 | 0 | 0 | 0.40398 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3022 | -123.1091 |  | POTTER VALLEY P H 110537476 | 2366 | 396 | CWSP 2022-2023 | Tier 2
35285247 | CWSP - UPPER LAKE 1101 1276 PH 2.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.48106 | 0 | 0.48106 | 0 | 0 | 0 | 0 | 0.48106 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1668 | -123.0058 |  | UPPER LAKE 11011276 | 1931 | 335 | CWSP 2022-2023 | Tier 2
35285248 | CWSP - UPPER LAKE 1101 1276 PH 2.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.461 | 0 | 1.461 | 0 | 0 | 0 | 0 | 1.461 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1679 | -123.0053 |  | UPPER LAKE 11011276 | 1931 | 335 | CWSP 2022-2023 | Tier 2
35285249 | CWSP - UPPER LAKE 1101 1276 PH 2.4 | Base SH | 08W | UNSE | Scoping/Scoped | 2.593 | 0 | 0 | 2.593 | 0 | 0 | 0 | 0 | 2.593 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1673 | -123.0087 |  | UPPER LAKE 11011276 | 1931 | 335 | CWSP 2022-2023 | Tier 2
35285250 | CWSP - UPPER LAKE 1101 1276 PH 2.5 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.51705 | 0 | 0.51705 | 0 | 0 | 0 | 0 | 0.51705 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1756 | -123.0186 |  | UPPER LAKE 11011276 | 1931 | 335 | CWSP 2022-2023 | Tier 2
35285251 | CWSP - UPPER LAKE 1101 1276 PH 2.6 | Base SH | 08W | UNSE | Scoping/Scoped | 0.65303 | 0 | 0 | 0.65303 | 0 | 0 | 0 | 0 | 0.65303 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1758 | -123.0191 |  | UPPER LAKE 11011276 | 1931 | 335 | CWSP 2022-2023 | Tier 2
35286103 | CWSP - BIG MEADOWS 21012510 | Base SH | 08W | UNSE | Scoping/Scoped | 13.9201 | 0 | 0 | 13.9201 | 0 | 0 | 0 | 0 | 13.9201 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | BIG MEADOWS 21012510 | 2457 | 3328 | CWSP 2022-2023 | Tier 2
35290295 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.197 | 0 | 1.197 | 0 | 0 | 0 | 0 | 1.197 | HB | Region 1 - North Coast | Calpella | Mendocino | 39.2738 | -123.0944 |  | POTTER VALLEY P H 11051904 | 1439 | 75 | CWSP 2022-2023 | Tier 2
35290296 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.93807 | 0 | 0.93807 | 0 | 0 | 0 | 0 | 0.93807 | HB | Region 1 - North Coast | Calpella | Mendocino | 39.2715 | -123.097 |  | POTTER VALLEY P H 11051904 | 1439 | 75 | CWSP 2022-2023 | Tier 2
35290297 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.0451 | 0 | 1.0451 | 0 | 0 | 0 | 0 | 1.0451 | HB | Region 1 - North Coast | Calpella | Mendocino | 39.2696 | -123.1053 |  | POTTER VALLEY P H 11051904 | 1439 | 75 | CWSP 2022-2023 | Tier 2
35290298 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.5 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.2799 | 0 | 1.2799 | 0 | 0 | 0 | 0 | 1.2799 | HB | Region 1 - North Coast | Calpella | Mendocino | 39.2619 | -123.1148 |  | POTTER VALLEY P H 11051904 | 1439 | 75 | CWSP 2022-2023 | Tier 2
35290299 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.6 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.4189 | 0 | 1.4189 | 0 | 0 | 0 | 0 | 1.4189 | HB | Region 1 - North Coast | Calpella | Mendocino | 39.2594 | -123.1172 |  | POTTER VALLEY P H 11051904 | 1439 | 75 | CWSP 2022-2023 | Tier 2
35290500 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.7 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.0229 | 0 | 1.0229 | 0 | 0 | 0 | 0 | 1.0229 | HB | Region 1 - North Coast | Calpella | Mendocino | 39.2537 | -123.1188 |  | POTTER VALLEY P H 11051904 | 1439 | 75 | CWSP 2022-2023 | Tier 2
35290501 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.64 | 0 | 1.64 | 0 | 0 | 0 | 0 | 1.64 | HB | Region 1 - North Coast | Calpella | Mendocino | 39.2328 | -123.1053 |  | POTTER VALLEY P H 11051904 | 1439 | 75 | CWSP 2022-2023 | Tier 2
35290502 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0 | 1.6299 | 1.6299 | 0 | 0 | 0 | 0 | 1.6299 | HB | Region 1 - North Coast | Calpella | Mendocino | 39.228 | -123.0887 |  | POTTER VALLEY P H 11051904 | 1439 | 75 | CWSP 2022-2023 | Tier 2
35290503 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.49 | 0 | 1.49 | 0 | 0 | 0 | 0 | 1.49 | HB | Region 1 - North Coast | Calpella | Mendocino | 39.2248 | -123.0882 |  | POTTER VALLEY P H 11051904 | 1439 | 75 | CWSP 2022-2023 | Tier 2
35290504 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.5 | Base SH | 08W | UNSE | Scoping/Scoped | 0.61004 | 0 | 0 | 0.61004 | 0 | 0 | 0 | 0 | 0.61004 | HB | Region 1 - North Coast | Calpella | Mendocino | 39.2145 | -123.0742 |  | POTTER VALLEY P H 11051904 | 1439 | 75 | CWSP 2022-2023 | Tier 2
35290506 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.6 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.09 | 0 | 2.09 | 0 | 0 | 0 | 0 | 2.09 | HB | Region 1 - North Coast | Calpella | Mendocino | 39.2105 | -123.0642 |  | POTTER VALLEY P H 11051904 | 1439 | 75 | CWSP 2022-2023 | Tier 2
35290507 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.7 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.77992 | 0 | 0.77992 | 0 | 0 | 0 | 0 | 0.77992 | HB | Region 1 - North Coast | Calpella | Mendocino | 39.1963 | -123.0435 |  | POTTER VALLEY P H 11051904 | 1439 | 75 | CWSP 2022-2023 | Tier 2
35290508 | CWSP POTTER VALLEY PH 1105 LR1904 PH3.8 | Base SH | 08W | UNSE | Scoping/Scoped | 0.62008 | 0 | 0 | 0.62008 | 0 | 0 | 0 | 0 | 0.62008 | HB | Region 1 - North Coast | Calpella | Mendocino | 39.1988 | -123.0496 |  | POTTER VALLEY P H 11051904 | 1439 | 75 | CWSP 2022-2023 | Tier 2
35290509 | CWSP POTTER VALLEY PH 1105 LR1904 PH4.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.09 | 0 | 1.09 | 0 | 0 | 0 | 0 | 1.09 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1918 | -123.0344 |  | POTTER VALLEY P H 11051904 | 1439 | 75 | CWSP 2022-2023 | Tier 2
35290510 | CWSP POTTER VALLEY PH 1105 LR1904 PH4.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.6 | 0 | 0.6 | 0 | 0 | 0 | 0 | 0.6 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1887 | -123.0323 |  | POTTER VALLEY P H 11051904 | 1439 | 75 | CWSP 2022-2023 | Tier 2
35290511 | CWSP - HIGHLANDS 1102 LR623120 PH1.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.2799 | 0 | 1.2799 | 0 | 0 | 0 | 0 | 1.2799 | HB | Region 1 - North Coast | Clearlake | Lake | 38.979 | -122.6124 |  | HIGHLANDS 1102623120 | 2966 | 74 | CWSP 2022-2023 | Tier 2
35290512 | CWSP - HIGHLANDS 1102 LR623120 PH1.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.06 | 0 | 2.06 | 0 | 0 | 0 | 0 | 2.06 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9543 | -122.6079 |  | HIGHLANDS 1102623120 | 2966 | 74 | CWSP 2022-2023 | Tier 2
35290513 | CWSP - HIGHLANDS 1102 LR623120 PH1.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 2.0201 | 0 | 2.0201 | 0 | 0 | 0 | 0 | 2.0201 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9769 | -122.6124 |  | HIGHLANDS 1102623120 | 2966 | 74 | CWSP 2022-2023 | Tier 2
35290514 | CWSP - HIGHLANDS 1102 LR623120 PH1.5 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 0.060038 | 0 | 0.060038 | 0 | 0 | 0 | 0 | 0.060038 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9794 | -122.6125 |  | HIGHLANDS 1102623120 | 2966 | 74 | CWSP 2022-2023 | Tier 2
35290807 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.8 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.2259 | 0 | 1.2259 | 0 | 0 | 0 | 0 | 1.2259 | HB | Region 1 - North Coast | Calpella | Mendocino | 39.2457 | -123.1271 |  | POTTER VALLEY P H 11051904 | 1439 | 75 | CWSP 2022-2023 | Tier 2
35290808 | CWSP POTTER VALLEY PH 1105 LR1904 PH2.9 | Base SH | 08W | UNSE | Scoping/Scoped | 0.24508 | 0 | 0 | 0.24508 | 0 | 0 | 0 | 0 | 0.24508 | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.2815 | -123.1027 |  | POTTER VALLEY P H 11051904 | 1439 | 75 | CWSP 2022-2023 | Tier 2
35293505 | CWSP MOUNTAIN QUARRIES 2101 CB PH2.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.39 | 0 | 1.39 | 0 | 0 | 0 | 0 | 1.39 | SI | Region 2 - North East | Cool | El Dorado | 38.8782 | -120.9979 |  | MOUNTAIN QUARRIES 2101CB | 412 | 68 | CWSP 2022-2023 | Tier 2
35293506 | CWSP MOUNTAIN QUARRIES 2101 CB PH2.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.39 | 0 | 1.39 | 0 | 0 | 0 | 0 | 1.39 | SI | Region 2 - North East | Cool | El Dorado | 38.8803 | -121.0037 |  | MOUNTAIN QUARRIES 2101CB | 412 | 68 | CWSP 2022-2023 | Tier 2
35293507 | CWSP MOUNTAIN QUARRIES 2101 CB PH2.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.39 | 0 | 1.39 | 0 | 0 | 0 | 0 | 1.39 | SI | Region 2 - North East | Cool | El Dorado | 38.8774 | -120.9979 |  | MOUNTAIN QUARRIES 2101CB | 412 | 68 | CWSP 2022-2023 | Tier 2
35293508 | CWSP MOUNTAIN QUARRIES 2101 CB PH2.5 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.39 | 0 | 1.39 | 0 | 0 | 0 | 0 | 1.39 | SI | Region 2 - North East | Cool | El Dorado | 38.8729 | -120.991 |  | MOUNTAIN QUARRIES 2101CB | 412 | 68 | CWSP 2022-2023 | Tier 2
35293509 | CWSP MOUNTAIN QUARRIES 2101 CB PH2.6 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.39 | 0 | 1.39 | 0 | 0 | 0 | 0 | 1.39 | SI | Region 2 - North East | Cool | El Dorado | 38.8608 | -120.993 |  | MOUNTAIN QUARRIES 2101CB | 412 | 68 | CWSP 2022-2023 | Tier 2
35293662 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.2087 | 0 | 1.2087 | 0 | 0 | 0 | 0 | 1.2087 | SI | Region 2 - North East | Cool | El Dorado | 38.8956 | -120.9606 |  | MOUNTAIN QUARRIES 21011350 | 1328 | 169 | CWSP 2022-2023 | Tier 2
35293663 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.2087 | 0 | 1.2087 | 0 | 0 | 0 | 0 | 1.2087 | SI | Region 2 - North East | Greenwood | El Dorado | 38.8964 | -120.922 |  | MOUNTAIN QUARRIES 21011350 | 1328 | 169 | CWSP 2022-2023 | Tier 2
35293664 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.2087 | 0 | 1.2087 | 0 | 0 | 0 | 0 | 1.2087 | SI | Region 2 - North East | Greenwood | El Dorado | 38.8981 | -120.914 |  | MOUNTAIN QUARRIES 21011350 | 1328 | 169 | CWSP 2022-2023 | Tier 2
35293665 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.5 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.2087 | 0 | 1.2087 | 0 | 0 | 0 | 0 | 1.2087 | SI | Region 2 - North East | Greenwood | El Dorado | 38.8973 | -120.9098 |  | MOUNTAIN QUARRIES 21011350 | 1328 | 169 | CWSP 2022-2023 | Tier 2
35293666 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.6 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.2087 | 0 | 1.2087 | 0 | 0 | 0 | 0 | 1.2087 | SI | Region 2 - North East | Cool | El Dorado | 38.9012 | -120.9346 |  | MOUNTAIN QUARRIES 21011350 | 1328 | 169 | CWSP 2022-2023 | Tier 2
35293667 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.7 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.2087 | 0 | 1.2087 | 0 | 0 | 0 | 0 | 1.2087 | SI | Region 2 - North East | Cool | El Dorado | 38.8974 | -120.9338 |  | MOUNTAIN QUARRIES 21011350 | 1328 | 169 | CWSP 2022-2023 | Tier 2
35293668 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.8 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.2087 | 0 | 1.2087 | 0 | 0 | 0 | 0 | 1.2087 | SI | Region 2 - North East | Cool | El Dorado | 38.8894 | -120.9589 |  | MOUNTAIN QUARRIES 21011350 | 1328 | 169 | CWSP 2022-2023 | Tier 2
35293669 | CWSP-MOUNTAIN QUARRIES 2101 LR1350 PH2.9 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.2087 | 0 | 1.2087 | 0 | 0 | 0 | 0 | 1.2087 | SI | Region 2 - North East | Cool | El Dorado | 38.8852 | -120.96 |  | MOUNTAIN QUARRIES 21011350 | 1328 | 169 | CWSP 2022-2023 | Tier 2
35293670 | CWSP-MOUNTAIN QUARRIES 21011350 PH2.10 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.2087 | 0 | 1.2087 | 0 | 0 | 0 | 0 | 1.2087 | SI | Region 2 - North East | Cool | El Dorado | 38.8805 | -120.9418 |  | MOUNTAIN QUARRIES 21011350 | 1328 | 169 | CWSP 2022-2023 | Tier 2
35293672 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1.2 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.0424 | 0 | 1.0424 | 0 | 0 | 0 | 0 | 1.0424 | SI | Region 2 - North East | Cool | El Dorado | 38.9075 | -121.0168 |  | MOUNTAIN QUARRIES 2101CB | 412 | 68 | CWSP 2022-2023 | Tier 2
35293673 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1.3 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.0424 | 0 | 1.0424 | 0 | 0 | 0 | 0 | 1.0424 | SI | Region 2 - North East | Cool | El Dorado | 38.8939 | -121.0149 |  | MOUNTAIN QUARRIES 2101CB | 412 | 68 | CWSP 2022-2023 | Tier 2
35293674 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1.4 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.0424 | 0 | 1.0424 | 0 | 0 | 0 | 0 | 1.0424 | SI | Region 2 - North East | Cool | El Dorado | 38.8882 | -121.0144 |  | MOUNTAIN QUARRIES 2101CB | 412 | 68 | CWSP 2022-2023 | Tier 2
35293675 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1.5 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.0424 | 0 | 1.0424 | 0 | 0 | 0 | 0 | 1.0424 | SI | Region 2 - North East | Cool | El Dorado | 38.8795 | -121.0164 |  | MOUNTAIN QUARRIES 2101CB | 412 | 68 | CWSP 2022-2023 | Tier 2
35293676 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1.6 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.0424 | 0 | 1.0424 | 0 | 0 | 0 | 0 | 1.0424 | SI | Region 2 - North East | Cool | El Dorado | 38.8745 | -121.0198 |  | MOUNTAIN QUARRIES 2101CB | 412 | 68 | CWSP 2022-2023 | Tier 2
35293677 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1.7 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.0424 | 0 | 1.0424 | 0 | 0 | 0 | 0 | 1.0424 | SI | Region 2 - North East | Cool | El Dorado | 38.8918 | -120.9988 |  | MOUNTAIN QUARRIES 2101CB | 412 | 68 | CWSP 2022-2023 | Tier 2
35293847 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1.8 | Base SH | 08W | UNSE | Scoping/Scoped | 0 | 1.0424 | 0 | 1.0424 | 0 | 0 | 0 | 0 | 1.0424 | SI | Region 2 - North East | Cool | El Dorado | 38.8704 | -121.0217 |  | MOUNTAIN QUARRIES 2101CB | 412 | 68 | CWSP 2022-2023 | Tier 2
74022384 | OCGC CWSP - FITCH MOUNTAIN 1113 LR 24918 | Base SH | 08W | FICL | Post-Construction | 0 | 5.2544 | 0 | 5.2544 | 0.96004 | 4.2943 | 0 | 0 | 0 | SO | Region 1 - North Coast | Geyserville | Sonoma | 38.5914 | -122.92 | FITCH MOUNTAIN 111324918 | FITCH MOUNTAIN 111324918 | 209 | 481 | Pre | Tier 3
31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | Fire Rebuild | 92F | UNSC | Ready for Construction | 0 | 1.0136 | 0 | 1.0136 | 0 | 0 | 1.0136 | 0 | 0 | NV | Region 2 - North East |  |  | 40.012 | -120.9667 |  |  |  |  | FRRB
35199565 | NO-NV-BUTTE 9/8/20- N. CMPLX FIRE SYS H | Fire Rebuild | 95A | ESTS | In-Construction* | 0 | 28.8953 | 0 | 28.8953 | 26.7508 | 2.1445 | 0 | 0 | 0 | NV | Region 2 - North East | Feather Falls | Butte | 39.5439 | -121.4323
35217268 | FRRB - BUCKS CREEK 1101 CB PH 1 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0.056818 | 0.056818 | 0 | 0.11364 | 0 | 0 | 0 | 0.11364 | 0 | NV | Region 2 - North East | Belden | Plumas | 0 | 0 | BUCKS CREEK 1101CB | BUCKS CREEK 1101CB | 1365 | 11 | Top 50 Miles | Tier 2 & 3
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Fire Rebuild | 08W | ESTS | Estimating | 2.2299 | 0 | 0 | 2.2299 | 0 | 0 | 0 | 2.2299 | 0 | PN | Region 3 - Bay Area | Pescadero | San Mateo | 37.2551 | -122.3815 | HALF MOON BAY 110369412 | HALF MOON BAY 110369412 | 1862 | 2055 | FRRB - UG - 2021 | Tier 2
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Fire Rebuild | 08W | ESTS | Estimating | 2.9 | 0 | 0 | 2.9 | 0 | 0 | 0 | 2.9 | 0 | PN | Region 3 - Bay Area | Pescadero | San Mateo | 37.2551 | -122.3815 | HALF MOON BAY 110369412 | HALF MOON BAY 110369412 | 1862 | 2055 | FRRB - UG - 2021 | Tier 2
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | Fire Rebuild | 08W | ESTS | Estimating | 0 | 0.95 | 0 | 0.95 | 0 | 0 | 0 | 0.95 | 0 | PN | Region 3 - Bay Area | Pescadero | San Mateo | 0 | 0 | HALF MOON BAY 11036012 | HALF MOON BAY 11036012 | 1585 | 2186 | FRRB - UG - 2021 | Tier 2
35223343 | FRRB - BIG BEND 1102 - LAKE MADRONE PH1 | Fire Rebuild | 08W | PEND | In-Construction* | 1.0176 | 0 | 0 | 1.0176 | 0 | 0.86458 | 0.15303 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6444 | -121.4314 | BIG BEND 11021972 | BIG BEND 11021972 | 64 | 1288 | FRRB - UG - 2021 | Tier 3
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Fire Rebuild | 08W | DOCC | Post-Construction | 1.5706 | 0 | 0 | 1.5706 | 0 | 1.5706 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6394 | -121.4295 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Fire Rebuild | 08W | CONS | In-Construction* | 3.7511 | 0 | 0 | 3.7511 | 0 | 3.6767 | 0.074432 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6348 | -121.3915 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - UG - 2021 | Tier 3
35224712 | FRRB - BUCKS CREEK 1101 CB PH 2 | Fire Rebuild | 08W | ESTS | Estimating | 1.73 | 0 | 0 | 1.73 | 0 | 0 | 0 | 1.7299 | 0 | NV | Region 2 - North East | Belden | Plumas | 0 | 0 | BUCKS CREEK 1101CB | BUCKS CREEK 1101CB | 1365 | 11 | Top 50 Miles | Tier 2 & 3
35224713 | FRRB - BUCKS CREEK 1101 CB PH 3 | Fire Rebuild | 08W | ESTS | Estimating | 1.83 | 0 | 0 | 1.83 | 0 | 0 | 0 | 1.8299 | 0 | NV | Region 2 - North East | Belden | Plumas | 0 | 0 | BUCKS CREEK 1101CB | BUCKS CREEK 1101CB | 1365 | 11 | Top 50 Miles | Tier 2 & 3
35225821 | FRRB - BIG BEND 1102 - LAKE MADRONE PH2 | Fire Rebuild | 08W | CONS | In-Construction* | 1.1858 | 0 | 0 | 1.1858 | 0 | 0 | 1.1858 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6444 | -121.4314 | BIG BEND 11021972 | BIG BEND 11021972 | 64 | 1288 | FRRB - UG - 2021 | Tier 3
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Fire Rebuild | 08W | MAPP | Post-Construction | 0.75152 | 0 | 0 | 0.75152 | 0 | 0.75152 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6394 | -121.4295 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Fire Rebuild | 08W | CONS | In-Construction* | 1.5968 | 0 | 0 | 1.5968 | 0 | 1.279 | 0.3178 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6348 | -121.3915 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - UG - 2021 | Tier 3
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | Fire Rebuild | 08W | CONS | In-Construction* | 2.5201 | 0 | 0 | 2.5201 | 0 | 2.2879 | 0.2322 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5047 | -121.4524 | WYANDOTTE 11031508 | WYANDOTTE 11031508 | 893 | 1176 | FRRB - UG - 2021 | Tier 2
35229043 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 1 | Fire Rebuild | 08W | UNSE | In-Construction* | 0.36648 | 0 | 0 | 0.36648 | 0 | 0.36648 | 0 | 0 | 0 | NV | Region 2 - North East | Feather Falls | Butte | 39.5752 | -121.3053 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35232298 | FRRB - WYANDOTTE 1103 - W1 PH 1.1 | Fire Rebuild | 08W | CONS | In-Construction* | 0.26155 | 0 | 0 | 0.26155 | 0 | 0.26155 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6425 | -121.4237 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35232718 | FRRB - WYANDOTTE 1103 - W2 PH 2.1 | Fire Rebuild | 08W | CONS | In-Construction* | 0.41667 | 0 | 0 | 0.41667 | 0 | 0.41667 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Fire Rebuild | 08W | DOCC | Post-Construction | 0.46875 | 0 | 0 | 0.46875 | 0 | 0.46875 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6425 | -121.4237 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | Fire Rebuild | 08W | UNSC | Ready for Construction | 0.46326 | 0 | 0 | 0.46326 | 0 | 0 | 0 | 0.46326 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6425 | -121.4237 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35233166 | FRRB - BIG BEND 1102 - B5 PH5.2 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 1.0491 | 0 | 0 | 1.0491 | 0 | 0 | 0 | 1.0491 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6444 | -121.4314 | BIG BEND 11021972 | BIG BEND 11021972 | 64 | 1288 | FRRB - UG - 2021 | Tier 3
35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | Fire Rebuild | 08W | UNSC | Ready for Construction | 0.37879 | 0 | 0 | 0.37879 | 0 | 0 | 0 | 0.37879 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6425 | -121.4237 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | Fire Rebuild | 08W | DOCC | Post-Construction | 0.12917 | 0 | 0 | 0.12917 | 0 | 0.12917 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6425 | -121.4237 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35233302 | FRRB - WYANDOTTE 1103 - W1 PH 1.6 | Fire Rebuild | 08W | UNSC | Ready for Construction | 0.15114 | 0 | 0 | 0.15114 | 0 | 0 | 0 | 0.15114 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6425 | -121.4237 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | Fire Rebuild | 08W | DOCC | Post-Construction | 0.065909 | 0 | 0 | 0.065909 | 0 | 0.065909 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6425 | -121.4237 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35233304 | FRRB - WYANDOTTE 1103 - W1 PH 1.8 | Fire Rebuild | 08W | CONS | In-Construction* | 0.35644 | 0 | 0 | 0.35644 | 0 | 0.35644 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6425 | -121.4237 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | Fire Rebuild | 08W | CONS | In-Construction* | 0.55114 | 0 | 0 | 0.55114 | 0 | 0.55114 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6425 | -121.4237 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35233306 | FRRB - WYANDOTTE 1103 - W1 PH1.10 | Fire Rebuild | 08W | DOCC | Post-Construction | 0.35398 | 0 | 0 | 0.35398 | 0 | 0.35398 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.63 | -121.421 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35233307 | FRRB - WYANDOTTE 1103 - W1 PH1.11 | Fire Rebuild | 08W | DOCC | Post-Construction | 0.33769 | 0 | 0 | 0.33769 | 0 | 0.33769 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6305 | -121.4215 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35233308 | FRRB - WYANDOTTE 1103 - W1 PH1.12 | Fire Rebuild | 08W | DOCC | Post-Construction | 1.047 | 0 | 0 | 1.047 | 0 | 1.047 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6333 | -121.4164 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35233309 | FRRB - WYANDOTTE 1103 - W1 PH1.13 | Fire Rebuild | 08W | CONS | In-Construction* | 0.38295 | 0 | 0 | 0.38295 | 0 | 0.38295 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6321 | -121.4205 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0.30246 | 0 | 0 | 0.30246 | 0 | 0 | 0 | 0.30246 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6338 | -121.4138 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35233311 | FRRB - WYANDOTTE 1103 - W2 PH 2.2 | Fire Rebuild | 08W | CONS | In-Construction* | 0.64205 | 0 | 0 | 0.64205 | 0 | 0.62178 | 0.020265 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 36.6329 | -121.3979 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35233312 | FRRB - WYANDOTTE 1103 - W2 PH 2.3 | Fire Rebuild | 08W | CONS | In-Construction* | 0.82576 | 0 | 0 | 0.82576 | 0 | 0 | 0.82576 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.633 | -121.388 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35233314 | FRRB - WYANDOTTE 1103 - W2 PH 2.4 | Fire Rebuild | 08W | CONS | In-Construction* | 2.4729 | 0 | 0 | 2.4729 | 0 | 0 | 2.4729 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6254 | -121.398 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35233315 | FRRB - WYANDOTTE 1103 - W2 PH 2.5 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0.80436 | 0 | 0 | 0.80436 | 0 | 0 | 0 | 0.80436 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6234 | -121.4009 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 | Fire Rebuild | 08W | CONS | In-Construction* | 1.7964 | 0 | 0 | 1.7964 | 0 | 0 | 1.7964 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6645 | -121.4316 | BIG BEND 11021972 | BIG BEND 11021972 | 64 | 1288 | FRRB - UG - 2021 | Tier 3
35235320 | FRRB - WYANDOTTE 1103 - W3 PH 3.1 | Fire Rebuild | 08W | UNSC | Ready for Construction | 0.24621 | 0 | 0 | 0.24621 | 0 | 0 | 0 | 0.24621 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6316 | -121.3793 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - UG - 2021 | Tier 3
35235669 | FRRB - WYANDOTTE 1103 - W4 PH 4.1 | Fire Rebuild | 08W | CONS | In-Construction* | 0.4197 | 0 | 0 | 0.4197 | 0 | 0 | 0.4197 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.646 | -121.4244 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - UG - 2021 | Tier 3
35235670 | FRRB - WYANDOTTE 1103 W5 PH5.1 FUTURE SM | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.11004 | 0 | 0 | 0.11004 | 0 | 0 | 0 | 0.11004 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.646 | -121.4244 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - UG - 2021 | Tier 3
35235671 | FRRB - WYANDOTTE 1103 - W4 PH 4.2 | Fire Rebuild | 08W | CONS | In-Construction* | 0.6161 | 0 | 0 | 0.6161 | 0 | 0.50417 | 0.11193 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.646 | -121.4244 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - UG - 2021 | Tier 3
35235672 | FRRB - WYANDOTTE 1103 W7 PH7.1 FUTURE SM | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.30303 | 0 | 0 | 0.30303 | 0 | 0 | 0 | 0.30303 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.5852 | -121.4309 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - UG - 2021 | Tier 3
35235673 | FRRB - WYANDOTTE 1103 - W3 PH3.10 | Fire Rebuild | 08W | CONS | In-Construction* | 0.66288 | 0 | 0 | 0.66288 | 0 | 0 | 0.66288 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.5852 | -121.4309 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - UG - 2021 | Tier 3
35235674 | FRRB - BIG BEND 1102 - B1 PH1.1 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.1108 | 0 | 0.1108 | 0 | 0 | 0 | 0.1108 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.655 | -121.459 | BIG BEND 1102CB | BIG BEND 1102CB | 900 | 865 | FRRB - UG - 2021 | Tier 3
35235675 | FRRB - WYANDOTTE 1103 W7 PH7.3 FUTURE SM | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.11364 | 0 | 0 | 0.11364 | 0 | 0 | 0 | 0.11364 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.655 | -121.459 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - UG - 2021 | Tier 3
35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 | Fire Rebuild | 08W | UNSC | Ready for Construction | 2.8788 | 0 | 0 | 2.8788 | 0 | 0 | 2.8788 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.655 | -121.459 | BIG BEND 11021972 | BIG BEND 11021972 | 64 | 1288 | FRRB - UG - 2021 | Tier 3
35235677 | FRRB - BIG BEND 1102 - B4 PH4.1 | Fire Rebuild | 08W | CONS | In-Construction* | 5.7636 | 0 | 0 | 5.7636 | 0 | 0 | 5.7636 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.655 | -121.459 | BIG BEND 11021972 | BIG BEND 11021972 | 64 | 1288 | FRRB - UG - 2021 | Tier 3
35235678 | FRRB - BIG BEND 1102 - B5 PH5.1 (M/L-S) | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.41667 | 0 | 0 | 0.41667 | 0 | 0 | 0.41667 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.655 | -121.459 | BIG BEND 11021972 | BIG BEND 11021972 | 64 | 1288 | FRRB - UG - 2021 | Tier 3
35235679 | FRRB - BIG BEND 1102 - B6 PH6.1 (M/L-N) | Fire Rebuild | 08W | ESTS | Estimating | 0.66004 | 0 | 0 | 0.66004 | 0 | 0 | 0.66004 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.655 | -121.459 | BIG BEND 11021972 | BIG BEND 11021972 | 64 | 1288 | FRRB - UG - 2021 | Tier 3
35235700 | FRRB - WYANDOTTE 1103 - W4 PH4.11 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 1.4083 | 0 | 0 | 1.4083 | 0 | 0 | 0 | 1.4083 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5757 | -121.3049 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - UG - 2021 | Tier 3
35235701 | FRRB - KANAKA 1101 - K2 PH2.1 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.10909 | 0 | 0.10909 | 0 | 0 | 0 | 0.10909 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5762 | -121.3051 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - UG - 2021 | Tier 3
35235702 | FRRB - KANAKA 1101 - K3 PH 3 | Fire Rebuild | 08W | CONS | In-Construction* | 1.9597 | 0 | 0 | 1.9597 | 0 | 0 | 0 | 1.9597 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5762 | -121.3051 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - UG - 2021 | Tier 3
35235704 | FRRB - KANAKA 1101 - K5 PH5.1 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.18902 | 0 | 0.18902 | 0 | 0 | 0 | 0.18902 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5762 | -121.3051 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - UG - 2021 | Tier 3
35235705 | FRRB - WYANDOTTE 1103 - W2 PH 2.6 | Fire Rebuild | 08W | CONS | In-Construction* | 1.739 | 0 | 0 | 1.739 | 0 | 0 | 1.739 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.646 | -121.4244 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35235706 | FRRB - WYANDOTTE 1103 - W2 PH 2.7 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0.7392 | 0 | 0 | 0.7392 | 0 | 0 | 0 | 0.7392 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.646 | -121.4244 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35235707 | FRRB - WYANDOTTE 1103 - W2 PH 2.8 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 1.0284 | 0 | 0 | 1.0284 | 0 | 0 | 0 | 1.0284 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.646 | -121.4244 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - REMG - 2021 | Tier 3
35236982 | FRRB - KANAKA 1101 - K6 PH6 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0 | 0 | 1.95 | 1.95 | 0 | 0 | 0 | 1.95 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5762 | -121.3051 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - REMG - 2021 | Tier 3
35236983 | FRRB - BIG BEND 1102 - B5 PH5.3 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0.34072 | 0 | 0 | 0.34072 | 0 | 0 | 0 | 0.34072 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.6772 | -121.4917 | BIG BEND 11021972 | BIG BEND 11021972 | 64 | 1288 | FRRB - REMG - 2021 | Tier 3
35236984 | FRRB - WYANDOTTE 1103 - W5 PH 5.5 | Fire Rebuild | 08W | UNSC | Ready for Construction | 1.9701 | 0 | 0 | 1.9701 | 0 | 0 | 0 | 1.9701 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6425 | -121.4237 | WYANDOTTE 11031508 | WYANDOTTE 11031508 | 893 | 1176 | FRRB - REMG - 2021 | Tier 3
35236985 | FRRB - KANAKA 1101 - K1 PH 1.1 | Fire Rebuild | 08W | UNSC | Ready for Construction | 1.5998 | 0 | 0 | 1.5998 | 0 | 0 | 1.5998 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5762 | -121.3051 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - REMG - 2021 | Tier 3
35236986 | FRRB - KANAKA 1101 - K5 PH5.4 | Fire Rebuild | 08W | CONS | In-Construction* | 0 | 1.9945 | 0 | 1.9945 | 0 | 0 | 1.9945 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5762 | -121.3051 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - REMG - 2021 | Tier 3
35236989 | FRRB - KANAKA 1101 - K2 PH2.2 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.51326 | 0 | 0.51326 | 0 | 0 | 0 | 0.51326 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5762 | -121.3051 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - OH - 2021 | Tier 3
35236990 | FRRB - WYANDOTTE 1103 - W3 PH 3.9 | Fire Rebuild | 08W | CONS | In-Construction* | 0.85303 | 0 | 0 | 0.85303 | 0 | 0 | 0.85303 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.646 | -121.4244 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - REMG - 2021 | Tier 3
35236991 | FRRB - WYANDOTTE 1103 - W4 PH 4.8 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 1.2616 | 0 | 0 | 1.2616 | 0 | 0 | 0 | 1.2616 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.646 | -121.4244 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - UG - 2021 | Tier 3
35236992 | FRRB - KANAKA 1101 - K1 PH 1.2 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0.66553 | 0 | 0 | 0.66553 | 0 | 0 | 0.66553 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5795 | -121.2969 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - REMG - 2021 | Tier 3
35236993 | FRRB - WYANDOTTE 1103 - W4 PH 4.9 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0.48011 | 0 | 0 | 0.48011 | 0 | 0 | 0 | 0.48011 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.646 | -121.4244 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - REMG - 2021 | Tier 3
35236995 | FRRB - WYANDOTTE 1103 - W4 PH4.10 | Fire Rebuild | 08W | CONS | In-Construction* | 2.2847 | 0 | 0 | 2.2847 | 0 | 0 | 2.2847 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.646 | -121.4244 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - REMG - 2021 | Tier 3
35236997 | FRRB - WYANDOTTE 1103 W7 PH7.2 FUTURE SM | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.28409 | 0 | 0 | 0.28409 | 0 | 0 | 0 | 0.28409 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6827 | -121.3105 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - REMG - 2021 | Tier 3
35236999 | FRRB - KANAKA 1101 - K5 PH5.2 | Fire Rebuild | 08W | CONS | In-Construction* | 0 | 0.175 | 0 | 0.175 | 0 | 0.175 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5707 | -121.3264 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - UG - 2021 | Tier 3
35237020 | FRRB - KANAKA 1101 - K5 PH5.3 | Fire Rebuild | 08W | CONS | In-Construction* | 0 | 0.50795 | 0 | 0.50795 | 0 | 0 | 0.50795 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5603 | -121.3467 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - REMG - 2021 | Tier 3
35237021 | FRRB - WYANDOTTE 1103 W7 PH7.4 FUTURE SM | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.24621 | 0 | 0 | 0.24621 | 0 | 0 | 0 | 0.24621 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5762 | -121.3051 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - UG - 2021 | Tier 3
35237889 | FRRB - WYANDOTTE 1103 - W3 PH 3.2 | Fire Rebuild | 08W | CONS | In-Construction* | 2.0742 | 0 | 0 | 2.0742 | 0 | 0 | 2.0742 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - UG - 2021 | Tier 3
35237890 | FRRB - WYANDOTTE 1103 - W3 PH 3.3 | Fire Rebuild | 08W | CONS | In-Construction* | 1.2223 | 0 | 0 | 1.2223 | 0 | 0 | 1.2223 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - UG - 2021 | Tier 3
35237891 | FRRB - WYANDOTTE 1103 - W3 PH 3.4 | Fire Rebuild | 08W | UNSC | Ready for Construction | 0.47197 | 0 | 0 | 0.47197 | 0 | 0 | 0 | 0.47197 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - UG - 2021 | Tier 3
35237893 | FRRB - WYANDOTTE 1103 - W3 PH 3.5 | Fire Rebuild | 08W | CONS | In-Construction* | 0.79659 | 0 | 0 | 0.79659 | 0 | 0 | 0.79659 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - UG - 2021 | Tier 3
35237894 | FRRB - WYANDOTTE 1103 - W3 PH 3.6 | Fire Rebuild | 08W | CONS | In-Construction* | 0.85985 | 0 | 0 | 0.85985 | 0 | 0 | 0.85985 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - UG - 2021 | Tier 3
35237896 | FRRB - WYANDOTTE 1103 - W3 PH 3.8 | Fire Rebuild | 08W | CONS | In-Construction* | 1.1121 | 0 | 0 | 1.1121 | 0 | 0 | 1.1121 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - UG - 2021 | Tier 3
35238587 | #CZUDOLAN 55459 HWY 1 BIG SUR | Fire Rebuild | 95F | CONS | In-Construction* | 0 | 0.36761 | 0 | 0.36761 | 0 | 0.36761 | 0 | 0 | 0 | CC | Region 4 - Central Coast | Big Sur | Monterey | 36.1159 | -121.6259
35239095 | FRRB - WYANDOTTE 1103 - W4 PH 4.3 | Fire Rebuild | 08W | CONS | In-Construction* | 1.6479 | 0 | 0 | 1.6479 | 0 | 0 | 1.6479 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6348 | -121.3915 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - UG - 2021 | Tier 3
35239096 | FRRB - WYANDOTTE 1103 - W4 PH 4.4 | Fire Rebuild | 08W | CONS | In-Construction* | 0.95833 | 0 | 0 | 0.95833 | 0 | 0 | 0.95833 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6348 | -121.3915 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - UG - 2021 | Tier 3
35239097 | FRRB - WYANDOTTE 1103 - W4 PH 4.5 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 1.1566 | 0 | 0 | 1.1566 | 0 | 0 | 0 | 1.1566 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6348 | -121.3915 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - UG - 2021 | Tier 3
35239098 | FRRB - WYANDOTTE 1103 - W4 PH 4.6 | Fire Rebuild | 08W | UNSC | Ready for Construction | 2.3248 | 0 | 0 | 2.3248 | 0 | 0 | 2.3248 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6348 | -121.3915 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - UG - 2021 | Tier 3
35239099 | FRRB - WYANDOTTE 1103 - W4 PH 4.7 | Fire Rebuild | 08W | UNSC | Ready for Construction | 0.4464 | 0 | 0 | 0.4464 | 0 | 0 | 0.4464 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6348 | -121.3915 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - UG - 2021 | Tier 3
35239522 | FRRB - WYANDOTTE 1103 - W2 PH 2.9 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0.34848 | 0 | 0 | 0.34848 | 0 | 0 | 0 | 0.34848 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35239523 | FRRB - WYANDOTTE 1103 - W2 PH2.10 | Fire Rebuild | 08W | CONS | In-Construction* | 0.24621 | 0 | 0 | 0.24621 | 0 | 0.21439 | 0.031818 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35239937 | FRRB - WYANDOTTE 1103 - W2 PH2.11 | Fire Rebuild | 08W | DOCC | Post-Construction | 0.46193 | 0 | 0 | 0.46193 | 0 | 0.46193 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35240542 | FRRB - KANAKA 1101 - K4 PH 4.19 | Fire Rebuild | 08W | CONS | In-Construction* | 0 | 0.90038 | 0 | 0.90038 | 0 | 0.82727 | 0.073106 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5707 | -121.3264 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - OH - 2021 | Tier 3
35240543 | FRRB - KANAKA 1101 - K4 PH 4.18 | Fire Rebuild | 08W | CONS | In-Construction* | 0 | 1.2068 | 0 | 1.2068 | 0 | 0 | 1.2068 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5707 | -121.3264 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - OH - 2021 | Tier 3
35240545 | FRRB - WYANDOTTE 1103 - W2 PH2.12 | Fire Rebuild | 08W | CONS | In-Construction* | 0.13125 | 0 | 0 | 0.13125 | 0 | 0.13125 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35240546 | FRRB - WYANDOTTE 1103 - W2 PH2.13 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0.13087 | 0 | 0 | 0.13087 | 0 | 0 | 0 | 0.13087 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35241075 | FRRB - WYANDOTTE 1103 W5 PH5.2 FUTURE SM | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.070076 | 0 | 0 | 0.070076 | 0 | 0 | 0 | 0.070076 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6348 | -121.3915 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - UG - 2021 | Tier 3
35241076 | FRRB - WYANDOTTE 1103 W5 PH5.3 FUTURE SM | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.11004 | 0 | 0 | 0.11004 | 0 | 0 | 0 | 0.11004 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6348 | -121.3915 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - UG - 2021 | Tier 3
35241077 | FRRB - WYANDOTTE 1103 W5 PH5.4 FUTURE SM | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.31004 | 0 | 0 | 0.31004 | 0 | 0 | 0 | 0.31004 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6348 | -121.3915 | WYANDOTTE 11031976 | WYANDOTTE 11031976 | 47 | 1299 | FRRB - UG - 2021 | Tier 3
35241078 | FRRB - BIG BEND 1102 - B1 PH1.2 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.18258 | 0 | 0.18258 | 0 | 0 | 0 | 0.18258 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.655 | -121.459 | BIG BEND 1102CB | BIG BEND 1102CB | 900 | 865 | FRRB - UG - 2021 | Tier 3
35241079 | FRRB - BIG BEND 1102 - B1 PH1.3 | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.074621 | 0 | 0.074621 | 0 | 0.074621 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.655 | -121.459 | BIG BEND 1102CB | BIG BEND 1102CB | 900 | 865 | FRRB - UG - 2021 | Tier 3
35242420 | FRRB - BIG BEND 1102 - B1 PH1.4 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.094697 | 0 | 0.094697 | 0 | 0 | 0 | 0.094697 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.655 | -121.459 | BIG BEND 1102CB | BIG BEND 1102CB | 900 | 865 | FRRB - UG - 2021 | Tier 3
35242421 | FRRB - BIG BEND 1102 - B6 PH6.2 (M/L-M) | Fire Rebuild | 08W | ESTS | Estimating | 0.75 | 0 | 0 | 0.75 | 0 | 0 | 0.75 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6444 | -121.4314 | BIG BEND 11021972 | BIG BEND 11021972 | 64 | 1288 | FRRB - UG - 2021 | Tier 3
35242422 | FRRB - BIG BEND 1102 - B6 PH6.3 (T/L-1) | Fire Rebuild | 08W | UNSC | Ready for Construction | 0.93883 | 0 | 0 | 0.93883 | 0 | 0 | 0.93883 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6444 | -121.4314 | BIG BEND 11021972 | BIG BEND 11021972 | 64 | 1288 | FRRB - UG - 2021 | Tier 3
35242423 | FRRB - BIG BEND 1102 - B6 PH6.4 (T/L-2) | Fire Rebuild | 08W | PEND | Permitting/Dependency | 1.0799 | 0 | 0 | 1.0799 | 0 | 0 | 1.0799 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6444 | -121.4314 | BIG BEND 11021972 | BIG BEND 11021972 | 64 | 1288 | FRRB - UG - 2021 | Tier 3
35242424 | FRRB - BIG BEND 1102 - B6 PH6.5 (T/L-3) | Fire Rebuild | 08W | CONS | In-Construction* | 0.42008 | 0 | 0 | 0.42008 | 0 | 0 | 0.42008 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6444 | -121.4314 | BIG BEND 11021972 | BIG BEND 11021972 | 64 | 1288 | FRRB - UG - 2021 | Tier 3
35242425 | FRRB - BIG BEND 1102 - B6 PH6.6 (T/L-4) | Fire Rebuild | 08W | PEND | Permitting/Dependency | 1.14 | 0 | 0 | 1.14 | 0 | 0 | 1.14 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6444 | -121.4314 | BIG BEND 11021972 | BIG BEND 11021972 | 64 | 1288 | FRRB - UG - 2021 | Tier 3
35242426 | FRRB - BIG BEND 1102 - B6 PH6.7 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0.63352 | 0 | 0 | 0.63352 | 0 | 0 | 0 | 0.63352 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6444 | -121.4314 | BIG BEND 11021972 | BIG BEND 11021972 | 64 | 1288 | FRRB - UG - 2021 | Tier 3
35242427 | FRRB - BIG BEND 1102 - B6 PH6.8 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0.87784 | 0 | 0 | 0.87784 | 0 | 0 | 0 | 0.87784 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6444 | -121.4314 | BIG BEND 11021972 | BIG BEND 11021972 | 64 | 1288 | FRRB - UG - 2021 | Tier 3
35242428 | FRRB - BIG BEND 1102 - B4 PH4.2 | Fire Rebuild | 08W | UNSC | Ready for Construction | 0.73598 | 0 | 0 | 0.73598 | 0 | 0 | 0.73598 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6444 | -121.4314 | BIG BEND 11021972 | BIG BEND 11021972 | 64 | 1288 | FRRB - UG - 2021 | Tier 3
35242429 | FRRB - BIG BEND 1102 - B4 PH4.3 | Fire Rebuild | 08W | UNSC | Ready for Construction | 0.59792 | 0 | 0 | 0.59792 | 0 | 0 | 0.59792 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6444 | -121.4314 | BIG BEND 11021972 | BIG BEND 11021972 | 64 | 1288 | FRRB - UG - 2021 | Tier 3
35244330 | FRRB - WYANDOTTE 11031974 - W1 SM1 | Fire Rebuild | 08W | DOCC | Post-Construction | 0.057386 | 0 | 0 | 0.057386 | 0 | 0.057386 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.646 | -121.4244 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35244696 | FRRB - KANAKA 1101 - K4 PH 4.1 | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.29678 | 0 | 0.29678 | 0 | 0.29678 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - OH - 2021 | Tier 3
35244697 | FRRB - KANAKA 1101 - K4 PH 4.2 | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 0.12405 | 0 | 0.12405 | 0 | 0 | 0 | 0.12405 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - OH - 2021 | Tier 3
35244698 | FRRB - KANAKA 1101 - K4 PH 4.3 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.090341 | 0 | 0.090341 | 0 | 0 | 0 | 0.090341 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - OH - 2021 | Tier 3
35244699 | FRRB - KANAKA 1101 - K4 PH 4.4 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.080114 | 0 | 0.080114 | 0 | 0 | 0 | 0.080114 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - OH - 2021 | Tier 3
35245140 | FRRB - KANAKA 1101 - K4 PH 4.5 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.27178 | 0 | 0.27178 | 0 | 0 | 0 | 0.27178 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - OH - 2021 | Tier 3
35245141 | FRRB - KANAKA 1101 - K4 PH 4.6 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.054545 | 0 | 0.054545 | 0 | 0 | 0 | 0.054545 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - OH - 2021 | Tier 3
35245142 | FRRB - KANAKA 1101 - K4 PH 4.7 | Fire Rebuild | 08W | MAPP | Post-Construction | 0 | 0.056818 | 0 | 0.056818 | 0 | 0.056818 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - OH - 2021 | Tier 3
35245143 | FRRB - KANAKA 1101 - K4 PH 4.8 | Fire Rebuild | 08W | MAPP | Post-Construction | 0 | 0.2589 | 0 | 0.2589 | 0 | 0.2589 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - OH - 2021 | Tier 3
35245144 | FRRB - KANAKA 1101 - K4 PH 4.9 | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.24886 | 0 | 0.24886 | 0 | 0.24886 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - OH - 2021 | Tier 3
35245145 | FRRB - KANAKA 1101 - K4 PH 4.10 | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.095455 | 0 | 0.095455 | 0 | 0.09545 | 4.5455e-06 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - OH - 2021 | Tier 3
35245146 | FRRB - KANAKA 1101 - K4 PH 4.11 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.13731 | 0 | 0.13731 | 0 | 0 | 0 | 0.13731 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - OH - 2021 | Tier 3
35245147 | FRRB - KANAKA 1101 - K4 PH 4.12 | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.39242 | 0 | 0.39242 | 0 | 0.39242 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - OH - 2021 | Tier 3
35245148 | FRRB - KANAKA 1101 - K4 PH 4.13 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.20492 | 0 | 0.20492 | 0 | 0 | 0 | 0.20492 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - OH - 2021 | Tier 3
35245149 | FRRB - KANAKA 1101 - K4 PH 4.14 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.26894 | 0 | 0.26894 | 0 | 0 | 0 | 0.26894 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - OH - 2021 | Tier 3
35245150 | FRRB - KANAKA 1101 - K4 PH 4.15 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.12557 | 0 | 0.12557 | 0 | 0 | 0 | 0.12557 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - OH - 2021 | Tier 3
35245151 | FRRB - KANAKA 1101 - K4 PH 4.16 | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.15455 | 0 | 0.15455 | 0 | 0.15455 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - OH - 2021 | Tier 3
35245152 | FRRB - KANAKA 1101 - K4 PH 4.17 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.48295 | 0 | 0.48295 | 0 | 0 | 0 | 0.48295 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5137 | -121.346 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - OH - 2021 | Tier 3
35248770 | FRRB - WYANDOTTE 11031974 - W1 SM2 | Fire Rebuild | 08W | DOCC | Post-Construction | 0.10814 | 0 | 0 | 0.10814 | 0 | 0.10814 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.646 | -121.4244 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35249161 | FRRB - WYANDOTTE 11031974 - W3 SM3 | Fire Rebuild | 08W | CONS | In-Construction* | 0.19508 | 0 | 0 | 0.19508 | 0 | 0.19508 | 0 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6397 | -121.3741 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35250343 | FRRB - KANAKA 1101CB - K2 SM1 | Fire Rebuild | 08W | UNSC | In-Construction* | 0.30019 | 0 | 0 | 0.30019 | 0 | 0.29432 | 0.0058712 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5737 | -121.3129 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - UG - 2021 | Tier 3
35253173 | FRRB - KANAKA 1101CB - K4 SM1 | Fire Rebuild | 08W | CONS | In-Construction* | 0 | 0.059848 | 0 | 0.059848 | 0 | 0.059848 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5466 | -121.3552 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - OH - 2021 | Tier 3
35253174 | FRRB - KANAKA 1101CB - K4 SM2 | Fire Rebuild | 08W | CONS | In-Construction* | 0 | 0.28826 | 0 | 0.28826 | 0 | 0.28826 | 0 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5462 | -121.3509 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - OH - 2021 | Tier 3
35254695 | FRRB - KANAKA 1101CB - K2 SM2 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0.067045 | 0 | 0 | 0.067045 | 0 | 0 | 0.067045 | 0 | 0 | NV | Region 2 - North East | Feather Falls | Butte | 39.5752 | -121.3053 | KANAKA 1101CB | KANAKA 1101CB | 1113 | 1480 | FRRB - UG - 2021 | Tier 3
35264250 | FRRB - ANTLER 1101 1612 | Fire Rebuild | 08W | ESTS | In-Construction* | 0 | 0.22727 | 0 | 0.22727 | 0 | 0.22727 | 0 | 0 | 0 | NV | Region 2 - North East | Lakehead | Shasta | 40.8915 | -122.3764 | ANTLER 11011612 | ANTLER 11011612 | 2352 | 1791 | FRRB - UG - 2021 | Tier 2 & 3
35270705 | FRRB - ANTLER 11011612 TL2 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0.56818 | 0.094697 | 0 | 0.66288 | 0 | 0 | 0.66288 | 0 | 0 | NV | Region 2 - North East | Lakehead | Shasta | 40.8743 | -122.3575 | ANTLER 11011612 | ANTLER 11011612 | 2352 | 1791 | FRRB - UG - 2021 | Tier 2 & 3
35270706 | FRRB - ANTLER 11011612 TL5 | Fire Rebuild | 08W | PEND | In-Construction* | 0.87102 | 0.10417 | 0 | 0.97519 | 0 | 0.10417 | 0.87102 | 0 | 0 | NV | Region 2 - North East | Lakehead | Shasta | 40.872 | -122.3592 | ANTLER 11011612 | ANTLER 11011612 | 2352 | 1791 | FRRB - UG - 2021 | Tier 2 & 3
35270755 | FRRB - ANTLER 11011612 TL1 | Fire Rebuild | 08W | UNSC | Ready for Construction | 0.43561 | 0 | 0 | 0.43561 | 0 | 0 | 0.43561 | 0 | 0 | NV | Region 2 - North East | Lakehead | Shasta | 40.8776 | -122.3623 | ANTLER 11011612 | ANTLER 11011612 | 2352 | 1791 | FRRB - UG - 2021 | Tier 2 & 3
35279181 | FRRB - BUCKS CREEK 1102CB PH1 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 5.589 | 0 | 0 | 5.589 | 0 | 0 | 0 | 5.589 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | BUCKS CREEK 1102CB | BUCKS CREEK 1102CB | 1739 | 378 | FRRB - UG - 2021 | Tier 2 & 3
35279182 | FRRB - BUCKS CREEK 1102CB PH2 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 2.0701 | 0 | 0 | 2.0701 | 0 | 0 | 0 | 2.0701 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | BUCKS CREEK 1102CB | BUCKS CREEK 1102CB | 1739 | 378 | FRRB - UG - 2021 | Tier 2 & 3
35279243 | FRRB - WYANDOTTE 11031974 - W3 SM4 | Fire Rebuild | 08W | UNSC | Ready for Construction | 0.25511 | 0 | 0 | 0.25511 | 0 | 0 | 0.25511 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6287 | -121.3656 | WYANDOTTE 11031974 | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35279307 | FRRB - GANSNER 11012424 UG PH1.2 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 2.25 | 0 | 0 | 2.25 | 0 | 0 | 0 | 2.25 | 0 | NV | Region 2 - North East | Quincy | Plumas | 40.0075 | -120.9605 |  | GANSNER 11012424 | 1231 | 1172 | FRRB | Tier 2 & 3
35279313 | FRRB - GANSNER 11012424 UG PH1.1 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.46 | 0 | 0 | 0.46 | 0 | 0 | 0 | 0.46 | 0 | NV | Region 2 - North East | Quincy | Plumas | 40.0075 | -120.9605 | GANSNER 11012424 | GANSNER 11012424 | 1231 | 1172 | FRRB | Tier 2 & 3
35279509 | FRRB - SG 1101 TL OH 02 05 12 | Fire Rebuild | 08W | MAPP | Post-Construction | 0 | 1.1801 | 0 | 1.1801 | 0 | 1.1801 | 0 | 0 | 0 | SI | Region 2 - North East | Colfax | Placer | 39.1057 | -120.9742 | SHADY GLEN 11012768 | SHADY GLEN 11012768 | 445 | 1885 | FRRB | Tier 2
35279510 | FRRB - SG 1102 TL UG 04 | Fire Rebuild | 08W | ESTS | Estimating | 1.1682 | 0 | 0 | 1.1682 | 0 | 0 | 0.091856 | 1.0763 | 0 | SI | Region 2 - North East | Colfax | Placer | 39.1057 | -120.9742 | SHADY GLEN 11012768 | SHADY GLEN 11012768 | 445 | 1885 | FRRB | Tier 2 & 3
35279512 | FRRB - BRUNSWICK 1106 UG - 02 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0.13542 | 0 | 0 | 0.13542 | 0 | 0 | 0 | 0.13542 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1174 | -120.9918 | BRUNSWICK 11062790 | BRUNSWICK 11062790 | 1201 | 715 | FRRB | Tier 3
35279604 | FRRB - BRUNSWICK 1106 OH | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 1.5146 | 0 | 1.5146 | 0 | 1.3017 | 0.10076 | 0.11212 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1461 | -120.9737 | BRUNSWICK 11062790 | BRUNSWICK 11062790 | 1201 | 715 | FRRB | Tier 3
35279605 | FRRB - BRUNSWICK 1106-TL-OH-06 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.72879 | 0 | 0.72879 | 0 | 0 | 0.72879 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1461 | -120.9737 | BRUNSWICK 11062790 | BRUNSWICK 11062790 | 1201 | 715 | FRRB | Tier 3
35279987 | FRRB - CHESTER 1102 2564 | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 1.4676 | 0.087121 | 1.5547 | 0 | 1.5547 | 0 | 0 | 0 | NV | Region 2 - North East | Chester | Plumas | 40.2927 | -121.2429 | CHESTER 11022564 | CHESTER 11022564 | 1482 | 2726 | FRRB | Tier 2
35280493 | FRRB -BIG MEADOWS 21012260 OH TL 1.13 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0 | 0.35 | 0 | 0.35 | 0 | 0 | 0 | 0.35 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | BIG MEADOWS 21012248 | BIG MEADOWS 21012248 | 1922 | 916 | FRRB | Tier 2
35280495 | FRRB - BIG MEADOW 21012260 OH TL PH1.1 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0 | 0.51004 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | BIG MEADOWS 21012248 | BIG MEADOWS 21012248 | 1922 | 916 | FRRB | Tier 2
35280496 | FRRB - CRESCENT MILLS 21012056 UG ML 1.2 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.82008 | 0 | 0 | 0.82008 | 0 | 0 | 0 | 0.82008 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | CRESCENT MILLS 21012056 | 551 | 895 | FRRB | Tier 2
35280498 | FRRB - CRESCENT MILLS 21012056 OH TL 1.1 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0 | 0.073295 | 0 | 0.073295 | 0 | 0 | 0 | 0.073295 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | CRESCENT MILLS 21012056 | CRESCENT MILLS 21012056 | 551 | 895 | FRRB | Tier 2
35280499 | FRRB - BUCKS CREEK 1102 CB PH3 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.85 | 0 | 0 | 0.85 | 0 | 0 | 0 | 0.85 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 |  | BUCKS CREEK 1102CB | 1739 | 378 | FRRB - UG - 2021 | Tier 2 & 3
35280560 | FRRB - BUCKS CREEK 1102CB PH4 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 2.64 | 0 | 0 | 2.64 | 0 | 0 | 0 | 2.64 | 0 | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 |  | BUCKS CREEK 1102CB | 1739 | 378 | FRRB - UG - 2021 | Tier 2 & 3
35281758 | FRRB - GRAYS FLAT 0401904916 PH1.1 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 1.4 | 0 | 0 | 1.4 | 0 | 0 | 0 | 1.4 | 0 | NV | Region 2 - North East | Twain | Plumas | 40.0222 | -121.0643 | GRAYS FLAT 0401CB | GRAYS FLAT 0401CB | 1562 | 1748 | FRRB | Tier 2
35281813 | FRRB - WILLOW CREEK 11032936 (OH) | Fire Rebuild | 08W | ADER | Estimating | 0 | 0.046591 | 0 | 0.046591 | 0 | 0 | 0 | 0.046591 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WILLOW CREEK 11032936 | WILLOW CREEK 11032936 | 1299 | 1474 | FRRB | Tier 2
35281815 | FRRB - WILLOW CREEK 11032936 UG ML1 | Fire Rebuild | 08W | ESTS | Estimating | 7.4284 | 0 | 0 | 7.4284 | 0 | 0 | 0 | 7.4284 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WILLOW CREEK 11032936 | WILLOW CREEK 11032936 | 1299 | 1474 | FRRB | Tier 2
35281816 | FRRB - WILLOW CREEK 11032936 UG ML2 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.18939 | 0 | 0 | 0.18939 | 0 | 0 | 0 | 0.18939 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WILLOW CREEK 11032936 |  |  |  | FRRB | Tier 2
35282126 | FRRB - EL DORADO PH 2101 UG | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 9.2 | 0 | 0 | 9.2 | 0 | 0 | 0 | 9.2 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.6385 | -120.5319 | EL DORADO PH 210126000 | EL DORADO PH 210126000 | 63 | 2252 | FRRB | Tier 2 & 3
35282131 | FRRB - KANAKA 1101CB - K1 SM1 | Fire Rebuild | 08W | UNSC | Ready for Construction | 0.093371 | 0 | 0 | 0.093371 | 0 | 0 | 0.093371 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5804 | -121.2945 |  | KANAKA 1101CB | 1113 | 1480 | FRRB - UG - 2021 | Tier 3
35282166 | FRFRRB - SPANISH CREEK UG ML PH1.1 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 2.5902 | 0 | 0 | 2.5902 | 0 | 0 | 0 | 2.5902 | 0 | NV | Region 2 - North East | Crescent Mills | Plumas | 40.0604 | -120.9643 | SPANISH CREEK 4401CB | SPANISH CREEK 4401CB | 462 | 1322 | FRRB | Tier 2
35282281 | FRRB - EL DORADO PH 2101 OH | Fire Rebuild | 08W | ESTS | In-Construction* | 0 | 0.47235 | 0 | 0.47235 | 0 | 0.19981 | 0.27254 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.6311 | -120.5678 | EL DORADO PH 210126000 | EL DORADO PH 210126000 | 63 | 2252 | FRRB | Tier 2 & 3
35283874 | FRRB - WYANDOTTE 1103 - W2 PH2.14 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0.42576 | 0 | 0 | 0.42576 | 0 | 0 | 0.42576 | 0 | 0 | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 |  | WYANDOTTE 11031974 | 11 | 1849 | FRRB - UG - 2021 | Tier 3
35284023 | FRRB - DUNBAR 1101416 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 1.1699 | 0 | 0 | 1.1699 | 0 | 0 | 0 | 1.1699 | 0 | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4361 | -122.5779 |  | DUNBAR 1101416 | 975 | 1684 | FRRB - UG - 2021 | Tier 3
35284567 | FRRB - SG 1101 TL UG 08 09 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0.64773 | 0 | 0 | 0.64773 | 0 | 0 | 0 | 0.64773 | 0 | SI | Region 2 - North East | Colfax | Placer | 39.1039 | -120.976 | SHADY GLEN 11012768 | SHADY GLEN 11012768 |  | 1885 | FRRB | Tier 2
35284568 | FRRB - SG 1101 TL UG 10 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.59318 | 0 | 0 | 0.59318 | 0 | 0 | 0 | 0.59318 | 0 | SI | Region 2 - North East | Colfax | Placer | 39.0914 | -120.9837 | SHADY GLEN 110132726 | SHADY GLEN 11012768 |  | 1885 | FRRB | Tier 2
35284569 | FRRB - SG 1102 TL UG 03 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0.68409 | 0 | 0 | 0.68409 | 0 | 0 | 0 | 0.68409 | 0 | SI | Region 2 - North East | Colfax | Placer | 39.1166 | -120.967 | SHADY GLEN 110248894 | SHADY GLEN 11012768 |  | 1885 | FRRB | Tier 2
35284570 | FRRB - SG 1101 TL OH 01 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0.31193 | 0 | 0 | 0.31193 | 0 | 0 | 0.31193 | 0 | 0 | SI | Region 2 - North East | Colfax | Placer | 39.1172 | -120.9705 | SHADY GLEN 11012768 | SHADY GLEN 11012768 |  | 1885 | FRRB | Tier 2
35284716 | FRRB - EDPH2101 - OH - 13 | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.7589 | 0 | 0.7589 | 0 | 0.7589 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.6375 | -120.5393 | EL DORADO PH 210126000 | EL DORADO PH 210126000 | 63 | 2252 | FRRB | Tier 2 & 3
35284717 | FRRB - EDPH2101 - OH - 14 | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 0.89489 | 0 | 0.89489 | 0 | 0.89489 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.6325 | -120.5421 | EL DORADO PH 210126000 | EL DORADO PH 210126000 | 63 | 2252 | FRRB | Tier 2 & 3
35284827 | FRRB - APPLE HILL 2102 - OH - 1 | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 1.2553 | 0.087121 | 1.3424 | 0 | 1.3424 | 0 | 0 | 0 | SI | Region 2 - North East | Somerset | El Dorado | 38.643 | -120.526 | APPLE HILL 21029722 |  |  |  | FRRB | Tier 2 & 3
35284828 | FRRB - EDPH2101 - OH - 10 | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.65606 | 0 | 0.65606 | 0 | 0.65606 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.643 | -120.526 | EL DORADO PH 210126000 | EL DORADO PH 210126000 | 63 | 2252 | FRRB | Tier 2 & 3
35284829 | FRRB - EDPH2101 - OH - 11 | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 0.62311 | 0 | 0.62311 | 0 | 0.57405 | 0.049053 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.643 | -120.526 | EL DORADO PH 210126000 | EL DORADO PH 210126000 | 63 | 2252 | FRRB | Tier 2 & 3
35284830 | FRRB - EDPH2101 - OH - 12 | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 0.76515 | 0 | 0.76515 | 0 | 0.76515 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.643 | -120.526 |  | EL DORADO PH 210126000 | 63 | 2252 | FRRB | Tier 2 & 3
35284831 | FRRB - EDPH2101 - OH - 9 | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 0.96402 | 0 | 0.96402 | 0 | 0.95076 | 0.013258 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.643 | -120.526 | EL DORADO PH 210126000 | EL DORADO PH 210126000 | 63 | 2252 | FRRB | Tier 2 & 3
35284832 | FRRB - EDPH2101 - OH - 8 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.89299 | 0 | 0.89299 | 0 | 0 | 0.89299 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.643 | -120.526 | EL DORADO PH 210126000 | EL DORADO PH 210126000 | 63 | 2252 | FRRB | Tier 2 & 3
35284833 | FRRB - EDPH2101 - OH - 7 | Fire Rebuild | 08W | ADER | Estimating | 0 | 0.87822 | 0 | 0.87822 | 0 | 0 | 0.87822 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.643 | -120.526 | EL DORADO PH 210126000 | EL DORADO PH 210126000 | 63 | 2252 | FRRB | Tier 2 & 3
35284834 | FRRB - EDPH2101 - OH - 6 | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 0.70587 | 0 | 0.70587 | 0 | 0.70587 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.643 | -120.526 | EL DORADO PH 210126000 | EL DORADO PH 210126000 | 63 | 2252 | FRRB | Tier 2 & 3
35284835 | FRRB - EDPH2101 - OH - 5 | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 0.47955 | 0 | 0.47955 | 0 | 0.47955 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.643 | -120.526 | EL DORADO PH 210126000 | EL DORADO PH 210126000 | 63 | 2252 | FRRB | Tier 2 & 3
35284836 | FRRB - EDPH2101 - OH - 4 | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 0.88182 | 0 | 0.88182 | 0 | 0.88182 | 0 | 0 | 0 | SI | Region 2 - North East | Somerset | El Dorado | 38.643 | -120.526 | EL DORADO PH 210126000 | EL DORADO PH 210126000 | 63 | 2252 | FRRB | Tier 2 & 3
35284837 | FRRB - EDPH2101 - OH - 3 | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 1.7884 | 0 | 1.7884 | 0 | 1.7884 | 0 | 0 | 0 | SI | Region 2 - North East | Somerset | El Dorado | 38.6544 | -120.5324 | EL DORADO PH 210126000 | EL DORADO PH 210126000 | 63 | 2252 | FRRB | Tier 2 & 3
35284838 | FRRB - EDPH2101 - OH - 2 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.60568 | 0 | 0.60568 | 0 | 0 | 0.60568 | 0 | 0 | SI | Region 2 - North East | Somerset | El Dorado | 38.6544 | -120.5324 | EL DORADO PH 210126000 | EL DORADO PH 210126000 | 63 | 2252 | FRRB | Tier 2 & 3
35284839 | FRRB - EDPH2101 - OH - 1 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.47595 | 0 | 0.47595 | 0 | 0 | 0.47595 | 0 | 0 | SI | Region 2 - North East | Somerset | El Dorado | 38.6533 | -120.5363 | EL DORADO PH 210126000 | EL DORADO PH 210126000 | 63 | 2252 | FRRB | Tier 2 & 3
35285048 | FRRB - EDPH2101 - OH - 15 | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.41212 | 0 | 0.41212 | 0 | 0.41212 | 0 | 0 | 0 | SI | Region 2 - North East | Kyburz | El Dorado | 38.643 | -120.526 | EL DORADO PH 210136764 | EL DORADO PH 210126000 | 63 | 2252 | FRRB | Tier 2 & 3
35285049 | FRRB - EDPH2101 - OH - 16 | Fire Rebuild | 08W | DOCC | Post-Construction | 0 | 0.18542 | 0 | 0.18542 | 0 | 0.18542 | 0 | 0 | 0 | SI | Region 2 - North East | Kyburz | El Dorado | 38.643 | -120.526 | EL DORADO PH 210136764 | EL DORADO PH 210126000 | 63 | 2252 | FRRB | Tier 2 & 3
35285050 | FRRB - EDPH2101 - OH - 17 | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 1.593 | 0 | 1.593 | 0 | 0.95246 | 0.64053 | 0 | 0 | SI | Region 2 - North East | Twin Bridges | El Dorado | 38.643 | -120.526 | EL DORADO PH 210113532 | EL DORADO PH 210126000 | 63 | 2252 | FRRB | Tier 2 & 3
35285352 | FRRB - ECHO SUMMIT 1101 - OH - 12 | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 0.27689 | 0 | 0.27689 | 0 | 0.13845 | 0.13845 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado | 0 | 0 | ECHO SUMMIT 1101481660 |  |  |  | FRRB | Tier 2
35285353 | FRRB - ECHO SUMMIT 1101 - OH - 11 | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 0.31856 | 0 | 0.31856 | 0 | 0.31856 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado | 0 | 0 | ECHO SUMMIT 1101481660 |  |  |  | FRRB | Tier 2
35285585 | FRRB - ECHO SUMMIT 1101 - OH - 1 | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 0.63902 | 0 | 0.63902 | 0 | 0.63902 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado | 0 | 0 | ECHO SUMMIT 110155262 |  |  |  | FRRB | Tier 2
35285586 | FRRB - ECHO SUMMIT 1101 - OH - 2 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.27216 | 0 | 0.27216 | 0 | 0 | 0.27216 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado | 0 | 0 | ECHO SUMMIT 1101344250 |  |  |  | FRRB | Tier 2
35285587 | FRRB - ECHO SUMMIT 1101 - OH - 3 | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 0.71136 | 0 | 0.71136 | 0 | 0.68636 | 0.025 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado | 0 | 0 | ECHO SUMMIT 1101344250 |  |  |  | FRRB | Tier 2
35285588 | FRRB - ECHO SUMMIT 1101 - OH - 4 | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 0.56307 | 0.046023 | 0.60909 | 0 | 0.60909 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado | 0 | 0 | ECHO SUMMIT 1101344250 |  |  |  | FRRB | Tier 2
35285589 | FRRB - ECHO SUMMIT 1101 - UG - 5 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.28295 | 0 | 0 | 0.28295 | 0 | 0 | 0 | 0.28295 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado | 0 | 0 | ECHO SUMMIT 1101344250 |  |  |  | FRRB | Tier 2
35285590 | FRRB - ECHO SUMMIT 1101 - OH - 6 | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 0.43674 | 0 | 0.43674 | 0 | 0.43674 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado | 0 | 0 | ECHO SUMMIT 1101344250 |  |  |  | FRRB | Tier 2
35285591 | FRRB - ECHO SUMMIT 1101 - OH - 7 | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 0.47595 | 0.032955 | 0.5089 | 0 | 0.5089 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado | 0 | 0 | ECHO SUMMIT 1101344250 |  |  |  | FRRB | Tier 2
35285592 | FRRB - ECHO SUMMIT 1101 - OH - 8 | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 0.76458 | 0 | 0.76458 | 0 | 0.76458 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado | 0 | 0 | ECHO SUMMIT 1101344250 |  |  |  | FRRB | Tier 2
35285593 | FRRB - ECHO SUMMIT 1101 - OH - 9 | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 0.26458 | 0 | 0.26458 | 0 | 0.26458 | 0 | 0 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado | 0 | 0 | ECHO SUMMIT 1101344250 |  |  |  | FRRB | Tier 2
35285594 | FRRB - ECHO SUMMIT 1101 - UG - 10 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.21989 | 0 | 0 | 0.21989 | 0 | 0 | 0 | 0.21989 | 0 | SI | Region 2 - North East | Echo Lake | El Dorado | 0 | 0 |  |  |  |  | FRRB | Tier 2
35285741 | FRRB - EL DORADO PH 2101 - OH - 18 | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 0.26837 | 0.027273 | 0.29564 | 0 | 0.29564 | 0 | 0 | 0 | SI | Region 2 - North East | Twin Bridges | El Dorado | 38.8098 | -120.1217 | EL DORADO PH 210136764 | EL DORADO PH 210126000 | 63 | 2252 | FRRB | Tier 2 & 3
35285742 | FRRB - EL DORADO PH 2101 - OH - 19 | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 0.24432 | 0.027462 | 0.27178 | 0 | 0.27178 | 0 | 0 | 0 | SI | Region 2 - North East | Twin Bridges | El Dorado | 38.8098 | -120.1217 | EL DORADO PH 210136764 | EL DORADO PH 210126000 | 63 | 2252 | FRRB | Tier 2 & 3
35286199 | FRRB - BRUNSWICK 1106-TL-OH-07 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.29167 | 0 | 0.29167 | 0 | 0 | 0.29167 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1461 | -120.9737 | BRUNSWICK 11062790 | BRUNSWICK 11062790 | 1201 | 715 | FRRB | Tier 3
35286483 | FRRB - EL DORADO PH 2101 - OH - 20 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 1.0843 | 0 | 1.0843 | 0 | 0 | 1.0843 | 0 | 0 | SI | Region 2 - North East | Twin Bridges | El Dorado | 38.8098 | -120.1217 |  | EL DORADO PH 210126000 | 63 | 2252 | FRRB | Tier 2 & 3
35286694 | FRRB - KANAKA 1101CB - K4 SM3 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 0.03447 | 0 | 0.03447 | 0 | 0 | 0.03447 | 0 | 0 | NV | Region 2 - North East | Oroville | Butte | 39.5626 | -121.33 |  | KANAKA 1101CB | 1113 | 1480 | FRRB - OH - 2021 | Tier 3
35286724 | FRRB - CRESCENT MILLS 21012056 OH ML 1.1 | Fire Rebuild | 08W | UNSC | Ready for Construction | 0 | 1.0659 | 0 | 1.0659 | 0 | 0 | 1.0659 | 0 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1746 | -120.9945 |  | CRESCENT MILLS 21012056 | 551 | 895 | FRRB | Tier 2
35290517 | FRRB - SPANISH CREEK UG TL PH1.2 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.86989 | 0 | 0 | 0.86989 | 0 | 0 | 0 | 0.86989 | 0 | NV | Region 2 - North East | Crescent Mills | Plumas | 40.0604 | -120.9643 |  | SPANISH CREEK 4401CB | 462 | 1322 | FRRB | Tier 2
35290540 | FRRB - BIG MEADOWS 21012248 UG ML PH1 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.78996 | 0 | 0 | 0.78996 | 0 | 0 | 0 | 0.78996 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | BIG MEADOWS 21012248 | 1922 | 916 | FRRB | Tier 2
35290541 | FRRB - BIG MEADOWS 21012586 OH TL 1.1 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0 | 1.1 | 0 | 1.1 | 0 | 0 | 0 | 1.1 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | BIG MEADOWS 21012586 | 1567 | 1285 | FRRB | Tier 2
35290542 | FRRB - BIG MEADOWS 21012260 UG ML PH1.2 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.56004 | 0 | 0 | 0.56004 | 0 | 0 | 0 | 0.56004 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | BIG MEADOWS 21012260 | 1667 | 995 | FRRB | Tier 2
35290544 | FRRB - BIG MEADOWS 21012260 UG ML PH1.3 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.97992 | 0 | 0 | 0.97992 | 0 | 0 | 0 | 0.97992 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | BIG MEADOWS 21012260 | 1667 | 995 | FRRB | Tier 2
35290944 | FRRB -BIG MEADOWS 21012260 UG TL 1.6 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.3 | 0 | 0 | 0.3 | 0 | 0 | 0 | 0.3 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | BIG MEADOWS 21012260 | 1667 | 995 | FRRB | Tier 2
35290946 | FRRB -BIG MEADOWS 21012260 UG TL 1.7 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.17992 | 0 | 0 | 0.17992 | 0 | 0 | 0 | 0.17992 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | BIG MEADOWS 21012260 | 1667 | 995 | FRRB | Tier 2
35290948 | FRRB -BIG MEADOWS 21012260 UG TL 1.8 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0.15 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | BIG MEADOWS 21012260 | 1667 | 995 | FRRB | Tier 2
35291895 | FRRB - STILLWATER 1102_OH_FH_TPL_1 | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 0.18864 | 0 | 0.18864 | 0 | 0.18864 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6952 | -122.3164 |  | STILLWATER 1102CB | 1317 | 502 | FRRB | Tier 2
35291982 | FRRB - STILLWATER 1102_OH_FH_TPL_2 | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 0.15076 | 0 | 0.15076 | 0 | 0.15076 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6862 | -122.3124 |  | STILLWATER 1102CB | 1317 | 502 | FRRB | Tier 2
35291983 | FRRB - STILLWATER 1102_OH_FH_TPL_3 | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 0.25038 | 0 | 0.25038 | 0 | 0.25038 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6853 | -122.3097 |  | STILLWATER 1102CB | 1317 | 502 | FRRB | Tier 2
35291984 | FRRB - STILLWATER 1102_OH_FH_TPL_4 | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 1.3708 | 0.11288 | 1.4837 | 0 | 1.4837 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6755 | -122.3215 |  | STILLWATER 1102CB | 1317 | 502 | FRRB | Tier 2
35291985 | FRRB - STILLWATER 1102_OH_FH_TPL_5 | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 0.91553 | 0.057008 | 0.97254 | 0 | 0.75492 | 0.21761 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6857 | -122.3155 |  | STILLWATER 1102CB | 1317 | 502 | FRRB | Tier 2
35291986 | FRRB - STILLWATER 1101_OH_FH_TPL_6 | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 1.8723 | 0 | 1.8723 | 0 | 1.464 | 0.40833 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6951 | -122.3174 |  | STILLWATER 110148950 | 1608 | 851 | FRRB | Tier 2
35292144 | FRRB - EL DORADO PH 2101 - OH - 21 | Fire Rebuild | 08W | ESTS | Estimating | 0 | 0.99 | 0 | 0.99 | 0 | 0 | 0.99 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.8098 | -120.1217 |  | EL DORADO PH 210126000 | 63 | 2252 | FRRB | Tier 2 & 3
35292145 | FRRB - EL DORADO PH 2101 - OH - 22 | Fire Rebuild | 08W | PEND | Permitting/Dependency | 0 | 2.1585 | 0 | 2.1585 | 0 | 0 | 2.1585 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.8098 | -120.1217 |  | EL DORADO PH 210126000 | 63 | 2252 | FRRB | Tier 2 & 3
35292188 | FRRB - EL DORADO PH 2101 - OH - 23 | Fire Rebuild | 08W | UNSC | In-Construction* | 0 | 0.13542 | 0 | 0.13542 | 0 | 0.13542 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.8098 | -120.1217 |  | EL DORADO PH 210126000 | 63 | 2252 | FRRB | Tier 2 & 3
35292189 | FRRB - EL DORADO PH 2101 - OH - 24 | Fire Rebuild | 08W | PEND | In-Construction* | 0 | 0.18125 | 0 | 0.18125 | 0 | 0.18125 | 0 | 0 | 0 | SI | Region 2 - North East | Grizzly Flats | El Dorado | 38.8098 | -120.1217 |  | EL DORADO PH 210126000 | 63 | 2252 | FRRB | Tier 2 & 3
35292753 | FRRB - CRESCENT MILLS 21012056 UG TL 1.3 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0.1 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | CRESCENT MILLS 21012056 | 551 | 895 | FRRB | Tier 2
35292754 | FRRB - BIG MEADOWS 21012248 UG ML PH2 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 4.2299 | 0 | 0 | 4.2299 | 0 | 0 | 0 | 4.2299 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | BIG MEADOWS 21012248 | 1922 | 916 | FRRB | Tier 2
35292755 | FRRB - BIG MEADOWS 21012248 UG ML PH3 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 2.74 | 0 | 0 | 2.74 | 0 | 0 | 0 | 2.74 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | BIG MEADOWS 21012248 | 1922 | 916 | FRRB | Tier 2
35292756 | FRRB - BIG MEADOWS 21012248 UG ML PH4.1 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.75 | 0 | 0 | 0.75 | 0 | 0 | 0 | 0.75 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | BIG MEADOWS 21012248 | 1922 | 916 | FRRB | Tier 2
35292758 | FRRB - BIG MEADOWS 21012248 UG TL 4.2 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.15 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0.15 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | BIG MEADOWS 21012248 | 1922 | 916 | FRRB | Tier 2
35292780 | FRRB -BIG MEADOWS 21012260 UG TL 1.9 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.17008 | 0 | 0 | 0.17008 | 0 | 0 | 0 | 0.17008 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | BIG MEADOWS 21012260 | 1667 | 995 | FRRB | Tier 2
35292782 | FRRB -BIG MEADOWS 21012260 UG TL 1.10 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.23011 | 0 | 0 | 0.23011 | 0 | 0 | 0 | 0.23011 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | BIG MEADOWS 21012260 | 1667 | 995 | FRRB | Tier 2
35292784 | FRRB -BIG MEADOWS 21012260 UG TL 1.11 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0.1 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | BIG MEADOWS 21012260 | 1667 | 995 | FRRB | Tier 2
35292786 | FRRB -BIG MEADOWS 21012260 UG TL 1.12 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0.1 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | BIG MEADOWS 21012260 | 1667 | 995 | FRRB | Tier 2
35292787 | FRRB -BIG MEADOWS 21012476 OH ML PH1.1 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0 | 0.16004 | 0 | 0.16004 | 0 | 0 | 0 | 0.16004 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | BIG MEADOWS 21012476 | 2379 | 2342 | FRRB | Tier 2
35292788 | FRRB -BIG MEADOWS 21012476 UG ML PH1.2 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 1.1 | 0 | 0 | 1.1 | 0 | 0 | 0 | 1.1 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | BIG MEADOWS 21012476 | 2379 | 2342 | FRRB | Tier 2
35292789 | FRRB -BIG MEADOWS 21012476 UG TL PH1.3 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.1 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0.1 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | BIG MEADOWS 21012476 | 2379 | 2342 | FRRB | Tier 2
35292791 | FRRB -BIG MEADOWS 21012568 UG PH1 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | 0.12008 | 0 | 0 | 0.12008 | 0 | 0 | 0 | 0.12008 | 0 | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 |  | BIG MEADOWS 21012586 | 1567 | 1285 | FRRB | Tier 2
31156970 | FT STS-COND_IDLE_REMV-4065GIBSONCANYONRD | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3869 | -122.0006 | VACAVILLE 111113652 | VACAVILLE 111113652 | 502 | 190 |  | Tier 2
31157088 | REMV IDLE SVC POLE LAGOON VALLEY ROAD BE | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.24053 | 0.24053 | 0 | 0 | 0.24053 | 0 | 0 | SA | Region 2 - North East | Fairfield | Solano | 38.315 | -122.0022 | VACAVILLE 11046542 | VACAVILLE 11046542 | 1469 | 42 |  | Tier 2
31211614 | IDLE OH 4004 BONES RD SEBASTOPOL*OCLH | Idle Facilities | 2AF | CLSD | Closed | 0 | 0 | 0.032197 | 0.032197 | 0 | 0.032197 | 0 | 0 | 0 | SO | Region 1 - North Coast | Sebastopol | Sonoma | 38.4361 | -122.9103 | MOLINO 110241392 | MOLINO 110241392 | 554 | 1468 |  | Tier 2
31255513 | FT~T2 REMV IDLE SVC POLE A/F 180 GEYSERS | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SO | Region 1 - North Coast | Cloverdale | Sonoma | 38.8316 | -123.0099 | CLOVERDALE 1102674 | CLOVERDALE 1102674 | 1285 | 680 |  | Tier 2
31323810 | T3-COND_IDLE_REMV-2042 HIDDEN VALL*OCLH | Idle Facilities | 2AF | CLSD | Closed | 0 | 0 | 0.034091 | 0.034091 | 0 | 0.034091 | 0 | 0 | 0 | SO | Region 1 - North Coast |  |  | 38.4597 | -122.7023 | SANTA ROSA A 110439786 | SANTA ROSA A 1104991788 | 2890 | 3369 |  | Tier 3
35009378 | FT~STS-COND_IDLE_REMV-1405 CLOVERDALE RD | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.60379 | 0.60379 | 0 | 0 | 0.60379 | 0 | 0 | PN | Region 3 - Bay Area | Pescadero | San Mateo | 37.1979 | -122.3466 | HALF MOON BAY 11036012 | HALF MOON BAY 11036012 | 1585 | 2186 |  | Tier 2
35028500 | *FT-REPL POLE:17SW/O C/O 7943 TO KATE H. | Idle Facilities | 2AF | CLSD | Closed | 0 | 0 | 0.69527 | 0.69527 | 0 | 0.69527 | 0 | 0 | 0 | SI | Region 2 - North East | Camptonville | Yuba | 39.4788 | -120.8891 | ALLEGHANY 1101806 | ALLEGHANY 1101806 | 127 | 1446 |  | Tier 3
35037377 | DR POD POLE_IDLE_REMV-18TH AVE. | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.5616 | -122.3634 | HIGHLANDS 1103CB | HIGHLANDS 1103CB | 1421 | 461 |  | Tier 2
35037563 | DR-COND_IDLE_REMV-4966 CANYON DR | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | HB | Region 1 - North Coast | Eureka | Humboldt | 40.7543 | -124.1477 | HARRIS 11082062 | HARRIS 11082062 | 2221 | 3118 |  | Tier 2
35037588 | T2 REMV IDLE COND L/S 5429 (5800 R | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.17216 | 0.17216 | 0 | 0 | 0.17216 | 0 | 0 | HB | Region 1 - North Coast | Fortuna | Humboldt | 40.5515 | -124.1124 | CARLOTTA 112142896 | CARLOTTA 112142896 | 2101 | 1918 |  | Tier 2
35037596 | TRAN_IDLE_REMV-OLD LIGHTHOUSE RD E.O | Idle Facilities | 2AF | CLSD | Closed | 0 | 0 | 0.2197 | 0.2197 | 0 | 0.2197 | 0 | 0 | 0 | HB | Region 1 - North Coast |  |  | 40.4392 | -124.4076 | EEL RIVER 11024814 | EEL RIVER 11024814 | 769 | 1252 |  | Tier 2
35037610 | COND_IDLE_REMV-2 POLES SE LCO 7255 | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.018939 | 0.018939 | 0 | 0.018939 | 0 | 0 | 0 | HB | Region 1 - North Coast |  |  | 40.4582 | -123.5098 | LOW GAP 11012094 | LOW GAP 11012094 | 533 | 1042 |  | Tier 2
35037613 | DR_POLE_IDLE_REMV-JAYMAN LN & HWY 36 | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | HB | Region 1 - North Coast | Bridgeville | Humboldt | 40.4723 | -123.87 | BRIDGEVILLE 110237486 | BRIDGEVILLE 110237486 | 2623 | 1315 |  | Tier 2
35037705 | T2 REMV IDLE 3 LOCS-BLUE ROCK RA.RD KET | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.125 | 0.125 | 0 | 0 | 0.125 | 0 | 0 | HB | Region 1 - North Coast | Zenia | Trinity | 40.1631 | -123.4516 | FORT SEWARD 11211602 | FORT SEWARD 11211602 | 1681 | 1194 |  | Tier 2
35037706 | T2 REMV IDLE -WOLF RANCH/WOLF RD | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.024811 | 0.024811 | 0 | 0 | 0.024811 | 0 | 0 | HB | Region 1 - North Coast | Garberville | Humboldt | 40.075 | -123.5871 | GARBERVILLE 11022500 | GARBERVILLE 11022500 | 380 | 1149 |  | Tier 2
35037707 | DR POLES_IDLE_REMV-25 POLES E/0 #4269 | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.21837 | 0.21837 | 0 | 0 | 0.21837 | 0 | 0 | HB | Region 1 - North Coast | Garberville | Humboldt | 40.0599 | -123.7294 | GARBERVILLE 110139524 | GARBERVILLE 110139524 | 2332 | 1245 |  | Tier 2
35037708 | OCGC-COND_IDLE_REMV-65709 CEDAR CREEK RD | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.13277 | 0.13277 | 0 | 0.13277 | 0 | 0 | 0 | HB | Region 1 - North Coast | Leggett | Mendocino | 39.5073 | -123.4238 | GARBERVILLE 110135706 | GARBERVILLE 110135706 | 505 | 928 |  | Tier 2
35037712 | COND_IDLE_REMV-NEXT TO PEG HOUSE G*HM | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.0079545 | 0.0079545 | 0 | 0 | 0.0079545 | 0 | 0 | HB | Region 1 - North Coast | Leggett | Mendocino | 39.8781 | -123.7293 | GARBERVILLE 11011770 | GARBERVILLE 11011770 | 2504 | 630 |  | Tier 2
35037854 | X STS-TRAN_IDLE_REMV-16 POLES FROM E.O. | Idle Facilities | 2AF | CLSD | Closed | 0 | 0 | 0.086553 | 0.086553 | 0 | 0.086553 | 0 | 0 | 0 | CC | Region 4 - Central Coast |  |  | 36.1328 | -121.2304 | KING CITY 11037038 | KING CITY 11037038 | 1392 | 1814 |  | Tier 2
35037880 | DR COND_IDLE_REMV-CLARK DR | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | HB | Region 1 - North Coast | Kelseyville | Lake | 39.0031 | -122.8175 | CLEAR LAKE 11011302 | CLEAR LAKE 11011302 | 1751 | 2020 |  | Tier 2
35037896 | DR~REMV IDLE FAC 9 POLES 7769 HWY 29 | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | HB | Region 1 - North Coast | Kelseyville | Lake | 38.9413 | -122.7786 | KONOCTI 1102965078 | KONOCTI 1102965078 | 2774 | 9 |  | Tier 2
35037897 | DR POD COND_IDLE_REMV-6069 ROLAND DR | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | HB | Region 1 - North Coast | Lucerne | Lake | 39.0597 | -122.4793 | LUCERNE 1106CB | LUCERNE 1106CB | 2177 | 2687 |  | Tier 2
35038065 | STS-COND_IDLE_REMV-17420 NEW YORK HOUSE | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.17973 | 0.17973 | 0 | 0.17973 | 0 | 0 | 0 | NV | Region 2 - North East | Brownsville | Yuba | 39.4687 | -121.2462 | CHALLENGE 11021064 | CHALLENGE 11021064 | 79 | 793 |  | Tier 3
35038382 | STS-TRAN_IDLE_REMV-BEHIND 4052 CLARK DR | Idle Facilities | 2AF | CLSD | Closed | 0 | 0 | 0.23106 | 0.23106 | 0 | 0.23106 | 0 | 0 | 0 | ST | Region 5 - Central Valley |  |  | 37.9214 | -121.2204 | No CPZ data for Weber 1109 Ckt | No CPZ data for Weber 1109 Ckt
35038557 | DR COND_IDLE_REMV-UKIAH POLICE SHOOTING | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | HB | Region 1 - North Coast | Calpella | Mendocino | 39.1731 | -123.1534 | UKIAH 11151216 | UKIAH 11151216 | 1733 | 1030 |  | Tier 2
35038562 | DR COND_IDLE_REMV-4700 JENKINS RD | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | HB | Region 1 - North Coast | Redwood Valley | Mendocino | 39.34 | -123.2195 | MENDOCINO 110148750 | MENDOCINO 110148750 | 315 | 1073 |  | Tier 2
35038648 | REMV IDLE-3 LOCS-44170 LAKEVIEW AVE | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.049811 | 0.049811 | 0 | 0.049811 | 0 | 0 | 0 | HB | Region 1 - North Coast |  |  | 39.4055 | -123.3027 | LAYTONVILLE 110264908 | LAYTONVILLE 110264908 | 767 | 1003 |  | Tier 2
35038650 | T2 REMV IDLE 2 LOC FCO 6641*ROK | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.037879 | 0.037879 | 0 | 0.037879 | 0 | 0 | 0 | HB | Region 1 - North Coast | Covelo | Mendocino | 39.4432 | -123.0954 | COVELO 1101516510 | COVELO 1101516510 | 3347 | 1591 |  | Tier 2
35038668 | REMV IDLE 3 LOCS-16211 RIDGEVIEW RIDGE | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.032197 | 0.032197 | 0 | 0.032197 | 0 | 0 | 0 | HB | Region 1 - North Coast | Willits | Mendocino | 39.3434 | -123.3491 | WILLITS 1104934 | WILLITS 1104934 | 211 | 778 |  | Tier 3
35038671 | REMV IDLE 2 LOCS 33500 SHIMMINS RIDGE | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.028409 | 0.028409 | 0 | 0.028409 | 0 | 0 | 0 | HB | Region 1 - North Coast | Willits | Mendocino | 39.5331 | -123.3829 | WILLITS 110337506 | WILLITS 110337506 | 516 | 1161 |  | Tier 2
35038672 | REMV IDLE 4 LOCS HEARST POST OFC RD | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.013826 | 0.013826 | 0 | 0.013826 | 0 | 0 | 0 | HB | Region 1 - North Coast | Willits | Mendocino | 39.4919 | -123.1866 | WILLITS 11032500 | WILLITS 11032500 | 1155 | 782 |  | Tier 2
35038684 | REMV IDLE 4 LOCS 48600 VALLEY DR LAY | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | HB | Region 1 - North Coast | Branscomb | Mendocino | 39.7297 | -123.5078 | LAYTONVILLE 1101402 | LAYTONVILLE 1101402 | 1764 | 1293 |  | Tier 2
35045886 | OCGC COND_IDLE_REMV-1 POLE N/O 911 LOGAN | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.41174 | 0.41174 | 0 | 0.41174 | 0 | 0 | 0 | HB | Region 1 - North Coast | Miranda | Humboldt | 40.1485 | -123.4884 | FRUITLAND 11422006 | FRUITLAND 11422006 | 1508 | 1426 |  | Tier 2
35046236 | STS-COND_IDLE_REMV-IMPOSSIBLE CANYON ROA | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | CC | Region 4 - Central Coast | Seaside | Monterey | 36.6184 | -121.7545 | DEL MONTE 21042624 | DEL MONTE 21042624 | 1182 | 2367 |  | Tier 2
35078178 | STS-COND_IDLE_REMV-295 EAST RD | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1304 | -122.1183 | BIG BASIN 11015028 | BIG BASIN 11015028 | 2968 | 832 |  | Tier 3
35078377 | DR-TRAN_IDLE_REMV - 8252 TWIN ROCKS GRA | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East | Granite Bay | Placer | 38.7654 | -121.1514 | HORSESHOE 110450142 | HORSESHOE 110450142 | 2708 | 618 |  | Tier 2
35078379 | *FT-COND_IDLE_REMV-5115 FINNING MILL RD | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.023864 | 0.023864 | 0 | 0.023864 | 0 | 0 | 0 | SI | Region 2 - North East | Foresthill | Placer | 39.0912 | -120.7805 | FORESTHILL 110137238 | FORESTHILL 110137238 | 1434 | 188 |  | Tier 3
35078722 | DR-COND_IDLE_REMV-470 TRI DALE LN | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East | Newcastle | Placer | 38.8908 | -121.1358 | WISE 11022234 | WISE 11022234 | 430 | 723 |  | Tier 2
35078723 | FT~COND_IDLE_REMV-580 RALSTON LN | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.074432 | 0.074432 | 0 | 0 | 0.074432 | 0 | 0 | SI | Region 2 - North East | Newcastle | Placer | 38.8919 | -121.1441 | WISE 11022234 | WISE 11022234 | 430 | 723 |  | Tier 2
35078725 | *FT-COND_IDLE_REMV-5431 JULIETTA PL | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.023674 | 0.023674 | 0 | 0.023674 | 0 | 0 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.951 | -121.1991 | WISE 1102307494 | WISE 1102307494 | 528 | 537 |  | Tier 2
35078735 | COND_IDLE_REMV-1403 FORBESTOWN ROAD | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.062879 | 0.062879 | 0 | 0 | 0.062879 | 0 | 0 | NV | Region 2 - North East | Feather Falls | Butte | 39.4969 | -121.3902 | WYANDOTTE 11071510 | WYANDOTTE 11071510 | 905 | 1216 |  | Tier 2
35078737 | *FT-COND_IDLE_REMV-10708 TRINITY ALLEY | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | NV | Region 2 - North East | Shasta | Shasta | 40.6007 | -122.4916 | KESWICK 11019712 | KESWICK 11019712 | 825 | 1614 |  | Tier 3
35079380 | STS-POLE_IDLE_REMV-17425 BAKER RILEY | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.21951 | 0.21951 | 0 | 0.21951 | 0 | 0 | 0 | ST | Region 5 - Central Valley |  |  | 38.2738 | -120.562 | WEST POINT 11024788 | WEST POINT 11024788 | 718 | 1206 |  | Tier 2
35079416 | STS-COND_IDLE_REMV-3/P/N/3/P/E/O ROCKY C | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.052841 | 0.052841 | 0 | 0.052841 | 0 | 0 | 0 | LP | Region 4 - Central Coast |  |  | 35.4896 | -120.539 | TEMPLETON 2113R82 | TEMPLETON 2113R82 | 2235 | 864 |  | Tier 2
35081029 | STS-COND_IDLE_REMV - 200 N RAIL WYORINDA | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.0075758 | 0.0075758 | 0 | 0.0075758 | 0 | 0 | 0 | DI | Region 3 - Bay Area | Orinda | Contra Costa | 37.8278 | -122.163 | MORAGA 1105CB | MORAGA 1105CB | 204 | 2619 |  | Tier 3
35081139 | STS-POLE_DECA_REPL - 1S/O R/O 2421 PINEO | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.098485 | 0.098485 | 0 | 0.098485 | 0 | 0 | 0 | SI | Region 2 - North East |  |  | 38.7112 | -120.9793 | SHINGLE SPRINGS 21092679 | SHINGLE SPRINGS 21092679 | 281 | 578 |  | Tier 3
35083687 | STS-COND_IDLE_REMV-10185MENDENHALLRDLI | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.050189 | 0.050189 | 0 | 0.050189 | 0 | 0 | 0 | MI | Region 3 - Bay Area | Livermore | Alameda | 37.5928 | -121.6812 | VASCO 1102MR176 | VASCO 1102MR176 | 1184 | 324 |  | Tier 2
35083695 | FT~STS-COND_IDLE_REMV - 125000 MENDENHAL | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.1661 | 0.1661 | 0 | 0.1661 | 0 | 0 | 0 | MI | Region 3 - Bay Area | Livermore | Alameda | 37.5738 | -121.6773 | VASCO 1102MR176 | VASCO 1102MR176 | 1184 | 324 |  | Tier 2
35083698 | STS-COND_IDLE_REMV-24654 HWY 108 | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.023674 | 0.023674 | 0 | 0.023674 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mi Wuk Village | Tuolumne | 38.0667 | -120.1866 | MIWUK 1701CB | MIWUK 1701CB | 2 | 2353
35083699 | STS-COND_IDLE_REMV-38113 PETERSON RD | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 | 0.075758 | 0 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0356 | -119.3337 | AUBERRY 1101R319 | AUBERRY 1101176050 | 2863 | 1302
35083700 | STS-COND_IDLE_REMV-22230 DAVID DR | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.02178 | 0.02178 | 0 | 0.02178 | 0 | 0 | 0 | YO | Region 5 - Central Valley |  |  | 38.0819 | -120.1447 | MIWUK 1701953336 | MIWUK 1701953336 | 2724 | 2267 |  | Tier 3
35083712 | STS-COND_IDLE_REMV-LOC #8, 23795 SOUTHFO | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.13769 | 0.13769 | 0 | 0 | 0.13769 | 0 | 0 | YO | Region 5 - Central Valley |  |  | 38.055 | -120.2323
35083719 | STS-POLE_IDLE_REMV - 42781 E OAK LN 1PE | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.045455 | 0.045455 | 0 | 0.045455 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Oakhurst | Madera | 37.3717 | -119.6102 | OAKHURST 11035480 | OAKHURST 11035480 | 854 | 1903 |  | Tier 3
35083725 | STS-COND_IDLE_REMV-3 3/10M NE/I5/BEARTRA | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.0094697 | 0.0094697 | 0 | 0.0094697 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8587 | -118.8147 | TEJON 11023760 | TEJON 11023760 | 2370 | 931 |  | Tier 2
35083726 | T2/T3-STS-COND_IDLE_REMV-17195 HWY 108 | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.048295 | 0.048295 | 0 | 0.048295 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Jamestown | Tuolumne | 37.9339 | -120.4425 | PEORIA 170510580 | PEORIA 170510580 | 1984 | 835 |  | Tier 2
35083733 | STS-COND_IDLE_REMV-36017 TOYON DR/SOUTH | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8441 | -118.8759 | TEJON 11023751 | TEJON 1102732836 | 2673 | 583 |  | Tier 2
35083737 | STS-COND_IDLE_REMV-1/10M N/O 5008 HIGH V | Idle Facilities | 2AF | UNSC | In-Construction* | 0 | 0 | 1.0197 | 1.0197 | 0 | 1.0197 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Frazier Park | Kern | 34.8884 | -118.9409 | TEJON 11023751 | TEJON 11023751 | 2272 | 691 |  | Tier 2
35083738 | STS-COND_IDLE_REMV-ON HWY 108, ACROSS TH | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.042992 | 0.042992 | 0 | 0.042992 | 0 | 0 | 0 | YO | Region 5 - Central Valley |  |  | 37.9388 | -120.4368 | PEORIA 170510580 | PEORIA 170510580 | 1984 | 835 |  | Tier 2
35083740 | STS-COND_IDLE_REMV-7633 HWY 120 | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.041288 | 0.041288 | 0 | 0.041288 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Groveland | Tuolumne | 37.8182 | -120.0588 | CURTIS 17039210 | CURTIS 17039210 | 1004 | 2348 |  | Tier 2
35083742 | STS-COND_IDLE_REMV-56060 NORTH FORK RD ( | Idle Facilities | 2AF | CLSD | Closed | 0 | 0 | 0.029356 | 0.029356 | 0 | 0.029356 | 0 | 0 | 0 | YO | Region 5 - Central Valley |  |  | 37.1789 | -119.6281 | SAN JOAQUIN #2 1103CB | SAN JOAQUIN #2 1103CB | 828 | 204 |  | Tier 2
35083743 | STS-COND_IDLE_REMV-ON N/S MILLERTON RD 1 | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.039394 | 0.039394 | 0 | 0.039394 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Clovis | Fresno | 36.9783 | -119.6277 | SHEPHERD 2111R1400 | SHEPHERD 2111707358 | 2974 | 247 |  | Tier 2
35083755 | STS-COND_IDLE_REMV-41563 LILLEY MOUNTAIN | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.059091 | 0.059091 | 0 | 0.059091 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Coarsegold | Madera | 37.1935 | -119.7916 | COARSEGOLD 210410400 | COARSEGOLD 210410400 | 815 | 263 |  | Tier 2
35083756 | STS-COND_IDLE_REMV-ACROSS FROM 57839 RD | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.044129 | 0.044129 | 0 | 0.044129 | 0 | 0 | 0 | YO | Region 5 - Central Valley |  |  | 37.2293 | -119.4931 | SAN JOAQUIN #3 1103CB | SAN JOAQUIN #3 1103CB | 909 | 849 |  | Tier 2
35083772 | STS-POLE_IDLE_REMV - 39850 DUNLOP RD/2PS | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.15152 | 0.15152 | 0 | 0.15152 | 0 | 0 | 0 | FR | Region 5 - Central Valley | Dunlap | Fresno | 36.7325 | -119.1122 | DUNLAP 11037220 | DUNLAP 11037220 | 1901 | 364 |  | Tier 2
35083773 | STS-COND_IDLE_REMV-20230 LYONS BALD MTN | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | YO | Region 5 - Central Valley | Sonora | Tuolumne | 37.9916 | -120.3717 | TAR FLAT 0401CB | TAR FLAT 0401CB | 1823 | 3142 |  | Tier 2
35083780 | STS-COND_IDLE_REMV-5088 TIPTOP RD | Idle Facilities | 2AF | CLSD | Closed | 0 | 0 | 0.034091 | 0.034091 | 0 | 0.034091 | 0 | 0 | 0 | YO | Region 5 - Central Valley |  |  | 37.4561 | -119.823 | MARIPOSA 210110990 | MARIPOSA 210110990 | 1118 | 199
35083807 | STS-COND_IDLE_REMV-5461 COLORADO RD | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.014583 | 0.014583 | 0 | 0 | 0.014583 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5622 | -119.9673 | MARIPOSA 21018030 | MARIPOSA 2101752630 | 2886 | 700 |  | Tier 2
35083812 | STS-COND_IDLE_REMV-2/10MI W/O LEBEC RD N | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.045076 | 0.045076 | 0 | 0.045076 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8274 | -118.885 | TEJON 11023751 | TEJON 1102732836 | 2673 | 583 |  | Tier 2
35083846 | STS-COND_IDLE_REMV-36985 LODGE RD | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.063636 | 0.063636 | 0 | 0 | 0.063636 | 0 | 0 | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0075 | -119.4093 | AUBERRY 1101R2578 | AUBERRY 1101R2578 | 1377 | 163 |  | Tier 2
35083864 | STS-COND_IDLE_REMV-22148 EDEN CANYON RD | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | MI | Region 3 - Bay Area | Castro Valley | Alameda | 37.7209 | -122.0385 | CASTRO VALLEY 1110MR243 | CASTRO VALLEY 1110MR243 | 2988 | 1914 |  | Tier 3
35083878 | STS-COND_IDLE_REMV-9685 MANZANITA WAY | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.045644 | 0.045644 | 0 | 0 | 0.045644 | 0 | 0 | YO | Region 5 - Central Valley | Coulterville | Mariposa | 37.7098 | -120.1164 | BEAR VALLEY 21059560 | BEAR VALLEY 21059560 | 1001 | 1547 |  | Tier 2
35083879 | STS-POLE_IDLE_REMV - NEGRO CK RD/RD 152 | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | FR | Region 5 - Central Valley | Orosi | Tulare | 36.6365 | -119.1961 | SAND CREEK 1103CB | SAND CREEK 1103CB | 1765 | 337 |  | Tier 2
35083888 | STS-COND_IDLE_REMV-#2W ON LINE A/F 916 N | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.072348 | 0.072348 | 0 | 0 | 0.072348 | 0 | 0 | ST | Region 5 - Central Valley | Jackson | Amador | 38.3595 | -120.7799 | MARTELL 110292172 | MARTELL 110292172 | 846 | 2054 |  | Tier 2
35083889 | STS-COND_IDLE_REMV-10039 JESUS MARIA RD | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.007197 | 0.007197 | 0 | 0.007197 | 0 | 0 | 0 | ST | Region 5 - Central Valley |  |  | 38.2952 | -120.6752 | CALAVERAS CEMENT 11012646 | CALAVERAS CEMENT 11012646 | 2720 | 1889 |  | Tier 2
35083893 | STS-COND_IDLE_REMV-5282 MINES RD | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.067424 | 0.067424 | 0 | 0 | 0.067424 | 0 | 0 | MI | Region 3 - Bay Area | Livermore | Alameda | 37.6459 | -121.7137 | VASCO 1102MR176 | VASCO 1102MR176 | 1184 | 324 |  | Tier 2
35083901 | STS-COND_IDLE_REMV-MARKER 1000 USONA RD | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.02178 | 0.02178 | 0 | 0.02178 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.3919 | -119.831 | MARIPOSA 210237288 | MARIPOSA 210237288 | 850 | 379 |  | Tier 2
35083904 | STS-COND_IDLE_REMV-4025 USONA RD | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.022727 | 0.022727 | 0 | 0.022727 | 0 | 0 | 0 | YO | Region 5 - Central Valley |  |  | 37.4086 | -119.8262 | MARIPOSA 210237288 | MARIPOSA 210237288 | 850 | 379
35083905 | STS-COND_IDLE_REMV-MARKER 1000 USONA RD | Idle Facilities | 2AF | CLSD | Closed | 0 | 0 | 0.017992 | 0.017992 | 0 | 0.017992 | 0 | 0 | 0 | YO | Region 5 - Central Valley |  |  | 37.3921 | -119.8313 | MARIPOSA 210237288 | MARIPOSA 210237288 | 850 | 379 |  | Tier 2
35083913 | STS-COND_IDLE_REMV-8236 CROW CANYON RD | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | MI | Region 3 - Bay Area | Castro Valley | Alameda | 37.7368 | -122.0325 | SAN RAMON 2108CB | SAN RAMON 2108CB | 318 | 1092 |  | Tier 3
35083917 | T2/T3-COND_IDLE_REMV-9463 NORRIS CYN, SR | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.022727 | 0.022727 | 0 | 0.022727 | 0 | 0 | 0 | MI | Region 5 - Central Valley |  |  | 37.7537 | -122.0063 | TASSAJARA 2113MR276 | TASSAJARA 2113MR276 | 920 | 1190 |  | Tier 3
35083919 | STS-COND_IDLE_REMV-3962 USONA RD | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.1108 | 0.1108 | 0 | 0.1108 | 0 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.3983 | -119.8281 | MARIPOSA 210237288 | MARIPOSA 210237288 | 850 | 379 |  | Tier 2
35083923 | 8/31-STS-COND_IDLE_REMV-4237 DIGIER RD. | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.079167 | 0.079167 | 0 | 0.079167 | 0 | 0 | 0 | KE | Region 5 - Central Valley | Lebec | Kern | 34.8793 | -118.9008 | [5 empty] | Tier 2
35085362 | ASAP REMV IDLE R/O 17020 ARMSTRON*AE | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.026515 | 0.026515 | 0 | 0.026515 | 0 | 0 | 0 | SO | Region 1 - North Coast | Guerneville | Sonoma | 38.5542 | -123.0043 | MONTE RIO 1113346 | MONTE RIO 1113346 | 737 | 2084 |  | Tier 3
35105894 | STS-OFAC_IDLE_REMV - 4993 BEN HUR MARIPO | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.441 | -119.9426 | MARIPOSA 210237282 | MARIPOSA 210237282 | 969 | 223 |  | Tier 3
35106410 | STS-OFAC_IDLE_DEEN - #2W T-PL#11/11 N/O | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.042803 | 0.042803 | 0 | 0.042803 | 0 | 0 | 0 | SI | Region 2 - North East |  |  | 38.6593 | -120.9544 | SHINGLE SPRINGS 2108CB | SHINGLE SPRINGS 2108CB | 1098 | 2298 |  | Tier 3
35106411 | STS-OFAC_IDLE_DEEN - 1S/O 543 DUTCH FLAT | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.038447 | 0.038447 | 0 | 0.038447 | 0 | 0 | 0 | SI | Region 2 - North East |  |  | 39.1966 | -120.8329 | BONNIE NOOK 1101CB | BONNIE NOOK 1101CB | 163 | 1526 |  | Tier 3
35109767 | STS-COND_IDLE_REMV - AMERICAN WY ON CLAR | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.054356 | 0.054356 | 0 | 0.054356 | 0 | 0 | 0 | NV | Region 2 - North East |  |  | 39.7387 | -121.6124 | PARADISE 11042034 | PARADISE 11042034 | 942 | 1537 |  | Tier 3
35111037 | +STS-COND_IDLE_REMV - 14655 HWY 41 1/P/N | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.030682 | 0.030682 | 0 | 0.030682 | 0 | 0 | 0 | LP | Region 4 - Central Coast |  |  | 35.461 | -120.7383 | ATASCADERO 1103A06 | ATASCADERO 1103440856 | 3143 | 1294 |  | Tier 3
35116082 | STS-COND_IDLE_REMV-2/POLES S/O DISCONNEC | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.023674 | 0.023674 | 0 | 0.023674 | 0 | 0 | 0 | SI | Region 2 - North East | Kyburz | El Dorado | 38.7881 | -120.1936 | EL DORADO PH 210136764 | EL DORADO PH 210136764 | 2633 | 2075 |  | Tier 2
35119600 | STS-OFAC_IDLE_REMV- 1NE/O 24099 DERSCH | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.39905 | 0.39905 | 0 | 0.39905 | 0 | 0 | 0 | NV | Region 2 - North East |  |  | 40.4714 | -122.1602 | PANORAMA 11021342 | PANORAMA 1102508502 | 2971 | 283 |  | Tier 2
35119954 | COND_IDLE_REMV-109 LAKESIDE AVE *PAR | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.024432 | 0.024432 | 0 | 0.024432 | 0 | 0 | 0 | SO | Region 1 - North Coast |  |  | 38.4261 | -122.9603 | MONTE RIO 11125040 | MONTE RIO 11125040 | 304 | 1113 |  | Tier 3
35120413 | DR-STS-COND_IDLE_REMV78TOYONDRIVE | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | NB | Region 1 - North Coast | Fairfax | Marin | 37.9797 | -122.604 | SAN RAFAEL 1108516 | SAN RAFAEL 1108516 | 679 | 1837 |  | Tier 3
35121398 | STS-COND_IDLE_REMV-WEST OF RR BRIDGE LOW | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.03447 | 0.03447 | 0 | 0 | 0.03447 | 0 | 0 | NV | Region 2 - North East | Lakehead | Shasta | 40.8412 | -122.3559 | ANTLER 11011378 | ANTLER 11011378 | 2031 | 1722 |  | Tier 2
35121520 | NR7 OFAC_IDLE_REMV-LAKEVIEW RD-14LOC | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.65606 | 0.65606 | 0 | 0 | 0.65606 | 0 | 0 | NV | Region 2 - North East | Lakehead | Shasta | 40.8127 | -122.2972 | ANTLER 11011378 | ANTLER 11011378 | 2031 | 1722 |  | Tier 2
35122244 | STS-COND_IDLE_REMV-3780 SANTA ROSA | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | LP | Region 4 - Central Coast | Lompoc | Santa Barbara | 34.6129 | -120.3726 | CABRILLO 1103Y46 | CABRILLO 1103Y46 | 1364 | 998 |  | Tier 2
35122245 | STS-COND_IDLE_REMV-1750 PRISIMA RD | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.028409 | 0.028409 | 0 | 0 | 0.028409 | 0 | 0 | LP | Region 4 - Central Coast | Lompoc | Santa Barbara | 34.6737 | -120.4351 | CABRILLO 1103Y10 | CABRILLO 1103Y10 | 1949 | 1278 |  | Tier 2
35122388 | T2/T3-STS-COND_IDLE_REMV-2/E/O 183 | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.034091 | 0.034091 | 0 | 0.034091 | 0 | 0 | 0 | NV | Region 2 - North East | Brownsville | Yuba | 39.4184 | -121.2562 | CHALLENGE 11021064 | CHALLENGE 11021064 | 79 | 793 |  | Tier 3
35122390 | T2/T3-STS-COND_IDLE_REMV-15839 FRENCHTOW | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.031061 | 0.031061 | 0 | 0 | 0.031061 | 0 | 0 | NV | Region 2 - North East | Brownsville | Yuba | 39.4231 | -121.26 | CHALLENGE 11021064 | CHALLENGE 11021064 | 79 | 793 |  | Tier 3
35126503 | STS-COND_IDLE_REMV-17820 ALMA BRIDGE RD | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.041667 | 0.041667 | 0 | 0 | 0.041667 | 0 | 0 | DA | Region 4 - Central Coast | Los Gatos | Santa Clara | 37.1904 | -121.985 | LOS GATOS 1107CB | LOS GATOS 1107CB | 1327 | 2606 |  | Tier 3
35132573 | STS-COND_IDLE_REMV-2538 LAYTON DOS RIOS | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.068182 | 0.068182 | 0 | 0 | 0.068182 | 0 | 0 | HB | Region 1 - North Coast | Laytonville | Mendocino | 39.6876 | -123.4485 | LAYTONVILLE 1102CB | LAYTONVILLE 1102CB | 485 | 786 |  | Tier 2
35132574 | T2-COND_IDLE_REMV-1625 HILL TOP RD*PAR | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.019697 | 0.019697 | 0 | 0.019697 | 0 | 0 | 0 | HB | Region 1 - North Coast | Willits | Mendocino | 39.3873 | -123.3232 | WILLITS 1103968 | WILLITS 1103968 | 221 | 1264 |  | Tier 2
35133680 | STS-COND_IDLE_REMV-SIERRA BUTTES RD | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.016098 | 0.016098 | 0 | 0.016098 | 0 | 0 | 0 | SI | Region 2 - North East |  |  | 39.5672 | -120.6402 | ALLEGHANY 1101804 | ALLEGHANY 1101804 | 291 | 1753 |  | Tier 2
35135297 | STS-REM IDLE 12KV-110 PARKHILL,S.MARGAR | Idle Facilities | 2AF | CLSD | Closed | 0 | 0 | 0.098864 | 0.098864 | 0 | 0.098864 | 0 | 0 | 0 | LP | Region 4 - Central Coast |  |  | 35.3707 | -120.4072 | TEMPLETON 2113A12 | TEMPLETON 2113A12 | 1446 | 133 |  | Tier 3
35135355 | STS-COND_IDLE_REMV-10048 ROCK CREEK RD | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.083523 | 0.083523 | 0 | 0.083523 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7891 | -120.7714 | PLACERVILLE 2106935216 | PLACERVILLE 2106935216 | 3025 | 904 |  | Tier 3
35135357 | STS-COND_IDLE_REMV-2931 CLAY ST | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.022348 | 0.022348 | 0 | 0.022348 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7313 | -120.7962 | PLACERVILLE 210619732 | PLACERVILLE 210619732 | 954 | 2992 |  | Tier 3
35137767 | REMV IDLE 2 LOCS 1E/O 6S/O R/O 12109 | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.032576 | 0.032576 | 0 | 0.032576 | 0 | 0 | 0 | NV | Region 2 - North East |  |  | 40.6374 | -122.2152 | DESCHUTES 11041370 | DESCHUTES 11041370 | 1954 | 100 |  | Tier 2
35138427 | STS-COND_IDLE_REMV-34705 ALTA BONNY NOOK | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.12197 | 0.12197 | 0 | 0 | 0.12197 | 0 | 0 | SI | Region 2 - North East | Alta | Placer | 39.2098 | -120.7934 | BONNIE NOOK 1102CB | BONNIE NOOK 1102CB | 67 | 2087 |  | Tier 3
35143499 | DR-COND_IDLE_REMV-30275 TERRY MILL ROAD | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.03125 | 0.03125 | 0 | 0 | 0.03125 | 0 | 0 | NV | Region 2 - North East | Round Mountain | Shasta | 40.4775 | -121.5503 | CEDAR CREEK 1101CB | CEDAR CREEK 1101CB | 1749 | 392 |  | Tier 3
35143764 | STS-COND_IDLE_REMV-3 N/O 7 W/O 1 S/O 338 | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.023485 | 0.023485 | 0 | 0 | 0.023485 | 0 | 0 | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3509 | -121.7729 | VOLTA 11011596 | VOLTA 11011596 | 2583 | 966 |  | Tier 2
35144989 | STS-POLE_IDLE_REMV - 10590 DESCHUTES RD | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.073485 | 0.073485 | 0 | 0 | 0.073485 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.5167 | -122.2386 | DESCHUTES 11049718 | DESCHUTES 11049718 | 1758 | 48 |  | Tier 2
35145458 | STS-POLE_IDLE_REMV - NW C/O BUCKMEADOWS | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 1.6263 | 1.6263 | 0 | 0 | 1.6263 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.758 | -120.0408 | BEAR VALLEY 21059560 | BEAR VALLEY 2105454432 | 2714 | 882 |  | Tier 2
35148037 | FT STS-COND_IDLE_REMV-8421 HAPPYVALLEYRD | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East | Somerset | El Dorado | 38.6783 | -120.579 | APPLE HILL 21029722 | APPLE HILL 21029722 | 890 | 1131 |  | Tier 3
35148039 | DR-COND_IDLE_REMV-CEDERVILLE ROAD ALMOS | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East | Somerset | El Dorado | 38.5692 | -120.6494 | APPLE HILL 21028372 | APPLE HILL 21028372 | 1139 | 654 |  | Tier 3
35148124 | FT_STS-COND_IDLE_REMV-5PN.2788 STONECRES | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7402 | -120.7772 | PLACERVILLE 210623190 | PLACERVILLE 210623190 | 1566 | 2430 |  | Tier 2
35148129 | STS-COND_IDLE_REMV-1167 IDAHO WAY | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.029924 | 0.029924 | 0 | 0.029924 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.8336 | -120.8156 | PLACERVILLE 210611132 | PLACERVILLE 210611132 | 875 | 1666
35148224 | DR~STS-TREE_OVRG_TRIM-P E/O/2846 LARSON | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7398 | -120.6765 | APPLE HILL 1104CB | APPLE HILL 1104CB | 530 | 1422 |  | Tier 2
35149060 | STS-COND_IDLE_REMV-2 SPANS S/O NEWTON RD | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.020455 | 0.020455 | 0 | 0 | 0.020455 | 0 | 0 | HB | Region 1 - North Coast | Weott | Humboldt | 40.3239 | -123.9266 | FRUITLAND 114195324 | FRUITLAND 1141200856 | 3102 | 1867 |  | Tier 2
35149117 | STS-COND_IDLE_REMV-20305 HWY 36 | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.099621 | 0.099621 | 0 | 0.099621 | 0 | 0 | 0 | HB | Region 1 - North Coast | Bridgeville | Humboldt | 40.4724 | -123.8654 | BRIDGEVILLE 110237486 | BRIDGEVILLE 110237486 | 2623 | 1315 |  | Tier 2
35149134 | OCGC-8/31-REMV IDLE 4 LOCS-C/O POLE 1321 | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.14773 | 0.14773 | 0 | 0.14773 | 0 | 0 | 0 | HB | Region 1 - North Coast | Cobb | Lake | 38.8591 | -122.7624 | MIDDLETOWN 11014646 | MIDDLETOWN 11014646 | 205 | 328 |  | Tier 3
35149206 | STS-COND_IDLE_REMV-1L/SC/O64139 32191*BD | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.0045455 | 0.0045455 | 0 | 0.0045455 | 0 | 0 | 0 | HB | Region 1 - North Coast |  |  | 39.227 | -123.7403 | ELK 11011272 | ELK 11011272 | 1089 | 2587 |  | Tier 2
35149232 | STS-COND_IDLE_REMV-2 POLES N/O SW 1537 | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.16098 | 0.16098 | 0 | 0.16098 | 0 | 0 | 0 | HB | Region 1 - North Coast | Miranda | Humboldt | 40.1504 | -123.4986 | FRUITLAND 11426054 | FRUITLAND 11426054 | 1573 | 1295 |  | Tier 2
35149235 | 8/31-REMV IDLE 6 LOCS 13311 HWY 29 HOLD | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.16515 | 0.16515 | 0 | 0 | 0.16515 | 0 | 0 | HB | Region 1 - North Coast | Lower Lake | Lake | 38.8609 | -122.6263 | HIGHLANDS 11031282 | HIGHLANDS 11031282 | 514 | 626 |  | Tier 2
35149246 | STS-COND_IDLE_REMV-16251 HWY 101*DIV | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.18277 | 0.18277 | 0 | 0 | 0.18277 | 0 | 0 | HB | Region 1 - North Coast | Hopland | Mendocino | 38.9503 | -123.0881 | HOPLAND 1101768 | HOPLAND 1101768 | 2000 | 110 |  | Tier 2
35149249 | STS-COND_IDLE_REMV-20144 JERUSALEM GR*KS | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.060606 | 0.060606 | 0 | 0.060606 | 0 | 0 | 0 | HB | Region 1 - North Coast |  |  | 38.8323 | -122.5362 | HIGHLANDS 1103520 | HIGHLANDS 1103520 | 210 | 440 |  | Tier 2
35149255 | STS-COND_IDLE_REMV-2E\O 2N\O A\F ENTRANC | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.044508 | 0.044508 | 0 | 0.044508 | 0 | 0 | 0 | HB | Region 1 - North Coast |  |  | 39.6573 | -123.6328 | LAYTONVILLE 1102682 | LAYTONVILLE 1102682 | 596 | 1508 |  | Tier 2
35149294 | T2-COND_IDLE_REMV-END OFSOUTH FORKTAP*MJ | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.082955 | 0.082955 | 0 | 0 | 0.082955 | 0 | 0 | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8031 | -123.5562 | WILLOW CREEK 11033090 | WILLOW CREEK 11033090 | 1843 | 1598 |  | Tier 2
35149328 | STS-COND_IDLE_REMV-JUNCTION OF FOURTH & | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | HB | Region 1 - North Coast | Alderpoint | Humboldt | 40.1782 | -123.6144 | FORT SEWARD 11211663 | FORT SEWARD 1121CB | 1742 | 566 |  | Tier 2
35149360 | T2/T3-STS-COND_IDLE_REMV-BEHIND USFS OFF | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.065152 | 0.065152 | 0 | 0.065152 | 0 | 0 | 0 | NV | Region 2 - North East | Paskenta | Tehama | 39.8852 | -122.544 | CORNING 110253184 | CORNING 110253184 | 1844 | 413 |  | Tier 2
35149392 | OCGCSTS-CONDIDLE_REMV-1S/O2E/O 21120COON | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.016477 | 0.016477 | 0 | 0 | 0.016477 | 0 | 0 | HB | Region 1 - North Coast | Lower Lake | Lake | 38.8335 | -122.5183 | HIGHLANDS 1103520 | HIGHLANDS 1103520 | 210 | 440 |  | Tier 2
35149422 | OCGCSTS-CONDIDLE_REMV-#1S#1E#1S#1W HWY 9 | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.044318 | 0.044318 | 0 | 0.044318 | 0 | 0 | 0 | HB | Region 1 - North Coast | Hoopa | Humboldt | 41.0441 | -123.6734 | HOOPA 11017468 | HOOPA 1101CB | 1174 | 2049 |  | Tier 2
35149930 | REMV IDLE 4 LOCS 18424 HARBIN SPGS | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.090341 | 0.090341 | 0 | 0 | 0.090341 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7864 | -122.6516 | MIDDLETOWN 1101CB | MIDDLETOWN 1101CB | 351 | 86 |  | Tier 3
35150103 | REMV IDLE 3 LOCS 2615 BRICELAND RD | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.038447 | 0.038447 | 0 | 0 | 0 | 0.038447 | 0 | HB | Region 1 - North Coast | Redway | Humboldt | 40.1302 | -123.8555 | GARBERVILLE 11021510 | GARBERVILLE 11021510 | 1358 | 1476 |  | Tier 2
35150116 | STS-COND_IDLE_REMV-10151 ORR SPRING *DIV | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.02197 | 0.02197 | 0 | 0 | 0.02197 | 0 | 0 | HB | Region 1 - North Coast | Calpella | Mendocino | 39.2202 | -123.3367 | UKIAH 1111534 | UKIAH 1111534 | 1397 | 205 |  | Tier 2
35150135 | REMV IDLE 2 LOCS -8120 HWY 29 KELSEY | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | HB | Region 1 - North Coast | Kelseyville | Lake | 38.9265 | -122.723 | KONOCTI 1102CB | KONOCTI 1102CB | 2123 | 407 |  | Tier 2
35150549 | STS-COND_IDLE_REMV-3E\O 3S\O 1E\O 2N\O 6 | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | HB | Region 1 - North Coast | Garberville | Humboldt | 40.103 | -123.7921 | GARBERVILLE 11011604 | GARBERVILLE 11011604 | 1969 | 522 |  | Tier 2
35150566 | REMV IDLE 2 LOCS HIGHWAY 175 MIDDLETOWN | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.031629 | 0.031629 | 0 | 0 | 0.031629 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.8086 | -122.7072 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 |  | Tier 3
35150623 | STS-COND_IDLE_REMV-17065 HOFACKER LN*KS | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.0085227 | 0.0085227 | 0 | 0.0085227 | 0 | 0 | 0 | HB | Region 1 - North Coast |  |  | 38.8511 | -122.5922 | HIGHLANDS 11031282 | HIGHLANDS 11031282 | 514 | 626 |  | Tier 2
35150629 | STS-COND_IDLE_REMV-2025 PARK PLACE BL*KS | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.013447 | 0.013447 | 0 | 0.013447 | 0 | 0 | 0 | HB | Region 1 - North Coast |  |  | 38.9844 | -122.6159 | HIGHLANDS 110280660 | HIGHLANDS 1102623120 | 2966 | 74 |  | Tier 2
35150641 | T2-COND_IDLE_REMV-16853 DAM RD *KS | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.07197 | 0.07197 | 0 | 0 | 0.07197 | 0 | 0 | HB | Region 1 - North Coast | Clearlake | Lake | 38.9248 | -122.5968 | HIGHLANDS 1103568 | HIGHLANDS 1103568 | 1493 | 212 |  | Tier 2
35150686 | COND_IDLE_REMV-54896 N HIGHWAY 1*PAR | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.0094697 | 0.0094697 | 0 | 0 | 0.0094697 | 0 | 0 | HB | Region 1 - North Coast | Westport | Mendocino | 39.8183 | -123.7831 | GARBERVILLE 11012026 | GARBERVILLE 11012026 | 768 | 415 |  | Tier 2
35150689 | T2 REMV IDLE 5 LOCS-31850 AIRPORT RD | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.23182 | 0.23182 | 0 | 0.23182 | 0 | 0 | 0 | HB | Region 1 - North Coast | Fort Bragg | Mendocino | 39.4661 | -123.7876 | FORT BRAGG A 11041316 | FORT BRAGG A 11041316 | 1400 | 2581 |  | Tier 2
35150918 | STS-TRAN_IDLE_REMV + #1N/O A/F 4374 NOVA | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.015152 | 0.015152 | 0 | 0.015152 | 0 | 0 | 0 | NB | Region 1 - North Coast |  |  | 38.1254 | -122.6724 | STAFFORD 11021202 | STAFFORD 11021202 | 607 | 112 |  | Tier 2
35150987 | STS-COND_IDLE_REMV-15808 SANBORN RD/4PE/ | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.060606 | 0.060606 | 0 | 0.060606 | 0 | 0 | 0 | DA | Region 4 - Central Coast | Saratoga | Santa Clara | 37.239 | -122.0699 | SARATOGA 1107413816 | SARATOGA 1107413816 | 760 | 2145 |  | Tier 3
35150991 | T2-POLE_IDLE_REMV - GIBNEY DR MIRANDA*RM | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.072159 | 0.072159 | 0 | 0 | 0.072159 | 0 | 0 | HB | Region 1 - North Coast | Miranda | Humboldt | 40.2176 | -123.8207 | FRUITLAND 114263170 | FRUITLAND 114263170 | 1410 | 1429 |  | Tier 2
35150992 | 8/31-REMV IDLE 2 LOCS-20333 HWY 29[BAR | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.061932 | 0.061932 | 0 | 0.061932 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7687 | -122.5914 | MIDDLETOWN 1102CB | MIDDLETOWN 1102302610 | 3061 | 8 |  | Tier 2
35151000 | STS-COND_IDLE_REMV-12250 PRATT RANCH RD | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.039773 | 0.039773 | 0 | 0.039773 | 0 | 0 | 0 | HB | Region 1 - North Coast |  |  | 38.9886 | -123.0573 | HOPLAND 1101960 | HOPLAND 1101CB | 2512 | 1099 |  | Tier 2
35151005 | 8/31 REMV IDLE 4 LOCS OLD WITTER SP*RA | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.28636 | 0.28636 | 0 | 0 | 0.28636 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1855 | -122.9893 | UPPER LAKE 1101412 | UPPER LAKE 1101412 | 2122 | 259 |  | Tier 2
35151024 | OCGCPOLEIDLE_REMV-3LOCS-SOCRATES MINE RD | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.1339 | 0.1339 | 0 | 0.1339 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7794 | -122.7062 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 |  | Tier 3
35151026 | 8/31-REMV IDLE 3 LOCS 2537 DESSIE | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.10152 | 0.10152 | 0 | 0 | 0.10152 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0686 | -122.9659 | HARTLEY 1101658 | HARTLEY 1101658 | 882 | 439 |  | Tier 2
35151027 | 8/31 REMV IDLE 3 LOCS 11667 RANCHERIA*RA | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.060606 | 0.060606 | 0 | 0 | 0.060606 | 0 | 0 | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1992 | -122.9146 | UPPER LAKE 110175370 | UPPER LAKE 110175370 | 2009 | 705 |  | Tier 2
35151029 | STS-COND_IDLE_REMV-2N/O 3W/O 1S/O A/F LO | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.02178 | 0.02178 | 0 | 0.02178 | 0 | 0 | 0 | HB | Region 1 - North Coast |  |  | 40.8115 | -123.4965 | WILLOW CREEK 11032936 | WILLOW CREEK 11032936 | 1299 | 1474 |  | Tier 2
35151032 | STS-COND_IDLE_REMV-10324 PINEWOOD WAY | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.028409 | 0.028409 | 0 | 0.028409 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.813 | -122.7155 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 |  | Tier 3
35151033 | STS-COND_IDLE_REMV-21720 HWY 29 | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.018939 | 0.018939 | 0 | 0.018939 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.7395 | -122.6242 | MIDDLETOWN 1101622 | MIDDLETOWN 1101644756 | 3049 | 314 |  | Tier 2
35151050 | 8/31- REMV IDLE 3 LOCS 2951 HENDRICKS RD | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.032765 | 0.032765 | 0 | 0.032765 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.0734 | -122.9655 | HARTLEY 1101658 | HARTLEY 1101658 | 882 | 439 |  | Tier 2
35151051 | PMO-POLE_IDLE_REMV-11345 BACHELOR VLY*RA | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.095455 | 0.095455 | 0 | 0 | 0.095455 | 0 | 0 | HB | Region 1 - North Coast | Witter Springs | Lake | 39.1944 | -122.9794 | UPPER LAKE 1101412 | UPPER LAKE 1101412 | 2122 | 259
35151070 | STS-COND_IDLE_REMV-10095 MILL ST 1PS/1PW | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.054924 | 0.054924 | 0 | 0.054924 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lower Lake | Lake | 38.9074 | -122.607 | HIGHLANDS 1103CB | HIGHLANDS 1103CB | 1421 | 461 |  | Tier 2
35151071 | STS-COND_IDLE_REMV-17050 MEADOWLARK CT | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.036364 | 0.036364 | 0 | 0.036364 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lower Lake | Lake | 38.9133 | -122.5938 | HIGHLANDS 1103568 | HIGHLANDS 1103568 | 1493 | 212 |  | Tier 2
35151074 | T2-REMV IDLE 7LOCS 18225 MORGAN VLY*KS | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.2964 | 0.2964 | 0 | 0.2964 | 0 | 0 | 0 | HB | Region 1 - North Coast | Lower Lake | Lake | 38.9014 | -122.5754 | HIGHLANDS 1103482 | HIGHLANDS 1103482 | 1426 | 181 |  | Tier 2
35154942 | POLE_BROK_REPL - 38601 JOSE BASIN RD AT | Idle Facilities | 07D | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | FR | Region 5 - Central Valley | Auberry | Fresno | 37.1159 | -119.4487 | AUBERRY 1101R322 | AUBERRY 1101R322 | 1886 | 956 |  | Tier 2
35155226 | STS-OFAC_IDLE_REMV - #1 E/O 152 LA HONDA | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.042045 | 0.042045 | 0 | 0 | 0.042045 | 0 | 0 | PN | Region 3 - Bay Area | La Honda | San Mateo | 37.3547 | -122.2661 | MENLO 1102W80 | MENLO 1102W80 | 1062 | 620 |  | Tier 2
35157244 | STS-MARK_MISS_INST - 5885[SGN]EVERGREEN | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.05303 | 0.05303 | 0 | 0 | 0.05303 | 0 | 0 | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5023 | -119.8278 | MARIPOSA 21019400 | MARIPOSA 21019400 | 705 | 655 |  | Tier 2
35157255 | STS-COND_IDLE_REMV - 22574 ELIZABETH PHO | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.0075758 | 0.0075758 | 0 | 0 | 0.0075758 | 0 | 0 | YO | Region 5 - Central Valley | Sonora | Tuolumne | 38.0323 | -120.2823 | CURTIS 17028000 | CURTIS 17028000 | 871 | 2175 |  | Tier 3
35159821 | STS-COND_IDLE_REMV-1140 TOMALES RD | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SO | Region 1 - North Coast | Petaluma | Sonoma | 38.2553 | -122.8194 | PETALUMA C 1108632 | PETALUMA C 1108632 | 2027 | 888 |  | Tier 2
35159826 | T2 REMV IDLE TX/SVC 35905 HAUSER BRI*PAR | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.015152 | 0.015152 | 0 | 0 | 0.015152 | 0 | 0 | SO | Region 1 - North Coast | Cazadero | Sonoma | 38.5925 | -123.301 | FORT ROSS 1121124 | FORT ROSS 1121124 | 511 | 1022 |  | Tier 2
35162302 | 8/31- STS-COND_IDLE_REMV - 2SW/O 10640 O | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.11629 | 0.11629 | 0 | 0.11629 | 0 | 0 | 0 | NV | Region 2 - North East | Oak Run | Shasta | 40.5988 | -122.1675 | DESCHUTES 11011580 | DESCHUTES 11011580 | 1451 | 375 |  | Tier 2
35162974 | EFC2-INSU_BROK_REPL - 1W/O R/O 4200 PLEA | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.21439 | 0.21439 | 0 | 0.21439 | 0 | 0 | 0 | SI | Region 2 - North East |  |  | 38.9481 | -121.1862 | WISE 1102307494 | WISE 1102307494 | 537 | 528 |  | Tier 2
35174308 | 8/31-FT~STS-OFAC_IDLE_REMV-2S/O 1E/O C/O | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.074432 | 0.074432 | 0 | 0.074432 | 0 | 0 | 0 | NV | Region 2 - North East | Whitmore | Shasta | 40.5867 | -121.935 | WHITMORE 110145262 | WHITMORE 110145262 | 1915 | 685 |  | Tier 2
35176816 | STS_COND_IDLE_REMV-R/O 9650 HWY 193 | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.14299 | 0.14299 | 0 | 0 | 0.14299 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7983 | -120.8166 | PLACERVILLE 210611132 | PLACERVILLE 210611132 | 875 | 1666 |  | Tier 3
35177215 | STS-OFAC_IDLE_REMV_4N/O 3E/O 1S/O C/ | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.22538 | 0.22538 | 0 | 0.22538 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6971 | -122.3392 | STILLWATER 11011320 | STILLWATER 11011320 | 1149 | 1828 |  | Tier 2
35185246 | NR4 B3 REMV IDLE FAC 6 LOC 4100 INAGAHEE | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.32784 | 0.32784 | 0 | 0 | 0.32784 | 0 | 0 | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.741 | -120.6011 | APPLE HILL 110413512 | APPLE HILL 110413512 | 89 | 1284 |  | Tier 3
35186134 | 8/31-REMV IDLE 3 LOCS 10985 HOUGHTON RAN | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.060417 | 0.060417 | 0 | 0 | 0.060417 | 0 | 0 | SI | Region 2 - North East | Penn Valley | Nevada | 39.2099 | -121.2252 | NARROWS 2105CB | NARROWS 2105CB | 1065 | 730 |  | Tier 2
35186848 | STS-GUY_MISS_INST - 794 TRINKLING CREEK | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.027083 | 0.027083 | 0 | 0 | 0.027083 | 0 | 0 | CC | Region 4 - Central Coast | Felton | Santa Cruz | 37.1074 | -122.0559 | CAMP EVERS 210511010 | CAMP EVERS 210511010 | 375 | 2039 |  | Tier 3
35198772 | STS-OFAC_IDLE_REMV - 7119-7185 CA-140MID | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.27652 | 0.27652 | 0 | 0 | 0.27652 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5917 | -119.9612 | MARIPOSA 210110240 | MARIPOSA 210110240 | 1009 | 679 |  | Tier 2
35198773 | STS-OFAC_IDLE_REMV - 7119-7185 CA-140MID | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 1.3098 | 1.3098 | 0 | 0 | 1.3098 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5963 | -119.9586 | MARIPOSA 210110240 | MARIPOSA 210110240 | 1009 | 679 |  | Tier 2
35198774 | STS-OFAC_IDLE_REMV - 7119-7185 CA-140MID | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.012311 | 0.012311 | 0 | 0 | 0.012311 | 0 | 0 | YO | Region 5 - Central Valley |  |  | 37.599 | -119.956 | MARIPOSA 210110240 | MARIPOSA 210110240 | 1009 | 679
35198775 | STS-OFAC_IDLE_REMV - 7119-7185 CA-140MID | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 1.3222 | 1.3222 | 0 | 0 | 1.3222 | 0 | 0 | YO | Region 5 - Central Valley |  |  | 37.5992 | -119.9562 | MARIPOSA 210110240 | MARIPOSA 210110240 | 1009 | 679
35198776 | STS-OFAC_IDLE_REMV - BRICEBURG SUBSTATIO | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.051136 | 0.051136 | 0 | 0 | 0.051136 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5956 | -119.9593 | MARIPOSA 210110240 | MARIPOSA 210110240 | 1009 | 679 |  | Tier 2
35198777 | STS-OFAC_IDLE_REMV - 7119-7185 CA-140MID | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.19223 | 0.19223 | 0 | 0 | 0.19223 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.6003 | -119.9578 | MARIPOSA 210110240 | MARIPOSA 210110240 | 1009 | 679 |  | Tier 3
35198778 | STS-OFAC_IDLE_REMV - 7119-7185 CA-140MID | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.15625 | 0.15625 | 0 | 0 | 0.15625 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.6006 | -119.9583 | MARIPOSA 210110240 | MARIPOSA 210110240 | 1009 | 679 |  | Tier 3
35198779 | STS-OFAC_IDLE_REMV - 7119-7185 CA-140MID | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.019886 | 0.019886 | 0 | 0 | 0.019886 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.602 | -119.9604 | MARIPOSA 210110240 | MARIPOSA 210110240 | 1009 | 679 |  | Tier 3
35198780 | STS-OFAC_IDLE_REMV - 7119-7185 CA-140MID | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.19242 | 0.19242 | 0 | 0 | 0.19242 | 0 | 0 | YO | Region 5 - Central Valley |  |  | 37.6022 | -119.9607 | MARIPOSA 210110240 | MARIPOSA 210110240 | 1009 | 679
35198781 | STS-OFAC_IDLE_REMV - 7119-7185 CA-140MID | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.13068 | 0.13068 | 0 | 0 | 0.13068 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.6041 | -119.9635 | MARIPOSA 210110240 | MARIPOSA 210110240 | 1009 | 679 |  | Tier 3
35198782 | STS-OFAC_IDLE_REMV - 7119-7185 CA-140MID | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.035985 | 0.035985 | 0 | 0 | 0.035985 | 0 | 0 | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.6033 | -119.9656 | MARIPOSA 210110240 | MARIPOSA 210110240 | 1009 | 679 |  | Tier 2
35199323 | XSTS-POLE_IDLE_REMV-102 MT HAMILTON RD Q | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.15814 | 0.15814 | 0 | 0.15814 | 0 | 0 | 0 | SJ | Region 4 - Central Coast |  |  | 37.3476 | -121.7276 | SWIFT 2110XR254 | SWIFT 2110XR254 | 1003 | 1228 |  | Tier 2
35204796 | FT-COND_IDLE_REMV-X/ST FEATHER FALLS SC | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.073106 | 0.073106 | 0 | 0.073106 | 0 | 0 | 0 | NV | Region 2 - North East |  |  | 39.5923 | -121.2637 | KANAKA 11011034 | KANAKA 11011034 | 201 | 1566 |  | Tier 3
35204801 | FT~STS-TRAN_IDLE_REMV-4 SPANS W/O15625 | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.30114 | 0.30114 | 0 | 0.30114 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3129 | -122.458 | COTTONWOOD 11011610 | COTTONWOOD 11011610 | 1340 | 470 |  | Tier 2
35204803 | DR~STS-POLE_IDLE_REMV-16250 BOWMAN RD | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.099621 | 0.099621 | 0 | 0 | 0 | 0.099621 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.3153 | -122.4504 | COTTONWOOD 11011610 | COTTONWOOD 11011610 | 1340 | 470 |  | Tier 2
35204806 | DR~STS-TRAN_IDLE_REMV-1P N/O 10133 FRAZ | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.044318 | 0.044318 | 0 | 0 | 0.044318 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.5829 | -122.3124 | OREGON TRAIL 1104CB | OREGON TRAIL 1104CB | 1577 | 255 |  | Tier 2
35204808 | DR-POLE_IDLE_REMV-BEHIND 10979 SPARROW | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.015152 | 0.015152 | 0 | 0.015152 | 0 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.6076 | -122.2417 | DESCHUTES 11041370 | DESCHUTES 11041370 | 1954 | 100 |  | Tier 2
35204810 | FT-COND_IDLE_REMV-11459 ANGLER LN | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | NV | Region 2 - North East | Whitmore | Shasta | 40.6225 | -121.9928 | WHITMORE 110145262 | WHITMORE 110145262 | 1915 | 685 |  | Tier 2
35204811 | FT~STS-POLE_IDL_REMV-4 POLES S/O CO#2413 | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.125 | 0.125 | 0 | 0 | 0 | 0.125 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6558 | -122.4231 | OREGON TRAIL 11021584 | OREGON TRAIL 11021584 | 1331 | 1773 |  | Tier 2
35204813 | FT-COND_IDLE_REMV-FERN RD -1 POLE N/O S | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.06875 | 0.06875 | 0 | 0 | 0.06875 | 0 | 0 | NV | Region 2 - North East | Whitmore | Shasta | 40.6847 | -121.9506 | WHITMORE 11011598 | WHITMORE 11011598 | 294 | 820 |  | Tier 3
35204814 | DR-COND_IDLE_REMV-14820 FERN RD | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.21023 | 0.21023 | 0 | 0 | 0.21023 | 0 | 0 | NV | Region 2 - North East | Whitmore | Shasta | 40.6613 | -121.9488 | WHITMORE 11011598 | WHITMORE 11011598 | 294 | 820 |  | Tier 3
35204816 | FT-COND_IDLE_REMV-28490 OAK RUN RD TO F | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.096402 | 0.096402 | 0 | 0.096402 | 0 | 0 | 0 | NV | Region 2 - North East |  |  | 40.7029 | -122.0395 | DESCHUTES 11011580 | DESCHUTES 11011580 | 1451 | 375 |  | Tier 3
35204820 | DRSTS-COND_IDLE_REMV-DRY CREEK RD (JONES | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.058523 | 0.058523 | 0 | 0.058523 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.6835 | -122.2448 | STILLWATER 11021644 | STILLWATER 11021644 | 1604 | 628 |  | Tier 2
35204821 | FT~STS-POLE_IDLE_REMV-5138 POPLAR AVE | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.10985 | 0.10985 | 0 | 0.10985 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.4356 | -122.3978 | JESSUP 11023105 | JESSUP 11023105 | 605 | 89 |  | Tier 2
35204826 | FT STS-OFAC_IDLE_REMV-BRIGHTPATHLN1ST TA | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.083333 | 0.083333 | 0 | 0.083333 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4283 | -122.4024 | JESSUP 110296554 | JESSUP 110296554 | 653 | 267 |  | Tier 2
35204830 | FT~STS-OFAC_IDLE_REMV-22249 ELK TRAIL | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.045833 | 0.045833 | 0 | 0 | 0.045833 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.7017 | -122.2323 | STILLWATER 11021466 | STILLWATER 11021466 | 1677 | 1251 |  | Tier 2
35204831 | DR~STS-OFAC_IDLE_REMV-LE CLAIRE RD | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.16439 | 0.16439 | 0 | 0.16439 | 0 | 0 | 0 | NV | Region 2 - North East | Redding | Shasta | 40.417 | -122.2059 | STILLWATER 1101CB | STILLWATER 1101CB | 1698 | 1737 |  | Tier 2
35204835 | DR~STS-COND_IDLE_REMV-INDIAN AVENUE | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.18636 | 0.18636 | 0 | 0 | 0.18636 | 0 | 0 | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.8363 | -121.9171 | CEDAR CREEK 11011664 | CEDAR CREEK 11011664 | 1544 | 281 |  | Tier 2
35204861 | FT~STS-COND_IDLE_REMV-4443 RHONDA RD | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.037121 | 0.037121 | 0 | 0.037121 | 0 | 0 | 0 | NV | Region 2 - North East | Anderson | Shasta | 40.4185 | -122.2842 | ANDERSON 11012051 | ANDERSON 11011752 | 2161 | 465 |  | Tier 2
35204865 | FT~STS-COND_IDLE_REMV-18195 WILLOW DR | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.0125 | 0.0125 | 0 | 0.0125 | 0 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.322 | -122.3459 | COTTONWOOD 11031348 | COTTONWOOD 11031348 | 1507 | 540 |  | Tier 2
35204871 | FT-COND_IDLE_REMV-7 SPANS S/ C/O 3503 | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.045455 | 0.045455 | 0 | 0 | 0.045455 | 0 | 0 | NV | Region 2 - North East | Oak Run | Shasta | 40.6765 | -122.0257 | DESCHUTES 11011580 | DESCHUTES 11011580 | 1451 | 375 |  | Tier 2
35204874 | DR~STS-COND_IDL_REM-A/F 1135 MOCKING BRD | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | HB | Region 1 - North Coast | Lakeport | Lake | 39.1397 | -122.9117 | LUCERNE 11031280 | LUCERNE 11031280 | 2282 | 512
35204877 | DR -COND_IDLE_REMV-R/O 544 FIRCREST DR | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | HB | Region 1 - North Coast | Calpella | Mendocino | 39.117 | -123.2145 | UKIAH 1113CB | UKIAH 1113548420 | 3251 | 1369 |  | Tier 2
35204902 | FT~STS-COND_IDLE_REMV-4506 PANORAMA PNT | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | NV | Region 2 - North East |  |  | 40.4192 | -122.2548 | PANORAMA 1101CB | PANORAMA 1101CB | 2425 | 1038 |  | Tier 2
35205028 | DR-STS-COND_IDLE_REMV-7140KELSEYCREEKDRI | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | HB | Region 1 - North Coast |  |  | 38.5713 | -122.5037 | KONOCTI 110264664 | KONOCTI 110264664 | 441 | 168 |  | Tier 2
35205036 | DR-COND_IDLE_REMV-2135 S AUBURN ST | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.062311 | 0.062311 | 0 | 0.062311 | 0 | 0 | 0 | SI | Region 2 - North East |  |  | 39.0804 | -120.9594 | SHADY GLEN 110151696 | SHADY GLEN 110151696 | 763 | 1581 |  | Tier 2
35205037 | DR~STS-COND_IDLE_REMV-22735 CANYON WY | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.082576 | 0.082576 | 0 | 0 | 0.082576 | 0 | 0 | SI | Region 2 - North East | Colfax | Placer | 39.0698 | -120.9575 | WEIMAR 11012058 | WEIMAR 11012058 | 1472 | 1379 |  | Tier 2
35205038 | DR-OFAC_IDLE_REMV-745 HWY 174 | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.10227 | 0.10227 | 0 | 0 | 0.10227 | 0 | 0 | SI | Region 2 - North East | Colfax | Placer | 39.1065 | -120.9503 | SHADY GLEN 1102CB | SHADY GLEN 1102CB | 299 | 1829 |  | Tier 2
35205100 | FT~STS-COND_IDLE_REMV-1593 BEALS RD | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.081818 | 0.081818 | 0 | 0.081818 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7473 | -120.8611 | DIAMOND SPRINGS 11039432 | DIAMOND SPRINGS 11039432 | 1080 | 1699 |  | Tier 2
35205102 | DR-COND_IDLE_REMV-1W/O 1S/O 1226 FRE | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.10985 | 0.10985 | 0 | 0 | 0.10985 | 0 | 0 | HB | Region 1 - North Coast | Eureka | Humboldt | 40.7703 | -124.0748 | HARRIS 1109700 | HARRIS 1109355914 | 2817 | 2462 |  | Tier 2
35205112 | FT-COND_IDLE_REMV-6746 OLIVERA LN | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.095644 | 0.095644 | 0 | 0.095644 | 0 | 0 | 0 | NV | Region 2 - North East | Marysville | Yuba | 39.3394 | -121.3619 | BANGOR 11011958 | BANGOR 11011958 | 1022 | 785 |  | Tier 2
35205116 | FT~STS-COND_IDLE_REMV-INTERSECTN BAKERS | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.017045 | 0.017045 | 0 | 0 | 0.017045 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7943 | -120.9196 | SHINGLE SPRINGS 210911092 | SHINGLE SPRINGS 210911092 | 1314 | 2116 |  | Tier 2
35205118 | DR~STS-COND_IDLE_REMV-2710 LITTLE OAK LN | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East | Rescue | El Dorado | 38.6944 | -120.9795 | SHINGLE SPRINGS 210519522 | SHINGLE SPRINGS 210519522 | 216 | 240 |  | Tier 3
35206049 | STS-COND_IDLE_REMV - WARREN FREEWAY OAKL | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.12917 | 0.12917 | 0 | 0.12917 | 0 | 0 | 0 | EB | Region 3 - Bay Area | Oakland | Alameda | 37.846 | -122.2281 | OAKLAND K 1103CB | OAKLAND K 1103CB | 2428 | 3435 |  | Tier 2
35206236 | STS-COND_IDLE_REMV-11259 FRESCO ST | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.11212 | 0.11212 | 0 | 0 | 0.11212 | 0 | 0 | CC | Region 4 - Central Coast | Felton | Santa Cruz | 37.1115 | -122.0491 | CAMP EVERS 210510294 | CAMP EVERS 210510294 | 131 | 2167 |  | Tier 3
35207802 | STS-COND_IDLE_REMV-MCARTHUR RD | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.013636 | 0.013636 | 0 | 0.013636 | 0 | 0 | 0 | NV | Region 2 - North East |  |  | 41.1141 | -121.5688 | MC ARTHUR 11011490 | MC ARTHUR 11011490 | 2607 | 1181
35207810 | DR-STS-POLE_IDLE_REMV-624 BPONDEROSATOEO | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.1678 | 0.1678 | 0 | 0 | 0.1678 | 0 | 0 | NV | Region 2 - North East | Chico | Butte | 39.9085 | -121.7172 | SYCAMORE CREEK 11112014 | SYCAMORE CREEK 11112014 | 1157 | 1137 |  | Tier 3
35207931 | 8/31-FT-COND_IDLE_REMV-6612 GIBSON CANYO | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.042424 | 0.042424 | 0 | 0.042424 | 0 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3788 | -121.9971 | VACAVILLE 1111CB | VACAVILLE 1111CB | 1453 | 500
35207960 | 8/31-DR STSCOND_IDLE_REMV-4881 FRISBY 1S | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.21136 | 0.21136 | 0 | 0.21136 | 0 | 0 | 0 | NV | Region 2 - North East | Oak Run | Shasta | 40.7827 | -121.8951 | CEDAR CREEK 1101CB | CEDAR CREEK 1101CB | 1749 | 392 |  | Tier 3
35207961 | STS-COND_IDLE_REMV - 2 NW/O POLLARD DR W | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.017803 | 0.017803 | 0 | 0.017803 | 0 | 0 | 0 | NV | Region 2 - North East |  |  | 40.6645 | -121.9503 | WHITMORE 11011598 | WHITMORE 11011598 | 294 | 820 |  | Tier 2
35207962 | FT-COND_IDLE_REMV-13080 FERN RD EAST | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | NV | Region 2 - North East | Whitmore | Shasta | 40.6574 | -121.8953 | WHITMORE 11011594 | WHITMORE 11011594 | 1390 | 678 |  | Tier 2
35207963 | DR-COND_IDLE_REMV-30759 WHITMORE | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.042992 | 0.042992 | 0 | 0 | 0.042992 | 0 | 0 | NV | Region 2 - North East | Whitmore | Shasta | 40.6302 | -121.9057 | WHITMORE 1101CB | WHITMORE 1101CB | 2126 | 1481 |  | Tier 2
35207965 | 8/31-DRSTS-COND_IDLE_REMV-2 W/O 3516 HAR | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.061364 | 0.061364 | 0 | 0 | 0.061364 | 0 | 0 | NV | Region 2 - North East |  |  | 40.3884 | -122.9869 | WILDWOOD 11011576 | WILDWOOD 11011576 | 1744 | 1125 |  | Tier 2
35207972 | FH-POLE_IDLE_REMV - 4646 LOTUS RD 3PLE | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7407 | -120.9325 | SHINGLE SPRINGS 21099372 | SHINGLE SPRINGS 21099372 | 472 | 227 |  | Tier 3
35207979 | STS-COND_IDLE_REMV - 1N/O 1244 CROW HAVE | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East | Colfax | Placer | 39.0948 | -120.9699 | SHADY GLEN 110132726 | SHADY GLEN 110132726 | 1475 | 2201 |  | Tier 2
35208004 | STS-COND_IDLE_REMV - 8080 KING RD R/O HO | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East | Loomis | Placer | 38.8236 | -121.1523 | PENRYN 1107346 | PENRYN 1107346 | 1770 | 1538 |  | Tier 2
35208005 | DR~STS-FAC_IDL_REM-17262 DONN LN.2PN PVT | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.10833 | 0.10833 | 0 | 0 | 0.10833 | 0 | 0 | NV | Region 2 - North East | Bella Vista | Shasta | 40.79 | -121.9593 | CEDAR CREEK 11011608 | CEDAR CREEK 11011608 | 1838 | 768 |  | Tier 2
35208006 | FT~STS-COND_IDLE_REMV-A/F MEADOW VIEW | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.017614 | 0.017614 | 0 | 0 | 0.017614 | 0 | 0 | SI | Region 2 - North East | Rough And Ready | Nevada | 39.2362 | -121.1552 | NARROWS 21052216 | NARROWS 21052216 | 752 | 737 |  | Tier 2
35208010 | COND_IDLE_REMV-405 DUTCH RAVINE RD | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East | Newcastle | Placer | 38.8801 | -121.1684 | PENRYN 11051342 | PENRYN 11051342 | 645 | 1016 |  | Tier 2
35208012 | FT~STS-COND_IDLE_REMV-10139 CLARK RANCH | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.1697 | 0.1697 | 0 | 0 | 0.1697 | 0 | 0 | SA | Region 2 - North East | Dobbins | Yuba | 39.399 | -121.2354 | DOBBINS 11011264 | DOBBINS 11011264 | 957 | 650 |  | Tier 2
35208016 | 8/31-FT~STS-POLE_IDLE_REM-LOOP RD BANGOR | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.058712 | 0.058712 | 0 | 0 | 0.058712 | 0 | 0 | SA | Region 2 - North East | Marysville | Yuba | 39.3171 | -121.4154 | BANGOR 110182350 | BANGOR 110182350 | 1019 | 363 |  | Tier 2
35208019 | DR~STS-COND_IDLE_REM-2S/O 16490 BLUE OAK | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.037121 | 0.037121 | 0 | 0 | 0.037121 | 0 | 0 | NV | Region 2 - North East | Cottonwood | Shasta | 40.2984 | -122.4261 | COTTONWOOD 11011610 | COTTONWOOD 11011610 | 1340 | 470 |  | Tier 2
35208021 | DR-COND_IDLE_REMV-3628 GATES CANYON RD | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.20739 | 0.20739 | 0 | 0 | 0.20739 | 0 | 0 | SA | Region 2 - North East | Vacaville | Solano | 38.3755 | -122.036 | VACAVILLE 11088762 | VACAVILLE 11088762 | 1395 | 64 |  | Tier 2
35208023 | T2/T3-STS-COND_IDLE_REMV-14461 S LINE RD | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.037311 | 0.037311 | 0 | 0.037311 | 0 | 0 | 0 | NV | Region 2 - North East | Whitmore | Shasta | 40.7054 | -121.9102 | WHITMORE 11011598 | WHITMORE 11011598 | 294 | 820 |  | Tier 3
35208024 | 8/31-DR~STS-COND_IDLE_REMV-12486 PLEASAN | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.1286 | 0.1286 | 0 | 0 | 0.1286 | 0 | 0 | SI | Region 2 - North East | Penn Valley | Nevada | 39.2337 | -121.2208 | NARROWS 21022718 | NARROWS 21022718 | 2074 | 1812 |  | Tier 2
35208030 | 8/31-FTSTS-COND_IDLE_REMV-1/P S/O SERV P | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.016667 | 0.016667 | 0 | 0.016667 | 0 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7675 | -120.9539 | SHINGLE SPRINGS 210913322 | SHINGLE SPRINGS 210913322 | 1005 | 1018 |  | Tier 3
35208036 | COND_IDLE_REMV-14511 MERRIAM RD | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.073485 | 0.073485 | 0 | 0 | 0.073485 | 0 | 0 | SA | Region 2 - North East | Dobbins | Yuba | 39.3802 | -121.2071 | DOBBINS 11011264 | DOBBINS 11011264 | 957 | 650 |  | Tier 3
35208044 | 8/31-STS-COND_IDLE_REMV-16091 INDIANA RD | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.20871 | 0.20871 | 0 | 0.20871 | 0 | 0 | 0 | SA | Region 2 - North East | Dobbins | Yuba | 39.4093 | -121.2213 | DOBBINS 11011264 | DOBBINS 11011264 | 957 | 650 |  | Tier 3
35208045 | 8/31-FT-COND_IDLE_REMV-W/O 1053 DONKEY L | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.11155 | 0.11155 | 0 | 0.11155 | 0 | 0 | 0 | SI | Region 2 - North East | Rescue | El Dorado | 38.7609 | -121.0101 | CLARKSVILLE 210413352 | CLARKSVILLE 210413352 | 238 | 586 |  | Tier 3
35208046 | STS-COND_IDLE_REMV-MAIDU TR | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SA | Region 2 - North East | Dobbins | Yuba | 39.3754 | -121.2247 | DOBBINS 11011264 | DOBBINS 11011264 | 957 | 650 |  | Tier 2
35208047 | FT-COND_IDLE_REMV-9775 EVANS WY | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.02178 | 0.02178 | 0 | 0 | 0.02178 | 0 | 0 | SA | Region 2 - North East | Dobbins | Yuba | 39.3775 | -121.249 | DOBBINS 11011808 | DOBBINS 11011808 | 1564 | 193 |  | Tier 2
35208050 | 8/31-STS-COND_IDLE_REMV-POLE 4 SPANS N/O | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.0094697 | 0.0094697 | 0 | 0.0094697 | 0 | 0 | 0 | SI | Region 2 - North East | Norden | Nevada | 39.3238 | -120.3444 | SUMMIT 110147786 | SUMMIT 110147786 | 2571 | 294 |  | Tier 2
35208054 | STS-COND_IDLE_REMV-BAYNE RD | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.14867 | 0.14867 | 0 | 0 | 0.14867 | 0 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7975 | -120.8281 | PLACERVILLE 210611132 | PLACERVILLE 210611132 | 875 | 1666 |  | Tier 2
35208064 | FT-COND_IDLE_REMV-879 OLD TOOL BRIDGE R | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.042614 | 0.042614 | 0 | 0 | 0.042614 | 0 | 0 | SI | Region 2 - North East | Alleghany | Sierra | 39.544 | -120.8671 | ALLEGHANY 1101806 | ALLEGHANY 1101806 | 127 | 1446 |  | Tier 3
35208066 | REMV IDLE FAC 7528 DESCHUTES RD | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.14205 | 0.14205 | 0 | 0 | 0.14205 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.5062 | -122.2412 | DESCHUTES 11049718 | DESCHUTES 11049718 | 1758 | 48 |  | Tier 2
35208069 | DR-POLE_IDLE_REMV - #3W ON LINE @ R/O 2 | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East | Placerville | El Dorado | 38.7701 | -120.5996 | EL DORADO PH 21026645 | EL DORADO PH 21026645 | 109 | 2469 |  | Tier 3
35208071 | DR-COND_IDLE_REMV-19828 WOODPECKER RAVI | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1654 | -121.0157 | BRUNSWICK 11062416 | BRUNSWICK 11062416 | 863 | 1638 |  | Tier 3
35208072 | DR STS-OFAC_IDLE_REMV -2PS3PE OF 465 OA | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.8754 | -121.2618 | LINCOLN 11012310 | LINCOLN 11012310 | 1962 | 1408 |  | Tier 2
35208076 | DRSTS-COND_IDLE_REMV-11100 BRICELANDRD 2 | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.092235 | 0.092235 | 0 | 0 | 0.092235 | 0 | 0 | HB | Region 1 - North Coast | Piercy | Mendocino | 39.9872 | -123.9261 | GARBERVILLE 11026084 | GARBERVILLE 11026084 | 1064 | 1777 |  | Tier 2
35208079 | FT~STS-COND_IDLE_REMV-5670 BASSI RD | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.15057 | 0.15057 | 0 | 0 | 0.15057 | 0 | 0 | SI | Region 2 - North East | Lotus | El Dorado | 38.8055 | -120.9278 | SHINGLE SPRINGS 210911092 | SHINGLE SPRINGS 210911092 | 1314 | 2116 |  | Tier 2
35208093 | STS-POLE_IDLE_REMV - 11635 N SEIGLER MID | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.034091 | 0.034091 | 0 | 0.034091 | 0 | 0 | 0 | HB | Region 1 - North Coast | Middletown | Lake | 38.8826 | -122.6936 | KONOCTI 110275382 | KONOCTI 110275382 | 387 | 728 |  | Tier 3
35208094 | FT STS-TRAN_IDLE_REMV-2W/O6NW/O 7251 WIL | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | HB | Region 1 - North Coast | Honeydew | Humboldt | 40.168 | -124.086 | GARBERVILLE 110237054 | GARBERVILLE 110237054 | 2218 | 1237 |  | Tier 2
35208096 | 8/31-HOLD REMV IDLE FAC -LONGVALLEY *KS | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.20663 | 0.20663 | 0 | 0 | 0.20663 | 0 | 0 | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0679 | -122.6917 | REDBUD 1101708166 | REDBUD 1101708166 | 407 | 345 |  | Tier 3
35208097 | 8/31-REMV IDLE 19824 MORGAN HOLD FOR 10J | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.017045 | 0.017045 | 0 | 0 | 0.017045 | 0 | 0 | HB | Region 1 - North Coast | Lower Lake | Lake | 38.8928 | -122.5438 | HIGHLANDS 1103482 | HIGHLANDS 1103482 | 1426 | 181 |  | Tier 2
35211204 | FT-COND_IDLE_REMV-15960 LE TOURNEAU LN | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1411 | -121.0815 | GRASS VALLEY 11032180 | GRASS VALLEY 11032180 | 1000 | 524 |  | Tier 2
35211210 | DR-COND_IDLE_REMV-3205 CLOVER VALLEY RD | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.11364 | 0.11364 | 0 | 0.11364 | 0 | 0 | 0 | SI | Region 2 - North East | Loomis | Placer | 38.8277 | -121.225 | PENRYN 110651674 | PENRYN 1106212772 | 3087 | 385 |  | Tier 2
35211211 | FT-COND_IDLE_REMV-3201 BUZZARDS ROOST R | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.15701 | 0.15701 | 0 | 0.15701 | 0 | 0 | 0 | NV | Region 2 - North East |  |  | 39.7283 | -121.524 | CLARK ROAD 110290548 | CLARK ROAD 110290548 | 811 | 1578 |  | Tier 3
35211212 | DR-COND_IDLE_REMV-17480 WOLF MOUNTAIN R | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.073864 | 0.073864 | 0 | 0.073864 | 0 | 0 | 0 | SI | Region 2 - North East | Grass Valley | Nevada | 39.1376 | -121.1011 | GRASS VALLEY 11032180 | GRASS VALLEY 11032180 | 1000 | 524 |  | Tier 2
35211225 | DR-COND_IDLE_REMV-11762 MCELROY LN | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East |  |  | 40.6294 | -122.3938 | OREGON TRAIL 110249144 | OREGON TRAIL 110249144 | 1646 | 968 |  | Tier 2
35211230 | DRCOND_IDLE_REMV-5726 EVERGLADE | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.061174 | 0.061174 | 0 | 0 | 0.061174 | 0 | 0 | SA | Region 2 - North East |  |  | 39.2454 | -121.3993 | BROWNS VALLEY 110193870 | BROWNS VALLEY 110193870 | 1545 | 774
35211232 | DR-COND_IDLE_REMV-25090 OAKHURST RD | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0.056818 | 0 | 0 | 0 | SI | Region 2 - North East |  |  | 39.0129 | -121.1047
35211234 | DR STS-COND_IDLE_REMV-BOWMANLAKERD(SEE N | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.15928 | 0.15928 | 0 | 0 | 0.15928 | 0 | 0 | SI | Region 2 - North East |  |  | 39.3057 | -120.6766 | SPAULDING 1101578852 | SPAULDING 1101578852 | 2630 | 1563 |  | Tier 2
35211237 | COND_IDLE_REMV-2607 CHILES POPE VALL | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | NB | Region 1 - North Coast |  |  | 38.5195 | -122.361 | SILVERADO 210234959 | SILVERADO 210234959 | 910 | 579 |  | Tier 3
35211247 | FT-COND_IDLE_REMV-2/P/SO 5817 @ 7TH ST | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.022727 | 0.022727 | 0 | 0.022727 | 0 | 0 | 0 | NB | Region 1 - North Coast | Novato | Marin | 38.1168 | -122.5786 | STAFFORD 11011298 | STAFFORD 1101803535 | 3608 | 3255 |  | Tier 2
35211249 | DR-FT-COND_IDLE_REMV-RITTER ROAD | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | NV | Region 2 - North East |  |  | 41.0969 | -121.5541 | MC ARTHUR 11011490 | MC ARTHUR 11011490 | 2607 | 1181 |  | Tier 2
35211254 | DR~STS-OFAC_IDLE_REM-11226 DESCHUTES RD | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.030114 | 0.030114 | 0 | 0 | 0 | 0.030114 | 0 | NV | Region 2 - North East |  |  | 40.6177 | -122.2349 | DESCHUTES 11041370 | DESCHUTES 11041370 | 1954 | 100 |  | Tier 2
35211257 | FT STS-COND_IDLEREMV-F/O15565 37THAVE 1/ | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | HB | Region 1 - North Coast |  |  | 38.9487 | -122.6207 | HIGHLANDS 110448262 | HIGHLANDS 110448262 | 1266 | 3295 |  | Tier 2
35211260 | FT-POLE_IDLE_REMV - 5960 HWY 49 AUBURN | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.036553 | 0.036553 | 0 | 0 | 0.036553 | 0 | 0 | SI | Region 2 - North East | Auburn | Placer | 38.9957 | -121.1091 | BELL 11082202 | BELL 11082202 | 1264 | 118 |  | Tier 2
35211261 | DR~STS-COND_IDLE_REMV-4244 WILFERN RD | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | NV | Region 2 - North East |  |  | 39.7853 | -121.4957 | BIG BEND 1101641808 | BIG BEND 1101641808 | 973 | 1608 |  | Tier 2
35211263 | REMV IDLE SEC/ANCH 11951 BEST LN | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | NV | Region 2 - North East |  |  | 40.6357 | -122.2644 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 |  | Tier 2
35211265 | DR-COND_IDLE_REMV-14438 MAGNOLIA RD | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.16837 | 0.16837 | 0 | 0.16837 | 0 | 0 | 0 | SI | Region 2 - North East |  |  | 39.0585 | -121.0274 | HIGGINS 11102408 | HIGGINS 1110166282 | 2757 | 1259 |  | Tier 2
35211266 | STS-COND_IDLE_REMV-NORTH OF HWY 128 | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SA | Region 2 - North East |  |  | 38.5178 | -122.1024 | PUTAH CREEK 110264044 | PUTAH CREEK 110264044 | 747 | 529 |  | Tier 2
35211284 | DR~STS-COND_IDL_REMV-3778 MANZANITA /1PW | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | HB | Region 1 - North Coast |  |  | 39.1229 | -122.8417 | LUCERNE 1103630 | LUCERNE 1103630 | 1357 | 1639
35211297 | DR~STS-COND_IDLE_REMV-2000 PONDEROSA WY | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.15682 | 0.15682 | 0 | 0 | 0.15682 | 0 | 0 | SI | Region 2 - North East |  |  | 39.02 | -120.944 | WEIMAR 11012084 | WEIMAR 11012084 | 1414 | 1801 |  | Tier 2
35211354 | FT-COND_IDLE_REMV-4 W/O R/O 20666 US HW | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.065909 | 0.065909 | 0 | 0.065909 | 0 | 0 | 0 | SI | Region 2 - North East |  |  | 38.8238 | -120.0492 | ECHO SUMMIT 1101344250 | ECHO SUMMIT 1101344250 | 2252 | 2461 |  | Tier 2
35211357 | FT-COND_IDLE_REMV-12434 WOLF RD | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.037879 | 0.037879 | 0 | 0.037879 | 0 | 0 | 0 | SI | Region 2 - North East |  |  | 39.0665 | -121.1227 | HIGGINS 1109CB | HIGGINS 1109CB | 1411 | 182 |  | Tier 2
35211601 | FT~STS-COND_IDLE_REMV -10955 ROUGH & REA | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.035606 | 0.035606 | 0 | 0 | 0.035606 | 0 | 0 | SI | Region 2 - North East |  |  | 39.2305 | -121.1568 | NARROWS 21052216 | NARROWS 21052216 | 752 | 737 |  | Tier 2
35211618 | FT~STS-COND_IDLE_REMV-SCHMIDT CT | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East |  |  | 39.2154 | -121.2723 | NARROWS 210551582 | NARROWS 210551582 | 2150 | 582 |  | Tier 2
35211630 | DR~COND_IDLE_REMV-18929 NEW YORK FLAT | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.060038 | 0.060038 | 0 | 0 | 0.060038 | 0 | 0 | NV | Region 2 - North East |  |  | 39.5106 | -121.2749 | KANAKA 110165606 | KANAKA 110165606 | 77 | 1201 |  | Tier 3
35211639 | DR~STS-COND_IDLE_REMV-12621 ALLISON RANC | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East |  |  | 39.19 | -121.0698 | GRASS VALLEY 11012208 | GRASS VALLEY 11012208 | 1278 | 1973 |  | Tier 2
35211641 | FT STS-COND_IDLE_REMV-NW/C/O29THAVEAND E | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.00625 | 0.00625 | 0 | 0.00625 | 0 | 0 | 0 | HB | Region 1 - North Coast |  |  | 38.9434 | -122.6176 | HIGHLANDS 1104CB | HIGHLANDS 1104CB | 1735 | 3243 |  | Tier 2
35211643 | DR-STS-COND_IDLE_REMV-6 PLS W/O 11554 ON | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | NV | Region 2 - North East |  |  | 40.6201 | -122.4408 | OREGON TRAIL 11031500 | OREGON TRAIL 11031500 | 1153 | 981 |  | Tier 2
35211645 | DR~STS-POLE_IDLE_REMV BTWN 1860 & 1850 | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East |  |  | 38.6054 | -120.8111 | DIAMOND SPRINGS 11057722 | DIAMOND SPRINGS 11057722 | 1084 | 649 |  | Tier 2
35211655 | DR-COND_IDLE_REMV-7253 N STATE ST | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | HB | Region 1 - North Coast |  |  | 39.2475 | -123.2092 | CALPELLA 11011204 | CALPELLA 1101619542 | 3241 | 1432 |  | Tier 2
35211656 | DR-COND_IDLE_REMV-23406 PURDON RD | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.019318 | 0.019318 | 0 | 0.019318 | 0 | 0 | 0 | SI | Region 2 - North East |  |  | 39.3517 | -121.061 | COLUMBIA HILL 1101CB | COLUMBIA HILL 1101CB | 785 | 1077 |  | Tier 3
35211657 | DR~STS-COND_IDLE_REMV-1540 DOG BAR RD | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East |  |  | 39.0636 | -121.0002 | WEIMAR 11012058 | WEIMAR 11012058 | 1472 | 1379 |  | Tier 2
35211659 | DR-COND_IDLE_REMV-14932 MOONSHINE RD | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.030303 | 0.030303 | 0 | 0 | 0.030303 | 0 | 0 | SI | Region 2 - North East |  |  | 39.3897 | -121.0964 | COLUMBIA HILL 1101764 | COLUMBIA HILL 1101764 | 95 | 1590 |  | Tier 3
35211671 | DR~STS-COND_IDLE_REMV-1120 NATUREWOOD DR | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East |  |  | 39.0289 | -121.0039 | WEIMAR 11022038 | WEIMAR 11022038 | 1908 | 2536
35211679 | DR-STS-COND_IDLE_REMV-10344 PEARDON RD | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East |  |  | 39.2098 | -121.2734 | NARROWS 210551582 | NARROWS 210551582 | 2150 | 582 |  | Tier 2
35211682 | DR~STS-COND_IDLE_REMV-OLD ORGN TRL N/ BE | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | NV | Region 2 - North East |  |  | 40.3745 | -122.3202 | STILLWATER 1102CB | STILLWATER 1102CB | 1317 | 502 |  | Tier 2
35211692 | STS-COND_IDLE_REMV-5081 OLD FRENCH TOWN | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.0094697 | 0.0094697 | 0 | 0 | 0.0094697 | 0 | 0 | SI | Region 2 - North East |  |  | 38.6613 | -120.8935 | DIAMOND SPRINGS 110518935 | DIAMOND SPRINGS 110518935 | 432 | 1031 |  | Tier 3
35211694 | DR~STS-COND_IDLE_REMV-1 SW/O 22319 ELK | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | NV | Region 2 - North East |  |  | 40.6995 | -122.2298 | STILLWATER 11021466 | STILLWATER 11021466 | 1677 | 1251 |  | Tier 2
35211698 | DR-COND_IDLE_REMV-CO POLE #85883 | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.074811 | 0.074811 | 0 | 0 | 0.074811 | 0 | 0 | NV | Region 2 - North East |  |  | 40.4475 | -122.3152 | JESSUP 1102CB | JESSUP 1102158468 | 3084 | 3114 |  | Tier 2
35211742 | FT-COND_IDLE_REMV-6250 BELLA VISTA PL | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.093561 | 0.093561 | 0 | 0 | 0.093561 | 0 | 0 | SI | Region 2 - North East |  |  | 39.0002 | -121.1184 | BELL 11082202 | BELL 11082202 | 1264 | 118 |  | Tier 2
35211743 | FT~STS-COND_IDLE_REMV-1S/O 1W/O 3881 WEL | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East | Shingle Springs | El Dorado | 38.6789 | -120.9472 | SHINGLE SPRINGS 2109CB | SHINGLE SPRINGS 2109CB | 742 | 1240 |  | Tier 3
35211749 | DR~STS-COND_IDLE_REMV-CHRISTIAN | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | NV | Region 2 - North East |  |  | 40.7013 | -122.28 | STILLWATER 1102CB | STILLWATER 1102CB | 1317 | 502 |  | Tier 2
35211753 | FT~STS-COND_IDL_REM-10937-10963 IRON MON | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | NV | Region 2 - North East |  |  | 40.6073 | -122.4623 | KESWICK 11011590 | KESWICK 11011590 | 859 | 848 |  | Tier 3
35211755 | FT-COND_IDLE_REMV-LOS VERJELES | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.10473 | 0.10473 | 0 | 0 | 0.10473 | 0 | 0 | NV | Region 2 - North East |  |  | 39.3512 | -121.3671 | BANGOR 11011958 | BANGOR 11011958 | 1022 | 785 |  | Tier 2
35211757 | DR-COND_IDLE_REMV-13716 LOS VERJELES | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SA | Region 2 - North East |  |  | 39.3561 | -121.3774 | BANGOR 110131502 | BANGOR 110131502 | 1616 | 225 |  | Tier 2
35211797 | DR~STS-POLE_IDLE_REMV-1E/O 10555 WALKER | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.045455 | 0.045455 | 0 | 0 | 0.045455 | 0 | 0 | SI | Region 2 - North East |  |  | 39.2207 | -121.081 | BRUNSWICK 11103907 | BRUNSWICK 11103907 | 864 | 2928 |  | Tier 2
35211802 | DR~STS-OFAC_IDLE_REMV-1E/O 4491 FORNI RD | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.055871 | 0.055871 | 0 | 0 | 0.055871 | 0 | 0 | SI | Region 2 - North East |  |  | 38.6879 | -120.8408 | DIAMOND SPRINGS 1104CB | DIAMOND SPRINGS 1104CB | 1172 | 2036 |  | Tier 3
35215883 | STS-POLE_OVRL_TEST - 45886 CHUCKWAGON RD | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.10303 | 0.10303 | 0 | 0 | 0.10303 | 0 | 0 | FR | Region 5 - Central Valley |  |  | 36.6914 | -119.1303 | SAND CREEK 110345190 | SAND CREEK 110345190 | 1301 | 195 |  | Tier 2
35215885 | 8/31-STS-OFAC_IDLE_DEEN - R/O 15499 SAND | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.010417 | 0.010417 | 0 | 0.010417 | 0 | 0 | 0 | FR | Region 5 - Central Valley |  |  | 36.6268 | -119.2447 | REEDLEY 1104274990 | REEDLEY 1104887932 | 2945 | 1431 |  | Tier 2
35215897 | STS-OFAC_IDLE_DEEN - 51016 GREENHILL LNS | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.020265 | 0.020265 | 0 | 0 | 0.020265 | 0 | 0 | FR | Region 5 - Central Valley |  |  | 36.678 | -119.0974 | SAND CREEK 110345190 | SAND CREEK 110345190 | 1301 | 195 |  | Tier 2
35215920 | STS-OFAC_IDLE_DEEN - 3121[HSE]OAK GROVE | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.042614 | 0.042614 | 0 | 0.042614 | 0 | 0 | 0 | YO | Region 5 - Central Valley |  |  | 37.3468 | -119.8762 | MARIPOSA 210237288 | MARIPOSA 210237288 | 850 | 379 |  | Tier 2
35215933 | XT2/T3-STS-GUY_LOOS_ADJU - 1SE/O 47155 A | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.03125 | 0.03125 | 0 | 0 | 0.03125 | 0 | 0 | CC | Region 4 - Central Coast |  |  | 36.2404 | -121.4345 | LOS OSITOS 21033010 | LOS OSITOS 21033010 | 1434 | 1509 |  | Tier 2
35215935 | STS-GUY_LOOS_ADJU - 1NE/O R/O 26201 JEAN | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.027273 | 0.027273 | 0 | 0.027273 | 0 | 0 | 0 | CC | Region 4 - Central Coast |  |  | 36.5446 | -121.7573 | DEL MONTE 21042760 | DEL MONTE 21042760 | 826 | 2444 |  | Tier 2
35217564 | DR-COND_IDLE_REMV - 1PWO 11188 TOWNSHIP | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SA | Region 2 - North East |  |  | 39.2871 | -121.3534 | NARROWS 21011202 | NARROWS 21011202 | 1107 | 758 |  | Tier 2
35217573 | DR~STS-COND_IDLE_REMV 16023 LITTLE VALEY | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East |  |  | 39.1372 | -121.0692 | HIGGINS 110332120 | HIGGINS 110332120 | 1120 | 1178 |  | Tier 2
35217667 | DR~STS-POLE_IDLE_REM-1S/O 10W/O 30520 MO | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.43371 | 0.43371 | 0 | 0 | 0.43371 | 0 | 0 | NV | Region 2 - North East |  |  | 40.5881 | -121.9244 | WHITMORE 110145262 | WHITMORE 110145262 | 1915 | 685 |  | Tier 2
35217676 | DRSTS-COND_IDLE_REMV-1NE/O C/O EMERALD W | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0.056818 | 0 | 0 | 0 | NV | Region 2 - North East |  |  | 40.6262 | -121.9196
35217691 | STS-COND_IDLE_REMV - C/O WINDY POINT RD/ | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | NV | Region 2 - North East |  |  | 40.8329 | -121.9285 | CEDAR CREEK 11011664 | CEDAR CREEK 11011664 | 1544 | 281 |  | Tier 2
35217692 | STS-COND_IDLE_REMV - S/P @ 4E/O 2S/O 158 | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | NV | Region 2 - North East | Red Bluff | Tehama | 40.0866 | -122.4534 | TYLER 110585132 | TYLER 110585132 | 1354 | 383 |  | Tier 2
35221199 | RCQ-STS-COND_IDLE_REMV116BROOKSDR | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | NV | Region 2 - North East |  |  | 39.8872 | -121.7521 | SYCAMORE CREEK 11112014 | SYCAMORE CREEK 11112014 | 1157 | 1137 |  | Tier 2
35221246 | DR~T2 REMV IDLE POLE 6 N/O #1 E/0 ENT | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | HB | Region 1 - North Coast |  |  | 38.9373 | -123.309 | PHILO 11013700 | PHILO 11013700 | 1905 | 417 |  | Tier 2
35221249 | DR~STS-COND_IDLE_REMV-1/N/O/AT 908 OREGN | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | NV | Region 2 - North East |  |  | 39.5519 | -121.5068 | CLARK ROAD 110292622 | CLARK ROAD 110292622 | 1774 | 771 |  | Tier 2
35221620 | STS-COND_IDLE_REMV-12345 HERITAGE WAY | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.042614 | 0.042614 | 0 | 0 | 0.042614 | 0 | 0 | SJ | Region 4 - Central Coast |  |  | 37.0534 | -121.6625 | MORGAN HILL 2105XR176 | MORGAN HILL 2105XR176 | 1018 | 854 |  | Tier 2
35221621 | STS-COND_IDLE_REMV-21578 ALMA CT | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.018939 | 0.018939 | 0 | 0 | 0.018939 | 0 | 0 | DA | Region 4 - Central Coast |  |  | 37.1532 | -121.985 | LOS GATOS 1106LA42 | LOS GATOS 1106LA42 | 904 | 3015 |  | Tier 3
35221646 | STS-COND_IDLE_REMV - 57902 HARTLAND CHRI | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | FR | Region 5 - Central Valley |  |  | 36.6566 | -118.958 | SAND CREEK 11037110 | SAND CREEK 11037110 | 2230 | 636 |  | Tier 2
35221652 | STS-COND_IDLE_REMV - 31016 HWY 168/3PSE. | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | FR | Region 5 - Central Valley |  |  | 37.033 | -119.5165 | AUBERRY 1102R902 | AUBERRY 1102R902 | 1688 | 213 |  | Tier 2
35221657 | STS-COND_IDLE_REMV - #1N 8689 E MURRAY C | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.066288 | 0.066288 | 0 | 0 | 0.066288 | 0 | 0 | ST | Region 5 - Central Valley |  |  | 38.236 | -120.5465 | CALAVERAS CEMENT 110180930 | CALAVERAS CEMENT 110180930 | 1126 | 1652 |  | Tier 2
35221659 | STS-COND_IDLE_REMV-1N/O 2W/O 10835 WATER | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | ST | Region 5 - Central Valley |  |  | 38.3666 | -120.9293 | CLAY 110113442 | CLAY 110113442 | 1269 | 744 |  | Tier 2
35221671 | 8/31- STS-COND_IDLE_REMV-46565 DRY CREEK | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.048864 | 0.048864 | 0 | 0.048864 | 0 | 0 | 0 | FR | Region 5 - Central Valley |  |  | 36.5921 | -119.0181 | SAND CREEK 11037110 | SAND CREEK 11037110 | 2230 | 636 |  | Tier 2
35221679 | 8/31-STS-COND_IDLE_REMV-HWY 41/KENNEDY 4 | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.019129 | 0.019129 | 0 | 0.019129 | 0 | 0 | 0 | YO | Region 5 - Central Valley |  |  | 37.2126 | -119.7088 | COARSEGOLD 2103CB | COARSEGOLD 2103CB | 1498 | 164 |  | Tier 2
35221700 | 8/31-STS-COND_IDLE_REMV-2 N/O BRANDY WIN | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.082955 | 0.082955 | 0 | 0.082955 | 0 | 0 | 0 | YO | Region 5 - Central Valley |  |  | 37.3193 | -119.6477 | OAKHURST 110210100 | OAKHURST 110210100 | 1337 | 796 |  | Tier 2
35221706 | 8/31-STS-COND_IDLE_REMV - 49250 STAGECOA | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.035795 | 0.035795 | 0 | 0.035795 | 0 | 0 | 0 | FR | Region 5 - Central Valley |  |  | 36.6138 | -118.9939 | SAND CREEK 11037110 | SAND CREEK 11037110 | 2230 | 636 |  | Tier 2
35221710 | STS-COND_IDLE_REMV-5572 WHITLOCK 1/P/S/O | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.040152 | 0.040152 | 0 | 0 | 0.040152 | 0 | 0 | YO | Region 5 - Central Valley |  |  | 37.5058 | -120.0009 | MARIPOSA 2101CB | MARIPOSA 2101CB | 2081 | 57 |  | Tier 2
35221715 | T2/T3-STS-COND_IDLE_REMV-20599 KINGS CT | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.041288 | 0.041288 | 0 | 0 | 0.041288 | 0 | 0 | YO | Region 5 - Central Valley |  |  | 37.9963 | -120.2637 | CURTIS 17058170 | CURTIS 17058170 | 1094 | 1770 |  | Tier 2
35221744 | 8/31-STS-COND_IDLE_REMV-5800 ILLILOUETTE | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.1447 | 0.1447 | 0 | 0.1447 | 0 | 0 | 0 | YO | Region 5 - Central Valley |  |  | 37.4892 | -119.838 | MARIPOSA 21019400 | MARIPOSA 21019400 | 705 | 655 |  | Tier 2
35221748 | STS-COND_IDLE_REMV-#1S 9743 MOUNTAIN RAN | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | ST | Region 5 - Central Valley | Mountain Ranch | Calaveras | 38.2433 | -120.5168 | CALAVERAS CEMENT 11014786 | CALAVERAS CEMENT 11014786 | 1115 | 804 |  | Tier 2
35221753 | STS-COND_IDLE_REMV-1051' S/W SUN RD - 99 | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | ST | Region 5 - Central Valley | Mountain Ranch | Calaveras | 38.2319 | -120.5127 | CALAVERAS CEMENT 11014786 | CALAVERAS CEMENT 11014786 | 1115 | 804
35221764 | STS-COND_IDLE_REMV-2S/O/1SW/O/A/F 1001 S | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.15473 | 0.15473 | 0 | 0 | 0.15473 | 0 | 0 | ST | Region 5 - Central Valley | Jackson | Amador | 38.3524 | -120.7929 | MARTELL 110368192 | MARTELL 110368192 | 1932 | 1330 |  | Tier 2
35221765 | STS-COND_IDLE_REMV - 1504 PINE DR ARNOLD | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | ST | Region 5 - Central Valley |  |  | 38.2531 | -120.3592 | STANISLAUS 170237278 | STANISLAUS 170237278 | 82 | 2810
35221768 | 8/31- STS-COND_IDLE_REMV-OBYRNES FERRY R | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.19811 | 0.19811 | 0 | 0.19811 | 0 | 0 | 0 | ST | Region 5 - Central Valley | Copperopolis | Calaveras | 37.9033 | -120.5655 | PEORIA 1704CB | PEORIA 1704CB | 2092 | 800 |  | Tier 2
35221770 | STS-COND_IDLE_REMV-15878-15998 WILDCAT R | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | DA | Region 4 - Central Coast |  |  | 37.2371 | -122.0364 | SARATOGA 1107LC12 | SARATOGA 1107LC12 | 865 | 2627 |  | Tier 3
35221807 | STS-COND_IDLE_REMV - 1142 RAILROAD FLAT | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | ST | Region 5 - Central Valley |  |  | 38.3496 | -120.5093 | WEST POINT 11024790 | WEST POINT 11024790 | 136 | 1664 |  | Tier 2
35221808 | STS-POLE_IDLE_REMV - #11S ON LINE @ 9227 | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | ST | Region 5 - Central Valley |  |  | 38.2402 | -120.5497 | CALAVERAS CEMENT 110180930 | CALAVERAS CEMENT 110180930 | 1126 | 1652 |  | Tier 2
35221818 | STS-COND_IDLE_REMV-#2E #2SW ON LINE @ 75 | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.071591 | 0.071591 | 0 | 0 | 0.071591 | 0 | 0 | ST | Region 5 - Central Valley |  |  | 38.2575 | -120.5304 | CALAVERAS CEMENT 110180930 | CALAVERAS CEMENT 110180930 | 1126 | 1652 |  | Tier 2
35221824 | STS-COND_IDLE_REMV-9995 HWY 26 | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.052652 | 0.052652 | 0 | 0 | 0.052652 | 0 | 0 | ST | Region 5 - Central Valley |  |  | 38.3044 | -120.672 | CALAVERAS CEMENT 11012646 | CALAVERAS CEMENT 11012646 | 2720 | 1889 |  | Tier 2
35221828 | OCLH T2/T3-COND_IDLE_REMV-8746 DOSTER RD | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.030303 | 0.030303 | 0 | 0.030303 | 0 | 0 | 0 | ST | Region 5 - Central Valley |  |  | 38.2335 | -120.6033 | CALAVERAS CEMENT 110147968 | CALAVERAS CEMENT 110147968 | 1380 | 1941 |  | Tier 2
35221833 | STS-COND_IDLE_REMV - A/F 13265 UPPER SHA | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | YO | Region 5 - Central Valley |  |  | 38.0399 | -120.3544 | CURTIS 17048140 | CURTIS 17048140 | 178 | 1604
35221984 | STS-COND_IDLE_REMV - 23384 RANCHO CASTAN | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.033712 | 0.033712 | 0 | 0.033712 | 0 | 0 | 0 | YO | Region 5 - Central Valley |  |  | 38.0479 | -120.3495 | CURTIS 17048140 | CURTIS 17048140 | 178 | 1604 |  | Tier 3
35221997 | T2/T3-X STS-COND_IDLE_REMV-#1W ON LINE @ | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.043561 | 0.043561 | 0 | 0 | 0.043561 | 0 | 0 | ST | Region 5 - Central Valley |  |  | 38.355 | -120.5021 | WEST POINT 11024790 | WEST POINT 11024790 | 136 | 1664 |  | Tier 2
35221998 | STS-COND_IDLE_REMV - #2N ON LINE @ R/O 1 | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.10985 | 0.10985 | 0 | 0 | 0.10985 | 0 | 0 | ST | Region 5 - Central Valley |  |  | 38.3547 | -120.504 | WEST POINT 11024790 | WEST POINT 11024790 | 136 | 1664 |  | Tier 2
35222060 | OCLHT2/T3-COND_IDLE_REMV-R/O 5767 HWY 49 | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.0094697 | 0.0094697 | 0 | 0.0094697 | 0 | 0 | 0 | ST | Region 5 - Central Valley |  |  | 38.2736 | -120.7144 | CALAVERAS CEMENT 110111188 | CALAVERAS CEMENT 110111188 | 1852 | 1534 |  | Tier 2
35222065 | OCGC STS-COND_IDLE_REMV-1704 BORO CT | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.022538 | 0.022538 | 0 | 0.022538 | 0 | 0 | 0 | ST | Region 5 - Central Valley |  |  | 38.2594 | -120.3203 | STANISLAUS 170275348 | STANISLAUS 170275348 | 49 | 2878 |  | Tier 3
35222066 | STS-COND_IDLE_REMV-#2S ON LINE A/F 1844 | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.03447 | 0.03447 | 0 | 0.03447 | 0 | 0 | 0 | ST | Region 5 - Central Valley |  |  | 38.3382 | -120.5537 | WEST POINT 11024790 | WEST POINT 11024790 | 136 | 1664 |  | Tier 3
35222069 | OCGC 8/31-STS-COND_IDLE_REMV-A/F 3225 | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.067045 | 0.067045 | 0 | 0.067045 | 0 | 0 | 0 | ST | Region 5 - Central Valley |  |  | 38.17 | -120.6304 | CALAVERAS CEMENT 110111236 | CALAVERAS CEMENT 110111236 | 2012 | 886 |  | Tier 2
35222072 | STS-COND_IDLE_REMV-A/F 7288 RAILROAD FLA | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.027652 | 0.027652 | 0 | 0 | 0.027652 | 0 | 0 | ST | Region 5 - Central Valley |  |  | 38.2442 | -120.5169 | CALAVERAS CEMENT 11014786 | CALAVERAS CEMENT 11014786 | 1115 | 804 |  | Tier 3
35222073 | STS-COND_IDLE_REMV-@ GATE 9677 MOUNTAIN | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | ST | Region 5 - Central Valley |  |  | 38.243 | -120.5179 | CALAVERAS CEMENT 11014786 | CALAVERAS CEMENT 11014786 | 1115 | 804 |  | Tier 2
35223204 | FT~T2-COND_IDLE_REMV - 3883 LOVALL VALL | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SO | Region 1 - North Coast | Sonoma | Sonoma | 38.3002 | -122.4061 | SONOMA 1105404 | SONOMA 1105229588 | 3033 | 720 |  | Tier 2
35223207 | DR~STS-COND_IDLE_REMV - N/E/C OF SNEATH | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | PN | Region 3 - Bay Area | San Bruno | San Mateo | 37.6247 | -122.4471 | SNEATH LANE 1106CB | SNEATH LANE 1106CB | 2371 | 2588 |  | Tier 2
35223212 | T2~COND_IDLE_REMV 4490 D ST EXT | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.033144 | 0.033144 | 0 | 0.033144 | 0 | 0 | 0 | SO | Region 1 - North Coast | Petaluma | Sonoma | 38.1996 | -122.6507 | PETALUMA C 1109128 | PETALUMA C 1109128 | 1014 | 381 |  | Tier 2
35223225 | FT~STS-COND_IDLE_REMV-W/S TOMALES RD 1/P | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.11269 | 0.11269 | 0 | 0 | 0.11269 | 0 | 0 | SO | Region 1 - North Coast | Petaluma | Sonoma | 38.2558 | -122.8152 | PETALUMA C 1108632 | PETALUMA C 1108632 | 2027 | 888 |  | Tier 2
35223226 | STS-COND_IDLE_REMV-2/P/N/E OF SW 6243 | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | EB | Region 3 - Bay Area | Oakland | Alameda | 37.8467 | -122.2284 | OAKLAND K 1103CB | OAKLAND K 1103CB | 2428 | 3435
35223241 | DR~STS-COND_IDLE_REMV-R/O 5500 ALPINE R | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | PN | Region 3 - Bay Area | Portola Valley | San Mateo | 37.3559 | -122.2178 | MENLO 11028896 | MENLO 11028896 | 570 | 1917 |  | Tier 2
35223248 | STS-COND_IDLE_REMV-5535 ARROYO RD | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.12879 | 0.12879 | 0 | 0.12879 | 0 | 0 | 0 | MI | Region 3 - Bay Area | Livermore | Alameda | 37.6185 | -121.7511 | LAS POSITAS 2108MR182 | LAS POSITAS 2108MR182 | 1515 | 803 |  | Tier 2
35223249 | DR~T2 COND_IDLE_REMV - 155 TWIN BRIDGE | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SO | Region 1 - North Coast |  |  | 38.2596 | -122.8553 | COTATI 1103132 | COTATI 1103132 | 529 | 965 |  | Tier 2
35223261 | STS-STS - S PARK RD & WILLOWS CAMP | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.039583 | 0.039583 | 0 | 0.039583 | 0 | 0 | 0 | EB | Region 3 - Bay Area |  |  | 37.8838 | -122.2232 | EL CERRITO G 1105BR160 | EL CERRITO G 1105BR160 | 1104 | 2792 |  | Tier 3
35223265 | 8/31-STS-COND_IDLE_REMV-BLACK DIAMOND TR | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 1.2379 | 1.2379 | 0 | 1.2379 | 0 | 0 | 0 | DI | Region 3 - Bay Area |  |  | 37.93 | -121.8694 | CLAYTON 2213CB | CLAYTON 2213CB | 2870 | 1367 |  | Tier 2
35223268 | DR~T3-COND_IDLE_REMV-CAMPAGNA LN | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SO | Region 1 - North Coast |  |  | 38.4376 | -122.5622 | DUNBAR 1101234 | DUNBAR 1101234 | 2094 | 2556
35223270 | DR~T3 REMV IDLE TX POLE 7205 GEYSER RD | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SO | Region 1 - North Coast | Geyserville | Sonoma | 38.7534 | -122.8254 | GEYSERVILLE 1102484 | GEYSERVILLE 1102484 | 1225 | 668 |  | Tier 3
35223288 | STS-COND_IDLE_REMV-7000 PINEHAVEN ROAD | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.034091 | 0.034091 | 0 | 0.034091 | 0 | 0 | 0 | EB | Region 3 - Bay Area |  |  | 37.8467 | -122.2121 | OAKLAND K 1102CR014 | OAKLAND K 1102CR014 | 734 | 2897 |  | Tier 3
35224438 | STS-COND_IDLE_REMV-SUDDEN RANCH AT RR TR | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.017235 | 0.017235 | 0 | 0 | 0.017235 | 0 | 0 | LP | Region 4 - Central Coast |  |  | 34.5387 | -120.5367 | CABRILLO 1104Y24 | CABRILLO 1104Y24 | 1061 | 949 |  | Tier 2
35224439 | *8/31STS-COND_IDLE_REMV-1020 BALLARD CYN | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.15777 | 0.15777 | 0 | 0.15777 | 0 | 0 | 0 | LP | Region 4 - Central Coast |  |  | 34.6194 | -120.1477 | BUELLTON 1102Y50 | BUELLTON 1102Y50 | 523 | 269 |  | Tier 2
35224441 | REMV IDLE LINE: 6477 HAPPY CYN, S.YNEZ | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.19697 | 0.19697 | 0 | 0 | 0.19697 | 0 | 0 | LP | Region 4 - Central Coast |  |  | 34.6256 | -119.9856 | SANTA YNEZ 1104Y66 | SANTA YNEZ 1104Y66 | 431 | 153 |  | Tier 2
35224443 | STS-COND_IDLE_REMV-JONATA PARK RD | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.096402 | 0.096402 | 0 | 0.096402 | 0 | 0 | 0 | LP | Region 4 - Central Coast |  |  | 34.6316 | -120.1869 | BUELLTON 1101Y26 | BUELLTON 1101Y26 | 1586 | 517 |  | Tier 2
35224444 | STS-COND_IDLE_REMV-ACROSS ST FROM 1271 S | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.32481 | 0.32481 | 0 | 0.32481 | 0 | 0 | 0 | LP | Region 4 - Central Coast |  |  | 34.6221 | -120.4538 | CABRILLO 1104Y24 | CABRILLO 1104Y24 | 1061 | 949 |  | Tier 2
35224451 | STS-POLE_IDLE_REMV - #1 S/O #1 W/O SURF | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.013258 | 0.013258 | 0 | 0 | 0.013258 | 0 | 0 | LP | Region 4 - Central Coast |  |  | 34.6842 | -120.6039 | CABRILLO 1104Y22 | CABRILLO 1104Y22 | 2132 | 1500 |  | Tier 2
35224519 | T2/T3-XSTS-COND_IDLE_REMV - 13052 CIENEG | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.0094697 | 0.0094697 | 0 | 0.0094697 | 0 | 0 | 0 | CC | Region 4 - Central Coast |  |  | 36.715 | -121.3471 | HOLLISTER 21054048 | HOLLISTER 21054048 | 1678 | 2382 |  | Tier 2
35224730 | STS-COND_IDLE_REMV - AF DW 99 MTN VIEW R | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.056818 | 0.056818 | 0 | 0.056818 | 0 | 0 | 0 | CC | Region 4 - Central Coast |  |  | 37.0548 | -121.9756 | [5 empty] | Tier 3
35224887 | STS-COND_IDLE_REMV - 2E/O 207 PUNTA DEL | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.018939 | 0.018939 | 0 | 0 | 0.018939 | 0 | 0 | CC | Region 4 - Central Coast |  |  | 36.4698 | -121.7262 | LAURELES 11112028 | LAURELES 11112028 | 2036 | 3199
35224892 | STS-POLE_IDLE_REMV - 1/W/O GRANITE ROCK | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | CC | Region 4 - Central Coast |  |  | 36.5946 | -121.9212 | VIEJO 2202CB | VIEJO 2202CB | 684 | 3216 |  | Tier 2
35224893 | STS-COND_IDLE_REMV - #1 N/O CARMEL VLY R | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.045455 | 0.045455 | 0 | 0 | 0.045455 | 0 | 0 | CC | Region 4 - Central Coast |  |  | 36.5434 | -121.8847 | HATTON 110137088 | HATTON 110137088 | 2198 | 2887 |  | Tier 2
35224941 | STS-COND_IDLE_REMV-R/O 2PE 1PS/O #67 BLU | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | LP | Region 4 - Central Coast |  |  | 35.3592 | -120.8268 | MORRO BAY 1102CB | MORRO BAY 1102CB | 2119 | 2399 |  | Tier 2
35224942 | STS-COND_IDLE_REMV-3\P\S\O 2500 LOOMIS S | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.010417 | 0.010417 | 0 | 0 | 0.010417 | 0 | 0 | LP | Region 4 - Central Coast |  |  | 35.2953 | -120.6391 | SAN LUIS OBISPO 1101483444 | SAN LUIS OBISPO 1101483444 | 2731 | 2146 |  | Tier 2
35224943 | STS-COND_IDLE_REMV-1/P/S/O/2/P/W/O 1255 | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.011364 | 0.011364 | 0 | 0 | 0.011364 | 0 | 0 | LP | Region 4 - Central Coast |  |  | 35.3118 | -120.6247 | SAN LUIS OBISPO 1101V12 | SAN LUIS OBISPO 1101V12 | 1100 | 1506 |  | Tier 2
35224947 | STS-COND_IDLE_REMV-1\P\N\O\2212 STENNER | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | LP | Region 4 - Central Coast |  |  | 35.3267 | -120.6707 | GOLDTREE 1105CB | GOLDTREE 1105CB | 919 | 1104 |  | Tier 2
35225003 | +8/31-STS-COND_IDLE_REMV - 11011 BOBCAT | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.015909 | 0.015909 | 0 | 0.015909 | 0 | 0 | 0 | LP | Region 4 - Central Coast |  |  | 35.1101 | -120.3814 | SANTA MARIA 1108M80 | SANTA MARIA 1108M80 | 930 | 1109 |  | Tier 2
35225004 | STS-POLE_IDLE_REMV - 6996 MONTE DR-2/P/W | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | LP | Region 4 - Central Coast |  |  | 35.1852 | -120.7001 | SAN LUIS OBISPO 1107V02 | SAN LUIS OBISPO 1107V02 | 1026 | 1317 |  | Tier 2
35225006 | +STS-TRAN_IDLE_REMV - 6996 MONTE DR-2/P/ | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.050947 | 0.050947 | 0 | 0.050947 | 0 | 0 | 0 | LP | Region 4 - Central Coast |  |  | 35.1864 | -120.6989 | SAN LUIS OBISPO 1107V02 | SAN LUIS OBISPO 1107V02 | 1026 | 1317 |  | Tier 2
35225009 | STS-COND_IDLE_REMV - 6/P/NW/1/P/E/O 2289 | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.08428 | 0.08428 | 0 | 0 | 0.08428 | 0 | 0 | LP | Region 4 - Central Coast |  |  | 35.3247 | -120.811 | MORRO BAY 1102W34 | MORRO BAY 1102W34 | 2657 | 2590 |  | Tier 2
35225011 | STS-COND_IDLE_REMV - AT 1580 PRESTON ST | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | LP | Region 4 - Central Coast |  |  | 35.5451 | -121.0716 | PERRY 1101V74 | PERRY 1101V74 | 1509 | 2433 |  | Tier 2
35225015 | STS-COND_IDLE_REMV-SAN SIMEON PEIR PARKI | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.038636 | 0.038636 | 0 | 0.038636 | 0 | 0 | 0 | LP | Region 4 - Central Coast |  |  | 35.644 | -121.1867 | CAMBRIA 1101858200 | CAMBRIA 1101858200 | 3395 | 1620 |  | Tier 2
35225016 | REMOVE IDLE P0LES, 2020 STERLING LN, SLO | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.32614 | 0.32614 | 0 | 0 | 0.32614 | 0 | 0 | LP | Region 4 - Central Coast |  |  | 35.2563 | -120.7044 | FOOTHILL 110299432 | FOOTHILL 110299432 | 1745 | 2765 |  | Tier 2
35225253 | STS-COND_IDLE_REMV-214 TABERNACLE DRIVE | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.028409 | 0.028409 | 0 | 0 | 0.028409 | 0 | 0 | CC | Region 4 - Central Coast |  |  | 37.0632 | -122.0333 | CAMP EVERS 21045096 | CAMP EVERS 21045096 | 372 | 2474
35225318 | +STS-COND_IDLE_REMV-CAT CANYON RD | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.094697 | 0.094697 | 0 | 0 | 0.094697 | 0 | 0 | LP | Region 4 - Central Coast |  |  | 34.8125 | -120.2732 | PALMER 1101M84 | PALMER 1101M84 | 2018 | 256 |  | Tier 2
35225319 | +STS-COND_IDLE_REMV-CAT CANYON RD. | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.094697 | 0.094697 | 0 | 0.094697 | 0 | 0 | 0 | LP | Region 4 - Central Coast |  |  | 34.8138 | -120.2786 | PALMER 1101M84 | PALMER 1101M84 | 2018 | 256 |  | Tier 2
35225344 | STS-COND_IDLE_REMV- | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.020833 | 0.020833 | 0 | 0 | 0.020833 | 0 | 0 | LP | Region 4 - Central Coast |  |  | 35.5343 | -120.7753 | TEMPLETON 2110R90 | TEMPLETON 2110901690 | 841 | 1098
35225347 | STS-COND_IDLE_REMV-679 HWY 58 | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.033712 | 0.033712 | 0 | 0 | 0.033712 | 0 | 0 | LP | Region 4 - Central Coast |  |  | 35.4554 | -120.3892 | TEMPLETON 21136055 | TEMPLETON 2113641367 | 3081 | 399 |  | Tier 2
35225404 | STS-COND_IDLE_REMV - 4293 CALF CANYON RD | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.014205 | 0.014205 | 0 | 0 | 0.014205 | 0 | 0 | LP | Region 4 - Central Coast |  |  | 35.4373 | -120.4873 | TEMPLETON 21136055 | TEMPLETON 2113641367 | 3081 | 399 |  | Tier 2
35225409 | 8/31-STS-POLE_IDLE_REMV - 2/P/S/O 5/P/W/ | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.1072 | 0.1072 | 0 | 0.1072 | 0 | 0 | 0 | LP | Region 4 - Central Coast |  |  | 35.5123 | -120.6445 | TEMPLETON 2113A70 | TEMPLETON 2113A70 | 542 | 955 |  | Tier 2
35225423 | STS-TRAN_IDLE_REMV - AT 63122 INDIAN VAL | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.0058712 | 0.0058712 | 0 | 0 | 0.0058712 | 0 | 0 | LP | Region 4 - Central Coast |  |  | 36.0022 | -120.6449 | SAN MIGUEL 1106605393 | SAN MIGUEL 1106605393 | 2710 | 469 |  | Tier 2
35225437 | +8/31-STS-COND_IDLE_REMV-3940 ADELAID | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.034659 | 0.034659 | 0 | 0.034659 | 0 | 0 | 0 | LP | Region 4 - Central Coast |  |  | 35.6608 | -120.7644 | PASO ROBLES 1104R56 | PASO ROBLES 1104R56 | 644 | 251
35225441 | STS-COND_IDLE_REMV-73580 PLEYTO CEMETARY | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | LP | Region 4 - Central Coast |  |  | 35.8652 | -121.0267 | OILFIELDS 1103N48 | OILFIELDS 1103N48 | 1419 | 508 |  | Tier 2
35225462 | STS-COND_IDLE_REMV - 1/S S\O OF 5025 FRE | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.051705 | 0.051705 | 0 | 0.051705 | 0 | 0 | 0 | CC | Region 4 - Central Coast |  |  | 36.9866 | -121.836 | ROB ROY 210410960 | ROB ROY 210410960 | 1381 | 2485 |  | Tier 2
35225467 | STS-COND_IDLE_REMV - 1/P/S/O/587 AVOCADO | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.023674 | 0.023674 | 0 | 0 | 0.023674 | 0 | 0 | CC | Region 4 - Central Coast |  |  | 37.0121 | -121.7963 | ROB ROY 210410298 | ROB ROY 210410298 | 817 | 2387 |  | Tier 2
35225468 | STS-COND_IDLE_REMV - 1/P/N/O/CO/VACA DEL | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | CC | Region 4 - Central Coast |  |  | 37.0299 | -121.8298 | ROB ROY 21045082 | ROB ROY 21045082 | 613 | 2526
35225543 | 8/31-STS-COND_IDLE_REMV-4E/O RD MTN MICR | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.1858 | 0.1858 | 0 | 0.1858 | 0 | 0 | 0 | KE | Region 5 - Central Valley |  |  | 35.502 | -118.8758 | POSO MOUNTAIN 210448268 | POSO MOUNTAIN 210448268 | 2409 | 402 |  | Tier 2
35229381 | STS-COND_IDLE_REMV-HWY 68 | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.12614 | 0.12614 | 0 | 0 | 0.12614 | 0 | 0 | CC | Region 4 - Central Coast |  |  | 36.5936 | -121.9216 | VIEJO 2202CB | VIEJO 2202CB | 684 | 3216 |  | Tier 2
35232678 | STS-COND_IDLE_REMV-3311 UPPER LOPEZ CANY | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.050189 | 0.050189 | 0 | 0 | 0.050189 | 0 | 0 | LP | Region 4 - Central Coast |  |  | 35.2352 | -120.4723 | SAN LUIS OBISPO 11042293 | SAN LUIS OBISPO 1104982992 | 3292 | 1248 |  | Tier 3
35236777 | STS-POLE _OVRL _TEST_R/O 5370 HAWVERS RD | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.0070076 | 0.0070076 | 0 | 0.0070076 | 0 | 0 | 0 | ST | Region 5 - Central Valley |  |  | 38.2544 | -120.6495 | CALAVERAS CEMENT 110147968 | CALAVERAS CEMENT 110147968 | 1380 | 1941
35237026 | DR-STS-COND_IDLE_REMV-S/ENDOFSILVERBRIDG | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.18769 | 0.18769 | 0 | 0 | 0.18769 | 0 | 0 | NV | Region 2 - North East | Palo Cedro | Shasta | 40.5062 | -122.2233 | DESCHUTES 11049718 | DESCHUTES 11049718 | 1758 | 48 |  | Tier 2
35237664 | OCGC8/31-REMV IDLE 9LOCS W/O NOYES RANCH | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.47273 | 0.47273 | 0 | 0.47273 | 0 | 0 | 0 | HB | Region 1 - North Coast |  |  | 38.7703 | -122.5157 | MIDDLETOWN 1103830 | MIDDLETOWN 1103830 | 1322 | 14 |  | Tier 2
35238953 | STS-OFAC_IDLE_REMV - 6445 NORTH VALLEY R | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 4.2356 | 4.2356 | 0 | 4.2356 | 0 | 0 | 0 | NV | Region 2 - North East |  |  | 40.131 | -120.8637 | CRESCENT MILLS 21012562 | CRESCENT MILLS 21012562 | 1950 | 1078 |  | Tier 2
35240792 | *8/31STS-COND_IDLE_REMV-7423 HAPPY CANYO | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.075189 | 0.075189 | 0 | 0.075189 | 0 | 0 | 0 | LP | Region 4 - Central Coast |  |  | 34.6423 | -119.9644 | BIG MEADOWS 21012260 | BIG MEADOWS 21012260 | 1667 | 995 |  | Tier 2
35242267 | STS-COND_IDLE_REMV-27674 DERSCH RD | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.18712 | 0.18712 | 0 | 0.18712 | 0 | 0 | 0 | NV | Region 2 - North East | Shingletown | Shasta | 40.5121 | -122.0332 | DESCHUTES 11011654 | DESCHUTES 11011654 | 1492 | 1086
35242663 | STS-TRAN_IDLE_REMV - R/O 4821 CRYSTAL AI | Idle Facilities | 2AF | DOCC | Post-Construction | 0 | 0 | 0.063636 | 0.063636 | 0 | 0.063636 | 0 | 0 | 0 | YO | Region 5 - Central Valley |  |  | 37.5505 | -119.9509 | MARIPOSA 21018030 | MARIPOSA 2101752630 | 2886 | 700 |  | Tier 2
35242865 | DR~STS-COND_IDLE_REMV-410 STAR HILL RD | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | PN | Region 3 - Bay Area | Redwood City | San Mateo | 37.4119 | -122.3299 | WOODSIDE 11018972 | WOODSIDE 11018972 | 280 | 1376 |  | Tier 3
35243374 | DR~--REMV IDLE 5 LOCS 3560 MONTICELLO R | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.6167 | 0.6167 | 0 | 0 | 0.61667 | 0 | 0 | NB | Region 1 - North Coast |  |  | 38.3601 | -122.1971 | MONTICELLO 11014360 | MONTICELLO 11014360 | 1496 | 757 |  | Tier 2
35243793 | STS-OFAC_IDLE_DEEN - 1 SW/O R/O 4561 FOO | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | NB | Region 1 - North Coast |  |  | 38.5694 | -122.5675 | CALISTOGA 1102634 | CALISTOGA 1102634 | 808 | 1477 |  | Tier 2
35244018 | STS-POLE_IDLE_REMV - 1 W/O 7 S/O 50386 C | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East |  |  | 39.3151 | -120.4573 | TAMARACK 1101CB | TAMARACK 1101CB | 966 | 2630 |  | Tier 2
35244086 | STS-COND_IDLE_REMV - 308 WALL RDNAPA | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | NB | Region 1 - North Coast |  |  | 38.4177 | -122.4763 | PUEBLO 2102792 | PUEBLO 2102792 | 36 | 951 |  | Tier 3
35244102 | STS-COND_IDLE_REMV-12366 LAKEVIEW DR | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | HB | Region 1 - North Coast |  |  | 39.0237 | -122.6803 | REDBUD 1101708166 | REDBUD 1101708166 | 407 | 345 |  | Tier 2
35244105 | DR-COND_IDLE_REMV-20095 HWY 175 | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | HB | Region 1 - North Coast |  |  | 38.7685 | -122.6637 | MIDDLETOWN 1101548 | MIDDLETOWN 1101548 | 26 | 474 |  | Tier 3
35244112 | FT--COND_IDLE_REMV-G/P 4444 COOK RANCH R | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East |  |  | 38.8622 | -120.8038 | PLACERVILLE 21069712 | PLACERVILLE 21069712 | 877 | 1646 |  | Tier 3
35244117 | FT--COND_IDLE_REMV-2S/O 1E/O 41210 SKYLI | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East |  |  | 39.286 | -120.6932 | DRUM 11011602 | DRUM 11011602 | 1033 | 2009 |  | Tier 3
35244145 | STS-COND_IDLE_REMV - R/O 3041 TEXENA CTP | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East |  |  | 38.7308 | -120.7551 | PLACERVILLE 1109CB | PLACERVILLE 1109CB | 2400 | 1761 |  | Tier 2
35244146 | FT-COND_IDLE_REMV-6935-6963 MORNING CAN | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East |  |  | 38.6208 | -120.7257 | APPLE HILL 2102186912 | APPLE HILL 2102186912 | 1223 | 1035 |  | Tier 2
35244147 | FT-COND_IDLE_REMV-5590 PONY EXPRESS TRL | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East | Camino | El Dorado | 38.7497 | -120.6168 | APPLE HILL 110413512 | APPLE HILL 110413512 | 89 | 1284 |  | Tier 3
35244148 | STS-COND_IDLE_REMV-A/F 5509 PONY EXPRESS | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East |  |  | 38.7495 | -120.6171 | APPLE HILL 110413512 | APPLE HILL 110413512 | 89 | 1284 |  | Tier 3
35244149 | DR-COND_IDLE_REMV-D/P AT 4536 STRING CA | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East |  |  | 38.6378 | -120.5347 | EL DORADO PH 210126000 | EL DORADO PH 210126000 | 63 | 2252
35244150 | FT-COND_IDLE_REMV-D/P R/O 19182 GERMAN | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East |  |  | 39.437 | -120.815 | ALLEGHANY 1102CB | ALLEGHANY 1102CB | 162 | 1700 |  | Tier 3
35244151 | FT-POLE_IDLE_REMV - A/F 15E/O A/F 13600 | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | HB | Region 1 - North Coast |  |  | 39.9765 | -123.9409 | GARBERVILLE 11026084 | GARBERVILLE 11026084 | 1064 | 1777 |  | Tier 2
35244154 | STS-COND_IDLE_REMV-18610 KENTUCKY RAVINE | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East |  |  | 39.2714 | -121.1798 | NARROWS 21022220 | NARROWS 21022220 | 1037 | 505 |  | Tier 2
35244155 | STS-COND_IDLE_REMV-1PS/O 5100 RAMBLING R | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East |  |  | 38.6643 | -120.7765 | DIAMOND SPRINGS 110610587 | DIAMOND SPRINGS 110610587 | 1334 | 632 |  | Tier 2
35244157 | FT-COND_IDLE_REMV-5100 RAMBLING RD | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East |  |  | 38.6646 | -120.7765 | DIAMOND SPRINGS 110610587 | DIAMOND SPRINGS 110610587 | 1334 | 632 |  | Tier 2
35244158 | FT-COND_IDLE_REMV-G/P 0FF 2NE/0 0FF 217 | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East | Goodyears Bar | Sierra | 39.5601 | -120.7512 | ALLEGHANY 1101804 | ALLEGHANY 1101804 | 291 | 1753 |  | Tier 3
35244159 | STS-COND_IDLE_REMV-1 E/O R/O 5387 SPRING | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East |  |  | 38.7181 | -120.9127 | DIAMOND SPRINGS 11071402 | DIAMOND SPRINGS 11071402 | 214 | 811 |  | Tier 3
35244167 | FT-COND_IDLE_REMV-WINCHESTER DR | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East | Meadow Vista | Placer | 38.9969 | -121.0593 | HALSEY 11011704 | HALSEY 11011704 | 1207 | 2500 |  | Tier 2
35244172 | STS-POLE_IDLE_REMV-4335 GARDEN BAR RD CO | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.16326 | 0.16326 | 0 | 0 | 0 | 0.16326 | 0 | SI | Region 2 - North East | Lincoln | Placer | 38.9514 | -121.2285 | LINCOLN 11042070 | LINCOLN 11042070 | 584 | 568 |  | Tier 2
35244173 | FT-COND_IDLE_REMV-5260 GRANITE CREEK RD | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East |  |  | 38.7888 | -120.9206 | SHINGLE SPRINGS 210911092 | SHINGLE SPRINGS 210911092 | 1314 | 2116 |  | Tier 2
35244175 | DR-COND_IDLE_REMV - 835 LOTUS RD PLACER | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East |  |  | 38.8083 | -120.8984 | SHINGLE SPRINGS 210981390 | SHINGLE SPRINGS 210981390 | 1288 | 1306 |  | Tier 2
35244181 | FT--COND_IDLE_REMV - 405 DUTCH RAVINE RD | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | SI | Region 2 - North East |  |  | 38.8799 | -121.1687 | PENRYN 11051342 | PENRYN 11051342 | 645 | 1016 |  | Tier 2
35244185 | STS-COND_IDLE_REMV-1E/O 11780 E. BENNETT | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0 | SI | Region 2 - North East |  |  | 39.2161 | -121.0312 | BRUNSWICK 1106CB | BRUNSWICK 1106CB | 254 | 1876 |  | Tier 3
35246795 | STS-TRAN_IDLE_REMV - 23384 RANCHO CASTAN | Idle Facilities | 2AF | MAPP | Post-Construction | 0 | 0 | 0.09053 | 0.09053 | 0 | 0.09053 | 0 | 0 | 0 | YO | Region 5 - Central Valley |  |  | 38.0478 | -120.3492 | CURTIS 17048140 | CURTIS 17048140 | 178 | 1604 |  | Tier 3
35247031 | STS-POLE_IDLE_REMV - 19025 LAUREL DR /1P | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.14981 | 0.14981 | 0 | 0 | 0 | 0.14981 | 0 | DA | Region 4 - Central Coast | Los Gatos | Santa Clara | 37.1963 | -122.0035 | LOS GATOS 1106LB44 | LOS GATOS 1106LB44 | 690 | 1864 |  | Tier 3
35250938 | STS-POLE_IDLE_REMV-4/S/O 1/N/O 4511 BROO | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.22557 | 0.22557 | 0 | 0 | 0.22557 | 0 | 0 | SI | Region 2 - North East |  |  | 38.6385 | -120.9907 | SHINGLE SPRINGS 210851476 | SHINGLE SPRINGS 210851476 | 355 | 424 |  | Tier 3
35253133 | DR STS-POLE_IDLE_REMV-3701 SPRING VALLEY | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.042614 | 0.042614 | 0 | 0 | 0 | 0.042614 | 0 | HB | Region 1 - North Coast |  |  | 39.0878 | -122.6097 | REDBUD 1101323962 | REDBUD 1101323962 | 293 | 423 |  | Tier 3
35254545 | STS-POLE_IDLE_REMV-NACIMIENTO LAKE RD/HE | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.29697 | 0.29697 | 0 | 0 | 0.29697 | 0 | 0 | LP | Region 4 - Central Coast |  |  | 35.7214 | -120.8474 | PASO ROBLES 1103N50 | PASO ROBLES 1103N50 | 465 | 138 |  | Tier 2
35255487 | T2 REMV IDLE FAC 4 LOCS 3220 PASSALACQUA | Idle Facilities | 2AF | PEND | Permitting/Dependency | 0 | 0 | 0.21818 | 0.21818 | 0 | 0 | 0.21818 | 0 | 0 | SO | Region 1 - North Coast |  |  | 38.6489 | -122.8547 | GEYSERVILLE 1102274 | GEYSERVILLE 1102274 | 695 | 940 |  | Tier 2
35255493 | T2/3-POLE_IDLE_REMV-4533 ARROYO RD./2PSE | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.12614 | 0.12614 | 0 | 0 | 0 | 0.12614 | 0 | MI | Region 5 - Central Valley |  |  | 37.6294 | -121.7632 | LAS POSITAS 2108MR182 | LAS POSITAS 2108MR182 | 1515 | 803 |  | Tier 2
35262342 | T2/T3POLE_IDL_REMV+13N/O 4W/O 2400 LUCAS | Idle Facilities | 2AF | FICL | Post-Construction | 0 | 0 | 0.16193 | 0.16193 | 0 | 0.16193 | 0 | 0 | 0 | NB | Region 1 - North Coast |  |  | 38.0537 | -122.5964 | LAS GALLINAS A 1105532 | LAS GALLINAS A 1105532 | 824 | 359 |  | Tier 3
35262343 | STS-POLE_IDLE_REMV-1N/O 22055 TIFFANY LN | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.05303 | 0.05303 | 0 | 0 | 0 | 0.05303 | 0 | NV | Region 2 - North East |  |  | 40.6447 | -122.2377 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 |  | Tier 2
35262344 | DR-STS-POLE_IDLE_REMV-1E/O21623SEVENLAKE | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.049621 | 0.049621 | 0 | 0 | 0 | 0.049621 | 0 | NV | Region 2 - North East |  |  | 0 | 0 | OREGON TRAIL 110335002 | OREGON TRAIL 110335002 | 943 | 49 |  | Tier 2
35262345 | DR-STS-POLE_IDLE_REMV-4S/OR/O3235MEADOW | Idle Facilities | 2AF | CONS | In-Construction* | 0 | 0 | 0.17803 | 0.17803 | 0 | 0 | 0.17803 | 0 | 0 | NV | Region 2 - North East |  |  | 40.3774 | -122.4351 | COTTONWOOD 11021578 | COTTONWOOD 11021578 | 1761 | 554
35262346 | DR-STS-POLE_IDLE_REMV-1S/O17160KESWICKDA | Idle Facilities | 2AF | ADER | Estimating | 0 | 0 | 0.1411 | 0.1411 | 0 | 0 | 0 | 0.1411 | 0 | NV | Region 2 - North East |  |  | 0 | 0 | OREGON TRAIL 11031500 | OREGON TRAIL 11031500 | 1153 | 981 |  | Tier 2
35262347 | STS-POLE_IDLE_REMV - A/F 45771 BUTTERNUT | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.069318 | 0.069318 | 0 | 0 | 0.069318 | 0 | 0 | FR | Region 5 - Central Valley |  |  | 36.6995 | -119.1257 | SAND CREEK 110345190 | SAND CREEK 110345190 | 1301 | 195 |  | Tier 2
35264102 | DRSTS-POLE_IDLE_REMV-1SO 6410 JOHNSTOWN | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.10833 | 0.10833 | 0 | 0 | 0 | 0.10833 | 0 | SI | Region 2 - North East |  |  | 38.8094 | -120.867 | PLACERVILLE 21067522 | PLACERVILLE 21067522 | 959 | 1363 |  | Tier 2
35264103 | T2/T3 POLE_IDLE_REMV-3411 LAWLEY RD R/O | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.13011 | 0.13011 | 0 | 0 | 0.13011 | 0 | 0 | NB | Region 1 - North Coast |  |  | 38.6206 | -122.5857 | CALISTOGA 110189150 | CALISTOGA 110189150 | 905 | 1093 |  | Tier 3
35264104 | DRSTS-OFAC_IDLE_REMV-7NE/O 15921 STATE H | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.10189 | 0.10189 | 0 | 0 | 0 | 0.10189 | 0 | SI | Region 2 - North East |  |  | 39.5593 | -120.8348 | ALLEGHANY 1101806 | ALLEGHANY 1101806 | 127 | 1446 |  | Tier 3
35273069 | DR-STS-IDLE_REMV - 13N/O 10E/O R/O 175 | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.20947 | 0.20947 | 0 | 0 | 0 | 0.20947 | 0 | SI | Region 2 - North East |  |  | 39.1778 | -120.8918 | SHADY GLEN 11022232 | SHADY GLEN 11022232 | 339 | 2022 |  | Tier 3
35274991 | STS-OFAC_IDLE_REMV - 600' S/O SWEDE CREE | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | NV | Region 2 - North East |  |  | 40.6927 | -122.0439 | DESCHUTES 11011580 | DESCHUTES 11011580 | 1451 | 375 |  | Tier 2
35275477 | STS-POLE_IDLE_REMV-3/P/E/5/P/N/O ENT. 34 | Idle Facilities | 2AF | UNSC | Ready for Construction | 0 | 0 | 0.043561 | 0.043561 | 0 | 0 | 0.043561 | 0 | 0 | CC | Region 4 - Central Coast |  |  | 36.4295 | -121.2649 | SOLEDAD 21027048 | SOLEDAD 2102955138 | 3270 | 623 |  | Tier 2
35275478 | STS-POLE_IDLE_REMV-23600 STATE HWY 9 | Idle Facilities | 2AF | ESTS | Estimating | 0 | 0 | 0.15852 | 0.15852 | 0 | 0 | 0 | 0.15852 | 0 | DA | Region 4 - Central Coast |  |  | 37.2476 | -122.0791 | SARATOGA 1107167792 | SARATOGA 1107167792 | 258 | 2354 |  | Tier 3
35275479 | FT-OFAC_IDLE_REMV - #7 ON LINE S/O CO#5 | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | NV | Region 2 - North East |  |  | 40.4236 | -121.8237 | VOLTA 110180454 | VOLTA 110180454 | 1550 | 532 |  | Tier 2
35275960 | FT-OFAC_IDLE_REMV - 4E/O 30146 OAK RUN | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | NV | Region 2 - North East |  |  | 40.7044 | -121.9215 | WHITMORE 11011598 | WHITMORE 11011598 | 294 | 820 |  | Tier 3
35275961 | FT-POLE_IDLE_REMV-13116 A/F GAS POINT R | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.14148 | 0.14148 | 0 | 0 | 0 | 0.14148 | 0 | NV | Region 2 - North East |  |  | 40.4427 | -122.5277 | JESSUP 110141356 | JESSUP 110141356 | 720 | 350 |  | Tier 2
35275962 | STS-COND_IDLE_REMV-1W/O 14508 WONDERLAND | Idle Facilities | 2BF | UNSE | Scoping/Scoped | 0 | 0 | 0.0056818 | 0.0056818 | 0 | 0 | 0 | 0.0056818 | 0 | NV | Region 2 - North East |  |  | 40.7096 | -122.3366 | STILLWATER 11011320 | STILLWATER 11011320 | 1149 | 1828 |  | Tier 2
35275963 | STS-OFAC_IDLE_REMV - 9S/O 5E/O 27223 HWY | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | NV | Region 2 - North East |  |  | 40.51 | -122.0382 | DESCHUTES 11011654 | DESCHUTES 11011654 | 1492 | 1086 |  | Tier 2
35277146 | STS-COND_IDLE_REMV-29040 SNOWHITE RD | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.13598 | 0.13598 | 0 | 0 | 0 | 0.13598 | 0 | YO | Region 5 - Central Valley |  |  | 38.1406 | -120.0571 | SPRING GAP 17029690 | SPRING GAP 17029690 | 151 | 2788 |  | Tier 3
35277147 | STS-POLE_IDLE_REMV-GREELY HILL RD CO#423 | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | YO | Region 5 - Central Valley |  |  | 37.7302 | -120.182 | BEAR VALLEY 210521160 | BEAR VALLEY 210521160 | 1757 | 1019 |  | Tier 2
35277148 | STS-POLE_IDLE_REMV-1PW 1PN 1PW 5219 FOUR | Idle Facilities | 2AF | UNSE | Scoping/Scoped | 0 | 0 | 0.056818 | 0.056818 | 0 | 0 | 0 | 0.056818 | 0 | YO | Region 5 - Central Valley |  |  | 0 | 0 | MARIPOSA 2101309438 | MARIPOSA 2101309438 | 3000 | 605 |  | Tier 2
35080162 | CALPELLA 1101 OH 12,000' RECONDUCTORING | Other | 06H | UNSC | Ready for Construction | 0 | 1.3748 | 0 | 1.3748 | 0 | 0 | 1.3748 | 0 | 0 | HB | Region 1 - North Coast | Redwood Valley | Mendocino | 39.2143 | -123.1889 | Calpella 1101CB | Calpella 1101CB | 2117 | 1256
35146106 | RECONDUCTOR - USASA - PHASE II - SM1104 | Other | 06H | FICL | Post-Construction | 0 | 3.621 | 0 | 3.621 | 0 | 3.621 | 0 | 0 | 0 | LP | Region 4 - Central Coast | Paso Robles | San Luis Obispo | 0 | 0 | SAN MIGUEL 1104N60 | SAN MIGUEL 1104N60 | 2143 | 229
35185022 | INSTALL 3RD PHASE ON ALLEGHANY 1101 | Other | 06I | FICL | Post-Construction | 0 | 0.41705 | 0 | 0.41705 | 0 | 0.41705 | 0 | 0 | 0 | SI | Region 2 - North East | Nevada City | Nevada | 39.3635 | -120.7913 | ALLEGHANY 1102CB | ALLEGHANY 1102CB | 162 | 1700
74008802 | INST ROSSMOOR 1109 FDR_MORAGA BK5 EMERG | Other | 06A | CONS | In-Construction* | 0.1108 | 1.0496 | 0 | 1.1604 | 0 | 1.1604 | 0 | 0 | 0 | DI | Region 3 - Bay Area | Lafayette | Contra Costa | 37.9561 | -122.0286 | ROSSMOOR 1108CB | ROSSMOOR 1108CB | 1251 | 2676

## Status
SAP Status | Status
UNSE | Scoping/Scoped
ADER | Estimating
APPR | Estimating
ESTS | Estimating
PEND | Permitting/Dependency
UNSC | Ready for Construction
CONS | In-Construction*
DOCC | Post-Construction
MAPP | Post-Construction
FICL | Post-Construction
CLSD | Closed
*May apply to projects with pre-Construction SAP statuses with completed miles

## ProjectType
ProjectType | Description
CWSP 2022-2023 | Community Wildfire Safety Program for projects aimed for 2022-2023
ECOP | EC Tag Optimization
ECOP - Top 20% | EC Tag Optimization in the top 20% of the 2021 risk model
FRRB - OH – 2021 | Fire Rebuild - Overhead Hardening
FRRB - REMG – 2021 | Fire Rebuild - Remote Grid Projects
FRRB - UG – 2021 | Fire Rebuild - Underground Hardening
PRE | Projects that had poles in the ground and construction had begun, based on 2018 risk model
PSPS - Community Resiliency | Public Safety Power Shutoff projects
PSPS – Scoped | Public Safety Power Shutoff projects that had been scoped, based on 2018 risk model
PSS Approved | Public Safety Specialists approved projects
Remote Grid | Remote Grid projects
Remote Grid Pilot | Remote Grid projects part of the Pilot program
Storm Rebuild | Storm Rebuild projects
Top 20% MAVF CPZ | Top 20% of Circuit Protection Zones based on the 2021 risk model
Top 250 miles | Top 250 miles based on the 2021 risk model
Top 50 Miles | Top 50 miles based on the 2021 risk model