## WMP2022_Cal Advocates_004-Q8
Order | Order Description | MAT Code | Program | UG Feet | OH Feet | Removal Feet | Total Feet | Total Miles | 2021 Complete Miles | 2022 Forecast Miles | 2023 Forecast Miles | Construction Start | Construction End | Circuit Protection Zone | Risk Rank | Segmentation ID#
35244158 | FT-COND_IDLE_REMV-G/P 0FF 2NE/0 0FF 217 | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | ALLEGHANY 1101804 | 1753
35208064 | FT-COND_IDLE_REMV-879 OLD TOOL BRIDGE R | 2AF | Idle Facilities | 0 | 0 | 225 | 225 | 0.042614 | 0 | 0.042614 | 0 |  |  | ALLEGHANY 1101806 | 1446
35264104 | DRSTS-OFAC_IDLE_REMV-7NE/O 15921 STATE H | 2AF | Idle Facilities | 0 | 0 | 538 | 538 | 0.10189 | 0 | 0.10189 | 0 |  |  | ALLEGHANY 1101806 | 1446
35244150 | FT-COND_IDLE_REMV-D/P R/O 19182 GERMAN | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | ALLEGHANY 1102CB | 1700
35121520 | NR7 OFAC_IDLE_REMV-LAKEVIEW RD-14LOC | 2AF | Idle Facilities | 0 | 0 | 3464 | 3464 | 0.65606 | 0 | 0.65606 | 0 | 2022-04-18 | 2022-04-18 | ANTLER 11011378 | 1722
35244148 | FT-STS-COND_IDLE_REMV-A/F 5509 PONY EXP | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | APPLE HILL 110413512 | 1284
35244146 | FT-COND_IDLE_REMV-6935-6963 MORNING CAN | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | APPLE HILL 2102186912 | 1035
35148039 | DR-COND_IDLE_REMV-CEDERVILLE ROAD ALMOS | 2AF | Idle Facilities | 0 | 0 | 575 | 575 | 0.1089 | 0 | 0.1089 | 0 | 2021-11-01 | 2022-02-02 | APPLE HILL 21028372 | 654
35083699 | STS-COND_IDLE_REMV-38113 PETERSON RD | 2AF | Idle Facilities | 0 | 0 | 400 | 400 | 0.075758 | 0 | 0.075758 | 0 |  |  | AUBERRY 1101176050 | 1302
35277926 | CWSP - AUBERRY 1101CB PH1.3 | 08W | SH | 0 | 18172 | 0 | 18172 | 3.4417 | 0 | 3.4417 | 0 | 2022-05-31 08:00 | 2022-12-12 17:00 | AUBERRY 1101CB | 63 | 35254078
35277929 | CWSP - AUBERRY 1101CB PH2.2 | 08W | SH | 0 | 14752 | 0 | 14752 | 2.7939 | 0 | 2.7939 | 0 | 2022-10-21 | 2022-11-29 17:00 | AUBERRY 1101CB | 63 | 35254079
35254078 | CWSP - AUBERRY 1101 CB PH1 | 08W | SH | 0 | 14157 | 0 | 14157 | 2.6812 | 0 | 2.6812 | 0 | 2022-05-31 08:00 | 2022-12-31 | AUBERRY 1101CB | 63 | 35254078
35254079 | CWSP - AUBERRY 1101 CB PH2 | 08W | SH | 0 | 12678 | 0 | 12678 | 2.4011 | 0 | 2.4011 | 0 | 2022-07-19 08:00 | 2022-12-30 | AUBERRY 1101CB | 63 | 35254079
35254245 | CWSP - AUBERRY 1101 LR R2578 PH3 | 08W | SH | 0 | 15618 | 0 | 15618 | 2.958 | 0 | 2.958 | 0 | 2022-08-15 | 2022-10-03 17:00 | AUBERRY 1101R2578 | 163 | 35254245
35254246 | CWSP - AUBERRY 1101 LR R2578 PH4 | 08W | SH | 0 | 13834 | 0 | 13834 | 2.6201 | 0 | 2.6201 | 0 | 2022-09-30 | 2022-09-30 | AUBERRY 1101R2578 | 163 | 35254246
35278096 | CWSP - AUBERRY 1101R2578 PH4.2 | 08W | SH | 0 | 6494 | 0 | 6494 | 1.2299 | 0 | 1.2299 | 0 | 2022-07-31 | 2022-10-13 17:00 | AUBERRY 1101R2578 | 163 | 35254246
35278097 | CWSP - AUBERRY 1101R2578 PH4.3 | 08W | SH | 0 | 6336 | 1563 | 7899 | 1.496 | 0 | 1.496 | 0 | 2022-07-08 08:00 | 2022-10-24 17:00 | AUBERRY 1101R2578 | 163 | 35254246
35278098 | CWSP - AUBERRY 1101R2578 PH4.4 | 08W | SH | 0 | 8131 | 0 | 8131 | 1.54 | 0 | 1.54 | 0 | 2022-07-31 | 2022-11-24 17:00 | AUBERRY 1101R2578 | 163 | 35254246
35154942 | POLE_BROK_REPL - 38601 JOSE BASIN RD AT | 07D | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 | 2022-02-23 | 2022-02-23 | AUBERRY 1101R322 | 956
35221652 | STS-COND_IDLE_REMV - 31016 HWY 168/3PSE. | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 | 2022-03-01 | 2022-03-01 | AUBERRY 1102R902 | 213
35211755 | FT-COND_IDLE_REMV-LOS VERJELES | 2AF | Idle Facilities | 0 | 0 | 553 | 553 | 0.10473 | 0 | 0.10473 | 0 | 2021-02-23 | 2022-03-04 | BANGOR 11011958 | 785
35211757 | DR-COND_IDLE_REMV-13716 LOS VERJELES | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | BANGOR 110131502 | 225
35277147 | STS-POLE_IDLE_REMV-GREELY HILL RD CO#423 | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | BEAR VALLEY 210521160 | 1019
35145458 | STS-POLE_IDLE_REMV - NW C/O BUCKMEADOWS | 2AF | Idle Facilities | 0 | 0 | 8587 | 8587 | 1.6263 | 0 | 1.6263 | 0 |  |  | BEAR VALLEY 2105454432 | 882
35083878 | STS-COND_IDLE_REMV-9685 MANZANITA WAY | 2AF | Idle Facilities | 0 | 0 | 241 | 241 | 0.045644 | 0 | 0.045644 | 0 |  |  | BEAR VALLEY 21059560 | 1547
35211260 | FT-POLE_IDLE_REMV - 5960 HWY 49 AUBURN | 2AF | Idle Facilities | 0 | 0 | 193 | 193 | 0.036553 | 0 | 0.036553 | 0 |  |  | BELL 11082202 | 118
35211742 | FT-COND_IDLE_REMV-6250 BELLA VISTA PL | 2AF | Idle Facilities | 0 | 0 | 494 | 494 | 0.093561 | 0 | 0.093561 | 0 | 2021-02-02 | 2022-03-22 | BELL 11082202 | 118
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | 08W | SH | 0 | 8063 | 0 | 8063 | 1.5271 | 0.57917 | 0.94792 | 0 | 2021-10-01 | 2022-02-15 | BIG BASIN 110110296 | 2456
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | 08W | SH | 0 | 17134 | 0 | 17134 | 3.2451 | 0 | 3.2451 | 0 | 2022-01-05 | 2022-11-14 17:00 | BIG BASIN 110110296 | 2456
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | 08W | SH | 0 | 12378 | 0 | 12378 | 2.3443 | 0 | 2.3443 | 0 | 2022-07-21 17:00 | 2022-12-29 17:00 | BIG BASIN 110110296 | 2456
35078178 | STS-COND_IDLE_REMV-295 EAST RD | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | BIG BASIN 11015028 | 2968
35300885 | FRRB-BIG BASIN 1102 2253 P1S1 18955CHINA | 08W | Fire Rebuild | 3000 | 0 | 0 | 3000 | 0.56818 | 0 | 0.56818 | 0 |  |  | BIG BASIN 11022253 | 2246
35242422 | FRRB - BIG BEND 1102 - B6 PH6.3 (T/L-1) | 08W | Fire Rebuild | 4509 | 0 | 0 | 4509 | 0.85398 | 0 | 0.85398 | 0 | 2021-10-02 | 2022-01-21 17:00 | BIG BEND 11021972 | 1288
35242423 | FRRB - BIG BEND 1102 - B6 PH6.4 (T/L-2) | 08W | Fire Rebuild | 4697 | 0 | 0 | 4697 | 0.88958 | 0 | 0.88958 | 0 | 2021-09-30 | 2022-01-21 17:00 | BIG BEND 11021972 | 1288
35242424 | FRRB - BIG BEND 1102 - B6 PH6.5 (T/L-3) | 08W | Fire Rebuild | 3693 | 0 | 0 | 3693 | 0.69943 | 0 | 0.69943 | 0 | 2021-09-30 | 2022-01-21 17:00 | BIG BEND 11021972 | 1288
35242425 | FRRB - BIG BEND 1102 - B6 PH6.6 (T/L-4) | 08W | Fire Rebuild | 3493 | 0 | 0 | 3493 | 0.66155 | 0 | 0.66155 | 0 | 2021-09-27 | 2022-01-21 17:00 | BIG BEND 11021972 | 1288
35242426 | FRRB - BIG BEND 1102 - B6 PH6.7 | 08W | Fire Rebuild | 3345 | 0 | 0 | 3345 | 0.63352 | 0 | 0.63352 | 0 | 2022-02-14 | 2022-06-30 17:00 | BIG BEND 11021972 | 1288
35242427 | FRRB - BIG BEND 1102 - B6 PH6.8 | 08W | Fire Rebuild | 4635 | 0 | 0 | 4635 | 0.87784 | 0 | 0.87784 | 0 | 2022-02-16 | 2022-06-30 17:00 | BIG BEND 11021972 | 1288
35242428 | FRRB - BIG BEND 1102 - B4 PH4.2 | 08W | Fire Rebuild | 3886 | 0 | 0 | 3886 | 0.73598 | 0 | 0.73598 | 0 | 2021-11-30 | 2022-03-11 | BIG BEND 11021972 | 1288
35242429 | FRRB - BIG BEND 1102 - B4 PH4.3 | 08W | Fire Rebuild | 3157 | 0 | 0 | 3157 | 0.59792 | 0 | 0.59792 | 0 | 2021-11-29 | 2022-03-31 17:00 | BIG BEND 11021972 | 1288
35236983 | FRRB - BIG BEND 1102 - B5 PH5.3 | 08W | Fire Rebuild | 1689 | 0 | 0 | 1689 | 0.31989 | 0 | 0.31989 | 0 | 2022-03-04 | 2022-03-07 | BIG BEND 11021972 | 1288
35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 | 08W | Fire Rebuild | 14264 | 0 | 0 | 14264 | 2.7015 | 0.11231 | 2.5892 | 0 | 2022-02-25 | 2022-03-09 17:00 | BIG BEND 11021972 | 1288
35235679 | FRRB - BIG BEND 1102 - B6 PH6.1 (M/L-N) | 08W | Fire Rebuild | 3843 | 0 | 0 | 3843 | 0.72784 | 0 | 0.72784 | 0 | 2021-08-04 | 2022-01-21 17:00 | BIG BEND 11021972 | 1288
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 | 08W | Fire Rebuild | 8077 | 0 | 0 | 8077 | 1.5297 | 1.2008 | 0.32898 | 0 | 2021-10-12 | 2022-02-25 | BIG BEND 11021972 | 1288
35233166 | FRRB - BIG BEND 1102 - B5 PH5.2 | 08W | Fire Rebuild | 5178 | 0 | 0 | 5178 | 0.98068 | 0 | 0.98068 | 0 | 2022-03-04 | 2022-03-08 | BIG BEND 11021972 | 1288
35225821 | FRRB - BIG BEND 1102 - LAKE MADRONE PH2 | 08W | Fire Rebuild | 5974 | 0 | 0 | 5974 | 1.1314 | 1.0252 | 0.10625 | 0 | 2021-08-03 08:00 | 2022-02-28 17:00 | BIG BEND 11021972 | 1288
35292754 | FRRB - BIG MEADOWS 21012248 UG ML PH2 | 08W | Fire Rebuild | 22334 | 0 | 0 | 22334 | 4.2299 | 0 | 4.2299 | 0 | 2022-10-31 08:00 | 2023-03-02 17:00 | BIG MEADOWS 21012248 | 916
35292755 | FRRB - BIG MEADOWS 21012248 UG ML PH3 | 08W | Fire Rebuild | 14467 | 0 | 0 | 14467 | 2.74 | 0 | 2.74 | 0 | 2022-11-03 08:00 | 2023-03-07 17:00 | BIG MEADOWS 21012248 | 916
35292756 | FRRB - BIG MEADOWS 21012248 UG ML PH4.1 | 08W | Fire Rebuild | 4752 | 0 | 0 | 4752 | 0.9 | 0 | 0.9 | 0 | 2022-11-03 08:00 | 2023-03-07 17:00 | BIG MEADOWS 21012248 | 916
35280493 | FRRB -BIG MEADOWS 21012260 OH TL 1.13 | 08W | Fire Rebuild | 0 | 1848 | 0 | 1848 | 0.35 | 0 | 0.35 | 0 | 2022-11-03 08:00 | 2023-03-07 17:00 | BIG MEADOWS 21012248 | 916
35280495 | FRRB - BIG MEADOW 21012260 OH TL PH1.1 | 08W | Fire Rebuild | 0 | 2752 | 0 | 2752 | 0.52121 | 0 | 0.52121 | 0 |  |  | BIG MEADOWS 21012248 | 916
35279985 | FRRB-BIG MEADOWS 2101 UG RND VALLY RES | 08W | Fire Rebuild | 16209 | 0 | 0 | 16209 | 3.0699 | 0 | 3.0699 | 0 | 2022-07-25 08:00 | 2022-11-24 17:00 | BIG MEADOWS 21012248 | 916
35290540 | FRRB - BIG MEADOWS 21012248 UG ML PH1 | 08W | Fire Rebuild | 4171 | 0 | 0 | 4171 | 0.78996 | 0 | 0.78996 | 0 | 2022-10-05 08:00 | 2023-02-06 17:00 | BIG MEADOWS 21012248 | 916
35290944 | FRRB -BIG MEADOWS 21012260 UG TL 1.6 | 08W | Fire Rebuild | 1584 | 0 | 0 | 1584 | 0.3 | 0 | 0.3 | 0 | 2022-11-22 08:00 | 2023-03-24 17:00 | BIG MEADOWS 21012260 | 995
35290946 | FRRB -BIG MEADOWS 21012260 UG TL 1.7 | 08W | Fire Rebuild | 950 | 0 | 0 | 950 | 0.17992 | 0 | 0.17992 | 0 | 2022-11-03 08:00 | 2023-03-07 17:00 | BIG MEADOWS 21012260 | 995
35290948 | FRRB -BIG MEADOWS 21012260 UG TL 1.8 | 08W | Fire Rebuild | 792 | 0 | 0 | 792 | 0.15 | 0 | 0.15 | 0 | 2022-11-03 08:00 | 2023-03-07 17:00 | BIG MEADOWS 21012260 | 995
35290542 | FRRB - BIG MEADOWS 21012260 UG ML PH1.2 | 08W | Fire Rebuild | 2957 | 0 | 0 | 2957 | 0.56004 | 0 | 0.56004 | 0 | 2022-11-03 08:00 | 2023-03-07 17:00 | BIG MEADOWS 21012260 | 995
35290544 | FRRB - BIG MEADOWS 21012260 UG ML PH1.3 | 08W | Fire Rebuild | 5174 | 0 | 0 | 5174 | 0.97992 | 0 | 0.97992 | 0 | 2022-11-03 08:00 | 2023-03-07 17:00 | BIG MEADOWS 21012260 | 995
35292780 | FRRB -BIG MEADOWS 21012260 UG TL 1.9 | 08W | Fire Rebuild | 898 | 0 | 0 | 898 | 0.17008 | 0 | 0.17008 | 0 | 2022-11-03 08:00 | 2023-03-07 17:00 | BIG MEADOWS 21012260 | 995
35292782 | FRRB -BIG MEADOWS 21012260 UG TL 1.10 | 08W | Fire Rebuild | 1215 | 0 | 0 | 1215 | 0.23011 | 0 | 0.23011 | 0 | 2022-11-28 08:00 | 2023-03-30 17:00 | BIG MEADOWS 21012260 | 995
35292784 | FRRB -BIG MEADOWS 21012260 UG TL 1.11 | 08W | Fire Rebuild | 528 | 0 | 0 | 528 | 0.1 | 0 | 0.1 | 0 | 2022-11-03 08:00 | 2023-03-07 17:00 | BIG MEADOWS 21012260 | 995
35292786 | FRRB -BIG MEADOWS 21012260 UG TL 1.12 | 08W | Fire Rebuild | 528 | 0 | 0 | 528 | 0.1 | 0 | 0.1 | 0 | 2022-11-03 08:00 | 2023-03-07 17:00 | BIG MEADOWS 21012260 | 995
35292787 | FRRB -BIG MEADOWS 21012476 OH ML PH1.1 | 08W | Fire Rebuild | 0 | 845 | 0 | 845 | 0.16004 | 0 | 0.16004 | 0 |  |  | BIG MEADOWS 21012476 | 2342
35292788 | FRRB -BIG MEADOWS 21012476 UG ML PH1.2 | 08W | Fire Rebuild | 5808 | 0 | 0 | 5808 | 1.1 | 0 | 1.1 | 0 | 2022-11-03 08:00 | 2023-03-07 17:00 | BIG MEADOWS 21012476 | 2342
35292789 | FRRB -BIG MEADOWS 21012248 UG TL PH1.1 | 08W | Fire Rebuild | 528 | 0 | 0 | 528 | 0.1 | 0 | 0.1 | 0 | 2022-11-03 08:00 | 2023-03-07 17:00 | BIG MEADOWS 21012476 | 2342
35292791 | FRRB -BIG MEADOWS 21012586 UG PH1 | 08W | Fire Rebuild | 634 | 0 | 0 | 634 | 0.12008 | 0 | 0.12008 | 0 | 2022-11-15 08:00 | 2023-03-17 17:00 | BIG MEADOWS 21012586 | 1285
35037613 | DR_POLE_IDLE_REMV-JAYMAR LN & HWY 36 | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | BRIDGEVILLE 110237486 | 1315
35211230 | DRCOND_IDLE_REMV-5726 EVERGLADE | 2AF | Idle Facilities | 0 | 0 | 323 | 323 | 0.061174 | 0 | 0.061174 | 0 |  |  | BROWNS VALLEY 110193870 | 774
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | SH | 0 | 8983 | 0 | 8983 | 1.7013 | 0.80076 | 0.90057 | 0 | 2021-12-20 | 2022-02-28 | BRUNSWICK 110350070 | 2144
35208071 | FT-COND_IDLE_REMV-19828 WOODPECKER RAVI | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | BRUNSWICK 11062416 | 1638
35302344 | FRRB - BRUNSWICK 1106- TL -OH - 05 | 08W | Fire Rebuild | 0 | 1000 | 0 | 1000 | 0.18939 | 0 | 0.18939 | 0 |  |  | BRUNSWICK 11062790 | 715
35279512 | FRRB - BRUNSWICK 1106 UG - 02 | 08W | Fire Rebuild | 0 | 935 | 0 | 935 | 0.17708 | 0 | 0.17708 | 0 | 2022-01-18 | 2022-01-28 | BRUNSWICK 11062790 | 715
35279604 | FRRB - BRUNSWICK 1106 OH | 08W | Fire Rebuild | 0 | 7511 | 0 | 7511 | 1.4225 | 1.3017 | 0.12083 | 0 | 2021-09-08 | 2022-03-12 | BRUNSWICK 11062790 | 715
35244185 | STS-COND_IDLE_REMV-1E/O 11780 E. BENNETT | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | BRUNSWICK 1106CB | 1876
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | 08W | SH | 381 | 0 | 97 | 478 | 0.09053 | 0 | 0.09053 | 0 | 2022-03-15 08:00 | 2022-06-17 | BRUNSWICK 1110CB | 2134
35224712 | FRRB - BUCKS CREEK 1101 CB PH 2 | 08W | Fire Rebuild | 9134 | 0 | 0 | 9134 | 1.7299 | 0 | 1.7299 | 0 | 2022-05-02 08:00 | 2022-12-30 17:00 | BUCKS CREEK 1101CB | 11 | 35217268
35224713 | FRRB - BUCKS CREEK 1101 CB PH 3.1 | 08W | Fire Rebuild | 9662 | 0 | 0 | 9662 | 1.8299 | 0 | 1.8299 | 0 | 2022-04-26 08:00 | 2022-10-21 17:00 | BUCKS CREEK 1101CB | 11 | 35217268
35217268 | FRRB - BUCKS CREEK 1101 CB PH 1.1 | 08W | Fire Rebuild | 211 | 300 | 0 | 511 | 0.09678 | 0 | 0.09678 | 0 | 2022-05-02 08:00 | 2022-11-21 17:00 | BUCKS CREEK 1101CB | 11 | 35217268
35279181 | FRRB - BUCKS CREEK 1102 CB PH1 | 08W | Fire Rebuild | 29510 | 0 | 0 | 29510 | 5.589 | 0 | 5.589 | 0 | 2022-07-12 08:00 | 2022-11-11 17:00 | BUCKS CREEK 1102CB | 378
35279182 | FRRB - BUCKS CREEK 1102 CB PH2 | 08W | Fire Rebuild | 10930 | 0 | 0 | 10930 | 2.0701 | 0 | 2.0701 | 0 | 2022-08-09 08:00 | 2022-12-09 17:00 | BUCKS CREEK 1102CB | 378
35280499 | FRRB - BUCKS CREEK 1102 CB PH3 | 08W | Fire Rebuild | 4488 | 0 | 0 | 4488 | 0.85 | 0 | 0.85 | 0 | 2022-09-20 08:00 | 2023-01-27 17:00 | BUCKS CREEK 1102CB | 378
35280560 | FRRB - BUCKS CREEK 1102 CB PH4 | 08W | Fire Rebuild | 13939 | 0 | 0 | 13939 | 2.64 | 0 | 2.64 | 0 | 2022-09-20 08:00 | 2023-01-27 17:00 | BUCKS CREEK 1102CB | 378
35122244 | +STS-COND_IDLE_REMV-3780 SANTA ROSA | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | CABRILLO 1103Y46 | 998
35224451 | STS-POLE_IDLE_REMV - #1 S/O #1 W/O SURF | 2AF | Idle Facilities | 0 | 0 | 70 | 70 | 0.013258 | 0 | 0.013258 | 0 |  |  | CABRILLO 1104Y22 | 1500
35224438 | +STS-COND_IDLE_REMV-SUDDEN RANCH AT RR X | 2AF | Idle Facilities | 0 | 0 | 91 | 91 | 0.017235 | 0 | 0.017235 | 0 |  |  | CABRILLO 1104Y24 | 949
35221824 | STS-COND_IDLE_REMV-9995 HWY 26 | 2AF | Idle Facilities | 0 | 0 | 178 | 178 | 0.033712 | 0 | 0.033712 | 0 | 2021-02-03 | 2022-03-31 | CALAVERAS CEMENT 11012646 | 1889
35221748 | STS-COND_IDLE_REMV-#1S 9743 MOUNTAIN RAN | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | CALAVERAS CEMENT 11014786 | 804
35222073 | STS-COND_IDLE_REMV-@ GATE 9677 MOUNTAIN | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | CALAVERAS CEMENT 11014786 | 804
35221818 | STS-COND_IDLE_REMV-#2E #2SW ON LINE @ 75 | 2AF | Idle Facilities | 0 | 0 | 378 | 378 | 0.071591 | 0 | 0.071591 | 0 |  |  | CALAVERAS CEMENT 110180930 | 1652
35264103 | T2/T3 POLE_IDLE_REMV-3411 LAWLEY RD R/O | 2AF | Idle Facilities | 0 | 0 | 687 | 687 | 0.13011 | 0 | 0.13011 | 0 |  |  | CALISTOGA 110189150 | 1093
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | 08W | SH | 0 | 693 | 0 | 693 | 0.13125 | 0 | 0.13125 | 0 | 2022-03-02 08:00 | 2022-05-13 17:00 | CALISTOGA 1102184814 | 3098
35243793 | STS-OFAC_IDLE_DEEN - 1 SW/O R/O 4561 FOO | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | CALISTOGA 1102634 | 1477
35211655 | DR-COND_IDLE_REMV-7253 N STATE ST | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | CALPELLA 1101619542 | 1432
35080162 | CALPELLA 1101 OH 12,000' RECONDUCTORING | 06H | Other | 0 | 7610 | 0 | 7610 | 1.4413 | 1.2462 | 0.19508 | 0 | 2021-04-29 | 2022-03-31 | Calpella 1101CB | 1256
35225253 | STS-COND_IDLE_REMV-214 TABERNACLE DRIVE | 2AF | Idle Facilities | 0 | 0 | 150 | 150 | 0.028409 | 0 | 0.028409 | 0 |  |  | CAMP EVERS 21045096 | 2474
35206236 | STS-COND_IDLE_REMV-11259 FRESCO ST | 2AF | Idle Facilities | 0 | 0 | 592 | 592 | 0.11212 | 0 | 0.11212 | 0 |  |  | CAMP EVERS 210510294 | 2167
35037588 | T2 REMV IDLE COND L/S 5429 (5800 R*RMTC | 2AF | Idle Facilities | 0 | 0 | 909 | 909 | 0.17216 | 0 | 0.17216 | 0 |  | 2022-03-23 | CARLOTTA 112142896 | 1918
35083864 | STS-COND_IDLE_REMV-22148 EDEN CANYON RD | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | CASTRO VALLEY 1110MR243 | 1914
35221249 | DR~STS-OFAC_IDLE_REMV - 1/N/O/AT 908 ORE | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | CLARK ROAD 110292622 | 771
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | SH | 21381 | 0 | 0 | 21381 | 4.0494 | 0 | 4.0494 | 0 | 2022-06-07 | 2022-12-30 | CLARKSVILLE 2104CB | 134
35221659 | STS-COND_IDLE_REMV-1N/O 2W/O 10835 WATER | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 | 2022-03-02 | 2022-03-02 | CLAY 110113442 | 744
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | 08W | SH | 0 | 5544 | 0 | 5544 | 1.05 | 0 | 1.05 | 0 | 2022-06-28 08:00 | 2022-10-13 17:00 | CLAYTON 221296224 | 377 | 35192280
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | 08W | SH | 7075 | 0 | 0 | 7075 | 1.34 | 0 | 1.34 | 0 | 2022-05-31 08:00 | 2022-12-30 17:00 | CLAYTON 221296224 | 377 | 35192280
35145001 | PSPS - CLAYTON 2215 - CB | 08W | SH | 9720 | 375 | 0 | 10095 | 1.9119 | 0 | 1.9119 | 0 | 2022-04-08 08:00 | 2022-09-08 17:00 | CLAYTON 2215184604 | 1739
35037880 | DR REMV IDLE 15 LOCS -CLARK DR KELSEY | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 | 2022-01-11 | 2022-01-21 | CLEAR LAKE 11011302 | 2020
31255513 | FT~T2 REMV IDLE SVC POLE A/F 180 GEYSERS | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 | 2021-04-02 | 2022-02-28 | CLOVERDALE 1102674 | 680
35243452 | CWSP - COARSEGOLD 210410030 - PH1.1 | 08W | SH | 0 | 17349 | 0 | 17349 | 3.2858 | 0 | 3.2858 | 0 | 2022-03-30 08:00 | 2022-09-27 17:00 | COARSEGOLD 210410030 | 144 | 35243452
35249996 | CWSP - COARSEGOLD 210410030 PH 1.2 | 08W | SH | 0 | 10315 | 0 | 10315 | 1.9536 | 0 | 1.9536 | 0 | 2022-03-30 08:00 | 2022-08-08 17:00 | COARSEGOLD 210410030 | 144 | 35243452
35249997 | CWSP - COARSEGOLD 210410030 PH 1.3 | 08W | SH | 0 | 10092 | 0 | 10092 | 1.9114 | 0 | 1.9114 | 0 | 2022-03-30 08:00 | 2023-02-06 17:00 | COARSEGOLD 210410030 | 144 | 35243452
35249998 | CWSP - COARSEGOLD 210410030 PH 1.4 | 08W | SH | 0 | 19416 | 0 | 19416 | 3.6773 | 0 | 3.6773 | 0 | 2022-04-18 08:00 | 2022-09-29 17:00 | COARSEGOLD 210410030 | 144 | 35243452
35249999 | CWSP - COARSEGOLD 210410030 PH 1.5 | 08W | SH | 0 | 10923 | 0 | 10923 | 2.0688 | 0 | 2.0688 | 0 | 2022-04-25 08:00 | 2022-10-12 | COARSEGOLD 210410030 | 144 | 35243452
35240160 | CWSP - COARSEGOLD 21045310 PH 1.1 | 08W | SH | 0 | 23148 | 0 | 23148 | 4.3841 | 0 | 4.3841 | 0 | 2022-03-30 08:00 | 2022-10-18 17:00 | COARSEGOLD 21045310 | 61 | 35240160
35240162 | CWSP - COARSEGOLD 21045310 PH 2.1 | 08W | SH | 0 | 11221 | 0 | 11221 | 2.1252 | 0 | 2.1252 | 0 | 2022-06-21 08:00 | 2022-11-25 17:00 | COARSEGOLD 21045310 | 61 | 35240162
35249871 | CWSP - COARSEGOLD 21045310 PH 1.2 | 08W | SH | 0 | 10658 | 0 | 10658 | 2.0186 | 0 | 2.0186 | 0 | 2022-04-05 08:00 | 2022-09-26 17:00 | COARSEGOLD 21045310 | 61 | 35240160
35249872 | CWSP - COARSEGOLD 21045310 PH 1.3 | 08W | SH | 0 | 14388 | 0 | 14388 | 2.725 | 0 | 2.725 | 0 | 2022-03-30 08:00 | 2022-10-11 17:00 | COARSEGOLD 21045310 | 61 | 35240160
35240165 | CWSP - COARSEGOLD 21046210 PH 1.1 | 08W | SH | 0 | 20327 | 0 | 20327 | 3.8498 | 0 | 3.8498 | 0 | 2022-04-26 08:00 | 2022-10-21 17:00 | COARSEGOLD 21046210 | 132 | 35240165
35249875 | CWSP - COARSEGOLD 21046210 PH 1.2 | 08W | SH | 0 | 13936 | 0 | 13936 | 2.6394 | 0 | 2.6394 | 0 | 2022-05-11 08:00 | 2022-11-22 17:00 | COARSEGOLD 21046210 | 132 | 35240165
35249876 | CWSP - COARSEGOLD 21046210 PH 1.3 | 08W | SH | 0 | 19263 | 0 | 19263 | 3.6483 | 0 | 3.6483 | 0 | 2022-06-01 08:00 | 2022-12-13 17:00 | COARSEGOLD 21046210 | 132 | 35240165
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | 08W | SH | 0 | 12921 | 0 | 12921 | 2.4472 | 0 | 2.4472 | 0 | 2022-02-28 | 2022-06-08 17:00 | COARSEGOLD 2104CB | 22 | 35219097
35211659 | DR-COND_IDLE_REMV-14932 MOONSHINE RD | 2AF | Idle Facilities | 0 | 0 | 160 | 160 | 0.030303 | 0 | 0.030303 | 0 |  |  | COLUMBIA HILL 1101764 | 1590
35223249 | DR~T2 COND_IDLE_REMV - 155 TWIN BRIDGE | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | COTATI 1103132 | 965
35208019 | DR~STS-COND_IDLE_REM-2S/O 16490 BLUE OAK | 2AF | Idle Facilities | 0 | 0 | 196 | 196 | 0.037121 | 0 | 0.037121 | 0 | 2021-05-05 | 2022-01-27 | COTTONWOOD 11011610 | 470
35204803 | DR~STS-POLE_IDLE_REMV-16250 BOWMAN RD | 2AF | Idle Facilities | 0 | 0 | 526 | 526 | 0.099621 | 0 | 0.099621 | 0 |  |  | COTTONWOOD 11011610 | 470
35262345 | DR-STS-POLE_IDLE_REMV-4S/OR/O3235MEADOW | 2AF | Idle Facilities | 0 | 0 | 940 | 940 | 0.17803 | 0 | 0.17803 | 0 |  |  | COTTONWOOD 11021578 | 554
35280496 | FRRB - CRESCENT MILLS 21012056 UG ML 1.2 | 08W | Fire Rebuild | 4330 | 0 | 0 | 4330 | 0.82008 | 0 | 0.82008 | 0 | 2022-02-25 08:00 | 2022-06-29 17:00 | CRESCENT MILLS 21012056 | 895
35280498 | FRRB - CRESCENT MILLS 21012056 OH TL 1.1 | 08W | Fire Rebuild | 0 | 387 | 0 | 387 | 0.073295 | 0 | 0.073295 | 0 |  |  | CRESCENT MILLS 21012056 | 895
35286724 | FRRB - CRESCENT MILLS 21012056 OH ML 1.1 | 08W | Fire Rebuild | 0 | 5722 | 0 | 5722 | 1.0837 | 1.0485 | 0.035227 | 0 |  |  | CRESCENT MILLS 21012056 | 895
35238953 | STS-OFAC_IDLE_REMV - 6445 NORTH VALLEY R | 2AF | Idle Facilities | 0 | 0 | 22364 | 22364 | 4.2356 | 0 | 4.2356 | 0 |  |  | CRESCENT MILLS 21012562 | 1078
35221715 | T2/T3-STS-COND_IDLE_REMV-20599 KINGS CT | 2AF | Idle Facilities | 0 | 0 | 218 | 218 | 0.041288 | 0 | 0.041288 | 0 |  |  | CURTIS 17058170 | 1770
35046236 | STS-COND_IDLE_REMV-IMPOSSIBLE CANYON ROA | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | DEL MONTE 21042624 | 2367
35274991 | STS-OFAC_IDLE_REMV - 600' S/O SWEDE CREE | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 | 2021-10-13 | 2022-04-15 | DESCHUTES 11011580 | 375
35204871 | FT-POLE_IDLE_REMV - 7 SPANS S/ C/O 3503 | 2AF | Idle Facilities | 0 | 0 | 240 | 240 | 0.045455 | 0 | 0.045455 | 0 |  |  | DESCHUTES 11011580 | 375
35275963 | STS-OFAC_IDLE_REMV - 9S/O 5E/O 27223 HWY | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | DESCHUTES 11011654 | 1086
35241072 | CWSP - DESCHUTES 11041370 PH1.1 | 08W | SH | 0 | 19008 | 1109 | 20117 | 3.81 | 0 | 3.81 | 0 | 2022-06-13 08:00 | 2022-11-29 17:00 | DESCHUTES 11041370 | 100 | 35241072
35243447 | CWSP - DESCHUTES 11041370 PH 2.1 | 08W | SH | 0 | 13939 | 174 | 14113 | 2.6729 | 0 | 2.6729 | 0 | 2022-05-18 08:00 | 2022-09-22 08:00 | DESCHUTES 11041370 | 100 | 35243447
35259511 | CWSP - DESCHUTES 11041370 PH 2.2 | 08W | SH | 0 | 14625.6 | 0 | 14625.6 | 2.77 | 0 | 2.77 | 0 | 2022-05-09 08:00 | 2022-09-20 08:00 | DESCHUTES 11041370 | 100 | 35243447
35259515 | CWSP - DESCHUTES 11041370 PH 1.2 | 08W | SH | 0 | 13069 | 0 | 13069 | 2.4752 | 0 | 2.4752 | 0 | 2022-05-09 08:00 | 2022-09-20 08:00 | DESCHUTES 11041370 | 100 | 35241072
35259516 | CWSP - DESCHUTES 11041370 PH 1.3 | 08W | SH | 1128 | 0 | 0 | 1128 | 0.21364 | 0 | 0.21364 | 0 | 2022-04-25 08:00 | 2022-09-06 17:00 | DESCHUTES 11041370 | 100 | 35241072
35211254 | DR~STS-OFAC_IDLE_REM-11226 DESCHUTES RD | 2AF | Idle Facilities | 0 | 0 | 159 | 159 | 0.030114 | 0 | 0.030114 | 0 |  |  | DESCHUTES 11041370 | 100
35241071 | CWSP - DESCHUTES 11041582 | 08W | SH | 0 | 10748 | 1716 | 12464 | 2.3606 | 0 | 2.3606 | 0 | 2022-05-23 08:00 | 2022-12-02 17:00 | DESCHUTES 11041582 | 301 | 35241071
35241073 | CWSP - DESCHUTES 110449024 PH1.1 | 08W | SH | 0 | 20356 | 0 | 20356 | 3.8553 | 0 | 3.8553 | 0 | 2022-05-10 08:00 | 2022-09-21 08:00 | DESCHUTES 110449024 | 99 | 35241073
35243448 | CWSP - DESCHUTES 110449024 PH 2.1 | 08W | SH | 0 | 19483 | 0 | 19483 | 3.69 | 0 | 3.69 | 0 | 2022-07-19 08:00 | 2022-11-30 08:00 | DESCHUTES 110449024 | 99 | 35243448
35259517 | CWSP - DESCHUTES 110449024 PH 1.2 | 08W | SH | 0 | 24292 | 0 | 24292 | 4.6008 | 0 | 4.6008 | 0 | 2022-06-20 08:00 | 2022-09-20 08:00 | DESCHUTES 110449024 | 99 | 35241073
35259513 | CWSP - DESCHUTES 1104499024 PH 2.2 | 08W | SH | 0 | 24499 | 0 | 24499 | 4.64 | 0 | 4.64 | 0 | 2022-07-19 08:00 | 2022-10-19 08:00 | DESCHUTES 110449024 | 99 | 35243448
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | 08W | SH | 0 | 18212 | 0 | 18212 | 3.4492 | 0 | 3.4492 | 0 | 2022-03-08 08:00 | 2022-06-10 17:00 | DESCHUTES 11049718 | 48 | 35219286
35232960 | CWSP - DESCHUTES 11049718 PH1.2 | 08W | SH | 0 | 15353 | 0 | 15353 | 2.9078 | 0 | 2.9078 | 0 | 2022-03-07 08:00 | 2022-06-10 17:00 | DESCHUTES 11049718 | 48 | 35219286
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 | 08W | SH | 0 | 16741 | 0 | 16741 | 3.1706 | 0 | 3.1706 | 0 | 2021-09-27 | 2022-03-07 17:00 | DESCHUTES 11049718 | 48 | 35225825
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 | 08W | SH | 0 | 18101 | 0 | 18101 | 3.4282 | 1.2443 | 2.1839 | 0 | 2021-09-20 | 2022-03-04 17:00 | DESCHUTES 11049718 | 48 | 35225825
35232445 | CWSP - DESCHUTES 11049718 PH 2.5 | 08W | SH | 0 | 13747 | 0 | 13747 | 2.6036 | 0.45246 | 2.1511 | 0 | 2021-09-16 08:00 | 2022-05-06 | DESCHUTES 11049718 | 48 | 35225825
35237026 | DR-STS-COND_IDLE_REMV-S/ENDOFSILVERBRIDG | 2AF | Idle Facilities | 0 | 0 | 991 | 991 | 0.18769 | 0 | 0.18769 | 0 | 2021-08-10 | 2022-03-31 | DESCHUTES 11049718 | 48
35144989 | STS-POLE_IDLE_REMV - 10590 DESCHUTES RD | 2AF | Idle Facilities | 0 | 0 | 388 | 388 | 0.073485 | 0 | 0.073485 | 0 | 2022-04-15 | 2022-04-16 | DESCHUTES 11049718 | 48
35208066 | REMV IDLE FAC 7528 DESCHUTES RD | 2AF | Idle Facilities | 0 | 0 | 750 | 750 | 0.14205 | 0 | 0.14205 | 0 |  |  | DESCHUTES 11049718 | 48
35211802 | DR~STS-OFAC_IDLE_REMV-1E/O 4491 FORNI RD | 2AF | Idle Facilities | 0 | 0 | 295 | 295 | 0.055871 | 0 | 0.055871 | 0 |  |  | DIAMOND SPRINGS 1104CB | 2036
35211692 | STS-COND_IDLE_REMV-5081 OLD FRENCH TOWN | 2AF | Idle Facilities | 0 | 0 | 50 | 50 | 0.0094697 | 0 | 0.0094697 | 0 |  |  | DIAMOND SPRINGS 110518935 | 1031
35244155 | STS-COND_IDLE_REMV-1PS/O 5100 RAMBLING R | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | DIAMOND SPRINGS 110610587 | 632
35244157 | FT-COND_IDLE_REMV-5100 RAMBLING RD | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | DIAMOND SPRINGS 110610587 | 632
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | 08W | SH | 0 | 26674 | 0 | 26674 | 5.0519 | 2.8996 | 2.1523 | 0 | 2021-11-22 08:00 | 2022-01-28 17:00 | DIAMOND SPRINGS 11071402 | 811
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | 08W | SH | 3742 | 0 | 0 | 3742 | 0.70871 | 0 | 0.70871 | 0 | 2022-06-29 08:00 | 2022-11-21 17:00 | DIAMOND SPRINGS 11071402 | 811 | 35192291
35244159 | STS-COND_IDLE_REMV-1 E/O R/O 5387 SPRING | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 | 2021-10-07 | 2022-02-21 | DIAMOND SPRINGS 11071402 | 811
35208046 | STS-COND_IDLE_REMV-MAIDU TR | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | DOBBINS 11011264 | 650
35208012 | FT~STS-COND_IDLE_REMV-10139 CLARK RANCH | 2AF | Idle Facilities | 0 | 0 | 896 | 896 | 0.1697 | 0 | 0.1697 | 0 |  |  | DOBBINS 11011264 | 650
35208047 | FT-COND_IDLE_REMV-9775 EVANS WY | 2AF | Idle Facilities | 0 | 0 | 115 | 115 | 0.02178 | 0 | 0.02178 | 0 | 2021-02-16 | 2022-03-16 | DOBBINS 11011808 | 193
35244117 | FT--COND_IDLE_REMV-2S/O 1E/O 41210 SKYLI | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | DRUM 11011602 | 2009
35284023 | FRRB - DUNBAR 1101416 | 08W | Fire Rebuild | 6177 | 0 | 0 | 6177 | 1.1699 | 0 | 1.1699 | 0 |  |  | DUNBAR 1101416 | 1684
35285589 | FRRB - ECHO SUMMIT 1101 - UG - 5 | 08W | Fire Rebuild | 1494 | 0 | 0 | 1494 | 0.28295 | 0 | 0.28295 | 0 | 2022-05-30 08:00 | 2022-12-08 17:00 | ECHO SUMMIT 1101344250 | 2461
35285594 | FRRB - ECHO SUMMIT 1101 - UG - 10 | 08W | Fire Rebuild | 1161 | 0 | 0 | 1161 | 0.21989 | 0 | 0.21989 | 0 | 2022-12-30 08:00 | 2023-08-07 17:00 | ECHO SUMMIT 1101481660 | 2005
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | SH | 1383 | 6681 | 0 | 8064 | 1.5273 | 0 | 1.5273 | 0 | 2022-09-06 | 2022-12-30 | EL DORADO PH 210119752 | 1946
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | SH | 3135 | 3779 | 0 | 6914 | 1.3095 | 0 | 1.3095 | 0 | 2022-08-02 | 2022-12-30 | EL DORADO PH 210119752 | 1946
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | SH | 12966 | 0 | 0 | 12966 | 2.4557 | 0 | 2.4557 | 0 | 2021-11-08 | 2022-02-26 | EL DORADO PH 210119752 | 1946
35109541 | CWSP - EL DORADO 2101- 19752 - PH 1.3 | 08W | SH | 1279 | 12807 | 0 | 14086 | 2.6678 | 0 | 2.6678 | 0 | 2022-05-12 08:00 | 2023-01-26 17:00 | EL DORADO PH 210119752 | 1946
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | SH | 1664 | 12975 | 0 | 14639 | 2.7725 | 0 | 2.7725 | 0 | 2022-06-17 08:00 | 2023-01-31 17:00 | EL DORADO PH 210119752 | 1946
35292145 | FRRB - EL DORADO PH 2101 - OH - 22 | 08W | Fire Rebuild | 0 | 11381 | 0 | 11381 | 2.1555 | 1.625 | 0.53049 | 0 | 2022-02-28 | 2022-02-28 | EL DORADO PH 210126000 | 2252
35295010 | FRRB - EL DORADO PH 2101 - UG - 25 | 08W | Fire Rebuild | 3379 | 0 | 0 | 3379 | 0.63996 | 0 | 0.63996 | 0 | 2022-04-01 08:00 | 2023-03-09 17:00 | EL DORADO PH 210126000 | 2252
35295011 | FRRB - EL DORADO PH 2101 - UG - 24 | 08W | Fire Rebuild | 950 | 0 | 0 | 950 | 0.17992 | 0 | 0.17992 | 0 | 2022-04-01 08:00 | 2023-03-09 17:00 | EL DORADO PH 210126000 | 2252
35295012 | FRRB - EL DORADO PH 2101 - UG - 23 | 08W | Fire Rebuild | 2112 | 0 | 0 | 2112 | 0.4 | 0 | 0.4 | 0 | 2022-04-01 08:00 | 2023-03-09 17:00 | EL DORADO PH 210126000 | 2252
35295013 | FRRB - EL DORADO PH 2101 - UG - 22 | 08W | Fire Rebuild | 739 | 0 | 0 | 739 | 0.13996 | 0 | 0.13996 | 0 | 2022-05-02 08:00 | 2023-03-09 17:00 | EL DORADO PH 210126000 | 2252
35295014 | FRRB - EL DORADO PH 2101 - UG - 21 | 08W | Fire Rebuild | 845 | 0 | 0 | 845 | 0.16004 | 0 | 0.16004 | 0 | 2022-05-02 08:00 | 2023-03-09 17:00 | EL DORADO PH 210126000 | 2252
35295015 | FRRB - EL DORADO PH 2101 - UG - 20 | 08W | Fire Rebuild | 1478 | 0 | 0 | 1478 | 0.27992 | 0 | 0.27992 | 0 | 2022-05-02 08:00 | 2023-03-09 17:00 | EL DORADO PH 210126000 | 2252
35295016 | FRRB - EL DORADO PH 2101 - UG - 19 | 08W | Fire Rebuild | 1637 | 0 | 0 | 1637 | 0.31004 | 0 | 0.31004 | 0 | 2022-05-02 08:00 | 2023-03-09 17:00 | EL DORADO PH 210126000 | 2252
35295017 | FRRB - EL DORADO PH 2101 - UG - 18 | 08W | Fire Rebuild | 2482 | 0 | 0 | 2482 | 0.47008 | 0 | 0.47008 | 0 | 2022-05-02 08:00 | 2023-03-09 17:00 | EL DORADO PH 210126000 | 2252
35295018 | FRRB - EL DORADO PH 2101 - UG - 17 | 08W | Fire Rebuild | 1954 | 0 | 0 | 1954 | 0.37008 | 0 | 0.37008 | 0 | 2022-05-02 08:00 | 2023-03-09 17:00 | EL DORADO PH 210126000 | 2252
35295019 | FRRB - EL DORADO PH 2101 - UG - 16 | 08W | Fire Rebuild | 5702 | 0 | 0 | 5702 | 1.0799 | 0 | 1.0799 | 0 | 2022-05-02 08:00 | 2023-03-09 17:00 | EL DORADO PH 210126000 | 2252
35295182 | FRRB - EL DORADO PH 2101 - UG - 2 | 08W | Fire Rebuild | 1373 | 0 | 0 | 1373 | 0.26004 | 0 | 0.26004 | 0 | 2022-05-02 08:00 | 2023-03-09 17:00 | EL DORADO PH 210126000 | 2252
35295184 | FRRB - EL DORADO PH 2101 - UG - 4 | 08W | Fire Rebuild | 2746 | 0 | 0 | 2746 | 0.52008 | 0 | 0.52008 | 0 | 2022-04-01 08:00 | 2023-03-09 17:00 | EL DORADO PH 210126000 | 2252
35295185 | FRRB - EL DORADO PH 2101 - UG - 5 | 08W | Fire Rebuild | 634 | 0 | 0 | 634 | 0.12008 | 0 | 0.12008 | 0 | 2022-04-01 08:00 | 2023-03-09 17:00 | EL DORADO PH 210126000 | 2252
35295186 | FRRB - EL DORADO PH 2101 - UG - 6 | 08W | Fire Rebuild | 6178 | 0 | 0 | 6178 | 1.1701 | 0 | 1.1701 | 0 | 2022-04-01 08:00 | 2023-03-09 17:00 | EL DORADO PH 210126000 | 2252
35295187 | FRRB - EL DORADO PH 2101 - UG - 7 | 08W | Fire Rebuild | 3379 | 0 | 0 | 3379 | 0.63996 | 0 | 0.63996 | 0 | 2022-04-01 08:00 | 2023-03-09 17:00 | EL DORADO PH 210126000 | 2252
35295188 | FRRB - EL DORADO PH 2101 - UG - 8 | 08W | Fire Rebuild | 3010 | 0 | 0 | 3010 | 0.57008 | 0 | 0.57008 | 0 | 2022-04-01 08:00 | 2023-03-09 17:00 | EL DORADO PH 210126000 | 2252
35295189 | FRRB - EL DORADO PH 2101 - UG - 9 | 08W | Fire Rebuild | 950 | 0 | 0 | 950 | 0.17992 | 0 | 0.17992 | 0 | 2022-04-01 08:00 | 2023-03-09 17:00 | EL DORADO PH 210126000 | 2252
35295190 | FRRB - EL DORADO PH 2101 - UG - 10 | 08W | Fire Rebuild | 1109 | 0 | 0 | 1109 | 0.21004 | 0 | 0.21004 | 0 | 2022-04-01 08:00 | 2023-03-09 17:00 | EL DORADO PH 210126000 | 2252
35295191 | FRRB - EL DORADO PH 2101 - UG - 11 | 08W | Fire Rebuild | 2065 | 0 | 0 | 2065 | 0.3911 | 0 | 0.3911 | 0 | 2022-04-01 08:00 | 2023-03-09 17:00 | EL DORADO PH 210126000 | 2252
35295192 | FRRB - EL DORADO PH 2101 - UG - 12 | 08W | Fire Rebuild | 1003 | 0 | 0 | 1003 | 0.18996 | 0 | 0.18996 | 0 | 2022-04-01 08:00 | 2023-03-09 17:00 | EL DORADO PH 210126000 | 2252
35295193 | FRRB - EL DORADO PH 2101 - UG - 13 | 08W | Fire Rebuild | 1162 | 0 | 0 | 1162 | 0.22008 | 0 | 0.22008 | 0 | 2022-05-02 08:00 | 2023-03-09 17:00 | EL DORADO PH 210126000 | 2252
35295194 | FRRB - EL DORADO PH 2101 - UG - 14 | 08W | Fire Rebuild | 739 | 0 | 0 | 739 | 0.13996 | 0 | 0.13996 | 0 | 2022-05-02 08:00 | 2023-03-09 17:00 | EL DORADO PH 210126000 | 2252
35295195 | FRRB - EL DORADO PH 2101 - UG - 15 | 08W | Fire Rebuild | 4858 | 0 | 0 | 4858 | 0.92008 | 0 | 0.92008 | 0 | 2022-05-02 08:00 | 2023-03-09 17:00 | EL DORADO PH 210126000 | 2252
35208069 | DR-POLE_IDLE_REMV - #3W ON LINE @ R/O 2 | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | EL DORADO PH 21026645 | 2469
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | 08W | SH | 0 | 3428 | 0 | 3428 | 0.64924 | 0 | 0.64924 | 0 | 2021-10-26 | 2022-02-18 08:00 | FORT BRAGG A 11013113 | 2140
35159826 | T2 REMV IDLE TX/SVC 35905 HAUSER BRI*PAR | 2AF | Idle Facilities | 0 | 0 | 80 | 80 | 0.015152 | 0 | 0.015152 | 0 |  |  | FORT ROSS 1121124 | 1022
35149328 | STS-COND_IDLE_REMV-JUNCTION OF FOURTH & | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | FORT SEWARD 1121CB | 566
35145540 | PSPS - FROGTOWN 1702 - CB | 08W | SH | 2846 | 3872 | 0 | 6718 | 1.2723 | 0 | 1.2723 | 0 | 2022-08-24 08:00 | 2023-02-21 17:00 | FROGTOWN 1702CB | 1316
35149060 | STS-COND_IDLE_REMV-2 SPANS S/O NEWTON RD | 2AF | Idle Facilities | 0 | 0 | 108 | 108 | 0.020455 | 0 | 0.020455 | 0 |  |  | FRUITLAND 1141200856 | 1867
35150991 | T2-POLE_IDLE_REMV - GIBNEY DR MIRANDA*RM | 2AF | Idle Facilities | 0 | 0 | 381 | 381 | 0.072159 | 0 | 0.072159 | 0 | 2022-02-07 | 2022-02-07 | FRUITLAND 114263170 | 1429
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | 08W | SH | 0 | 4422 | 0 | 4422 | 0.8375 | 0.11629 | 0.72121 | 0 | 2021-11-02 08:00 | 2022-02-24 | FULTON 1107604 | 637 | 35192292
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | 08W | SH | 0 | 4190 | 0 | 4190 | 0.79356 | 0 | 0.79356 | 0 | 2021-11-02 08:00 | 2022-02-17 | FULTON 1107604 | 637 | 35192292
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | 08W | SH | 0 | 4420 | 0 | 4420 | 0.83712 | 0 | 0.83712 | 0 | 2021-11-02 08:00 | 2022-03-10 08:00 | FULTON 1107604 | 637 | 35192292
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | 08W | SH | 9424 | 1029 | 0 | 10453 | 1.9797 | 0 | 1.9797 | 0 | 2022-03-15 08:00 | 2022-10-21 17:00 | FULTON 1107604 | 637 | 35192292
31547582 | T2 CARIBOU #2 - 60 KV_;001/001 | 92F | Fire Rebuild | 0 | 5352 | 0 | 5352 | 1.0136 | 0 | 1.0136 | 0 |  |  | GANSNER 11012424 | 1172
35279307 | FRRB - GANSNER 11012424 UG PH1.2 | 08W | Fire Rebuild | 11880 | 0 | 0 | 11880 | 2.25 | 0 | 2.25 | 0 | 2022-08-23 08:00 | 2022-12-23 17:00 | GANSNER 11012424 | 1172
35279313 | FRRB - GANSNER 11012424 UG PH1.1 | 08W | Fire Rebuild | 2428 | 0 | 0 | 2428 | 0.45985 | 0 | 0.45985 | 0 | 2022-12-13 08:00 | 2023-04-14 17:00 | GANSNER 11012424 | 1172
35150549 | STS-COND_IDLE_REMV-3E\O 3S\O 1E\O 2N\O 6 | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 | 2022-01-24 | 2022-01-24 | GARBERVILLE 11011604 | 522
35037707 | DR POLES_IDLE_REMV-25 POLES E/0 #4269 | 2AF | Idle Facilities | 0 | 0 | 1153 | 1153 | 0.21837 | 0 | 0.21837 | 0 |  |  | GARBERVILLE 110139524 | 1245
35150103 | REMV IDLE 3 LOCS 2615 BRICELAND RD*RMTC | 2AF | Idle Facilities | 0 | 0 | 203 | 203 | 0.038447 | 0 | 0.038447 | 0 | 2022-02-10 | 2022-02-10 | GARBERVILLE 11021510 | 1476
35037706 | T2 REMV IDLE -WOLF RANCH/WOLF RD*RMTC | 2AF | Idle Facilities | 0 | 0 | 131 | 131 | 0.024811 | 0 | 0.024811 | 0 | 2021-01-05 | 2022-01-31 | GARBERVILLE 11022500 | 1149
35208094 | FT STS-TRAN_IDLE_REMV-2W/O6NW/O 7251 WIL | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | GARBERVILLE 110237054 | 1237
35208076 | COND_IDLE_REMV-11100 BRICELANDRD | 2AF | Idle Facilities | 0 | 0 | 487 | 487 | 0.092235 | 0 | 0.092235 | 0 |  |  | GARBERVILLE 11026084 | 1777
35244151 | FT-POLE_IDLE_REMV - A/F 15E/O A/F 13600 | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | GARBERVILLE 11026084 | 1777
35255487 | T2 REMV IDLE FAC 4 LOCS 3220 PASSALACQUA | 2AF | Idle Facilities | 0 | 0 | 1152 | 1152 | 0.21818 | 0 | 0.21818 | 0 |  |  | GEYSERVILLE 1102274 | 940
35223270 | DR~T3 REMV IDLE TX POLE 7205 GEYSER RD | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | GEYSERVILLE 1102484 | 668
35224947 | +STS-COND_IDLE_REMV-1\P\N\O\2212 STENNER | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | GOLDTREE 1105CB | 1104
35211639 | DR~STS-COND_IDLE_REMV-12621 ALLISON RANC | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | GRASS VALLEY 11012208 | 1973
35211204 | FT-COND_IDLE_REMV-15960 LE TOURNEAU LN | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | GRASS VALLEY 11032180 | 524
35281758 | FRRB - GRAYS FLAT 0401904916 PH1.1 | 08W | Fire Rebuild | 7392 | 0 | 0 | 7392 | 1.4 | 0 | 1.4 | 0 | 2022-02-25 08:00 | 2022-06-29 17:00 | GRAYS FLAT 0401CB | 1748
35009378 | FT~STS-COND_IDLE_REMV-1405 CLOVERDALE RD | 2AF | Idle Facilities | 0 | 0 | 3188 | 3188 | 0.60379 | 0 | 0.60379 | 0 |  |  | HALF MOON BAY 11036012 | 2186
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | 08W | Fire Rebuild | 4555 | 0 | 0 | 4555 | 0.86269 | 0 | 0.86269 | 0 | 2021-07-27 | 2022-02-04 | HALF MOON BAY 11036012 | 2186
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | 08W | Fire Rebuild | 11774 | 0 | 0 | 11774 | 2.2299 | 0 | 2.2299 | 0 | 2022-11-01 08:00 | 2023-03-10 17:00 | HALF MOON BAY 110369412 | 2055
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | 08W | Fire Rebuild | 15312 | 0 | 0 | 15312 | 2.9 | 0 | 2.9 | 0 | 2022-07-15 08:00 | 2022-11-10 17:00 | HALF MOON BAY 110369412 | 2055
35244167 | FT-COND_IDLE_REMV-WINCHESTER DR | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | HALSEY 11011704 | 2500
35037563 | DR-COND_IDLE_REMV-4966 CANYON DR | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | HARRIS 11082062 | 3118
35205102 | DR-COND_IDLE_REMV-1W/O 1S/O 1226 FRE | 2AF | Idle Facilities | 0 | 0 | 580 | 580 | 0.10985 | 0 | 0.10985 | 0 |  |  | HARRIS 1109355914 | 2462
35151026 | 8/31-REMV IDLE 3 LOCS 2537 DESSIE | 2AF | Idle Facilities | 0 | 0 | 536 | 536 | 0.10152 | 0 | 0.10152 | 0 | 2022-01-20 | 2022-01-20 | HARTLEY 1101658 | 439
35224893 | STS-COND_IDLE_REMV - #1 N/O CARMEL VLY R | 2AF | Idle Facilities | 0 | 0 | 240 | 240 | 0.045455 | 0 | 0.045455 | 0 |  |  | HATTON 110137088 | 2887
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | 08W | SH | 0 | 14398 | 0 | 14398 | 2.7269 | 0 | 2.7269 | 0 | 2022-05-13 08:00 | 2022-09-26 08:00 | HIGHLANDS 1102628 | 27 | 35219099
35231621 | CWSP - HIGHLANDS 1102628 PH 1.3 | 08W | SH | 7210 | 0 | 0 | 7210 | 1.3655 | 0 | 1.3655 | 0 |  |  | HIGHLANDS 1102628 | 27 | 35219099
35231626 | CWSP - HIGHLANDS 1102628 PH 1.8 | 08W | SH | 0 | 3607 | 0 | 3607 | 0.68314 | 0 | 0.68314 | 0 | 2022-05-26 08:00 | 2022-12-07 17:00 | HIGHLANDS 1102628 | 27 | 35219099
35231627 | CWSP - HIGHLANDS 1102628 PH 1.9 | 08W | SH | 0 | 2105 | 0 | 2105 | 0.39867 | 0 | 0.39867 | 0 | 2022-06-27 08:00 | 2022-09-27 08:00 | HIGHLANDS 1102628 | 27 | 35219099
35231630 | OCGC-CWSP - HIGHLANDS 1102628 PH 1.12 | 08W | SH | 0 | 1883 | 0 | 1883 | 0.35663 | 0 | 0.35663 | 0 | 2022-01-17 | 2022-02-04 08:00 | HIGHLANDS 1102628 | 27 | 35219099
35231631 | CWSP - HIGHLANDS 1102628 PH 1.13 | 08W | SH | 0 | 2465 | 0 | 2465 | 0.46686 | 0 | 0.46686 | 0 | 2022-06-27 08:00 | 2022-09-27 08:00 | HIGHLANDS 1102628 | 27 | 35219099
35149235 | 8/31-REMV IDLE 6 LOCS 13311 HWY 29 HOLD | 2AF | Idle Facilities | 0 | 0 | 872 | 872 | 0.16515 | 0 | 0.16515 | 0 |  |  | HIGHLANDS 11031282 | 626
35208097 | 8/31-REMV IDLE 19824 MORGAN HOLD FOR 10J | 2AF | Idle Facilities | 0 | 0 | 90 | 90 | 0.017045 | 0 | 0.017045 | 0 |  |  | HIGHLANDS 1103482 | 181
35150641 | T2-COND_IDLE_REMV-16853 DAM RD *KS | 2AF | Idle Facilities | 0 | 0 | 380 | 380 | 0.07197 | 0 | 0.07197 | 0 | 2022-03-24 | 2022-03-24 | HIGHLANDS 1103568 | 212
35037377 | DR POD POLE_IDLE_REMV-18TH AVE. | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 | 2022-01-31 | 2022-02-04 | HIGHLANDS 1103CB | 461
35211257 | FT STS-COND_IDLEREMV-F/O15565 37THAVE 1/ | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | HIGHLANDS 110448262 | 3295
35149246 | STS-COND_IDLE_REMV-16251 HWY 101*JM | 2AF | Idle Facilities | 0 | 0 | 965 | 965 | 0.18277 | 0 | 0.18277 | 0 | 2022-04-19 | 2022-04-19 | HOPLAND 1101768 | 110
35078377 | DR-TRAN_IDLE_REMV - 8252 TWIN ROCKS GRA | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | HORSESHOE 110450142 | 2708
35275961 | FT-POLE_IDLE_REMV-13116 A/F GAS POINT R | 2AF | Idle Facilities | 0 | 0 | 747 | 747 | 0.14148 | 0 | 0.14148 | 0 |  |  | JESSUP 110141356 | 350
35211630 | DR~COND_IDLE_REMV-18929 NEW YORK FLAT | 2AF | Idle Facilities | 0 | 0 | 317 | 317 | 0.060038 | 0 | 0.060038 | 0 |  |  | KANAKA 110165606 | 1201
35294385 | FRRB - KANAKA 1101CB - K4 SM4 | 08W | Fire Rebuild | 0 | 193 | 0 | 193 | 0.036553 | 0 | 0.036553 | 0 | 2022-01-13 | 2022-01-14 | KANAKA 1101CB | 1480
35282131 | FRRB - KANAKA 1101CB - K1 SM1 | 08W | Fire Rebuild | 203 | 0 | 0 | 203 | 0.038447 | 0 | 0.038447 | 0 | 2021-12-10 | 2022-02-28 17:00 | KANAKA 1101CB | 1480
35254695 | FRRB - KANAKA 1101CB - K2 SM2 | 08W | Fire Rebuild | 292 | 0 | 0 | 292 | 0.055303 | 0 | 0.055303 | 0 | 2021-12-04 | 2022-01-26 | KANAKA 1101CB | 1480
35250343 | FRRB - KANAKA 1101CB - K2 SM1 | 08W | Fire Rebuild | 1554 | 0 | 0 | 1554 | 0.29432 | 0 | 0.29432 | 0 | 2021-11-30 | 2022-01-26 | KANAKA 1101CB | 1480
35245140 | FRRB - KANAKA 1101 - K4 PH 4.5 | 08W | Fire Rebuild | 0 | 1435 | 0 | 1435 | 0.27178 | 0 | 0.27178 | 0 | 2022-02-21 | 2022-10-10 17:00 | KANAKA 1101CB | 1480 | 35244696
35236985 | FRRB - KANAKA 1101 - K1 PH 1.1 | 08W | Fire Rebuild | 10906 | 0 | 0 | 10906 | 2.0655 | 0 | 2.0655 | 0 | 2022-02-14 08:00 | 2022-03-31 17:00 | KANAKA 1101CB | 1480
35236992 | FRRB - KANAKA 1101 - K1 PH 1.2 | 08W | Fire Rebuild | 3727 | 0 | 0 | 3727 | 0.70587 | 0 | 0.70587 | 0 | 2022-03-01 | 2022-03-31 17:00 | KANAKA 1101CB | 1480
35235702 | FRRB - KANAKA 1101 - K3 PH 3 | 08W | Fire Rebuild | 9691 | 0 | 0 | 9691 | 1.8354 | 0 | 1.8354 | 0 | 2022-02-07 08:00 | 2022-03-31 17:00 | KANAKA 1101CB | 1480
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | SH | 4515 | 0 | 0 | 4515 | 0.85511 | 0 | 0.85511 | 0 | 2022-09-26 08:00 | 2023-02-16 17:00 | KESWICK 11011586 | 7 | 35217272
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | SH | 25376 | 0 | 0 | 25376 | 4.8061 | 0 | 4.8061 | 0 | 2022-09-12 08:00 | 2022-12-13 17:00 | KESWICK 11011586 | 7 | 35217272
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | SH | 0 | 7392 | 177 | 7569 | 1.4335 | 0 | 1.4335 | 0 | 2021-10-27 08:00 | 2022-03-12 | KESWICK 11011586 | 7 | 35217272
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | SH | 1584 | 0 | 0 | 1584 | 0.3 | 0 | 0.3 | 0 | 2022-05-26 08:00 | 2022-11-09 17:00 | KESWICK 11011586 | 7 | 35217272
35211753 | FT~STS-OFAC_IDL_REM-10937-10963 IRON MON | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | KESWICK 11011590 | 848
35205028 | DR-STS-COND_IDLE_REMV-7140KELSEYCREEKDRI | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | KONOCTI 110264664 | 168
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | 08W | SH | 0 | 4661 | 0 | 4661 | 0.88277 | 0 | 0.88277 | 0 | 2022-03-31 08:00 | 2022-06-28 17:00 | KONOCTI 1102965078 | 9 | 35217270
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | 08W | SH | 0 | 4469 | 3340 | 7809 | 1.479 | 0 | 1.479 | 0 | 2022-03-31 08:00 | 2022-06-28 17:00 | KONOCTI 1102965078 | 9 | 35217270
35037896 | DR~REMV IDLE FAC 9 POLES 7769 HWY 29 | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 | 2021-01-05 | 2022-02-16 | KONOCTI 1102965078 | 9
35150135 | REMV IDLE 2 LOCS -8120 HWY 29 KELSEY | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | KONOCTI 1102CB | 407
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | 08W | SH | 8410 | 0 | 0 | 8410 | 1.5928 | 0 | 1.5928 | 0 | 2022-04-27 08:00 | 2022-09-08 08:00 | LAS GALLINAS A 110599904 | 215 | 35191319
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | 08W | SH | 6767 | 0 | 0 | 6767 | 1.2816 | 0 | 1.2816 | 0 | 2022-04-05 08:00 | 2022-10-14 17:00 | LAS GALLINAS A 110599904 | 215 | 35191319
35255493 | V-4533 ARROYO RD./2PSE | 2AF | Idle Facilities | 0 | 0 | 666 | 666 | 0.12614 | 0 | 0.12614 | 0 |  |  | LAS POSITAS 2108MR182 | 803
35038684 | REMV IDLE 4 LOCS 48600 VALLEY DR LAY | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | LAYTONVILLE 1101402 | 1293
35132573 | STS-COND_IDLE_REMV-2538 LAYTON DOS RIOS | 2AF | Idle Facilities | 0 | 0 | 360 | 360 | 0.068182 | 0 | 0.068182 | 0 |  |  | LAYTONVILLE 1102CB | 786
35208072 | DR STS-OFAC_IDLE_REMV -2PS3PE OF 465 OA | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 | 2021-12-28 | 2022-02-23 | LINCOLN 11012310 | 1408
35244172 | STS-POLE_IDLE_REMV-4335 GARDEN BAR RD CO | 2AF | Idle Facilities | 0 | 0 | 862 | 862 | 0.16326 | 0 | 0.16326 | 0 | 2021-11-16 | 2022-02-12 | LINCOLN 11042070 | 568
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | 08W | SH | 0 | 4483 | 0 | 4483 | 0.84905 | 0 | 0.84905 | 0 |  | 2022-07-07 17:00 | LOS GATOS 1106LB44 | 1864
35247031 | STS-POLE_IDLE_REMV - 19025 LAUREL DR /1P | 2AF | Idle Facilities | 0 | 0 | 791 | 791 | 0.14981 | 0 | 0.14981 | 0 |  |  | LOS GATOS 1106LB44 | 1864
35126503 | STS-COND_IDLE_REMV-17820 ALMA BRIDGE RD | 2AF | Idle Facilities | 0 | 0 | 220 | 220 | 0.041667 | 0 | 0.041667 | 0 |  |  | LOS GATOS 1107CB | 2606
35037897 | DR POD COND_IDLE_REMV-6069 ROLAND DR | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 | 2022-01-31 | 2022-02-04 | LUCERNE 1106CB | 2687
35277148 | STS-POLE_IDLE_REMV-1PW 1PN 1PW 5219 FOUR | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | MARIPOSA 2101309438 | 605
35238088 | REMG 531 - MARIPOSA 2101,SLAUGHTER HOUSE | 08W | SH | 0 | 0 | 5280 | 5280 | 1 | 0 | 1 | 0 | 2022-07-11 08:00 | 2022-11-21 17:00 | MARIPOSA 210135244 | 428
35083807 | STS-COND_IDLE_REMV-5461 COLORADO RD | 2AF | Idle Facilities | 0 | 0 | 77 | 77 | 0.014583 | 0 | 0.014583 | 0 |  |  | MARIPOSA 2101752630 | 700
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 | 08W | SH | 0 | 619 | 1522 | 2141 | 0.40549 | 0 | 0.40549 | 0 | 2022-01-26 | 2022-02-24 17:00 | MARIPOSA 210197142 | 36 | 35219268
35219587 | CWSP - MARIPOSA 2102440236 PH1.2 | 08W | SH | 0 | 10718 | 0 | 10718 | 2.0299 | 0 | 2.0299 | 0 | 2022-05-24 08:00 | 2022-09-16 17:00 | MARIPOSA 2102440236 | 50 | 35219267
35219588 | CWSP - MARIPOSA 2102440236 PH1.3 | 08W | SH | 0 | 7339 | 0 | 7339 | 1.39 | 0 | 1.39 | 0 | 2022-04-22 08:00 | 2022-09-02 | MARIPOSA 2102440236 | 50 | 35219267
35219267 | CWSP - MARIPOSA 2102440236 PH1.1 | 08W | SH | 0 | 8715 | 272 | 8987 | 1.7021 | 0 | 1.7021 | 0 | 2022-02-08 08:00 | 2022-04-06 17:00 | MARIPOSA 2102440236 | 50 | 35219267
35219266 | CWSP - MARIPOSA 2102CB PH 1 | 08W | SH | 0 | 15708 | 0 | 15708 | 2.975 | 0 | 2.975 | 0 | 2021-10-21 08:00 | 2022-03-31 17:00 | MARIPOSA 2102CB | 35 | 35219266
35234526 | PSPS - MARTELL 1101 - SUTTER CREEK PH1.3 | 08W | SH | 7089 | 0 | 0 | 7089 | 1.3426 | 0 | 1.3426 | 0 | 2022-03-30 08:00 | 2022-08-30 17:00 | MARTELL 1101CB | 999 | 35223038
35234284 | PSPS - MARTELL 1101 - SUTTER CREEK PH1.2 | 08W | SH | 0 | 1270 | 0 | 1270 | 0.24053 | 0 | 0.24053 | 0 | 2022-03-30 08:00 | 2022-07-26 17:00 | MARTELL 1101CB | 999 | 35223038
35223038 | PSPS - MARTELL 1101 - SUTTER CREEK PH1.1 | 08W | SH | 2814 | 0 | 0 | 2814 | 0.53295 | 0 | 0.53295 | 0 | 2022-03-30 08:00 | 2022-10-11 17:00 | MARTELL 1101CB | 999 | 35223038
35083888 | STS-COND_IDLE_REMV-#2W ON LINE A/F 916 N | 2AF | Idle Facilities | 0 | 0 | 382 | 382 | 0.072348 | 0 | 0.072348 | 0 |  |  | MARTELL 110292172 | 2054
35211249 | DR-FT-COND_IDLE_REMV-RITTER ROAD | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | MC ARTHUR 11011490 | 1181
35038562 | DR COND_IDLE_REMV-4700 JENKINS RD | 2AF | Idle Facilities | 0 | 0 | 290 | 290 | 0.054924 | 0 | 0.054924 | 0 |  |  | MENDOCINO 110148750 | 1073
35223241 | DR~STS-COND_IDLE_REMV-R/O 5500 ALPINE R | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | MENLO 11028896 | 1917
35155226 | STS-OFAC_IDLE_REMV - #1 E/O 152 LA HONDA | 2AF | Idle Facilities | 0 | 0 | 222 | 222 | 0.042045 | 0 | 0.042045 | 0 |  |  | MENLO 1102W80 | 620
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | 08W | SH | 0 | 3296 | 337 | 3633 | 0.68807 | 0 | 0.68807 | 0 | 2022-04-11 08:00 | 2022-06-08 17:00 | MIDDLETOWN 1101118494 | 23 | 35219098
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | 08W | SH | 3093 | 0 | 0 | 3093 | 0.5858 | 0 | 0.5858 | 0 | 2022-04-01 08:00 | 2022-09-30 17:00 | MIDDLETOWN 1101118494 | 23 | 35219098
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | 08W | SH | 0 | 7279 | 0 | 7279 | 1.3786 | 0 | 1.3786 | 0 | 2021-10-01 | 2022-03-22 08:00 | MIDDLETOWN 11014646 | 328
35137596 | OCGC WSP-ECOP-MIDDLETOWN1101-LR 4646-H08 | 08W | SH | 0 | 5341 | 0 | 5341 | 1.0116 | 0 | 1.0116 | 0 |  |  | MIDDLETOWN 11014646 | 328
35219272 | CWSP - MIDDLETOWN 1101481876 | 08W | SH | 0 | 4224 | 0 | 4224 | 0.8 | 0 | 0.8 | 0 | 2021-11-03 08:00 | 2022-03-04 08:00 | MIDDLETOWN 1101481876 | 38
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | 08W | SH | 0 | 4013 | 0 | 4013 | 0.76004 | 0 | 0.76004 | 0 | 2022-06-27 08:00 | 2023-01-06 17:00 | MIDDLETOWN 110148212 | 468 | 35192282
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | 08W | SH | 0 | 6072 | 0 | 6072 | 1.15 | 0 | 1.15 | 0 | 2022-04-26 08:00 | 2022-09-29 17:00 | MIDDLETOWN 110148212 | 468 | 35192282
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 | 08W | SH | 0 | 3943 | 0 | 3943 | 0.74678 | 0 | 0.74678 | 0 | 2022-02-14 08:00 | 2022-05-04 17:00 | MIDDLETOWN 110148212 | 468 | 35192282
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | 08W | SH | 0 | 4171 | 0 | 4171 | 0.78996 | 0 | 0.78996 | 0 | 2022-05-02 | 2022-07-14 17:00 | MIDDLETOWN 110148212 | 468 | 35192281
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | 08W | SH | 0 | 3168 | 0 | 3168 | 0.6 | 0 | 0.6 | 0 | 2022-05-02 | 2022-05-23 17:00 | MIDDLETOWN 110148212 | 468 | 35192281
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | 08W | SH | 0 | 5491 | 0 | 5491 | 1.04 | 0 | 1.04 | 0 | 2022-05-02 | 2022-06-20 17:00 | MIDDLETOWN 110148212 | 468 | 35192281
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | 08W | SH | 7287 | 0 | 0 | 7287 | 1.3801 | 0 | 1.3801 | 0 | 2022-05-05 08:00 | 2022-10-10 17:00 | MIDDLETOWN 110148212 | 468 | 35192281
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | 08W | SH | 8184 | 0 | 0 | 8184 | 1.55 | 0 | 1.55 | 0 | 2022-08-12 08:00 | 2023-01-17 17:00 | MIDDLETOWN 110148212 | 468 | 35192281
35236437 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.7 | 08W | SH | 0 | 1998 | 0 | 1998 | 0.37841 | 0 | 0.37841 | 0 | 2022-03-23 08:00 | 2022-06-09 17:00 | MIDDLETOWN 110148212 | 468 | 35192281
35236438 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.8 | 08W | SH | 0 | 2744 | 0 | 2744 | 0.5197 | 0 | 0.5197 | 0 | 2022-02-15 08:00 | 2022-04-13 17:00 | MIDDLETOWN 110148212 | 468 | 35192281
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | 08W | SH | 0 | 2756 | 0 | 2756 | 0.52197 | 0 | 0.52197 | 0 | 2022-03-22 08:00 | 2022-05-02 17:00 | MIDDLETOWN 110148212 | 468 | 35192281
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | 08W | SH | 9820 | 0 | 0 | 9820 | 1.8598 | 0 | 1.8598 | 0 | 2022-11-14 08:00 | 2023-04-28 17:00 | MIDDLETOWN 1101548 | 474 | 35174501
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | 08W | SH | 5914 | 0 | 0 | 5914 | 1.1201 | 0 | 1.1201 | 0 |  |  | MIDDLETOWN 1101548 | 474 | 35174479
35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 | 08W | SH | 2534 | 0 | 0 | 2534 | 0.47992 | 0 | 0.47992 | 0 | 2022-04-25 08:00 | 2022-10-04 17:00 | MIDDLETOWN 1101548 | 474 | 35174479
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | 08W | SH | 4488 | 0 | 0 | 4488 | 0.85 | 0 | 0.85 | 0 | 2022-11-25 08:00 | 2023-04-14 17:00 | MIDDLETOWN 1101548 | 474 | 35174478
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | 08W | SH | 0 | 3485 | 0 | 3485 | 0.66004 | 0 | 0.66004 | 0 | 2022-11-18 08:00 | 2023-03-21 17:00 | MIDDLETOWN 1101548 | 474 | 35174478
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | 08W | SH | 0 | 3062 | 0 | 3062 | 0.57992 | 0 | 0.57992 | 0 | 2022-11-18 08:00 | 2023-04-07 17:00 | MIDDLETOWN 1101548 | 474 | 35174478
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | 08W | SH | 0 | 3348 | 0 | 3348 | 0.63409 | 0 | 0.63409 | 0 | 2022-03-07 08:00 | 2022-05-26 17:00 | MIDDLETOWN 1101548 | 474 | 35174479
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | 08W | SH | 0 | 1926 | 0 | 1926 | 0.36477 | 0 | 0.36477 | 0 | 2022-03-01 | 2022-04-30 | MIDDLETOWN 1101548 | 474 | 35174479
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | 08W | SH | 0 | 1238 | 0 | 1238 | 0.23447 | 0 | 0.23447 | 0 | 2022-03-01 | 2022-04-30 | MIDDLETOWN 1101548 | 474 | 35174479
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | 08W | SH | 0 | 2980 | 0 | 2980 | 0.56439 | 0 | 0.56439 | 0 | 2022-03-01 | 2022-04-30 | MIDDLETOWN 1101548 | 474 | 35174479
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | 08W | SH | 0 | 2197 | 0 | 2197 | 0.4161 | 0 | 0.4161 | 0 | 2022-03-07 08:00 | 2022-06-02 17:00 | MIDDLETOWN 1101548 | 474 | 35174479
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | 08W | SH | 0 | 1115 | 2395 | 3510 | 0.66477 | 0 | 0.66477 | 0 | 2022-03-07 08:00 | 2022-06-02 17:00 | MIDDLETOWN 1101548 | 474 | 35174479
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | 08W | SH | 1839 | 0 | 0 | 1839 | 0.3483 | 0 | 0.3483 | 0 |  |  | MIDDLETOWN 1101548 | 474 | 35174479
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | 08W | SH | 0 | 1805 | 0 | 1805 | 0.34186 | 0 | 0.34186 | 0 | 2022-11-18 08:00 | 2023-04-07 17:00 | MIDDLETOWN 1101548 | 474 | 35174501
35150566 | REMV IDLE 2 LOCS HIGHWAY 175 MIDDLETOWN | 2AF | Idle Facilities | 0 | 0 | 167 | 167 | 0.031629 | 0 | 0.031629 | 0 |  |  | MIDDLETOWN 1101548 | 474
35244105 | DR-COND_IDLE_REMV-20095 HWY 175 | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | MIDDLETOWN 1101548 | 474
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | 08W | SH | 0 | 2075 | 0 | 2075 | 0.39299 | 0 | 0.39299 | 0 | 2021-11-15 | 2022-03-21 08:00 | MIDDLETOWN 1101CB | 86
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | 08W | SH | 1690 | 0 | 0 | 1690 | 0.32008 | 0 | 0.32008 | 0 |  |  | MIDDLETOWN 1102302610 | 8 | 35217269
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | 08W | SH | 0 | 2429 | 0 | 2429 | 0.46004 | 0 | 0.46004 | 0 | 2022-03-31 08:00 | 2022-06-14 17:00 | MIDDLETOWN 1102302610 | 8 | 35217269
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | 08W | SH | 0 | 2731 | 0 | 2731 | 0.51723 | 0 | 0.51723 | 0 | 2022-03-31 08:00 | 2022-06-28 17:00 | MIDDLETOWN 1102302610 | 8 | 35217269
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | 08W | SH | 0 | 10507 | 0 | 10507 | 1.99 | 0 | 1.99 | 0 | 2022-07-20 08:00 | 2023-01-31 17:00 | MIDDLETOWN 1102302610 | 8 | 35217269
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | 08W | SH | 0 | 2270 | 0 | 2270 | 0.42992 | 0 | 0.42992 | 0 | 2022-05-26 08:00 | 2022-12-07 17:00 | MIDDLETOWN 1102302610 | 8 | 35217269
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | 08W | SH | 1478 | 0 | 0 | 1478 | 0.27992 | 0 | 0.27992 | 0 | 2022-08-04 08:00 | 2023-02-15 17:00 | MIDDLETOWN 1103830 | 14 | 35220896
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | 08W | SH | 0 | 4699 | 0 | 4699 | 0.88996 | 0 | 0.88996 | 0 | 2022-04-01 08:00 | 2022-04-29 17:00 | MIDDLETOWN 1103830 | 14 | 35222045
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | 08W | SH | 5333 | 0 | 0 | 5333 | 1.01 | 0 | 1.01 | 0 | 2022-05-18 08:00 | 2022-11-29 17:00 | MIDDLETOWN 1103830 | 14 | 35220896
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | 08W | SH | 9504 | 0 | 0 | 9504 | 1.8 | 0 | 1.8 | 0 | 2022-07-06 08:00 | 2023-01-17 17:00 | MIDDLETOWN 1103830 | 14 | 35220896
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | 08W | SH | 8290 | 0 | 0 | 8290 | 1.5701 | 0 | 1.5701 | 0 | 2022-08-04 08:00 | 2023-02-15 17:00 | MIDDLETOWN 1103830 | 14 | 35220896
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | 08W | SH | 0 | 7665 | 0 | 7665 | 1.4517 | 0 | 1.4517 | 0 | 2022-02-08 08:00 | 2022-05-19 17:00 | MIDDLETOWN 1103830 | 14 | 35217271
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | 08W | SH | 0 | 6513 | 0 | 6513 | 1.2335 | 0 | 1.2335 | 0 | 2022-02-15 08:00 | 2022-04-14 17:00 | MIDDLETOWN 1103830 | 14 | 35217271
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | 08W | SH | 0 | 4196 | 0 | 4196 | 0.7947 | 0 | 0.7947 | 0 | 2022-02-08 08:00 | 2022-03-31 17:00 | MIDDLETOWN 1103830 | 14 | 35217271
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | 08W | SH | 3274 | 0 | 0 | 3274 | 0.62008 | 0 | 0.62008 | 0 |  |  | MIDDLETOWN 1103830 | 14 | 35217271
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | 08W | SH | 0 | 5187 | 0 | 5187 | 0.98239 | 0.052652 | 0.92973 | 0 | 2021-11-08 08:00 | 2022-03-17 17:00 | MIDDLETOWN 1103830 | 14 | 35217271
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | 08W | SH | 0 | 2112 | 0 | 2112 | 0.4 | 0 | 0.4 | 0 | 2022-03-31 08:00 | 2022-09-05 17:00 | MIDDLETOWN 1103830 | 14 | 35217271
35236661 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 | 08W | SH | 0 | 1067 | 0 | 1067 | 0.20208 | 0 | 0.20208 | 0 | 2022-03-31 08:00 | 2022-06-07 17:00 | MIDDLETOWN 1103830 | 14 | 35220895
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | 08W | SH | 0 | 7349 | 0 | 7349 | 1.3919 | 1.0422 | 0.34962 | 0 |  |  | MIWUK 1701953336 | 2267
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | 08W | SH | 0 | 7239 | 0 | 7239 | 1.371 | 0 | 1.371 | 0 | 2022-03-09 08:00 | 2022-08-22 17:00 | MIWUK 1701953336 | 2267
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | 08W | SH | 0 | 8082 | 0 | 8082 | 1.5307 | 0 | 1.5307 | 0 | 2022-03-17 08:00 | 2022-08-12 17:00 | MIWUK 1701953336 | 2267
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | 08W | SH | 0 | 10903 | 0 | 10903 | 2.065 | 0.38883 | 1.6761 | 0 | 2021-04-13 | 2022-03-18 17:00 | MIWUK 170238218 | 2678
35243374 | DR~--REMV IDLE 5 LOCS 3560 MONTICELLO R | 2AF | Idle Facilities | 0 | 0 | 3256 | 3256 | 0.61667 | 0 | 0.61667 | 0 |  |  | MONTICELLO 11014360 | 757
35145003 | PSPS CWSP - MORAGA 1103 - CB | 08W | SH | 643 | 660 | 1346 | 2649 | 0.5017 | 0 | 0.5017 | 0 | 2021-11-10 | 2022-03-25 | MORAGA 1103CB | 2631
35221620 | STS-COND_IDLE_REMV-12345 HERITAGE WAY | 2AF | Idle Facilities | 0 | 0 | 225 | 225 | 0.042614 | 0 | 0.042614 | 0 |  |  | MORGAN HILL 2105XR176 | 854
35224941 | STS-COND_IDLE_REMV-R/O 2PE 1PS/O #67 BLU | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | MORRO BAY 1102CB | 2399
35225009 | STS-COND_IDLE_REMV - 6/P/NW/1/P/E/O 2289 | 2AF | Idle Facilities | 0 | 0 | 445 | 445 | 0.08428 | 0 | 0.08428 | 0 |  |  | MORRO BAY 1102W34 | 2590
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | 08W | SH | 11101 | 0 | 0 | 11101 | 2.1025 | 0 | 2.1025 | 0 | 2022-01-18 | 2022-07-29 17:00 | MOUNTAIN QUARRIES 21016953 | 45 | 35219281
35232650 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.2 | 08W | SH | 7100 | 0 | 0 | 7100 | 1.3447 | 0 | 1.3447 | 0 | 2022-04-11 08:00 | 2022-09-16 17:00 | MOUNTAIN QUARRIES 21016953 | 45 | 35219281
35217564 | DR-COND_IDLE_REMV - 1PWO 11188 TOWNSHIP | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | NARROWS 21011202 | 758
35244154 | STS-COND_IDLE_REMV-18610 KENTUCKY RAVINE | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | NARROWS 21022220 | 505
35211601 | FT~STS-COND_IDLE_REMV -10955 ROUGH & REA | 2AF | Idle Facilities | 0 | 0 | 188 | 188 | 0.035606 | 0 | 0.035606 | 0 |  |  | NARROWS 21052216 | 737
35211618 | FT~STS-COND_IDLE_REMV-SCHMIDT CT | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | NARROWS 210551582 | 582
35186134 | 8/31-REMV IDLE 3 LOCS 10985 HOUGHTON RAN | 2AF | Idle Facilities | 0 | 0 | 319 | 319 | 0.060417 | 0 | 0.060417 | 0 |  | 2022-03-25 | NARROWS 2105CB | 730
35241060 | REMG 581 - OAKHURST 1101, MIAMI MOUNTAIN | 08W | SH | 0 | 0 | 7920 | 7920 | 1.5 | 0 | 1.5 | 0 | 2022-07-14 08:00 | 2022-10-20 17:00 | OAKHURST 110110090 | 421
35223037 | PSPS - OAKHURST 1101 - OAKHURST | 08W | SH | 0 | 0 | 42 | 42 | 0.0079545 | 0 | 0.0079545 | 0 | 2021-04-07 08:00 | 2022-03-03 17:00 | OAKHURST 1101CB | 847
35225441 | +STS-COND_IDLE_REMV-73580 PLEYTO CEMETAR | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | OILFIELDS 1103N48 | 508
35204811 | FT~STS-POLE_IDL_REMV-4 POLES S/O CO#2413 | 2AF | Idle Facilities | 0 | 0 | 660 | 660 | 0.125 | 0 | 0.125 | 0 |  |  | OREGON TRAIL 11021584 | 1773
35211225 | DR-COND_IDLE_REMV-11762 MCELROY LN | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | OREGON TRAIL 110249144 | 968
35211643 | DR-STS-COND_IDLE_REMV-6 PLS W/O 11554 ON | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | OREGON TRAIL 11031500 | 981
35262346 | DR-STS-POLE_IDLE_REMV-1S/O17160KESWICKDA | 2AF | Idle Facilities | 0 | 0 | 745 | 745 | 0.1411 | 0 | 0.1411 | 0 |  |  | OREGON TRAIL 11031500 | 981
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6.1 | 08W | SH | 0 | 12652 | 0 | 12652 | 2.3962 | 0 | 2.3962 | 0 | 2022-05-02 08:00 | 2022-12-15 17:00 | OREGON TRAIL 110335002 | 49 | 35219287
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | 08W | SH | 22991 | 0 | 0 | 22991 | 4.3544 | 0 | 4.3544 | 0 | 2022-06-13 08:00 | 2022-09-30 17:00 | OREGON TRAIL 110335002 | 49 | 35219289
35233947 | CWSP - OREGON TRAIL 110335002 PH1.2 | 08W | SH | 0 | 9734 | 0 | 9734 | 1.8436 | 0 | 1.8436 | 0 | 2022-04-12 08:00 | 2022-10-31 17:00 | OREGON TRAIL 110335002 | 49 | 35219289
35233948 | CWSP - OREGON TRAIL 110335002 PH1.3 | 08W | SH | 13660 | 0 | 0 | 13660 | 2.5871 | 0 | 2.5871 | 0 | 2022-08-23 08:00 | 2023-01-13 17:00 | OREGON TRAIL 110335002 | 49 | 35219289
35233949 | CWSP - OREGON TRAIL 110335002 PH1.4 | 08W | SH | 0 | 10438 | 0 | 10438 | 1.9769 | 0 | 1.9769 | 0 | 2022-04-13 08:00 | 2022-10-17 17:00 | OREGON TRAIL 110335002 | 49 | 35219289
35233950 | CWSP - OREGON TRAIL 110335002 PH1.5 | 08W | SH | 15282 | 0 | 0 | 15282 | 2.8943 | 0 | 2.8943 | 0 | 2022-08-16 08:00 | 2023-01-02 17:00 | OREGON TRAIL 110335002 | 49 | 35219289
35233951 | CWSP - OREGON TRAIL 110335002 PH1.6 | 08W | SH | 0 | 8262 | 0 | 8262 | 1.5648 | 0 | 1.5648 | 0 | 2022-04-11 08:00 | 2022-09-08 17:00 | OREGON TRAIL 110335002 | 49 | 35219289
35233952 | CWSP - OREGON TRAIL 110335002 PH2.2 | 08W | SH | 0 | 11413 | 0 | 11413 | 2.1616 | 0 | 2.1616 | 0 | 2022-08-02 08:00 | 2022-11-03 17:00 | OREGON TRAIL 110335002 | 49 | 35225826
35233953 | CWSP - OREGON TRAIL 110335002 PH2.3 | 08W | SH | 4437 | 0 | 0 | 4437 | 0.84034 | 0 | 0.84034 | 0 | 2022-05-04 08:00 | 2022-07-13 17:00 | OREGON TRAIL 110335002 | 49 | 35225826
35233954 | CWSP - OREGON TRAIL 110335002 PH3.2 | 08W | SH | 0 | 1027 | 0 | 1027 | 0.19451 | 0 | 0.19451 | 0 | 2022-06-08 08:00 | 2022-12-19 17:00 | OREGON TRAIL 110335002 | 49 | 35225827
35233955 | CWSP - OREGON TRAIL 110335002 PH2.4 | 08W | SH | 2900 | 0 | 0 | 2900 | 0.54924 | 0 | 0.54924 | 0 | 2022-05-31 08:00 | 2022-08-03 17:00 | OREGON TRAIL 110335002 | 49 | 35225826
35233956 | CWSP - OREGON TRAIL 110335002 PH3.3 | 08W | SH | 0 | 1378 | 0 | 1378 | 0.26098 | 0 | 0.26098 | 0 | 2022-06-08 08:00 | 2022-12-19 17:00 | OREGON TRAIL 110335002 | 49 | 35225827
35233957 | CWSP - OREGON TRAIL 110335002 PH2.5 | 08W | SH | 539 | 0 | 0 | 539 | 0.10208 | 0 | 0.10208 | 0 | 2022-05-06 08:00 | 2022-07-06 17:00 | OREGON TRAIL 110335002 | 49 | 35225826
35233958 | CWSP - OREGON TRAIL 110335002 PH3.4 | 08W | SH | 0 | 995 | 0 | 995 | 0.18845 | 0 | 0.18845 | 0 | 2022-06-28 08:00 | 2023-01-09 17:00 | OREGON TRAIL 110335002 | 49 | 35225827
35233959 | CWSP - OREGON TRAIL 110335002 PH2.6 | 08W | SH | 0 | 1827 | 0 | 1827 | 0.34602 | 0 | 0.34602 | 0 | 2022-07-15 08:00 | 2022-11-16 17:00 | OREGON TRAIL 110335002 | 49 | 35225826
35234380 | CWSP - OREGON TRAIL 110335002 PH3.5 | 08W | SH | 0 | 11837 | 0 | 11837 | 2.2419 | 0 | 2.2419 | 0 | 2022-06-08 08:00 | 2022-12-19 17:00 | OREGON TRAIL 110335002 | 49 | 35225827
35234381 | CWSP - OREGON TRAIL 110335002 PH2.7 | 08W | SH | 0 | 8167 | 0 | 8167 | 1.5468 | 0 | 1.5468 | 0 | 2022-07-12 08:00 | 2022-09-28 17:00 | OREGON TRAIL 110335002 | 49 | 35225826
35234382 | CWSP - OREGON TRAIL 110335002 PH2.8 | 08W | SH | 0 | 8382 | 0 | 8382 | 1.5875 | 0 | 1.5875 | 0 | 2022-05-05 08:00 | 2022-08-25 17:00 | OREGON TRAIL 110335002 | 49 | 35225826
35234383 | CWSP - OREGON TRAIL 110335002 PH3.6 | 08W | SH | 6328 | 0 | 0 | 6328 | 1.1985 | 0 | 1.1985 | 0 | 2022-06-07 08:00 | 2022-12-08 17:00 | OREGON TRAIL 110335002 | 49 | 35225827
35234384 | CWSP - OREGON TRAIL 110335002 PH3.7 | 08W | SH | 0 | 267 | 0 | 267 | 0.050568 | 0 | 0.050568 | 0 | 2022-06-08 08:00 | 2022-12-19 17:00 | OREGON TRAIL 110335002 | 49 | 35225827
35234385 | CWSP - OREGON TRAIL 110335002 PH3.8 | 08W | SH | 0 | 3561 | 0 | 3561 | 0.67443 | 0 | 0.67443 | 0 | 2022-06-08 08:00 | 2022-12-19 17:00 | OREGON TRAIL 110335002 | 49 | 35225827
35234386 | CWSP - OREGON TRAIL 110335002 PH3.9 | 08W | SH | 0 | 4529 | 0 | 4529 | 0.85777 | 0 | 0.85777 | 0 | 2022-06-08 08:00 | 2022-12-19 17:00 | OREGON TRAIL 110335002 | 49 | 35225827
35234387 | CWSP - OREGON TRAIL 110335002 PH4.2 | 08W | SH | 0 | 4963 | 0 | 4963 | 0.93996 | 0 | 0.93996 | 0 | 2022-05-31 08:00 | 2022-12-30 17:00 | OREGON TRAIL 110335002 | 49 | 35225828
35234388 | CWSP - OREGON TRAIL 110335002 PH4.3 | 08W | SH | 0 | 10772 | 0 | 10772 | 2.0402 | 0 | 2.0402 | 0 | 2022-05-31 08:00 | 2022-12-29 17:00 | OREGON TRAIL 110335002 | 49 | 35225828
35234389 | CWSP - OREGON TRAIL 110335002 PH4.4 | 08W | SH | 0 | 4752 | 0 | 4752 | 0.9 | 0 | 0.9 | 0 | 2022-04-27 08:00 | 2022-12-30 17:00 | OREGON TRAIL 110335002 | 49 | 35225828
35234390 | CWSP - OREGON TRAIL 110335002 PH4.5 | 08W | SH | 0 | 2746 | 0 | 2746 | 0.52008 | 0 | 0.52008 | 0 | 2022-05-25 08:00 | 2022-10-21 17:00 | OREGON TRAIL 110335002 | 49 | 35225828
35234391 | CWSP - OREGON TRAIL 110335002 PH4.6 | 08W | SH | 0 | 6653 | 0 | 6653 | 1.26 | 0 | 1.26 | 0 | 2022-05-02 08:00 | 2022-08-30 17:00 | OREGON TRAIL 110335002 | 49 | 35225828
35234392 | CWSP - OREGON TRAIL 110335002 PH4.7 | 08W | SH | 0 | 8765 | 0 | 8765 | 1.66 | 0 | 1.66 | 0 | 2022-05-11 08:00 | 2022-10-10 17:00 | OREGON TRAIL 110335002 | 49 | 35225828
35234393 | CWSP - OREGON TRAIL 110335002 PH5.2 | 08W | SH | 0 | 12778 | 0 | 12778 | 2.4201 | 0 | 2.4201 | 0 | 2022-08-19 08:00 | 2023-01-05 17:00 | OREGON TRAIL 110335002 | 49 | 35225829
35234394 | CWSP - OREGON TRAIL 110335002 PH5.3 | 08W | SH | 0 | 9451 | 0 | 9451 | 1.79 | 0 | 1.79 | 0 | 2022-11-24 08:00 | 2023-03-30 17:00 | OREGON TRAIL 110335002 | 49 | 35225829
35234395 | CWSP - OREGON TRAIL 110335002 PH5.4 | 08W | SH | 0 | 14309 | 0 | 14309 | 2.71 | 0 | 2.71 | 0 | 2022-11-23 08:00 | 2023-03-09 17:00 | OREGON TRAIL 110335002 | 49 | 35225829
35234396 | CWSP - OREGON TRAIL 110335002 PH5.5 | 08W | SH | 0 | 8923 | 0 | 8923 | 1.69 | 0 | 1.69 | 0 | 2022-12-20 08:00 | 2023-04-11 17:00 | OREGON TRAIL 110335002 | 49 | 35225829
35234397 | CWSP - OREGON TRAIL 110335002 PH5.6 | 08W | SH | 0 | 3802 | 0 | 3802 | 0.72008 | 0 | 0.72008 | 0 | 2022-12-23 08:00 | 2023-04-03 17:00 | OREGON TRAIL 110335002 | 49 | 35225829
35234398 | CWSP - OREGON TRAIL 110335002 PHASE 6.2 | 08W | SH | 0 | 15061 | 0 | 15061 | 2.8525 | 0 | 2.8525 | 0 | 2022-05-05 08:00 | 2022-12-30 17:00 | OREGON TRAIL 110335002 | 49 | 35219287
35234399 | CWSP - OREGON TRAIL 110335002 PHASE 6.3 | 08W | SH | 2535 | 0 | 0 | 2535 | 0.48011 | 0 | 0.48011 | 0 | 2022-06-08 08:00 | 2022-10-07 17:00 | OREGON TRAIL 110335002 | 49 | 35219287
35234400 | CWSP - OREGON TRAIL 110335002 PHASE 6.4 | 08W | SH | 0 | 7339 | 0 | 7339 | 1.39 | 0 | 1.39 | 0 | 2022-05-16 08:00 | 2022-10-21 17:00 | OREGON TRAIL 110335002 | 49 | 35219287
35234401 | CWSP - OREGON TRAIL 110335002 PHASE 6.5 | 08W | SH | 0 | 9768 | 0 | 9768 | 1.85 | 0 | 1.85 | 0 | 2022-06-01 08:00 | 2022-11-08 17:00 | OREGON TRAIL 110335002 | 49 | 35219287
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | 08W | SH | 0 | 13424 | 0 | 13424 | 2.5424 | 0 | 2.5424 | 0 | 2022-04-13 08:00 | 2022-10-06 17:00 | OREGON TRAIL 110335002 | 49 | 35225826
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | 08W | SH | 4465 | 0 | 0 | 4465 | 0.84564 | 0 | 0.84564 | 0 | 2022-06-29 08:00 | 2023-02-27 17:00 | OREGON TRAIL 110335002 | 49 | 35225827
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | 08W | SH | 13366 | 0 | 0 | 13366 | 2.5314 | 0 | 2.5314 | 0 | 2022-06-20 08:00 | 2022-12-27 17:00 | OREGON TRAIL 110335002 | 49 | 35225828
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | 08W | SH | 0 | 11563 | 0 | 11563 | 2.19 | 0 | 2.19 | 0 | 2022-06-16 08:00 | 2022-08-25 17:00 | OREGON TRAIL 110335002 | 49 | 35225829
35262343 | STS-POLE_IDLE_REMV-1N/O 22055 TIFFANY LN | 2AF | Idle Facilities | 0 | 0 | 280 | 280 | 0.05303 | 0 | 0.05303 | 0 |  |  | OREGON TRAIL 110335002 | 49
35262344 | DR-STS-POLE_IDLE_REMV-1E/O21623SEVENLAKE | 2AF | Idle Facilities | 0 | 0 | 262 | 262 | 0.049621 | 0 | 0.049621 | 0 |  |  | OREGON TRAIL 110335002 | 49
35211263 | H TAG REMV IDLE SEC/ANCH 11951 BEST LN | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | OREGON TRAIL 110335002 | 49
35243440 | PSPS-OREGON TRAIL 1103 CB & 35002-PH7 | 08W | SH | 2270 | 0 | 0 | 2270 | 0.42992 | 0 | 0.42992 | 0 | 2022-08-04 08:00 | 2022-12-30 17:00 | OREGON TRAIL 1103CB | 290
35204806 | DR~STS-TRAN_IDLE_REMV-1P N/O 10133 FRAZ | 2AF | Idle Facilities | 0 | 0 | 234 | 234 | 0.044318 | 0 | 0.044318 | 0 |  |  | OREGON TRAIL 1104CB | 255
35225318 | +STS-COND_IDLE_REMV-CAT CANYON RD | 2AF | Idle Facilities | 0 | 0 | 500 | 500 | 0.094697 | 0 | 0.094697 | 0 |  |  | PALMER 1101M84 | 256
35204902 | FT~STS-COND_IDLE_REMV-4506 PANORAMA PNT | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | PANORAMA 1101CB | 1038
35279630 | CWSP - PASO ROBLES 1103 LR59763 PH1.2 | 08W | SH | 0 | 8923 | 0 | 8923 | 1.69 | 0 | 1.69 | 0 | 2022-06-21 08:00 | 2023-01-02 17:00 | PASO ROBLES 110359763 | 615 | 35254251
35254251 | CWSP - PASO ROBLES 1103 LR 59763 PH 1.1 | 08W | SH | 0 | 5966.4 | 0 | 5966.4 | 1.13 | 0 | 1.13 | 0 | 2022-06-01 08:00 | 2022-12-13 17:00 | PASO ROBLES 110359763 | 615 | 35254251
35254252 | CWSP - PASO ROBLES 1103 LR N52 | 08W | SH | 0 | 13147 | 343 | 13490 | 2.5549 | 0 | 2.5549 | 0 |  |  | PASO ROBLES 1103N52 | 291 | 35254252
35278882 | CWSP - PASO ROBLES 1103 LRN54 PH1.4 | 08W | SH | 0 | 10612.8 | 0 | 10612.8 | 2.01 | 0 | 2.01 | 0 | 2022-07-05 08:00 | 2022-11-25 17:00 | PASO ROBLES 1103N54 | 69 | 35254249
35278883 | CWSP - PASO ROBLES 1103 LRN54 PH2.2 | 08W | SH | 0 | 9556.8 | 0 | 9556.8 | 1.81 | 0 | 1.81 | 0 | 2022-08-02 | 2023-02-13 | PASO ROBLES 1103N54 | 69 | 35254250
35278884 | CWSP - PASO ROBLES 1103 LRN54 PH2.3 | 08W | SH | 0 | 14625.6 | 0 | 14625.6 | 2.77 | 0 | 2.77 | 0 | 2022-07-05 08:00 | 2023-01-23 | PASO ROBLES 1103N54 | 69 | 35254250
35254249 | CWSP - PASO ROBLES 1103 LR N54 PH1.1 | 08W | SH | 0 | 14256 | 0 | 14256 | 2.7 | 0 | 2.7 | 0 | 2022-07-05 08:00 | 2022-12-02 17:00 | PASO ROBLES 1103N54 | 69 | 35254249
35254248 | CWSP - PASO ROBLES 1103 LR N58 | 08W | SH | 0 | 7550.4 | 0 | 7550.4 | 1.43 | 0 | 1.43 | 0 | 2022-06-07 08:00 | 2022-12-19 17:00 | PASO ROBLES 1103N58 | 257 | 35254248
35279631 | CWSP PASO ROBLES 1103 LRN58 PH1.2 | 08W | SH | 0 | 16209.6 | 0 | 16209.6 | 3.07 | 0 | 3.07 | 0 | 2022-06-20 08:00 | 2022-12-30 17:00 | PASO ROBLES 1103N58 | 257 | 35254248
35208010 | COND_IDLE_REMV-405 DUTCH RAVINE RD | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | PENRYN 11051342 | 1016
35225011 | STS-COND_IDLE_REMV - AT 1580 PRESTON ST | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 | 2022-01-11 | 2022-01-11 | PERRY 1101V74 | 2433
35159821 | STS-COND_IDLE_REMV-1140 TOMALES RD | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  | 2022-02-28 | PETALUMA C 1108632 | 888
35223225 | FT~STS-COND_IDLE_REMV-W/S TOMALES RD 1/P | 2AF | Idle Facilities | 0 | 0 | 595 | 595 | 0.11269 | 0 | 0.11269 | 0 | 2021-04-08 | 2022-02-28 | PETALUMA C 1108632 | 888
35221246 | DR~T2 REMV IDLE POLE 6 N/O #1 E/0 ENT | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | PHILO 11013700 | 417
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | 08W | SH | 494 | 7193 | 0 | 7687 | 1.4559 | 0 | 1.4559 | 0 |  | 2022-06-24 17:00 | PINE GROVE 11021222 | 2271
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | 08W | SH | 878 | 0 | 255 | 1133 | 0.21458 | 0 | 0.21458 | 0 | 2022-03-14 08:00 | 2022-08-02 17:00 | PLACERVILLE 1112CB | 2123
35176816 | STS_COND_IDLE_REMV-R/O 9650 HWY 193 | 2AF | Idle Facilities | 0 | 0 | 755 | 755 | 0.14299 | 0 | 0.14299 | 0 |  | 2022-02-05 | PLACERVILLE 210611132 | 1666
35208054 | STS-COND_IDLE_REMV-BAYNE RD | 2AF | Idle Facilities | 0 | 0 | 785 | 785 | 0.14867 | 0 | 0.14867 | 0 |  |  | PLACERVILLE 210611132 | 1666
35148124 | FT_STS-COND_IDLE_REMV-5PN.2788 STONECRES | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 | 2021-03-29 | 2022-03-03 | PLACERVILLE 210623190 | 2430
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | 08W | SH | 1471 | 0 | 0 | 1471 | 0.2786 | 0 | 0.2786 | 0 | 2022-07-26 08:00 | 2023-01-09 17:00 | PLACERVILLE 21067522 | 1363 | 35224377
35233995 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.2 | 08W | SH | 3690 | 0 | 0 | 3690 | 0.69886 | 0 | 0.69886 | 0 | 2022-08-18 08:00 | 2022-12-19 08:00 | PLACERVILLE 21067522 | 1363 | 35224377
35233996 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.3 | 08W | SH | 4486 | 0 | 2752 | 7238 | 1.3708 | 0 | 1.3708 | 0 | 2022-08-04 08:00 | 2022-12-30 17:00 | PLACERVILLE 21067522 | 1363 | 35224377
35264102 | DRSTS-POLE_IDLE_REMV-1SO 6410 JOHNSTOWN | 2AF | Idle Facilities | 0 | 0 | 572 | 572 | 0.10833 | 0 | 0.10833 | 0 | 2022-04-29 | 2022-04-29 | PLACERVILLE 21067522 | 1363
35244112 | FT--COND_IDLE_REMV-G/P 4444 COOK RANCH R | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | PLACERVILLE 21069712 | 1646
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | 08W | SH | 0 | 8976 | 0 | 8976 | 1.7 | 0 | 1.7 | 0 | 2022-04-04 | 2022-06-29 17:00 | POTTER VALLEY P H 110564118 | 43 | 35219280
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | 08W | SH | 560 | 0 | 0 | 560 | 0.10606 | 0 | 0.10606 | 0 | 2022-03-29 08:00 | 2022-10-10 17:00 | POTTER VALLEY P H 110564118 | 43 | 35219280
35244086 | STS-COND_IDLE_REMV - 308 WALL RDNAPA | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | PUEBLO 2102792 | 951
35219275 | CWSP - PUTAH CREEK 110246012 | 08W | SH | 0 | 5402 | 0 | 5402 | 1.0231 | 0 | 1.0231 | 0 |  |  | PUTAH CREEK 110246012 | 41
35240176 | CWSP - PUTAH CREEK 110264044 PH 1.1 | 08W | SH | 0 | 12672 | 0 | 12672 | 2.4 | 0 | 2.4 | 0 | 2022-05-12 08:00 | 2022-10-05 17:00 | PUTAH CREEK 110264044 | 529 | 35240176
35240177 | CWSP - PUTAH CREEK 110264044 PH 2 | 08W | SH | 0 | 17424 | 0 | 17424 | 3.3 | 0 | 3.3 | 0 | 2022-06-02 08:00 | 2022-11-08 17:00 | PUTAH CREEK 110264044 | 529 | 35240177
35254177 | CWSP - PUTAH CREEK 110264044 PH 2.2 | 08W | SH | 0 | 1636.8 | 0 | 1636.8 | 0.31 | 0 | 0.31 | 0 | 2022-05-17 08:00 | 2022-08-16 17:00 | PUTAH CREEK 110264044 | 529 | 35240177
35254178 | CWSP - PUTAH CREEK 110267858 PH 1.3 | 08W | SH | 0 | 6615.84 | 0 | 6615.84 | 1.253 | 0 | 1.253 | 0 | 2022-04-26 08:00 | 2022-09-26 17:00 | PUTAH CREEK 110267858 | 92 | 35240175
35254260 | CWSP - PUTAH CREEK 110267858 PH 1.6 | 08W | SH | 2112 | 0 | 0 | 2112 | 0.4 | 0 | 0.4 | 0 |  |  | PUTAH CREEK 110267858 | 92 | 35240175
35254261 | CWSP - PUTAH CREEK 110267858 PH 1.5 | 08W | SH | 0 | 14794.56 | 0 | 14794.56 | 2.802 | 0 | 2.802 | 0 | 2022-04-05 08:00 | 2022-09-12 17:00 | PUTAH CREEK 110267858 | 92 | 35240175
35254262 | CWSP - PUTAH CREEK 110267858 PH 1.4 | 08W | SH | 0 | 11109 | 0 | 11109 | 2.104 | 0 | 2.104 | 0 | 2022-05-03 08:00 | 2022-10-03 17:00 | PUTAH CREEK 110267858 | 92 | 35240175
35254560 | CWSP - PUTAH CREEK 110267858 PH 1.2 | 08W | SH | 0 | 6394.08 | 0 | 6394.08 | 1.211 | 0 | 1.211 | 0 | 2022-04-06 08:00 | 2022-09-06 17:00 | PUTAH CREEK 110267858 | 92 | 35240175
35240175 | CWSP - PUTAH CREEK 110267858 PH 1 | 08W | SH | 0 | 18195 | 0 | 18195 | 3.446 | 0 | 3.446 | 0 | 2022-06-01 08:00 | 2022-12-13 17:00 | PUTAH CREEK 110267858 | 92 | 35240175
35254263 | CWSP - PUTAH CREEK 1102710384 PH 1.2 | 08W | SH | 0 | 6468 | 0 | 6468 | 1.225 | 0 | 1.225 | 0 | 2022-06-21 08:00 | 2022-09-23 17:00 | PUTAH CREEK 1102710384 | 418 | 35240178
35240178 | CWSP - PUTAH CREEK 1102710384 PH 1.1 | 08W | SH | 0 | 18073 | 0 | 18073 | 3.4229 | 0 | 3.4229 | 0 | 2022-06-07 08:00 | 2022-11-25 17:00 | PUTAH CREEK 1102710384 | 418 | 35240178
35254264 | CWSP - PUTAH CREEK 11028352 PH 1.2 | 08W | SH | 0 | 7022.4 | 0 | 7022.4 | 1.33 | 0 | 1.33 | 0 | 2022-04-19 08:00 | 2022-10-10 17:00 | PUTAH CREEK 11028352 | 171 | 35240173
35254265 | CWSP - PUTAH CREEK 11028352 PH 2.2 | 08W | SH | 0 | 14572.8 | 0 | 14572.8 | 2.76 | 0 | 2.76 | 0 | 2022-05-02 08:00 | 2022-10-07 17:00 | PUTAH CREEK 11028352 | 171 | 35240174
35254266 | CWSP - PUTAH CREEK 11028352 PH 2.3 | 08W | SH | 0 | 686.4 | 0 | 686.4 | 0.13 | 0 | 0.13 | 0 | 2022-08-18 08:00 | 2022-12-27 17:00 | PUTAH CREEK 11028352 | 171 | 35240174
35240173 | CWSP - PUTAH CREEK 11028352 PH 1.1 | 08W | SH | 0 | 6442 | 0 | 6442 | 1.2201 | 0 | 1.2201 | 0 | 2022-06-14 08:00 | 2022-09-30 17:00 | PUTAH CREEK 11028352 | 171 | 35240173
35240174 | CWSP - PUTAH CREEK 1102 8352 PH 2.1 | 08W | SH | 0 | 5649.6 | 0 | 5649.6 | 1.07 | 0 | 1.07 | 0 | 2022-03-08 08:00 | 2022-08-05 17:00 | PUTAH CREEK 11028352 | 171 | 35240174
35253133 | DR STS-POLE_IDLE_REMV-3701 SPRING VALLEY | 2AF | Idle Facilities | 0 | 0 | 225 | 225 | 0.042614 | 0 | 0.042614 | 0 |  |  | REDBUD 1101323962 | 423
35244102 | STS-COND_IDLE_REMV-12366 LAKEVIEW DR | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | REDBUD 1101708166 | 345
35208096 | 8/31-HOLD REMV IDLE FAC -LONGVALLEY *KS | 2AF | Idle Facilities | 0 | 0 | 1091 | 1091 | 0.20663 | 0 | 0.20663 | 0 |  |  | REDBUD 1101708166 | 345
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | 08W | SH | 6774 | 1056 | 0 | 7830 | 1.483 | 1.1737 | 0.30928 | 0 | 2021-04-19 | 2022-05-19 17:00 | RINCON 1104CB | 3302
35225467 | STS-COND_IDLE_REMV - 1/P/S/O/587 AVOCADO | 2AF | Idle Facilities | 0 | 0 | 125 | 125 | 0.023674 | 0 | 0.023674 | 0 |  |  | ROB ROY 210410298 | 2387
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | 08W | SH | 2985 | 0 | 0 | 2985 | 0.56534 | 0 | 0.56534 | 0 | 2021-09-28 | 2022-03-31 | ROSSMOOR 1106CB | 3259
35224942 | STS-COND_IDLE_REMV-3\P\S\O 2500 LOOMIS S | 2AF | Idle Facilities | 0 | 0 | 55 | 55 | 0.010417 | 0 | 0.010417 | 0 |  |  | SAN LUIS OBISPO 1101483444 | 2146
35225004 | +STS-POLE_IDLE_REMV -6996 MONTE DR-2/P/W | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | SAN LUIS OBISPO 1107V02 | 1317
35225423 | STS-TRAN_IDLE_REMV - AT 63122 INDIAN VAL | 2AF | Idle Facilities | 0 | 0 | 31 | 31 | 0.0058712 | 0 | 0.0058712 | 0 | 2021-02-22 | 2022-01-14 | SAN MIGUEL 1106605393 | 469
35120413 | DR-STS-COND_IDLE_REMV78TOYONDRIVE | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | SAN RAFAEL 1108516 | 1837
35083913 | STS-COND_IDLE_REMV-8236 CROW CANYON RD | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | SAN RAMON 2108CB | 1092
35215883 | STS-TRAN_CORR_REPL - 45886 CHUCKWAGON RD | 2AA | Idle Facilities | 0 | 0 | 544 | 544 | 0.10303 | 0 | 0.10303 | 0 |  |  | SAND CREEK 110345190 | 195
35262347 | STS-POLE_IDLE_REMV - A/F 45771 BUTTERNUT | 2AF | Idle Facilities | 0 | 0 | 366 | 366 | 0.069318 | 0 | 0.069318 | 0 |  |  | SAND CREEK 110345190 | 195
35221646 | STS-COND_IDLE_REMV - 57902 HARTLAND CHRI | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 | 2021-11-09 | 2022-02-04 | SAND CREEK 11037110 | 636
35083879 | STS-POLE_IDLE_REMV - NEGRO CK RD/RD 152 | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | SAND CREEK 1103CB | 337
35271002 | CWSP - SANTA YNEZ 110477098 PH 1.6 | 08W | SH | 0 | 6441.6 | 0 | 6441.6 | 1.22 | 0 | 1.22 | 0 | 2022-09-01 08:00 | 2022-12-09 17:00 | SANTA YNEZ 110477098 | 308 | 35240224
35264191 | CWSP - SANTA YNEZ 110477098 PH 1.2 | 08W | SH | 0 | 12408 | 0 | 12408 | 2.35 | 0 | 2.35 | 0 | 2022-04-12 08:00 | 2022-09-13 17:00 | SANTA YNEZ 110477098 | 308 | 35240224
35264192 | CWSP - SANTA YNEZ 110477098 PH 1.3 | 08W | SH | 0 | 12672 | 0 | 12672 | 2.4 | 0 | 2.4 | 0 | 2022-05-20 08:00 | 2022-07-27 17:00 | SANTA YNEZ 110477098 | 308 | 35240224
35264193 | CWSP - SANTA YNEZ 110477098 PH 1.4 | 08W | SH | 0 | 10982.4 | 0 | 10982.4 | 2.08 | 0 | 2.08 | 0 | 2022-07-12 08:00 | 2022-11-21 17:00 | SANTA YNEZ 110477098 | 308 | 35240224
35264194 | CWSP - SANTA YNEZ 110477098 PH 1.5 | 08W | SH | 0 | 10560 | 0 | 10560 | 2 | 0 | 2 | 0 | 2022-07-12 08:00 | 2022-11-15 17:00 | SANTA YNEZ 110477098 | 308 | 35240224
35240224 | CWSP - SANTA YNEZ 110477098 PH 1.1 | 08W | SH | 0 | 9874 | 0 | 9874 | 1.8701 | 0 | 1.8701 | 0 | 2022-03-10 08:00 | 2022-08-09 17:00 | SANTA YNEZ 110477098 | 308 | 35240224
35240179 | CWSP - SANTA YNEZ 1104CB | 08W | SH | 0 | 1320 | 0 | 1320 | 0.25 | 0 | 0.25 | 0 | 2022-03-30 08:00 | 2022-07-26 17:00 | SANTA YNEZ 1104CB | 137 | 35240179
35240220 | CWSP - SANTA YNEZ 1104Y04 PH 1.1 | 08W | SH | 0 | 14710 | 0 | 14710 | 2.786 | 0 | 2.786 | 0 | 2022-03-16 08:00 | 2022-08-03 17:00 | SANTA YNEZ 1104Y04 | 108 | 35240220
35240221 | CWSP - SANTA YNEZ 1104Y04 PH 2.1 | 08W | SH | 0 | 15470.4 | 0 | 15470.4 | 2.93 | 0 | 2.93 | 0 | 2022-04-06 08:00 | 2022-08-17 17:00 | SANTA YNEZ 1104Y04 | 108 | 35240221
35264181 | CWSP - SANTA YNEZ 1104Y04 PH 1.2 | 08W | SH | 0 | 13500 | 0 | 13500 | 2.5568 | 0 | 2.5568 | 0 | 2022-05-03 08:00 | 2022-09-16 17:00 | SANTA YNEZ 1104Y04 | 108 | 35240220
35264182 | CWSP - SANTA YNEZ 1104Y04 PH 1.3 | 08W | SH | 0 | 12232 | 0 | 12232 | 2.3167 | 0 | 2.3167 | 0 | 2022-06-07 08:00 | 2022-10-21 17:00 | SANTA YNEZ 1104Y04 | 108 | 35240220
35264183 | CWSP - SANTA YNEZ 1104Y04 PH 2.2 | 08W | SH | 0 | 12883 | 0 | 12883 | 2.44 | 0 | 2.44 | 0 | 2022-05-03 08:00 | 2022-09-16 17:00 | SANTA YNEZ 1104Y04 | 108 | 35240221
35264184 | CWSP - SANTA YNEZ 1104Y04 PH 2.3 | 08W | SH | 0 | 11088 | 0 | 11088 | 2.1 | 0 | 2.1 | 0 | 2022-05-11 08:00 | 2022-09-19 17:00 | SANTA YNEZ 1104Y04 | 108 | 35240221
35275478 | STS-POLE_IDLE_REMV-23600 STATE HWY 9 | 2AF | Idle Facilities | 0 | 0 | 837 | 837 | 0.15852 | 0 | 0.15852 | 0 |  |  | SARATOGA 1107167792 | 2354
35221770 | STS-COND_IDLE_REMV-15878-15998 WILDCAT R | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | SARATOGA 1107LC12 | 2627
35295009 | FRRB - SG 1101 TL UG 06 | 08W | Fire Rebuild | 5647 | 0 | 0 | 5647 | 1.0695 | 0 | 1.0695 | 0 | 2021-12-28 | 2022-02-21 | SHADY GLEN 11012768 | 1885
35284567 | FRRB - SG 1101 TL UG 08 09 | 08W | Fire Rebuild | 3205 | 0 | 0 | 3205 | 0.60701 | 0 | 0.60701 | 0 |  |  | SHADY GLEN 11012768 | 1885
35207979 | STS-COND_IDLE_REMV - 1N/O 1244 CROW HAVE | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 | 2021-11-01 | 2022-03-17 | SHADY GLEN 110132726 | 2201
35284568 | FRRB - SG 1101 TL UG 10 | 08W | Fire Rebuild | 3132 | 0 | 0 | 3132 | 0.59318 | 0 | 0.59318 | 0 |  |  | SHADY GLEN 110132726 | 2201
35273069 | DR-STS-IDLE_REMV - 13N/O 10E/O R/O 175 | 2AF | Idle Facilities | 0 | 0 | 1076 | 1076 | 0.20379 | 0 | 0.20379 | 0 | 2021-11-30 | 2022-01-21 | SHADY GLEN 11022232 | 2022
35284569 | FRRB - SG 1102 TL UG 03 | 08W | Fire Rebuild | 3290 | 0 | 0 | 3290 | 0.62311 | 0 | 0.62311 | 0 |  |  | SHADY GLEN 110248894 | 1378
35205038 | DR-OFAC_IDLE_REMV-745 HWY 174 | 2AF | Idle Facilities | 0 | 0 | 540 | 540 | 0.10227 | 0 | 0.10227 | 0 |  |  | SHADY GLEN 1102CB | 1829
35250938 | STS-POLE_IDLE_REMV-4/S/O 1/N/O 4511 BROO | 2AF | Idle Facilities | 0 | 0 | 1191 | 1191 | 0.22557 | 0 | 0.22557 | 0 |  |  | SHINGLE SPRINGS 210851476 | 424
35208079 | FT~STS-COND_IDLE_REMV-5670 BASSI RD | 2AF | Idle Facilities | 0 | 0 | 795 | 795 | 0.15057 | 0 | 0.15057 | 0 |  |  | SHINGLE SPRINGS 210911092 | 2116
35244173 | FT-COND_IDLE_REMV-5260 GRANITE CREEK RD | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | SHINGLE SPRINGS 210911092 | 2116
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | 08W | SH | 17353 | 0 | 0 | 17353 | 3.2866 | 0 | 3.2866 | 0 | 2022-07-26 08:00 | 2022-12-23 17:00 | SHINGLE SPRINGS 210935598 | 159 | 35062376
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | 08W | SH | 0 | 10124 | 0 | 10124 | 1.9174 | 0 | 1.9174 | 0 | 2022-01-19 08:00 | 2022-04-01 | SHINGLE SPRINGS 210935598 | 159 | 35062376
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | 08W | SH | 0 | 10600 | 1920 | 12520 | 2.3712 | 0 | 2.3712 | 0 | 2021-07-01 08:00 | 2022-04-22 | SHINGLE SPRINGS 210935598 | 159 | 35062376
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | 08W | SH | 0 | 5771 | 0 | 5771 | 1.093 | 0 | 1.093 | 0 | 2021-09-30 08:00 | 2022-04-01 | SHINGLE SPRINGS 210935598 | 159 | 35062376
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | 08W | SH | 0 | 7812 | 0 | 7812 | 1.4795 | 0 | 1.4795 | 0 | 2021-06-15 | 2022-03-25 | SHINGLE SPRINGS 21099372 | 227 | 35062374
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | 08W | SH | 0 | 6832 | 1186 | 8018 | 1.5186 | 0 | 1.5186 | 0 | 2022-02-18 | 2022-04-20 17:00 | SHINGLE SPRINGS 21099372 | 227 | 35062374
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | 08W | SH | 0 | 14964 | 0 | 14964 | 2.8341 | 0 | 2.8341 | 0 | 2022-08-01 | 2022-11-01 | SHINGLE SPRINGS 21099372 | 227 | 35062375
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | 08W | SH | 9398 | 0 | 0 | 9398 | 1.7799 | 0 | 1.7799 | 0 | 2022-07-26 08:00 | 2023-03-28 17:00 | SHINGLE SPRINGS 21099372 | 227 | 35062375
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | 08W | SH | 0 | 7748 | 0 | 7748 | 1.4674 | 0.18542 | 1.282 | 0 | 2022-02-01 | 2022-02-25 | SHINGLE SPRINGS 21099372 | 227 | 35062375
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | 08W | SH | 0 | 10883 | 0 | 10883 | 2.0612 | 0 | 2.0612 | 0 | 2022-01-03 | 2022-06-07 17:00 | SHINGLE SPRINGS 21099372 | 227 | 35062375
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | 08W | SH | 0 | 7441 | 0 | 7441 | 1.4093 | 0 | 1.4093 | 0 | 2021-06-22 08:00 | 2022-03-18 | SHINGLE SPRINGS 21099372 | 227 | 35062374
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | 08W | SH | 0 | 9228 | 832 | 10060 | 1.9053 | 0 | 1.9053 | 0 | 2021-06-21 | 2022-03-04 17:00 | SHINGLE SPRINGS 21099372 | 227 | 35062374
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | 08W | SH | 10831 | 0 | 0 | 10831 | 2.0513 | 0 | 2.0513 | 0 | 2022-03-22 08:00 | 2022-09-13 17:00 | SHINGLE SPRINGS 21099372 | 227 | 35062374
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | 08W | SH | 8261 | 0 | 0 | 8261 | 1.5646 | 0 | 1.5646 | 0 | 2022-05-17 08:00 | 2022-11-10 17:00 | SHINGLE SPRINGS 21099372 | 227 | 35062375
35207972 | H TAGPOLE_IDLE_REMV - 4646 LOTUS RD 3PLE | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 | 2022-02-28 | 2022-02-28 | SHINGLE SPRINGS 21099372 | 227
35211743 | FT~STS-COND_IDLE_REMV-1S/O 1W/O 3881 WEL | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | SHINGLE SPRINGS 2109CB | 1240
35211237 | COND_IDLE_REMV-2607 CHILES POPE VALL | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | SILVERADO 210234959 | 579
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | 08W | SH | 0 | 11791 | 0 | 11791 | 2.2331 | 0 | 2.2331 | 0 | 2021-11-10 | 2022-02-12 | SILVERADO 210258626 | 663
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | 08W | SH | 10930 | 0 | 0 | 10930 | 2.0701 | 0 | 2.0701 | 0 | 2022-03-11 08:00 | 2022-08-10 17:00 | SILVERADO 2104726 | 279 | 35192284
35223024 | ECOP - SILVERADO 2104 - H05 - LR726 PH 2 | 08W | SH | 11827 | 0 | 0 | 11827 | 2.24 | 0 | 2.24 | 0 | 2022-05-10 08:00 | 2022-10-20 17:00 | SILVERADO 2104726 | 279 | 35192284
35223026 | ECOP - SILVERADO 2104 - H05 - LR726 PH 3 | 08W | SH | 9504 | 0 | 0 | 9504 | 1.8 | 0 | 1.8 | 0 | 2022-08-10 08:00 | 2022-12-22 17:00 | SILVERADO 2104726 | 279 | 35192284
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | 08W | SH | 0 | 9281 | 0 | 9281 | 1.7578 | 0.35909 | 1.3987 | 0 | 2022-01-10 08:00 | 2022-03-25 17:00 | SILVERADO 2104726 | 279 | 35192284
35223207 | DR~STS-COND_IDLE_REMV - N/E/C OF SNEATH | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | SNEATH LANE 1106CB | 2588
35144944 | PSPS - SNEATH LANE 1107 - LR 48338 | 08W | SH | 1348 | 0 | 0 | 1348 | 0.2553 | 0 | 0.2553 | 0 | 2022-03-23 08:00 | 2022-06-30 17:00 | SNEATH LANE 110748338 | 3550
35223204 | FT~T2-COND_IDLE_REMV - 3883 LOVALL VALL | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | SONOMA 1105229588 | 720
35281759 | FRRB - SPANISH CREEK (REMOVAL) | 08W | Fire Rebuild | 0 | 0 | 10000 | 10000 | 1.8939 | 0 | 1.8939 | 0 |  |  | SPANISH CREEK 4401CB | 1322
35282166 | FRRB - SPANISH CREEK UG ML PH1.1 | 08W | Fire Rebuild | 13676 | 0 | 5000 | 18676 | 3.5371 | 0 | 3.5371 | 0 | 2022-02-25 08:00 | 2022-06-29 17:00 | SPANISH CREEK 4401CB | 1322
35290517 | FRRB - SPANISH CREEK UG TL PH1.2 | 08W | Fire Rebuild | 4593 | 0 | 5000 | 9593 | 1.8169 | 0 | 1.8169 | 0 | 2022-02-25 08:00 | 2022-06-29 17:00 | SPANISH CREEK 4401CB | 1322
35277146 | STS-COND_IDLE_REMV-29040 SNOWHITE RD | 2AF | Idle Facilities | 0 | 0 | 718 | 718 | 0.13598 | 0 | 0.13598 | 0 |  |  | SPRING GAP 17029690 | 2788
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | 08W | SH | 172 | 9383 | 0 | 9555 | 1.8097 | 0 | 1.8097 | 0 | 2022-03-08 08:00 | 2022-07-29 | STANISLAUS 17021804 | 2712
35221765 | STS-COND_IDLE_REMV - 1504 PINE DR ARNOLD | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | STANISLAUS 170237278 | 2810
35275962 | STS-COND_IDLE_REMV-1W/O 14508 WONDERLAND | 2BF | Idle Facilities | 0 | 0 | 30 | 30 | 0.0056818 | 0 | 0.0056818 | 0 |  |  | STILLWATER 11011320 | 1828
35291986 | FRRB - STILLWATER 1101_OH_FH_TPL_6 | 08W | Fire Rebuild | 0 | 9622 | 0 | 9622 | 1.8223 | 1.6958 | 0.12652 | 0 |  |  | STILLWATER 110148950 | 851
35297984 | FRRB - STILLWATER 1101_UG_FH_TPL_7 | 08W | Fire Rebuild | 5914 | 0 | 0 | 5914 | 1.1201 | 0 | 1.1201 | 0 |  |  | STILLWATER 110148950 | 851
35204830 | FT~STS-OFAC_IDLE_REMV-22249 ELK TRAIL | 2AF | Idle Facilities | 0 | 0 | 242 | 242 | 0.045833 | 0 | 0.045833 | 0 |  |  | STILLWATER 11021466 | 1251
35211694 | EMV-1 SW/O 22319 ELK | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | STILLWATER 11021466 | 1251
35291985 | FRRB - STILLWATER 1102_OH_FH_TPL_5 | 08W | Fire Rebuild | 0 | 4987 | 0 | 4987 | 0.94451 | 0.8875 | 0.057008 | 0 |  |  | STILLWATER 1102CB | 502
35207810 | DR-STS-POLE_IDLE_REMV-624 BPONDEROSATOEO | 2AF | Idle Facilities | 0 | 0 | 383 | 383 | 0.072538 | 0 | 0.072538 | 0 | 2021-06-07 | 2022-02-07 | SYCAMORE CREEK 11112014 | 1137
35221199 | RCQ-STS-COND_IDLE_REMV116BROOKSDR | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | SYCAMORE CREEK 11112014 | 1137
35244018 | STS-POLE_IDLE_REMV - 1 W/O 7 S/O 50386 C | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | TAMARACK 1101CB | 2630
35083773 | STS-COND_IDLE_REMV-20230 LYONS BALD MTN | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | TAR FLAT 0401CB | 3142
35083733 | STS-COND_IDLE_REMV-36017 TOYON DR/SOUTH | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | TEJON 1102732836 | 583
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | 08W | SH | 6019 | 0 | 0 | 6019 | 1.14 | 0 | 1.14 | 0 | 2022-04-18 08:00 | 2022-07-29 08:00 | TIDEWATER 210614072 | 18 | 35219093
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | 08W | SH | 6864 | 0 | 0 | 6864 | 1.3 | 0 | 1.3 | 0 | 2022-06-21 08:00 | 2022-11-02 17:00 | TIDEWATER 210614072 | 18 | 35219093
35217692 | STS-COND_IDLE_REMV - S/P @ 4E/O 2S/O 158 | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 | 2021-11-17 | 2022-04-16 | TYLER 110585132 | 383
35204877 | DR -COND_IDLE_REMV-R/O 544 FIRCREST DR | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 | 2021-10-12 | 2022-01-29 | UKIAH 1113548420 | 1369
35038557 | DR COND_IDLE_REMV-UKIAH POLICE SHOOTING | 2AF | Idle Facilities | 0 | 0 | 430 | 430 | 0.081439 | 0 | 0.081439 | 0 |  |  | UKIAH 11151216 | 1030
35151005 | 8/31 REMV IDLE 4 LOCS OLD WITTER SP*RA | 2AF | Idle Facilities | 0 | 0 | 1512 | 1512 | 0.28636 | 0 | 0.28636 | 0 | 2022-04-08 | 2022-04-08 | UPPER LAKE 1101412 | 259
35217273 | SH - UPPER LAKE 1101 CB | 08W | SH | 0 | 5702 | 0 | 5702 | 1.0799 | 0 | 1.0799 | 0 | 2022-03-31 08:00 | 2022-06-16 17:00 | UPPER LAKE 1101CB | 6
35219291 | CWSP - VACA DIXON 1101126774 | 08W | SH | 0 | 1931 | 0 | 1931 | 0.36572 | 0 | 0.36572 | 0 |  |  | VACA DIXON 1101126774 | 20
35219269 | CWSP - VACA DIXON 110540092 PH 1.1 | 08W | SH | 0 | 11299 | 0 | 11299 | 2.14 | 0 | 2.14 | 0 | 2022-04-12 08:00 | 2022-11-04 17:00 | VACA DIXON 110540092 | 37 | 35219269
35237258 | CWSP - VACA DIXON 110540092 PH 1.2 | 08W | SH | 0 | 11352 | 0 | 11352 | 2.15 | 0 | 2.15 | 0 | 2022-04-05 08:00 | 2022-10-28 17:00 | VACA DIXON 110540092 | 37 | 35219269
35237259 | CWSP - VACA DIXON 110540092 PH 1.3 | 08W | SH | 0 | 18873 | 0 | 18873 | 3.5744 | 0 | 3.5744 | 0 | 2022-04-22 08:00 | 2022-12-21 17:00 | VACA DIXON 110540092 | 37 | 35219269
35237360 | CWSP - VACA DIXON 110540092 PH 1.4 | 08W | SH | 0 | 15893 | 0 | 15893 | 3.01 | 0 | 3.01 | 0 | 2022-04-12 08:00 | 2022-11-25 17:00 | VACA DIXON 110540092 | 37 | 35219269
35237361 | CWSP - VACA DIXON 110540092 PH 1.5 | 08W | SH | 0 | 12346 | 0 | 12346 | 2.3383 | 0 | 2.3383 | 0 | 2022-04-04 08:00 | 2022-11-03 17:00 | VACA DIXON 110540092 | 37 | 35219269
35237364 | CWSP - VACA DIXON 110540092 PH 1.6 | 08W | SH | 0 | 14946 | 0 | 14946 | 2.8307 | 0 | 2.8307 | 0 | 2022-04-04 08:00 | 2022-11-17 17:00 | VACA DIXON 110540092 | 37 | 35219269
35237365 | CWSP - VACA DIXON 110540092 PH 1.7 | 08W | SH | 0 | 14762 | 0 | 14762 | 2.7958 | 0 | 2.7958 | 0 | 2022-04-19 08:00 | 2022-09-02 17:00 | VACA DIXON 110540092 | 37 | 35219269
35237366 | CWSP - VACA DIXON 110540092 PH 1.8 | 08W | SH | 0 | 11775 | 0 | 11775 | 2.2301 | 0 | 2.2301 | 0 | 2022-04-22 08:00 | 2022-08-24 17:00 | VACA DIXON 110540092 | 37 | 35219269
35237368 | CWSP - VACA DIXON 110540092 PH 1.9 | 08W | SH | 0 | 15167 | 0 | 15167 | 2.8725 | 0 | 2.8725 | 0 | 2022-04-12 08:00 | 2022-10-28 17:00 | VACA DIXON 110540092 | 37 | 35219269
35237369 | CWSP - VACA DIXON 110540092 PH 1.10 | 08W | SH | 0 | 17105 | 0 | 17105 | 3.2396 | 0 | 3.2396 | 0 | 2022-05-03 08:00 | 2022-09-29 17:00 | VACA DIXON 110540092 | 37 | 35219269
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 | 08W | SH | 0 | 19345 | 0 | 19345 | 3.6638 | 0 | 3.6638 | 0 | 2022-04-19 08:00 | 2022-10-14 17:00 | VACA DIXON 110540092 | 37 | 35219269
35237371 | CWSP - VACA DIXON 110540092 PH 1.12 | 08W | SH | 0 | 1810 | 0 | 1810 | 0.3428 | 0 | 0.3428 | 0 | 2022-04-22 08:00 | 2022-07-13 17:00 | VACA DIXON 110540092 | 37 | 35219269
35219590 | CWSP - VACA DIXON 1105965390 | 08W | SH | 0 | 8777 | 0 | 8777 | 1.6623 | 0 | 1.6623 | 0 | 2022-03-01 08:00 | 2022-06-08 17:00 | VACA DIXON 1105965390 | 53
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | 08W | SH | 19685 | 0 | 0 | 19685 | 3.7282 | 0 | 3.7282 | 0 | 2022-06-10 08:00 | 2022-12-15 17:00 | VACAVILLE 11046542 | 42 | 35219276
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | 08W | SH | 0 | 15253 | 401 | 15654 | 2.9648 | 1.1445 | 1.8203 | 0 | 2021-09-15 08:00 | 2022-03-31 | VACAVILLE 11046542 | 42 | 35224378
35227656 | CWSP - VACAVILLE 11046542 - PH 2.3 | 08W | SH | 8765 | 0 | 0 | 8765 | 1.66 | 0 | 1.66 | 0 | 2022-08-09 08:00 | 2023-02-10 17:00 | VACAVILLE 11046542 | 42 | 35224378
35227658 | CWSP - VACAVILLE 11046542 - PH 2.5 | 08W | SH | 0 | 2181 | 0 | 2181 | 0.41307 | 0 | 0.41307 | 0 | 2022-04-04 08:00 | 2022-08-22 17:00 | VACAVILLE 11046542 | 42 | 35224378
35227659 | CWSP - VACAVILLE 11046542 - PH 2.6 | 08W | SH | 0 | 1650 | 0 | 1650 | 0.3125 | 0.25568 | 0.056818 | 0 |  |  | VACAVILLE 11046542 | 42 | 35224378
35227870 | CWSP - VACAVILLE 11046542 - PH 2.2 | 08W | SH | 7840 | 0 | 0 | 7840 | 1.4848 | 0 | 1.4848 | 0 | 2022-01-25 08:00 | 2022-08-01 17:00 | VACAVILLE 11046542 | 42 | 35224378
35227651 | CWSP - VACAVILLE 11046542 PH 1.2 | 08W | SH | 0 | 14437 | 0 | 14437 | 2.7343 | 0 | 2.7343 | 0 | 2021-10-28 | 2022-03-14 08:00 | VACAVILLE 11046542 | 42 | 35219276
35227652 | CWSP - VACAVILLE 11046542 PH 1.3 | 08W | SH | 2851 | 0 | 0 | 2851 | 0.53996 | 0 | 0.53996 | 0 | 2022-04-27 08:00 | 2022-08-23 17:00 | VACAVILLE 11046542 | 42 | 35219276
35227653 | CWSP - VACAVILLE 11046542 PH 1.4 | 08W | SH | 0 | 13730 | 340 | 14070 | 2.6648 | 0 | 2.6648 | 0 | 2021-11-30 08:00 | 2022-03-30 17:00 | VACAVILLE 11046542 | 42 | 35219276
35227654 | CWSP - VACAVILLE 11046542 PH 1.5 | 08W | SH | 0 | 0 | 4603 | 4603 | 0.87178 | 0 | 0.87178 | 0 | 2022-08-02 08:00 | 2022-11-01 17:00 | VACAVILLE 11046542 | 42 | 35219276
35271455 | CWSP - VACAVILLE 11046542 PH 1.6 | 08W | SH | 0 | 2853 | 0 | 2853 | 0.54034 | 0 | 0.54034 | 0 | 2022-03-28 08:00 | 2022-08-11 17:00 | VACAVILLE 11046542 | 42
31157088 | REMV IDLE SVC POLE LAGOON VALLEY ROAD BE | 2AF | Idle Facilities | 0 | 0 | 1270 | 1270 | 0.24053 | 0 | 0.24053 | 0 |  |  | VACAVILLE 11046542 | 42
35208021 | DR-COND_IDLE_REMV-3628 GATES CANYON RD | 2AF | Idle Facilities | 0 | 0 | 1095 | 1095 | 0.20739 | 0 | 0.20739 | 0 |  |  | VACAVILLE 11088762 | 64
31156970 | FT STS-COND_IDLE_REMV-4065GIBSONCANYONRD | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | VACAVILLE 111113652 | 190
35083893 | STS-COND_IDLE_REMV-5282 MINES RD | 2AF | Idle Facilities | 0 | 0 | 356 | 356 | 0.067424 | 0 | 0.067424 | 0 |  |  | VASCO 1102MR176 | 324
35254720 | CWSP - VOLTA 11011568 PH 1.6 | 08W | SH | 0 | 7550 | 0 | 7550 | 1.4299 | 0 | 1.4299 | 0 | 2022-05-20 08:00 | 2022-09-08 17:00 | VOLTA 11011568 | 85 | 35240169
35254721 | CWSP - VOLTA 11011568 PH 1.7 | 08W | SH | 0 | 11642 | 0 | 11642 | 2.2049 | 0 | 2.2049 | 0 | 2022-03-31 08:00 | 2022-08-01 17:00 | VOLTA 11011568 | 85 | 35240169
35254941 | CWSP - VOLTA 11011568 PH 3.3 | 08W | SH | 0 | 11500 | 0 | 11500 | 2.178 | 0 | 2.178 | 0 | 2022-05-09 08:00 | 2022-09-19 17:00 | VOLTA 11011568 | 85 | 35240171
35254942 | CWSP - VOLTA 11011568 PH 3.4 | 08W | SH | 0 | 7825 | 0 | 7825 | 1.482 | 0 | 1.482 | 0 | 2022-05-24 08:00 | 2022-09-30 17:00 | VOLTA 11011568 | 85 | 35240171
35254943 | CWSP - VOLTA 11011568 PH 3.5 | 08W | SH | 0 | 4921 | 0 | 4921 | 0.93201 | 0 | 0.93201 | 0 | 2022-05-09 08:00 | 2022-10-19 17:00 | VOLTA 11011568 | 85 | 35240171
35254656 | CWSP - VOLTA 11011568 PH 1.2 | 08W | SH | 2334 | 0 | 0 | 2334 | 0.44205 | 0 | 0.44205 | 0 |  |  | VOLTA 11011568 | 85 | 35240169
35254657 | CWSP - VOLTA 11011568 PH 1.3 | 08W | SH | 0 | 0 | 845 | 845 | 0.16004 | 0 | 0.16004 | 0 | 2022-03-30 08:00 | 2022-09-26 17:00 | VOLTA 11011568 | 85 | 35240169
35254658 | CWSP - VOLTA 11011568 PH 1.4 | 08W | SH | 0 | 9272 | 0 | 9272 | 1.7561 | 0 | 1.7561 | 0 | 2022-05-16 08:00 | 2022-11-18 17:00 | VOLTA 11011568 | 85 | 35240169
35254659 | CWSP - VOLTA 11011568 PH 1.5 | 08W | SH | 0 | 14129 | 0 | 14129 | 2.6759 | 0 | 2.6759 | 0 | 2022-04-15 08:00 | 2022-10-04 17:00 | VOLTA 11011568 | 85 | 35240169
35240169 | CWSP - VOLTA 11011568 PH 1.1 | 08W | SH | 0 | 10006 | 0 | 10006 | 1.8951 | 0 | 1.8951 | 0 | 2022-05-04 08:00 | 2022-11-15 17:00 | VOLTA 11011568 | 85 | 35240169
35240170 | CWSP - VOLTA 11011568 PH 2.1 | 08W | SH | 0 | 4421 | 0 | 4421 | 0.83731 | 0 | 0.83731 | 0 | 2022-04-14 08:00 | 2022-09-07 17:00 | VOLTA 11011568 | 85 | 35240170
35240171 | CWSP - VOLTA 11011568 PH 3.1 | 08W | SH | 0 | 7080 | 0 | 7080 | 1.3409 | 0 | 1.3409 | 0 | 2022-05-09 08:00 | 2022-07-29 17:00 | VOLTA 11011568 | 85 | 35240171
35243453 | CWSP-VOLTA-11011596-PH1 | 08W | SH | 0 | 6358 | 0 | 6358 | 1.2042 | 0 | 1.2042 | 0 | 2022-05-31 08:00 | 2022-10-12 08:00 | VOLTA 11011596 | 966 | 35243453
35254944 | CWSP - VOLTA 11011596 - PH1.2 | 08W | SH | 0 | 279 | 633.6 | 912.6 | 0.17284 | 0 | 0.17284 | 0 | 2022-06-15 08:00 | 2022-10-27 08:00 | VOLTA 11011596 | 966 | 35243453
35254946 | CWSP - VOLTA 11011596 - PH1.4 | 08W | SH | 0 | 4694 | 0 | 4694 | 0.88902 | 0 | 0.88902 | 0 | 2022-05-02 08:00 | 2022-09-13 08:00 | VOLTA 11011596 | 966 | 35243453
35254948 | CWSP - VOLTA 11011596 - PH1.6 | 08W | SH | 0 | 5169 | 0 | 5169 | 0.97898 | 0 | 0.97898 | 0 | 2022-05-09 08:00 | 2022-11-18 17:00 | VOLTA 11011596 | 966 | 35243453
35143764 | STS-COND_IDLE_REMV-3 N/O 7 W/O 1 S/O 338 | 2AF | Idle Facilities | 0 | 0 | 124 | 124 | 0.023485 | 0 | 0.023485 | 0 |  |  | VOLTA 11011596 | 966
31534930 | CWSP - VOLTA 110149742 | 08H | SH | 0 | 12041 | 0 | 12041 | 2.2805 | 0 | 2.2805 | 0 | 2022-01-31 | 2022-04-22 | VOLTA 110149742 | 39 | 35219273
35219273 | CWSP - VOLTA 110149742 | 08W | SH | 0 | 6082 | 0 | 6082 | 1.1519 | 0 | 1.1519 | 0 | 2022-03-28 | 2022-06-15 17:00 | VOLTA 110149742 | 39
35240168 | CWSP - VOLTA 110153118 PH 1.1 | 08W | SH | 0 | 7920 | 0 | 7920 | 1.5 | 0 | 1.5 | 0 | 2022-08-03 08:00 | 2022-11-01 17:00 | VOLTA 110153118 | 157 | 35240168
35254649 | CWSP - VOLTA 110153118 PH 1.2 | 08W | SH | 3728 | 0 | 0 | 3728 | 0.70606 | 0 | 0.70606 | 0 | 2022-06-22 08:00 | 2022-12-30 17:00 | VOLTA 110153118 | 157 | 35240168
35254651 | CWSP - VOLTA 110153118 PH 1.4 | 08W | SH | 0 | 12805 | 0 | 12805 | 2.4252 | 0 | 2.4252 | 0 | 2022-06-28 08:00 | 2022-08-24 17:00 | VOLTA 110153118 | 157 | 35240168
35254652 | CWSP - VOLTA 110153118 PH 1.5 | 08W | SH | 0 | 10212 | 0 | 10212 | 1.9341 | 0 | 1.9341 | 0 | 2022-07-15 | 2022-09-30 | VOLTA 110153118 | 157 | 35240168
35254653 | CWSP - VOLTA 110153118 PH 1.6 | 08W | SH | 0 | 10708 | 0 | 10708 | 2.028 | 0 | 2.028 | 0 | 2022-09-16 08:00 | 2022-12-09 17:00 | VOLTA 110153118 | 157 | 35240168
35254654 | CWSP - VOLTA 110153118 PH 1.7 | 08W | SH | 0 | 819 | 0 | 819 | 0.15511 | 0 | 0.15511 | 0 | 2022-07-25 08:00 | 2022-11-18 17:00 | VOLTA 110153118 | 157 | 35240168
35254655 | CWSP - VOLTA 110153118 PH 1.8 | 08W | SH | 0 | 2916 | 0 | 2916 | 0.55227 | 0 | 0.55227 | 0 | 2022-09-16 08:00 | 2022-12-15 17:00 | VOLTA 110153118 | 157 | 35240168
35275479 | FT-OFAC_IDLE_REMV - #7 ON LINE S/O CO#5 | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | VOLTA 110180454 | 532
31548160 | CWSP - VOLTA 1101CB PH 1.1 | 08H | SH | 0 | 11273 | 0 | 11273 | 2.135 | 0 | 2.135 | 0 | 2022-03-07 | 2022-04-22 | VOLTA 1101CB | 76 | 35240166
35254640 | CWSP - VOLTA 1101CB PH 1.4 | 08W | SH | 0 | 5452 | 0 | 5452 | 1.0326 | 0 | 1.0326 | 0 | 2022-03-28 08:00 | 2022-04-22 17:00 | VOLTA 1101CB | 76 | 35240166
35254641 | CWSP - VOLTA 1101CB PH 1.5 | 08W | SH | 2758 | 401 | 2520 | 5679 | 1.0756 | 0 | 1.0756 | 0 | 2022-07-18 08:00 | 2023-01-06 17:00 | VOLTA 1101CB | 76 | 35240166
35254642 | CWSP - VOLTA 1101CB PH 1.6 | 08W | SH | 0 | 4279 | 0 | 4279 | 0.81042 | 0 | 0.81042 | 0 | 2022-05-04 08:00 | 2022-05-30 17:00 | VOLTA 1101CB | 76 | 35240166
35254643 | CWSP - VOLTA 1101CB PH 1.7 | 08W | SH | 6389 | 0 | 5797 | 12186 | 2.308 | 0 | 2.308 | 0 | 2022-06-24 08:00 | 2022-12-09 17:00 | VOLTA 1101CB | 76 | 35240166
35254644 | CWSP - VOLTA 1101CB PH 1.8 | 08W | SH | 0 | 2165 | 0 | 2165 | 0.41004 | 0 | 0.41004 | 0 | 2022-07-04 | 2022-10-11 17:00 | VOLTA 1101CB | 76 | 35240166
35254645 | CWSP - VOLTA 1101CB PH 2.2 | 08W | SH | 0 | 3965 | 0 | 3965 | 0.75095 | 0 | 0.75095 | 0 | 2022-05-31 08:00 | 2022-07-04 17:00 | VOLTA 1101CB | 76 | 35240167
35254646 | CWSP - VOLTA 1101CB PH 2.3 | 08W | SH | 0 | 0 | 1816 | 1816 | 0.34394 | 0 | 0.34394 | 0 | 2022-05-18 08:00 | 2022-11-01 17:00 | VOLTA 1101CB | 76 | 35240167
35254647 | CWSP - VOLTA 1101CB PH 2.4 | 08W | SH | 2672 | 0 | 0 | 2672 | 0.50606 | 0 | 0.50606 | 0 | 2022-07-18 08:00 | 2022-12-09 17:00 | VOLTA 1101CB | 76 | 35240167
35254648 | CWSP - VOLTA 1101CB PH 2.5 | 08W | SH | 0 | 2560 | 0 | 2560 | 0.48485 | 0 | 0.48485 | 0 | 2022-07-04 | 2022-11-01 17:00 | VOLTA 1101CB | 76 | 35240167
35240166 | CWSP - VOLTA 1101CB PH 1.1 | 08W | SH | 0 | 2523 | 0 | 2523 | 0.47784 | 0 | 0.47784 | 0 | 2022-02-28 08:00 | 2022-03-25 17:00 | VOLTA 1101CB | 76 | 35240166
35240167 | CWSP - VOLTA 1101CB PH 2.1 | 08W | SH | 2180 | 200 | 0 | 2380 | 0.45076 | 0 | 0.45076 | 0 | 2022-07-18 08:00 | 2022-12-09 17:00 | VOLTA 1101CB | 76 | 35240167
35205037 | DR~STS-COND_IDLE_REMV-22735 CANYON WY | 2AF | Idle Facilities | 0 | 0 | 152 | 152 | 0.028788 | 0 | 0.028788 | 0 | 2021-06-09 | 2022-02-18 | WEIMAR 11012058 | 1379
35211657 | DR~STS-COND_IDLE_REMV-1540 DOG BAR RD | 2AF | Idle Facilities | 0 | 0 | 518 | 518 | 0.098106 | 0 | 0.098106 | 0 |  |  | WEIMAR 11012058 | 1379
35211297 | DR~STS-COND_IDLE_REMV-2000 PONDEROSA WY | 2AF | Idle Facilities | 0 | 0 | 828 | 828 | 0.15682 | 0 | 0.15682 | 0 |  |  | WEIMAR 11012084 | 1801
35211671 | DR~STS-COND_IDLE_REMV-1120 NATUREWOOD DR | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | WEIMAR 11022038 | 2536
35221807 | STS-COND_IDLE_REMV - 1142 RAILROAD FLAT | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 | 2021-12-10 | 2022-03-07 | WEST POINT 11024790 | 1664
35207962 | FT-COND_IDLE_REMV-13080 FERN RD EAST | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | WHITMORE 11011594 | 678
35204813 | FT-COND_IDLE_REMV-FERN RD -1 POLE N/O S | 2AF | Idle Facilities | 0 | 0 | 363 | 363 | 0.06875 | 0 | 0.06875 | 0 |  |  | WHITMORE 11011598 | 820
35204814 | DR-COND_IDLE_REMV-14820 FERN RD | 2AF | Idle Facilities | 0 | 0 | 1110 | 1110 | 0.21023 | 0 | 0.21023 | 0 |  |  | WHITMORE 11011598 | 820
35275960 | FT-OFAC_IDLE_REMV - 4E/O 30146 OAK RUN | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | WHITMORE 11011598 | 820
35217667 | DR~STS-POLE_IDLE_REM-1S/O 10W/O 30520 MO | 2AF | Idle Facilities | 0 | 0 | 522 | 522 | 0.098864 | 0 | 0.098864 | 0 |  |  | WHITMORE 110145262 | 685
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | 08W | SH | 0 | 8994 | 0 | 8994 | 1.7034 | 0 | 1.7034 | 0 | 2022-07-01 08:00 | 2023-01-27 17:00 | WILDWOOD 11011454 | 52 | 35224321
35226799 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | 08W | SH | 0 | 0 | 1015 | 1015 | 0.19223 | 0 | 0.19223 | 0 | 2022-04-04 08:00 | 2022-11-01 17:00 | WILDWOOD 11011454 | 52 | 35224321
35226900 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH4 | 08W | SH | 0 | 3441 | 0 | 3441 | 0.6517 | 0 | 0.6517 | 0 | 2022-04-11 08:00 | 2022-10-17 17:00 | WILDWOOD 11011454 | 52 | 35224321
35297692 | FRRB - WILLOW CREEK 11032936 UG ML4 | 08W | Fire Rebuild | 24604 | 0 | 0 | 24604 | 4.6598 | 0 | 4.6598 | 0 | 2022-02-28 | 2022-03-16 | WILLOW CREEK 11032936 | 1474
35297693 | FRRB - WILLOW CREEK 11032936 UG ML5 | 08W | Fire Rebuild | 5280 | 0 | 0 | 5280 | 1 | 0 | 1 | 0 |  |  | WILLOW CREEK 11032936 | 1474
35297694 | FRRB - WILLOW CREEK 11032936 UG ML6 | 08W | Fire Rebuild | 5016 | 0 | 0 | 5016 | 0.95 | 0 | 0.95 | 0 |  |  | WILLOW CREEK 11032936 | 1474
35297695 | FRRB - WILLOW CREEK 11032936 UG TL1 | 08W | Fire Rebuild | 2323 | 0 | 0 | 2323 | 0.43996 | 0 | 0.43996 | 0 | 2022-01-28 | 2022-02-04 | WILLOW CREEK 11032936 | 1474
35297696 | FRRB - WILLOW CREEK 11032936 UG TL2 | 08W | Fire Rebuild | 4171 | 0 | 0 | 4171 | 0.78996 | 0 | 0.78996 | 0 | 2022-02-15 | 2022-02-25 | WILLOW CREEK 11032936 | 1474
35297697 | FRRB - WILLOW CREEK 11032936 UG TL3 | 08W | Fire Rebuild | 78 | 0 | 0 | 78 | 0.014773 | 0 | 0.014773 | 0 | 2022-02-22 | 2022-02-24 | WILLOW CREEK 11032936 | 1474
35297699 | FRRB - WILLOW CREEK 11032936 UG ML3 | 08W | Fire Rebuild | 5385 | 0 | 0 | 5385 | 1.0199 | 0 | 1.0199 | 0 | 2022-02-07 | 2022-02-09 | WILLOW CREEK 11032936 | 1474
35281815 | FRRB - WILLOW CREEK 11032936 UG ML1 | 08W | Fire Rebuild | 2428 | 0 | 0 | 2428 | 0.45985 | 0 | 0.45985 | 0 |  |  | WILLOW CREEK 11032936 | 1474
35078722 | DR-COND_IDLE_REMV-470 TRI DALE LN | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | WISE 11022234 | 430
35242865 | DR~STS-COND_IDLE_REMV-410 STAR HILL RD | 2AF | Idle Facilities | 0 | 0 | 300 | 300 | 0.056818 | 0 | 0.056818 | 0 |  |  | WOODSIDE 11018972 | 1376
35295745 | FRRB - WYANDOTTE 1103 W5 SM5 | 08W | Fire Rebuild | 2213 | 0 | 0 | 2213 | 0.41913 | 0 | 0.41913 | 0 | 2022-01-13 | 2022-04-04 17:00 | WYANDOTTE 11031508 | 1176
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | 08W | Fire Rebuild | 14250 | 0 | 0 | 14250 | 2.6989 | 2.2879 | 0.41098 | 0 |  |  | WYANDOTTE 11031508 | 1176
35236984 | FRRB - WYANDOTTE 1103 - W5 PH 5.5 | 08W | Fire Rebuild | 10402 | 0 | 0 | 10402 | 1.9701 | 0 | 1.9701 | 0 | 2022-01-13 | 2022-04-05 | WYANDOTTE 11031508 | 1176
35235706 | FRRB - WYANDOTTE 1103 - W2 PH 2.7 | 08W | Fire Rebuild | 3717 | 0 | 0 | 3717 | 0.70398 | 0 | 0.70398 | 0 | 2021-10-07 | 2022-02-28 17:00 | WYANDOTTE 11031974 | 1849 | 35232718
35235707 | FRRB - WYANDOTTE 1103 - W2 PH 2.8 | 08W | Fire Rebuild | 4987 | 0 | 0 | 4987 | 0.94451 | 0 | 0.94451 | 0 | 2021-11-21 | 2022-03-04 | WYANDOTTE 11031974 | 1849 | 35232718
35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | 08W | Fire Rebuild | 2229 | 0 | 0 | 2229 | 0.42216 | 0 | 0.42216 | 0 | 2021-11-15 | 2022-02-17 | WYANDOTTE 11031974 | 1849 | 35232298
35239522 | FRRB - WYANDOTTE 1103 - W2 PH 2.9 | 08W | Fire Rebuild | 1297 | 0 | 0 | 1297 | 0.24564 | 0 | 0.24564 | 0 | 2021-11-13 | 2022-03-31 17:00 | WYANDOTTE 11031974 | 1849 | 35232718
35240546 | FRRB - WYANDOTTE 1103 - W2 PH2.13 | 08W | Fire Rebuild | 650 | 0 | 0 | 650 | 0.12311 | 0 | 0.12311 | 0 | 2022-02-28 | 2022-09-15 17:00 | WYANDOTTE 11031974 | 1849
35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | 08W | Fire Rebuild | 1907 | 0 | 0 | 1907 | 0.36117 | 0 | 0.36117 | 0 | 2021-11-03 | 2022-01-27 | WYANDOTTE 11031974 | 1849 | 35232298
35233302 | FRRB - WYANDOTTE 1103 - W1 PH 1.6 | 08W | Fire Rebuild | 750 | 0 | 0 | 750 | 0.14205 | 0 | 0.14205 | 0 | 2021-11-08 | 2022-02-16 | WYANDOTTE 11031974 | 1849 | 35232298
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 | 08W | Fire Rebuild | 1597 | 0 | 0 | 1597 | 0.30246 | 0 | 0.30246 | 0 | 2022-02-28 | 2022-10-28 17:00 | WYANDOTTE 11031974 | 1849 | 35232298
35233312 | FRRB - WYANDOTTE 1103 - W2 PH 2.3 | 08W | Fire Rebuild | 4138 | 0 | 0 | 4138 | 0.78371 | 0 | 0.78371 | 0 |  |  | WYANDOTTE 11031974 | 1849 | 35232718
35233314 | FRRB - WYANDOTTE 1103 - W2 PH 2.4 | 08W | Fire Rebuild | 12514 | 0 | 0 | 12514 | 2.3701 | 2.0169 | 0.35322 | 0 |  |  | WYANDOTTE 11031974 | 1849 | 35232718
35233315 | FRRB - WYANDOTTE 1103 - W2 PH 2.5 | 08W | Fire Rebuild | 4013 | 0 | 0 | 4013 | 0.76004 | 0 | 0.76004 | 0 | 2022-02-25 | 2022-03-31 17:00 | WYANDOTTE 11031974 | 1849 | 35232718
35283874 | FRRB - WYANDOTTE 1103 - W2 PH2.14 | 08W | Fire Rebuild | 2127 | 0 | 795 | 2922 | 0.55341 | 0 | 0.55341 | 0 | 2021-11-05 | 2022-03-14 17:00 | WYANDOTTE 11031974 | 1849
35237889 | FRRB - WYANDOTTE 1103 - W3 PH 3.2 | 08W | Fire Rebuild | 8855 | 0 | 0 | 8855 | 1.6771 | 0 | 1.6771 | 0 | 2021-12-06 | 2022-02-28 17:00 | WYANDOTTE 11031976 | 1299 | 35235320
35237890 | FRRB - WYANDOTTE 1103 - W3 PH 3.3 | 08W | Fire Rebuild | 5998 | 0 | 0 | 5998 | 1.136 | 0 | 1.136 | 0 | 2021-09-20 | 2022-03-07 17:00 | WYANDOTTE 11031976 | 1299 | 35235320
35237891 | FRRB - WYANDOTTE 1103 - W3 PH 3.4 | 08W | Fire Rebuild | 2258 | 0 | 0 | 2258 | 0.42765 | 0 | 0.42765 | 0 | 2022-01-31 | 2022-03-11 | WYANDOTTE 11031976 | 1299 | 35235320
35237893 | FRRB - WYANDOTTE 1103 - W3 PH 3.5 | 08W | Fire Rebuild | 3950 | 0 | 0 | 3950 | 0.74811 | 0 | 0.74811 | 0 | 2021-09-11 | 2022-03-31 17:00 | WYANDOTTE 11031976 | 1299 | 35235320
35237894 | FRRB - WYANDOTTE 1103 - W3 PH 3.6 | 08W | Fire Rebuild | 6257 | 0 | 0 | 6257 | 1.185 | 0 | 1.185 | 0 |  |  | WYANDOTTE 11031976 | 1299 | 35235320
35237896 | FRRB - WYANDOTTE 1103 - W3 PH 3.8 | 08W | Fire Rebuild | 7548 | 0 | 0 | 7548 | 1.4295 | 0 | 1.4295 | 0 | 2021-09-17 | 2022-02-28 17:00 | WYANDOTTE 11031976 | 1299 | 35235320
35237021 | FRRB - WYANDOTTE 1103 W7 SM1 | 08W | Fire Rebuild | 1020 | 0 | 0 | 1020 | 0.19318 | 0 | 0.19318 | 0 | 2022-03-16 08:00 | 2022-09-21 17:00 | WYANDOTTE 11031976 | 1299
35239095 | FRRB - WYANDOTTE 1103 - W4 PH 4.3 | 08W | Fire Rebuild | 7924 | 50 | 0 | 7974 | 1.5102 | 0 | 1.5102 | 0 | 2021-09-01 | 2022-03-31 17:00 | WYANDOTTE 11031976 | 1299
35239096 | FRRB - WYANDOTTE 1103 - W4 PH 4.4 | 08W | Fire Rebuild | 4145 | 0 | 0 | 4145 | 0.78504 | 0 | 0.78504 | 0 | 2022-02-05 | 2022-04-08 | WYANDOTTE 11031976 | 1299
35239097 | FRRB - WYANDOTTE 1103 - W4 PH 4.5 | 08W | Fire Rebuild | 5704 | 0 | 0 | 5704 | 1.0803 | 0 | 1.0803 | 0 | 2021-10-19 | 2022-04-08 | WYANDOTTE 11031976 | 1299
35239098 | FRRB - WYANDOTTE 1103 - W4 PH 4.6 | 08W | Fire Rebuild | 11438 | 0 | 0 | 11438 | 2.1663 | 0 | 2.1663 | 0 | 2021-11-05 | 2022-04-08 | WYANDOTTE 11031976 | 1299
35239099 | FRRB - WYANDOTTE 1103 - W4 PH 4.7 | 08W | Fire Rebuild | 2167 | 0 | 0 | 2167 | 0.41042 | 0 | 0.41042 | 0 | 2021-10-04 | 2022-01-24 17:00 | WYANDOTTE 11031976 | 1299
35235700 | FRRB - WYANDOTTE 1103 - W4 PH4.11 | 08W | Fire Rebuild | 6661 | 178 | 0 | 6839 | 1.2953 | 0 | 1.2953 | 0 | 2021-11-18 | 2022-04-08 | WYANDOTTE 11031976 | 1299
35235320 | FRRB - WYANDOTTE 1103 - W3 PH 3.1 | 08W | Fire Rebuild | 1300 | 0 | 0 | 1300 | 0.24621 | 0 | 0.24621 | 0 | 2022-01-27 | 2022-09-09 17:00 | WYANDOTTE 11031976 | 1299 | 35235320
35236993 | FRRB - WYANDOTTE 1103 - W4 PH 4.9 | 08W | Fire Rebuild | 2316 | 0 | 0 | 2316 | 0.43864 | 0 | 0.43864 | 0 | 2022-02-25 | 2022-04-18 | WYANDOTTE 11031976 | 1299
35236995 | FRRB - WYANDOTTE 1103 - W4 PH4.10 | 08W | Fire Rebuild | 12056 | 0 | 0 | 12056 | 2.2833 | 0 | 2.2833 | 0 | 2021-12-06 | 2022-03-31 17:00 | WYANDOTTE 11031976 | 1299
35236990 | FRRB - WYANDOTTE 1103 - W3 PH 3.9 | 08W | Fire Rebuild | 4504 | 0 | 0 | 4504 | 0.85303 | 0 | 0.85303 | 0 |  |  | WYANDOTTE 11031976 | 1299 | 35235320
35236991 | FRRB - WYANDOTTE 1103 - W4 PH 4.8 | 08W | Fire Rebuild | 5533 | 0 | 0 | 5533 | 1.0479 | 0 | 1.0479 | 0 | 2022-02-25 | 2022-09-20 17:00 | WYANDOTTE 11031976 | 1299
35078735 | COND_IDLE_REMV-1403 FORBESTOWN ROAD | 2AF | Idle Facilities | 0 | 0 | 332 | 332 | 0.062879 | 0 | 0.062879 | 0 |  |  | WYANDOTTE 11071510 | 905
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | SH | 0 | 4901 | 4579 | 9480 | 1.7955 | 0.87803 | 0.91742 | 0 | 2021-09-15 | 2022-04-15 | WYANDOTTE 110932586 | 29 | 35219260
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | SH | 4066 | 0 | 0 | 4066 | 0.77008 | 0 | 0.77008 | 0 | 2022-04-13 08:00 | 2022-09-09 17:00 | WYANDOTTE 1109702710 | 218
35324156 | PSPS - ROSSMOOR 1108 CB | 08W | SH | 4031 | 0 | 0 | 4031 | 0.76345 | 0 | 0.76345 | 0 |  |  | ROSSMOOR 1108CB | 2676 | 35145004
35224856 | EP HWY 191 RELOCATION, PARADISE CALTRANS | 10Q | Other | 14800 | 580 | 0 | 15380 | 2.9129 | 0 | 1.1364 | 1.7765
35083712 | STS-COND_IDLE_REMV-LOC #8, 23795 SOUTHFO | 2AF | Idle Facilities | 0 | 0 | 727 | 727 | 0.13769 | 0 | 0.13769 | 0
35207842 | DR-POLE_IDLE_REMV-2110 DUPONTE DR | 2AF | Idle Facilities | 0 | 0 | 200 | 200 | 0.037879 | 0 | 0.037879 | 0 | 2021-06-11 | 2022-02-03
35211241 | FT STS-POLE_IDLE_REMV-95667PLACERVILLE | 2AF | Idle Facilities | 0 | 0 | 395 | 395 | 0.074811 | 0 | 0.074811 | 0
35225436 | STS-OFAC_IDLE_REMV-SS/O 74267 CROSS COUN | 2AF | Idle Facilities | 0 | 0 | 200 | 200 | 0.037879 | 0 | 0.037879 | 0 | 2021-02-24 | 2022-01-14
35222036 | CZUSCRUZ 21600 BIG BASIN, BOULDER CRK | 95F | Fire Rebuild | 0 | 2770 | 0 | 2770 | 0.52462 | 0 | 0.52462 | 0
35235158 | #CZUSCRUZ 2151 PINE FLAT RD, SCRUZ | 95F | Fire Rebuild | 0 | 163 | 0 | 163 | 0.030871 | 0 | 0.030871 | 0
35237593 | #CZUSCRUZ 425 SAN VICENTE TERRACE, SCRUZ | 95F | Fire Rebuild | 0 | 145 | 0 | 145 | 0.027462 | 0 | 0.027462 | 0
35238840 | CZUSCRUZ 230 SWANTON RD, DAVENPORT | 95F | Fire Rebuild | 2435 | 725 | 0 | 3160 | 0.59848 | 0 | 0.59848 | 0
35239462 | DAVIDCRUZ 1675 FOXGLOVE, BOULDER CREE | 95F | Fire Rebuild | 0 | 1520 | 0 | 1520 | 0.28788 | 0.22879 | 0.059091 | 0
35239464 | #CZUSCRUZ 395 BOULDER BROOK DR, BCREEK | 95F | Fire Rebuild | 0 | 371 | 0 | 371 | 0.070265 | 0 | 0.070265 | 0
35245029 | XPOLE_BURN_REPL - 890 ROBLES DR. SANTA C | 95F | Fire Rebuild | 0 | 1650 | 0 | 1650 | 0.3125 | 0 | 0.3125 | 0
35250987 | XCZUSCRUZ 185 KNOB HILL DR, BOULDER CREE | 95F | Fire Rebuild | 0 | 466 | 0 | 466 | 0.088258 | 0 | 0.088258 | 0
35263364 | XCZUSCRUZ 20801 LITTLE BASIN RD,BOULDER | 95F | Fire Rebuild | 0 | 2048 | 0 | 2048 | 0.38788 | 0 | 0.38788 | 0 | 2021-08-19 | 2022-01-21
35318072 | FRRB-BIG BASIN 1101 10720 P1S1 705BOULDB | 08W | Fire Rebuild | 675 | 0 | 0 | 675 | 0.12784 | 0 | 0.12784 | 0 |  |  | BIG BASIN 110110720 | 2435