## Sheet1
Order | Program | Order Description | MAT | UG Miles | OH Miles | Removal Miles | Total Miles | County | Construction Start | Construction End | Circuit | Circuit Name | Circuit Protection Zone | Projects Costs (Actuals/Forecast - thousands) | Notes
35194522 | Fire Rebuild | SR-CC-SANTA CRUZ-08-16-20 CZU COMPLEX | 95B | 0.50739 | 0 | 0 | 0.50739 | Santa Cruz | [6 empty] | Work completed in MWC 95, but costs captured in comingled 08W orders and cannot split for this specific scope of work
35199922 | Fire Rebuild | CV-FR - CREEK 9/13/20 - CREEK FIRE SYS H | 95A | 0.37197 | 17.26 | 0 | 17.632 | Fresno | [5 empty] | 6190 | Work completed in MWC 95, but costs captured in 08W
35200051 | Fire Rebuild | NO-NV-BUTTE 9/8/20- N. CMPLX FIRE SYS H | 95B | 1.4746 | 0 | 0 | 1.4746 | BUTTE | [6 empty] | Work completed in MWC 95, but costs captured in comingled 08W orders and cannot split for this specific scope of work
35238840 | Fire Rebuild | CZUSCRUZ 230 SWANTON RD, DAVENPORT | 95F | 0.46117 | 0.13731 | 0 | 0.59848 | SANTA CRUZ | 2021-08-17 | 2021-11-19 |  |  |  | 1110 | Non-08W project
35270705 | Fire Rebuild | FRRB - ANTLER 11011612 TL2 | 08W | 0.79394 | 0 | 0 | 0.79394 | SHASTA | 2021-08-11 | 2021-11-15 | 103271101 | ANTLER 1101 | ANTLER 11011612 | 1400
35270706 | Fire Rebuild | FRRB - ANTLER 11011612 TL5 | 08W | 0.87102 | 0.10417 | 0 | 0.97519 | SHASTA | 2021-08-04 | 2021-11-20 | 103271101 | ANTLER 1101 | ANTLER 11011612 | 2780
35270755 | Fire Rebuild | FRRB - ANTLER 11011612 TL1 | 08W | 0.74867 | 0 | 0 | 0.74867 | SHASTA | 2021-08-09 | 2021-11-20 | 103271101 | ANTLER 1101 | ANTLER 11011612 | 1460
35242421 | Fire Rebuild | FRRB - BIG BEND 1102 - B6 PH6.2 (M/L-M) | 08W | 1.2674 | 0 | 0 | 1.2674 | BUTTE | 2021-08-06 | 2021-12-14 | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 2450
35242422 | Fire Rebuild | FRRB - BIG BEND 1102 - B6 PH6.3 (T/L-1) | 08W | 0.85398 | 0 | 0 | 0.85398 | BUTTE | 2021-10-02 | 2021-12-14 | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 1710
35242423 | Fire Rebuild | FRRB - BIG BEND 1102 - B6 PH6.4 (T/L-2) | 08W | 0.88958 | 0 | 0 | 0.88958 | BUTTE | 2021-09-30 | 2021-12-14 | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 1780
35242424 | Fire Rebuild | FRRB - BIG BEND 1102 - B6 PH6.5 (T/L-3) | 08W | 0.69943 | 0 | 0 | 0.69943 | BUTTE | 2021-09-30 | 2021-12-18 | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 1400
35242425 | Fire Rebuild | FRRB - BIG BEND 1102 - B6 PH6.6 (T/L-4) | 08W | 0.66155 | 0 | 0 | 0.66155 | BUTTE | 2021-09-27 | 2021-12-14 | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 1370
35223343 | Fire Rebuild | FRRB - BIG BEND 1102 - LAKE MADRONE PH1 | 08W | 0.95473 | 0.0094697 | 0 | 0.9642 | BUTTE | 2021-06-28 | 2021-09-02 | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 2890
35225821 | Fire Rebuild | FRRB - BIG BEND 1102 - LAKE MADRONE PH2 | 08W | 1.1314 | 0 | 0 | 1.1314 | BUTTE | 2021-08-02 | 2021-09-25 | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 2420
35235677 | Fire Rebuild | FRRB - BIG BEND 1102 - B4 PH4.1 | 08W | 5.414 | 0 | 0 | 5.414 | BUTTE | 2021-08-16 | 2021-12-18 | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 11670
35235678 | Fire Rebuild | FRRB - BIG BEND 1102 - B5 PH5.1 (M/L-S) | 08W | 1.2422 | 0 | 0 | 1.2422 | BUTTE | 2021-08-16 | 2021-12-18 | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 3340
35235679 | Fire Rebuild | FRRB - BIG BEND 1102 - B6 PH6.1 (M/L-N) | 08W | 0.72784 | 0 | 0 | 0.72784 | BUTTE | 2021-08-04 | 2021-12-14 | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 2730
35112076 | Base SH | OCGC FULTON 1107-OH TO UG MARK W SPG | 08W | 0.69261 | 1.5093 | 0 | 2.2019 | SONOMA | 2019-09-12 | 2020-03-10 |  |  | FULTON 1107214 | 4090
35282131 | Fire Rebuild | FRRB - KANAKA 1101CB - K1 SM1 | 08W | 0.038447 | 0 | 0 | 0.038447 | Butte | 2021-12-10 | 2022-01-26 | 103221101 | KANAKA 1101 | KANAKA 1101CB | 240
35254695 | Fire Rebuild | FRRB - KANAKA 1101CB - K2 SM2 | 08W | 0.055303 | 0 | 0 | 0.055303 | Butte | 2021-12-04 | 2022-01-26 | 103221101 | KANAKA 1101 | KANAKA 1101CB | 180
35250343 | Fire Rebuild | FRRB - KANAKA 1101CB - K2 SM1 | 08W | 0.29432 | 0 | 0 | 0.29432 | BUTTE | 2021-11-01 | 2022-01-26 | 103221101 | KANAKA 1101 | KANAKA 1101CB | 590
35031662 | Base SH | CWSP - LOS GATOS 1106 - LB44 - PHASE 2.1 | 08W | 0.09678 | 0.46723 | 0 | 0.56402 | Santa Clara | 2020-02-10 | 2020-03-27 |  |  | LOS GATOS 1106LB44 | 980
35116801 | Base SH | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | 08W | 0.10417 | 1.1737 | 0 | 1.2778 | Tuolumne | 2020-06-22 | 2021-05-03 | 163661702 | MIWUK 1702 | MIWUK 1702823548 | 2000
35114431 | Base SH | CWSP - MORAGA 1101 - LR108540 - PH5 | 08W | 0.031439 | 1.4055 | 0 | 1.4369 | CONTRA COSTA | 2020-03-02 | 2020-03-27 |  |  | MORAGA 1101108540 | 3830
35103325 | Base SH | CWSP - MORAGA 1102 & 1104 - OCB | 08W | 0.71117 | 0.5983 | 0 | 1.3095 | CONTRA COSTA | 2019-05-21 | 2020-03-14 |  |  | MORAGA 1102CB | 3140
74022388 | Base SH | OCGC CWSP: X-1104 OH RECOND SKYLINE | 08W | 0.72159 | 0 | 0 | 0.72159 | ALAMEDA | 2020-02-14 | 2020-11-04 |  |  | OAKLAND X 1104CR022 | 3880
35145524 | Base SH | PSPS - RINCON 1101 1103 SYSTEM HARDENING | 08W | 1.5216 | 0 | 0 | 1.5216 | Sonoma | 2021-04-26 | 2021-08-31 | 43321103 | RINCON 1103 | RINCON 1103CB | 6390
74008802 | Other | INST ROSSMOOR 1109 FDR_MORAGA BK5 EMERG | 06A | 0.099432 | 1.0496 | 0 | 1.1491 | Contra Costa | 2020-07-07 08:00 | 2021-11-17 |  |  | ROSSMOOR 1108CB | 15420 | Non-08W project - includes scope beyond HFTD miles captured as part of System Hardening
35279510 | Fire Rebuild | FRRB - SG 1102 TL UG 04 | 08W | 0.091856 | 0 | 0 | 0.091856 | PLACER | 2021-08-25 | 2021-08-27 | 152431101 | SHADY GLEN 1101 | SHADY GLEN 110248894 | 160
35225824 | Fire Rebuild | FRRB - WYANDOTTE 1103 - HWY 162 | 08W | 2.2879 | 0 | 0 | 2.2879 | BUTTE | 2021-05-17 | 2021-06-30 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 5400
35235705 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W2 PH 2.6 | 08W | 1.7104 | 0 | 0 | 1.7104 | Butte | 2021-07-22 | 2021-11-20 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 3520
35235706 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W2 PH 2.7 | 08W | 0.7108 | 0 | 0 | 0.7108 | Butte | 2021-08-31 | 2022-01-31 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 2340
35233038 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | 08W | 0.46932 | 0 | 0 | 0.46932 | BUTTE | 2021-06-28 | 2021-09-02 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 1010
35233039 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | 08W | 0.42216 | 0 | 0 | 0.42216 | BUTTE | 2021-11-15 | 2022-02-17 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 1050
35240545 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W2 PH2.12 | 08W | 0.13125 | 0 | 0 | 0.13125 | Butte | 2021-09-07 | 2021-09-29 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 780
35239522 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W2 PH 2.9 | 08W | 0.24564 | 0 | 0 | 0.24564 | Butte | 2021-11-13 | 2022-01-28 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 1110
35239523 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W2 PH2.10 | 08W | 0.22917 | 0 | 0 | 0.22917 | Butte | 2021-09-13 | 2021-11-20 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 820
35239937 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W2 PH2.11 | 08W | 0.46193 | 0 | 0 | 0.46193 | Butte | 2021-08-20 | 2021-10-04 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 2590
35232298 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W1 PH 1.1 | 08W | 0.26155 | 0 | 0 | 0.26155 | BUTTE | 2021-08-14 | 2021-09-17 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 1460
35232718 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W2 PH 2.1 | 08W | 0.37652 | 0 | 0 | 0.37652 | Butte | 2021-08-24 | 2021-10-20 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 1340
35233300 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | 08W | 0.36117 | 0 | 0 | 0.36117 | BUTTE | 2021-01-06 | 2021-11-15 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 950
35233301 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | 08W | 0.12917 | 0 | 0 | 0.12917 | BUTTE | 2021-07-28 | 2021-09-08 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 1000
35233302 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W1 PH 1.6 | 08W | 0.14205 | 0 | 0 | 0.14205 | BUTTE | 2021-11-08 | 2022-02-16 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 850
35233303 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | 08W | 0.065909 | 0 | 0 | 0.065909 | BUTTE | 2021-07-22 | 2021-09-02 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 340
35233304 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W1 PH 1.8 | 08W | 0.35644 | 0 | 0 | 0.35644 | BUTTE | 2021-08-19 | 2021-10-08 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 870
35233305 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | 08W | 0.55114 | 0 | 0 | 0.55114 | BUTTE | 2021-08-10 | 2021-10-08 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 1200
35233306 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W1 PH1.10 | 08W | 0.35398 | 0 | 0 | 0.35398 | BUTTE | 2021-09-07 | 2021-10-08 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 710
35233307 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W1 PH1.11 | 08W | 0.36402 | 0 | 0 | 0.36402 | Butte | 2021-06-29 | 2021-08-25 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 1090
35233308 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W1 PH1.12 | 08W | 1.047 | 0 | 0 | 1.047 | BUTTE | 2021-06-23 | 2021-09-21 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 2280
35233309 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W1 PH1.13 | 08W | 0.38295 | 0 | 0 | 0.38295 | Butte | 2021-08-04 | 2021-10-08 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 1160
35233311 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W2 PH 2.2 | 08W | 0.64205 | 0 | 0 | 0.64205 | Butte | 2021-06-28 | 2021-09-28 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 2440
35233312 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W2 PH 2.3 | 08W | 0.78371 | 0 | 0 | 0.78371 | Butte | 2021-09-20 | 2021-12-22 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 2370
35233314 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W2 PH 2.4 | 08W | 2.3701 | 0 | 0 | 2.3701 | Butte | 2021-06-28 | 2021-11-20 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 4490
35223344 | Fire Rebuild | FRRB - WANDOTTE 1103 BALD ROCK ZONE 1&2 | 08W | 3.8902 | 0 | 0 | 3.8902 | BUTTE | 2021-02-15 | 2021-05-20 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 7780
35225822 | Fire Rebuild | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | 08W | 0.75152 | 0 | 0 | 0.75152 | BUTTE | 2021-03-01 | 2021-06-30 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 3540
35283874 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W2 PH2.14 | 08W | 0.40284 | 0 | 0.15057 | 0.55341 | Butte | 2021-09-20 | 2022-01-10 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 630
35244330 | Fire Rebuild | FRRB - WYANDOTTE 11031974 - W1 SM1 | 08W | 0.057386 | 0 | 0 | 0.057386 | Butte | 2021-05-20 | 2021-08-11 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 240
35248770 | Fire Rebuild | FRRB - WYANDOTTE 11031974 - W1 SM2 | 08W | 0.10814 | 0 | 0 | 0.10814 | Butte | 2021-05-20 | 2021-09-03 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 530
35249161 | Fire Rebuild | FRRB - WYANDOTTE 11031974 - W3 SM3 | 08W | 0.19508 | 0 | 0 | 0.19508 | BUTTE | 2021-09-07 | 2021-10-04 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 560
35279243 | Fire Rebuild | FRRB - WYANDOTTE 11031974 - W3 SM4 | 08W | 0.20511 | 0 | 0 | 0.20511 | BUTTE | 2021-11-11 | 2021-12-21 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 620
35225823 | Fire Rebuild | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | 08W | 1.3602 | 0 | 0 | 1.3602 | BUTTE | 2021-05-28 | 2021-10-20 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 3080
35223345 | Fire Rebuild | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | 08W | 3.7676 | 0 | 0 | 3.7676 | BUTTE | 2021-04-13 | 2021-08-11 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 10890
35237889 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W3 PH 3.2 | 08W | 1.7973 | 0 | 0 | 1.7973 | Butte | 2022-01-10 | 2022-02-28 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 4150
35237890 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W3 PH 3.3 | 08W | 1.2286 | 0 | 0 | 1.2286 | Butte | 2021-09-20 | 2022-02-23 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 2380
35237894 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W3 PH 3.6 | 08W | 1.185 | 0 | 0 | 1.185 | Butte | 2021-09-10 | 2021-12-02 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 2230
35237896 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W3 PH 3.8 | 08W | 1.4295 | 0 | 0 | 1.4295 | Butte | 2021-01-03 | 2021-11-20 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 2860
35235669 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W4 PH 4.1 | 08W | 0.39148 | 0 | 0 | 0.39148 | Butte | 2021-09-24 | 2021-11-08 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 780
35235671 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W4 PH 4.2 | 08W | 0.6161 | 0 | 0 | 0.6161 | Butte | 2021-08-13 | 2021-11-15 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 1180
35235673 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W3 PH3.10 | 08W | 0.49356 | 0 | 0 | 0.49356 | Butte | 2021-09-22 | 2021-12-21 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 720
35236990 | Fire Rebuild | FRRB - WYANDOTTE 1103 - W3 PH 3.9 | 08W | 0.85303 | 0 | 0 | 0.85303 | Butte | 2021-09-13 | 2021-12-23 | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 3060