## Sheet1
A | B | C | D | E | F | G | H | I | J | K | L | M | N | O | P | Q
Order | Circuit | CPZ (entirely) | CPZ (partially) | Circuit Voltage | County | Start Date | Completion Date | Circuit Miles | Total Trenching Miles | Life Cycle Costs (electric) | Life Cycle Costs (non-electric) | Rule 20A Project | WMP Project | Post Fire Project | Telecom Participation | Gas Participation
35091907 | Paradise 1106 |  |  | 12kV | Butte | 2019-09-03 | 2020-01-05 | 0.40133 | 1.1932 | 2025348.3 | 621298.7 | No | Yes | Yes | No | Yes
35112876 | Paradise 1106 |  |  | 12kV | Butte | 2019-07-31 | 2020-01-21 | 1.3831 | 1.985 | 636268.6 | 448596.3 | No | Yes | Yes | No | Yes
35112090 | Paradise 1106 |  |  | 12kV | Butte | 2019-09-23 | 2020-01-31 | 0.78939 | 1.3975 | 1488688.5 | 245597 | No | Yes | Yes | No | Yes
35120949 | Notre Dame 1103 |  |  | 12kV | Butte | 2019-08-05 | 2020-02-01 | 1.99 | 0 | 12284765.2 | 0 | No | Yes | Yes | No | No
35103940 | Paradise 1106 |  |  | 12kV | Butte | 2019-10-17 | 2020-02-07 | 0.82652 | 1.3508 | 1133773 | 481471.2 | No | Yes | Yes | No | Yes
35099654 | Paradise 1106 |  |  | 12kV | Butte | 2019-07-08 | 2020-02-14 | 1.0237 | 1.9672 | 1732070.5 | 2333611.6 | No | Yes | Yes | No | Yes
35109832 | Paradise 1105 |  |  | 12kV | Butte | 2019-09-03 | 2020-02-28 | 0.69583 | 1.3981 | 2798721.5 | 938284.1 | No | Yes | Yes | No | Yes
35101876 | Paradise 1106 |  |  | 12kV | Butte | 2019-08-12 | 2020-03-11 | 0.72045 | 1.0847 | 1473980.8 | 622232.7 | No | Yes | Yes | No | Yes
35094034 | Paradise 1105 |  |  | 12kV | Butte | 2019-05-31 | 2020-03-13 | 0.18958 | 0.50985 | 540854 | 0 | No | Yes | Yes | No | No
35101743 | Paradise 1105 |  |  | 12kV | Butte | 2019-07-18 | 2020-03-13 | 0.27557 | 0.4214 | 577519.5 | 0 | No | Yes | Yes | No | No
35112182 | Paradise 1105 |  |  | 12kV | Butte | 2019-08-05 | 2020-03-13 | 0.65303 | 0.97652 | 1237919.2 | 0 | No | Yes | Yes | No | No
35112089 | Paradise 1106 |  |  | 12kV | Butte | 2019-10-21 | 2020-03-13 | 1.3028 | 1.4503 | 2084562.1 | 977857.6 | No | Yes | Yes | No | Yes
35105717 | Paradise 1104 |  |  | 12kV | Butte | 2019-10-10 | 2020-03-17 | 0.34091 | 0.90114 | 1097685.8 | 444372.3 | No | Yes | Yes | No | Yes
35101875 | Paradise 1106 |  |  | 12kV | Butte | 2019-09-10 | 2020-03-19 | 0.90833 | 1.6871 | 1842439.8 | 339226.6 | No | Yes | Yes | No | Yes
74010581 | Paradise 1103 |  |  | 12kV | Butte | 2019-07-08 | 2020-03-20 | 1.614 | 1.9295 | 4129714.8 |  | Yes | Yes | Yes | No | No
35095246 | Paradise 1104 |  |  | 12kV | Butte | 2019-05-09 | 2020-03-21 | 0.055492 | 0.13902 | 145546 | 0 | No | Yes | Yes | No | No
35101031 | Paradise 1103 |  |  | 12kV | Butte | 2019-05-30 | 2020-03-21 | 0.50133 | 0.43239 | 1216910.8 | 0 | No | Yes | Yes | No | No
35105654 | Paradise 1104 |  |  | 12kV | Butte | 2019-10-04 | 2020-04-01 | 1.0047 | 1.2591 | 1019582.5 | 386481.9 | No | Yes | Yes | No | Yes
35105644 | Paradise 1105 |  |  | 12kV | Butte | 2019-09-23 | 2020-04-06 | 0.56534 | 1.0025 | 2112094.4 | 481891.4 | No | Yes | Yes | No | Yes
35110372 | Paradise 1105 |  |  | 12kV | Butte | 2019-11-15 | 2020-04-10 | 0.24091 | 0.45436 | 1083918.8 | 140973.6 | No | Yes | Yes | No | Yes
35101877 | Paradise 1106 |  |  | 12kV | Butte | 2019-09-03 | 2020-04-15 | 0.34091 | 2.0629 | 2902676.2 | 835929.2 | No | Yes | Yes | No | Yes
35110369 | Paradise 1105 |  |  | 12kV | Butte | 2019-11-18 | 2020-04-15 | 0.73939 | 1.196 | 1763219.7 | 255875 | No | Yes | Yes | No | Yes
35112092 | Paradise 1104 |  |  | 12kV | Butte | 2019-10-11 | 2020-04-16 | 1.0797 | 1.5966 | 1601109.1 | 1119371.1 | No | Yes | Yes | No | Yes
35112091 | Paradise 1106 |  |  | 12kV | Butte | 2019-10-23 | 2020-04-17 | 0.63447 | 1.0072 | 1232736.9 | 359439.1 | No | Yes | Yes | No | Yes
35105649 | Paradise 1104 |  |  | 12kV | Butte | 2019-10-28 | 2020-04-17 | 0.99261 | 1.7598 | 2311008.1 | 461013.3 | No | Yes | Yes | No | Yes
35105647 | Paradise 1104 |  |  | 12kV | Butte | 2019-09-03 | 2020-04-24 | 0.9536 | 1.1434 | 2421383.3 | 563679.3 | No | Yes | Yes | No | Yes
35110377 | Paradise 1105 |  |  | 12kV | Butte | 2019-09-23 | 2020-04-30 | 1.8472 | 2.1919 | 4320018.4 | 672700.5 | No | Yes | Yes | No | Yes
35112249 | Paradise 1103 |  |  | 12kV | Butte | 2019-10-30 | 2020-05-15 | 1.8706 | 1.7725 | 4279116.1 | 1322660.7 | No | Yes | Yes | No | Yes
35112128 | Paradise 1106 |  |  | 12kV | Butte | 2019-11-18 | 2020-05-15 | 0.63068 | 1.2528 | 2007141.8 | 468324.7 | No | Yes | Yes | No | Yes
35110376 | Paradise 1104, Paradise 1105 |  |  | 12kV | Butte | 2020-01-29 | 2020-06-16 17:00 | 1.0606 | 1.3739 | 1910565.8 | 573929.1 | No | Yes | Yes | No | Yes
35105655 | Paradise 1104 |  |  | 12kV | Butte | 2020-01-27 | 2020-08-14 17:00 | 1.3133 | 1.7583 | 1655052.1 | 647369.4 | No | Yes | Yes | No | Yes
35137332 | Camp Evers 2106, Paradise 1104 |  |  | 12kV | Butte | 2020-04-06 | 2020-10-03 | 2.7856 | 2.192 | 5299323 | 1391371.4 | No | Yes | Yes | No | Yes
35118663 | Paradise 1106 |  |  | 12kV | Butte | 2020-07-06 | 2020-11-25 | 1.0223 | 1.2848 | 2083218 | 405888.3 | No | Yes | Yes | No | Yes
35132419 | Paradise 1105, Paradise 1104 |  |  | 12kV | Butte | 2020-04-22 | 2020-12-05 | 2.6383 | 4.2972 | 5795333.1 | 2531774.3 | No | Yes | Yes | No | Yes
35110373 | Paradise 1104, Paradise 1105 |  |  | 12kV | Butte | 2020-07-07 | 2020-12-12 | 1.1898 | 1.7642 | 2709438.1 | 73796.4 | No | Yes | Yes | No | Yes
35112220 | Paradise 1103 |  |  | 12kV | Butte | 2020-07-01 | 2021-02-12 | 1.4773 | 2.6231 | 3174181.5 | 806336.1 | No | Yes | Yes | No | Yes
35127542 | Paradise 1106, Paradise 1104 |  |  | 12kV | Butte | 2020-06-01 | 2021-03-19 | 4.3333 | 4.9652 | 7311327.8 | 2326453.7 | No | Yes | Yes | No | Yes
35126754 | Paradise 1103 |  |  | 12kV | Butte | 2020-07-13 | 2021-04-30 | 2.3814 | 4.1589 | 4651412.4 | 1338701.2 | No | Yes | Yes | No | Yes
35127553 | Paradise 1104 |  |  | 12kV | Butte | 2020-07-22 | 2021-03-01 | 1.6979 | 3.0828 | 3653399.3 | 1500220.4 | No | Yes | Yes | No | Yes
35127541 | Paradise 1104 |  |  | 12kV | Butte | 2020-07-27 | 2021-09-14 | 2.6027 | 4.5769 | 4739817 | 1452859 | No | Yes | Yes | No | Yes
35127546 | Paradise 1103 |  |  | 12kV | Butte | 2020-07-27 | 2021-05-06 | 4.5481 | 5.3614 | 7485672.9 | 1508288.4 | No | Yes | Yes | No | Yes
35105646 | Paradise 1104 |  |  | 12kV | Butte | 2020-08-03 | 2021-03-15 | 1.3843 | 1.8009 | 2571019 | 941289.4 | No | Yes | Yes | No | Yes
35170663 | Paradise 1103, Buck's Creek 1102, Buck's Creek 1101 |  |  | 12kV | Butte | 2020-10-12 | 2021-11-17 | 3.2229 | 3.414 | 9599256.7 | 45178.1 | No | Yes | Yes | No | No
35132170 | Paradise 1104 |  |  | 12kV | Butte | 2020-11-16 | 2021-06-21 | 1.9438 | 3.1803 | 5957458.1 | 2229603.4 | No | Yes | Yes | No | Yes
35159697 | Paradise 1104 |  |  | 12kV | Butte | 2020-12-21 | 2021-09-28 | 1.9981 | 2.418 | 3515029.1 | 1262569.9 | No | Yes | Yes | No | Yes
35159693 | Paradise 1104 |  |  | 12kV | Butte | 2021-03-08 | 2021-08-23 | 2.7254 | 3.5951 | 4621328.6 | 2750663.9 | No | Yes | Yes | Yes | Yes
35159685 | Paradise 1105 |  |  | 12kV | Butte | 2021-06-07 | 2022-02-04 | 1.3208 | 1.554 | 2899179.1 | 1034039.3 | No | Yes | Yes | Yes | Yes
35177253 | Paradise 1104 |  |  | 12kV | Butte | 2021-07-26 | 2021-12-13 | 1.5638 | 1.6248 | 3181610.4 | 446821.7 | No | Yes | Yes | Yes | Yes
35170561 | Paradise 1104 |  |  | 12kV | Butte | 2020-09-20 | 2020-09-10 | 0.11004 | 0.22708 | 235132.9 | 179413.8 | No | Yes | Yes | No | Yes
35174095 | Paradise 1104 |  |  | 12kV | Butte | 2020-06-19 | 2020-06-23 | 0.24848 | 0.43636 | 399484 | 183558 | No | Yes | Yes | No | Yes
35174783 | Paradise 1104 |  |  | 12kV | Butte | 2020-08-25 | 2020-08-26 | 0.045644 | 0.095265 | 90874.9 | 0 | No | Yes | Yes | No | No
35175487 | Paradise 1106 |  |  | 12kV | Butte | 2020-07-17 | 2020-08-10 | 0.086364 | 0.21667 | 252454.1 | 150508.2 | No | Yes | Yes | No | Yes
35177086 | Paradise 1103 |  |  | 12kV | Butte | 2020-07-27 | 2020-07-27 | 0.030492 | 0.10114 | 128806.1 | 61841.7 | No | Yes | Yes | No | Yes
35177866 | Paradise 1104 |  |  | 12kV | Butte | 2020-07-31 | 2020-11-14 | 0.057955 | 0.1339 | 163096.1 | 75114.4 | No | Yes | Yes | No | Yes
35178338 | Paradise 1104 |  |  | 12kV | Butte | 2020-07-25 | 2020-08-21 | 0.052462 | 0.14394 | 126170.2 | 54855.6 | No | Yes | Yes | No | Yes
35179069 | Paradise 1103 |  |  | 12kV | Butte | 2020-08-14 | 2020-09-04 | 0.1392 | 0.2286 | 194773.4 | 56394.4 | No | Yes | Yes | No | Yes
35179328 | Paradise 1103 |  |  | 12kV | Butte | 2020-11-10 | 2020-12-18 | 0.079735 | 0.10473 | 138623.4 | 99081.8 | No | Yes | Yes | No | Yes
35180088 | Paradise 1104 |  |  | 12kV | Butte | 2020-11-04 | 2020-11-20 | 0.02803 | 0.10417 | 131240.9 | 103279.6 | No | Yes | Yes | No | Yes
35181318 | Paradise 1106 |  |  | 12kV | Butte | 2020-11-04 | 2020-12-18 | 0.048106 | 0.11364 | 144456.5 | 84241.3 | No | Yes | Yes | No | Yes
35181319 | Paradise 1105 |  |  | 12kV | Butte | 2020-09-18 | 2020-10-16 | 0.10114 | 0.090909 | 113378.4 | 73700.6 | No | Yes | Yes | No | Yes
35181934 | Paradise 1104 |  |  | 12kV | Butte | 2020-09-25 | 2020-11-07 | 0.039773 | 0.089205 | 112537.1 | 45427.6 | No | Yes | Yes | No | Yes
35181936 | Paradise 1104 |  |  | 12kV | Butte | 2020-09-02 | 2020-09-14 | 0.1089 | 0.26023 | 273540.6 | 146006.6 | No | Yes | Yes | No | Yes
35182208 | Paradise 1105 |  |  | 12kV | Butte | 2020-10-20 | 2020-12-03 | 0.21894 | 0.37765 | 459065.7 | 80065.7 | No | Yes | Yes | No | Yes
35182209 | Paradise 1104 |  |  | 12kV | Butte | 2020-09-01 | 2020-09-25 | 0.066288 | 0.13617 | 109264.2 | 75283.1 | No | Yes | Yes | No | Yes
35182210 | Paradise 1104 |  |  | 12kV | Butte | 2020-11-30 | 2020-12-18 | 0.05303 | 0.10208 | 221023 | 86729.4 | No | Yes | Yes | No | Yes
35183481 | Paradise 1103 |  |  | 12kV | Butte | 2020-08-25 | 2020-08-28 | 0.00625 | 0.095455 | 115722 | 69245.8 | No | Yes | Yes | No | Yes
35184176 | Paradise 1104 |  |  | 12kV | Butte | 2020-11-21 | 2021-01-07 | 0.11799 | 0.24564 | 151774.3 | 146341.1 | No | Yes | Yes | No | Yes
35186503 | Paradise 1104 |  |  | 12kV | Butte | 2020-11-02 | 2020-12-05 | 0.46742 | 0.825 | 716270.5 | 352131.7 | No | Yes | Yes | No | Yes
35186617 | Paradise 1103 |  |  | 12kV | Butte | 2020-10-21 | 2020-12-04 | 0.08428 | 0.13826 | 81572.1 | 267098.5 | No | Yes | Yes | No | Yes
35187286 | Paradise 1104 |  |  | 12kV | Butte | 2020-12-19 | 2020-12-30 | 0.12841 | 0.26913 | 235373 | 97812.2 | No | Yes | Yes | No | Yes
35191076 | Paradise 1105 |  |  | 12kV | Butte | 2020-09-05 | 2020-09-04 | 0.086174 | 0.11269 | 130688.2 | 76289.6 | No | Yes | Yes | No | Yes
35191566 | Paradise 1105 |  |  | 12kV | Butte | 2020-11-21 | 2020-12-08 | 0.013068 | 0.0625 | 108752.7 | 78472 | No | Yes | Yes | No | Yes
35193883 | Paradise 1104 |  |  | 12kV | Butte | 2020-11-24 | 2020-12-29 | 0.066098 | 0.060985 | 236180.8 | 0 | No | Yes | Yes | No | No
35194490 | Paradise 1104 |  |  | 12kV | Butte | 2020-12-07 | 2020-12-17 | 0.098485 | 0.17614 | 241639.7 | 89345.9 | No | Yes | Yes | No | Yes
35200101 | Paradise 1104 |  |  | 12kV | Butte | 2020-12-19 | 2020-12-16 | 0.024053 | 0.096591 | 99750.6 | 81268.4 | No | Yes | Yes | No | Yes
35207668 | Paradise 1104 |  |  | 12kV | Butte | 2020-12-10 | 2020-12-23 | 0.082197 | 0.19432 | 225027.3 | 124218.8 | No | Yes | Yes | No | Yes
35207705 | Paradise 1104 |  |  | 12kV | Butte | 2021-02-13 | 2021-02-19 | 0.076894 | 0.18485 | 200421.5 | 132475.3 | No | Yes | Yes | No | Yes
35179966 | Paradise 1104 |  |  | 12kV | Butte | 2022-02-07 | 2022-02-28 | 0.070076 | 0.068561 | 28295.9 | 17244 | No | Yes | Yes | No | No
35192583 | Paradise 1105 |  |  | 12kV | Butte | 2021-05-03 | 2021-05-17 | 0.096023 | 0.10114 | 196709.5 | 0 | No | Yes | Yes | Yes | No
35199063 | Paradise 1106 |  |  | 12kV | Butte | 2021-03-05 | 2021-03-27 | 0.10758 | 0.11951 | 278610.1 | 87895.8 | No | Yes | Yes | No | Yes
35199561 | Paradise 1104 |  |  | 12kV | Butte | 2021-03-16 | 2021-04-29 | 0.20398 | 0.16364 | 326381 | 79865.1 | No | Yes | Yes | No | Yes
35200008 | Paradise 1105 |  |  | 12kV | Butte | 2021-02-18 | 2021-03-04 | 0.14867 | 0.2911 | 399769.6 | 161068.2 | No | Yes | Yes | No | Yes
35207704 | Paradise 1104 |  |  | 12kV | Butte | 2021-02-06 | 2021-03-12 | 0.17898 | 0.28561 | 285246.5 | 83692.1 | No | Yes | Yes | No | Yes
35207706 | Paradise 1104 |  |  | 12kV | Butte | 2021-03-24 | 2021-04-02 | 0.095644 | 0.13144 | 190410.5 | 77907.2 | No | Yes | Yes | Yes | Yes
35207708 | Paradise 1104 |  |  | 12kV | Butte | 2021-02-22 | 2021-03-04 | 0.088258 | 0.19943 | 234044.3 | 139932.2 | No | Yes | Yes | No | Yes
35214044 | Paradise 1104 |  |  | 12kV | Butte | 2021-03-22 | 2021-04-06 | 0.15644 | 0.23788 | 394960.1 | 177464.1 | No | Yes | Yes | No | Yes
35214203 | Paradise 1104 |  |  | 12kV | Butte | 2021-04-06 | 2021-05-14 | 0.17083 | 0.26989 | 355487.3 | 320657.7 | No | Yes | Yes | Yes | Yes
35217062 | Paradise 1105 |  |  | 12kV | Butte | 2021-04-28 | 2021-05-18 | 0 | 0.13958 | 166978.2 | 81442.8 | No | Yes | Yes | Yes | Yes
35217542 | Paradise 1104 |  |  | 12kV | Butte | 2021-04-07 | 2021-04-30 | 0.20682 | 0.14792 | 404169.7 | 151470.4 | No | Yes | Yes | Yes | Yes
35219327 | Paradise 1104 |  |  | 12kV | Butte | 2021-08-02 | 2021-08-16 | 0.048106 | 0.095833 | 69679.8 | 239502.9 | No | Yes | Yes | Yes | Yes
35219328 | Paradise 1104 |  |  | 12kV | Butte | 2021-05-10 | 2021-08-05 | 0.18258 | 0.31932 | 433394.4 | 207542.8 | No | Yes | Yes | Yes | Yes
35222240 | Paradise 1104 |  |  | 12kV | Butte | 2021-05-10 | 2021-08-05 | 0.38466 | 0.42064 | 432065.9 | 853672.5 | No | Yes | Yes | Yes | Yes
35222243 | Paradise 1105 |  |  | 12kV | Butte | 2021-03-04 | 2021-03-19 | 0.033712 | 0.092614 | 150262.3 | 91334.4 | No | Yes | Yes | No | Yes
35224131 | Paradise 1106 |  |  | 12kV | Butte | 2021-08-10 | 2021-09-07 | 0.072348 | 0.1411 | 268196.8 | 117585.4 | No | Yes | Yes | Yes | Yes
35231603 | Paradise 1104 |  |  | 12kV | Butte | 2021-11-17 | 2022-01-18 | 0.058712 | 0.12576 | 113594.6 | 377519.3 | No | Yes | Yes | Yes | Yes
35231834 | Paradise 1103 |  |  | 12kV | Butte | 2021-09-14 | 2021-11-29 | 0.16686 | 0.30701 | 115348 | 833338.8 | No | Yes | Yes | Yes | Yes
35232294 | Paradise 1105 |  |  | 12kV | Butte | 2021-05-24 | 2021-06-04 | 0.055871 | 0.10549 | 135090.5 | 51892.9 | No | Yes | Yes | Yes | Yes
35232296 | Paradise 1104 |  |  | 12kV | Butte | 2021-05-10 | 2021-08-05 | 0.12557 | 0.11818 | 217968.1 | 0 | No | Yes | Yes | Yes | No
35235217 | Paradise 1104 |  |  | 12kV | Butte | 2021-07-12 | 2021-08-07 | 0.054167 | 0.094508 | 297594 | 134168.1 | No | Yes | Yes | Yes | Yes
35240411 | Paradise 1104 |  |  | 12kV | Butte | 2021-06-07 | 2021-06-11 | 0 | 0.059091 | 59746.8 | 29723.4 | No | Yes | Yes | Yes | Yes
35245803 | Paradise 1104 |  |  | 12kV | Butte | 2021-06-10 | 2021-07-06 | 0.15568 | 0.24413 | 73152.4 | 490652.6 | No | Yes | Yes | No | Yes
35278011 | Paradise 1104 |  |  | 12kV | Butte | 2022-01-24 | 2022-02-09 | 0.0064394 | 0.018939 | 62734.4 | 0 | No | Yes | Yes | No | No

## Sheet2
|  |  | Elec | Total | Gas
Electric Order | TeleCom Status | 35140980 | 6793.4 | 6793.4 | 0
35140980 | Not Incl | 35140985 | 50373.5 | 50373.5 | 0
35140985 | Not Incl | 35142489 | 17468.5 | 17468.5 | 0
35142489 | Not Incl | 35169703 | 28197.8 | 28197.8 | 0
35169703 |  | 35170311 | 50299.8 | 50299.8 | 0
35170311 | Not Incl | 35170561 | 235132.9 | 414546.7 | 179413.8
35170561 | Not Incl | 35174094 | 87436.8 | 222291.2 | 134854.4
35174094 | Not Incl | 35174095 | 399484 | 583042 | 183558
35174095 | Not Incl | 35174783 | 90874.9 | 90874.9 | 0
35174783 | Not Incl | 35174784 | 22246.7 | 22246.7 | 0
35174784 | Not Incl | 35174790 | 165052.1 | 165052.1 | 0
35174790 | Not Incl | 35174963 | 215589.9 | 215589.9 | 0
35174963 | Not Incl | 35175487 | 252454.1 | 402962.3 | 150508.2
35175487 | Not Incl | 35177086 | 128806.1 | 190647.8 | 61841.7
35177086 | Not Incl | 35177865 | 52218.7 | 104519.1 | 52300.4
35177865 | Not Incl | 35177866 | 163096.1 | 238210.5 | 75114.4
35177866 | Not Incl | 35178338 | 126170.2 | 181025.8 | 54855.6
35178338 | Not Incl | 35178700 | 81464.2 | 81464.2 | 0
35178700 | Not Incl | 35179067 | 3049.8 | 9189.5 | 6139.7
35179067 | Not Incl | 35179068 | 12395.1 | 12395.1 | 0
35179068 | Not Incl | 35179069 | 194773.4 | 251167.8 | 56394.4
35179069 | Not Incl | 35179328 | 138623.4 | 237705.2 | 99081.8
35179328 | Not Incl | 35179966 | 28295.9 | 45539.9 | 17244
35179966 | Not Incl | 35180088 | 131240.9 | 234520.5 | 103279.6
35180088 | Not Incl | 35181318 | 144456.5 | 228697.8 | 84241.3
35181318 | Not Incl | 35181319 | 113378.4 | 187079 | 73700.6
35181319 | Not Incl | 35181924 | 140667 | 250138.4 | 109471.4
35181924 | Not Incl | 35181934 | 112537.1 | 157964.7 | 45427.6
35181934 | Not Incl | 35181936 | 273540.6 | 419547.2 | 146006.6
35181936 | Not Incl | 35182203 | 107224 | 107224 | 0
35182203 | Not Incl | 35182208 | 459065.7 | 539131.4 | 80065.7
35182208 | Not Incl | 35182209 | 109264.2 | 184547.3 | 75283.1
35182209 | Not Incl | 35182210 | 221023 | 307752.4 | 86729.4
35182210 | Not Incl | 35183419 | 99795.8 | 99795.8 | 0
35183419 | Not Incl | 35183481 | 115722 | 184967.8 | 69245.8
35183481 | Not Incl | 35184176 | 151774.3 | 298115.4 | 146341.1
35184176 | Not Incl | 35184426 | 14116.3 | 14116.3 | 0
35184426 | Not Incl | 35186503 | 716270.5 | 1068402.2 | 352131.7
35186503 | Not Incl | 35186617 | 81572.1 | 348670.6 | 267098.5
35186617 | Not Incl | 35186726 | 5046.6 | 11732.6 | 6686
35186726 | Not Incl | 35187286 | 235373 | 333185.2 | 97812.2
35187286 | Not Incl | 35187444 | 1225.2 | 1225.2 | 0
35187444 | Not Incl | 35190514 |  | 0 | 0
35190514 | Not Incl | 35191076 | 130688.2 | 206977.8 | 76289.6
35191076 | Not Incl | 35191566 | 108752.7 | 187224.7 | 78472
35191566 | Not Incl | 35192326 | 17548.7 | 17548.7 | 0
35192326 | Not Incl | 35192583 | 196709.5 | 196709.5 | 0
35192583 | Complete | 35193883 | 236180.8 | 236180.8 | 0
35193883 | Not Incl | 35193885 | 77570.9 | 77570.9 | 0
35193885 | Not Incl | 35194490 | 241639.7 | 330985.6 | 89345.9
35194490 | Not Incl | 35199063 | 278610.1 | 366505.9 | 87895.8
35199063 | Not Incl | 35199074 | 17.8 | 17.8 | 0
35199074 | Not Incl | 35199561 | 326381 | 406246.1 | 79865.1
35199561 | Not Incl | 35199563 | 153080.1 | 153080.1 | 0
35199563 | Not Incl | 35200008 | 399769.6 | 560837.8 | 161068.2
35200008 | Not Incl | 35200100 | 4378.3 | 4378.3 | 0
35200100 | Not Incl | 35200101 | 99750.6 | 181019 | 81268.4
35200101 | Not Incl | 35205538 |  | 0 | 0
35205538 | Not Incl | 35207668 | 225027.3 | 349246.1 | 124218.8
35207668 | Not Incl | 35207704 | 285246.5 | 368938.6 | 83692.1
35207704 | Not Incl | 35207705 | 200421.5 | 332896.8 | 132475.3
35207705 | Not Incl | 35207706 | 190410.5 | 268317.7 | 77907.2
35207706 | Complete | 35207708 | 234044.3 | 373976.5 | 139932.2
35207708 | Not Incl | 35207710 |  | 0 | 0
35207710 | Not Incl | 35214044 | 394960.1 | 572424.2 | 177464.1
35214044 | Not Incl | 35214203 | 355487.3 | 676145 | 320657.7
35214203 | Complete | 35214210 | 163318 | 287569.9 | 124251.9
35214210 | Not Incl | 35217062 | 166978.2 | 248421 | 81442.8
35217062 | Complete | 35217542 | 404169.7 | 555640.1 | 151470.4
35217542 | Complete | 35219327 | 69679.8 | 309182.7 | 239502.9
35219327 | Complete | 35219328 | 433394.4 | 640937.2 | 207542.8
35219328 | Complete | 35222240 | 432065.9 | 1285738.4 | 853672.5
35222240 | Complete | 35222243 | 150262.3 | 241596.7 | 91334.4
35222243 | Not Incl | 35224131 | 268196.8 | 385782.2 | 117585.4
35224131 | Complete | 35231603 | 113594.6 | 491113.9 | 377519.3
35231603 | Complete | 35231834 | 115348 | 948686.8 | 833338.8
35231834 | Complete | 35232294 | 135090.5 | 186983.4 | 51892.9
35232294 | Complete | 35232296 | 217968.1 | 217968.1 | 0
35232296 | Complete | 35235217 | 297594 | 431762.1 | 134168.1
35235217 | Complete | 35240411 | 59746.8 | 89470.2 | 29723.4
35240411 | Complete | 35245803 | 73152.4 | 563805 | 490652.6
35245803 | Not Incl | 35245804 | 88455.6 | 170338.7 | 81883.1
35245804 |  | 35254271 | 3072.6 | 12401.1 | 9328.5
35254271 |  | 35254272 | 4069.8 | 17821.6 | 13751.8
35254272 |  | 35254273 | 4759.5 | 14468.1 | 9708.6
35254273 |  | 35254274 | 2718.5 | 15573.1 | 12854.6
35254274 |  | 35254275 | 2883.3 | 12900 | 10016.7
35254275 |  | 35254276 | 2489 | 5094.6 | 2605.6
35254276 |  | 35254341 | 3016.6 | 5918.6 | 2902
35254341 |  | 35254342 | 3100.8 | 11004.7 | 7903.9
35254342 |  | 35254343 | 4705.6 | 13213.3 | 8507.7
35254343 |  | 35254344 | 0 | 9618 | 9618
35254344 |  | 35254345 | 960 | 4662.3 | 3702.3
35254345 |  | 35254346 |  | 2516.7 | 2516.7
35254346 |  | 35259417 | 4301.8 | 4301.8 | 0
35259417 |  | 35263029 | 53726.1 | 1839182.4 | 1785456.3
35263029 | Complete | 35276483 | 114293.4 | 167546.6 | 53253.2
35276483 |  | 35278011 | 62734.4 | 62734.4 | 0
35278011 |  | 35293309 | 1199.9 | 3086.9 | 1887
35293309 |  | 35332262 |  | 188.4 | 188.4
35332262