## Slide 1
Compliance Plan Quarterly Update
Q4 2021
February 14, 2022

## Slide 2: Compliance Plan Quarterly Update – Q4 2021 Executive Summary
This report is a quarterly update on the Wildfire Safety Inspection Program (WSIP) Compliance Plan and Interim Controls (“Compliance Plan”) to CPUC. The original Compliance Plan was communicated to CPUC on August 20, 2019.
Following the original Compliance Plan, the scope of reporting was expanded to include Non-WSIP and Non-HFTD tags created in 2019 and on.
Starting with 2021 Q1, PG&E is expanding the reporting to include all Open inspection driven electric equipment repair tags, that were created prior to 2019.
Summary of corrective tags created and corrective tags that are currently open (as of December 31, 2021) is shown on the right.
Starting with 2020 Q3, PG&E started using an automated report to query the number of open, created, and closed tags, which has resulted in variances between the Q2 and Q3 updates. Where variances are observed, PG&E has provided explanations throughout the report. PG&E is continuing to identify additional enhancements to the report which may result in further changes to the data and format of future reports.
System | Tags Created1 (data as of 12/31/2021) | Tags Open2 (data as of 12/31/2021)
Electric Distribution | 761,452 | 507,904
Electric Transmission | 191,676 | 75,211
Electric Substation | 36,662 | 3,881
Total | 989,790 | 586,996
1 Tags created on or after 1/1/2019
2 Starting with 2021 Q1, includes tags created prior to 1/1/2019

## Slide 3: Compliance Plan Quarterly Update – Q4 2021 Table 1: Tags Created
Table 1 summarizes tags created since January 1, 2019, using PG&E’s programs adopted to comply with GO 95, 165, and 174.
1 For Distribution, WSIP tags are defined by tags in HFTD Tier 3, Tier 2, or Zone 1 created through WSIP from the data as of 10/31/19; starting with 2020 Q2, the distribution compliance plan data categorizes notifications found in “Buffer Zones” as the WSIP inspection source.
2 Counts as reported to CPUC in 2019 Q4 update; does not include Non-HFTD tags
3 The 2020 Q2 distribution tags counts inadvertently included staging notifications (referred to as “S9” notifications for Distribution) and Can’t Get Ins (CGI’s), which have since been excluded.
4 Prior to 2020 Q3, Transmission WSIP created tag counts inadvertently included staging notifications (referred to as “S5” notifications for Transmission), which have since been excluded. Removal of S5 tags have resulted in a reduction of the number of WSIP tags created. There are several reasons S5 notifications are cancelled and do not become an LC tag, including:
  The notification is a duplicate, e.g. another notification S5 or LC exists to perform the same work
  Work will be performed under another notification before the due date of the S5, e.g. pole replacement LC due before insulator repair S5
  Work has been performed under another notification or project, e.g. recent pole replacement project or emergency pole replacement (fire)
  Issue has been eliminated with another project, e.g. S5 for insulator repair canceled for a line because the conductor/insulators have been removed from tower under another project
  Issue not valid per PG&E’s Electric Transmission Preventative Maintenance (ETPM) Manual or Job Aids
  Non-conformance exists on a distribution/substation asset, S5 will be canceled once a notification under Distribution or Substations is created
5 Effective in the 2020 Q3 report, we have automated the reporting for all three lines of businesses and further refined the criteria for EC and LC tags to include in the quarterly updates. As a result, some variances may be observed between the 2020 Q2 and 2020 Q3 data.
6 Prior to further refining the criteria for the 2020 Q3 report, there were a number of tags included in the 2020 Q2 update, that are excluded in the 2020 Q3 report, such as tags created prior to 2019 or tags for removed equipment.
7 Starting in 2020 Q3, there are some WSIP Non-HFTD tags from the prior updates that are categorized under non-HFTD tags.
8 PG&E has an ongoing effort to realign Electric Distribution GIS structures in Tiers 2 and 3 HFTD areas to their correct geographic location. This process uses high-accuracy LiDAR data and aerial imagery to spatially adjust structures and their associated attached equipment, to their real-world locations. This process can result in specific assets moving into or out of a HFTD.
9 The WSIP substation tags reported in 2020 Q4 inadvertently excluded certain tags that qualified as WSIP tags. PG&E has made the correction in its 2021 Q1 report.
Asset Type | Tag Type | Inspection Source |  | 2019 Q4 Update (19Q4) (data as of 10/31/19) | 2020 Q1 (20Q1) (date as of 2/5/2020) | 2020 Q2 (20Q2) (data as of 6/8/2020) | 2020 Q3 (20Q3) (data as of 9/30/2020) | 2020 Q4 (20Q4) (data as of 12/31/2020) | 2021 Q1 (21Q4) (data as of 3/31/2021) | 2021 Q2 (21Q2) (data as of 6/30/2021) | 2021 Q3 (21Q3) (data as of 9/30/2021) | 2021 Q4 (21Q4) (data as of 12/31/2021)
Electric Distribution 4 | EC | HFTD | WSIP 1,3 | 189,305 | 189,305 | 225,928 | 208,510 | 207,010 | 206,284 | 205,229​ | 204,489 | 204,279
 |  |  | Non-WSIP | 60,043 | 69,041 | 42,926 | 84,949 | 99,970 | 105,637 | 167,889​ | 185,962 | 191,050
 |  | Non-HFTD / Non-WSIP 2 |  |  | 123,349 | 98,377 | 132,731 | 211,737 | 224,558 | 257,285​ | 318,678 | 366,123
 |  | Subtotal |  | 249,348 | 381,695 | 367,231 | 426,190 | 518,717 | 536,479 | 630,403​ | 709,129 | 761,452
Electric Transmission | LC | HFTD | WSIP 5 | 100,878 | 101,584 | 101,584 | 52,573 | 52,577 | 52,589 | 52,591​ | 52,596 | 52,612
 |  |  | Non-WSIP | 4,619 | 5,355 | 14,088 | 19,489 | 21,285 | 22,778 | 37,186​ | 41,383 | 41,999
 |  | Non-HFTD / Non-WSIP 2 |  |  | 13,761 | 18,167 | 45,375 | 57,605 | 59,588 | 72,053​ | 86,592 | 97,065
 |  | Subtotal |  | 105,497 | 120,700 | 133,839 | 117,437 | 131,467 | 134,955 | 161,830​ | 180,571 | 191,676
Electric Substation 7 | LC | HFTD | WSIP | 3,144 | 3,150 | 3,157 | 3,057 | 3,057 | 3,659 | 3,663​ | 3,663 | 3,663
 |  |  | Non-WSIP | 3,132 | 3,531 | 3,960 | 5,311 | 5,920 | 5,850 | 8,788​ | 9,346 | 9,836
 |  | Non-HFTD / Non-WSIP 2 |  |  | 5987 | 7,882 | 11,415 | 14,807 | 16,477 | 18,845​ | 20,769 | 23,163
 |  | Subtotal |  | 6,276 | 12,668 | 14,999 | 19,783 | 23,784 | 25,986 | 31,296​ | 33,778 | 36,662
Grand Total |  | WSIP |  | 293,327 | 294,039 | 330,669 | 264,140 | 262,644 | 262,532 | 230,690​ | 260,748 | 260,554
 |  | Non-WSIP |  | 67,794 | 77,927 | 60,974 | 109,749 | 127,175 | 134,265 | 212,231​ | 236,691 | 242,885
 |  | Non-HFTD / Non-WSIP |  |  | 143,097 | 124,426 | 189,521 | 284,149 | 300,623 | 338,478​ | 426,039 | 486,351
 |  | Total |  | 361,121 | 515,063 | 516,069 | 563,410 | 673,968 | 697,420 | 823,529​ | 923,478 | 989,790

## Slide 4: Compliance Plan Quarterly Update – Q4 2021 Table 3: Summary of Inspection Results
Table 3 summarizes the total tags created since January 1, 2019, by quarterly update and by priority.
10 For distribution tags, PG&E's 2020 Q1 update included all Emergency A tags associated with Emergency/Restoration program for Distribution tags. Starting with the Q2 update, PG&E only includes inspection related A-tags associated with Overhead (OH) Expense and Overhead (OH )Capital.
11 Priority H tags in the 2019 Q4 Update were reported as either E or F
Asset Type | Inspection Source 8 |  | 2021 Q3 Update (21 Q3) (data as of 09/30/2021) |  |  |  |  |  | 2021 Q4 Update (21 Q4) (data as of 12/31/2021) |  |  |  |  | 
 |  |  | A10 | B | E | F | H11 | Subtotal | A10 | B | E | F | H11 | Subtotal
Electric Distribution 3 | HFTD | WSIP 1 | 996 | 9,305 | 173,236 | 9,982 | 10,970 | 204,489 | 995 | 9,452 | 172,721 | 9,918 | 11,193 | 204,279
 |  | Non-WSIP | 12,551 | 24,538 | 118,278 | 29,535 | 1,060 | 185,962 | 13,595 | 25,451 | 120,618 | 30,057 | 1,329 | 191,050
 | Non-HFTD / Non-WSIP |  | 39,790 | 36,839 | 178,684 | 63,316 | 49 | 318,678 | 43,613 | 41,481 | 205,516 | 75,447 | 66 | 366,123
 | Subtotal |  | 53,337 | 70,682 | 470,198 | 102,833 | 12,079 | 709,129 | 58,203 | 76,384 | 498,855 | 115,422 | 12,588 | 761,452
Electric Transmission | HFTD | WSIP 4 | 69 | 4,350 | 42,920 | 5,257 | 0 | 52,596 | 69 | 4,352 | 42,933 | 5,258 | - | 52,612
 |  | Non-WSIP | 740 | 4,167 | 22,368 | 14,108 | 0 | 41,383 | 830 | 4,193 | 22,697 | 14,279 | - | 41,999
 | Non-HFTD / Non-WSIP 7 |  | 1,552 | 11,310 | 49,192 | 24,538 | 0 | 86,592 | 1,653 | 13,104 | 54,730 | 27,578 | - | 97,065
 | Subtotal |  | 2,361 | 19,827 | 114,480 | 43,903 | 0 | 180,571 | 2,552 | 21,649 | 120,360 | 47,115 | - | 191,676
Electric Substation 6 | HFTD | WSIP 9 | 107 | 728 | 2,828 | 0 | 0 | 3,663 | 107 | 728 | 2,828 | - | - | 3,663
 |  | Non-WSIP | 522 | 1,910 | 6,765 | 149 | 0 | 9,346 | 546 | 2,021 | 7,095 | 174 | - | 9,836
 | Non-HFTD / Non-WSIP |  | 1,585 | 5,886 | 13,121 | 177 | 0 | 20,769 | 1,690 | 6,583 | 14,658 | 232 | - | 23,163
 | Subtotal |  | 2,214 | 8,524 | 22,714 | 326 | 0 | 33,778 | 2,343 | 9,332 | 24,581 | 406 | - | 36,662
Grand Total | HFTD | WSIP | 1,172 | 14,383 | 218,984 | 15,239 | 10,970 | 260,748 | 1,171 | 14,532 | 218,482 | 15,176 | 11,193 | 260,554
 |  | Non-WSIP | 13,813 | 30,615 | 147,411 | 43,792 | 1,060 | 236,691 | 14,971 | 31,665 | 150,410 | 44,510 | 1,329 | 242,885
 | Non-HFTD / Non-WSIP |  | 42,927 | 54,035 | 240,997 | 88,031 | 49 | 426,039 | 46,956 | 61,168 | 274,904 | 103,257 | 66 | 486,351
 | Total |  | 57,912 | 99,033 | 607,392 | 147,062 | 12,079 | 923,478 | 63,098 | 107,365 | 643,796 | 162,943 | 12,588 | 989,790

## Slide 5: Compliance Plan Quarterly Update – Q4 2021 Table 4: Summary of Open Tags
Table 4 summarizes open tags by tag priority that have not yet been addressed as of December 31, 2021.
12 Closed tags include cancelled, deleted, or tags moved out of scope, in addition to physically completed work; reflects new tags closed since January 1, 2019.
13 Created Tags reflects the summation of tags open and closed since January 1, 2019, consistent with prior quarterly reports, and not does reflect open tags created prior to 2019.
14 All B tags initially identified through the WSIP were completed by year 2020; open WSIP B tags reflected below are tags that have had their priority upgraded since the tags were created.
Asset Type | Inspection Source 8 |  | Total Created Tags (21Q4)1, 13 (carry-forward from Table 3) |  |  |  |  |  | Tags Closed (C) 12 (data as of 12/31/21) |  |  |  |  |  | Total Open Tags (O = 21Q4-C)2 (data as of 12/31/21) |  |  |  |  | 
 |  |  | A10 | B | E | F | H11 | Sub-total | A10 | B | E | F | H11 | Sub-total | A10 | B 14 | E | F | H11 | Sub-total
Electric Distribution | HFTD | WISP | 995 | 9,452 | 172,721 | 9,918 | 11,193 | 204,279 | 995 | 8,947 | 118,936 | 6,917 | 4,571 | 140,366 | - | 505 | 53,785 | 3,001 | 6,622 | 63,913
 |  | Non-WISP | 13,595 | 25,451 | 120,618 | 30,057 | 1,329 | 191,050 | 13,527 | 24,358 | 28,643 | 4,478 | 189 | 71,195 | 68 | 1,129 | 92,692 | 40,062 | 1,892 | 135,843
 | Non-HFTD / Non-WSIP |  | 43,613 | 41,481 | 205,516 | 75,447 | 66 | 366,123 | 43,533 | 38,257 | 37,231 | 5,203 | 6 | 124,230 | 80 | 3,359 | 169,215 | 135,415 | 79 | 308,148
 | Subtotal |  | 58,203 | 76,384 | 498,855 | 115,422 | 12,588 | 761,452 | 58,055 | 71,562 | 184,810 | 16,598 | 4,766 | 335,791 | 148 | 4,993 | 315,692 | 178,478 | 8,593 | 507,904
Electric Transmission | HFTD | WISP | 69 | 4,352 | 42,933 | 5,258 | - | 52,612 | 69 | 4,350 | 41,709 | 4,184 | - | 50,312 | - | 2 | 1,224 | 1,074 | - | 2,300
 |  | Non-WISP | 829 | 4,193 | 22,697 | 14,279 | - | 41,998 | 766 | 4,159 | 12,821 | 6,100 | - | 23,846 | 64 | 35 | 10,098 | 8,199 | - | 18,396
 | Non-HFTD / Non-WSIP |  | 1,653 | 13,103 | 54,730 | 27,578 | - | 97,064 | 1,650 | 12,362 | 20,336 | 8,386 | - | 42,734 | 3 | 745 | 34,520 | 19,247 | - | 54,515
 | Subtotal |  | 2,551 | 21,648 | 120,360 | 47,115 | - | 191,674 | 2,485 | 20,871 | 74,866 | 18,670 | - | 116,892 | 67 | 782 | 45,842 | 28,520 | - | 75,211
Electric Substation | HFTD | WISP | 107 | 728 | 2,828 | - | - | 3,663 | 107 | 728 | 2,801 | - | - | 3,636 | - | - | 27 | - | - | 27
 |  | Non-WISP | 546 | 2,021 | 7,095 | 174 | - | 9,836 | 546 | 1,986 | 5,674 | 37 | - | 8,243 | - | 35 | 1,422 | 147 | - | 1,604
 | Non-HFTD / Non-WSIP |  | 1,690 | 6,583 | 14,658 | 232 | - | 23,163 | 1,690 | 6,389 | 12,754 | 101 | - | 20,934 | - | 194 | 1,911 | 145 | - | 2,250
 | Subtotal |  | 2,343 | 9,332 | 24,581 | 406 | - | 36,662 | 2,343 | 9,103 | 21,229 | 138 | - | 32,813 | - | 229 | 3,360 | 292 | - | 3,881
Grand Total | HFTD | WISP | 1,171 | 14,532 | 218,482 | 15,176 | 11,193 | 260,554 | 1,171 | 14,025 | 163,446 | 11,101 | 4,571 | 194,314 | - | 507 | 55,036 | 4,075 | 6,622 | 66,240
 |  | Non-WISP | 14,970 | 31,665 | 150,410 | 44,510 | 1,329 | 242,884 | 14,839 | 30,503 | 47,138 | 10,615 | 189 | 103,284 | 132 | 1,199 | 104,212 | 48,408 | 1,892 | 155,843
 | Non-HFTD / Non-WSIP |  | 46,956 | 61,167 | 274,904 | 103,257 | 66 | 486,350 | 46,873 | 57,008 | 70,321 | 13,690 | 6 | 187,898 | 83 | 4,298 | 205,646 | 154,807 | 79 | 364,913
 | Subtotal |  | 63,097 | 107,364 | 643,796 | 162,943 | 12,588 | 989,788 | 62,883 | 101,536 | 280,905 | 35,406 | 4,766 | 485,496 | 215 | 6,004 | 364,894 | 207,290 | 8,593 | 586,996

## Slide 6
Appendix

## Slide 7: Glossary
Acronym | Term | Description
WSIP | Wildfire Safety Inspection Program | As part of PG&E’s Wildfire Safety Plan (“WSP”), PG&E created and launched the 2018/2019 Wildfire Safety Inspection Program (WSIP) to perform accelerated and enhanced inspections of its electric distribution, transmission and substation facilities with the objective of identifying and repairing non-conformances on its facilities that pose a safety and/or reliability risk.
HFTD | High Fire-Threat District | The High Fire-Threat District Map was adopted by the CPUC in January 2018 and consists of three designations of high fire risk: Tier 3 is extreme risk (including likelihood and potential impacts of occurrence) from wildfires associated with overhead utility powerlines or overhead utility powerlines also supporting communication facilities, including impacts to people or improved property. Tier 2 is elevated risk (including likelihood and potential impacts of occurrence) from wildfires associated with overhead utility powerlines or overhead utility powerlines also supporting communication facilities, including impacts to people or improved property. Zone 1 is Tree Mortality High Hazard Zones as determined by the California Department of Forestry and Fire Protection (CAL FIRE) and the U.S. Forest Service (USFS).
EC | Electric Corrective | Electric Corrective (“EC”) refers distribution tags.
LC | Line Corrective | Line Corrective (“LC”) refers to transmission and substation tags.
- | Staging Notifications | A staging notification is the initial input from the field inspector that has not yet been reviewed and validated by the Gatekeeper to turn into an EC or LC tag. Staging notifications are referred to as “S5” notifications for Transmission, “S9” notifications for Distribution, and “S7” notifications for Substations.
- | Can’t Get Ins | "Can’t Get Ins" (CGIs) are EC notifications that PG&E uses to create work orders to request support, enabling inspectors access to complete their inspection. These notifications are not considered repair tags.
GO | General Order | EC and LC tags are created using PG&E’s programs adopted to comply with CPUC General Orders ("GOs”) 95,165,174. For more information about CPUC’s general orders, visit their website at https://www.cpuc.ca.gov/gos/index.html
- | Buffer Zone | Areas that are not in the High Fire-Threat District (HFTD) but are adjacent to an HFTD area.
- | Safety Reassessment | Distribution: PG&E will perform annual safety re-assessments of tags to field-verify that the non-conformance poses no immediate risk to safety or reliability, although the tag is in excess of its compliance date. Transmission: For higher risk (time-dependent) tags in excess of their compliance dates, PG&E will follow the same methodology used for Distribution tags. However, additional reassessment will be performed, additional steps such as de-energization may be taken, and additional factors will be applied in re-prioritizing work based on the field re-assessment. Substations: For S-WSIP identified EC/LC tags with potential to exceed their compliance dates due to factors beyond our control such as clearance, permitting reviews or materials availability, PG&E will review the condition of the non-conformance during the routine monthly or bi-monthly inspections to ensure that it poses no additional risk to safety or reliability. If the condition deteriorates, a new due date based on the current conditions will be established.