## 2025 WMP Target Risk
WMP Initiative | 2023 - 2025 WMP Commitment Name | WMP Expected Risk Reduction( As Listed in WMP R8) | Actual Risk Reduction Achieved | Explanation and Actions taken
AI-02 | Detailed Inspection Transmission – Ground | TBD | 23.36% (Eyes-on-Risk) | N/A
AI-04 | Detailed Inspection Transmission – Aerial | TBD | 30.68% (Eyes-on-Risk) | N/A
AI-05 | Detailed Inspection Transmission – Climbing | TBD | 1.77% (Eyes-on-Risk) | N/A
AI-06 | Perform transmission infrared inspections | TBD | 63.95% (Eyes-on-Risk) | N/A
AI-07 | Detailed Ground Inspections - Distribution | 45% (Eyes-on-Risk) | 33.54% (Eyes-on-Risk) | We achieved 33.54% Eyes-on-Risk (EOR) in 2025, versus the annual WMP projected target of 45%. This is because the work plan for the three-year WMP was front loaded with higher risk assets in 2023 and 2024. Despite the lower EOR in 2025, we successfully met the overall intent of the commitment by averaging 48% Eyes on Risk across the three-year 2023-2025 period, exceeding the 44% three-year average Eyes on Risk target established in the 2023-2025 WMP.
AI-08 | Supplemental Inspections - Substation Distribution | TBD | 68% (Eyes-on-Risk) | N/A
AI-09 | Supplemental Inspections - Substation Transmission | TBD | 22% (Eyes-on-Risk) | N/A
AI-10 | Supplemental Inspections - Hydroelectric Substations and Powerhouses | TBD | 10% (Eyes-on-Risk) | N/A
CO-02 | Community Engagement - Surveys | N/A | N/A | N/A
EP-06 | Annually review of the Company Emergency Response Plan (CERP) and Wildfire and PSPS Annex | N/A | N/A | N/A
GH-01 | System Hardening - Distribution | 4.7% | 5.31% | N/A
GH-04 | 10K Undergrounding | 3.5% | 3.8% | N/A
GH-05 | System Hardening – Transmission | <1% | <1% | N/A
GH-06 | System Hardening - Transmission Shunt Splices | TBD | 0.01% | N/A
GH-10 | Non-Exempt Expulsion Fuse - Removal | <1% | 0.27% | N/A
GH-11 | System Hardening – Transmission Conductor Segment Replacement | <1% | <1% | N/A
GM-01 | Asset Inspections - Quality Assurance | N/A | N/A | N/A
GM-03 | HFTD-HFRA Open Tag Reduction – Distribution Backlog | <1% | 0.38% | N/A
GM-06 | EPSS - Down Conductor Detection (DCD) | <1% | 0.79% | N/A
GM-09 | Asset Inspection – Quality Control | N/A | N/A | N/A
PS-06 | Provide 12,000 cumulative new or replacement portable batteries to PG&E customers at risk of PSPS or EPSS, focusing on but not limited to AFN, MBL, and self-identified vulnerable populations | N/A | N/A | N/A
PS-07 | Reduce PSPS impacts by ~38k customer events (2.4%) for 2023-2025 period by completing planned Wildfire mitigation projects including but not limited to MSO switch replacements and undergrounding | N/A | N/A | N/A
SA-02 | Line Sensor - Installations | TBD | 4.34% (Eyes-on-Risk) | N/A
SA-10 | Distribution Fault Anticipation (DFA) Installations | 5.1% (Eyes-on-Risk) | 6.17% (Eyes-on-Risk) | N/A
SA-11 | Early Fault Detection (EFD) Installations | 2.8% (Eyes-on-Risk) | 3.11% (Eyes-on-Risk) | N/A
VM-01 | LiDAR Data Collection - Transmission | N/A | N/A | N/A
VM-02 | Pole Clearing Program | <1% | 0.11% | N/A
VM-03 | Focused Tree Inspection (FTI) | <1% | 0.11% | N/A
VM-04 | Tree Removal Inventory (TRI) | <1% | 1.81% | N/A
VM-05 | Defensible Space Inspections - Distribution Substation | 53% (Eyes-on-Risk) | 53.50% (Eyes-on-Risk) | N/A
VM-06 | Defensible Space Inspections - Transmission Substation | 22% (Eyes-on-Risk) | 22.63% (Eyes-on-Risk) | N/A
VM-07 | Defensible Space Inspections - Hydroelectric Substations and Powerhouses | 25% (Eyes-on-Risk) | 23.87% (Eyes-on-Risk) | The expected risk reduction was not achieved, as two powerhouses were removed from scope due to divestures (transfer of ownership) and two powerhouses that are indefinitely shutdown and disconnected from the grid. One generating station was added due to HFRA boundary change. Please note that, out of an abundance of caution, we completed defensible space inspection at the two decommissioned locations because distribution service still existed at these locations. However, given that there are no longer any active high or medium voltage assets at these locations, we are not counting these inspections toward our target. This work was merely precautionary in measure.
VM-08 | Vegetation Management – Quality Assurance | N/A | N/A | N/A
VM-13 | Routine Ground - Transmission | 100% (Eyes-on-Risk) PG&E system | 100% (Eyes-on-Risk) | N/A
VM-14 | Transmission Second Patrol | 100% (Eyes-on-Risk) HFTD / HFRA | 100% (Eyes-on-Risk) | N/A
VM-15 | Integrated Vegetation Management - Transmission | TBD | 0.008% | N/A
VM-16 | Distribution Routine Patrol | <1% | 0.6% | N/A
VM-17 | Distribution Second Patrol | <1% | 0.55% | N/A
VM-18 | VM for Operational Mitigations (VMOM) | TBD | 0.05% | N/A
VM-22 | Vegetation Management - Quality Control | N/A | N/A | N/A