## table_6_4
Line No. | Circuit Segment Name | Initial Overall Utility Risk | 2026 Activities | 2026 Overall Utility Risk | 2027 Activities | 2027 Overall Utility Risk | 2028 Activities | 2028 Overall Utility Risk
1 | CLAYTON 2212681608 | 99.7013 | Line removal Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 41.8763 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 38.7737 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 35.6712
2 | BALCH NO 1 1101105414 | 91.5229 | Overhead hardening Pole clearing Vegetation routine patrol Vegetation hazard patrol | 68.6521 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 68.5629 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 68.4737
3 | CLOVERDALE 1102672 | 80.9024 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 79.0821 | Line removal Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 0.33416 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 0.33416
4 | PLACERVILLE 21067522 | 72.8321 | Line removal Pole clearing Vegetation routine patrol Vegetation hazard patrol | 69.7054 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 67.2946 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 64.8837
5 | PLACERVILLE 210611132 | 67.324 | Line removal Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 29.772 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 29.0437 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 28.3153
6 | MIDDLETOWN 1101644756 | 66.8951 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 65.1651 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 63.4351 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 61.7051
7 | STANISLAUS 1701CB | 64.2834 | Overhead hardening Pole clearing Vegetation routine patrol Vegetation hazard patrol | 55.2868 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 51.7395 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 26.4214
8 | EL DORADO PH 210119752 | 61.3359 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 59.5211 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 57.7062 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 28.886
9 | CALPINE 1144CB | 60.6956 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 60.6838 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 60.6721 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 60.6604
10 | ALLEGHANY 1102CB | 60.0599 | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 52.7153 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 2.46 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 1.7004
11 | MARIPOSA 210237282 | 59.3946 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 57.4002 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 55.4057 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 53.4112
12 | BIG BEND 1101CB | 57.5444 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 56.7199 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 55.8954 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 55.0708
13 | WEST POINT 11024788 | 57.4156 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 55.6302 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 53.8448 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 52.0594
14 | CALAVERAS CEMENT 1101544800 | 57.3184 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 56.2128 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 35.9639 | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 5.4244
15 | CALAVERAS CEMENT 1101502 | 56.1338 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 56.0581 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 55.9823 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 55.9065
16 | CORNING 110185152 | 54.4345 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 53.6284 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 52.8222 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 52.0161
17 | CURTIS 17048140 | 54.0429 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 52.3102 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 50.5776 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 48.8449
18 | COLUMBIA HILL 1101CB | 53.4681 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 51.6536 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 49.8391 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 48.0246
19 | TEMPLETON 2113A12 | 53.4192 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 52.0023 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 50.5853 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 49.1683
20 | FORT ROSS 112170288 | 52.9255 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 50.6604 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 3.8524 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 1.5873
21 | BIG BEND 1101641808 | 52.57 | Line removal Pole clearing Vegetation routine patrol Vegetation hazard patrol | 48.6755 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 47.7238 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 46.7722
22 | MARIPOSA 2101752630 | 51.4021 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 50.5266 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 18.3255 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 17.4501
23 | SILVERADO 2104633600 | 50.5596 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 49.9464 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 49.3333 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 21.3377
24 | VACAVILLE 110838316 | 49.3106 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 48.4254 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 47.5402 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 46.655
25 | APPLE HILL 110497086 | 49.1966 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 47.4369 | Overhead hardening Pole clearing Vegetation routine patrol Vegetation hazard patrol | 39.8229 | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 7.3169
26 | APPLE HILL 21029722 | 48.5389 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 47.9649 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 47.3909 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 46.8169
27 | MIDDLETOWN 1101548 | 48.4984 | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 41.0289 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 25.448 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 4.682
28 | PINE GROVE 11026080 | 48.1154 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 48.0867 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 48.058 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 48.0294
29 | HIGHLANDS 1102628 | 46.8557 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 36.2144 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 24.9875 | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 6.63
30 | PLACERVILLE 21069712 | 46.2948 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 45.8968 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 45.4987 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 10.621
31 | HARTLEY 1101698 | 46.1802 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 44.8476 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 29.6301 | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 21.4281
32 | PUEBLO 2103678 | 45.963 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 44.3434 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 4.1542 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 2.5347
33 | MARTELL 110191216 | 45.6481 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 43.8524 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 42.0566 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 40.2609
34 | REDBUD 1101323962 | 45.5277 | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 43.4014 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 42.8733 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 42.3452
35 | MOLINO 1102318 | 45.412 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 43.4677 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 41.5233 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 39.5789
36 | HIGHLANDS 1103520 | 44.295 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 42.9457 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 41.5965 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 40.2472
37 | COARSEGOLD 210410110 | 43.9578 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 42.5033 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 41.0488 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 39.5944
38 | AUBERRY 1101R2578 | 43.6409 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 33.7404 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 32.3142 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 30.8881
39 | MARIPOSA 210237288 | 43.5691 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 41.9851 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 40.4011 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 38.8171
40 | FROGTOWN 170113412 | 43.5543 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 42.3725 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 41.1908 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 40.0091
41 | ELECTRA 1101CB | 43.215 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 42.3309 | Overhead hardening Pole clearing Vegetation routine patrol Vegetation hazard patrol | 25.4358 | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 15.5761
42 | CORNING 11021622 | 42.7053 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 42.242 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 41.7787 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 41.3154
43 | DIAMOND SPRINGS 110676088 | 42.3199 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 41.2933 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 40.2666 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 39.2399
44 | BONNIE NOOK 1102CB | 41.8552 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 40.5429 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 7.7742 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 6.4619
45 | BRUNSWICK 11021010 | 41.6777 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 41.2205 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 40.7632 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 40.306
46 | CURTIS 170390320 | 41.0182 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 40.2806 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 39.5429 | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 12.9646
47 | MARIPOSA 210110070 | 40.9066 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 39.5391 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 33.9409 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 13.5366
48 | GIRVAN 11011330 | 40.5343 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 39.323 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 38.1116 | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 11.4485
49 | APPLE HILL 110413512 | 40.3039 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 39.1676 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 38.0312 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 36.8948
50 | DIAMOND SPRINGS 11057722 | 40.1837 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 38.8571 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 37.5305 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 36.2039
51 | BALCH NO 1 1101406582 | 40.1094 | Overhead hardening Pole clearing Vegetation routine patrol Vegetation hazard patrol | 18.4775 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 18.4363 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 18.3951
52 | MOUNTAIN QUARRIES 21011130 | 39.6503 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 39.6096 | Overhead hardening Pole clearing Vegetation routine patrol Vegetation hazard patrol | 25.2491 | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 16.7108
53 | APPLE HILL 2102836878 | 39.4699 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 38.5094 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 37.5488 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 36.5883
54 | COALINGA NO 2 11059260 | 39.3637 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 39.353 | Line removal Pole clearing Vegetation routine patrol Vegetation hazard patrol | 31.0302 | Line removal Pole clearing Vegetation routine patrol Vegetation hazard patrol | 13.5297
55 | LAYTONVILLE 1101518 | 38.8951 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 37.689 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 36.483 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 17.4875
56 | APPLE HILL 21028372 | 38.7665 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 38.0332 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 37.3 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 36.5667
57 | LOS OSITOS 21037014 | 38.7165 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 38.7011 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 38.6856 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 38.6701
58 | STILLWATER 11021466 | 38.3929 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 37.2395 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 36.0861 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 6.814
59 | PIT NO 3 21011482 | 37.308 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 36.9761 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 4.6965 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 4.3647
60 | GEYSERVILLE 1102904170 | 36.9939 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 36.4337 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 35.8736 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 16.069
61 | FORESTHILL 11011802 | 36.4406 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 35.2727 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 7.8442 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 6.6763
62 | FITCH MOUNTAIN 111324918 | 36.4262 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 34.9169 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 33.4077 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 31.8984
63 | MARIPOSA 2101439030 | 36.0716 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 35.1724 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 34.2731 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 33.3739
64 | CLAYTON 221296224 | 35.9806 | Line removal Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 22.818 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 18.329 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 17.769
65 | PEORIA 170190090 | 35.8543 | Overhead hardening Pole clearing Vegetation routine patrol Vegetation hazard patrol | 34.1478 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 33.6493 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 33.1508
66 | HOPLAND 11014626 | 35.6066 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 34.4019 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 33.1972 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 31.9925
67 | SILVERADO 2104632 | 35.5808 | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 19.5847 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 18.3347 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 17.0846
68 | PLACERVILLE 2106935216 | 35.4512 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 2.8418 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 1.7385 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 0.63519
69 | APPLE HILL 2102186912 | 34.9302 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 34.2345 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 33.5388 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 32.843
70 | SHADY GLEN 1101941844 | 34.5974 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 34.2285 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 33.8595 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 12.1228
71 | PINE GROVE 1102269286 | 34.1506 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 33.2106 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 32.2705 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 31.3305
72 | ORO FINO 110239154 | 34.0841 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 32.9732 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 31.8623 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 30.7514
73 | WEST POINT 110234416 | 33.9065 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 32.7425 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 31.5785 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 30.4144
74 | CEDAR CREEK 1101CB | 33.7551 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 32.7622 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 31.7693 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 30.7764
75 | SISQUOC 1102M52 | 33.4088 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 32.538 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 31.6672 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 30.7964
76 | TEMPLETON 2113641367 | 33.3923 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 32.7985 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 32.2047 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 31.611
77 | MARIPOSA 21019400 | 33.2984 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 32.2279 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 30.4347 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 29.3642
78 | FORESTHILL 1102359542 | 32.7979 | Line removal Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 5.2569 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 4.1556 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 3.0543
79 | CALAVERAS CEMENT 11011419 | 32.6283 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 32.5975 | Overhead hardening Pole clearing Vegetation routine patrol Vegetation hazard patrol | 31.7277 | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 5.0503
80 | BRUNSWICK 110651486 | 32.0751 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 30.9165 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 29.7579 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 28.5993
81 | SHINGLE SPRINGS 210913322 | 32.0191 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 30.9298 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 29.8405 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 28.7512
82 | PINE GROVE 11013170 | 32.0008 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 31.8842 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 31.7676 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 31.6511
83 | WEST POINT 110236676 | 31.795 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 30.7237 | Overhead hardening Pole clearing Vegetation routine patrol Vegetation hazard patrol | 25.7849 | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 5.0155
84 | APPLE HILL 21021532 | 31.4372 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 30.8737 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 30.3103 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 29.7468
85 | CALAVERAS CEMENT 110147968 | 30.7825 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 30.7253 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 30.6682 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 5.2033
86 | WILDWOOD 1101384582 | 30.7606 | EPSS Vegetation routine patrol Vegetation hazard patrol | 30.7606 | EPSS Vegetation routine patrol Vegetation hazard patrol | 30.7606 | EPSS Vegetation routine patrol Vegetation hazard patrol | 30.7606
87 | SANTA YNEZ 1102320270 | 30.7321 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 29.9348 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 29.1375 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 15.9573
88 | FRENCH GULCH 11022902 | 30.5736 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 30.5008 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 14.5884 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 14.5155
89 | STANISLAUS 17011812 | 30.5553 | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 17.3433 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 10.2072 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | 0.094365
90 | PERRY 110179696 | 30.4315 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 29.3311 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 28.2307 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | 27.1303

## Sheet2 (hidden)
Line No. | Circuit Segment Name | Initial Overall Utility Risk | 2026 Activities | 2026 Overall Utility Risk | 2027 Activities | 2027 Overall Utility Risk | 2028 Activities | 2028 Overall Utility Risk |  | Jan. 1, 2026 Overall Risk
1 | CLAYTON 2212681608 | 99.7013 | Line removal Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
2 | BALCH NO 1 1101105414 | 91.5229 | Overhead hardening Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
3 | CLOVERDALE 1102672 | 80.9024 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Line removal Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
4 | PLACERVILLE 21067522 | 72.8321 | Line removal Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
5 | PLACERVILLE 210611132 | 67.324 | Line removal Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
6 | MIDDLETOWN 1101644756 | 66.8951 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
7 | STANISLAUS 1701CB | 64.2834 | Overhead hardening Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
8 | EL DORADO PH 210119752 | 61.3359 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
9 | CALPINE 1144CB | 60.6956 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
10 | ALLEGHANY 1102CB | 60.0599 | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
11 | MARIPOSA 210237282 | 59.3946 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
12 | BIG BEND 1101CB | 57.5444 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
13 | WEST POINT 11024788 | 57.4156 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
14 | CALAVERAS CEMENT 1101544800 | 57.3184 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
15 | CALAVERAS CEMENT 1101502 | 56.1338 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
16 | CORNING 110185152 | 54.4345 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
17 | CURTIS 17048140 | 54.0429 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
18 | COLUMBIA HILL 1101CB | 53.4681 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
19 | TEMPLETON 2113A12 | 53.4192 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
20 | FORT ROSS 112170288 | 52.9255 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
21 | BIG BEND 1101641808 | 52.57 | Line removal Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
22 | MARIPOSA 2101752630 | 51.4021 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
23 | SILVERADO 2104633600 | 50.5596 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
24 | VACAVILLE 110838316 | 49.3106 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
25 | APPLE HILL 110497086 | 49.1966 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
26 | APPLE HILL 21029722 | 48.5389 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
27 | MIDDLETOWN 1101548 | 48.4984 | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
28 | PINE GROVE 11026080 | 48.1154 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
29 | HIGHLANDS 1102628 | 46.8557 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
30 | PLACERVILLE 21069712 | 46.2948 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
31 | HARTLEY 1101698 | 46.1802 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
32 | PUEBLO 2103678 | 45.963 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
33 | MARTELL 110191216 | 45.6481 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
34 | REDBUD 1101323962 | 45.5277 | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
35 | MOLINO 1102318 | 45.412 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
36 | HIGHLANDS 1103520 | 44.295 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
37 | COARSEGOLD 210410110 | 43.9578 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
38 | AUBERRY 1101R2578 | 43.6409 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
39 | MARIPOSA 210237288 | 43.5691 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
40 | FROGTOWN 170113412 | 43.5543 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
41 | ELECTRA 1101CB | 43.215 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
42 | CORNING 11021622 | 42.7053 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
43 | DIAMOND SPRINGS 110676088 | 42.3199 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
44 | BONNIE NOOK 1102CB | 41.8552 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
45 | BRUNSWICK 11021010 | 41.6777 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
46 | CURTIS 170390320 | 41.0182 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
47 | MARIPOSA 210110070 | 40.9066 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
48 | GIRVAN 11011330 | 40.5343 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
49 | APPLE HILL 110413512 | 40.3039 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
50 | DIAMOND SPRINGS 11057722 | 40.1837 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
51 | BALCH NO 1 1101406582 | 40.1094 | Overhead hardening Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
52 | MOUNTAIN QUARRIES 21011130 | 39.6503 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
53 | APPLE HILL 2102836878 | 39.4699 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
54 | COALINGA NO 2 11059260 | 39.3637 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Line removal Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Line removal Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
55 | LAYTONVILLE 1101518 | 38.8951 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
56 | APPLE HILL 21028372 | 38.7665 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
57 | LOS OSITOS 21037014 | 38.7165 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
58 | STILLWATER 11021466 | 38.3929 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
59 | PIT NO 3 21011482 | 37.308 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
60 | GEYSERVILLE 1102904170 | 36.9939 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
61 | FORESTHILL 11011802 | 36.4406 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
62 | FITCH MOUNTAIN 111324918 | 36.4262 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
63 | MARIPOSA 2101439030 | 36.0716 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
64 | CLAYTON 221296224 | 35.9806 | Line removal Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
65 | PEORIA 170190090 | 35.8543 | Overhead hardening Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
66 | HOPLAND 11014626 | 35.6066 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
67 | SILVERADO 2104632 | 35.5808 | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
68 | PLACERVILLE 2106935216 | 35.4512 | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
69 | APPLE HILL 2102186912 | 34.9302 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
70 | SHADY GLEN 1101941844 | 34.5974 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
71 | PINE GROVE 1102269286 | 34.1506 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
72 | ORO FINO 110239154 | 34.0841 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
73 | WEST POINT 110234416 | 33.9065 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
74 | CEDAR CREEK 1101CB | 33.7551 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
75 | SISQUOC 1102M52 | 33.4088 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
76 | TEMPLETON 2113641367 | 33.3923 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
77 | MARIPOSA 21019400 | 33.2984 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
78 | FORESTHILL 1102359542 | 32.7979 | Line removal Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
79 | CALAVERAS CEMENT 11011419 | 32.6283 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
80 | BRUNSWICK 110651486 | 32.0751 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
81 | SHINGLE SPRINGS 210913322 | 32.0191 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
82 | PINE GROVE 11013170 | 32.0008 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
83 | WEST POINT 110236676 | 31.795 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
84 | APPLE HILL 21021532 | 31.4372 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
85 | CALAVERAS CEMENT 110147968 | 30.7825 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
86 | WILDWOOD 1101384582 | 30.7606 | EPSS Vegetation routine patrol Vegetation hazard patrol | #REF! | EPSS Vegetation routine patrol Vegetation hazard patrol | #REF! | EPSS Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!
87 | SANTA YNEZ 1102320270 | 30.7321 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
88 | FRENCH GULCH 11022902 | 30.5736 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
89 | STANISLAUS 17011812 | 30.5553 | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! |  | #REF!
90 | PERRY 110179696 | 30.4315 | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | Pole clearing Vegetation routine patrol Vegetation hazard patrol | #REF! | x | #REF!

## data
Line_No | cs_name | percent_risk_reduced_2026 | percent_risk_reduced_2027 | percent_risk_reduced_2028 | 2026_initiative_activities | 2027_initiative_activities | 2028_initiative_activities | 2026 Activities | 2027 Activities | 2028 Activities
1 | CLAYTON 2212681608 | 0.57998 | 0.074088 | 0.080016 | Line removal, Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Line removal Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
2 | BALCH NO 1 1101105414 | 0.24989 | 0.001299 | 0.0013007 | Overhead hardening, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
3 | CLOVERDALE 1102672 | 0.0225 | 0.99577 | 0 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Line removal, Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Line removal Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
4 | PLACERVILLE 21067522 | 0.042929 | 0.034586 | 0.035825 | Line removal, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Line removal Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
5 | PLACERVILLE 210611132 | 0.55778 | 0.024465 | 0.025078 | Line removal, Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Line removal Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
6 | MIDDLETOWN 1101644756 | 0.025862 | 0.026548 | 0.027272 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
7 | STANISLAUS 1701CB | 0.13995 | 0.064161 | 0.48934 | Overhead hardening, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol
8 | EL DORADO PH 210119752 | 0.029588 | 0.03049 | 0.49943 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol
9 | CALPINE 1144CB | 0.00019354 | 0.00019357 | 0.00019361 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
10 | ALLEGHANY 1102CB | 0.12229 | 0.95333 | 0.30878 | Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
11 | MARIPOSA 210237282 | 0.03358 | 0.034747 | 0.035998 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
12 | BIG BEND 1101CB | 0.014328 | 0.014537 | 0.014751 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
13 | WEST POINT 11024788 | 0.031097 | 0.032095 | 0.033159 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
14 | CALAVERAS CEMENT 1101544800 | 0.019289 | 0.36022 | 0.84917 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol
15 | CALAVERAS CEMENT 1101502 | 0.0013498 | 0.0013516 | 0.0013534 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
16 | CORNING 110185152 | 0.014809 | 0.015032 | 0.015261 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
17 | CURTIS 17048140 | 0.032061 | 0.033123 | 0.034258 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
18 | COLUMBIA HILL 1101CB | 0.033936 | 0.035128 | 0.036407 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
19 | TEMPLETON 2113A12 | 0.026525 | 0.027248 | 0.028011 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
20 | FORT ROSS 112170288 | 0.042798 | 0.92396 | 0.58798 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
21 | BIG BEND 1101641808 | 0.074082 | 0.019551 | 0.019941 | Line removal, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Line removal Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
22 | MARIPOSA 2101752630 | 0.017031 | 0.63731 | 0.04777 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
23 | SILVERADO 2104633600 | 0.012127 | 0.012276 | 0.56748 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol
24 | VACAVILLE 110838316 | 0.017951 | 0.018279 | 0.01862 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
25 | APPLE HILL 110497086 | 0.03577 | 0.16051 | 0.81626 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Pole clearing Vegetation routine patrol Vegetation hazard patrol | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol
26 | APPLE HILL 21029722 | 0.011826 | 0.011967 | 0.012112 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
27 | MIDDLETOWN 1101548 | 0.15402 | 0.37975 | 0.81602 | Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol
28 | PINE GROVE 11026080 | 0.00059566 | 0.00059602 | 0.00059637 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
29 | HIGHLANDS 1102628 | 0.22711 | 0.31001 | 0.73467 | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol
30 | PLACERVILLE 21069712 | 0.008598 | 0.0086726 | 0.76657 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol
31 | HARTLEY 1101698 | 0.028858 | 0.33932 | 0.27681 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol
32 | PUEBLO 2103678 | 0.035236 | 0.90632 | 0.38986 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
33 | MARTELL 110191216 | 0.039339 | 0.04095 | 0.042698 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
34 | REDBUD 1101323962 | 0.046703 | 0.012168 | 0.012318 | Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
35 | MOLINO 1102318 | 0.042816 | 0.044731 | 0.046826 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
36 | HIGHLANDS 1103520 | 0.030461 | 0.031418 | 0.032437 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
37 | COARSEGOLD 210410110 | 0.033088 | 0.03422 | 0.035433 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
38 | AUBERRY 1101R2578 | 0.22686 | 0.042268 | 0.044134 | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
39 | MARIPOSA 210237288 | 0.036356 | 0.037727 | 0.039206 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
40 | FROGTOWN 170113412 | 0.027132 | 0.027889 | 0.028689 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
41 | ELECTRA 1101CB | 0.020459 | 0.39912 | 0.38763 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Pole clearing Vegetation routine patrol Vegetation hazard patrol | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol
42 | CORNING 11021622 | 0.010848 | 0.010967 | 0.011089 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
43 | DIAMOND SPRINGS 110676088 | 0.02426 | 0.024863 | 0.025497 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
44 | BONNIE NOOK 1102CB | 0.031354 | 0.80825 | 0.1688 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
45 | BRUNSWICK 11021010 | 0.010971 | 0.011093 | 0.011217 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
46 | CURTIS 170390320 | 0.017983 | 0.018313 | 0.67214 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol
47 | MARIPOSA 210110070 | 0.033431 | 0.14159 | 0.60117 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol
48 | GIRVAN 11011330 | 0.029885 | 0.030805 | 0.69961 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol
49 | APPLE HILL 110413512 | 0.028195 | 0.029013 | 0.02988 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
50 | DIAMOND SPRINGS 11057722 | 0.033014 | 0.034141 | 0.035347 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
51 | BALCH NO 1 1101406582 | 0.53932 | 0.0022302 | 0.0022352 | Overhead hardening, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
52 | MOUNTAIN QUARRIES 21011130 | 0.0010279 | 0.36255 | 0.33817 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Pole clearing Vegetation routine patrol Vegetation hazard patrol | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol
53 | APPLE HILL 2102836878 | 0.024336 | 0.024943 | 0.025581 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
54 | COALINGA NO 2 11059260 | 0.00027112 | 0.21149 | 0.56398 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Line removal, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Line removal, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Line removal Pole clearing Vegetation routine patrol Vegetation hazard patrol | Line removal Pole clearing Vegetation routine patrol Vegetation hazard patrol
55 | LAYTONVILLE 1101518 | 0.031007 | 0.032 | 0.52067 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol
56 | APPLE HILL 21028372 | 0.018915 | 0.019279 | 0.019658 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
57 | LOS OSITOS 21037014 | 0.00039978 | 0.00039994 | 0.0004001 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
58 | STILLWATER 11021466 | 0.030042 | 0.030972 | 0.81117 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol
59 | PIT NO 3 21011482 | 0.0088957 | 0.87298 | 0.070665 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
60 | GEYSERVILLE 1102904170 | 0.015141 | 0.015374 | 0.55207 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol
61 | FORESTHILL 11011802 | 0.032049 | 0.77761 | 0.14888 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
62 | FITCH MOUNTAIN 111324918 | 0.041433 | 0.043224 | 0.045177 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
63 | MARIPOSA 2101439030 | 0.02493 | 0.025567 | 0.026238 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
64 | CLAYTON 221296224 | 0.36583 | 0.19673 | 0.030551 | Line removal, Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Line removal Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
65 | PEORIA 170190090 | 0.047596 | 0.014598 | 0.014814 | Overhead hardening, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
66 | HOPLAND 11014626 | 0.033834 | 0.035019 | 0.036289 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
67 | SILVERADO 2104632 | 0.44957 | 0.063827 | 0.068179 | Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
68 | PLACERVILLE 2106935216 | 0.91984 | 0.38824 | 0.63463 | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
69 | APPLE HILL 2102186912 | 0.019918 | 0.020323 | 0.020744 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
70 | SHADY GLEN 1101941844 | 0.010665 | 0.01078 | 0.64197 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol
71 | PINE GROVE 1102269286 | 0.027526 | 0.028305 | 0.02913 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
72 | ORO FINO 110239154 | 0.032593 | 0.033691 | 0.034866 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
73 | WEST POINT 110234416 | 0.034331 | 0.035551 | 0.036862 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
74 | CEDAR CREEK 1101CB | 0.029414 | 0.030306 | 0.031253 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
75 | SISQUOC 1102M52 | 0.026065 | 0.026762 | 0.027498 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
76 | TEMPLETON 2113641367 | 0.017782 | 0.018104 | 0.018438 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
77 | MARIPOSA 21019400 | 0.03215 | 0.05564 | 0.035175 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
78 | FORESTHILL 1102359542 | 0.83972 | 0.2095 | 0.26502 | Line removal, Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Line removal Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
79 | CALAVERAS CEMENT 11011419 | 0.00094378 | 0.026682 | 0.84082 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Pole clearing Vegetation routine patrol Vegetation hazard patrol | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol
80 | BRUNSWICK 110651486 | 0.036121 | 0.037474 | 0.038933 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
81 | SHINGLE SPRINGS 210913322 | 0.03402 | 0.035218 | 0.036504 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
82 | PINE GROVE 11013170 | 0.0036427 | 0.003656 | 0.0036694 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
83 | WEST POINT 110236676 | 0.033695 | 0.16075 | 0.80549 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Pole clearing Vegetation routine patrol Vegetation hazard patrol | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol
84 | APPLE HILL 21021532 | 0.017923 | 0.01825 | 0.01859 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
85 | CALAVERAS CEMENT 110147968 | 0.0018562 | 0.0018597 | 0.83034 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol
86 | WILDWOOD 1101384582 | 0 | 0 | 0 | EPSS, Vegetation routine patrol, Vegetation hazard patrol | EPSS, Vegetation routine patrol, Vegetation hazard patrol | EPSS, Vegetation routine patrol, Vegetation hazard patrol | EPSS Vegetation routine patrol Vegetation hazard patrol | EPSS Vegetation routine patrol Vegetation hazard patrol | EPSS Vegetation routine patrol Vegetation hazard patrol
87 | SANTA YNEZ 1102320270 | 0.025945 | 0.026636 | 0.45234 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol
88 | FRENCH GULCH 11022902 | 0.0023837 | 0.52171 | 0.0049957 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol
89 | STANISLAUS 17011812 | 0.4324 | 0.41146 | 0.99076 | Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Overhead hardening, Undergrounding, Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol | Overhead hardening Undergrounding Pole clearing Vegetation routine patrol Vegetation hazard patrol
90 | PERRY 110179696 | 0.03616 | 0.037516 | 0.038978 | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing, Vegetation routine patrol, Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol | Pole clearing Vegetation routine patrol Vegetation hazard patrol