## Table 1
METRIC NUMBER | UTILITY ID | SUBMISSION DATE | WMP CATEGORY | WMP INITIATIVE | WMP ACTIVITY NAME | TARGET ID (IF MULTIPLE) | UTILITY MITIGATION ACTIVITY TRACKING ID (UMAT) | ACTIVITY CLASSIFICATION | ACTIVITY DESCRIPTION | ACTIVITY OBJECTIVE | WMP SECTION | RISK COMPONENT TARGETED | QUANT / QUAL | QUANT TARGET UNITS | MIDYEAR TARGET (YES / NO) | COMMENTS | BLANK MEANING | REPORTING YEAR | REPORTING QUARTER | QUANT YTD VALUE | QUAL YTD VALUE | STATUS | CORRECTIVE ACTIONS IF DELAYED
1010000000 | PG&E | 2026-08-03 | Grid Design, Operations, and Maintenance | Asset Inspections | Detailed Inspection - Transmission |  | AI-04 | Program | Complete detailed inspections on transmission structures, which will be identified in PG&E's asset registry at the time of workplan development. Inspections may be completed by either ground or aerial methods | Perform detailed inspections on transmission structures in PG&E's asset registry | 8.3.1 | Equipment ignition likelihood | Quantitative | Transmission Structures | Yes |  |  | 2026 | 2 | 24693 |  | Completed
1010000001 | PG&E | 2026-08-03 | Grid Design, Operations, and Maintenance | Asset Inspections | Infrared Inspections - Transmission |  | AI-06 | Program | Infrared patrols will be performed on circuit miles of energized transmission line | Perform infrared patrols on circuit miles of energized transmission line | 8.3.3 | Equipment ignition likelihood | Quantitative | Circuit Miles | Yes |  |  | 2026 | 2 | 1961.37 |  | In Progress
1010000002 | PG&E | 2026-08-03 | Grid Design, Operations, and Maintenance | Asset Inspections | Aerial Scan Inspections - Distribution |  | AI-07A | Program | Complete aerial scan inspections on distribution poles, which will be identified in PG&E's asset registry at the time of work plan development | Perform Aerian scan inspections on distribution poles in PG&E's asset registry | 8.3.8 | Equipment ignition likelihood | Quantitative | Distribution Poles | Yes |  |  | 2026 | 2 | 44484 |  | In Progress
1010000003 | PG&E | 2026-08-03 | Grid Design, Operations, and Maintenance | Asset Inspections | Detailed Inspections - Distribution |  | AI-07D | Program | Complete detailed inspections on distribution poles, which will be identified in PG&E's asset registry at the time of workplan development. Inspections may be completed by either ground or aerial methods | Perform detailed inspections on distribution poles in PG&E's asset registry | 8.3.8 | Equipment ignition likelihood | Quantitative | Distribution Poles | Yes |  |  | 2026 | 2 | 114444 |  | In Progress
1010000004 | PG&E | 2026-08-03 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | Asset Inspections Distribution Quality Assurance |  | GM-01D | Program | Ensure inspections are following electrical corporation procedures for inspections (TABLE 8-3) to achieve a cumulative Pass Rate target at targeted volume of Sample Distribution Poles stated in Table 8-4 | Ensure Aerial Scan inspections (AI-07A) and Detailed Inspections – Distribution (AI-07D) performed in HFTD, HFRA, and buffer areas are following electrical corporation procedures and meet the applicable quality assurance standards | 8.5.1 | Equipment ignition likelihood | Quantitative | % Pass Rate | No | Pass Rate -> 99.48% Total # of Locations Audited -> 385 Total # of Locations Passed -> 383 Total # of Locations Failed -> 2 |  | 2026 | 2 | 99.48% |  | In Progress
1010000005 | PG&E | 2026-08-03 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | Asset Inspections Transmission Quality Assurance |  | GM-01T | Program | Ensure inspections are following electrical corporation procedures for inspections (TABLE 8-3) to achieve a cumulative Pass Rate target at targeted volume of Sample Transmission Structures stated in Table 8-4 | Ensure Transmission – Detailed Inspection Program (AI-04) performed in HFTD, HFRA, and buffer areas are following electrical corporation procedures and meet the applicable quality assurance standards | 8.5.1 | Equipment ignition likelihood | Quantitative | % Pass Rate | No | Pass Rate -> 100% Total # of Locations Audited -> 300 Total # of Locations Passed -> 300 Total # of Locations Failed -> 0 |  | 2026 | 2 | 1 |  | In Progress
1010000006 | PG&E | 2026-08-03 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | Asset Inspections Distribution Quality Control |  | GM-09D | Program | Ensure inspections are following procedures for inspections (TABLE 8-3) to achieve a cumulative Pass Rate target at targeted volume of Sample Distribution Poles stated in Table 8-4 | Ensure Aerial Scan inspections (AI-07A) and Detailed Inspections – Distribution (AI-07D) performed in HFTD, HFRA, and buffer areas are following electrical corporation procedures and meet the applicable quality control standards | 8.5.1 | Equipment ignition likelihood | Quantitative | % Pass Rate | No | Pass Rate -> 99.83% Total # of Locations Audited -> 33,241 Total # of Locations Passed -> 33,183 Total # of Locations Failed -> 58 |  | 2026 | 2 | 99.83% |  | In Progress
1010000007 | PG&E | 2026-08-03 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | Asset Inspection Transmission Quality Control |  | GM-09T | Program | Ensure inspections are following procedures for inspections (TABLE 8-3) to achieve a cumulative Pass Rate target at targeted volume of Sample Transmission Structures stated in Table 8-4. | Ensure Transmission – Detailed Inspection Program (AI-04) performed in HFTD, HFRA, and buffer areas are following electrical corporation procedures and meet the applicable quality control standards | 8.5.1 | Equipment ignition likelihood | Quantitative | % Pass Rate | No | Pass Rate -> 99.67% Total # of Locations Audited -> 9,339 Total # of Locations Passed -> 9,308 Total # of Locations Failed -> 31 |  | 2026 | 2 | 99.67% |  | In Progress
1010000008 | PG&E | 2026-08-03 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | System Hardening Distribution Quality Assurance |  | GM-10D | Program | Ensure that new construction meets applicable standards (TABLE 8 3) to achieve a cumulative Pass Rate target at targeted volume of Sample Circuit Miles stated in Table 8-4 | Ensure PG&E's Undergrounding target (GH-04) that includes all undergrounding work as part of System Hardening and any other undergrounding work performed in HFTD, HFRA, Buffer Zone, or fire rebuild areas meet the applicable quality assurance standards | 8.5.1 | Equipment ignition likelihood | Quantitative | % Pass Rate | No | YTD Miles Completed: 21.61 YTD Total Opportunities Audited:6,374 YTD Total Opportunities Passed: 6,301 YTD Total Opportunities Failed: 73 YTD Pass Rate %: 98.85% |  | 2026 | 2 | 98.85% |  | In Progress
1010000009 | PG&E | 2026-08-03 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | System Hardening Distribution Quality Control |  | GM-11D | Program | Ensure that new construction meets applicable standards (TABLE 8-3) to achieve a cumulative Pass Rate target at targeted volume of Sample Circuit Miles stated in Table 8-4 | Ensure PG&E's Undergrounding target (GH-04) that includes all undergrounding work as part of System Hardening and any other undergrounding work performed in HFTD, HFRA, Buffer Zone, or fire rebuild areas meet the applicable quality control standards | 8.5.1 | Equipment ignition likelihood | Quantitative | % Pass Rate | No | YTD Miles Completed : 41.65 YTD Total Opportunities Audited: 11,552 YTD Total Opportunities Passed: 11,407 YTD Total Opportunities Failed: 145 YTD Pass Rate %: 99.29% |  | 2026 | 2 | 98.74% |  | In Progress
1010000010 | PG&E | 2026-08-03 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | Open Tag Reduction Distribution Quality Assurance |  | GM-12D | Program | Ensure that corrective repair work meets applicable standards (TABLE 8-3) to achieve a cumulative Pass Rate target at targeted volume of Sample Distribution EC Tags stated in Table 8-4 | Ensure that corrective repair work for Open Tag Reduction – Distribution performed in HFTD, HFRA and buffer areas (GM-03) meets the applicable quality assurance standards | 8.5.1 | Equipment ignition likelihood | Quantitative | % Pass Rate | No | YTD Units Completed: 385 YTD Total Opportunities Audited - 7,175 YTD Total Opportunities Passed - 7,117 YTD Total Opportunities Failed - 58 YTD Pass Rate %: 99.19% |  | 2026 | 2 | 99.19% |  | In Progress
1010000011 | PG&E | 2026-08-03 | Grid Design, Operations, and Maintenance | Quality Assurance and Quality Control (Asset Management) | Open Tag Reduction Distribution Quality Control |  | GM-13D | Program | Ensure that corrective repair work meets applicable standards (TABLE 8-3) to achieve a cumulative Pass Rate target at targeted volume of Sample Distribution EC Tags stated in Table 8-4 | Ensure that corrective repair work for Open Tag Reduction – Distribution performed in HFTD, HFRA and buffer areas (GM-03) meets the applicable quality control standards | 8.5.1 | Equipment ignition likelihood | Quantitative | % Pass Rate | No | YTD Units Completed:14,192 YTD Total Opportunities Audited:204,713 YTD Total Opportunities Passed:195,463 YTD Total Opportunities Failed:9,250 YTD Pass Rate %: 95.48% |  | 2026 | 2 | 95.48% |  | In Progress
1010000012 | PG&E | 2026-08-03 | Grid Design, Operations, and Maintenance | Work Orders (Asset Management) | Open Tag Reduction - Distribution |  | GM-03 | Program | Close out a volume of tags equivalent to the Target Percentage of the EC notifications created in HFTD/HFRA locations during the previous year | Close EC notifications and reduce wildfire risk | 8.6.2 | Equipment ignition likelihood | Quantitative | Distribution EC Tags | No |  |  | 2026 | 2 | 48383 |  | In Progress
1010000013 | PG&E | 2026-08-03 | Grid Design, Operations, and Maintenance | Grid Operations and Procedures | Updates on EPSS Reliability Study |  | GM-07 | Project | Provide annually an updated Enhanced Powerline Safety Settings (EPSS) reliability impact study in alignment with prior WMP EPSS reliability studies and any associated ACIs | Provide annually an updated Enhanced Powerline Safety Settings (EPSS) reliability impact study | 8.7.1.1 | Equipment ignition likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | This commitment was completed in Q1 2026. | Completed
1010000014 | PG&E | 2026-08-03 | Grid Design, Operations, and Maintenance | Workforce Planning (Asset Management) | Workforce Planning - Distribution Asset Inspection |  | GM-15 | Project | PG&E will continue our annual training program review for Qualified Company Representative (QCR) Inspectors focused on ground or aerial inspections, which supports wildfire mitigation | Conduct annual training program review for QCR Inspectors focused on ground or aerial inspections | 8.8.1 | Equipment ignition likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | PG&E has completed its annual training program review for Qualified Company Representative (QCR) Inspectors focused on ground or aerial inspections and has incorporated approved changes from the Standards and Asset Strategy teams. This commitment is completed for 2026. | Completed
1010000015 | PG&E | 2026-08-03 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) | Vegetation Management Quality Assurance - Distribution |  | VM-08D | Program | Complete the annual Quality Assurance Audit Plan to calculate and report the pass rate of VM Distribution Routine program locations | Quality Assurance - VM Distribution Routine | 9.11 | Contact from vegetation ignition likelihood | Quantitative | % Pass Rate | No | Pass Rate -> 99.90% Total YTD Miles -> 264.97 Total # Grow In of Trees Inspected – 29,072 Total # Grow In of Trees Passed – 29,044 Total # Grow In of Trees Failed – 28 |  | 2026 | 2 | 99.9% |  | In Progress
1010000016 | PG&E | 2026-08-03 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) | Vegetation Management Quality Assurance - Transmission |  | VM-08T | Program | Complete the annual Quality Assurance Audit Plan to calculate and report the pass rate of VM Transmission Routine program locations | Quality Assurance - VM Transmission Routine | 9.11 | Contact from vegetation ignition likelihood | Quantitative | % Pass Rate | No | Pass Rate -> 100.00% Total YTD Miles -> 178.91 Total # Grow In of Trees Inspected – 2699 Total # Grow In of Trees Passed – 2699 Total # Grow In of Trees Failed – 0 |  | 2026 | 2 | 1 |  | In Progress
1010000017 | PG&E | 2026-08-03 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) | Vegetation Management Quality Control - Distribution Routine |  | VM-22D | Program | Complete the annual Quality Control Audit Plan to determine the pass rate of VM Distribution Routine Program locations | Quality Control - VM Distribution Routine | 9.11 | Contact from vegetation ignition likelihood | Quantitative | % Pass Rate | No | Pass Rate -> 99.75% Spans Audited – 59,668 Total Trees Inspected – 644,002 Total Trees Passed – 642,380 Total Trees Failed – 1,622 |  | 2026 | 2 | 99.75% |  | In Progress
1010000018 | PG&E | 2026-08-03 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) | Vegetation Management Quality Control - Pole Clearing |  | VM-22P | Program | Complete the annual Quality Control Audit Plan to determine the pass rate of VM Pole Clearing Program locations | Quality Control - VM Pole Clearing | 9.11 | Contact from vegetation ignition likelihood | Quantitative | % Pass Rate | No | Pass Rate -> 99.68% Poles Inspected – 5,872 Poles Passed – 5,853 Poles Failed – 19 |  | 2026 | 2 | 0.9968 |  | In Progress
1010000019 | PG&E | 2026-08-03 | Vegetation Management and Inspections | Quality Assurance and Quality Control (Vegetation Management) | Vegetation Management Quality Control - Transmission Routine |  | VM-22T | Program | Complete the annual Quality Control Audit Plan to determine the Pass Rate of VM Transmission Routine Program locations | Quality Control - VM Transmission Routine | 9.11 | Contact from vegetation ignition likelihood | Quantitative | % Pass Rate | No | Pass Rate -> 99.96% Spans Audited – 8,049 Total Trees Inspected – 29,730 Total Trees Passed – 29,718 Total Trees Failed – 12 |  | 2026 | 2 | 99.96% |  | In Progress
1010000020 | PG&E | 2026-08-03 | Vegetation Management and Inspections | Workforce Planning (Vegetation Management) | ​​Workforce Planning - Vegetation Management​ |  | VM-24 | Project | Continue annually on its execution of planned recruitment, retention, and training of vegetation management and inspections personnel and partnerships. (RN-PGE-26-08) | Recruitment, retention, training of vegetation management and inspections personnel and partnerships | 9.13 | Contact from vegetation ignition likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | The VM Training team has met the 2026 target allocation for retention-related expenses. The team continues to deliver One VM Training and VM Basic Curriculum courses for VMI personnel, with 74 One VM Training completions and 621 VM Basic Curriculum completions to date in 2026. Community college scholarship funding has not yet been provided and is expected to be included in Q3 2026.Training will continue through the remainder of the year to support achievement of the VM-24 WMP target. | In Progress
1010000021 | PG&E | 2026-08-03 | Vegetation Management and Inspections | Vegetation Management Inspections | Distribution Routine Patrol |  | VM-16 | Program | Complete Distribution Routine Patrol territory-wide on overhead electric facilities (excluding service drops) | VM Distribution Routine Annual Patrol Inspection | 9.2.1 | Contact from vegetation ignition likelihood | Quantitative | Span Miles | Yes |  |  | 2026 | 2 | 54237.2 |  | In Progress
1010000022 | PG&E | 2026-08-03 | Vegetation Management and Inspections | Vegetation Management Inspections | Mitigation of Legacy Tree Removal Inventory (TRI) |  | VM-26 | Program | Mitigate 135,000 trees from the legacy Tree Removal Inventory (cumulative) between 2026-2028 | Reduce Tree Removal Inventory | 9.2.1 | Contact from vegetation ignition likelihood | Quantitative | Trees | No |  |  | 2026 | 2 | 56350 |  | Completed
1010000023 | PG&E | 2026-08-03 | Vegetation Management and Inspections | Vegetation Management Inspections | Distribution Hazard Patrol |  | VM-17 | Program | Complete Distribution Hazard Patrol (previously second patrol, tree mortality) inspections on risk-prioritized subset of HFTD and HFRA offset from the Distribution Routine Patrol | VM Distribution Hazard Patrol Inspection | 9.2.2 | Contact from vegetation ignition likelihood | Quantitative | Span Miles | Yes |  |  | 2026 | 2 | 8846.8 |  | In Progress
1010000024 | PG&E | 2026-08-03 | Vegetation Management and Inspections | Vegetation Management Inspections | Routine Transmission - Ground |  | VM-13 | Program | Complete Routine Transmission Ground Inspection as defined by Transmissions Routine LiDAR detection point data systemwide | Routine Transmission Ground Inspection | 9.2.3 | Contact from vegetation ignition likelihood | Quantitative | Circuit Miles | Yes |  |  | 2026 | 2 | 16722 |  | In Progress
1010000025 | PG&E | 2026-08-03 | Vegetation Management and Inspections | Vegetation Management Inspections | Transmission Hazard Patrol |  | VM-14 | Program | Complete Transmission Hazard Patrol Inspection, dependent on remote sensing (ORTHO Imagery) | Transmission Hazard Patrol Inspection | 9.2.4 | Contact from vegetation ignition likelihood | Quantitative | Circuit Miles | Yes | Program to start in Q3, workplan defined and approved |  | 2026 | 2 | 0 |  | In Progress
1010000026 | PG&E | 2026-08-03 | Vegetation Management and Inspections | Pole Clearing | Pole Clearing Program - Compliance |  | VM-02C | Program | Inspect and clear vegetation, as necessary, around subject distribution poles and transmission structures during the initial clear cycle to achieve compliance | Inspect and clear distribution poles and transmission structures | 9.4 | Contact from vegetation ignition likelihood | Quantitative | Poles | Yes |  |  | 2026 | 2 | 43270 |  | In Progress
1010000027 | PG&E | 2026-08-03 | Vegetation Management and Inspections | Pole Clearing | Pole Clearing Program - Risk Reduction |  | VM-02R | Program | Inspect and clear vegetation, as necessary, around subject distribution poles and transmission structures during the initial clear cycle to achieve risk reduction | Inspect and clear distribution poles and transmission structures | 9.4 | Contact from vegetation ignition likelihood | Quantitative | Poles | Yes |  |  | 2026 | 2 | 26211 |  | Completed
1010000028 | PG&E | 2026-08-03 | Vegetation Management and Inspections | Defensible Space | Substation Inspections - Distribution |  | VM-05 | Program | Complete defensible space inspections at distribution substations in HFTD/HFRA | Defensible space inspections - Distribution Substations | 9.6 | Wildfire exposure potential | Quantitative | Distribution Substations | Yes |  |  | 2026 | 2 | 130 |  | Completed
1010000029 | PG&E | 2026-08-03 | Vegetation Management and Inspections | Defensible Space | Substation Inspections - Transmission |  | VM-06 | Program | Complete defensible space inspections at transmission substations in HFTD/HFRA | Defensible space inspections - Transmission Substations | 9.6 | Wildfire exposure potential | Quantitative | Transmission Substations | Yes | PG&E completed 53 of the 55 targeted inspections. The remaining two facilities, Colgate Powerhouse and Colgate Switching Station, are currently deactivated due to station damage caused by the hydro penstock failure. PG&E is marking this commitment as complete because the initiative’s full applicable scope has been completed. |  | 2026 | 2 | 55 |  | Completed
1010000030 | PG&E | 2026-08-03 | Vegetation Management and Inspections | Defensible Space | Substation Inspections - Power Generation |  | VM-07 | Program | Complete defensible space inspections at Power Generation Powerhouses and associated Switchyards in HFTD/HFRA | Defensible space inspections - Power Generation Switchyards and Powerhouses | 9.6 | Wildfire exposure potential | Quantitative | Power Generation Switchyards and Powerhouses | Yes |  |  | 2026 | 2 | 58 |  | Completed
1010000031 | PG&E | 2026-08-03 | Situational Awareness and Forecasting | Environmental Monitoring Systems | Live Fuel Moisture Data Collection |  | SA-12 | Program | Collect and process live fuel moisture (LFM) samples | Collect and process live fuel moisture samples | 10.2.1 / 10.2.4 | Equipment ignition likelihood | Quantitative | Sample Locations | No |  |  | 2026 | 2 | 190 |  | In progress
1010000032 | PG&E | 2026-08-03 | Situational Awareness and Forecasting | Environmental Monitoring Systems | Weather Station Network Evaluation |  | SA-13 | Project | Review weather station coverage annually to determine priority installation strategy | Determine priority installation or optimization locations | 10.2.4 | Equipment ignition likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | This commitment was completed in Q1 2026. | Completed
1010000033 | PG&E | 2026-08-03 | Situational Awareness and Forecasting | Grid Monitoring Systems | Line Sensor - Installations |  | SA-02 | Program | Install Line Sensor devices on circuit locations | Install Line Sensor devices on circuit locations | 10.3.1 | Equipment ignition likelihood | Quantitative | Sensor Locations | No |  |  | 2026 | 2 | 21 |  | In Progress
1010000034 | PG&E | 2026-08-03 | Situational Awareness and Forecasting | Grid Monitoring Systems | Distribution Fault Anticipation (DFA) Installations |  | SA-10 | Program | Install Distribution Fault Anticipation (DFA) sensors on circuits. One sensor will be installed per circuit | Install Distribution Fault Anticipation (DFA) sensors on circuits. | 10.3.1 | Equipment ignition likelihood | Quantitative | Sensor Locations | No |  |  | 2026 | 2 | 9 |  | In Progress
1010000035 | PG&E | 2026-08-03 | Situational Awareness and Forecasting | Grid Monitoring Systems | Early Fault Detection (EFD) - Installations |  | SA-11 | Program | Install Early Fault Detection (EFD) sensors on circuit locations | Install Early Fault Detection (EFD) sensors on circuit locations | 10.3.1 | Equipment ignition likelihood | Quantitative | Sensor Locations | No |  |  | 2026 | 2 | 120 |  | In Progress
1010000036 | PG&E | 2026-08-03 | Situational Awareness and Forecasting | Ignition Detection Systems | Evaluate camera AI system performance and new functionalities. |  | SA-08 | Project | In partnership with Digital Path, evaluate camera AI system performance and explore additional enhancements | Evaluate camera AI system performance and explore additional enhancements | 10.4.1 | Equipment ignition likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | This initiative is on track. All required ROE items have been collected and uploaded YTD. The vendor has released new features and is continuing to fine-tune them alongside their latest fire detection model. | In Progress
1010000037 | PG&E | 2026-08-03 | Situational Awareness and Forecasting | Ignition Detection Systems | Weekly uptime of Wildfire Cameras |  | SA-15 | Program | Maintain weekly average uptime percentage of Wildfire Cameras | Maintain weekly average uptime percentage of Wildfire Cameras | 10.4.1 | Equipment ignition likelihood | Quantitative | Average weekly uptime percentage | No |  |  | 2026 | 2 | 96.88% |  | In Progress
1010000038 | PG&E | 2026-08-03 | Situational Awareness and Forecasting | Weather Forecasting | Weather Model Verification Tool |  | SA-16 | Program | Develop an in-house model verification tool to evaluate performance of multiple weather models | Develop an in-house weather model verification tool | 10.5.3 | Equipment ignition likelihood | Quantitative | Weather Model Verification Tool | No | This commitment was completed in Q1 2026. |  | 2026 | 2 | 1 |  | Completed
1010000039 | PG&E | 2026-08-03 | Situational Awareness and Forecasting | Weather Forecasting | Weather Station Network Health |  | SA-18 | Program | By October 1 of each year, ensure weather stations are operational and within internal calibration guidance | Ensure weather stations are operational and within internal calibration guidance | 10.5.5 | Equipment ignition likelihood | Quantitative | Percent of Weather Stations | No |  |  | 2026 | 2 | 97.31% |  | In Progress
1010000040 | PG&E | 2026-08-03 | Situational Awareness and Forecasting | Weather Forecasting | Weather Station Network Optimization |  | SA-19 | Project | Annually review stations that are no longer accessible or safe and determine opportunities to remove or optimize | Remove or optimize stations that are no longer accessible or safe | 10.5.5 | Equipment ignition likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | This commitment was completed in Q1 2026. | Completed
1010000041 | PG&E | 2026-08-03 | Emergency Preparedness, Collaboration and Public Awareness | External Collaboration and Coordination | Continue sharing PSPS lessons learned |  | PS-10 | Project | PG&E will share PSPS lessons learned and best practices with IOUs through monthly meetings focused on PSPS. | Continue sharing PSPS lessons learned and best practices with other IOUs | 11.3 | PSPS likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | Met with SCE and SDG&E monthly and submitted report to CPUC within 14 days following each meeting. | In Progress
1010000042 | PG&E | 2026-08-03 | Emergency Preparedness, Collaboration and Public Awareness | Public Communication, Outreach, and Education Awareness | Community Engagement - Outreach to HFRA Infrastructure Customers |  | CO-04 | Project | PG&E will perform annual outreach via email and/or phone to assigned Critical Infrastructure customers in the HFRA through Business Energy Solutions (assigned account managers). Outreach will cover the WMP, including potential PSPS and EPSS impacts, and updating contact information for critical accounts in the HFRA | Perform annual outreach via email and/or phone to assigned Critical Infrastructure customers in the HFRA to provide WMP, including potential PSPS and EPSS impacts, and update critical contact details | 11.4.3 | Wildfire vulnerability | Qualitative |  | No |  |  | 2026 | 2 |  | This commitment is on track. Phase I outreach to HFRA Critical Infrastructure customers was completed on 5/29/2026. Phase II will commence in August 2026. | In Progress
1010000043 | PG&E | 2026-08-03 | Emergency Preparedness, Collaboration and Public Awareness | Public Communication, Outreach, and Education Awareness | Community Engagement - Outage Preparedness Campaign |  | CO-05 | Project | PG&E will conduct at least one direct-to-customer outage preparedness campaign annually via email and/or direct mail targeting residential customers within the PSPS and EPSS program scope. | Conduct an annual outage‑preparedness campaign to PSPS/EPSS residential customers via email or direct mail | 11.4.3 | Wildfire vulnerability | Qualitative |  | No |  |  | 2026 | 2 |  | This commitment is on track. The marketing and customer outreach team are in the process of setting email delivery to the targeted customer base set to be delivered by the end of July. | In Progress
1010000044 | PG&E | 2026-08-03 | Enterprise Systems | Enterprise Systems Development | Participate in Company Disaster Recovery Exercise |  | ES-04 | Project | Meteorology Operations and Fire Science will participate in company disaster recovery exercise and test the failover capabilities of our AWS-cloud Meteorology Enterprise System | Participate in company disaster recovery exercise and test the failover capabilities of our AWS-cloud Meteorology Enterprise System | 12.1.1 | Wildfire exposure potential | Qualitative |  | No |  |  | 2026 | 2 |  | This commitment was completed in Q1 2026. | Completed
1010000045 | PG&E | 2026-08-03 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Overhead Hardening - Distribution |  | GH-12 | Program | Complete circuit miles of overhead hardening work. PG&E’s Overhead Hardening target is GH-12 and includes work associated with overhead hardening for base system hardening work, fire rebuild work, and other (e.g. work requested by other, capacity) overhead hardening work. This commitment excludes community rebuild areas per revision notice RN-PG&E-26-05 | Overhead system hardening | 8.2.1 | Equipment ignition likelihood | Quantitative | Circuit Miles | No |  |  | 2026 | 2 | 144.378 |  | In Progress
1010000046 | PG&E | 2026-08-03 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Service Breakaway Connectors |  | GM-14 | Program | Add OH service Breakaway Disconnects at service points. | Add OH service Breakaway Disconnects at service points | 8.2.10.6 | Equipment ignition likelihood | Quantitative | Service Breakaway Connectors | No |  |  | 2026 | 2 | 261 |  | Completed
1010000047 | PG&E | 2026-08-03 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | System Hardening - Undergrounding |  | GH-04 | Program | Complete circuit miles of undergrounding work associated with undergrounding for base system hardening work, fire rebuild work and any other (e.g. work requested by other, capacity, and rule 20A) undergrounding work. This commitment excludes community rebuild areas per revision notice RN-PGE-26-05 | Undergrounding electric distribution system assets | 8.2.2 | Equipment ignition likelihood | Quantitative | Circuit Miles | No | As of Q2 2026, We completed 69.61 miles of undergrounding toward its annual target of 360 miles. The program is approximately 9 miles behind the internal year-to-date target due to sequencing and permitting issues. PG&E has implemented a corrective action plan and expects to complete the annual commitment by year-end. Because GH-04 is an annual target with no quarterly milestones, the initiative has not been marked as delayed in Table 1 above. |  | 2026 | 2 | 69.61 |  | In Progress
1010000048 | PG&E | 2026-08-03 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | System Hardening - Transmission Conductor Segment Replacement |  | GH-11 | Program | Replace conductor segments on transmission lines traversing HFTD/HFRA areas | Replace conductor segments on transmission lines | 8.2.5.1 | Equipment ignition likelihood | Quantitative | Conductor Segment | No |  |  | 2026 | 2 | 5 |  | Completed
1010000049 | PG&E | 2026-08-03 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | System Hardening - Transmission Shunt Splices |  | GH-06 | Program | Install shunt splice(s) on transmission lines | Install shunt splice(s) on transmission lines | 8.2.5.1 | Equipment ignition likelihood | Quantitative | Shunt Splices | No |  |  | 2026 | 2 | 250 |  | Completed
1010000050 | PG&E | 2026-08-03 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Line Removal Enabled by Remote Grid - Distribution |  | GH-14 | Program | Complete circuit miles of distribution line removal by remote grid. PG&E’s line removal enabled by remote grid target is GH-14 and includes work associated with line removal enabled by remote grid for base system hardening work and fire rebuild work. This commitment excludes community rebuild areas per revision notice RN-PG&E-26-05. Line removal mileage from idle facilities and circuit re-routing will not be reported in actuals towards the GH-14 target | Overhead line removal associated with remote grid installations | 8.2.7.1 | Equipment ignition likelihood | Quantitative | Circuit Miles | No |  |  | 2026 | 2 | 4.007 |  | Completed
1010000051 | PG&E | 2026-08-03 | Emergency Preparedness, Collaboration and Public Awareness | Emergency Preparedness and Recovery Plan | Common Operating Picture Technology |  | EP-07 | Project | ​Design and deploy a common operating picture | ​Design and deploy a common operating picture | 11.2 | Wildfire exposure potential | Qualitative |  | No |  |  | 2026 | 2 |  | This commitment was completed in Q1 2026. | Completed
1010000052 | PG&E | 2026-08-03 | Enterprise Systems | Enterprise Systems Development | VM Critical Datasets Data Quality Remediation |  | ES-01 | Project | VM critical data sets data quality remediation describes how PG&E will improve VM data through proactive identification of data quality issues, and the development and execution of data quality mitigation plans | PG&E will analyze critical Vegetation Management data sets and develop and execute an improvement plan for data quality | 12.1.1 | Contact from vegetation ignition likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | This objective continues to be on track. The 4 highest prioritized data sets have monitoring enabled via business rules applied to all critical data elements in Ataccama (Ataccama is PGE's Enterprise-wide data quality application). We have also managed and are monitoring an additional 6 data sets, for a total of 10 data sets. | In Progress
1010000053 | PG&E | 2026-08-03 | Enterprise Systems | Enterprise Systems Development | Evaluate and create new methods(s) to improve accuracy of Asset Inventory Data |  | ES-02 | Project | Pilot method(s) for validating and improving the accuracy of asset inventory data for risk prioritized distribution and transmission equipment | Pilot method(s) for validating and improving the accuracy of asset inventory data for risk prioritized distribution and transmission equipment | 12.1.1 | Equipment ignition likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | This commitment was completed in Q1 2026. | Completed
1010000054 | PG&E | 2026-08-03 | Enterprise Systems | Enterprise Systems Development | Grid Monitoring Sensor Systems Efficacy Assessment |  | ES-03 | Project | Validate efficacy of Grid Monitoring Sensor Systems for realizing wildfire risk reduction | Validate efficacy of Grid Monitoring Sensor Systems for realizing wildfire risk reduction | 12.1.1 | Wildfire exposure potential | Qualitative |  | No |  |  | 2026 | 2 |  | This commitment was completed in Q1 2026. | Completed
1010000055 | PG&E | 2026-08-03 | Enterprise Systems | Enterprise Systems Development | Integration of continuous grid monitoring technologies |  | ES-05 | Project | Integration of continuous grid monitoring technologies to deliver enhanced situational awareness to PG&E Operations.• Add sensor asset family in GIS databases for asset inventory and location visibility purposes• Create centralized system and dashboard for sensor asset health monitoring• Deliver evaluated alerts that are actionable by PG&E Operations• Implement tracking system for trending analysis and to further refine alert evaluation methodologies | Integration of continuous grid monitoring technologies to deliver enhanced situational awareness to PG&E Operations | 12.1.1 | Wildfire exposure potential | Qualitative |  | No |  |  | 2026 | 2 |  | This commitment was completed in Q1 2026. | Completed
1010000056 | PG&E | 2026-08-03 | Grid Design, Operations, and Maintenance | Grid Design and System Hardening | Proactive Avian Abatement Feasibility Study – Transmission |  | GH-13 | Project | Provide an Avian Abatement Feasibility Study | Provide an Avian Abatement Feasibility Study | 8.2.13.1 | Wildfire vulnerability | Qualitative |  | No |  |  | 2026 | 2 |  | This commitment was completed in Q1 2026. | Completed
1010000057 | PG&E | 2026-08-03 | Emergency Preparedness, Collaboration and Public Awareness | Customer Support in Wildfire and PSPS Emergencies | Access and Functional Needs (AFN) Customer Support During PSPS Emergencies |  | PS-12 | Project | Continue providing access to portable battery storage solutions and in-event support including hotels, transportation, food vouchers, and fuel cards for AFN customers impacted by PSPS and Wildfire outages | Continue providing access to portable battery storage solutions and in-event support for AFN customers impacted by PSPS and Wildfire outages | 11.5 | PSPS vulnerability | Qualitative |  | No |  |  | 2026 | 2 |  | This commitment was completed in Q1 2026. | Completed
1010000058 | PG&E | 2026-08-03 | Situational Awareness and Forecasting | Grid Monitoring Systems | SmartMeters next generation capability evaluation |  | SA-14 | Project | Evaluate the viability of next generation SmartMeter technology for reducing wildfire risk and, if it is found viable, develop a path to production for the technology | Evaluate Next Generation SmartMeter’s capability for wildfire risk reduction and develop a path to production if technology is found to be viable | 10.3.3 | Wildfire vulnerability | Qualitative |  | No |  |  | 2026 | 2 |  | This commitment was completed in Q1 2026. | Completed
1010000059 | PG&E | 2026-08-03 | Situational Awareness and Forecasting | Weather Forecasting | Weather Model Enhancements leveraging AI-ML |  | SA-17 | Project | Evaluate the skill and performance of weather model output (e.g., wind speed, temperature or relative humidity) using models enhanced with Artificial Intelligence (AI) or Machine Learning (ML) | Evaluate the skill and performance of weather model output using models enhanced with Artificial Intelligence (AI) or Machine Learning (ML) | 10.5.3 | Wildfire spread | Qualitative |  | No |  |  | 2026 | 2 |  | This commitment was completed in Q1 2026. | Completed
1010000060 | PG&E | 2026-08-03 | Vegetation Management and Inspections | Wood and Slash Management | Wood Management Benchmarking |  | VM-23 | Project | Develop peer utility wood management benchmarking to identify best practices | Develop peer utility wood management benchmarking to identify best practices | 9.5 | Contact from vegetation ignition likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | A calendar invitation for the VM-23 Benchmarking kickoff call was sent to the participating IOU's on 5/21/26. The kickoff call was held on 6/18/26 with representation from all participating IOU's in attendance. Participating IOUs are Pacific Power Corp, SCE, SDGE, and Liberty Utilities. | In Progress
1010000061 | PG&E | 2026-08-03 | Vegetation Management and Inspections | Integrated Vegetation Management | Integrated Vegetation Management Benchmarking |  | VM-25 | Project | Develop and execute peer utility Integrated Vegetation Management benchmarking study to identify best practices | Develop peer utility Integrated Vegetation Management benchmarking study to identify best practices | 9.7 | Contact from vegetation ignition likelihood | Qualitative |  | No |  |  | 2026 | 2 |  | A calendar invitation for the VM-25 Benchmarking kickoff call was sent to the participating IOU's on 5/21/26. The kickoff call was held on 6/18/26 with representation from all participating IOU's in attendance. Participating IOUs are Pacific Power Corp, SCE, SDGE, and Liberty Utilities. | In Progress

## Table 2
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | HFTD TIER | LINE TYPE | INSPECTION TYPE | INSPECTION METHOD | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1020000000 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 22
1020000001 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 1
1020000002 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000003 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 1489
1020000004 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 3
1020000005 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000006 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000007 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 704
1020000008 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | RFW only | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 497
1020000009 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW only | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000010 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000011 | Risk Events | Number of all events with probability of ignition, including wires down, contacts with objects, line slap, events with evidence of heat generation, and other events that cause sparking or have the potential to cause ignition | Neither | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 8527
1020000012 | Risk Events | Number of wires down | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000013 | Risk Events | Number of wires down | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000014 | Risk Events | Number of wires down | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000015 | Risk Events | Number of wires down | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 95
1020000016 | Risk Events | Number of wires down | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000017 | Risk Events | Number of wires down | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000018 | Risk Events | Number of wires down | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000019 | Risk Events | Number of wires down | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 60
1020000020 | Risk Events | Number of wires down | RFW only | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 47
1020000021 | Risk Events | Number of wires down | HWW only | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000022 | Risk Events | Number of wires down | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000023 | Risk Events | Number of wires down | Neither | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 429
1020000024 | Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 21
1020000025 | Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 1
1020000026 | Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000027 | Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 1410
1020000028 | Risk Events | Number of outage events not caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 3
1020000029 | Risk Events | Number of outage events not caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000030 | Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000031 | Risk Events | Number of outage events not caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 590
1020000032 | Risk Events | Number of outage events not caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 418
1020000033 | Risk Events | Number of outage events not caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000034 | Risk Events | Number of outage events not caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000035 | Risk Events | Number of outage events not caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 8225
1020000036 | Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 1
1020000037 | Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000038 | Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000039 | Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 79
1020000040 | Risk Events | Number of outage events caused by contact with vegetation | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000041 | Risk Events | Number of outage events caused by contact with vegetation | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000042 | Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000043 | Risk Events | Number of outage events caused by contact with vegetation | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 114
1020000044 | Risk Events | Number of outage events caused by contact with vegetation | RFW only | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 79
1020000045 | Risk Events | Number of outage events caused by contact with vegetation | HWW only | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000046 | Risk Events | Number of outage events caused by contact with vegetation | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000047 | Risk Events | Number of outage events caused by contact with vegetation | Neither | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 302
1020000048 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 14
1020000049 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000050 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000051 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 2 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 215
1020000052 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 2
1020000053 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000054 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000055 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | HFTD Tier 3 |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 122
1020000056 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | RFW only | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 65
1020000057 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW only | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000058 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | HWW & RFW | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1020000059 | Risk Events | Number of outage events on circuits with adjusted settings for protective devices enabled. | Neither | Non-HFTD |  |  |  | Number of events |  |  | PG&E | 2026 | 2 | 415
1020000060 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Distribution |  |  | days |  |  | PG&E | 2026 | 2 | 103.875
1020000061 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | days |  |  | PG&E | 2026 | 2 | 318.125
1020000062 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Distribution |  |  | days |  |  | PG&E | 2026 | 2 | 102.8333
1020000063 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | days |  |  | PG&E | 2026 | 2 | 324.9167
1020000064 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Distribution |  |  | days |  |  | PG&E | 2026 | 2 | 153.875
1020000065 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | days |  |  | PG&E | 2026 | 2 | 313.2917
1020000066 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 2 | Transmission |  |  | days | Transmission only includes data from the legacy database. |  | PG&E | 2026 | 2 | 44.5
1020000067 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | days | Transmission only includes data from the legacy database. |  | PG&E | 2026 | 2 | 175.5833
1020000068 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | HFTD Tier 3 | Transmission |  |  | days | Transmission only includes data from the legacy database. |  | PG&E | 2026 | 2 | 63.5417
1020000069 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | days | Transmission only includes data from the legacy database. |  | PG&E | 2026 | 2 | 242.5833
1020000070 | Time between vegetation inspection finding and resulting trimming activity | Median time |  | Non-HFTD | Transmission |  |  | days | Transmission only includes data from the legacy database. |  | PG&E | 2026 | 2 | 52.5417
1020000071 | Time between vegetation inspection finding and resulting trimming activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | days | Transmission only includes data from the legacy database. |  | PG&E | 2026 | 2 | 147.5625
1020000072 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 0
1020000073 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 1
1020000074 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 0
1020000075 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 1
1020000076 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 0
1020000077 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 1
1020000078 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 1
1020000079 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 3
1020000080 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 0.5
1020000081 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 1
1020000082 | Time between level 1 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 0
1020000083 | Time between level 1 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 12
1020000084 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 684
1020000085 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 2464
1020000086 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 429
1020000087 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 2557
1020000088 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 664
1020000089 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 2159
1020000090 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 335
1020000091 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 1081
1020000092 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 116.5
1020000093 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 1075
1020000094 | Time between level 2 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 1387.5
1020000095 | Time between level 2 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 2074
1020000096 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 1043
1020000097 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 3278
1020000098 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 1467.5
1020000099 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 3012
1020000100 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 2016
1020000101 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Distribution |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 3618
1020000102 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 2 | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 1036
1020000103 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 2 | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 1803
1020000104 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | HFTD Tier 3 | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 756
1020000105 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | HFTD Tier 3 | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 1802
1020000106 | Time between level 3 asset inspection finding and resulting maintenance activity | Median time |  | Non-HFTD | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 1299
1020000107 | Time between level 3 asset inspection finding and resulting maintenance activity | 95 percentile time |  | Non-HFTD | Transmission |  |  | hours | Please note that PGE is reporting this metric in Days as the duration of correcting these infractions are typically in months. |  | PG&E | 2026 | 2 | 2069
1020000108 | Vegetation management work orders | Number of vegetation management open work orders (total) | [5 empty] | Number of orders | Data is in total number of trees.​ This data includes Legacy (Distribution and Transmission) and One VM data. |  | PG&E | 2026 | 2 | 10483
1020000109 | Vegetation management work orders | Number of vegetation management past due work orders (total) | [5 empty] | Number of orders | Data is in total number of trees and is based off P1/P2 and Second Patrol numbers. These numbers do not include constrained trees. |  | PG&E | 2026 | 2 | 0
1020000110 | Asset management work orders | Number of asset management open work orders (total) | [5 empty] | Number of orders |  |  | PG&E | 2026 | 2 | 901238
1020000111 | Asset management work orders | Number of asset management past due work orders (total) | [5 empty] | Number of orders |  |  | PG&E | 2026 | 2 | 621616
1020000112 | Response Time | Response time to locked open circuit breaker | [5 empty] | Hours |  | For this metric, data for crew response time to a locked circuit breaker incident is only readily available for instances involving hazard conditions such as 911 or wire down calls. PG&E will continue to review the available information in its outage systems to provide this information in a future filing, although we anticipate creating a system to capture this data could take many months. Currently, any quarterly data would reflect only 911 and wire down events and is not a good representation of our overall response time. | PG&E | 2026 | 2
1020000113 | Fatalities and injuries due to utility-related ignitions | Fatalities due to utility-related ignitions (total) | [5 empty] | Number of fatalities | CPUC Reportable, fire size >10 acre |  | PG&E | 2026 | 2 | 0
1020000114 | Fatalities and injuries due to utility-related ignitions | Injuries due to utility-related ignitions (total) | [5 empty] | Number of injuries | CPUC Reportable, fire size >10 acre |  | PG&E | 2026 | 2 | 1
1020000115 | Value of assets destroyed by utility-related ignitions, listed by asset type | Value of assets destroyed by utility-related ignitions (total) | [5 empty] | Dollars |  |  | PG&E | 2026 | 2 | 0
1020000116 | Structures damaged or destroyed by utility-related ignitions | Number of structures destroyed by utility-related ignitions (total) | [5 empty] | Number of structures | CPUC Reportable, fire size >10 acre |  | PG&E | 2026 | 2 | 0
1020000117 | Structures damaged or destroyed by utility-related ignitions | Critical infrastructure damaged/destroyed by utility-related ignitions (total) | [5 empty] | Number of structures | CPUC Reportable, fire size >10 acre |  | PG&E | 2026 | 2 | 0
1020000118 | Acreage burned by utility-ignited wildfires | Acreage burned by utility-ignited wildfires | [5 empty] | Acres | CPUC Reportable, fire size >10 acre |  | PG&E | 2026 | 2 | 1215
1020000119 | Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 2 |  |  |  | Number of ignitions | CPUC Reportable, fire size >10 acre |  | PG&E | 2026 | 2 | 0
1020000120 | Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 2 |  |  |  | Number of ignitions | CPUC Reportable, fire size >10 acre |  | PG&E | 2026 | 2 | 0
1020000121 | Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 2 |  |  |  | Number of ignitions | CPUC Reportable, fire size >10 acre |  | PG&E | 2026 | 2 | 0
1020000122 | Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 2 |  |  |  | Number of ignitions | CPUC Reportable, fire size >10 acre |  | PG&E | 2026 | 2 | 0
1020000123 | Number of utility-related ignitions | Number of ignitions | RFW only | HFTD Tier 3 |  |  |  | Number of ignitions | CPUC Reportable, fire size >10 acre |  | PG&E | 2026 | 2 | 0
1020000124 | Number of utility-related ignitions | Number of ignitions | HWW only | HFTD Tier 3 |  |  |  | Number of ignitions | CPUC Reportable, fire size >10 acre |  | PG&E | 2026 | 2 | 0
1020000125 | Number of utility-related ignitions | Number of ignitions | HWW & RFW | HFTD Tier 3 |  |  |  | Number of ignitions | CPUC Reportable, fire size >10 acre |  | PG&E | 2026 | 2 | 0
1020000126 | Number of utility-related ignitions | Number of ignitions | Neither | HFTD Tier 3 |  |  |  | Number of ignitions | CPUC Reportable, fire size >10 acre |  | PG&E | 2026 | 2 | 0
1020000127 | Number of utility-related ignitions | Number of ignitions | RFW only | Non-HFTD |  |  |  | Number of ignitions | CPUC Reportable, fire size >10 acre |  | PG&E | 2026 | 2 | 3
1020000128 | Number of utility-related ignitions | Number of ignitions | HWW only | Non-HFTD |  |  |  | Number of ignitions | CPUC Reportable, fire size >10 acre |  | PG&E | 2026 | 2 | 0
1020000129 | Number of utility-related ignitions | Number of ignitions | HWW & RFW | Non-HFTD |  |  |  | Number of ignitions | CPUC Reportable, fire size >10 acre |  | PG&E | 2026 | 2 | 0
1020000130 | Number of utility-related ignitions | Number of ignitions | Neither | Non-HFTD |  |  |  | Number of ignitions | CPUC Reportable, fire size >10 acre |  | PG&E | 2026 | 2 | 9
1020000131 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000132 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000133 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000134 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PG&E | 2026 | 2 | 269827
1020000135 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000136 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | The aerial program, which includes drone inspections, described in PG&E's WMP is represented in Table 2 in the rows for "Detailed inspection, subcategory 'Aerial". |  | PG&E | 2026 | 2 | 62209
1020000137 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000138 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | PG&E interprets "Other Inspection Method" as Detailed Ground Inspections. |  | PG&E | 2026 | 2 | 37051
1020000139 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000140 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000141 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000142 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000143 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000144 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000145 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000146 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | PG&E | 2026 | 2 | 10118.5125
1020000147 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000148 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PG&E | 2026 | 2 | 2332.8375
1020000149 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000150 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility | PG&E interprets "Other Inspection Method" as Detailed Ground Inspections. |  | PG&E | 2026 | 2 | 1389.4125
1020000151 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000152 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000153 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000154 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000155 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000156 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000157 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000158 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 11
1020000159 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000160 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 116
1020000161 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000162 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 48
1020000163 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000164 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000165 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000166 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 518
1020000167 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000168 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000169 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000170 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 24
1020000171 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000172 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 1962
1020000173 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000174 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 454
1020000175 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000176 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000177 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000178 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 650
1020000179 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000180 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000181 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000182 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 0
1020000183 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000184 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 190
1020000185 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000186 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 54
1020000187 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000188 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000189 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000190 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 62
1020000191 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000192 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000193 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000194 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PG&E | 2026 | 2 | 123707
1020000195 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000196 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | The aerial program, which includes drone inspections, described in PG&E's WMP is represented in Table 2 in the rows for "Detailed inspection, subcategory 'Aerial". |  | PG&E | 2026 | 2 | 9914
1020000197 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000198 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | PG&E interprets "Other Inspection Method" as Detailed Ground Inspections. |  | PG&E | 2026 | 2 | 3317
1020000199 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000200 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000201 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000202 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000203 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000204 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000205 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000206 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | PG&E | 2026 | 2 | 4639.0125
1020000207 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000208 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PG&E | 2026 | 2 | 371.775
1020000209 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000210 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility | PG&E interprets "Other Inspection Method" as Detailed Ground Inspections. |  | PG&E | 2026 | 2 | 124.3875
1020000211 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000212 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000213 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000214 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000215 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000216 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000217 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000218 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 2
1020000219 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000220 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 26
1020000221 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000222 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 7
1020000223 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000224 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000225 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000226 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 278
1020000227 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000228 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000229 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000230 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 11
1020000231 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000232 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 1478
1020000233 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000234 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 138
1020000235 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000236 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000237 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000238 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 509
1020000239 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000240 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000241 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000242 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 0
1020000243 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000244 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 350
1020000245 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000246 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 45
1020000247 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000248 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000249 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000250 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 23
1020000251 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000252 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000253 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000254 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PG&E | 2026 | 2 | 784155
1020000255 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000256 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | The aerial program, which includes drone inspections, described in PG&E's WMP is represented in Table 2 in the rows for "Detailed inspection, subcategory 'Aerial". |  | PG&E | 2026 | 2 | 1528
1020000257 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000258 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility | PG&E interprets "Other Inspection Method" as Detailed Ground Inspections. |  | PG&E | 2026 | 2 | 160511
1020000259 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000260 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000261 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000262 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000263 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000264 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000265 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000266 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | PG&E | 2026 | 2 | 29405.8125
1020000267 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000268 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PG&E | 2026 | 2 | 57.3
1020000269 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000270 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | PG&E | 2026 | 2 | 6019.1625
1020000271 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000272 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000273 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000274 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Distribution | Other Inspection | Other | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000275 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000276 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000277 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000278 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 113
1020000279 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000280 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 26
1020000281 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000282 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 785
1020000283 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000284 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000285 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000286 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 3820
1020000287 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000288 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000289 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000290 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 197
1020000291 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000292 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 1654
1020000293 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000294 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 3013
1020000295 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000296 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000297 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000298 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 3196
1020000299 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000300 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000301 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000302 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 0
1020000303 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000304 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 191
1020000305 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000306 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 98
1020000307 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000308 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000309 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000310 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Distribution | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 428
1020000311 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000312 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000313 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000314 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PG&E | 2026 | 2 | 20654
1020000315 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000316 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PG&E | 2026 | 2 | 19537
1020000317 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000318 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PG&E | 2026 | 2 | 5050
1020000319 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000320 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000321 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000322 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000323 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000324 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000325 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000326 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | PG&E | 2026 | 2 | 2271.94
1020000327 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000328 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PG&E | 2026 | 2 | 2149.07
1020000329 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000330 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | PG&E | 2026 | 2 | 555.5
1020000331 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000332 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000333 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000334 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000335 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000336 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 1
1020000337 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000338 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 5
1020000339 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000340 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 3
1020000341 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000342 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 6
1020000343 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000344 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000345 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000346 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 6
1020000347 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000348 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 2
1020000349 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000350 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 12
1020000351 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000352 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 1485
1020000353 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000354 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 210
1020000355 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000356 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000357 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000358 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 51
1020000359 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000360 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 0
1020000361 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000362 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 0
1020000363 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000364 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 782
1020000365 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000366 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 98
1020000367 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000368 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000369 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000370 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 19
1020000371 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000372 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000373 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000374 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PG&E | 2026 | 2 | 14205
1020000375 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000376 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PG&E | 2026 | 2 | 4339
1020000377 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000378 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PG&E | 2026 | 2 | 2496
1020000379 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000380 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000381 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000382 | Grid condition findings from inspection | Number of assets inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000383 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000384 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000385 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000386 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | PG&E | 2026 | 2 | 1562.55
1020000387 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000388 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PG&E | 2026 | 2 | 477.29
1020000389 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000390 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | PG&E | 2026 | 2 | 274.56
1020000391 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000392 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000393 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000394 | Grid condition findings from inspection | Number of circuit miles inspected |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000395 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000396 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 0
1020000397 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000398 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 0
1020000399 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000400 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 1
1020000401 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000402 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 0
1020000403 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000404 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000405 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000406 | Grid condition findings from inspection | Level 1 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 1
1020000407 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000408 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 0
1020000409 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000410 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 7
1020000411 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000412 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 227
1020000413 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000414 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 47
1020000415 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000416 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000417 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000418 | Grid condition findings from inspection | Level 2 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 14
1020000419 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000420 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 0
1020000421 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000422 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 1
1020000423 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000424 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 131
1020000425 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000426 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 43
1020000427 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000428 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000429 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000430 | Grid condition findings from inspection | Level 3 findings |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 2
1020000431 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000432 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000433 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000434 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PG&E | 2026 | 2 | 21124
1020000435 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000436 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PG&E | 2026 | 2 | 3260
1020000437 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000438 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  |  | PG&E | 2026 | 2 | 3816
1020000439 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000440 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000441 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000442 | Grid condition findings from inspection | Number of assets inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of assets / structures (such as poles, transformers, etc.) inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000443 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000444 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000445 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000446 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of circuit miles inspected by the utility |  |  | PG&E | 2026 | 2 | 2323.64
1020000447 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000448 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of circuit miles inspected by the utility |  |  | PG&E | 2026 | 2 | 358.6
1020000449 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000450 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of circuit miles inspected by the utility |  |  | PG&E | 2026 | 2 | 419.76
1020000451 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Drone | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000452 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000453 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000454 | Grid condition findings from inspection | Number of circuit miles inspected |  | Non-HFTD | Transmission | Other Inspection | Other | # of circuit miles inspected by the utility |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000455 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000456 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 2
1020000457 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000458 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 34
1020000459 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000460 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 0
1020000461 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000462 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 4
1020000463 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000464 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000465 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000466 | Grid condition findings from inspection | Level 1 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 35
1020000467 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000468 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 28
1020000469 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000470 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 37
1020000471 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000472 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 157
1020000473 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000474 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 271
1020000475 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000476 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000477 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000478 | Grid condition findings from inspection | Level 2 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 216
1020000479 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000480 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 2
1020000481 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000482 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 0
1020000483 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000484 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 137
1020000485 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000486 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 164
1020000487 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Drone | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000488 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000489 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of findings from these asset inspections |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000490 | Grid condition findings from inspection | Level 3 findings |  | Non-HFTD | Transmission | Other Inspection | Other | # of findings from these asset inspections |  |  | PG&E | 2026 | 2 | 20
1020000491 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000492 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000493 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000494 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 11
1020000495 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000496 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 114
1020000497 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000498 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 46
1020000499 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000500 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000501 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000502 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 510
1020000503 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000504 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000505 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000506 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 35
1020000507 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000508 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 7518
1020000509 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000510 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 5688
1020000511 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000512 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000513 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000514 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 3877
1020000515 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000516 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000517 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000518 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 3
1020000519 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000520 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 125
1020000521 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000522 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 1439
1020000523 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000524 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000525 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000526 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 678
1020000527 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000528 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000529 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000530 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 2
1020000531 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000532 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 26
1020000533 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000534 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 7
1020000535 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000536 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000537 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000538 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 273
1020000539 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000540 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000541 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000542 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 14
1020000543 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000544 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 5430
1020000545 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000546 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 1370
1020000547 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000548 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000549 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000550 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 2130
1020000551 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000552 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000553 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000554 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 0
1020000555 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000556 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 54
1020000557 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000558 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 273
1020000559 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000560 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000561 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000562 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 171
1020000563 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000564 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000565 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000566 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 114
1020000567 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000568 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 26
1020000569 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000570 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 758
1020000571 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000572 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000573 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000574 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 3767
1020000575 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000576 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000577 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000578 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 256
1020000579 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000580 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 715
1020000581 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000582 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 7802
1020000583 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000584 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000585 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000586 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 4244
1020000587 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000588 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000589 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000590 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 5
1020000591 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000592 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 30
1020000593 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000594 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 6283
1020000595 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000596 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000597 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Distribution Inspections. | PG&E | 2026 | 2
1020000598 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Distribution | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 1347
1020000599 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000600 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 1
1020000601 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000602 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 4
1020000603 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000604 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 3
1020000605 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000606 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 6
1020000607 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000608 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000609 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000610 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 6
1020000611 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000612 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 6
1020000613 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000614 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 6
1020000615 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000616 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 370
1020000617 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000618 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 110
1020000619 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000620 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000621 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000622 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 80
1020000623 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000624 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 0
1020000625 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000626 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 0
1020000627 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000628 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 205
1020000629 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000630 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 55
1020000631 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000632 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000633 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000634 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 2 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 14
1020000635 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000636 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 0
1020000637 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000638 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 0
1020000639 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000640 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 1
1020000641 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000642 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 0
1020000643 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000644 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000645 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000646 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 1
1020000647 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000648 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 2
1020000649 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000650 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 1
1020000651 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000652 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 54
1020000653 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000654 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 14
1020000655 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000656 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000657 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000658 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 19
1020000659 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000660 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 0
1020000661 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000662 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 0
1020000663 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000664 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 70
1020000665 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000666 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 11
1020000667 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000668 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000669 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000670 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | HFTD Tier 3 | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 2
1020000671 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000672 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 3
1020000673 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000674 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 33
1020000675 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000676 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 0
1020000677 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000678 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 4
1020000679 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000680 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000681 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000682 | Grid condition fixes in response to inspection findings | Level 1 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 31
1020000683 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000684 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 51
1020000685 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000686 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 33
1020000687 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000688 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 1796
1020000689 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000690 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 830
1020000691 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000692 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000693 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000694 | Grid condition fixes in response to inspection findings | Level 2 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 450
1020000695 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000696 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 7
1020000697 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000698 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Patrol Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 0
1020000699 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000700 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Aerial | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 534
1020000701 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000702 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Detailed Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 257
1020000703 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Drone | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000704 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Aerial | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000705 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | LiDAR | # of asset inspection findings which have been fixed |  | These metrics are not applicable for the Transmission Inspections. | PG&E | 2026 | 2
1020000706 | Grid condition fixes in response to inspection findings | Level 3 findings fixed |  | Non-HFTD | Transmission | Other Inspection | Other | # of asset inspection findings which have been fixed |  |  | PG&E | 2026 | 2 | 115
1020000707 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000708 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000709 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | PG&E | 2026 | 2 | 0
1020000710 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2026 | 2 | 96073
1020000711 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000712 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | PG&E | 2026 | 2 | 0
1020000713 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000714 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2026 | 2 | 8621
1020000715 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000716 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000717 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000718 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2026 | 2 | 514
1020000719 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000720 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000721 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | PG&E | 2026 | 2 | 0
1020000722 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2026 | 2 | 6493
1020000723 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000724 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000725 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | PG&E | 2026 | 2 | 0
1020000726 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2026 | 2 | 73794
1020000727 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000728 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | PG&E | 2026 | 2 | 0
1020000729 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000730 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2026 | 2 | 11550
1020000731 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000732 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000733 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000734 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2026 | 2 | 829
1020000735 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000736 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000737 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | PG&E | 2026 | 2 | 0
1020000738 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2026 | 2 | 4668
1020000739 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000740 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000741 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | PG&E | 2026 | 2 | 0
1020000742 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2026 | 2 | 133344
1020000743 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000744 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  |  | PG&E | 2026 | 2 | 0
1020000745 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000746 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2026 | 2 | 1053
1020000747 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000748 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000749 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000750 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2026 | 2 | 90
1020000751 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000752 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000753 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | PG&E | 2026 | 2 | 0
1020000754 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Distribution | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2026 | 2 | 8309
1020000755 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000756 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000757 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | The count provided in the Q1 is for the calendar year. |  | PG&E | 2026 | 2 | 1685297
1020000758 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | PG&E | 2026 | 2 | 6548
1020000759 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000760 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000761 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000762 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000763 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000764 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000765 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000766 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000767 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000768 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000769 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | The count provided in the Q1 is for the calendar year. |  | PG&E | 2026 | 2 | 1
1020000770 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 2 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2026 | 2 | 0
1020000771 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000772 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000773 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | The count provided in the Q1 is for the calendar year. |  | PG&E | 2026 | 2 | 598014
1020000774 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | PG&E | 2026 | 2 | 5294
1020000775 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000776 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000777 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000778 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000779 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000780 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000781 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000782 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000783 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000784 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000785 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | The count provided in the Q1 is for the calendar year. |  | PG&E | 2026 | 2 | 0
1020000786 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | HFTD Tier 3 | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2026 | 2 | 0
1020000787 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000788 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000789 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | The count provided in the Q1 is for the calendar year. |  | PG&E | 2026 | 2 | 4679393
1020000790 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  |  | PG&E | 2026 | 2 | 12775
1020000791 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000792 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000793 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000794 | Vegetation clearance findings from inspection | Number of trees inspected for vegetation compliance |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees inspected for vegetation compliance based on GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000795 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000796 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000797 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000798 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Non-Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of non-routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000799 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Drone | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000800 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Aerial | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. |  | PG&E does not perform this inspection type by this inspection method | PG&E | 2026 | 2
1020000801 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | LiDAR | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | The count provided in the Q1 is for the calendar year. |  | PG&E | 2026 | 2 | 17
1020000802 | Vegetation clearance findings from inspection | Number of trees inspected where at least some vegetation was found in non-compliant condition |  | Non-HFTD | Transmission | Routine | Other | # of trees found to be non-compliant with GO 95, Rule 35, and PRC 4293 at the time of routine inspection. | Inspection Method "Other" includes ground patrols. |  | PG&E | 2026 | 2 | 4
1020000803 | Community outreach metrics | % of customers notified of evacuation in evacuation zone of a utility-ignited wildfire | [5 empty] | Percentage of customers notified of evacuation |  | PG&E does not issue wildfire evacuation notices to customers and does not maintain metrics on the number of customers in an evacuation zone or the number of customers notified of evacuation orders. Because of this, PG&E is unable to report on evacuation related requirements in this table. PG&E anticipates this to be a recurring challenge going forward. | PG&E | 2026 | 2

## Table 3
METRIC NUMBER | METRIC | DEFINITION | PURPOSE | ASSUMPTIONS MADE TO CONNECT METRIC TO PURPOSE | THIRD-PARTY VALIDATION (IF ANY) | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1030000000 | Weather-Normalized CPUC-Reportable Fire Ignitions Rate in R3+ Conditions (Rolling 365 days) | The metric measures the rate of Distribution and Transmission ignition incidents occurring in high-risk weather conditions normalized by 100,000 circuit miles and meeting the following criteria: Occur within PG&E’s High Fire Threat District (HFTD) and High Fire Risk Area (HFRA) Occur in high-risk weather conditions defined as meeting the criteria of Fire Potential Index (FPI) of R3, R4, R5 or R5+ Reportable to the CPUC per Decision 14-02-015. A reportable fire incident includes all the following: 1) Ignition is associated with PG&E’s electric assets, 2) something other than PG&E facilities burned, and 3) the resulting fire travelled more than one meter from the ignition point. The metric is reported as a YTD indicator for a rolling 365-day period. In case of a leap year, the metric will be reported for a rolling 366-day period. | This lagging metric enabled PG&E to assess its performance relative to the scale of the infrastructure and elevated risk conditions and directly supports the overarching goal of reducing wildfire risk. | (1) The metric focuses on ignitions occurring in elevated wildfire risk conditions as measured by the FPI of R3 and above; historical ignitions occurring in R3+ conditions result in the most consequential fires; (2) The rolling metric addresses the issue of considerable swings during the first half of the year when the number of R3 days is low (often 0) | The metric performance is validated quarterly by PG&E’s Internal Audit. | Count of CPUC Reportable Ignitions in HFTD or HFRA occurring in high-risk weather conditions *100,000 / cumulative count of circuit miles in Fire Index Areas (FIA) exposed to high-risk weather conditions, calculated for a rolling 365-day period. | *100,000 / (cumulative count of circuit miles in Fire Index Areas (FIA) exposed to high-risk weather conditions) = 30*100,000 / 3,165,502 = 0.95. |  | PG&E | 2026 | 2 | 0.95

## Table 4
METRIC NUMBER | METRIC TYPE | METRIC NAME | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1040000000 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | Red flag warning overhead circuit mile days |  |  | PG&E | 2026 | 2 | 491.2832
1040000001 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | Red flag warning overhead circuit mile days |  |  | PG&E | 2026 | 2 | 205.2161
1040000002 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Distribution | Non-HFTD | Red flag warning overhead circuit mile days |  |  | PG&E | 2026 | 2 | 52447.7102
1040000003 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | Red flag warning overhead circuit mile days |  |  | PG&E | 2026 | 2 | 182.5805
1040000004 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | Red flag warning overhead circuit mile days |  |  | PG&E | 2026 | 2 | 112.4813
1040000005 | Red flag warning only overhead circuit mile days | Red Flag Warning Only overhead circuit mile days | Transmission | Non-HFTD | Red flag warning overhead circuit mile days |  |  | PG&E | 2026 | 2 | 11237.9861
1040000006 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  |  | PG&E | 2026 | 2 | 90.8633
1040000007 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  |  | PG&E | 2026 | 2 | 33.9237
1040000008 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Distribution | Non-HFTD | High Wind Warning overhead circuit mile days |  |  | PG&E | 2026 | 2 | 61.3041
1040000009 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 2 | High Wind Warning overhead circuit mile days |  |  | PG&E | 2026 | 2 | 28.308
1040000010 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | HFTD Tier 3 | High Wind Warning overhead circuit mile days |  |  | PG&E | 2026 | 2 | 9.543
1040000011 | Wind condition overhead circuit mile days | High Wind Warning Only overhead circuit mile days | Transmission | Non-HFTD | High Wind Warning overhead circuit mile days |  |  | PG&E | 2026 | 2 | 7.334
1040000012 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  |  | PG&E | 2026 | 2 | 582.1465
1040000013 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  |  | PG&E | 2026 | 2 | 239.1399
1040000014 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Distribution | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  |  | PG&E | 2026 | 2 | 52509.0143
1040000015 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 2 | High wind warning and red flag warning overhead circuit mile days |  |  | PG&E | 2026 | 2 | 210.8885
1040000016 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | HFTD Tier 3 | High wind warning and red flag warning overhead circuit mile days |  |  | PG&E | 2026 | 2 | 122.0243
1040000017 | Wind condition and Red flag warning overhead circuit mile days | High Wind Warning and Red Flag Warning overhead circuit mile days | Transmission | Non-HFTD | High wind warning and red flag warning overhead circuit mile days |  |  | PG&E | 2026 | 2 | 11245.3201
1040000018 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | PG&E | 2026 | 2 | 336877.6588
1040000019 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | PG&E | 2026 | 2 | 86985.382
1040000020 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Distribution | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | PG&E | 2026 | 2 | 85147.9569
1040000021 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 2 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | PG&E | 2026 | 2 | 73426.9388
1040000022 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | HFTD Tier 3 | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | PG&E | 2026 | 2 | 16328.8267
1040000023 | Fire potential index overhead circuit mile days | Fire potential index circuit mile days | Transmission | Non-HFTD | High fire potential index (as defined by the utility in its WMP) overhead circuit mile days |  |  | PG&E | 2026 | 2 | 31162.1202

## Table 5
METRIC NUMBER | METRIC TYPE | METRIC NAME | RISK EVENT DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1050000000 | Fire | Wire down event | Fire | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000001 | Fire | Wire down event | Fire | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000002 | Fire | Wire down event | Fire | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000003 | Fire | Wire down event | Fire | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000004 | Fire | Wire down event | Fire | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000005 | Fire | Wire down event | Fire | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000006 | Contact from object | Wire down event | Animal contact | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 17
1050000007 | Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000008 | Contact from object | Wire down event | Animal contact | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000009 | Contact from object | Wire down event | Animal contact | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000010 | Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000011 | Contact from object | Wire down event | Animal contact | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000012 | Contact from object | Wire down event | Balloon contact | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 7
1050000013 | Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000014 | Contact from object | Wire down event | Balloon contact | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000015 | Contact from object | Wire down event | Balloon contact | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000016 | Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000017 | Contact from object | Wire down event | Balloon contact | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000018 | Contact from object | Wire down event | Land vehicle contact | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 97
1050000019 | Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 11
1050000020 | Contact from object | Wire down event | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 4
1050000021 | Contact from object | Wire down event | Land vehicle contact | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000022 | Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000023 | Contact from object | Wire down event | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000024 | Contact from object | Wire down event | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000025 | Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000026 | Contact from object | Wire down event | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000027 | Contact from object | Wire down event | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000028 | Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000029 | Contact from object | Wire down event | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000030 | Contact from object | Wire down event | 3rd party contact | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 8
1050000031 | Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 2
1050000032 | Contact from object | Wire down event | 3rd party contact | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 2
1050000033 | Contact from object | Wire down event | 3rd party contact | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000034 | Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000035 | Contact from object | Wire down event | 3rd party contact | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000036 | Contact from object | Wire down event | Other (contact from object) | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 3
1050000037 | Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000038 | Contact from object | Wire down event | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000039 | Contact from object | Wire down event | Other (contact from object) | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000040 | Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000041 | Contact from object | Wire down event | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000042 | Contact from object | Wire down event | Unknown (contact from object) | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000043 | Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000044 | Contact from object | Wire down event | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000045 | Contact from object | Wire down event | Unknown (contact from object) | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000046 | Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000047 | Contact from object | Wire down event | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000048 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000049 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000050 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000051 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000052 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000053 | Vegetation contact | Wire down event | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000054 | Vegetation contact | Wire down event | Grow-in | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000055 | Vegetation contact | Wire down event | Grow-in | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000056 | Vegetation contact | Wire down event | Grow-in | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000057 | Vegetation contact | Wire down event | Grow-in | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000058 | Vegetation contact | Wire down event | Grow-in | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000059 | Vegetation contact | Wire down event | Grow-in | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000060 | Vegetation contact | Wire down event | Blow-in | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 59
1050000061 | Vegetation contact | Wire down event | Blow-in | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 24
1050000062 | Vegetation contact | Wire down event | Blow-in | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 29
1050000063 | Vegetation contact | Wire down event | Blow-in | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000064 | Vegetation contact | Wire down event | Blow-in | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000065 | Vegetation contact | Wire down event | Blow-in | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000066 | Vegetation contact | Wire down event | Trunk failure | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000067 | Vegetation contact | Wire down event | Trunk failure | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000068 | Vegetation contact | Wire down event | Trunk failure | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000069 | Vegetation contact | Wire down event | Trunk failure | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000070 | Vegetation contact | Wire down event | Trunk failure | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000071 | Vegetation contact | Wire down event | Trunk failure | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000072 | Vegetation contact | Wire down event | Root failure | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000073 | Vegetation contact | Wire down event | Root failure | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000074 | Vegetation contact | Wire down event | Root failure | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000075 | Vegetation contact | Wire down event | Root failure | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000076 | Vegetation contact | Wire down event | Root failure | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000077 | Vegetation contact | Wire down event | Root failure | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000078 | Vegetation contact | Wire down event | Detached frond / limb / bark | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 29
1050000079 | Vegetation contact | Wire down event | Detached frond / limb / bark | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 7
1050000080 | Vegetation contact | Wire down event | Detached frond / limb / bark | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 9
1050000081 | Vegetation contact | Wire down event | Detached frond / limb / bark | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000082 | Vegetation contact | Wire down event | Detached frond / limb / bark | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000083 | Vegetation contact | Wire down event | Detached frond / limb / bark | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000084 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000085 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000086 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000087 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000088 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000089 | Equipment / facility failure or damage | Wire down event | Anchor / guy | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000090 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000091 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000092 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000093 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000094 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000095 | Equipment / facility failure or damage | Wire down event | Capacitor bank | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000096 | Equipment / facility failure or damage | Wire down event | Conductor | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 88
1050000097 | Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 6
1050000098 | Equipment / facility failure or damage | Wire down event | Conductor | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000099 | Equipment / facility failure or damage | Wire down event | Conductor | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000100 | Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000101 | Equipment / facility failure or damage | Wire down event | Conductor | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000102 | Equipment / facility failure or damage | Wire down event | Connection device | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000103 | Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000104 | Equipment / facility failure or damage | Wire down event | Connection device | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000105 | Equipment / facility failure or damage | Wire down event | Connection device | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000106 | Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000107 | Equipment / facility failure or damage | Wire down event | Connection device | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000108 | Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 8
1050000109 | Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000110 | Equipment / facility failure or damage | Wire down event | Crossarm | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000111 | Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000112 | Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000113 | Equipment / facility failure or damage | Wire down event | Crossarm | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000114 | Equipment / facility failure or damage | Wire down event | Fuse | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000115 | Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000116 | Equipment / facility failure or damage | Wire down event | Fuse | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000117 | Equipment / facility failure or damage | Wire down event | Fuse | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000118 | Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000119 | Equipment / facility failure or damage | Wire down event | Fuse | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000120 | Equipment / facility failure or damage | Wire down event | Cutout | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000121 | Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000122 | Equipment / facility failure or damage | Wire down event | Cutout | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000123 | Equipment / facility failure or damage | Wire down event | Cutout | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000124 | Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000125 | Equipment / facility failure or damage | Wire down event | Cutout | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000126 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000127 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000128 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000129 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000130 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000131 | Equipment / facility failure or damage | Wire down event | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000132 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000133 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000134 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000135 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000136 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000137 | Equipment / facility failure or damage | Wire down event | Lightning arrester | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000138 | Equipment / facility failure or damage | Wire down event | Pole | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 17
1050000139 | Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000140 | Equipment / facility failure or damage | Wire down event | Pole | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000141 | Equipment / facility failure or damage | Wire down event | Pole | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000142 | Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000143 | Equipment / facility failure or damage | Wire down event | Pole | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000144 | Equipment / facility failure or damage | Wire down event | Recloser | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000145 | Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000146 | Equipment / facility failure or damage | Wire down event | Recloser | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000147 | Equipment / facility failure or damage | Wire down event | Recloser | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000148 | Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000149 | Equipment / facility failure or damage | Wire down event | Recloser | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000150 | Equipment / facility failure or damage | Wire down event | Relay | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000151 | Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000152 | Equipment / facility failure or damage | Wire down event | Relay | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000153 | Equipment / facility failure or damage | Wire down event | Relay | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000154 | Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000155 | Equipment / facility failure or damage | Wire down event | Relay | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000156 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000157 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000158 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000159 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000160 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000161 | Equipment / facility failure or damage | Wire down event | Sectionalizer | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000162 | Equipment / facility failure or damage | Wire down event | Splice | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 30
1050000163 | Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 3
1050000164 | Equipment / facility failure or damage | Wire down event | Splice | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000165 | Equipment / facility failure or damage | Wire down event | Splice | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000166 | Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000167 | Equipment / facility failure or damage | Wire down event | Splice | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000168 | Equipment / facility failure or damage | Wire down event | Switch | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000169 | Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000170 | Equipment / facility failure or damage | Wire down event | Switch | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000171 | Equipment / facility failure or damage | Wire down event | Switch | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000172 | Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000173 | Equipment / facility failure or damage | Wire down event | Switch | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000174 | Equipment / facility failure or damage | Wire down event | Tap | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000175 | Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000176 | Equipment / facility failure or damage | Wire down event | Tap | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000177 | Equipment / facility failure or damage | Wire down event | Tap | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000178 | Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000179 | Equipment / facility failure or damage | Wire down event | Tap | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000180 | Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000181 | Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000182 | Equipment / facility failure or damage | Wire down event | Tie wire | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000183 | Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000184 | Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000185 | Equipment / facility failure or damage | Wire down event | Tie wire | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000186 | Equipment / facility failure or damage | Wire down event | Transformer | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000187 | Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000188 | Equipment / facility failure or damage | Wire down event | Transformer | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000189 | Equipment / facility failure or damage | Wire down event | Transformer | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000190 | Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000191 | Equipment / facility failure or damage | Wire down event | Transformer | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000192 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000193 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000194 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000195 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000196 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000197 | Equipment / facility failure or damage | Wire down event | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000198 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000199 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000200 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000201 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000202 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000203 | Equipment / facility failure or damage | Wire down event | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000204 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000205 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000206 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000207 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000208 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000209 | Equipment / facility failure or damage | Wire down event | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000210 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000211 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000212 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000213 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000214 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000215 | Wire-to-wire contact | Wire down event | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000216 | Contamination | Wire down event | Contamination | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000217 | Contamination | Wire down event | Contamination | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000218 | Contamination | Wire down event | Contamination | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000219 | Contamination | Wire down event | Contamination | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000220 | Contamination | Wire down event | Contamination | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000221 | Contamination | Wire down event | Contamination | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000222 | Vandalism / theft | Wire down event | Vandalism / theft | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 4
1050000223 | Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000224 | Vandalism / theft | Wire down event | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000225 | Vandalism / theft | Wire down event | Vandalism / theft | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000226 | Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000227 | Vandalism / theft | Wire down event | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000228 | Lightning | Wire down event | Lightning | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 10
1050000229 | Lightning | Wire down event | Lightning | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 2
1050000230 | Lightning | Wire down event | Lightning | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000231 | Lightning | Wire down event | Lightning | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000232 | Lightning | Wire down event | Lightning | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000233 | Lightning | Wire down event | Lightning | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000234 | Unknown | Wire down event | Unknown (unknown) | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 40
1050000235 | Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 24
1050000236 | Unknown | Wire down event | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 12
1050000237 | Unknown | Wire down event | Unknown (unknown) | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000238 | Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000239 | Unknown | Wire down event | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000240 | Other | Wire down event | Other (other) | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 5
1050000241 | Other | Wire down event | Other (other) | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000242 | Other | Wire down event | Other (other) | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000243 | Other | Wire down event | Other (other) | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000244 | Other | Wire down event | Other (other) | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000245 | Other | Wire down event | Other (other) | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000246 | Dig-in | Unplanned Outage | Dig-in | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 25
1050000247 | Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 5
1050000248 | Dig-in | Unplanned Outage | Dig-in | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000249 | Dig-in | Unplanned Outage | Dig-in | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000250 | Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000251 | Dig-in | Unplanned Outage | Dig-in | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000252 | Fire | Unplanned Outage | Fire | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 28
1050000253 | Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 6
1050000254 | Fire | Unplanned Outage | Fire | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000255 | Fire | Unplanned Outage | Fire | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 4
1050000256 | Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000257 | Fire | Unplanned Outage | Fire | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000258 | Contact from object | Unplanned Outage | Animal contact | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 632
1050000259 | Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 75
1050000260 | Contact from object | Unplanned Outage | Animal contact | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 15
1050000261 | Contact from object | Unplanned Outage | Animal contact | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 20
1050000262 | Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 5
1050000263 | Contact from object | Unplanned Outage | Animal contact | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000264 | Contact from object | Unplanned Outage | Balloon contact | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 123
1050000265 | Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000266 | Contact from object | Unplanned Outage | Balloon contact | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000267 | Contact from object | Unplanned Outage | Balloon contact | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000268 | Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000269 | Contact from object | Unplanned Outage | Balloon contact | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000270 | Contact from object | Unplanned Outage | Land vehicle contact | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 357
1050000271 | Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 36
1050000272 | Contact from object | Unplanned Outage | Land vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 15
1050000273 | Contact from object | Unplanned Outage | Land vehicle contact | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 10
1050000274 | Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000275 | Contact from object | Unplanned Outage | Land vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000276 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000277 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000278 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000279 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000280 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000281 | Contact from object | Unplanned Outage | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000282 | Contact from object | Unplanned Outage | 3rd party contact | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 25
1050000283 | Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 8
1050000284 | Contact from object | Unplanned Outage | 3rd party contact | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 7
1050000285 | Contact from object | Unplanned Outage | 3rd party contact | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 20
1050000286 | Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000287 | Contact from object | Unplanned Outage | 3rd party contact | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000288 | Contact from object | Unplanned Outage | Other (contact from object) | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 55
1050000289 | Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 3
1050000290 | Contact from object | Unplanned Outage | Other (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 2
1050000291 | Contact from object | Unplanned Outage | Other (contact from object) | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000292 | Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000293 | Contact from object | Unplanned Outage | Other (contact from object) | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000294 | Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000295 | Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000296 | Contact from object | Unplanned Outage | Unknown (contact from object) | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000297 | Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000298 | Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000299 | Contact from object | Unplanned Outage | Unknown (contact from object) | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000300 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 6
1050000301 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000302 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000303 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000304 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000305 | Vegetation contact | Unplanned Outage | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000306 | Vegetation contact | Unplanned Outage | Grow-in | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 60
1050000307 | Vegetation contact | Unplanned Outage | Grow-in | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 4
1050000308 | Vegetation contact | Unplanned Outage | Grow-in | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 10
1050000309 | Vegetation contact | Unplanned Outage | Grow-in | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000310 | Vegetation contact | Unplanned Outage | Grow-in | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000311 | Vegetation contact | Unplanned Outage | Grow-in | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000312 | Vegetation contact | Unplanned Outage | Blow-in | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 119
1050000313 | Vegetation contact | Unplanned Outage | Blow-in | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 48
1050000314 | Vegetation contact | Unplanned Outage | Blow-in | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 52
1050000315 | Vegetation contact | Unplanned Outage | Blow-in | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000316 | Vegetation contact | Unplanned Outage | Blow-in | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000317 | Vegetation contact | Unplanned Outage | Blow-in | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000318 | Vegetation contact | Unplanned Outage | Trunk failure | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000319 | Vegetation contact | Unplanned Outage | Trunk failure | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000320 | Vegetation contact | Unplanned Outage | Trunk failure | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000321 | Vegetation contact | Unplanned Outage | Trunk failure | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000322 | Vegetation contact | Unplanned Outage | Trunk failure | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000323 | Vegetation contact | Unplanned Outage | Trunk failure | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000324 | Vegetation contact | Unplanned Outage | Root failure | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000325 | Vegetation contact | Unplanned Outage | Root failure | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000326 | Vegetation contact | Unplanned Outage | Root failure | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000327 | Vegetation contact | Unplanned Outage | Root failure | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000328 | Vegetation contact | Unplanned Outage | Root failure | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000329 | Vegetation contact | Unplanned Outage | Root failure | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000330 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 196
1050000331 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 27
1050000332 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 52
1050000333 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000334 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000335 | Vegetation contact | Unplanned Outage | Detached frond / limb / bark | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000336 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 9
1050000337 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000338 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000339 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000340 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000341 | Equipment / facility failure or damage | Unplanned Outage | Anchor / guy | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000342 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 10
1050000343 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000344 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000345 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000346 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000347 | Equipment / facility failure or damage | Unplanned Outage | Capacitor bank | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000348 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 611
1050000349 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 89
1050000350 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 32
1050000351 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 6
1050000352 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000353 | Equipment / facility failure or damage | Unplanned Outage | Conductor | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000354 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 142
1050000355 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 11
1050000356 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 6
1050000357 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000358 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000359 | Equipment / facility failure or damage | Unplanned Outage | Connection device | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000360 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 275
1050000361 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 40
1050000362 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 12
1050000363 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000364 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000365 | Equipment / facility failure or damage | Unplanned Outage | Crossarm | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000366 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 173
1050000367 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 9
1050000368 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 7
1050000369 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000370 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000371 | Equipment / facility failure or damage | Unplanned Outage | Fuse | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000372 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000373 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000374 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000375 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000376 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000377 | Equipment / facility failure or damage | Unplanned Outage | Cutout | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000378 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 56
1050000379 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 21
1050000380 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 11
1050000381 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 5
1050000382 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000383 | Equipment / facility failure or damage | Unplanned Outage | Insulator and bushing | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000384 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 18
1050000385 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 4
1050000386 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000387 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000388 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000389 | Equipment / facility failure or damage | Unplanned Outage | Lightning arrester | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000390 | Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 531
1050000391 | Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 83
1050000392 | Equipment / facility failure or damage | Unplanned Outage | Pole | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 31
1050000393 | Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 3
1050000394 | Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 2
1050000395 | Equipment / facility failure or damage | Unplanned Outage | Pole | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000396 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 18
1050000397 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 3
1050000398 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000399 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000400 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000401 | Equipment / facility failure or damage | Unplanned Outage | Recloser | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000402 | Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000403 | Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000404 | Equipment / facility failure or damage | Unplanned Outage | Relay | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000405 | Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 26
1050000406 | Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000407 | Equipment / facility failure or damage | Unplanned Outage | Relay | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000408 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000409 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000410 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000411 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000412 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000413 | Equipment / facility failure or damage | Unplanned Outage | Sectionalizer | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000414 | Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 138
1050000415 | Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 18
1050000416 | Equipment / facility failure or damage | Unplanned Outage | Splice | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 6
1050000417 | Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000418 | Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000419 | Equipment / facility failure or damage | Unplanned Outage | Splice | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000420 | Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 55
1050000421 | Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 3
1050000422 | Equipment / facility failure or damage | Unplanned Outage | Switch | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 2
1050000423 | Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 38
1050000424 | Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 4
1050000425 | Equipment / facility failure or damage | Unplanned Outage | Switch | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 3
1050000426 | Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000427 | Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000428 | Equipment / facility failure or damage | Unplanned Outage | Tap | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000429 | Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000430 | Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000431 | Equipment / facility failure or damage | Unplanned Outage | Tap | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000432 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000433 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000434 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000435 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000436 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000437 | Equipment / facility failure or damage | Unplanned Outage | Tie wire | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000438 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 1155
1050000439 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 196
1050000440 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 66
1050000441 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 2
1050000442 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000443 | Equipment / facility failure or damage | Unplanned Outage | Transformer | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000444 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 19
1050000445 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000446 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 2
1050000447 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000448 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000449 | Equipment / facility failure or damage | Unplanned Outage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000450 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000451 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000452 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000453 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000454 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000455 | Equipment / facility failure or damage | Unplanned Outage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000456 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 171
1050000457 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 14
1050000458 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 12
1050000459 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 10
1050000460 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000461 | Equipment / facility failure or damage | Unplanned Outage | Other (equipment failure) | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000462 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000463 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000464 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000465 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000466 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000467 | Wire-to-wire contact | Unplanned Outage | Wire-to-wire contact | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000468 | Contamination | Unplanned Outage | Contamination | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 11
1050000469 | Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000470 | Contamination | Unplanned Outage | Contamination | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000471 | Contamination | Unplanned Outage | Contamination | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000472 | Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000473 | Contamination | Unplanned Outage | Contamination | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000474 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 44
1050000475 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 3
1050000476 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 3
1050000477 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 3
1050000478 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000479 | Vandalism / theft | Unplanned Outage | Vandalism / theft | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000480 | Lightning | Unplanned Outage | Lightning | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 259
1050000481 | Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 129
1050000482 | Lightning | Unplanned Outage | Lightning | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 62
1050000483 | Lightning | Unplanned Outage | Lightning | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 37
1050000484 | Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 24
1050000485 | Lightning | Unplanned Outage | Lightning | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 5
1050000486 | Government agency request | Unplanned Outage | Government agency request | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000487 | Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000488 | Government agency request | Unplanned Outage | Government agency request | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000489 | Government agency request | Unplanned Outage | Government agency request | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000490 | Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000491 | Government agency request | Unplanned Outage | Government agency request | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000492 | Customer request | Unplanned Outage | Customer request | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000493 | Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000494 | Customer request | Unplanned Outage | Customer request | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000495 | Customer request | Unplanned Outage | Customer request | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 14
1050000496 | Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 1
1050000497 | Customer request | Unplanned Outage | Customer request | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 3
1050000498 | Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000499 | Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000500 | Emergency repairs | Unplanned Outage | Emergency repairs | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000501 | Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 5
1050000502 | Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000503 | Emergency repairs | Unplanned Outage | Emergency repairs | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 0
1050000504 | Unknown | Unplanned Outage | Unknown (unknown) | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 2906
1050000505 | Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 481
1050000506 | Unknown | Unplanned Outage | Unknown (unknown) | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 222
1050000507 | Unknown | Unplanned Outage | Unknown (unknown) | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 36
1050000508 | Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 30
1050000509 | Unknown | Unplanned Outage | Unknown (unknown) | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 3
1050000510 | Other | Unplanned Outage | Other (other) | Distribution | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 400
1050000511 | Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 102
1050000512 | Other | Unplanned Outage | Other (other) | Distribution | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 58
1050000513 | Other | Unplanned Outage | Other (other) | Transmission | Non-HFTD | # risk events |  |  | PG&E | 2026 | 2 | 30
1050000514 | Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 2 | # risk events |  |  | PG&E | 2026 | 2 | 7
1050000515 | Other | Unplanned Outage | Other (other) | Transmission | HFTD Tier 3 | # risk events |  |  | PG&E | 2026 | 2 | 1

## Table 6
METRIC NUMBER | METRIC TYPE | IGNITION DRIVER | LINE TYPE | HFTD TIER | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1060000000 | Dig-in | Dig-in | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000001 | Dig-in | Dig-in | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000002 | Dig-in | Dig-in | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000003 | Dig-in | Dig-in | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000004 | Dig-in | Dig-in | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000005 | Dig-in | Dig-in | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000006 | Contact from object | Animal contact | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 29
1060000007 | Contact from object | Animal contact | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000008 | Contact from object | Animal contact | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 1
1060000009 | Contact from object | Animal contact | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 4
1060000010 | Contact from object | Animal contact | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000011 | Contact from object | Animal contact | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000012 | Contact from object | Balloon contact | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 7
1060000013 | Contact from object | Balloon contact | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000014 | Contact from object | Balloon contact | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000015 | Contact from object | Balloon contact | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 1
1060000016 | Contact from object | Balloon contact | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000017 | Contact from object | Balloon contact | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000018 | Contact from object | Land vehicle contact | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 20
1060000019 | Contact from object | Land vehicle contact | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 1
1060000020 | Contact from object | Land vehicle contact | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 1
1060000021 | Contact from object | Land vehicle contact | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000022 | Contact from object | Land vehicle contact | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000023 | Contact from object | Land vehicle contact | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000024 | Contact from object | Aircraft vehicle contact | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 1
1060000025 | Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000026 | Contact from object | Aircraft vehicle contact | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000027 | Contact from object | Aircraft vehicle contact | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000028 | Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000029 | Contact from object | Aircraft vehicle contact | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000030 | Contact from object | 3rd party facility | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 3
1060000031 | Contact from object | 3rd party facility | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000032 | Contact from object | 3rd party facility | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000033 | Contact from object | 3rd party facility | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000034 | Contact from object | 3rd party facility | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000035 | Contact from object | 3rd party facility | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000036 | Contact from object | Unknown (contact from object) | Distribution | Non-HFTD | # ignitions | Ignitions caused by contact from an unidentified object would be included under the following: Metric Type: Contact from object, Ignition Driver: Other (contact from object) or Metric Type: Unknown, Ingition Driver: Unknown (unknown). |  | PG&E | 2026 | 2 | 0
1060000037 | Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 2 | # ignitions | Ignitions caused by contact from an unidentified object would be included under the following: Metric Type: Contact from object, Ignition Driver: Other (contact from object) or Metric Type: Unknown, Ingition Driver: Unknown (unknown). |  | PG&E | 2026 | 2 | 0
1060000038 | Contact from object | Unknown (contact from object) | Distribution | HFTD Tier 3 | # ignitions | Ignitions caused by contact from an unidentified object would be included under the following: Metric Type: Contact from object, Ignition Driver: Other (contact from object) or Metric Type: Unknown, Ingition Driver: Unknown (unknown). |  | PG&E | 2026 | 2 | 0
1060000039 | Contact from object | Unknown (contact from object) | Transmission | Non-HFTD | # ignitions | Ignitions caused by contact from an unidentified object would be included under the following: Metric Type: Contact from object, Ignition Driver: Other (contact from object) or Metric Type: Unknown, Ingition Driver: Unknown (unknown). |  | PG&E | 2026 | 2 | 0
1060000040 | Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 2 | # ignitions | Ignitions caused by contact from an unidentified object would be included under the following: Metric Type: Contact from object, Ignition Driver: Other (contact from object) or Metric Type: Unknown, Ingition Driver: Unknown (unknown). |  | PG&E | 2026 | 2 | 0
1060000041 | Contact from object | Unknown (contact from object) | Transmission | HFTD Tier 3 | # ignitions | Ignitions caused by contact from an unidentified object would be included under the following: Metric Type: Contact from object, Ignition Driver: Other (contact from object) or Metric Type: Unknown, Ingition Driver: Unknown (unknown). |  | PG&E | 2026 | 2 | 0
1060000042 | Contact from object | Other (contact from object) | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 4
1060000043 | Contact from object | Other (contact from object) | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000044 | Contact from object | Other (contact from object) | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000045 | Contact from object | Other (contact from object) | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 1
1060000046 | Contact from object | Other (contact from object) | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000047 | Contact from object | Other (contact from object) | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000048 | Vegetation contact | Uncategorized / other (vegetation contact) | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 17
1060000049 | Vegetation contact | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 1
1060000050 | Vegetation contact | Uncategorized / other (vegetation contact) | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 2
1060000051 | Vegetation contact | Uncategorized / other (vegetation contact) | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000052 | Vegetation contact | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000053 | Vegetation contact | Uncategorized / other (vegetation contact) | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000054 | Vegetation contact | Grow-in | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 4
1060000055 | Vegetation contact | Grow-in | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000056 | Vegetation contact | Grow-in | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000057 | Vegetation contact | Grow-in | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000058 | Vegetation contact | Grow-in | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000059 | Vegetation contact | Grow-in | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000060 | Vegetation contact | Blow-in | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000061 | Vegetation contact | Blow-in | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000062 | Vegetation contact | Blow-in | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000063 | Vegetation contact | Blow-in | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000064 | Vegetation contact | Blow-in | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000065 | Vegetation contact | Blow-in | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000066 | Vegetation contact | Trunk failure | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 4
1060000067 | Vegetation contact | Trunk failure | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 3
1060000068 | Vegetation contact | Trunk failure | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 1
1060000069 | Vegetation contact | Trunk failure | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000070 | Vegetation contact | Trunk failure | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000071 | Vegetation contact | Trunk failure | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000072 | Vegetation contact | Root failure | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 1
1060000073 | Vegetation contact | Root failure | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 2
1060000074 | Vegetation contact | Root failure | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000075 | Vegetation contact | Root failure | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000076 | Vegetation contact | Root failure | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000077 | Vegetation contact | Root failure | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000078 | Vegetation contact | Detached frond / limb / bark | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000079 | Vegetation contact | Detached frond / limb / bark | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000080 | Vegetation contact | Detached frond / limb / bark | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000081 | Vegetation contact | Detached frond / limb / bark | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000082 | Vegetation contact | Detached frond / limb / bark | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000083 | Vegetation contact | Detached frond / limb / bark | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000084 | Equipment / facility failure or damage | Anchor / guy | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000085 | Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000086 | Equipment / facility failure or damage | Anchor / guy | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000087 | Equipment / facility failure or damage | Anchor / guy | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000088 | Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000089 | Equipment / facility failure or damage | Anchor / guy | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000090 | Equipment / facility failure or damage | Capacitor bank | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000091 | Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000092 | Equipment / facility failure or damage | Capacitor bank | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000093 | Equipment / facility failure or damage | Capacitor bank | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000094 | Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000095 | Equipment / facility failure or damage | Capacitor bank | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000096 | Equipment / facility failure or damage | Conductor | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 15
1060000097 | Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 2
1060000098 | Equipment / facility failure or damage | Conductor | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000099 | Equipment / facility failure or damage | Conductor | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 1
1060000100 | Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000101 | Equipment / facility failure or damage | Conductor | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000102 | Equipment / facility failure or damage | Connection device | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 19
1060000103 | Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 2
1060000104 | Equipment / facility failure or damage | Connection device | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000105 | Equipment / facility failure or damage | Connection device | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 1
1060000106 | Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 1
1060000107 | Equipment / facility failure or damage | Connection device | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000108 | Equipment / facility failure or damage | Crossarm | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 1
1060000109 | Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000110 | Equipment / facility failure or damage | Crossarm | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000111 | Equipment / facility failure or damage | Crossarm | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000112 | Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000113 | Equipment / facility failure or damage | Crossarm | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000114 | Equipment / facility failure or damage | Fuse | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 4
1060000115 | Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000116 | Equipment / facility failure or damage | Fuse | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000117 | Equipment / facility failure or damage | Fuse | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000118 | Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000119 | Equipment / facility failure or damage | Fuse | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000120 | Equipment / facility failure or damage | Cutout | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000121 | Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000122 | Equipment / facility failure or damage | Cutout | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000123 | Equipment / facility failure or damage | Cutout | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000124 | Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000125 | Equipment / facility failure or damage | Cutout | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000126 | Equipment / facility failure or damage | Insulator and bushing | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000127 | Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000128 | Equipment / facility failure or damage | Insulator and bushing | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 1
1060000129 | Equipment / facility failure or damage | Insulator and bushing | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000130 | Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 1
1060000131 | Equipment / facility failure or damage | Insulator and bushing | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000132 | Equipment / facility failure or damage | Lightning arrester | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 1
1060000133 | Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000134 | Equipment / facility failure or damage | Lightning arrester | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000135 | Equipment / facility failure or damage | Lightning arrester | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000136 | Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000137 | Equipment / facility failure or damage | Lightning arrester | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000138 | Equipment / facility failure or damage | Pole | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 5
1060000139 | Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000140 | Equipment / facility failure or damage | Pole | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000141 | Equipment / facility failure or damage | Pole | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000142 | Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000143 | Equipment / facility failure or damage | Pole | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000144 | Equipment / facility failure or damage | Recloser | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 2
1060000145 | Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000146 | Equipment / facility failure or damage | Recloser | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000147 | Equipment / facility failure or damage | Recloser | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000148 | Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000149 | Equipment / facility failure or damage | Recloser | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000150 | Equipment / facility failure or damage | Relay | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000151 | Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000152 | Equipment / facility failure or damage | Relay | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000153 | Equipment / facility failure or damage | Relay | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000154 | Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000155 | Equipment / facility failure or damage | Relay | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000156 | Equipment / facility failure or damage | Sectionalizer | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000157 | Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000158 | Equipment / facility failure or damage | Sectionalizer | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000159 | Equipment / facility failure or damage | Sectionalizer | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000160 | Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000161 | Equipment / facility failure or damage | Sectionalizer | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000162 | Equipment / facility failure or damage | Splice | Distribution | Non-HFTD | # ignitions | With the exception of automatic wire splices, ignitions related to splice failures are characterized as connection device failures in PG&E's ignitions database. Because of this, ignitions caused by automatic wire splice failures have been included in Metric Type: Equipment / facility failure or damage, Ignition Driver: Connection Device. |  | PG&E | 2026 | 2 | 3
1060000163 | Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 2 | # ignitions | With the exception of automatic wire splices, ignitions related to splice failures are characterized as connection device failures in PG&E's ignitions database. Because of this, ignitions caused by automatic wire splice failures have been included in Metric Type: Equipment / facility failure or damage, Ignition Driver: Connection Device. |  | PG&E | 2026 | 2 | 0
1060000164 | Equipment / facility failure or damage | Splice | Distribution | HFTD Tier 3 | # ignitions | With the exception of automatic wire splices, ignitions related to splice failures are characterized as connection device failures in PG&E's ignitions database. Because of this, ignitions caused by automatic wire splice failures have been included in Metric Type: Equipment / facility failure or damage, Ignition Driver: Connection Device. |  | PG&E | 2026 | 2 | 0
1060000165 | Equipment / facility failure or damage | Splice | Transmission | Non-HFTD | # ignitions | With the exception of automatic wire splices, ignitions related to splice failures are characterized as connection device failures in PG&E's ignitions database. Because of this, ignitions caused by automatic wire splice failures have been included in Metric Type: Equipment / facility failure or damage, Ignition Driver: Connection Device. |  | PG&E | 2026 | 2 | 1
1060000166 | Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 2 | # ignitions | With the exception of automatic wire splices, ignitions related to splice failures are characterized as connection device failures in PG&E's ignitions database. Because of this, ignitions caused by automatic wire splice failures have been included in Metric Type: Equipment / facility failure or damage, Ignition Driver: Connection Device. |  | PG&E | 2026 | 2 | 0
1060000167 | Equipment / facility failure or damage | Splice | Transmission | HFTD Tier 3 | # ignitions | With the exception of automatic wire splices, ignitions related to splice failures are characterized as connection device failures in PG&E's ignitions database. Because of this, ignitions caused by automatic wire splice failures have been included in Metric Type: Equipment / facility failure or damage, Ignition Driver: Connection Device. |  | PG&E | 2026 | 2 | 0
1060000168 | Equipment / facility failure or damage | Switch | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 1
1060000169 | Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000170 | Equipment / facility failure or damage | Switch | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000171 | Equipment / facility failure or damage | Switch | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000172 | Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000173 | Equipment / facility failure or damage | Switch | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000174 | Equipment / facility failure or damage | Tap | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000175 | Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000176 | Equipment / facility failure or damage | Tap | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000177 | Equipment / facility failure or damage | Tap | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000178 | Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000179 | Equipment / facility failure or damage | Tap | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000180 | Equipment / facility failure or damage | Tie wire | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000181 | Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000182 | Equipment / facility failure or damage | Tie wire | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000183 | Equipment / facility failure or damage | Tie wire | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000184 | Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000185 | Equipment / facility failure or damage | Tie wire | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000186 | Equipment / facility failure or damage | Transformer | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 5
1060000187 | Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000188 | Equipment / facility failure or damage | Transformer | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000189 | Equipment / facility failure or damage | Transformer | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000190 | Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000191 | Equipment / facility failure or damage | Transformer | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000192 | Equipment / facility failure or damage | Voltage regulator / booster | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000193 | Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000194 | Equipment / facility failure or damage | Voltage regulator / booster | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000195 | Equipment / facility failure or damage | Voltage regulator / booster | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000196 | Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000197 | Equipment / facility failure or damage | Voltage regulator / booster | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000198 | Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | Non-HFTD | # ignitions | Ignitions caused by an unidentified equipment failure would be included under the following: Metric Type: Contact from object, Ignition Driver: Other (contact from object) or Metric Type: Unknown, Ingition Driver: Unknown (unknown). |  | PG&E | 2026 | 2 | 0
1060000199 | Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 2 | # ignitions | Ignitions caused by an unidentified equipment failure would be included under the following: Metric Type: Contact from object, Ignition Driver: Other (contact from object) or Metric Type: Unknown, Ingition Driver: Unknown (unknown). |  | PG&E | 2026 | 2 | 0
1060000200 | Equipment / facility failure or damage | Unknown (equipment failure) | Distribution | HFTD Tier 3 | # ignitions | Ignitions caused by an unidentified equipment failure would be included under the following: Metric Type: Contact from object, Ignition Driver: Other (contact from object) or Metric Type: Unknown, Ingition Driver: Unknown (unknown). |  | PG&E | 2026 | 2 | 0
1060000201 | Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | Non-HFTD | # ignitions | Ignitions caused by an unidentified equipment failure would be included under the following: Metric Type: Contact from object, Ignition Driver: Other (contact from object) or Metric Type: Unknown, Ingition Driver: Unknown (unknown). |  | PG&E | 2026 | 2 | 0
1060000202 | Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 2 | # ignitions | Ignitions caused by an unidentified equipment failure would be included under the following: Metric Type: Contact from object, Ignition Driver: Other (contact from object) or Metric Type: Unknown, Ingition Driver: Unknown (unknown). |  | PG&E | 2026 | 2 | 0
1060000203 | Equipment / facility failure or damage | Unknown (equipment failure) | Transmission | HFTD Tier 3 | # ignitions | Ignitions caused by an unidentified equipment failure would be included under the following: Metric Type: Contact from object, Ignition Driver: Other (contact from object) or Metric Type: Unknown, Ingition Driver: Unknown (unknown). |  | PG&E | 2026 | 2 | 0
1060000204 | Equipment / facility failure or damage | Other (equipment failure) | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 2
1060000205 | Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000206 | Equipment / facility failure or damage | Other (equipment failure) | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000207 | Equipment / facility failure or damage | Other (equipment failure) | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000208 | Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000209 | Equipment / facility failure or damage | Other (equipment failure) | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000210 | Wire-to-wire contact | Wire-to-wire contact | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 8
1060000211 | Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000212 | Wire-to-wire contact | Wire-to-wire contact | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000213 | Wire-to-wire contact | Wire-to-wire contact | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000214 | Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000215 | Wire-to-wire contact | Wire-to-wire contact | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000216 | Contamination | Contamination | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 4
1060000217 | Contamination | Contamination | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000218 | Contamination | Contamination | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000219 | Contamination | Contamination | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000220 | Contamination | Contamination | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000221 | Contamination | Contamination | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000222 | Protective device operation | Protective device operation | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000223 | Protective device operation | Protective device operation | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000224 | Protective device operation | Protective device operation | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000225 | Protective device operation | Protective device operation | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000226 | Protective device operation | Protective device operation | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000227 | Protective device operation | Protective device operation | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000228 | Vandalism / theft | Vandalism / theft | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 7
1060000229 | Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000230 | Vandalism / theft | Vandalism / theft | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000231 | Vandalism / theft | Vandalism / theft | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000232 | Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000233 | Vandalism / theft | Vandalism / theft | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000234 | Lightning | Lightning | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000235 | Lightning | Lightning | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000236 | Lightning | Lightning | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000237 | Lightning | Lightning | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000238 | Lightning | Lightning | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000239 | Lightning | Lightning | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000240 | Unknown | Unknown (unknown) | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 3
1060000241 | Unknown | Unknown (unknown) | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000242 | Unknown | Unknown (unknown) | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000243 | Unknown | Unknown (unknown) | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000244 | Unknown | Unknown (unknown) | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000245 | Unknown | Unknown (unknown) | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000246 | Other | Other (other) | Distribution | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 5
1060000247 | Other | Other (other) | Distribution | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 3
1060000248 | Other | Other (other) | Distribution | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000249 | Other | Other (other) | Transmission | Non-HFTD | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000250 | Other | Other (other) | Transmission | HFTD Tier 2 | # ignitions |  |  | PG&E | 2026 | 2 | 0
1060000251 | Other | Other (other) | Transmission | HFTD Tier 3 | # ignitions |  |  | PG&E | 2026 | 2 | 0

## Table 7
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1070000000 | Overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 4646.3894
1070000001 | Overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 9609.3521
1070000002 | Overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 6940.8258
1070000003 | Overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 28152.1407
1070000004 | Overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 421.9268
1070000005 | Overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 5456.794
1070000006 | Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 697.037
1070000007 | Overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 114.339
1070000008 | Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 8345.7525
1070000009 | Overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 5229.2572
1070000010 | Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 834.2994
1070000011 | Overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 2419.8065
1070000012 | Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 251.199
1070000013 | Overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 34.1283
1070000014 | Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 3946.7145
1070000015 | Overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 1623.6324
1070000016 | Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 341.5597
1070000017 | Overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 359.3379
1070000018 | Overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 577.5804
1070000019 | Overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 1652.955
1070000020 | Overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 871.3017
1070000021 | Overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 7676.9145
1070000022 | Overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 46.9168
1070000023 | Overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 1611.2355
1070000024 | Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 103.7766
1070000025 | Overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 112.2447
1070000026 | Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 845.8161
1070000027 | Overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 2027.5743
1070000028 | Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 71.4353
1070000029 | Overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 980.6613
1070000030 | Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 33.0837
1070000031 | Overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 23.1532
1070000032 | Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 302.927
1070000033 | Overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 746.9926
1070000034 | Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 26.8636
1070000035 | Overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 143.4323
1070000036 | Underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 6488.4886
1070000037 | Underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 12437.0919
1070000038 | Underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 2780.6588
1070000039 | Underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 3538.2994
1070000040 | Underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 65.7546
1070000041 | Underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 168.9687
1070000042 | Underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 364.8982
1070000043 | Underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 56.5197
1070000044 | Underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 1321.8777
1070000045 | Underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 545.308
1070000046 | Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 109.5515
1070000047 | Underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 240.1033
1070000048 | Underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 116.9322
1070000049 | Underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 7.2315
1070000050 | Underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 856.2329
1070000051 | Underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 251.5299
1070000052 | Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 41.2635
1070000053 | Underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 55.0753
1070000054 | Underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 26.0859
1070000055 | Underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 101.9998
1070000056 | Underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 8.3173
1070000057 | Underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 36.1393
1070000058 | Underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 0
1070000059 | Underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 2.2787
1070000060 | Underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 1.6534
1070000061 | Underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 0.14894
1070000062 | Underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 1.1211
1070000063 | Underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 7.8692
1070000064 | Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 0
1070000065 | Underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 0
1070000066 | Underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 0
1070000067 | Underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 0
1070000068 | Underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 0.58353
1070000069 | Underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 0.35051
1070000070 | Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 0
1070000071 | Underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 0
1070000072 | Critical facilities |  | Non-HFTD | Urban | WUI | Number of critical facilities |  |  | PG&E | 2026 | 2 | 12937
1070000073 | Critical facilities |  | Non-HFTD | Urban | Non-WUI | Number of critical facilities |  |  | PG&E | 2026 | 2 | 30404
1070000074 | Critical facilities |  | Non-HFTD | Rural | WUI | Number of critical facilities |  |  | PG&E | 2026 | 2 | 6340
1070000075 | Critical facilities |  | Non-HFTD | Rural | Non-WUI | Number of critical facilities |  |  | PG&E | 2026 | 2 | 8148
1070000076 | Critical facilities |  | Non-HFTD | Highly rural | WUI | Number of critical facilities |  |  | PG&E | 2026 | 2 | 230
1070000077 | Critical facilities |  | Non-HFTD | Highly rural | Non-WUI | Number of critical facilities |  |  | PG&E | 2026 | 2 | 697
1070000078 | Critical facilities |  | HFTD Tier 2 | Urban | WUI | Number of critical facilities |  |  | PG&E | 2026 | 2 | 971
1070000079 | Critical facilities |  | HFTD Tier 2 | Urban | Non-WUI | Number of critical facilities |  |  | PG&E | 2026 | 2 | 179
1070000080 | Critical facilities |  | HFTD Tier 2 | Rural | WUI | Number of critical facilities |  |  | PG&E | 2026 | 2 | 3004
1070000081 | Critical facilities |  | HFTD Tier 2 | Rural | Non-WUI | Number of critical facilities |  |  | PG&E | 2026 | 2 | 1406
1070000082 | Critical facilities |  | HFTD Tier 2 | Highly rural | WUI | Number of critical facilities |  |  | PG&E | 2026 | 2 | 325
1070000083 | Critical facilities |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of critical facilities |  |  | PG&E | 2026 | 2 | 432
1070000084 | Critical facilities |  | HFTD Tier 3 | Urban | WUI | Number of critical facilities |  |  | PG&E | 2026 | 2 | 358
1070000085 | Critical facilities |  | HFTD Tier 3 | Urban | Non-WUI | Number of critical facilities |  |  | PG&E | 2026 | 2 | 50
1070000086 | Critical facilities |  | HFTD Tier 3 | Rural | WUI | Number of critical facilities |  |  | PG&E | 2026 | 2 | 1657
1070000087 | Critical facilities |  | HFTD Tier 3 | Rural | Non-WUI | Number of critical facilities |  |  | PG&E | 2026 | 2 | 579
1070000088 | Critical facilities |  | HFTD Tier 3 | Highly rural | WUI | Number of critical facilities |  |  | PG&E | 2026 | 2 | 158
1070000089 | Critical facilities |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of critical facilities |  |  | PG&E | 2026 | 2 | 122
1070000090 | Residential customers |  | Non-HFTD | Urban | WUI | Number of residential customers |  |  | PG&E | 2026 | 2 | 1256511
1070000091 | Residential customers |  | Non-HFTD | Urban | Non-WUI | Number of residential customers |  |  | PG&E | 2026 | 2 | 2637388
1070000092 | Residential customers |  | Non-HFTD | Rural | WUI | Number of residential customers |  |  | PG&E | 2026 | 2 | 406355
1070000093 | Residential customers |  | Non-HFTD | Rural | Non-WUI | Number of residential customers |  |  | PG&E | 2026 | 2 | 315434
1070000094 | Residential customers |  | Non-HFTD | Highly rural | WUI | Number of residential customers |  |  | PG&E | 2026 | 2 | 10349
1070000095 | Residential customers |  | Non-HFTD | Highly rural | Non-WUI | Number of residential customers |  |  | PG&E | 2026 | 2 | 13801
1070000096 | Residential customers |  | HFTD Tier 2 | Urban | WUI | Number of residential customers |  |  | PG&E | 2026 | 2 | 70931
1070000097 | Residential customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of residential customers |  |  | PG&E | 2026 | 2 | 3826
1070000098 | Residential customers |  | HFTD Tier 2 | Rural | WUI | Number of residential customers |  |  | PG&E | 2026 | 2 | 190605
1070000099 | Residential customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of residential customers |  |  | PG&E | 2026 | 2 | 32505
1070000100 | Residential customers |  | HFTD Tier 2 | Highly rural | WUI | Number of residential customers |  |  | PG&E | 2026 | 2 | 16746
1070000101 | Residential customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of residential customers |  |  | PG&E | 2026 | 2 | 10732
1070000102 | Residential customers |  | HFTD Tier 3 | Urban | WUI | Number of residential customers |  |  | PG&E | 2026 | 2 | 27410
1070000103 | Residential customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of residential customers |  |  | PG&E | 2026 | 2 | 1809
1070000104 | Residential customers |  | HFTD Tier 3 | Rural | WUI | Number of residential customers |  |  | PG&E | 2026 | 2 | 105308
1070000105 | Residential customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of residential customers |  |  | PG&E | 2026 | 2 | 11339
1070000106 | Residential customers |  | HFTD Tier 3 | Highly rural | WUI | Number of residential customers |  |  | PG&E | 2026 | 2 | 9224
1070000107 | Residential customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of residential customers |  |  | PG&E | 2026 | 2 | 2686
1070000108 | Commercial customers |  | Non-HFTD | Urban | WUI | Number of commercial customers |  |  | PG&E | 2026 | 2 | 99077
1070000109 | Commercial customers |  | Non-HFTD | Urban | Non-WUI | Number of commercial customers |  |  | PG&E | 2026 | 2 | 310627
1070000110 | Commercial customers |  | Non-HFTD | Rural | WUI | Number of commercial customers |  |  | PG&E | 2026 | 2 | 53356
1070000111 | Commercial customers |  | Non-HFTD | Rural | Non-WUI | Number of commercial customers |  |  | PG&E | 2026 | 2 | 153964
1070000112 | Commercial customers |  | Non-HFTD | Highly rural | WUI | Number of commercial customers |  |  | PG&E | 2026 | 2 | 1809
1070000113 | Commercial customers |  | Non-HFTD | Highly rural | Non-WUI | Number of commercial customers |  |  | PG&E | 2026 | 2 | 14071
1070000114 | Commercial customers |  | HFTD Tier 2 | Urban | WUI | Number of commercial customers |  |  | PG&E | 2026 | 2 | 3320
1070000115 | Commercial customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of commercial customers |  |  | PG&E | 2026 | 2 | 782
1070000116 | Commercial customers |  | HFTD Tier 2 | Rural | WUI | Number of commercial customers |  |  | PG&E | 2026 | 2 | 17741
1070000117 | Commercial customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of commercial customers |  |  | PG&E | 2026 | 2 | 10618
1070000118 | Commercial customers |  | HFTD Tier 2 | Highly rural | WUI | Number of commercial customers |  |  | PG&E | 2026 | 2 | 1786
1070000119 | Commercial customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of commercial customers |  |  | PG&E | 2026 | 2 | 3588
1070000120 | Commercial customers |  | HFTD Tier 3 | Urban | WUI | Number of commercial customers |  |  | PG&E | 2026 | 2 | 1249
1070000121 | Commercial customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of commercial customers |  |  | PG&E | 2026 | 2 | 176
1070000122 | Commercial customers |  | HFTD Tier 3 | Rural | WUI | Number of commercial customers |  |  | PG&E | 2026 | 2 | 7771
1070000123 | Commercial customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of commercial customers |  |  | PG&E | 2026 | 2 | 3293
1070000124 | Commercial customers |  | HFTD Tier 3 | Highly rural | WUI | Number of commercial customers |  |  | PG&E | 2026 | 2 | 684
1070000125 | Commercial customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of commercial customers |  |  | PG&E | 2026 | 2 | 587
1070000126 | AFN customers |  | Non-HFTD | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2026 | 2 | 327479
1070000127 | AFN customers |  | Non-HFTD | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2026 | 2 | 861031
1070000128 | AFN customers |  | Non-HFTD | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2026 | 2 | 109368
1070000129 | AFN customers |  | Non-HFTD | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2026 | 2 | 117903
1070000130 | AFN customers |  | Non-HFTD | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2026 | 2 | 2835
1070000131 | AFN customers |  | Non-HFTD | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2026 | 2 | 3769
1070000132 | AFN customers |  | HFTD Tier 2 | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2026 | 2 | 10846
1070000133 | AFN customers |  | HFTD Tier 2 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2026 | 2 | 600
1070000134 | AFN customers |  | HFTD Tier 2 | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2026 | 2 | 50652
1070000135 | AFN customers |  | HFTD Tier 2 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2026 | 2 | 7608
1070000136 | AFN customers |  | HFTD Tier 2 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2026 | 2 | 4279
1070000137 | AFN customers |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2026 | 2 | 2421
1070000138 | AFN customers |  | HFTD Tier 3 | Urban | WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2026 | 2 | 3875
1070000139 | AFN customers |  | HFTD Tier 3 | Urban | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2026 | 2 | 282
1070000140 | AFN customers |  | HFTD Tier 3 | Rural | WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2026 | 2 | 26273
1070000141 | AFN customers |  | HFTD Tier 3 | Rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2026 | 2 | 2409
1070000142 | AFN customers |  | HFTD Tier 3 | Highly rural | WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2026 | 2 | 1612
1070000143 | AFN customers |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of customers belonging to access and functional needs populations |  |  | PG&E | 2026 | 2 | 521
1070000144 | Substations |  | Non-HFTD | Urban | WUI | Number of substations |  |  | PG&E | 2026 | 2 | 97
1070000145 | Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | PG&E | 2026 | 2 | 206
1070000146 | Substations |  | Non-HFTD | Rural | WUI | Number of substations |  |  | PG&E | 2026 | 2 | 61
1070000147 | Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | PG&E | 2026 | 2 | 285
1070000148 | Substations |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | PG&E | 2026 | 2 | 6
1070000149 | Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | PG&E | 2026 | 2 | 63
1070000150 | Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | PG&E | 2026 | 2 | 13
1070000151 | Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | PG&E | 2026 | 2 | 5
1070000152 | Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | PG&E | 2026 | 2 | 40
1070000153 | Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | PG&E | 2026 | 2 | 65
1070000154 | Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | PG&E | 2026 | 2 | 14
1070000155 | Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | PG&E | 2026 | 2 | 49
1070000156 | Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | PG&E | 2026 | 2 | 0
1070000157 | Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | PG&E | 2026 | 2 | 0
1070000158 | Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | PG&E | 2026 | 2 | 21
1070000159 | Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | PG&E | 2026 | 2 | 20
1070000160 | Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | PG&E | 2026 | 2 | 5
1070000161 | Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | PG&E | 2026 | 2 | 20
1070000162 | Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 22
1070000163 | Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 38
1070000164 | Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 76
1070000165 | Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 205
1070000166 | Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 8
1070000167 | Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 77
1070000168 | Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 11
1070000169 | Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 7
1070000170 | Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 191
1070000171 | Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 377
1070000172 | Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 38
1070000173 | Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 256
1070000174 | Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 9
1070000175 | Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 5
1070000176 | Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 107
1070000177 | Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 160
1070000178 | Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 15
1070000179 | Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 40

## Table 8
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1080000000 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0.58029
1080000001 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | -1.4309
1080000002 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | -1.9152
1080000003 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 3.3641
1080000004 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | -1.1955
1080000005 | Net addition (or removal) - overhead circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 2.4125
1080000006 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | -0.26288
1080000007 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | -0.20577
1080000008 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | -12.5836
1080000009 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | -4.8011
1080000010 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0.003631
1080000011 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | -0.82568
1080000012 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | -0.062842
1080000013 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0.018611
1080000014 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | -16.3789
1080000015 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | -8.2234
1080000016 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | -0.4603
1080000017 | Net addition (or removal) - overhead circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | -0.25864
1080000018 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | -0.38983
1080000019 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0.114
1080000020 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0.005938
1080000021 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0.31887
1080000022 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000023 | Net addition (or removal) - overhead circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0.34635
1080000024 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | -0.064219
1080000025 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0.061171
1080000026 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0.19606
1080000027 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | -0.039848
1080000028 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | -0.000724
1080000029 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | -0.082709
1080000030 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000031 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000032 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | -0.006921
1080000033 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0.011607
1080000034 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000035 | Net addition (or removal) - overhead circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0.002402
1080000036 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 11.1045
1080000037 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 33.1112
1080000038 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 14.512
1080000039 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 19.9347
1080000040 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 1.3185
1080000041 | Net addition (or removal) - underground circuit miles | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0.98206
1080000042 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0.27448
1080000043 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0.017051
1080000044 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 14.2603
1080000045 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 2.0438
1080000046 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0.49711
1080000047 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 1.1099
1080000048 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0.1458
1080000049 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0.050989
1080000050 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 17.6085
1080000051 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 9.2027
1080000052 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 1.275
1080000053 | Net addition (or removal) - underground circuit miles | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 1.2368
1080000054 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000055 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000056 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000057 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0.31213
1080000058 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000059 | Net addition (or removal) - underground circuit miles | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000060 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000061 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000062 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000063 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000064 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000065 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000066 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000067 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000068 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000069 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000070 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000071 | Net addition (or removal) - underground circuit miles | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000072 | Net addition (or removal) - Substations |  | Non-HFTD | Urban | WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000073 | Net addition (or removal) - Substations |  | Non-HFTD | Urban | Non-WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000074 | Net addition (or removal) - Substations |  | Non-HFTD | Rural | WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 1
1080000075 | Net addition (or removal) - Substations |  | Non-HFTD | Rural | Non-WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | -1
1080000076 | Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000077 | Net addition (or removal) - Substations |  | Non-HFTD | Highly rural | Non-WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000078 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000079 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000080 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 1
1080000081 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000082 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000083 | Net addition (or removal) - Substations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000084 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000085 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000086 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000087 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000088 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000089 | Net addition (or removal) - Substations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000090 | Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000091 | Net addition (or removal) - Weather stations |  | Non-HFTD | Urban | Non-WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000092 | Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000093 | Net addition (or removal) - Weather stations |  | Non-HFTD | Rural | Non-WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 5
1080000094 | Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000095 | Net addition (or removal) - Weather stations |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 2
1080000096 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000097 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000098 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 4
1080000099 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 1
1080000100 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 2
1080000101 | Net addition (or removal) - Weather stations |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 1
1080000102 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000103 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000104 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | -1
1080000105 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 1
1080000106 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 0
1080000107 | Net addition (or removal) - Weather stations |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations | Actual values are derived based on the previous quarter actuals. For example: Q1 2026 is the variance between Q1 2026 and Q4 2025. |  | PG&E | 2026 | 2 | 1

## Table 9
METRIC NUMBER | METRIC TYPE | LINE TYPE | HFTD TIER | AREA TYPE | WUI STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1090000000 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | WUI | Circuit miles | The 2026 actual values reported here represent work completed from 2026-2028 WMP Initiatives GH-04, GH-12, and GH-14. |  | PG&E | 2026 | 2 | 0
1090000001 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Urban | Non-WUI | Circuit miles | The 2026 actual values reported here represent work completed from 2026-2028 WMP Initiatives GH-04, GH-12, and GH-14. |  | PG&E | 2026 | 2 | 0
1090000002 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | WUI | Circuit miles | The 2026 actual values reported here represent work completed from 2026-2028 WMP Initiatives GH-04, GH-12, and GH-14. |  | PG&E | 2026 | 2 | 0
1090000003 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Rural | Non-WUI | Circuit miles | The 2026 actual values reported here represent work completed from 2026-2028 WMP Initiatives GH-04, GH-12, and GH-14. |  | PG&E | 2026 | 2 | 0
1090000004 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | WUI | Circuit miles | The 2026 actual values reported here represent work completed from 2026-2028 WMP Initiatives GH-04, GH-12, and GH-14. |  | PG&E | 2026 | 2 | 0
1090000005 | Number of overhead circuit miles upgraded | Distribution | Non-HFTD | Highly rural | Non-WUI | Circuit miles | The 2026 actual values reported here represent work completed from 2026-2028 WMP Initiatives GH-04, GH-12, and GH-14. |  | PG&E | 2026 | 2 | 0
1090000006 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | WUI | Circuit miles | The 2026 actual values reported here represent work completed from 2026-2028 WMP Initiatives GH-04, GH-12, and GH-14. |  | PG&E | 2026 | 2 | 1.6
1090000007 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Urban | Non-WUI | Circuit miles | The 2026 actual values reported here represent work completed from 2026-2028 WMP Initiatives GH-04, GH-12, and GH-14. |  | PG&E | 2026 | 2 | 0
1090000008 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | WUI | Circuit miles | The 2026 actual values reported here represent work completed from 2026-2028 WMP Initiatives GH-04, GH-12, and GH-14. |  | PG&E | 2026 | 2 | 40.7
1090000009 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Rural | Non-WUI | Circuit miles | The 2026 actual values reported here represent work completed from 2026-2028 WMP Initiatives GH-04, GH-12, and GH-14. |  | PG&E | 2026 | 2 | 43.7
1090000010 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | WUI | Circuit miles | The 2026 actual values reported here represent work completed from 2026-2028 WMP Initiatives GH-04, GH-12, and GH-14. |  | PG&E | 2026 | 2 | 5.6
1090000011 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles | The 2026 actual values reported here represent work completed from 2026-2028 WMP Initiatives GH-04, GH-12, and GH-14. |  | PG&E | 2026 | 2 | 25.6
1090000012 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | WUI | Circuit miles | The 2026 actual values reported here represent work completed from 2026-2028 WMP Initiatives GH-04, GH-12, and GH-14. |  | PG&E | 2026 | 2 | 0
1090000013 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Urban | Non-WUI | Circuit miles | The 2026 actual values reported here represent work completed from 2026-2028 WMP Initiatives GH-04, GH-12, and GH-14. |  | PG&E | 2026 | 2 | 0
1090000014 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | WUI | Circuit miles | The 2026 actual values reported here represent work completed from 2026-2028 WMP Initiatives GH-04, GH-12, and GH-14. |  | PG&E | 2026 | 2 | 61.8
1090000015 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Rural | Non-WUI | Circuit miles | The 2026 actual values reported here represent work completed from 2026-2028 WMP Initiatives GH-04, GH-12, and GH-14. |  | PG&E | 2026 | 2 | 25.8
1090000016 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | WUI | Circuit miles | The 2026 actual values reported here represent work completed from 2026-2028 WMP Initiatives GH-04, GH-12, and GH-14. |  | PG&E | 2026 | 2 | 8.2
1090000017 | Number of overhead circuit miles upgraded | Distribution | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles | The 2026 actual values reported here represent work completed from 2026-2028 WMP Initiatives GH-04, GH-12, and GH-14. |  | PG&E | 2026 | 2 | 5.1
1090000018 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 0
1090000019 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 0
1090000020 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 0
1090000021 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 0
1090000022 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 0
1090000023 | Number of overhead circuit miles upgraded | Transmission | Non-HFTD | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 0
1090000024 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 0
1090000025 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 0
1090000026 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 0
1090000027 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 0
1090000028 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 0
1090000029 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 2 | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 0
1090000030 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 0
1090000031 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Urban | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 0
1090000032 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 0
1090000033 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 0
1090000034 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 0
1090000035 | Number of overhead circuit miles upgraded | Transmission | HFTD Tier 3 | Highly rural | Non-WUI | Circuit miles |  |  | PG&E | 2026 | 2 | 0
1090000036 | Number of substations upgraded |  | Non-HFTD | Urban | WUI | Number of substations |  |  | PG&E | 2026 | 2 | 0
1090000037 | Number of substations upgraded |  | Non-HFTD | Urban | Non-WUI | Number of substations |  |  | PG&E | 2026 | 2 | 1
1090000038 | Number of substations upgraded |  | Non-HFTD | Rural | WUI | Number of substations |  |  | PG&E | 2026 | 2 | 0
1090000039 | Number of substations upgraded |  | Non-HFTD | Rural | Non-WUI | Number of substations |  |  | PG&E | 2026 | 2 | 1
1090000040 | Number of substations upgraded |  | Non-HFTD | Highly rural | WUI | Number of substations |  |  | PG&E | 2026 | 2 | 0
1090000041 | Number of substations upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of substations |  |  | PG&E | 2026 | 2 | 0
1090000042 | Number of substations upgraded |  | HFTD Tier 2 | Urban | WUI | Number of substations |  |  | PG&E | 2026 | 2 | 0
1090000043 | Number of substations upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of substations |  |  | PG&E | 2026 | 2 | 0
1090000044 | Number of substations upgraded |  | HFTD Tier 2 | Rural | WUI | Number of substations |  |  | PG&E | 2026 | 2 | 0
1090000045 | Number of substations upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of substations |  |  | PG&E | 2026 | 2 | 0
1090000046 | Number of substations upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of substations |  |  | PG&E | 2026 | 2 | 0
1090000047 | Number of substations upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of substations |  |  | PG&E | 2026 | 2 | 0
1090000048 | Number of substations upgraded |  | HFTD Tier 3 | Urban | WUI | Number of substations |  |  | PG&E | 2026 | 2 | 0
1090000049 | Number of substations upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of substations |  |  | PG&E | 2026 | 2 | 0
1090000050 | Number of substations upgraded |  | HFTD Tier 3 | Rural | WUI | Number of substations |  |  | PG&E | 2026 | 2 | 0
1090000051 | Number of substations upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of substations |  |  | PG&E | 2026 | 2 | 0
1090000052 | Number of substations upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of substations |  |  | PG&E | 2026 | 2 | 0
1090000053 | Number of substations upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of substations |  |  | PG&E | 2026 | 2 | 0
1090000054 | Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 0
1090000055 | Number of weather stations with hardware upgraded |  | Non-HFTD | Urban | Non-WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 0
1090000056 | Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 0
1090000057 | Number of weather stations with hardware upgraded |  | Non-HFTD | Rural | Non-WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 0
1090000058 | Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 0
1090000059 | Number of weather stations with hardware upgraded |  | Non-HFTD | Highly rural | Non-WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 0
1090000060 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 0
1090000061 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Urban | Non-WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 0
1090000062 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 0
1090000063 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Rural | Non-WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 0
1090000064 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 0
1090000065 | Number of weather stations with hardware upgraded |  | HFTD Tier 2 | Highly rural | Non-WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 0
1090000066 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 0
1090000067 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Urban | Non-WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 0
1090000068 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 0
1090000069 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Rural | Non-WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 0
1090000070 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 0
1090000071 | Number of weather stations with hardware upgraded |  | HFTD Tier 3 | Highly rural | Non-WUI | Number of weather stations |  |  | PG&E | 2026 | 2 | 0

## Table 10
METRIC NUMBER | METRIC TYPE | METRIC NAME | WIND WARNING STATUS | UNIT(S) | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER | ACTUAL VALUE
1100000000 | Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | RFW only | Number of events |  |  | PG&E | 2026 | 2 | 1
1100000001 | Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW only | Number of events |  |  | PG&E | 2026 | 2 | 0
1100000002 | Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | HWW & RFW | Number of events |  |  | PG&E | 2026 | 2 | 0
1100000003 | Recent use of PSPS and fast-trip | Frequency of PSPS events (total) | Neither | Number of events |  |  | PG&E | 2026 | 2 | 1
1100000004 | Recent use of PSPS and fast-trip | Scope of PSPS events (total) | RFW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | PG&E | 2026 | 2 | 22
1100000005 | Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW only | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | PG&E | 2026 | 2 | 0
1100000006 | Recent use of PSPS and fast-trip | Scope of PSPS events (total) | HWW & RFW | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | PG&E | 2026 | 2 | 0
1100000007 | Recent use of PSPS and fast-trip | Scope of PSPS events (total) | Neither | Circuit-events, measured in number of events multiplied by number of circuits de-energized |  |  | PG&E | 2026 | 2 | 31
1100000008 | Recent use of PSPS and fast-trip | Duration of PSPS events (total) | RFW only | Customer hours |  |  | PG&E | 2026 | 2 | 72206.9278
1100000009 | Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW only | Customer hours |  |  | PG&E | 2026 | 2 | 0
1100000010 | Recent use of PSPS and fast-trip | Duration of PSPS events (total) | HWW & RFW | Customer hours |  |  | PG&E | 2026 | 2 | 0
1100000011 | Recent use of PSPS and fast-trip | Duration of PSPS events (total) | Neither | Customer hours |  |  | PG&E | 2026 | 2 | 127044.0647
1100000012 | Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | RFW only | Number of events |  |  | PG&E | 2026 | 2 | 84
1100000013 | Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW only | Number of events |  |  | PG&E | 2026 | 2 | 0
1100000014 | Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | HWW & RFW | Number of events |  |  | PG&E | 2026 | 2 | 0
1100000015 | Recent use of PSPS and fast-trip | Frequency of fast-trip events (total) | Neither | Number of events |  |  | PG&E | 2026 | 2 | 647
1100000016 | Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | RFW only | Circuit mile days |  |  | PG&E | 2026 | 2 | 358870
1100000017 | Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW only | Circuit mile days |  |  | PG&E | 2026 | 2 | 0
1100000018 | Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | HWW & RFW | Circuit mile days |  |  | PG&E | 2026 | 2 | 0
1100000019 | Recent use of PSPS and fast-trip | Circuit mile days with fast-trip settings enabled (total) | Neither | Circuit mile days |  |  | PG&E | 2026 | 2 | 1409564.819
1100000020 | Customer hours of PSPS and other outages | Customer hours of planned outages including PSPS (total) |  | Customer hours |  |  | PG&E | 2026 | 2 | 1022110.8167
1100000021 | Customer hours of PSPS and other outages | Customer hours of unplanned outages, not including PSPS or fast-trip (total) |  | Customer hours |  |  | PG&E | 2026 | 2 | 3668153.2833
1100000022 | Customer hours of PSPS and other outages | Customer hours of unplanned outages resulting from fast-trip |  | Customer hours |  |  | PG&E | 2026 | 2 | 1411192.6167
1100000023 | Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (including PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served | Data is reported in minutes. |  | PG&E | 2026 | 2 | 62.9
1100000024 | Customer hours of PSPS and other outages | System Average Interruption Duration Index (SAIDI) (excluding PSPS) |  | SAIDI index value = sum of all interruptions in time period where each interruption is defined as sum(duration of interruption * # of customer interruptions) / Total number of customers served | Data is reported in minutes. |  | PG&E | 2026 | 2 | 60.6
1100000025 | Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (including PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  |  | PG&E | 2026 | 2 | 0.45
1100000026 | Customer hours of PSPS and other outages | System Average Interruption Frequency Index (SAIFI) (excluding PSPS) |  | SAIFI index value = sum of all interruptions in time period where each interruption is defined as (total # of customer interruptions) / (total # of customers served) |  |  | PG&E | 2026 | 2 | 0.448
1100000027 | Critical infrastructure impacted by PSPS | Critical infrastructure impacted by PSPS |  | Number of critical infrastructure (in accordance with D.19-05-042) locations impacted multiplied by hours offline |  |  | PG&E | 2026 | 2 | 8704.0561
1100000028 | Community outreach of PSPS metrics | # of customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PG&E | 2026 | 2 | 8839
1100000029 | Community outreach of PSPS metrics | # of medical baseline customers impacted by PSPS |  | # of customers impacted by PSPS (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PG&E | 2026 | 2 | 460
1100000030 | Community outreach of PSPS metrics | # of customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PG&E | 2026 | 2 | 12472
1100000031 | Community outreach of PSPS metrics | # of medical baseline customers notified prior to initiation of PSPS event |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PG&E | 2026 | 2 | 561
1100000032 | Community outreach of PSPS metrics | # of customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PG&E | 2026 | 2 | 8803
1100000033 | Community outreach of PSPS metrics | # of medical baseline customers notified prior to a PSPS event impacting them |  | # of customers notified (if multiple PSPS events impact the same customer, count each event as a separate customer) |  |  | PG&E | 2026 | 2 | 460
1100000034 | Other PSPS metrics | Number of PSPS events in which a notification was sent but no de-energization occurred |  | Number of events |  |  | PG&E | 2026 | 2 | 0
1100000035 | Other PSPS metrics | Average number of customers located on de-energized circuit |  | Number of customers |  |  | PG&E | 2026 | 2 | 1315.1509
1100000036 | Other PSPS metrics | Customer hours of PSPS per RFW OH circuit mile day |  | Customer hours per RFW OH circuit mile day in time period |  |  | PG&E | 2026 | 2 | 3.0807
1100000037 | Other PSPS metrics | Customer hours of PSPS per HWW OH circuit mile day |  | Customer hours per HWW OH circuit mile day in time period |  |  | PG&E | 2026 | 2 | 861.5286
1100000038 | Other PSPS metrics | Customer hours of PSPS per high FPIOH circuit mile day |  | Customer hours per FPI OH circuit mile day in time period |  |  | PG&E | 2026 | 2 | 0.31631
1100000039 | Other PSPS metrics | Median time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours |  |  | PG&E | 2026 | 2 | 23.55
1100000040 | Other PSPS metrics | 95 percentile of time between de-energization, due to PSPS, and inspection of a circuit segment |  | hours |  |  | PG&E | 2026 | 2 | 29.65
1100000041 | Other PSPS metrics | Median time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours |  |  | PG&E | 2026 | 2 | 0.57
1100000042 | Other PSPS metrics | 95 percentile of time between de-energization, due to fast-trip, and inspection of a circuit segment |  | hours |  |  | PG&E | 2026 | 2 | 1.39
1100000043 | Other PSPS metrics | Number of risk events occurring on a de-energized circuit |  | Number of risk events |  |  | PG&E | 2026 | 2 | 9

## Table 12
METRIC NUMBER | WORK ORDER NUMBER | EQUIPMENT TYPE | HFTD TIER | LINE TYPE | DATE OPENED | DUE DATE | GO 95 RULE 18 PRIORITY | UTILITY SPECIFIC REPAIR PRIORITY | DATE REINSPECTED | DATE MODIFIED | DUE DATE AFTER REINSPECTED OR MODIFIED | GO 95 RULE 18 PRIORITY AFTER REINSPECTED OR MODIFIED | REASON FOR REINSPECTION | COMMENTS | BLANK MEANING | UTILITY ID | REPORTING YEAR | REPORTING QUARTER
CSV PROVIDED