## 2022 Env Issues
Project: Project Name | Project: Workstream | Issue Category | Project: Region
Alleghany 1101 B_12kV_Routine_TNF_2021_192854_WP2 | Routine - Distribution | RPM Not Implemented | Sierra
Alleghany 1101 B_12kV_Routine_TNF_2021_192854 | Routine - Distribution | RPM Not Implemented | Sierra
Bucks Creek 1103_12kV_CEMA_PNF_2021_195008 | CEMA - Distribution | Monitoring | North Valley
Bucks Creek 1103_12kV_CEMA_PNF_2021_195008 | CEMA - Distribution | RPM Not Implemented | North Valley
Alleghany 1101B Section 1_12kV_Routine_TNF_2021_191534 | Routine - Distribution | RPM Not Implemented | Sierra
Pike City 1102_12kV_EVM_TNF_2021 | EVM | Other | Sierra
Alleghany 1101B Section 5_12kV_Routine_TNF_2021_191854 | Routine - Distribution |  | Sierra
Fitch Mountain 1113_12kV_EVM_Black ECL_2021 | EVM | Wetlands/Waterways | North Coast
Emerald Lake 0402_4kV_Routine_SMCP_2021 | Routine - Distribution | Other | Bay Area
French Gulch 1102_12kV_Routine_WNR_2021_197760 | Routine - Distribution | Monitoring | North Valley
Half Moon Bay 1103_12kV_Routine_CT_CZ_2021 | Routine - Distribution | Area Not Assessed | Bay Area
Grass Valley 1101_12kV_Routine_CT_2021_192565 | Routine - Distribution | ERTC/Permit not obtained prior to work | Sierra
Dunlap 1102 High NPS_12_Routine - Distribution_2022_197688 | Routine - Distribution | RPM Not Implemented | Central Valley
LOW GAP 1101 FS Six National Forest_12kV_Routine_SRF_2021_193473 | Routine - Distribution | ERTC/Permit conditions not followed | North Coast
Caribou #2_60kV_Routine_PNF_2021_188329_WP2 | Routine - Transmission | RPM Not Implemented | North Valley
Woodchuck 2101_12kV_Routine_SNF_2021_190134 | Routine - Distribution | Protected Species | Central Valley
PENRYN 1105_12kV_EVM_CT_2021 | EVM | Surveys | Sierra
PENRYN 1105_12kV_EVM_CT_2021 | EVM | RPM Not Implemented | Sierra
DIAMOND SPRINGS 1105_12kV_EVM_CT_Hwy 49_2021 | EVM | ERTC/Permit conditions not followed | Sierra
DIAMOND SPRINGS 1105_12kV_EVM_CT_Hwy 49_2021 | EVM | ERTC/Permit not obtained prior to work | Sierra
Woodside 1101_12kV_EVM_CT & MIDPEN_Hwy 35 & 84_2021 | EVM | Other | Bay Area
Hat Creek #1 to Westwood #2_60kV_Routine_LNF_2021_188689 | Routine - Transmission | RPM Not Implemented | North Valley
Challenge 1102_12kV_Routine_PNF_2021_192421 | Routine - Distribution | RPM Not Implemented | North Valley
Narrows 2101_24kV_EVM_CT_2021 | EVM | RPM Not Implemented | Sierra
Hoopa 1101_12kV_CEMA_SRF_2021_195926 | CEMA - Distribution | Unauthorized Veg removal | North Coast
Challenge 1101_12kV_Routine_PNF_2021_191318 | Routine - Distribution | Monitoring | North Valley
Challenge 1101_12kV_Routine_PNF_2021_191318 | Routine - Distribution | Other | North Valley
Challenge 1101_12kV_Routine_PNF_2021_191318 | Routine - Distribution | Monitoring | North Valley
Challenge 1101_12kV_Routine_PNF_2021_191318 | Routine - Distribution | RPM Not Implemented | North Valley
Humboldt State Parks South_WRT_SP_Routine_2021_193166 | Routine - Distribution | RPM Not Implemented | North Coast
Trinidad 1102_12kV_CEMA_CZ_2021_195891 | CEMA - Distribution | ERTC/Permit not obtained prior to work | North Coast
Salt Springs, Tiger Creek, Craig Thurber_115kV_TVMR_STF_2021 | Transmission Veg. Mgmt. Reliability | Stormwater | Central Valley
Salt Springs-Tiger Creek_115kV_TVMR_ENF_2021_5792870 | Transmission Veg. Mgmt. Reliability | RPM Not Implemented | Sierra
Salt Springs-Tiger Creek_115kV_TVMR_ENF_2021_5792870 | Transmission Veg. Mgmt. Reliability | Other | Sierra
Bolinas 1101_12kV_CEMA_Mt Tamalpais SP_CZ_2021_194430 | CEMA - Distribution | Other | Bay Area
Oakhurst 1103B_12kV_Routine_YNP_2021_193250 | Routine - Distribution |  | Central Valley
Franklin 1101_60kV_Routine_JMLT_2021_1221 | Routine - Distribution | Protected Species | Bay Area
Point Arena 1101_12kV_Routine_UKIBLM_2021_189900 | Routine - Distribution | Wetlands/Waterways | North Coast
Point Arena 1101_12kV_Routine_UKIBLM_2021_189900 | Routine - Distribution | Wetlands/Waterways | North Coast
Point Arena 1101_12kV_Routine_CZ_2021_189900 | Routine - Distribution | RPM Not Implemented | North Coast
Girvan 1101_12kV_CEMA_REDBLM_2021_195151 | CEMA - Distribution | RPM Not Implemented | North Valley
Mendocino State Parks_12_Routine - Distribution_2022_192849 | Routine - Distribution | ERTC/Permit conditions not followed | North Coast
Half Moon Bay 1102_12kV_Routine_CZ_Montara State Beach_2021 | Routine - Distribution | RPM Not Implemented | Bay Area
Keswick 1101_12kV_CEMA_REDBLM_2021_195162 | CEMA - Distribution | RPM Not Implemented | North Valley
Colgate - Challenge_60kV_Routine_PNF_2022_198179 | Routine - Transmission | RPM Not Implemented | North Valley
Bolinas 1101_12kV_Routine_CZ_CT_2022_192716 | Routine - Distribution | ERTC/Permit not obtained prior to work | Bay Area
Bolinas 1101_12kV_Routine_Mt Tamalpais SP_CZ_2022_192716 | Routine - Distribution | ERTC/Permit not obtained prior to work | Bay Area
Hill Park Main Line Under Ground_Other_DeMille Road_2022 | Other | ERTC/Permit not obtained prior to work | North Valley
Girvan 1101_12kV_EVM_REDBLM_2022_WP2 | EVM | RPM Not Implemented | North Valley
NARROWS 2105_21kV_EVM_RR_F-00007577_2022 | Riparian Review | Wetlands/Waterways | Sierra
Oakhurst 1103_12kV_EVM_Riparian Review_2022 | EVM | Wetlands/Waterways | Central Valley
Oakhurst 1103_12kV_EVM_Riparian Review_2022 | EVM | Stormwater | Central Valley
Columbia Hill 1101_12kV_EVM_MLOBLM_2022 | EVM | RPM Not Implemented | Sierra
Columbia Hill 1101_12kV_EVM_MLOBLM_2022 | EVM |  | Sierra
SALT SPRINGS 2101_21kV_CEMA_STF_2022_205282 | CEMA - Distribution | RPM Not Implemented | Central Valley
French Gulch and Keswick 1101_12kV_CEMA_WNR_2022_204670 | CEMA - Distribution | Monitoring | North Valley
French Gulch and Keswick 1101_12kV_CEMA_WNR_2022_204670 | CEMA - Distribution | Monitoring | North Valley
Trinity-Cottonwood, Keswick-Trinity_115kV_TVMR_WNR_205806 | Transmission Veg. Mgmt. Reliability | Unauthorized Veg removal | North Valley
French Gulch 1102_12kV_Urgent_WNR_2022 | CEMA - Distribution | Wetlands/Waterways | North Valley
Hollister 2101_21kV_Routine_Hollister Hills SVRA_2022_190778 | Routine - Distribution | ERTC/Permit conditions not followed | Central Coast
Centerville - Table MTN - Oroville_60kV_Routine_CT_2022_198471 | Routine - Transmission | Surveys | North Valley
Spring Gap 1702 & Pinecrest 0401_17kV_CEMA_STF_Timbersale_2022_195450 | CEMA - Distribution | Area Not Assessed | Central Valley
Nicolaus-Catlett Jct_60kV_Routine_BOR_2022_198462 | Routine - Transmission | RPM Not Implemented | Sierra
Pit 3 1101_12kV_Routine_FERC_LNF_2022_204621 | Routine - Distribution | Nesting Birds | North Valley
Pit 3 1101_12kV_Routine_FERC_LNF_2022_204621 | Routine - Distribution | Nesting Birds | North Valley
Pit 3 1101_12kV_Routine_FERC_LNF_2022_204621 | Routine - Distribution | RPM Not Implemented | North Valley
Pit 3 1101_12kV_Routine_FERC_SHF_2022_204621 | Routine - Distribution | Surveys | North Valley
Pit 3 1101_12kV_Routine_FERC_SHF_2022_204621 | Routine - Distribution | RPM Not Implemented | North Valley
Pit 3 1101_12kV_Routine_FERC_SHF_2022_204621 | Routine - Distribution | Nesting Birds | North Valley
Pit 3 1101_12kV_Routine_FERC_SHF_2022_204621 | Routine - Distribution | Protected Species | North Valley
Multi Circuit_21kV_Routine_MLOBLM_2022_202386 | Routine - Distribution | Surveys | Sierra
Multi Circuit_21kV_Routine_MLOBLM_2022_202386 | Routine - Distribution | RPM Not Implemented | Sierra
Volta 1102, Rising River 1101_12kV_CEMA_LNF_2022_204662 | CEMA - Distribution | RPM Not Implemented | North Valley
Garberville 1102_12kV_EVM_ARCBLM_2022 | EVM | ERTC/Permit not obtained prior to work | North Coast
CR Bellota-Melones-Wilson_230kV_NERC_BOR_Routine_2022_197961 | Routine - Transmission | Surveys | Central Valley
Otter 1101_12kV_Multiple-Routine_CZ_2022 | Routine - Distribution |  | Central Coast
Woodchuck 2101_21kV_CEMA_SNF_2022_203568 | CEMA - Distribution | RPM Not Implemented | Central Valley
ITS VM Nest Reviews | Nest Review | Nesting Birds | Bay Area
ITS VM Nest Reviews | Nest Review |  | Bay Area
ITS VM Nest Reviews | Nest Review |  | Bay Area
ITS VM Nest Reviews | Nest Review |  | Bay Area
ITS VM Nest Reviews | Nest Review |  | Bay Area
ITS VM Nest Reviews | Nest Review |  | Bay Area
ITS VM Nest Reviews | Nest Review |  | Bay Area
ITS VM Nest Reviews | Nest Review |  | Bay Area
ITS VM Nest Reviews | Nest Review |  | Bay Area
ITS VM Nest Reviews | Nest Review |  | Bay Area
ITS VM Nest Reviews | Nest Review | Nesting Birds | Bay Area
Dunlap 1103_12kV_Routine_CEMA_SNP_2020_177915 | Routine - Distribution | ERTC/Permit conditions not followed | Central Valley
Alleghany 1101_12kV_Routine_TNF_2020_181019 | Routine - Distribution | ERTC/Permit conditions not followed | Sierra
Fort Ross 1121_12kV_Multiple-Routine_Sonoma-Mendocino SP CZ_2020_181251 | Routine - Distribution | ERTC/Permit conditions not followed | North Coast
Wyandotte 1105_12kV_CEMA_Lake Oroville RA_2021_195048 | CEMA - Distribution | RPM Not Implemented | North Valley
Echo Summit_1101_12kV_Routine_ENF_2021_191633 | Routine - Distribution | RPM Not Implemented | Sierra
Monta Vista-Jefferson_230kV_Routine _NERC_SMCPD_Huddard Pk_2021_188230 | Routine - Transmission | Other | Bay Area
Monta Vista-Jefferson_230kV_Routine _NERC_SMCPD_Huddard Pk_2021_188230 | Routine - Transmission | Other | Bay Area
Monta Vista-Jefferson_230kV_Routine _NERC_SMCPD_Huddard Pk_2021_188230 | Routine - Transmission | Other | Bay Area
Monta Vista-Jefferson_230kV_Routine_NERC_SMCPD_2021_188230 | Routine - Transmission | Stormwater | Bay Area
Humboldt-Trinity-Maple Creek_115kV_Routine_SRF_2021_188258 | Routine - Transmission | RPM Not Implemented | North Coast
Accelerate-Eel River 1102_12kV_Routine_CDFW_CZ_2022_202699 | Routine - Distribution | ERTC/Permit conditions not followed | North Coast
Dairyville 1101 12kV_RiparianPostAssessment_2022 | Routine - Distribution | Wetlands/Waterways | North Valley
Rio Dell Jct-Bridgeville_60kV_Routine_Grizzly Creek Redwoods SP_2022_198463 | Routine - Transmission | ERTC/Permit conditions not followed | North Coast
Rock Creek-POE_230kV_Routine_PNF_2022_198654 | Routine - Transmission | RPM Not Implemented | North Valley
Geyserville 1101_12kV_EVM_USACE_2022 | EVM | Protected Species | North Coast
Challenge 1102_12kV_CEMA_MLOBLM_2022_195108 | CEMA - Distribution | RPM Not Implemented | Sierra
Bridgeville-Cottonwood-Lowgap_115kV_Routine_SHF_2022_198085 | Routine - Transmission | ERTC/Permit conditions not followed | North Valley
Molin 1102_12kV_EVM_NR_2130 Bohemian Hwy_2022 | Nest Review | Nesting Birds | North Coast
Humboldt-Trinity_115kV_TVMR_SHF_2022_189396_WP1 | Transmission Veg. Mgmt. Reliability | Other | North Valley
Tudor 1101_12kV_Routine_CDFW_2022 | Routine - Distribution | Area Not Assessed | Sierra
Bonnie Nook 1101_12kV_CEMA_MLOBLM_2022_204989 | CEMA - Distribution | RPM Not Implemented | Sierra
Drum Grass Valley Weimar_60kV_Routine_Empire Mine SHP_2022_198460 | Routine - Transmission | RPM Not Implemented | Sierra
Middle Fork Gold Hill_230kV_Routine_ENF_2022_198103 | Routine - Transmission | Monitoring | Sierra
Middle Fork Gold Hill_230kV_Routine_ENF_2022_198103 | Routine - Transmission | RPM Not Implemented | Sierra
Cancelled-Woodacre 1102_12kV_EVM_RR_F-00009469_2022 | EVM | Stormwater | Bay Area
Harris 1109_12kV_Routine_CZ_2022_199639 | Routine - Distribution | Other | North Coast
Placerville 2106_21kV_EVM_ENF_2022_WP2 | EVM | RPM Not Implemented | Sierra
Balch 1101_12kV_Routine_SNF_FERC_2022_199569 | Routine - Distribution | RPM Not Implemented | Central Valley
Balch 1101_12kV_Routine_SNF_FERC_2022_199569 | Routine - Distribution | RPM Not Implemented | Central Valley
Multi-Line CEMA Routine CZ 05/22 192063; 204171; 194590; 192412 | Routine - Distribution | Other | North Coast
Moraga-Castro Valley_230kV_Routine_EBMUD_2022 | Routine - Transmission | ERTC/Permit conditions not followed | Bay Area
P2 Trees-Alleghany 1101-B_12kV_Routine_TNF_2022 | Routine - Distribution | RPM Not Implemented | Sierra
Woodside 1101_12kV_EVM_MIDPEN_2022 | EVM | ERTC/Permit not obtained prior to work | Bay Area
P2 Trees - Halsey 1102_12kV_CEMA_BOR_2022_WP2 | CEMA - Distribution | ERTC/Permit not obtained prior to work | Sierra
Harris 1109_Humboldt County_Wetland Work_2022565 | Routine - Distribution | ERTC/Permit conditions not followed | North Coast
Cotati 1105_12kV_CEMA_CZ_2022_204203 | CEMA - Distribution | Wetlands/Waterways | North Coast
P2 - Alleghany 1101-A_12kV_Routine_TNF_CT_Hwy 49_2022 | Routine - Distribution | ERTC/Permit not obtained prior to work | Sierra
Colusa 1101_12kV_Class IV_CDFW_River Fire Emergency Work_2022 | Routine - Distribution | Area Not Assessed | North Valley
VM Environmental Issues - Humboldt | Other | Wetlands/Waterways | North Coast
VM Environmental Issues - Sonoma | Other | Stormwater | North Coast
VM Environmental Issues - San Mateo | Other | Stormwater | Bay Area
VM Environmental Issues - San Mateo | Other | Stormwater | Bay Area
VM Environmental Issues - Mendocino | Other | Wetlands/Waterways | North Coast
VM Environmental Issues - Marin | Other | Stormwater | Bay Area
VM Environmental Issues - Marin | Other | Stormwater | Bay Area
VM Environmental Issues - Marin | Other | Stormwater | Bay Area
VM Environmental Issues - Marin | Other | Stormwater | Bay Area
VM Environmental Issues - Marin | Other | Stormwater | Bay Area
VM Environmental Issues - Marin | Other |  | Bay Area
VM Environmental Issues - Shasta | Other | Wetlands/Waterways | North Valley
VM Environmental Issues - Contra Costa | Other | Stormwater | Bay Area
VM Environmental Issues - Santa Clara | Other | Stormwater | Bay Area
VM Environmental Issues - Napa | Other | Stormwater | Bay Area
VM Environmental Issues - Napa | Other | Stormwater | Bay Area
VM Environmental Issues - Napa | Other | Stormwater | Bay Area
VM Environmental Issues - Napa | Other | Stormwater | Bay Area
VM Environmental Issues - Napa | Other | Stormwater | Bay Area
VM Environmental Issues - Napa | Other | Stormwater | Bay Area
VM Environmental Issues - Napa | Other | Stormwater | Bay Area
VM Environmental Issues - Napa | Other | Stormwater | Bay Area
VM Environmental Issues - Napa | Other | Stormwater | Bay Area
VM Environmental Issues - Napa | Other | Stormwater | Bay Area
VM Environmental Issues - Butte | Other | Stormwater | North Valley
VM Environmental Issues - Santa Cruz | Other | Stormwater | Central Coast
VM Environmental Issues - Nevada | Other | Stormwater | Sierra
VM Environmental Issues - Nevada | Other | Stormwater | Sierra
Willow Creek 1103_12kV_CEMA_SHF_2022_195879 | CEMA - Distribution | RPM Not Implemented | North Coast
CR-Pit 1- Burney_230kV_Routine_FERC_2022 | Routine - Transmission | Monitoring | North Valley
P2 - Alleghany 1101-A_12kV_Routine_TNF_2022 | Routine - Distribution | ERTC/Permit not obtained prior to work | Sierra
P2 Trees-Rio Dell 1102_12kV_Routine_Humboldt Redwoods SP_2022_202705 | Routine - Distribution | ERTC/Permit not obtained prior to work | North Coast
Olema 1101_12kV_Routine_PNS_2020 | Routine - Distribution | Unauthorized Veg removal | Bay Area
Olema 1101_12kV_Routine_PNS_2020 | Routine - Distribution | Other | Bay Area
Pueblo 2103_21kV_EVM Black ECL_1300 Mt Veeder Rd_2021 | EVM | Wetlands/Waterways | Bay Area
Pueblo 2103_21kV_EVM Black ECL_1300 Mt Veeder Rd_2021 | EVM | Discharge | Bay Area
Willow Creek 1103_12kV_Routine_SRF_2021_193476 | Routine - Distribution | Resource Impacted | North Coast
Humboldt State Parks North SP_12kV_Routine_CZ_Multiple SP_2020_181256 | Routine - Distribution | ERTC/Permit not obtained prior to work | North Coast
Big Meadows 2101_21kV_CEMA_LNF_2021_195031 | CEMA - Distribution | Resource Impacted | North Valley
El Dorado PH_2101_21kV_Routine_ENF_2021_191644 | Routine - Distribution | RPM Not Implemented | Sierra
El Dorado PH_2101_21kV_Routine_ENF_2021_191644 | Routine - Distribution | RPM Not Implemented | Sierra
Grass Valley 1103_12kV_Routine_MLOBLM_2021_192480 | Routine - Distribution | RPM Not Implemented | Sierra
Alleghany 1101B Section 3_12kV_Routine_TNF_2021_191534 | Routine - Distribution | RPM Not Implemented | Sierra
Alleghany 1101 A_12kV_Routine_PNF_2021_191534 | Routine - Distribution | RPM Not Implemented | Sierra
Alleghany 1101 A_12kV_Routine_PNF_2021_191534 | Routine - Distribution |  | Sierra
Alleghany 1101 A_12kV_Routine_PNF_2021_191534 | Routine - Distribution | Monitoring | Sierra
Alleghany 1101 A_12kV_Routine_TNF_2021_191534 | Routine - Distribution | Monitoring | Sierra
Alleghany 1101 A_12kV_Routine_TNF_2021_191534 | Routine - Distribution | Tailboards | Sierra
P2 Trees-Pike City 1102_12kV_Routine_TNF_2022_WP3 | Routine - Distribution | ERTC/Permit not obtained prior to work | Sierra
Jessup 1102_12kV_EVM_NR_F-00010465_2022 | EVM |  | North Valley
Placerville 2106 - Georgetown_21kV_Routine_ENF_2022_199650 | Routine - Distribution | RPM Not Implemented | Sierra
P2 Trees-Alleghany 1101-A_12kV_Routine_TNF_2022_WP2 | Routine - Distribution | Monitoring | Sierra
Challenge 1102_12kV_Routine_MLOBLM_2022_199118 | Routine - Distribution |  | North Valley
Placerville 2106 21kV_TreesWorked_ENF_2022_06.13-15 | Routine - Distribution | ERTC/Permit not obtained prior to work | Sierra
Jefferson-Stanford_60kV_Routine_SFPUC_2022 | Routine - Transmission | Other | Bay Area
P2 Trees - Alleghany 1101-A_12kV_Routine_PNF_2022 | Routine - Distribution | RPM Not Implemented | Sierra
P2 Trees - Alleghany 1101-A_12kV_Routine_PNF_2022 | Routine - Distribution | Monitoring | Sierra
CR-Twain-Elizabeth_60kV_Routine_PNF_2022_198133 | Routine - Transmission | RPM Not Implemented | North Valley
CR Salt Springs Tiger Creek_115kV_Routine_ENF_FERC_2022_197977 | Routine - Transmission | RPM Not Implemented | Central Valley
Foresthill 1101_12kV_Routine_MLOBLM_2022_201384 | Routine - Distribution | Stationary Engine | Sierra
CR Donnells Curtis_115kV_Routine_FERC_STF_2022_198508 | Routine - Transmission | Area Not Assessed | Central Valley
CR Donnells Curtis_115kV_Routine_FERC_STF_2022_198508 | Routine - Transmission | RPM Not Implemented | Central Valley
Alleghany 1101-A_12kV_Routine_TNF_2022_200779 | Routine - Distribution | Monitoring | Sierra
Alleghany 1101-A_12kV_Routine_TNF_2022_200779 | Routine - Distribution | Monitoring | Sierra
Alleghany 1101-A_12kV_Routine_TNF_2022_200779 | Routine - Distribution | ERTC/Permit not obtained prior to work | Sierra
Alleghany 1101-A_12kV_Routine_TNF_2022_200779 | Routine - Distribution | ERTC/Permit not obtained prior to work | Sierra
Alleghany 1101-A_12kV_Routine_TNF_2022_200779 | Routine - Distribution | Wetlands/Waterways | Sierra
Multi Circuit_12kV_Routine_MLOBLM_2022_202387 | Routine - Distribution | RPM Not Implemented | Sierra
Multi Circuit_12kV_Routine_MLOBLM_2022_202387 | Routine - Distribution | RPM Not Implemented | Sierra
P2 Trees-Horseshoe 1102_12kV_Routine_Folsom Lake SRA_2022 | Routine - Distribution | ERTC/Permit not obtained prior to work | Sierra
Bear Valley 2105A_21kV_CEMA_STF_2022_205385 | CEMA - Distribution | RPM Not Implemented | Central Valley
P2 Trees - Rio Dell 1102_12kV_Routine_ACRBLM_2022_202705 | Routine - Distribution | ERTC/Permit not obtained prior to work | North Coast
Indian Flat 1104_12kV_CEMA_YNP_2022_205383 | CEMA - Distribution | Area Not Assessed | Central Valley
Woodside 1101_12kV_EVM-WM_F-00011307_2022 | EVM | Stormwater | Bay Area
CR-Caribou #2_60kV_Routine_PNF_FERC_2022_198150 | Routine - Transmission | RPM Not Implemented | North Valley
CR-Caribou #2_60kV_Routine_PNF_FERC_2022_198150 | Routine - Transmission | RPM Not Implemented | North Valley
CR-Caribou #2_60kV_Routine_PNF_FERC_2022_198150 | Routine - Transmission | RPM Not Implemented | North Valley
Kanaka 1101 Feather Falls_12kV_CEMA_BIA_2022_204561 | CEMA - Distribution | RPM Not Implemented | North Valley
Antler1101_12kV_EVM_SHF_2022_WP2 | EVM | RPM Not Implemented | North Valley
Kirker 2104_Routine_EBRPD_2022 | Routine - Distribution | ERTC/Permit not obtained prior to work | Bay Area
P2 Trees - Penryn 1103_12kV_Routine_Folsom Lake SRA_2022 | Routine - Distribution | ERTC/Permit not obtained prior to work | Sierra
551504_MOSS LANDING-GREEN VALLEY_115kV_RiparianReview_0 San Juan RD_2022 | Riparian Review | ERTC/Permit conditions not followed | Central Coast
Big Meadows 2101_12kV_CEMA_LNF_FERC_2022_204473 | CEMA - Distribution | ERTC/Permit not obtained prior to work | North Valley
Gansner 1101_12kV_CEMA_CT_Hwy 70/89_2022_201135 | CEMA - Distribution | ERTC/Permit not obtained prior to work | North Valley
P2 Trees-Perry 1101_12kV_CEMA_CZ_2022 | CEMA - Distribution |  | Central Coast
Volta 1102_12kV_EVM_CT_Hwy 44_2022_WP1 | EVM | Unauthorized Veg removal | North Valley
Volta 1102_12kV_EVM_CT_Hwy 44_2022_WP2 | EVM | ERTC/Permit not obtained prior to work | North Valley
Pit No 3 2101_21kV_Routine_FERC_McArthur-Burney Falls Memorial SP_2022_202480 | Routine - Distribution | RPM Not Implemented | North Valley
Middle Fork Gold Hill_230kV_Routine_ENF_NERC_2022_198021 | Routine - Transmission | RPM Not Implemented | Sierra
Salt Springs 2101_21kV_Routine_STF_2022_200362 | Routine - Distribution | Area Not Assessed | Central Valley
P2 Trees - Dunlap 1103 High_12kV_Routine_Kings Canyon NP_2022_202806 | Routine - Distribution | RPM Not Implemented | Central Valley
P2 Trees-Apple Hill 2102-3_21kV_Routine_ENF_2022 | Routine - Distribution | ERTC/Permit not obtained prior to work | Sierra
P2 Trees-Alpine Menlo_12kV_Routine_SMRPD_2022 | Routine - Distribution | ERTC/Permit conditions not followed | Bay Area
Kanaka 1101_12kV_EVM_BIA_Mooretown_2022 | EVM | RPM Not Implemented | North Valley
Salt Springs 2102_21kV_Routine_STF_2022_201857 | Routine - Distribution | Unauthorized Veg removal | Central Valley
Salt Springs 2102_21kV_Routine_STF_2022_201857 | Routine - Distribution | Area Not Assessed | Central Valley
Salmon Creek 1101_12kV_Routine_CZ_2022_202688_WP2 | Routine - Distribution |  | North Coast
Rising River 1101_12kV_Routine_LNF_SP_2022_202094 | Routine - Distribution | RPM Not Implemented | North Valley
Cancelled-DOBBINS 1101_12kV_Pole UDS_TNF_2022_1537411011 | Pole Utility Defensible Space | ERTC/Permit not obtained prior to work | Sierra
Girvan 1102_12kV_EVM_REDBLM_2022_WP2 | EVM | RPM Not Implemented | North Valley
Moraga-San Leandro #1_115kV_Routine_EBMUD_2022_198043 | Routine - Transmission | Other | Bay Area
Placerville 2106, Mountain Quarries 1101_21kV_Routine_HWY 193_CT_2022_200166 | Routine - Distribution | ERTC/Permit not obtained prior to work | Sierra
Callistoga 1101_12kV_CEMA_Robert Louis Stevenson SP_2022_204040 | CEMA - Distribution | Area Not Assessed | Bay Area
P2 Trees - Oakhurst 1103B_12kV_Routine_YNP_2022_F-00012428 | Routine - Distribution | Surveys | Central Valley
Halsey 1101_12kV_EVM_FERC_2022 | EVM | RPM Not Implemented | Sierra
CZ_Olema 1101_12kV_CEMA_2022_204096 | CEMA - Distribution |  | Bay Area
CR-Big Bar-Trinity_115kV_Routine_REDBLM_2022_197941 | Routine - Transmission | Wetlands/Waterways | North Coast
P2 Trees - Stanislaus 1701_17kV_Routine_BOR_2022_201196 | Routine - Distribution | ERTC/Permit not obtained prior to work | Central Valley
P2 Trees - Stanislaus 1701_17kV_Routine_MLOBLM_2022_201196 | Routine - Distribution | ERTC/Permit not obtained prior to work | Central Valley
Drum Higgins_115kV_Routine_MLOBLM_2022_198105 | Routine - Transmission | RPM Not Implemented | Sierra
Spaulding 1101_12kV_Routine_CT_2022_200497 | Routine - Distribution | ERTC/Permit not obtained prior to work | Sierra
Mountain Quarries Tap_60kV_Routine_Auburn SRA_BOR_2022_198019 | Routine - Transmission | ERTC/Permit not obtained prior to work | Sierra
Volta 1102 Upper_12kV_Routine_CT_HWY 44_2022_202274 | Routine - Distribution | ERTC/Permit not obtained prior to work | North Valley
Konocti 1102_12kV_EVM_RR_F-00013012_2022 | EVM | Wetlands/Waterways | North Coast
San Joaquin #3 1101_12kV_Routine_SNF_FERC_2022_202462 | Routine - Distribution | Other | Central Valley
Oro Fino 1102_12kV_Routine_CT_HWY 32_2022_201455 | Routine - Distribution | ERTC/Permit not obtained prior to work | North Valley
Jessup 1101_12kV_EVM_REDBLM_2022_WP2 | EVM | RPM Not Implemented | North Valley
Willits_NOV_Dec_Project Placeholder | EVM |  | North Coast
Challenge 1102 & Kanaka 1101_12kV_EVM_PNF_2022 | EVM | RPM Not Implemented | North Valley
Challenge 1102 & Kanaka 1101_12kV_EVM_PNF_2022 | EVM | ATC/Permit Management | North Valley
Multiple Circuits1102-1107_12kV_Routine_GNR_2021 | Routine - Distribution | Protected Species | Bay Area

## BMP 12 Waterway Inspections
Project: Project Name | Project: Workstream | Issue Category | Project: Region
INSPECTION_EVM_Central_Valley | EVM | Wetlands/Waterways | Central Valley
INSPECTION_EVM_Central_Valley | EVM | Wetlands/Waterways | Central Valley
INSPECTION_EVM_Central_Valley | EVM | Wetlands/Waterways | Central Valley
INSPECTION_EVM_Bay_Area | EVM | Stormwater | Bay Area
INSPECTION_EVM_Bay_Area | EVM | Wetlands/Waterways | Bay Area
INSPECTION_EVM_Bay_Area | EVM | Stormwater | Bay Area
INSPECTION_EVM_Bay_Area | EVM | Wetlands/Waterways | Bay Area
INSPECTION_EVM_Bay_Area | EVM | Wetlands/Waterways | Bay Area
INSPECTION_EVM_Bay_Area | EVM | Wetlands/Waterways | Bay Area
INSPECTION_EVM_Bay_Area | EVM | Wetlands/Waterways | Bay Area
INSPECTION_EVM_Bay_Area | EVM | Wetlands/Waterways | Bay Area
INSPECTION_EVM_Bay_Area | EVM | Wetlands/Waterways | Bay Area
INSPECTION_EVM_Bay_Area | EVM | Wetlands/Waterways | Bay Area
INSPECTION_EVM_Sierra | EVM | Stormwater | Sierra
INSPECTION_EVM_Sierra | EVM | Wetlands/Waterways | Sierra
INSPECTION_EVM_Sierra | EVM | Stormwater | Sierra
INSPECTION_EVM_Sierra | EVM | Wetlands/Waterways | Sierra
INSPECTION_EVM_Sierra | EVM | Stormwater | Sierra
INSPECTION_EVM_Sierra | EVM | Stormwater | Sierra
INSPECTION_EVM_Sierra | EVM | Stormwater | Sierra
INSPECTION_EVM_Sierra | EVM | Stormwater | Sierra
INSPECTION_EVM_Sierra | EVM | Stormwater | Sierra
INSPECTION_EVM_Sierra | EVM | Stormwater | Sierra
INSPECTION_EVM_Sierra | EVM | Stormwater | Sierra
INSPECTION_EVM_Sierra | EVM | Stormwater | Sierra
INSPECTION_EVM_Sierra | EVM | Wetlands/Waterways | Sierra
INSPECTION_EVM_Sierra | EVM | Stormwater | Sierra
INSPECTION_EVM_Sierra | EVM | Stormwater | Sierra
INSPECTION_EVM_Sierra | EVM | Stormwater | Sierra
INSPECTION_EVM_Sierra | EVM | Stormwater | Sierra
INSPECTION_EVM_Sierra | EVM | Stormwater | Sierra
INSPECTION_EVM_Sierra | EVM | Stormwater | Sierra
INSPECTION_EVM_North_Valley | EVM | Stormwater | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Stormwater | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Stormwater | North Valley
INSPECTION_EVM_North_Valley | EVM | Stormwater | North Valley
INSPECTION_EVM_North_Valley | EVM | Stormwater | North Valley
INSPECTION_EVM_North_Valley | EVM | Stormwater | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Stormwater | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Stormwater | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Stormwater | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Stormwater | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Stormwater | North Valley
INSPECTION_EVM_North_Valley | EVM | Stormwater | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Stormwater | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Valley | EVM | Wetlands/Waterways | North Valley
INSPECTION_EVM_North_Coast | EVM | Wetlands/Waterways | North Coast
INSPECTION_EVM_North_Coast | EVM | Wetlands/Waterways | North Coast
INSPECTION_EVM_North_Coast | EVM | Wetlands/Waterways | North Coast
INSPECTION_EVM_North_Coast | EVM | Wetlands/Waterways | North Coast
INSPECTION_EVM_North_Coast | EVM | Wetlands/Waterways | North Coast
INSPECTION_EVM_North_Coast | EVM | Wetlands/Waterways | North Coast
INSPECTION_EVM_North_Coast | EVM | Wetlands/Waterways | North Coast
INSPECTION_EVM_North_Coast | EVM | Wetlands/Waterways | North Coast
INSPECTION_EVM_North_Coast | EVM | Wetlands/Waterways | North Coast
INSPECTION_EVM_North_Coast | EVM | Wetlands/Waterways | North Coast
INSPECTION_EVM_North_Coast | EVM | Wetlands/Waterways | North Coast
INSPECTION_EVM_North_Coast | EVM | Wetlands/Waterways | North Coast
INSPECTION_EVM_North_Coast | EVM | Wetlands/Waterways | North Coast
INSPECTION_EVM_North_Coast | EVM | Wetlands/Waterways | North Coast
INSPECTION_EVM_North_Coast | EVM | Wetlands/Waterways | North Coast
INSPECTION_EVM_North_Coast | EVM | Stormwater | North Coast
INSPECTION_EVM_North_Coast | EVM | Wetlands/Waterways | North Coast
INSPECTION_EVM_North_Coast | EVM | Stormwater | North Coast
INSPECTION_EVM_North_Coast | EVM | Stormwater | North Coast
INSPECTION_EVM_North_Coast | EVM | Wetlands/Waterways | North Coast
INSPECTION_EVM_North_Coast | EVM | Wetlands/Waterways | North Coast
INSPECTION_EVM_North_Coast | EVM | Wetlands/Waterways | North Coast
INSPECTION_EVM_North_Coast | EVM | Wetlands/Waterways | North Coast
INSPECTION_EVM_North_Coast | EVM | Wetlands/Waterways | North Coast
INSPECTION_EVM_North_Coast | EVM | Wetlands/Waterways | North Coast
INSPECTION_EVM_North_Coast | EVM | Wetlands/Waterways | North Coast
INSPECTION_EVM_North_Coast | EVM | Wetlands/Waterways | North Coast
INSPECTION_EVM_North_Coast | EVM | Wetlands/Waterways | North Coast