## Legend
Action | 2022 | 2023
i) The CPZs that underwent review, | See column B on tab "2022 MOREs" | See columns B & C on tab "2023 MOREs"
ii) The result of each CPZ's review, | See column C on tab "2022 MOREs" | See column D on tab "2023 MOREs"
iii) If the CPZ's review had action items generated | See column C on tab "2022 MOREs" | See column D on tab "2023 MOREs"
iv) Detailed about each action item, if applicable | See column C on tab "2022 MORE Action Items" | See column D on tab "2023 MORE Action Items"
v) If an action item was not created, provide a brief explanation as to why, | See column C on tab "2022 MOREs" | See column D on tab "2023 MOREs"
vi) The status of each action item, | See column G on tab "2022 MORE Action Items" | See column H on tab "2023 MORE Action Items"
vii) Completion due date of each action item, | See column E on tab "2022 MORE Action Items" | See column F on tab "2023 MORE Action Items"
viii) The date each action item was completed, if applicable, | See column F on tab "2022 MORE Action Items" | See column G on tab "2023 MORE Action Items"
ix) If an action item was not completed by its due date, provide a brief explanation as to why it was not completed on time | See Narrative Response | See Narrative Response

## Action Item Definitions
Action | Description
Accelerate EPSS Activation | Signifies a request regarding EPSS settings on the circuit/device.
Ad Hoc Fault Indicator Installation ¦ Escalation: Fault Indicators ¦ Fault Indicator Assessment ¦ FI Request/Installations | Signifies that an Action Item owner should identify if additional fault indicators are needed and send to PG&E dispatch for completion
Additional Detailed Patrol ¦ Patrol ¦ Escalation: Patrol ¦ ORT Patrol ¦ Request Accelerated Patrol | Signifies that an Additional Detailed Patrol opportunity should be reviewed and, if necessary, initiated and sent to dispatch for completion.
Animal Guard ¦ Escalation: Animal Guard ¦ Escalation: Bird Tag | Signifies that locations with Animal Outages should be mitigated to prevent future outages.
Animal Mitigation Review | Signifies a review of Animal Mitigation activites on the circuit/device and if they could be accelerated due to outage activity (specifically Animal-caused outages).
Circuit Configuration | Signifies a review of the circuit configuration and if any adjustments are necessary.
Customer Impact | Signifies a review of the customer experiencing multiple interruption (CEMI) metric for the circuit/device.
EC Tag Work ¦ EC/ER Tag ¦ New Tag Creation | Signifies a review of EC Tags on the circuit/device and if any should be escalated if necessary for completion.
Escalation: Alarm Mode | Signifies a review of the circuit/device with respect to the Alarm Mode of a device with DCD settings.
Escalation: CPUC Complaint | Signifies a review of the circuit/device in response to a CPUC complaint
Escalation: Repair | Signifies an escalation of repair work on a circuit/device.
Escalation: Vegetation XOC ¦ Escalation: XOC | Signifies an escalation for a Vegetation Extent of Condition (XOC) project in response to an EPSS outage.
FuseSaver Installation | Signifies that either a FuseSaver was to be installed on the circuit and that the Team would push for an accelerated installation if possible or that a FuseSaver installation would be of potential benefit.
ILIS Record Update ¦ Cause Investigation | Signifies an investigation into the Cause of an EPSS Outage in order to push for a cause code change.
Inspection Review | Signifies a review of the Inspection activities on the circuit/device.
Investigation ¦ Escalation: Investigation | Signifies a general review or investigation into the circuit/device in order to improve reliability.
Line Sensor Installation | Signifies that either a Line Sensor was to be installed on the circuit and that the Team would push for an accelerated installation if possible or that a Line Sensor installation would be of potential benefit.
Load Transfer | Signifies when customers were transferred from one circuit/device to another for better reliability
MORe Investigation Request ¦ Escalation: ORT Investigation ¦ Escalate ORT Review | Signifies a general review or investigation into the circuit/device in order to improve reliability.
Outage Information Gathering ¦ ORT GDAT Prioritization ¦ ORT Action Item Follow Up | Signifies a general review of the outages or to collaborate with the Outage Review Team (ORT) to push for improved reliability.
Patrol Zones | Signifies a review of potential patrol zones in the field as a part of a potential Additional Detailed Patrol.
Planned Work and Opportunities ¦ Project ¦ Project(s) ¦ Proposed Project ¦ Escalation: Project ¦ Sectionalization Assessment ¦ Request Accelerated Project Timeline | Signifies a review of planned Line Recloser and FuseSaver projects in the area and to recommend acceleration if appropriate. Additionally, Teams should assess additional Reliability opportunities for circuit configuration adjustment and Line Recloser and FuseSaver installations for the future
Proactive Fault Indicator Installation | Signifies an escalated request to install fault indicators in line with Proactive Fault Indicator (FI) Program.
Protection/Coordination Review ¦ Settings Review ¦ Escalation: Settings Review ¦ Planning/Coordination Review ¦ Escalation: DCD Settings ¦ Escalation: Abnormal Configuration | Signifies a review of current EPSS settings to determine if there is an opportunity to modify or improve settings
Review CAIDI Performance ¦ Review CAIDI ¦ Escalation: CAIDI Review | Signifies a review of outages with high CAIDIs to identify potential improvement opportunities
Review Outage for Cause | Signifies a review of outages for potential cause code changes
Review Response Time | Signifies a review of outages with Response Time over 60 to identify potential improvement opportunities
Settings Adjustment ¦ Escalation: Confirm Settings Adjustment | Upon a Settings Review being complete, Settings would either need to be adjusted or not adjusted due to coordination issues. If the Settings were adjusted for improved coordination, this Action signified that it took place on a circuit/device.
Tag Prioritization | Signifies a review of EC Tags on the circuit/device and if any should be escalated for completion.
Trigger Level Outage Actions | Signifies a collaboration with other PG&E Teams to make sure that trigger-level reviews of outages are taking place and that Action Items are being initiated.
Validate Ad Hoc Fault Indicators Installation | Signifies that if Fault Indicators (FIs) were slated to be installed on the circuit/device, this Action was to confirm that they were successfully installed.
Vegetation Management Cycle Review ¦ Escalation: Veg Review ¦ Vegetation Work ¦ Vegetation Work Assessment | Signifies a review of the Vegetation Management activities on the circuit/device and if they could be accelerated due to outage activity (specifically Vegetation-caused outages).

## 2022 MOREs
Circuit | Status
ANNAPOLIS 1101 | Complete - additional action(s) created
APPLE HILL 2102 | Complete - additional action(s) created
ATASCADERO 1102 | Complete - additional action(s) created
ATASCADERO 1103 | Complete - additional action(s) created
AUBERRY 1101 | Complete - additional action(s) created
AUBERRY 1102 | Complete - additional action(s) created
BEAR VALLEY 2101 | Complete - additional action(s) created
BEAR VALLEY 2105 | Complete - additional action(s) created
BELLEVUE 2101 | Complete - no additional action required
BELLEVUE 2103 | Complete - additional action(s) created
BEN LOMOND 0401 | Complete - additional action(s) created
BEN LOMOND 1101 | Complete - additional action(s) created
BIG BASIN 1101 | Complete - additional action(s) created
BIG BASIN 1102 | Complete - additional action(s) created
BIG BEND 1102 | Complete - no additional action required
BONNIE NOOK 1102 | Complete - no additional action required
BRENTWOOD 2105 | Complete - additional action(s) created
BRUNSWICK 1102 | Complete - additional action(s) created
BRUNSWICK 1105 | Complete - additional action(s) created
BRUNSWICK 1106 | Complete - additional action(s) created
BRUNSWICK 1110 | Complete - additional action(s) created
BUELLTON 1101 | Complete - additional action(s) created
BURNS 2101 | Complete - additional action(s) created
CALAVERAS CEMENT 1101 | Complete - additional action(s) created
CALISTOGA 1101 | Complete - additional action(s) created
CALISTOGA 1102 | Complete - additional action(s) created
CALPELLA 1101 | Complete - additional action(s) created
CAMP EVERS 2103 | Complete - additional action(s) created
CAMP EVERS 2105 | Complete - additional action(s) created
CAMP EVERS 2106 | Complete - additional action(s) created
CHOLAME 2102 | Complete - additional action(s) created
CLAY 1101 | Complete - additional action(s) created
CLAYTON 2212 | Complete - no additional action required
CLOVERDALE 1102 | Complete - no additional action required
COARSEGOLD 2103 | Complete - additional action(s) created
COARSEGOLD 2104 | Complete - additional action(s) created
COLUMBIA HILL 1101 | Complete - additional action(s) created
CORNING 1101 | Complete - additional action(s) created
CORNING 1102 | Complete - no additional action required
CORRAL 1101 | Complete - additional action(s) created
CORRAL 1103 | Complete - additional action(s) created
COTTONWOOD 1103 | Complete - additional action(s) created
COVELO 1101 | Complete - additional action(s) created
CURTIS 1702 | Complete - additional action(s) created
CURTIS 1703 | Complete - additional action(s) created
CURTIS 1704 | Complete - additional action(s) created
CURTIS 1705 | Complete - additional action(s) created
DEL MONTE 2104 | Complete - no additional action required
DIAMOND SPRINGS 1103 | Complete - additional action(s) created
DUNBAR 1101 | Complete - additional action(s) created
DUNLAP 1102 | Complete - additional action(s) created
ELECTRA 1101 | Complete - additional action(s) created
ELK CREEK 1101 | Complete - additional action(s) created
EMERALD LAKE 0401 | Complete - no additional action required
EMERALD LAKE 0402 | Complete - no additional action required
FAIRVIEW 2207 | Complete - additional action(s) created
FITCH MOUNTAIN 1113 | Complete - no additional action required
FOOTHILL 1102 | Complete - additional action(s) created
FORESTHILL 1101 | Complete - additional action(s) created
FROGTOWN 1701 | Complete - additional action(s) created
FROGTOWN 1702 | Complete - additional action(s) created
GABILAN 1101 | Complete - additional action(s) created
GANSNER 1101 | Complete - additional action(s) created
GARBERVILLE 1101 | Complete - additional action(s) created
GARBERVILLE 1102 | Complete - additional action(s) created
GEYSERVILLE 1101 | Complete - additional action(s) created
GEYSERVILLE 1102 | Complete - additional action(s) created
GREEN VALLEY 2101 | Complete - additional action(s) created
GUSTINE 1102 | Complete - additional action(s) created
HALF MOON BAY 1103 | Complete - additional action(s) created
HALSEY 1101 | Complete - additional action(s) created
HALSEY 1102 | Complete - additional action(s) created
HARTLEY 1101 | Complete - additional action(s) created
HATTON 1101 | Complete - no additional action required
HICKS 2101 | Complete - additional action(s) created
HIGGINS 1103 | Complete - additional action(s) created
HIGGINS 1104 | Complete - additional action(s) created
HIGHLANDS 1102 | Complete - additional action(s) created
HOLLISTER 2105 | Complete - additional action(s) created
HOOPA 1101 | Complete - additional action(s) created
HOPLAND 1101 | Complete - additional action(s) created
HORSESHOE 1104 | Complete - additional action(s) created
JAMESON 1105 | Complete - additional action(s) created
JESSUP 1101 | Complete - additional action(s) created
JOLON 1102 | Complete - additional action(s) created
JOLON 1103 | Complete - additional action(s) created
KING CITY 1103 | Complete - no additional action required
KONOCTI 1102 | Complete - additional action(s) created
LAKEVILLE 1102 | Complete - additional action(s) created
LAURELES 1111 | Complete - additional action(s) created
LINCOLN 1104 | Complete - additional action(s) created
LOGAN CREEK 2102 | Complete - no additional action required
LOS GATOS 1106 | Complete - additional action(s) created
LOS GATOS 1107 | Complete - additional action(s) created
LOS OSITOS 2103 | Complete - additional action(s) created
LUCERNE 1103 | Complete - additional action(s) created
MADISON 2101 | Complete - additional action(s) created
Magunden 1108 | Complete - additional action(s) created
MARIPOSA 2101 | Complete - additional action(s) created
MARIPOSA 2102 | Complete - additional action(s) created
MC ARTHUR 1101 | Complete - additional action(s) created
MENLO 1102 | Complete - additional action(s) created
MERCED FALLS 1102 | Complete - additional action(s) created
MIDDLETOWN 1101 | Complete - no additional action required
MIRABEL 1101 | Complete - additional action(s) created
MIWUK 1702 | Complete - additional action(s) created
MOLINO 1102 | Complete - additional action(s) created
MONTE RIO 1111 | Complete - additional action(s) created
MONTICELLO 1101 | Complete - additional action(s) created
MORGAN HILL 2105 | Complete - additional action(s) created
MORGAN HILL 2109 | Complete - additional action(s) created
MORGAN HILL 2111 | Complete - additional action(s) created
MOUNTAIN QUARRIES 2101 | Complete - additional action(s) created
NARROWS 2102 | Complete - additional action(s) created
NARROWS 2105 | Complete - additional action(s) created
NORTH BRANCH 1101 | Complete - additional action(s) created
NORTH DUBLIN 2103 | Complete - additional action(s) created
OAKHURST 1101 | Complete - no additional action required
OCEANO 1104 | Complete - additional action(s) created
OILFIELDS 1103 | Complete - additional action(s) created
OLEMA 1101 | Complete - additional action(s) created
OLETA 1102 | Complete - additional action(s) created
ORO FINO 1102 | Complete - no additional action required
PANORAMA 1102 | Complete - additional action(s) created
PARADISE 1105 | Complete - no additional action required
PAUL SWEET 2106 | Complete - additional action(s) created
PENRYN 1103 | Complete - additional action(s) created
PENRYN 1105 | Complete - additional action(s) created
PEORIA 1701 | Complete - additional action(s) created
PEORIA 1704 | Complete - additional action(s) created
PEORIA 1705 | Complete - additional action(s) created
PETALUMA C 1109 | Complete - additional action(s) created
PHILO 1102 | Complete - additional action(s) created
PIERCY 2110 | Complete - no additional action required
PINE GROVE 1102 | Complete - no additional action required
PLACERVILLE 2106 | Complete - additional action(s) created
POSO MOUNTAIN 2101 | Complete - additional action(s) created
POSO MOUNTAIN 2103 | Complete - no additional action required
PUEBLO 1104 | Complete - no additional action required
PUEBLO 2102 | Complete - no additional action required
PUEBLO 2103 | Complete - additional action(s) created
PUEBLO 2104 | Complete - additional action(s) created
PUTAH CREEK 1105 | Complete - additional action(s) created
RACETRACK 1703 | Complete - no additional action required
RED BLUFF 1104 | Complete - additional action(s) created
REDBUD 1101 | Complete - no additional action required
REDBUD 1102 | Complete - no additional action required
RESERVATION ROAD 1101 | Complete - additional action(s) created
RESERVATION ROAD 1102 | Complete - additional action(s) created
RIO DELL 1102 | Complete - additional action(s) created
ROB ROY 2104 | Complete - additional action(s) created
ROB ROY 2105 | Complete - additional action(s) created
ROSSMOOR 1106 | Complete - no additional action required
ROSSMOOR 1108 | Complete - additional action(s) created
SALT SPRINGS 2102 | Complete - no additional action required
SAN JUSTO 1101 | Complete - additional action(s) created
SAN LUIS OBISPO 1104 | Complete - additional action(s) created
SAN LUIS OBISPO 1107 | Complete - additional action(s) created
SAN RAMON 2103 | Complete - additional action(s) created
SAN RAMON 2107 | Complete - additional action(s) created
SAND CREEK 1103 | Complete - additional action(s) created
SANTA YNEZ 1101 | Complete - additional action(s) created
SANTA YNEZ 1102 | Complete - no additional action required
SANTA YNEZ 1104 | Complete - no additional action required
SARATOGA 1103 | Complete - additional action(s) created
SHINGLE SPRINGS 2105 | Complete - no additional action required
SHINGLE SPRINGS 2108 | Complete - additional action(s) created
SHINGLE SPRINGS 2109 | Complete - additional action(s) created
SILVERADO 2102 | Complete - additional action(s) created
SILVERADO 2103 | Complete - additional action(s) created
SILVERADO 2104 | Complete - additional action(s) created
SILVERADO 2105 | Complete - additional action(s) created
SISQUOC 1102 | Complete - additional action(s) created
SOLEDAD 2102 | Complete - no additional action required
SOLEDAD 2105 | Complete - no additional action required
SONOMA 1102 | Complete - additional action(s) created
SONOMA 1105 | Complete - no additional action required
SONOMA 1107 | Complete - additional action(s) created
STAFFORD 1102 | Complete - additional action(s) created
STANISLAUS 1701 | Complete - additional action(s) created
STANISLAUS 1702 | Complete - additional action(s) created
STONE CORRAL 1108 | Complete - additional action(s) created
SUNOL 1101 | Complete - additional action(s) created
SWIFT 2102 | Complete - additional action(s) created
TASSAJARA 2103 | Complete - additional action(s) created
TEMPLETON 2110 | Complete - additional action(s) created
TEMPLETON 2111 | Complete - additional action(s) created
TEMPLETON 2113 | Complete - additional action(s) created
TIVY VALLEY 1107 | Complete - additional action(s) created
TYLER 1105 | Complete - additional action(s) created
TYLER 1106 | Complete - additional action(s) created
TYLER 1107 | Complete - additional action(s) created
UPPER LAKE 1101 | Complete - additional action(s) created
VASCO 1102 | Complete - additional action(s) created
VOLTA 1101 | Complete - additional action(s) created
WEST POINT 1102 | Complete - additional action(s) created
WHITMORE 1101 | Complete - additional action(s) created
WILLITS 1103 | Complete - additional action(s) created
WISE 1102 | Complete - additional action(s) created
WOODACRE 1102 | Complete - additional action(s) created
WYANDOTTE 1103 | Complete - no additional action required
WYANDOTTE 1107 | Complete - no additional action required
WYANDOTTE 1109 | Complete - no additional action required

## 2022 MORE Action Items
Circuit | Action | Date Action Item Initiated | Target Completion Date of Action Item | Date Action Item Completed | Status
ANNAPOLIS 1101 | Ad Hoc Fault Indicator Installation | 2022-11-08 | 2022-11-22 | 2022-11-14 | Complete
ANNAPOLIS 1101 | Settings Review | 2022-11-08 | 2022-11-22 | 2022-11-12 | Complete
APPLE HILL 2102 | Ad Hoc Fault Indicator Installation | 2022-06-04 | 2022-06-11 | 2022-06-07 | Complete
APPLE HILL 2102 | Additional Detailed Patrol | 2022-06-04 | 2022-06-11 | 2022-06-07 | Complete
APPLE HILL 2102 | Ad Hoc Fault Indicator Installation | 2022-07-01 | 2022-07-08 | 2022-07-14 | Complete
APPLE HILL 2102 | Additional Detailed Patrol | 2022-07-01 | 2022-07-06 | 2022-07-14 | Complete
APPLE HILL 2102 | Customer Impact | 2022-07-01 | 2022-07-08 | 2022-07-07 | Complete
APPLE HILL 2102 | Planned Work and Opportunities | 2022-07-01 | 2022-07-28 | 2022-08-05 | Complete
APPLE HILL 2102 | Planned Work and Opportunities | 2022-07-01 | 2022-07-28 | 2022-08-05 | Complete
APPLE HILL 2102 | Settings Review | 2022-07-01 | 2022-07-07 | 2022-07-08 | Complete
APPLE HILL 2102 | Trigger Level Outage Actions | 2022-11-04 | 2022-11-18 | 2022-11-04 | Complete
APPLE HILL 2102 | Trigger Level Outage Actions | 2022-11-04 | 2022-11-18 | 2022-11-04 | Complete
APPLE HILL 2102 | Trigger Level Outage Actions | 2022-11-04 | 2022-11-18 | 2022-11-04 | Complete
APPLE HILL 2102 | Trigger Level Outage Actions | 2022-11-04 | 2022-11-18 | 2022-11-04 | Complete
APPLE HILL 2102 | Trigger Level Outage Actions | 2022-11-04 | 2022-11-18 | 2022-11-04 | Complete
APPLE HILL 2102 | Trigger Level Outage Actions | 2022-11-04 | 2022-11-18 | 2022-11-04 | Complete
APPLE HILL 2102 | Trigger Level Outage Actions | 2022-11-04 | 2022-11-18 | 2022-11-04 | Complete
ATASCADERO 1102 | Ad Hoc Fault Indicator Installation | 2022-09-13 | 2022-09-27 | 2022-09-28 | Complete
ATASCADERO 1102 | Additional Detailed Patrol | 2022-09-13 | 2022-09-27 | 2022-09-28 | Complete
ATASCADERO 1102 | Planned Work and Opportunities | 2022-09-13 | 2022-09-27 | 2022-09-28 | Complete
ATASCADERO 1102 | Settings Review | 2022-09-13 | 2022-09-27 | 2022-09-28 | Complete
ATASCADERO 1103 | Ad Hoc Fault Indicator Installation | 2022-08-03 | 2022-08-17 | 2022-09-06 | Complete
ATASCADERO 1103 | Additional Detailed Patrol | 2022-08-03 | 2022-08-17 | 2022-09-06 | Complete
ATASCADERO 1103 | Animal Guard | 2022-08-03 | 2022-08-17 | 2023-02-23 | Complete
ATASCADERO 1103 | Customer Impact | 2022-08-03 | 2022-08-17 | 2022-08-05 | Complete
ATASCADERO 1103 | Planned Work and Opportunities | 2022-08-03 | 2022-08-17 | 2022-08-10 | Complete
ATASCADERO 1103 | Planned Work and Opportunities | 2022-08-03 | 2022-08-17 | 2022-08-10 | Complete
ATASCADERO 1103 | Settings Review | 2022-08-03 | 2022-08-17 | 2022-08-11 | Complete
ATASCADERO 1103 | Vegetation Management Cycle Review | 2022-08-03 | 2022-08-17 | 2022-08-10 | Complete
AUBERRY 1101 | Ad Hoc Fault Indicator Installation | 2022-08-08 | 2022-08-22 | 2022-08-29 | Complete
AUBERRY 1101 | Additional Detailed Patrol | 2022-08-08 | 2022-08-22 | 2022-08-29 | Complete
AUBERRY 1101 | Planned Work and Opportunities | 2022-08-08 | 2022-08-22 | 2022-08-31 | Complete
AUBERRY 1101 | Planned Work and Opportunities | 2022-08-08 | 2022-08-22 | 2022-08-31 | Complete
AUBERRY 1101 | Settings Review | 2022-08-08 | 2022-08-22 | 2022-08-31 | Complete
AUBERRY 1101 | Vegetation Management Cycle Review | 2022-08-08 | 2022-08-22 | 2022-08-09 | Complete
AUBERRY 1102 | Ad Hoc Fault Indicator Installation | 2022-09-06 | 2022-09-20 | 2022-10-18 | Complete
AUBERRY 1102 | Additional Detailed Patrol | 2022-09-06 | 2022-09-20 | 2022-10-18 | Complete
AUBERRY 1102 | Animal Guard | 2022-09-06 | 2022-09-20 | 2022-09-28 | Complete
AUBERRY 1102 | Planned Work and Opportunities | 2022-09-06 | 2022-09-20 | 2022-09-28 | Complete
AUBERRY 1102 | Settings Review | 2022-09-06 | 2022-09-20 | 2022-09-15 | Complete
BEAR VALLEY 2101 | Ad Hoc Fault Indicator Installation | 2022-08-08 | 2022-08-22 | 2023-06-05 | Complete
BEAR VALLEY 2101 | Planned Work and Opportunities | 2022-08-08 | 2022-08-22 | 2022-10-31 | Complete
BEAR VALLEY 2101 | Settings Review | 2022-08-08 | 2022-08-22 | 2022-08-31 | Complete
BEAR VALLEY 2105 | Ad Hoc Fault Indicator Installation | 2022-09-20 | 2022-10-04 | 2022-10-18 | Complete
BEAR VALLEY 2105 | Additional Detailed Patrol | 2022-09-20 | 2022-10-04 | 2022-10-18 | Complete
BEAR VALLEY 2105 | Animal Guard | 2022-09-20 | 2022-10-04 | 2022-09-21 | Complete
BEAR VALLEY 2105 | Planned Work and Opportunities | 2022-09-20 | 2022-10-04 | 2022-11-14 | Complete
BEAR VALLEY 2105 | Settings Review | 2022-09-20 | 2022-10-04 | 2022-10-07 | Complete
BELLEVUE 2103 | Ad Hoc Fault Indicator Installation | 2022-09-13 | 2022-09-27 | 2022-09-23 | Complete
BELLEVUE 2103 | Additional Detailed Patrol | 2022-09-13 | 2022-09-27 | 2022-09-23 | Complete
BELLEVUE 2103 | Animal Guard | 2022-09-13 | 2022-09-27 | 2022-09-23 | Complete
BELLEVUE 2103 | Planned Work and Opportunities | 2022-09-13 | 2022-09-27 | 2022-09-18 | Complete
BELLEVUE 2103 | Proactive Fault Indicator Installation | 2022-09-13 | 2022-09-27 | 2022-07-31 | Complete
BELLEVUE 2103 | Settings Review | 2022-09-13 | 2022-09-27 | 2022-10-26 | Complete
BELLEVUE 2103 | Vegetation Management Cycle Review | 2022-09-13 | 2022-09-27 | 2022-10-19 | Complete
BEN LOMOND 0401 | Vegetation Management Cycle Review | 2022-07-13 | 2022-07-27 | 2022-09-06 | Complete
BEN LOMOND 0401 | Vegetation Management Cycle Review | 2022-10-05 | 2022-10-19 | 2022-10-27 | Complete
BEN LOMOND 1101 | Vegetation Management Cycle Review | 2022-09-26 | 2022-10-10 | 2022-10-27 | Complete
BIG BASIN 1101 | Ad Hoc Fault Indicator Installation | 2022-09-02 | 2022-09-16 | 2022-09-28 | Complete
BIG BASIN 1101 | Additional Detailed Patrol | 2022-09-02 | 2022-09-16 | 2022-09-28 | Complete
BIG BASIN 1101 | Planned Work and Opportunities | 2022-09-02 | 2022-09-16 | 2022-09-28 | Complete
BIG BASIN 1101 | Proactive Fault Indicator Installation | 2022-09-02 | 2022-09-16 | 2022-06-17 | Complete
BIG BASIN 1101 | Settings Review | 2022-09-02 | 2022-09-16 | 2022-09-28 | Complete
BIG BASIN 1101 | Vegetation Management Cycle Review | 2022-09-02 | 2022-09-16 | 2022-09-09 | Complete
BIG BASIN 1102 | Ad Hoc Fault Indicator Installation | 2022-09-09 | 2022-09-23 | 2022-10-18 | Complete
BIG BASIN 1102 | Additional Detailed Patrol | 2022-09-09 | 2022-09-23 | 2022-10-18 | Complete
BIG BASIN 1102 | Animal Guard | 2022-09-09 | 2022-09-23 | 2022-09-30 | Complete
BIG BASIN 1102 | Planned Work and Opportunities | 2022-09-09 | 2022-09-23 | 2022-10-18 | Complete
BIG BASIN 1102 | Proactive Fault Indicator Installation | 2022-09-09 | 2022-09-23 | 2022-06-17 | Complete
BIG BASIN 1102 | Settings Review | 2022-09-09 | 2022-09-23 | 2022-10-18 | Complete
BIG BASIN 1102 | Vegetation Management Cycle Review | 2022-09-09 | 2022-09-23 | 2022-10-26 | Complete
BRENTWOOD 2105 | Additional Detailed Patrol | 2022-07-14 | 2022-07-28 | 2022-07-20 | Complete
BRENTWOOD 2105 | Planned Work and Opportunities | 2022-07-14 | 2022-07-28 | 2022-07-20 | Complete
BRENTWOOD 2105 | Planned Work and Opportunities | 2022-07-14 | 2022-07-28 | 2022-07-20 | Complete
BRENTWOOD 2105 | Settings Review | 2022-07-14 | 2022-07-28 | 2022-07-20 | Complete
BRENTWOOD 2105 | Vegetation Management Cycle Review | 2022-07-14 | 2022-07-28 | 2022-07-14 | Complete
BRUNSWICK 1102 | Animal Guard | 2022-09-26 | 2022-10-10 | 2022-12-13 | Complete
BRUNSWICK 1102 | Animal Mitigation Review | 2022-09-26 | 2022-10-10 | 2022-10-19 | Complete
BRUNSWICK 1102 | Planned Work and Opportunities | 2022-09-26 | 2022-10-10 | 2022-10-12 | Complete
BRUNSWICK 1102 | Review CAIDI Performance | 2022-09-26 | 2022-10-10 | 2022-12-19 | Complete
BRUNSWICK 1102 | Vegetation Management Cycle Review | 2022-09-26 | 2022-11-11 | 2022-11-11 | Complete
BRUNSWICK 1105 | Ad Hoc Fault Indicator Installation | 2022-09-06 | 2022-09-20 | 2022-12-27 | Complete
BRUNSWICK 1105 | Additional Detailed Patrol | 2022-09-06 | 2022-09-20 | 2022-12-13 | Complete
BRUNSWICK 1105 | Animal Guard | 2022-09-06 | 2022-09-20 | 2022-12-13 | Complete
BRUNSWICK 1105 | Planned Work and Opportunities | 2022-09-06 | 2022-09-20 | 2022-09-23 | Complete
BRUNSWICK 1105 | Proactive Fault Indicator Installation | 2022-09-06 | 2022-10-31 | 2022-06-17 | Complete
BRUNSWICK 1105 | Settings Review | 2022-09-06 | 2022-09-20 | 2022-10-06 | Complete
BRUNSWICK 1106 | Animal Guard | 2022-09-20 | 2022-10-04 | 2022-12-13 | Complete
BRUNSWICK 1106 | Vegetation Management Cycle Review | 2022-09-20 | 2022-10-04 | 2022-10-11 | Complete
BRUNSWICK 1110 | Ad Hoc Fault Indicator Installation | 2022-08-26 | 2022-09-09 | 2022-12-27 | Complete
BRUNSWICK 1110 | Additional Detailed Patrol | 2022-08-26 | 2022-09-09 | 2022-12-13 | Complete
BRUNSWICK 1110 | Animal Guard | 2022-08-26 | 2022-09-09 | 2022-08-26 | Complete
BRUNSWICK 1110 | Planned Work and Opportunities | 2022-08-26 | 2022-09-09 | 2022-09-18 | Complete
BRUNSWICK 1110 | Settings Review | 2022-08-26 | 2022-09-09 | 2022-09-15 | Complete
BUELLTON 1101 | Ad Hoc Fault Indicator Installation | 2022-09-20 | 2022-10-04 | 2022-10-05 | Complete
BUELLTON 1101 | Additional Detailed Patrol | 2022-09-20 | 2022-10-04 | 2022-10-05 | Complete
BUELLTON 1101 | Animal Guard | 2022-09-20 | 2022-10-04 | 2023-05-26 | Complete
BUELLTON 1101 | Planned Work and Opportunities | 2022-09-20 | 2022-10-04 | 2022-10-11 | Complete
BUELLTON 1101 | Vegetation Management Cycle Review | 2022-09-20 | 2022-10-04 | 2022-10-27 | Complete
BURNS 2101 | Review Outage for Cause | 2022-11-08 | 2022-11-22 | 2022-12-01 | Complete
BURNS 2101 | Vegetation Management Cycle Review | 2022-11-08 | 2022-11-22 | 2022-11-22 | Complete
BURNS 2101 | Settings Review | 2022-11-29 | 2022-12-13 | 2022-11-29 | Complete
CALAVERAS CEMENT 1101 | Ad Hoc Fault Indicator Installation | 2022-10-06 | 2022-10-20 | 2022-10-07 | Complete
CALAVERAS CEMENT 1101 | Additional Detailed Patrol | 2022-10-06 | 2022-10-20 | 2022-10-07 | Complete
CALAVERAS CEMENT 1101 | Animal Guard | 2022-10-06 | 2022-10-20 | 2022-10-18 | Complete
CALAVERAS CEMENT 1101 | Planned Work and Opportunities | 2022-10-06 | 2022-10-20 | 2022-11-16 | Complete
CALAVERAS CEMENT 1101 | Proactive Fault Indicator Installation | 2022-10-06 | 2022-10-20 | 2022-09-09 | Complete
CALAVERAS CEMENT 1101 | Settings Review | 2022-10-06 | 2022-10-20 | 2022-10-12 | Complete
CALISTOGA 1101 | Ad Hoc Fault Indicator Installation | 2022-07-22 | 2022-08-05 | 2022-07-29 | Complete
CALISTOGA 1101 | Additional Detailed Patrol | 2022-07-22 | 2022-08-05 | 2022-09-15 | Complete
CALISTOGA 1101 | Customer Impact | 2022-07-22 | 2022-08-05 | 2022-08-05 | Complete
CALISTOGA 1101 | Patrol Zones | 2022-07-22 | 2022-08-05 | 2022-07-29 | Complete
CALISTOGA 1101 | Planned Work and Opportunities | 2022-07-22 | 2022-08-05 | 2022-07-29 | Complete
CALISTOGA 1101 | Planned Work and Opportunities | 2022-07-22 | 2022-08-05 | 2022-07-29 | Complete
CALISTOGA 1101 | Settings Review | 2022-07-22 | 2022-08-05 | 2022-07-29 | Complete
CALISTOGA 1101 | Vegetation Management Cycle Review | 2022-07-22 | 2022-08-05 | 2022-08-10 | Complete
CALISTOGA 1101 | Ad Hoc Fault Indicator Installation | 2022-08-11 | 2022-08-25 | 2022-09-15 | Complete
CALISTOGA 1102 | Settings Review | 2022-10-17 | 2022-10-31 | 2022-10-21 | Complete
CALPELLA 1101 | Ad Hoc Fault Indicator Installation | 2022-11-02 | 2022-11-16 | 2022-12-09 | Complete
CALPELLA 1101 | Additional Detailed Patrol | 2022-11-02 | 2022-11-16 | 2022-12-09 | Complete
CALPELLA 1101 | Planned Work and Opportunities | 2022-11-02 | 2022-11-16 | 2022-11-18 | Complete
CALPELLA 1101 | Settings Review | 2022-11-02 | 2022-11-16 | 2022-12-06 | Complete
CAMP EVERS 2103 | Ad Hoc Fault Indicator Installation | 2022-09-20 | 2022-10-04 | 2022-10-18 | Complete
CAMP EVERS 2103 | Additional Detailed Patrol | 2022-09-20 | 2022-10-04 | 2022-10-18 | Complete
CAMP EVERS 2103 | Planned Work and Opportunities | 2022-09-20 | 2022-10-04 | 2022-10-18 | Complete
CAMP EVERS 2103 | Settings Review | 2022-09-20 | 2022-10-04 | 2022-10-18 | Complete
CAMP EVERS 2103 | Vegetation Management Cycle Review | 2022-09-20 | 2022-10-04 | 2022-10-26 | Complete
CAMP EVERS 2105 | Planned Work and Opportunities | 2022-07-18 | 2022-08-01 | 2022-08-11 | Complete
CAMP EVERS 2105 | Planned Work and Opportunities | 2022-07-18 | 2022-08-01 | 2022-08-11 | Complete
CAMP EVERS 2105 | Proactive Fault Indicator Installation | 2022-07-18 |  | 2022-07-20 | Complete
CAMP EVERS 2105 | Settings Review | 2022-07-18 | 2022-08-01 | 2022-08-26 | Complete
CAMP EVERS 2105 | Vegetation Management Cycle Review | 2022-07-18 | 2022-08-01 | 2022-08-26 | Complete
CAMP EVERS 2106 | Ad Hoc Fault Indicator Installation | 2022-07-19 | 2022-08-02 | 2022-10-18 | Complete
CAMP EVERS 2106 | Additional Detailed Patrol | 2022-07-19 | 2022-08-02 | 2022-10-18 | Complete
CAMP EVERS 2106 | Customer Impact | 2022-07-19 | 2022-08-02 | 2022-08-05 | Complete
CAMP EVERS 2106 | Planned Work and Opportunities | 2022-07-19 | 2022-08-02 | 2022-08-29 | Complete
CAMP EVERS 2106 | Planned Work and Opportunities | 2022-07-19 | 2022-08-02 | 2022-09-20 | Complete
CAMP EVERS 2106 | Proactive Fault Indicator Installation | 2022-07-19 | 2022-10-31 | 2022-10-31 | Complete
CAMP EVERS 2106 | Settings Review | 2022-07-19 | 2022-08-02 | 2022-08-11 | Complete
CAMP EVERS 2106 | Vegetation Management Cycle Review | 2022-07-19 | 2022-08-02 | 2022-09-02 | Complete
CAMP EVERS 2106 | Animal Guard | 2022-09-02 | 2022-09-16 | 2022-10-11 | Complete
CHOLAME 2102 | Settings Review | 2022-11-28 | 2022-12-12 | 2022-12-06 | Complete
CLAY 1101 | Animal Guard | 2022-10-03 | 2022-10-17 | 2022-10-18 | Complete
CLAY 1101 | Vegetation Management Cycle Review | 2022-10-03 | 2022-11-11 | 2022-11-11 | Complete
COARSEGOLD 2103 | Ad Hoc Fault Indicator Installation | 2022-10-17 | 2022-10-31 | 2022-11-01 | Complete
COARSEGOLD 2103 | Additional Detailed Patrol | 2022-10-17 | 2022-10-31 | 2022-11-01 | Complete
COARSEGOLD 2103 | Animal Guard | 2022-10-17 | 2022-10-31 | 2022-11-01 | Complete
COARSEGOLD 2103 | Planned Work and Opportunities | 2022-10-17 | 2022-10-31 | 2022-11-28 | Complete
COARSEGOLD 2103 | Settings Review | 2022-10-17 | 2022-10-31 | 2022-10-21 | Complete
COARSEGOLD 2104 | Ad Hoc Fault Indicator Installation | 2022-09-21 | 2022-10-05 | 2022-10-12 | Complete
COARSEGOLD 2104 | Additional Detailed Patrol | 2022-09-21 | 2022-10-05 | 2022-10-12 | Complete
COARSEGOLD 2104 | Planned Work and Opportunities | 2022-09-21 | 2022-10-05 | 2022-11-14 | Complete
COARSEGOLD 2104 | Proactive Fault Indicator Installation | 2022-09-21 | 2022-10-31 | 2022-07-14 | Complete
COARSEGOLD 2104 | Settings Review | 2022-09-21 | 2022-10-05 | 2022-10-07 | Complete
COLUMBIA HILL 1101 | Animal Guard | 2022-10-17 | 2022-10-31 | 2022-12-13 | Complete
CORNING 1101 | Ad Hoc Fault Indicator Installation | 2022-07-28 | 2022-08-11 | 2022-08-29 | Complete
CORNING 1101 | Additional Detailed Patrol | 2022-07-28 | 2022-08-11 | 2022-08-29 | Complete
CORNING 1101 | Customer Impact | 2022-07-28 | 2022-08-11 | 2022-08-05 | Complete
CORNING 1101 | Planned Work and Opportunities | 2022-07-28 | 2022-08-11 | 2022-08-08 | Complete
CORNING 1101 | Planned Work and Opportunities | 2022-07-28 | 2022-08-11 | 2022-08-08 | Complete
CORNING 1101 | Settings Review | 2022-07-28 | 2022-08-11 | 2022-08-29 | Complete
CORNING 1101 | Vegetation Management Cycle Review | 2022-07-28 | 2022-08-11 | 2022-08-10 | Complete
CORRAL 1101 | Ad Hoc Fault Indicator Installation | 2022-10-17 | 2022-10-31 | 2023-01-19 | Complete
CORRAL 1101 | Additional Detailed Patrol | 2022-10-17 | 2022-10-31 | 2023-01-19 | Complete
CORRAL 1101 | Planned Work and Opportunities | 2022-10-17 | 2022-10-31 | 2022-11-21 | Complete
CORRAL 1101 | Settings Review | 2022-10-17 | 2022-10-31 | 2022-10-21 | Complete
CORRAL 1101 | Vegetation Management Cycle Review | 2022-10-17 | 2022-11-11 | 2022-11-22 | Complete
CORRAL 1103 | Planned Work and Opportunities | 2022-11-14 | 2022-11-28 | 2022-11-14 | Complete
CORRAL 1103 | Trigger Level Outage Actions | 2022-11-14 | 2022-11-28 | 2022-11-30 | Complete
CORRAL 1103 | Trigger Level Outage Actions | 2022-11-14 | 2022-11-28 | 2022-11-30 | Complete
COTTONWOOD 1103 | Ad Hoc Fault Indicator Installation | 2022-10-03 | 2022-10-17 | 2022-10-12 | Complete
COTTONWOOD 1103 | Additional Detailed Patrol | 2022-10-03 | 2022-10-17 | 2022-10-12 | Complete
COTTONWOOD 1103 | Animal Guard | 2022-10-03 | 2022-10-17 | 2023-06-20 | Complete
COTTONWOOD 1103 | Planned Work and Opportunities | 2022-10-03 | 2022-10-17 | 2022-10-15 | Complete
COTTONWOOD 1103 | Proactive Fault Indicator Installation | 2022-10-03 | 2022-10-31 | 2022-10-19 | Complete
COTTONWOOD 1103 | Settings Review | 2022-10-03 | 2022-10-17 | 2022-10-13 | Complete
COTTONWOOD 1103 | Vegetation Management Cycle Review | 2022-10-03 | 2022-11-11 | 2022-11-11 | Complete
COVELO 1101 | Ad Hoc Fault Indicator Installation | 2022-09-22 | 2022-10-06 | 2022-10-20 | Complete
COVELO 1101 | Additional Detailed Patrol | 2022-09-22 | 2022-10-06 | 2022-10-15 | Complete
COVELO 1101 | Planned Work and Opportunities | 2022-09-22 | 2022-10-06 | 2022-10-15 | Complete
COVELO 1101 | Proactive Fault Indicator Installation | 2022-09-22 | 2022-10-06 | 2022-07-11 | Complete
COVELO 1101 | Review CAIDI Performance | 2022-09-22 | 2022-10-06 | 2022-12-14 | Complete
COVELO 1101 | Review Response Time | 2022-09-22 | 2022-10-06 | 2022-12-14 | Complete
COVELO 1101 | Settings Review | 2022-09-22 | 2022-10-06 | 2022-10-17 | Complete
COVELO 1101 | Vegetation Management Cycle Review | 2022-09-22 | 2022-11-11 | 2022-11-11 | Complete
CURTIS 1702 | Ad Hoc Fault Indicator Installation | 2022-08-08 | 2022-08-22 | 2022-09-15 | Complete
CURTIS 1702 | Additional Detailed Patrol | 2022-08-08 | 2022-08-22 | 2022-09-15 | Complete
CURTIS 1702 | Animal Guard | 2022-08-08 | 2022-08-22 | 2022-09-21 | Complete
CURTIS 1702 | Planned Work and Opportunities | 2022-08-08 | 2022-08-22 | 2022-08-19 | Complete
CURTIS 1702 | Planned Work and Opportunities | 2022-08-08 | 2022-08-22 | 2022-08-19 | Complete
CURTIS 1702 | Settings Review | 2022-08-08 | 2022-08-22 | 2022-08-19 | Complete
CURTIS 1702 | Vegetation Management Cycle Review | 2022-08-08 | 2022-08-22 | 2022-08-10 | Complete
CURTIS 1703 | Ad Hoc Fault Indicator Installation | 2022-09-09 | 2022-09-23 | 2022-10-05 | Complete
CURTIS 1703 | Additional Detailed Patrol | 2022-09-09 | 2022-09-23 | 2022-10-05 | Complete
CURTIS 1703 | Planned Work and Opportunities | 2022-09-09 | 2022-09-23 | 2022-11-01 | Complete
CURTIS 1703 | Proactive Fault Indicator Installation | 2022-09-09 | 2022-09-23 | 2022-07-08 | Complete
CURTIS 1703 | Settings Review | 2022-09-09 | 2022-09-23 | 2022-09-15 | Complete
CURTIS 1704 | Settings Review | 2022-08-22 | 2022-09-05 | 2022-09-08 | Complete
CURTIS 1704 | Ad Hoc Fault Indicator Installation | 2022-09-13 | 2022-09-27 | 2022-10-06 | Complete
CURTIS 1704 | Additional Detailed Patrol | 2022-09-13 | 2022-09-27 | 2022-10-06 | Complete
CURTIS 1704 | Animal Guard | 2022-09-13 | 2022-09-27 | 2022-09-21 | Complete
CURTIS 1704 | Planned Work and Opportunities | 2022-09-13 | 2022-09-27 | 2022-11-03 | Complete
CURTIS 1704 | Proactive Fault Indicator Installation | 2022-09-13 | 2022-10-31 | 2022-07-07 | Complete
CURTIS 1705 | Ad Hoc Fault Indicator Installation | 2022-09-20 | 2022-10-04 | 2022-10-12 | Complete
CURTIS 1705 | Additional Detailed Patrol | 2022-09-20 | 2022-10-04 | 2022-10-12 | Complete
CURTIS 1705 | Animal Guard | 2022-09-20 | 2022-10-04 | 2022-09-23 | Complete
CURTIS 1705 | Planned Work and Opportunities | 2022-09-20 | 2022-10-04 | 2022-10-31 | Complete
CURTIS 1705 | Settings Review | 2022-09-20 | 2022-10-04 | 2022-09-23 | Complete
DIAMOND SPRINGS 1103 | Animal Guard | 2022-11-09 | 2022-11-23 | 2022-12-13 | Complete
DIAMOND SPRINGS 1103 | Review CAIDI Performance | 2022-11-09 | 2022-11-23 | 2022-10-19 | Complete
DIAMOND SPRINGS 1103 | Trigger Level Outage Actions | 2022-11-09 | 2022-11-23 | 2022-11-18 | Complete
DIAMOND SPRINGS 1103 | Trigger Level Outage Actions | 2022-11-09 | 2022-11-23 | 2022-11-18 | Complete
DIAMOND SPRINGS 1103 | Trigger Level Outage Actions | 2022-11-09 | 2022-11-23 | 2022-11-18 | Complete
DUNBAR 1101 | Ad Hoc Fault Indicator Installation | 2022-09-21 | 2022-10-05 | 2022-10-06 | Complete
DUNBAR 1101 | Additional Detailed Patrol | 2022-09-21 | 2022-10-05 | 2022-10-06 | Complete
DUNBAR 1101 | Animal Guard | 2022-09-21 | 2022-10-05 | 2022-10-06 | Complete
DUNBAR 1101 | Planned Work and Opportunities | 2022-09-21 | 2022-10-05 | 2022-10-07 | Complete
DUNBAR 1101 | Proactive Fault Indicator Installation | 2022-09-21 | 2022-10-05 | 2022-07-22 | Complete
DUNBAR 1101 | Settings Review | 2022-09-21 | 2022-10-05 | 2022-10-06 | Complete
DUNBAR 1101 | Vegetation Management Cycle Review | 2022-09-21 | 2022-11-11 | 2022-11-11 | Complete
DUNLAP 1102 | Ad Hoc Fault Indicator Installation | 2022-09-20 | 2022-10-04 | 2022-10-13 | Complete
DUNLAP 1102 | Additional Detailed Patrol | 2022-09-20 | 2022-10-04 | 2022-10-13 | Complete
DUNLAP 1102 | Animal Guard | 2022-09-20 | 2022-10-04 | 2022-10-14 | Complete
DUNLAP 1102 | Planned Work and Opportunities | 2022-09-20 | 2022-10-04 | 2022-11-11 | Complete
DUNLAP 1102 | Settings Review | 2022-09-20 | 2022-10-04 | 2022-09-22 | Complete
ELECTRA 1101 | Ad Hoc Fault Indicator Installation | 2022-09-14 | 2022-09-28 | 2022-09-15 | Complete
ELECTRA 1101 | Additional Detailed Patrol | 2022-09-14 | 2022-09-28 | 2022-09-15 | Complete
ELECTRA 1101 | Planned Work and Opportunities | 2022-09-14 | 2022-09-28 | 2022-09-15 | Complete
ELECTRA 1101 | Settings Review | 2022-09-14 | 2022-09-28 | 2022-09-15 | Complete
ELK CREEK 1101 | Ad Hoc Fault Indicator Installation | 2022-09-02 | 2022-09-16 | 2022-09-20 | Complete
ELK CREEK 1101 | Additional Detailed Patrol | 2022-09-02 | 2022-09-16 | 2022-09-20 | Complete
ELK CREEK 1101 | Animal Guard | 2022-09-02 | 2022-09-16 | 2023-06-20 | Complete
ELK CREEK 1101 | Planned Work and Opportunities | 2022-09-02 | 2022-09-16 | 2022-09-23 | Complete
ELK CREEK 1101 | Settings Review | 2022-09-02 | 2022-09-16 | 2022-09-06 | Complete
FAIRVIEW 2207 | Ad Hoc Fault Indicator Installation | 2022-06-24 | 2022-07-28 | 2022-11-06 | Complete
FAIRVIEW 2207 | Additional Detailed Patrol | 2022-06-24 | 2022-07-28 | 2022-11-06 | Complete
FAIRVIEW 2207 | Settings Review | 2022-06-24 | 2022-07-08 | 2022-07-07 | Complete
FAIRVIEW 2207 | Proactive Fault Indicator Installation | 2022-07-20 | 2022-08-03 | 2022-07-20 | Complete
FAIRVIEW 2207 | Planned Work and Opportunities | 2022-10-07 | 2022-10-21 | 2022-10-07 | Complete
FAIRVIEW 2207 | Trigger Level Outage Actions | 2022-11-04 | 2022-11-18 | 2022-11-04 | Complete
FAIRVIEW 2207 | Trigger Level Outage Actions | 2022-11-04 | 2022-11-18 | 2022-11-04 | Complete
FOOTHILL 1102 | Ad Hoc Fault Indicator Installation | 2022-09-06 | 2022-09-20 | 2022-09-09 | Complete
FOOTHILL 1102 | Additional Detailed Patrol | 2022-09-06 | 2022-09-20 | 2022-09-09 | Complete
FOOTHILL 1102 | Planned Work and Opportunities | 2022-09-06 | 2022-09-20 | 2022-09-06 | Complete
FOOTHILL 1102 | Settings Review | 2022-09-06 | 2022-09-20 | 2022-09-07 | Complete
FORESTHILL 1101 | Ad Hoc Fault Indicator Installation | 2022-08-08 | 2022-08-22 | 2022-10-18 | Complete
FORESTHILL 1101 | Planned Work and Opportunities | 2022-08-08 | 2022-08-22 | 2022-09-01 | Complete
FORESTHILL 1101 | Settings Review | 2022-08-08 | 2022-08-22 | 2022-09-07 | Complete
FORESTHILL 1101 | Vegetation Management Cycle Review | 2022-08-08 | 2022-08-22 | 2022-08-29 | Complete
FROGTOWN 1701 | Ad Hoc Fault Indicator Installation | 2022-10-11 | 2022-10-25 | 2022-11-01 | Complete
FROGTOWN 1701 | Additional Detailed Patrol | 2022-10-11 | 2022-10-25 | 2022-11-01 | Complete
FROGTOWN 1701 | Animal Guard | 2022-10-11 | 2022-10-25 | 2022-10-18 | Complete
FROGTOWN 1701 | Planned Work and Opportunities | 2022-10-11 | 2022-10-25 | 2022-10-12 | Complete
FROGTOWN 1701 | Settings Review | 2022-10-11 | 2022-10-25 | 2022-10-12 | Complete
FROGTOWN 1702 | Ad Hoc Fault Indicator Installation | 2022-09-21 | 2022-10-05 | 2022-10-12 | Complete
FROGTOWN 1702 | Additional Detailed Patrol | 2022-09-21 | 2022-10-05 | 2022-10-12 | Complete
FROGTOWN 1702 | Animal Guard | 2022-09-21 | 2022-10-05 | 2022-09-22 | Complete
FROGTOWN 1702 | Planned Work and Opportunities | 2022-09-21 | 2022-10-05 | 2022-11-14 | Complete
FROGTOWN 1702 | Proactive Fault Indicator Installation | 2022-09-21 | 2022-10-05 | 2022-09-02 | Complete
FROGTOWN 1702 | Settings Review | 2022-09-21 | 2022-10-05 | 2022-10-07 | Complete
GABILAN 1101 | Ad Hoc Fault Indicator Installation | 2022-10-12 | 2022-10-26 | 2022-10-14 | Complete
GABILAN 1101 | Additional Detailed Patrol | 2022-10-12 | 2022-10-26 | 2022-10-14 | Complete
GABILAN 1101 | Planned Work and Opportunities | 2022-10-12 | 2022-10-26 | 2022-10-14 | Complete
GABILAN 1101 | Settings Review | 2022-10-12 | 2022-10-26 | 2022-11-01 | Complete
GANSNER 1101 | Ad Hoc Fault Indicator Installation | 2022-09-23 | 2022-10-07 | 2022-10-04 | Complete
GANSNER 1101 | Additional Detailed Patrol | 2022-09-23 | 2022-10-07 | 2022-10-04 | Complete
GANSNER 1101 | Planned Work and Opportunities | 2022-09-23 | 2022-10-07 | 2022-10-07 | Complete
GANSNER 1101 | Settings Review | 2022-09-23 | 2022-10-07 | 2022-10-03 | Complete
GARBERVILLE 1101 | Ad Hoc Fault Indicator Installation | 2022-11-09 | 2022-11-23 | 2022-11-29 | Complete
GARBERVILLE 1101 | Additional Detailed Patrol | 2022-11-09 | 2022-11-23 | 2022-11-29 | Complete
GARBERVILLE 1101 | Planned Work and Opportunities | 2022-11-09 | 2022-11-23 | 2022-11-18 | Complete
GARBERVILLE 1101 | Settings Review | 2022-11-09 | 2022-11-23 | 2022-11-12 | Complete
GARBERVILLE 1101 | Vegetation Management Cycle Review | 2022-11-09 | 2022-11-23 | 2022-11-22 | Complete
GARBERVILLE 1102 | Ad Hoc Fault Indicator Installation | 2022-09-19 | 2022-10-03 | 2022-10-14 | Complete
GARBERVILLE 1102 | Additional Detailed Patrol | 2022-09-19 | 2022-10-03 | 2022-10-14 | Complete
GARBERVILLE 1102 | Planned Work and Opportunities | 2022-09-19 | 2022-10-03 | 2022-10-15 | Complete
GARBERVILLE 1102 | Proactive Fault Indicator Installation | 2022-09-19 | 2022-10-31 | 2022-10-18 | Complete
GARBERVILLE 1102 | Settings Review | 2022-09-19 | 2022-10-03 | 2022-10-31 | Complete
GARBERVILLE 1102 | Vegetation Management Cycle Review | 2022-09-19 | 2022-11-11 | 2022-11-11 | Complete
GEYSERVILLE 1101 | Ad Hoc Fault Indicator Installation | 2022-09-06 | 2022-09-20 | 2022-09-27 | Complete
GEYSERVILLE 1101 | Additional Detailed Patrol | 2022-09-06 | 2022-09-20 | 2022-09-27 | Complete
GEYSERVILLE 1101 | Animal Guard | 2022-09-06 | 2022-09-20 | 2022-11-01 | Complete
GEYSERVILLE 1101 | Planned Work and Opportunities | 2022-09-06 | 2022-09-20 | 2022-09-18 | Complete
GEYSERVILLE 1101 | Proactive Fault Indicator Installation | 2022-09-06 | 2022-09-20 | 2022-08-08 | Complete
GEYSERVILLE 1101 | Settings Review | 2022-09-06 | 2022-09-20 | 2022-09-08 | Complete
GEYSERVILLE 1102 | Ad Hoc Fault Indicator Installation | 2022-09-02 | 2022-09-16 | 2022-10-05 | Complete
GEYSERVILLE 1102 | Additional Detailed Patrol | 2022-09-02 | 2022-09-16 | 2022-10-05 | Complete
GEYSERVILLE 1102 | Animal Guard | 2022-09-02 | 2022-09-16 | 2022-11-01 | Complete
GEYSERVILLE 1102 | Planned Work and Opportunities | 2022-09-02 | 2022-09-16 | 2022-09-23 | Complete
GEYSERVILLE 1102 | Proactive Fault Indicator Installation | 2022-09-02 | 2022-09-16 | 2022-07-18 | Complete
GEYSERVILLE 1102 | Settings Review | 2022-09-02 | 2022-09-16 | 2022-12-06 | Complete
Green Valley 2101 | Ad Hoc Fault Indicator Installation | 2022-08-08 | 2022-08-22 | 2022-09-12 | Complete
Green Valley 2101 | Additional Detailed Patrol | 2022-08-08 | 2022-08-22 | 2022-09-12 | Complete
Green Valley 2101 | Animal Guard | 2022-08-08 | 2022-08-22 | 2022-09-02 | Complete
Green Valley 2101 | Planned Work and Opportunities | 2022-08-08 | 2022-08-22 | 2022-08-29 | Complete
Green Valley 2101 | Planned Work and Opportunities | 2022-08-08 | 2022-08-22 | 2022-08-29 | Complete
Green Valley 2101 | Settings Review | 2022-08-08 | 2022-08-22 | 2022-10-28 | Complete
Green Valley 2101 | Vegetation Management Cycle Review | 2022-08-08 | 2022-08-22 | 2022-08-10 | Complete
Green Valley 2101 | Ad Hoc Fault Indicator Installation | 2022-11-07 | 2022-11-21 | 2022-11-14 | Complete
Green Valley 2101 | Additional Detailed Patrol | 2022-11-07 | 2022-11-21 | 2022-11-14 | Complete
GREEN VALLEY 2101 | Settings Adjustment | 2022-11-14 | 2022-11-28 | 2022-11-14 | Complete
GUSTINE 1102 | Ad Hoc Fault Indicator Installation | 2022-08-26 | 2022-09-09 | 2022-09-20 | Complete
GUSTINE 1102 | Additional Detailed Patrol | 2022-08-26 | 2022-09-09 | 2022-09-20 | Complete
GUSTINE 1102 | Animal Guard | 2022-08-26 | 2022-09-09 | 2022-09-21 | Complete
GUSTINE 1102 | Planned Work and Opportunities | 2022-08-26 | 2022-09-09 | 2022-08-31 | Complete
GUSTINE 1102 | Planned Work and Opportunities | 2022-08-26 | 2022-09-09 | 2022-08-31 | Complete
GUSTINE 1102 | Settings Review | 2022-08-26 | 2022-09-09 | 2022-09-02 | Complete
HALF MOON BAY 1103 | Ad Hoc Fault Indicator Installation | 2022-06-23 | 2022-07-28 | 2022-08-01 | Complete
HALF MOON BAY 1103 | Settings Review | 2022-06-23 | 2022-07-07 | 2022-07-02 | Complete
HALF MOON BAY 1103 | Vegetation Management Cycle Review | 2022-06-23 | 2022-07-28 | 2022-09-06 | Complete
HALF MOON BAY 1103 | Additional Detailed Patrol | 2022-07-08 | 2022-07-15 | 2022-07-11 | Complete
HALSEY 1101 | Ad Hoc Fault Indicator Installation | 2022-09-06 | 2022-09-20 | 2022-09-23 | Complete
HALSEY 1101 | Additional Detailed Patrol | 2022-09-06 | 2022-09-20 | 2022-09-23 | Complete
HALSEY 1101 | Animal Guard | 2022-09-06 | 2022-09-20 | 2022-12-13 | Complete
HALSEY 1101 | Planned Work and Opportunities | 2022-09-06 | 2022-09-20 | 2022-09-07 | Complete
HALSEY 1101 | Proactive Fault Indicator Installation | 2022-09-06 | 2022-09-20 | 2022-06-30 | Complete
HALSEY 1101 | Settings Review | 2022-09-06 | 2022-09-20 | 2022-09-09 | Complete
HALSEY 1101 | Vegetation Management Cycle Review | 2022-09-06 | 2022-09-20 | 2022-09-27 | Complete
HALSEY 1102 | Ad Hoc Fault Indicator Installation | 2022-09-20 | 2022-10-04 | 2022-10-13 | Complete
HALSEY 1102 | Additional Detailed Patrol | 2022-09-20 | 2022-10-04 | 2022-10-13 | Complete
HALSEY 1102 | Animal Guard | 2022-09-20 | 2022-10-04 | 2022-10-18 | Complete
HALSEY 1102 | Planned Work and Opportunities | 2022-09-20 | 2022-10-04 | 2022-10-12 | Complete
HALSEY 1102 | Settings Review | 2022-09-20 | 2022-10-04 | 2022-10-21 | Complete
HALSEY 1102 | Vegetation Management Cycle Review | 2022-09-20 | 2022-10-04 | 2022-10-11 | Complete
HALSEY 1102 | Planned Work and Opportunities | 2022-11-04 | 2022-11-18 | 2022-11-04 | Complete
HARTLEY 1101 | Ad Hoc Fault Indicator Installation | 2022-09-21 | 2022-10-05 | 2022-10-14 | Complete
HARTLEY 1101 | Animal Guard | 2022-09-21 | 2022-10-05 | 2022-10-11 | Complete
HARTLEY 1101 | Planned Work and Opportunities | 2022-09-21 | 2022-10-05 | 2022-10-15 | Complete
HARTLEY 1101 | Settings Review | 2022-09-21 | 2022-10-05 | 2022-10-14 | Complete
HARTLEY 1101 | Vegetation Management Cycle Review | 2022-09-21 | 2022-11-11 | 2022-11-11 | Complete
HICKS 2101 | Ad Hoc Fault Indicator Installation | 2022-06-23 | 2022-06-30 | 2022-06-24 | Complete
HICKS 2101 | Additional Detailed Patrol | 2022-06-23 | 2022-06-30 | 2022-06-24 | Complete
HICKS 2101 | Planned Work and Opportunities | 2022-07-13 | 2022-08-03 | 2022-07-20 | Complete
HICKS 2101 | Proactive Fault Indicator Installation | 2022-07-13 | 2022-08-03 | 2022-08-03 | Complete
HICKS 2101 | Vegetation Management Cycle Review | 2022-07-15 | 2022-07-29 | 2022-08-09 | Complete
HICKS 2101 | Ad Hoc Fault Indicator Installation | 2022-09-07 | 2022-09-21 | 2022-09-30 | Complete
HICKS 2101 | Settings Review | 2022-09-14 | 2022-09-28 | 2022-09-16 | Complete
HICKS 2101 | Trigger Level Outage Actions | 2022-11-08 | 2022-11-22 | 2022-11-08 | Complete
HICKS 2101 | Trigger Level Outage Actions | 2022-11-08 | 2022-11-22 | 2022-11-08 | Complete
HICKS 2101 | Trigger Level Outage Actions | 2022-11-08 | 2022-11-22 | 2022-11-08 | Complete
HIGGINS 1103 | Ad Hoc Fault Indicator Installation | 2022-09-06 | 2022-09-20 | 2022-12-27 | Complete
HIGGINS 1103 | Additional Detailed Patrol | 2022-09-06 | 2022-09-20 | 2022-11-29 | Complete
HIGGINS 1103 | Animal Guard | 2022-09-06 | 2022-09-20 | 2022-12-13 | Complete
HIGGINS 1103 | Planned Work and Opportunities | 2022-09-06 | 2022-09-20 | 2022-09-23 | Complete
HIGGINS 1103 | Settings Review | 2022-09-06 | 2022-09-20 | 2022-10-06 | Complete
HIGGINS 1103 | Vegetation Management Cycle Review | 2022-09-06 | 2022-09-20 | 2022-09-21 | Complete
HIGGINS 1104 | Animal Guard | 2022-10-03 | 2022-10-17 | 2022-12-13 | Complete
HIGHLANDS 1102 | Animal Guard | 2022-09-09 | 2022-09-23 | 2022-09-09 | Complete
HOLLISTER 2105 | Ad Hoc Fault Indicator Installation | 2022-09-20 | 2022-10-04 | 2022-10-05 | Complete
HOLLISTER 2105 | Additional Detailed Patrol | 2022-09-20 | 2022-10-04 | 2022-10-05 | Complete
HOLLISTER 2105 | Planned Work and Opportunities | 2022-09-20 | 2022-10-04 | 2022-10-11 | Complete
HOLLISTER 2105 | Proactive Fault Indicator Installation | 2022-09-20 | 2022-10-04 | 2022-10-14 | Complete
HOLLISTER 2105 | Settings Review | 2022-09-20 | 2022-10-04 | 2022-11-01 | Complete
HOLLISTER 2105 | Vegetation Management Cycle Review | 2022-09-20 | 2022-10-04 | 2022-10-26 | Complete
HOOPA 1101 | Ad Hoc Fault Indicator Installation | 2022-07-22 | 2022-08-05 | 2022-09-13 | Complete
HOOPA 1101 | Additional Detailed Patrol | 2022-07-22 | 2022-08-05 | 2022-09-13 | Complete
HOOPA 1101 | Animal Guard | 2022-07-22 | 2022-08-05 | 2022-09-13 | Complete
HOOPA 1101 | Customer Impact | 2022-07-22 | 2022-08-05 | 2022-08-05 | Complete
HOOPA 1101 | Planned Work and Opportunities | 2022-07-22 | 2022-08-05 | 2022-08-05 | Complete
HOOPA 1101 | Planned Work and Opportunities | 2022-07-22 | 2022-08-05 | 2022-08-05 | Complete
HOOPA 1101 | Settings Review | 2022-07-22 | 2022-08-05 | 2022-09-15 | Complete
HOOPA 1101 | Vegetation Management Cycle Review | 2022-07-22 | 2022-08-05 | 2022-09-06 | Complete
HOPLAND 1101 | Ad Hoc Fault Indicator Installation | 2022-10-19 | 2022-11-02 | 2022-10-28 | Complete
HOPLAND 1101 | Additional Detailed Patrol | 2022-10-19 | 2022-11-02 | 2022-10-28 | Complete
HOPLAND 1101 | Planned Work and Opportunities | 2022-10-19 | 2022-11-02 | 2022-10-24 | Complete
HOPLAND 1101 | Review CAIDI Performance | 2022-10-19 | 2022-11-02 | 2022-12-14 | Complete
HOPLAND 1101 | Settings Review | 2022-10-19 | 2022-11-02 | 2022-10-31 | Complete
HORSESHOE 1104 | Ad Hoc Fault Indicator Installation | 2022-09-20 | 2022-10-04 | 2022-09-27 | Complete
HORSESHOE 1104 | Additional Detailed Patrol | 2022-09-20 | 2022-10-04 | 2022-09-27 | Complete
HORSESHOE 1104 | Planned Work and Opportunities | 2022-09-20 | 2022-10-04 | 2022-09-23 | Complete
HORSESHOE 1104 | Settings Review | 2022-09-20 | 2022-10-04 | 2022-10-11 | Complete
JAMESON 1105 | Ad Hoc Fault Indicator Installation | 2022-08-15 | 2022-08-29 | 2022-08-29 | Complete
JAMESON 1105 | Additional Detailed Patrol | 2022-08-15 | 2022-08-29 | 2022-08-29 | Complete
JAMESON 1105 | Planned Work and Opportunities | 2022-08-15 | 2022-08-29 | 2022-08-29 | Complete
JAMESON 1105 | Planned Work and Opportunities | 2022-08-15 | 2022-08-29 | 2022-08-29 | Complete
JAMESON 1105 | Proactive Fault Indicator Installation | 2022-08-15 | 2022-08-29 | 2022-06-09 | Complete
JAMESON 1105 | Settings Review | 2022-08-15 | 2022-08-29 | 2022-08-29 | Complete
JESSUP 1101 | Ad Hoc Fault Indicator Installation | 2022-09-02 | 2022-09-16 | 2022-09-02 | Complete
JESSUP 1101 | Additional Detailed Patrol | 2022-09-02 | 2022-09-16 | 2022-09-02 | Complete
JESSUP 1101 | Animal Guard | 2022-09-02 | 2022-09-16 | 2022-11-29 | Complete
JESSUP 1101 | Planned Work and Opportunities | 2022-09-02 | 2022-09-16 | 2022-09-23 | Complete
JESSUP 1101 | Settings Review | 2022-09-02 | 2022-09-16 | 2022-09-07 | Complete
JOLON 1102 | Ad Hoc Fault Indicator Installation | 2022-11-15 | 2022-11-29 | 2022-11-29 | Complete
JOLON 1102 | Additional Detailed Patrol | 2022-11-15 | 2022-11-29 | 2022-11-29 | Complete
JOLON 1102 | Planned Work and Opportunities | 2022-11-15 | 2022-11-29 | 2022-12-01 | Complete
JOLON 1102 | Settings Review | 2022-11-15 | 2022-11-29 | 2022-11-29 | Complete
JOLON 1103 | Planned Work and Opportunities | 2022-10-11 | 2022-10-25 | 2022-10-11 | Complete
JOLON 1103 | Settings Review | 2022-10-11 | 2022-10-25 | 2022-10-28 | Complete
KONOCTI 1102 | Ad Hoc Fault Indicator Installation | 2022-09-06 | 2022-09-20 | 2022-09-07 | Complete
KONOCTI 1102 | Additional Detailed Patrol | 2022-09-06 | 2022-09-20 | 2022-09-07 | Complete
KONOCTI 1102 | Planned Work and Opportunities | 2022-09-06 | 2022-09-20 | 2022-09-07 | Complete
KONOCTI 1102 | Settings Review | 2022-09-06 | 2022-09-20 | 2022-09-08 | Complete
KONOCTI 1102 | Vegetation Management Cycle Review | 2022-09-06 | 2022-09-20 | 2022-10-19 | Complete
LAKEVILLE 1102 | Ad Hoc Fault Indicator Installation | 2022-09-20 | 2022-10-04 | 2022-09-26 | Complete
LAKEVILLE 1102 | Additional Detailed Patrol | 2022-09-20 | 2022-10-04 | 2022-09-26 | Complete
LAKEVILLE 1102 | Planned Work and Opportunities | 2022-09-20 | 2022-10-04 | 2022-10-07 | Complete
LAKEVILLE 1102 | Settings Review | 2022-09-20 | 2022-10-04 | 2022-10-14 | Complete
LAURELES 1111 | Ad Hoc Fault Indicator Installation | 2022-10-07 | 2022-10-21 | 2022-10-11 | Complete
LAURELES 1111 | Additional Detailed Patrol | 2022-10-07 | 2022-10-21 | 2022-10-11 | Complete
LAURELES 1111 | Animal Guard | 2022-10-07 | 2022-10-21 | 2022-10-13 | Complete
LAURELES 1111 | Planned Work and Opportunities | 2022-10-07 | 2022-10-21 | 2022-10-23 | Complete
LAURELES 1111 | Settings Review | 2022-10-07 | 2022-10-21 | 2022-10-11 | Complete
LAURELES 1111 | Vegetation Management Cycle Review | 2022-10-07 | 2022-10-21 | 2022-10-27 | Complete
LINCOLN 1104 | Ad Hoc Fault Indicator Installation | 2022-09-20 | 2022-10-04 | 2022-09-29 | Complete
LINCOLN 1104 | Additional Detailed Patrol | 2022-09-20 | 2022-10-04 | 2022-09-29 | Complete
LINCOLN 1104 | Animal Guard | 2022-09-20 | 2022-10-04 | 2022-12-13 | Complete
LINCOLN 1104 | Planned Work and Opportunities | 2022-09-20 | 2022-10-04 | 2022-10-07 | Complete
LINCOLN 1104 | Proactive Fault Indicator Installation | 2022-09-20 | 2022-10-31 | 2022-10-14 | Complete
LINCOLN 1104 | Settings Review | 2022-09-20 | 2022-10-04 | 2022-10-11 | Complete
LOS GATOS 1106 | Ad Hoc Fault Indicator Installation | 2022-09-13 | 2022-09-27 | 2022-10-18 | Complete
LOS GATOS 1106 | Additional Detailed Patrol | 2022-09-13 | 2022-09-27 | 2022-10-18 | Complete
LOS GATOS 1106 | Animal Guard | 2022-09-13 | 2022-09-27 | 2022-11-04 | Complete
LOS GATOS 1106 | Planned Work and Opportunities | 2022-09-13 | 2022-09-27 | 2022-10-23 | Complete
LOS GATOS 1106 | Proactive Fault Indicator Installation | 2022-09-13 | 2022-09-27 | 2022-05-14 | Complete
LOS GATOS 1106 | Settings Review | 2022-09-13 | 2022-09-27 | 2022-10-03 | Complete
LOS GATOS 1106 | Vegetation Management Cycle Review | 2022-09-13 | 2022-09-27 | 2022-10-27 | Complete
LOS GATOS 1107 | Ad Hoc Fault Indicator Installation | 2022-09-09 | 2022-09-23 | 2022-10-18 | Complete
LOS GATOS 1107 | Additional Detailed Patrol | 2022-09-09 | 2022-09-23 | 2022-10-18 | Complete
LOS GATOS 1107 | Animal Guard | 2022-09-09 | 2022-09-23 | 2022-11-04 | Complete
LOS GATOS 1107 | Planned Work and Opportunities | 2022-09-09 | 2022-09-23 | 2022-10-23 | Complete
LOS GATOS 1107 | Proactive Fault Indicator Installation | 2022-09-09 | 2022-09-23 | 2022-07-31 | Complete
LOS GATOS 1107 | Settings Review | 2022-09-09 | 2022-09-23 | 2022-10-03 | Complete
LOS GATOS 1107 | Vegetation Management Cycle Review | 2022-09-09 | 2022-09-23 | 2022-10-27 | Complete
LOS OSITOS 2103 | Ad Hoc Fault Indicator Installation | 2022-08-30 | 2022-09-13 | 2022-09-02 | Complete
LOS OSITOS 2103 | Additional Detailed Patrol | 2022-08-30 | 2022-09-13 | 2022-09-02 | Complete
LOS OSITOS 2103 | Planned Work and Opportunities | 2022-08-30 | 2022-09-13 | 2022-09-02 | Complete
LOS OSITOS 2103 | Settings Review | 2022-08-30 | 2022-09-13 | 2022-09-02 | Complete
LUCERNE 1103 | Ad Hoc Fault Indicator Installation | 2022-09-20 | 2022-10-04 | 2022-09-27 | Complete
LUCERNE 1103 | Additional Detailed Patrol | 2022-09-20 | 2022-10-04 | 2022-09-27 | Complete
LUCERNE 1103 | Animal Guard | 2022-09-20 | 2022-10-04 | 2022-10-11 | Complete
LUCERNE 1103 | Planned Work and Opportunities | 2022-09-20 | 2022-10-04 | 2022-09-27 | Complete
LUCERNE 1103 | Settings Review | 2022-09-20 | 2022-10-04 | 2022-10-14 | Complete
MADISON 2101 | Planned Work and Opportunities | 2022-06-13 | 2022-07-11 | 2022-07-12 | Complete
MADISON 2101 | Settings Review | 2022-06-13 | 2022-07-11 | 2022-06-22 | Complete
MADISON 2101 | Ad Hoc Fault Indicator Installation | 2022-06-18 | 2022-06-25 | 2022-06-20 | Complete
MADISON 2101 | Additional Detailed Patrol | 2022-06-18 | 2022-06-25 | 2022-06-20 | Complete
MADISON 2101 | Planned Work and Opportunities | 2022-09-19 | 2022-10-03 | 2022-09-20 | Complete
Magunden 1108 | Ad Hoc Fault Indicator Installation | 2022-08-08 | 2022-08-22 | 2022-08-16 | Complete
Magunden 1108 | Additional Detailed Patrol | 2022-08-08 | 2022-08-22 | 2022-08-16 | Complete
Magunden 1108 | Planned Work and Opportunities | 2022-08-08 | 2022-08-22 | 2022-08-08 | Complete
Magunden 1108 | Planned Work and Opportunities | 2022-08-08 | 2022-08-22 | 2022-08-08 | Complete
Magunden 1108 | Settings Review | 2022-08-08 | 2022-08-22 | 2022-08-16 | Complete
Magunden 1108 | Vegetation Management Cycle Review | 2022-08-08 | 2022-08-22 | 2022-08-10 | Complete
MARIPOSA 2101 | Ad Hoc Fault Indicator Installation | 2022-09-14 | 2022-09-28 | 2023-06-05 | Complete
MARIPOSA 2101 | Additional Detailed Patrol | 2022-09-14 | 2022-09-28 | 2023-06-05 | Complete
MARIPOSA 2101 | Planned Work and Opportunities | 2022-09-14 | 2022-09-28 | 2022-11-09 | Complete
MARIPOSA 2101 | Proactive Fault Indicator Installation | 2022-09-14 | 2022-10-31 | 2022-10-10 | Complete
MARIPOSA 2101 | Settings Review | 2022-09-14 | 2022-09-28 | 2022-10-07 | Complete
MARIPOSA 2102 | Ad Hoc Fault Indicator Installation | 2022-09-06 | 2022-09-20 | 2023-06-05 | Complete
MARIPOSA 2102 | Additional Detailed Patrol | 2022-09-06 | 2022-09-20 | 2023-06-05 | Complete
MARIPOSA 2102 | Planned Work and Opportunities | 2022-09-06 | 2022-09-20 | 2022-11-01 | Complete
MARIPOSA 2102 | Proactive Fault Indicator Installation | 2022-09-06 | 2022-10-31 | 2022-10-10 | Complete
MARIPOSA 2102 | Settings Review | 2022-09-06 | 2022-09-20 | 2022-09-07 | Complete
MC ARTHUR 1101 | Ad Hoc Fault Indicator Installation | 2022-08-02 | 2022-08-16 | 2022-09-14 | Complete
MC ARTHUR 1101 | Additional Detailed Patrol | 2022-08-02 | 2022-08-16 | 2022-09-14 | Complete
MC ARTHUR 1101 | Customer Impact | 2022-08-02 | 2022-08-16 | 2022-08-05 | Complete
MC ARTHUR 1101 | Planned Work and Opportunities | 2022-08-02 | 2022-08-16 | 2022-08-17 | Complete
MC ARTHUR 1101 | Planned Work and Opportunities | 2022-08-02 | 2022-08-16 | 2022-08-17 | Complete
MC ARTHUR 1101 | Settings Review | 2022-08-02 | 2022-08-16 | 2022-09-08 | Complete
MC ARTHUR 1101 | Vegetation Management Cycle Review | 2022-08-02 | 2022-08-16 | 2022-08-10 | Complete
MC ARTHUR 1101 | Proactive Fault Indicator Installation | 2022-08-15 | 2022-08-29 | 2022-06-30 | Complete
MENLO 1102 | Ad Hoc Fault Indicator Installation | 2022-10-06 | 2022-10-20 | 2022-11-01 | Complete
MENLO 1102 | Additional Detailed Patrol | 2022-10-06 | 2022-10-20 | 2022-11-01 | Complete
MENLO 1102 | Animal Guard | 2022-10-06 | 2022-10-20 | 2022-10-13 | Complete
MENLO 1102 | Planned Work and Opportunities | 2022-10-06 | 2022-10-20 | 2022-10-23 | Complete
MENLO 1102 | Proactive Fault Indicator Installation | 2022-10-06 | 2022-10-20 | 2022-10-28 | Complete
MENLO 1102 | Review CAIDI Performance | 2022-10-06 | 2022-10-20 | 2022-10-13 | Complete
MENLO 1102 | Settings Review | 2022-10-06 | 2022-10-20 | 2022-10-07 | Complete
MERCED FALLS 1102 | Ad Hoc Fault Indicator Installation | 2022-09-23 | 2022-10-07 | 2023-06-05 | Complete
MERCED FALLS 1102 | Additional Detailed Patrol | 2022-09-23 | 2022-10-07 | 2023-06-05 | Complete
MERCED FALLS 1102 | Animal Guard | 2022-09-23 | 2022-10-07 | 2022-10-12 | Complete
MERCED FALLS 1102 | Planned Work and Opportunities | 2022-09-23 | 2022-10-07 | 2022-11-15 | Complete
MERCED FALLS 1102 | Proactive Fault Indicator Installation | 2022-09-23 | 2022-10-31 | 2022-10-26 | Complete
MERCED FALLS 1102 | Settings Review | 2022-09-23 | 2022-10-07 | 2022-10-12 | Complete
MIRABEL 1101 | Ad Hoc Fault Indicator Installation | 2022-11-04 | 2022-11-18 | 2022-12-07 | Complete
MIRABEL 1101 | Additional Detailed Patrol | 2022-11-04 | 2022-11-18 | 2022-12-07 | Complete
MIRABEL 1101 | Animal Guard | 2022-11-04 | 2022-11-18 | 2022-12-12 | Complete
MIRABEL 1101 | Planned Work and Opportunities | 2022-11-04 | 2022-11-18 | 2022-11-18 | Complete
MIRABEL 1101 | Settings Review | 2022-11-04 | 2022-11-18 | 2022-12-06 | Complete
MIRABEL 1101 | Vegetation Management Cycle Review | 2022-11-04 | 2022-11-18 | 2022-11-22 | Complete
MIWUK 1702 | Trigger Level Outage Actions | 2022-11-15 | 2022-11-29 | 2022-11-29 | Complete
MIWUK 1702 | Planned Work and Opportunities | 2022-11-29 | 2022-12-13 | 2022-11-29 | Complete
MOLINO 1102 | Ad Hoc Fault Indicator Installation | 2022-10-06 | 2022-10-20 | 2022-10-27 | Complete
MOLINO 1102 | Additional Detailed Patrol | 2022-10-06 | 2022-10-20 | 2022-10-27 | Complete
MOLINO 1102 | Planned Work and Opportunities | 2022-10-06 | 2022-10-20 | 2022-10-24 | Complete
MOLINO 1102 | Proactive Fault Indicator Installation | 2022-10-06 | 2022-10-20 | 2022-07-26 | Complete
MOLINO 1102 | Settings Review | 2022-10-06 | 2022-10-20 | 2022-10-14 | Complete
MOLINO 1102 | Vegetation Management Cycle Review | 2022-10-06 | 2022-11-11 | 2022-11-11 | Complete
MONTE RIO 1111 | Ad Hoc Fault Indicator Installation | 2022-08-26 | 2022-09-09 | 2022-09-20 | Complete
MONTE RIO 1111 | Additional Detailed Patrol | 2022-08-26 | 2022-09-09 | 2022-09-20 | Complete
MONTE RIO 1111 | Planned Work and Opportunities | 2022-08-26 | 2022-09-09 | 2022-09-18 | Complete
MONTE RIO 1111 | Settings Review | 2022-08-26 | 2022-09-09 | 2022-12-06 | Complete
MONTICELLO 1101 | Ad Hoc Fault Indicator Installation | 2022-10-19 | 2022-11-02 | 2023-01-10 | Complete
MONTICELLO 1101 | Additional Detailed Patrol | 2022-10-19 | 2022-11-02 | 2023-01-10 | Complete
MONTICELLO 1101 | Planned Work and Opportunities | 2022-10-19 | 2022-11-02 | 2022-10-24 | Complete
MONTICELLO 1101 | Proactive Fault Indicator Installation | 2022-10-19 | 2022-11-02 | 2022-12-02 | Complete
MONTICELLO 1101 | Settings Review | 2022-10-19 | 2022-11-02 | 2022-10-20 | Complete
MORGAN HILL 2105 | Ad Hoc Fault Indicator Installation | 2022-09-09 | 2022-09-23 | 2022-10-12 | Complete
MORGAN HILL 2105 | Additional Detailed Patrol | 2022-09-09 | 2022-09-23 | 2022-10-12 | Complete
MORGAN HILL 2105 | Animal Guard | 2022-09-09 | 2022-09-23 | 2022-10-27 | Complete
MORGAN HILL 2105 | Planned Work and Opportunities | 2022-09-09 | 2022-09-23 | 2022-10-23 | Complete
MORGAN HILL 2105 | Proactive Fault Indicator Installation | 2022-09-09 | 2022-09-23 | 2022-08-05 | Complete
MORGAN HILL 2105 | Settings Review | 2022-09-14 | 2022-09-28 | 2022-10-03 | Complete
MORGAN HILL 2109 | Ad Hoc Fault Indicator Installation | 2022-09-09 | 2022-09-23 | 2022-10-06 | Complete
MORGAN HILL 2109 | Additional Detailed Patrol | 2022-09-09 | 2022-09-23 | 2022-10-06 | Complete
MORGAN HILL 2109 | Planned Work and Opportunities | 2022-09-09 | 2022-09-23 | 2022-10-06 | Complete
MORGAN HILL 2109 | Settings Review | 2022-09-09 | 2022-09-23 | 2022-09-13 | Complete
MORGAN HILL 2111 | Settings Review | 2022-09-09 | 2022-09-23 | 2022-09-20 | Complete
MORGAN HILL 2111 | Ad Hoc Fault Indicator Installation | 2022-09-14 | 2022-09-28 | 2022-10-12 | Complete
MORGAN HILL 2111 | Additional Detailed Patrol | 2022-09-14 | 2022-09-28 | 2022-10-12 | Complete
MORGAN HILL 2111 | Planned Work and Opportunities | 2022-09-14 | 2022-09-28 | 2022-10-23 | Complete
MORGAN HILL 2111 | Proactive Fault Indicator Installation | 2022-09-14 | 2022-10-31 | 2022-10-20 | Complete
MORGAN HILL 2111 | Vegetation Management Cycle Review | 2022-09-14 | 2022-09-28 | 2022-10-13 | Complete
MOUNTAIN QUARRIES 2101 | Ad Hoc Fault Indicator Installation | 2022-09-19 | 2022-10-03 | 2022-10-20 | Complete
MOUNTAIN QUARRIES 2101 | Additional Detailed Patrol | 2022-09-19 | 2022-10-03 | 2022-10-20 | Complete
MOUNTAIN QUARRIES 2101 | Animal Guard | 2022-09-19 | 2022-10-03 | 2022-12-13 | Complete
MOUNTAIN QUARRIES 2101 | Planned Work and Opportunities | 2022-09-19 | 2022-10-03 | 2022-10-15 | Complete
MOUNTAIN QUARRIES 2101 | Proactive Fault Indicator Installation | 2022-09-19 | 2022-10-31 | 2022-07-07 | Complete
MOUNTAIN QUARRIES 2101 | Settings Review | 2022-09-19 | 2022-10-03 | 2022-10-11 | Complete
NARROWS 2102 | Ad Hoc Fault Indicator Installation | 2022-08-02 | 2022-08-16 | 2022-09-23 | Complete
NARROWS 2102 | Additional Detailed Patrol | 2022-08-02 | 2022-08-16 | 2022-09-23 | Complete
NARROWS 2102 | Customer Impact | 2022-08-02 | 2022-08-16 | 2022-08-05 | Complete
NARROWS 2102 | Planned Work and Opportunities | 2022-08-02 | 2022-08-16 | 2022-08-26 | Complete
NARROWS 2102 | Planned Work and Opportunities | 2022-08-02 | 2022-08-16 | 2022-08-26 | Complete
NARROWS 2102 | Settings Review | 2022-08-02 | 2022-08-16 | 2022-09-15 | Complete
NARROWS 2105 | Settings Review | 2022-05-26 | 2022-07-07 | 2022-06-14 | Complete
NARROWS 2105 | Ad Hoc Fault Indicator Installation | 2022-08-08 | 2022-08-22 | 2022-09-16 | Complete
NARROWS 2105 | Animal Guard | 2022-08-08 | 2022-08-22 | 2022-09-13 | Complete
NARROWS 2105 | Planned Work and Opportunities | 2022-08-08 | 2022-08-22 | 2022-08-29 | Complete
NARROWS 2105 | Planned Work and Opportunities | 2022-08-08 | 2022-08-22 | 2022-08-26 | Complete
NARROWS 2105 | Settings Review | 2022-08-08 | 2022-08-22 | 2022-10-06 | Complete
NARROWS 2105 | Vegetation Management Cycle Review | 2022-08-08 | 2022-08-22 | 2022-08-29 | Complete
NORTH BRANCH 1101 | Ad Hoc Fault Indicator Installation | 2022-07-11 |  | 2022-07-11 | Complete
NORTH BRANCH 1101 | Additional Detailed Patrol | 2022-07-11 |  | 2022-07-11 | Complete
NORTH BRANCH 1101 | Trigger Level Outage Actions | 2022-11-03 | 2022-11-17 | 2022-11-28 | Complete
NORTH BRANCH 1101 | Trigger Level Outage Actions | 2022-11-03 | 2022-11-17 | 2022-11-28 | Complete
NORTH BRANCH 1101 | Trigger Level Outage Actions | 2022-11-03 | 2022-11-17 | 2022-11-28 | Complete
NORTH BRANCH 1101 | Trigger Level Outage Actions | 2022-11-03 | 2022-11-17 | 2022-11-28 | Complete
North Dublin 2103 | Ad Hoc Fault Indicator Installation | 2022-08-08 | 2022-08-22 | 2022-09-09 | Complete
North Dublin 2103 | Additional Detailed Patrol | 2022-08-08 | 2022-08-22 | 2022-09-09 | Complete
North Dublin 2103 | Inspection Review | 2022-08-08 | 2022-08-22 | 2022-09-02 | Complete
North Dublin 2103 | Planned Work and Opportunities | 2022-08-08 | 2022-08-22 | 2022-08-12 | Complete
North Dublin 2103 | Planned Work and Opportunities | 2022-08-08 | 2022-08-22 | 2022-08-12 | Complete
North Dublin 2103 | Settings Review | 2022-08-08 | 2022-08-22 | 2022-09-09 | Complete
North Dublin 2103 | Vegetation Management Cycle Review | 2022-08-08 | 2022-08-22 | 2022-08-10 | Complete
North Dublin 2103 | Trigger Level Outage Actions | 2022-11-03 | 2022-11-17 | 2022-11-16 | Complete
North Dublin 2103 | Trigger Level Outage Actions | 2022-11-03 | 2022-11-17 | 2022-11-16 | Complete
North Dublin 2103 | Trigger Level Outage Actions | 2022-11-03 | 2022-11-17 | 2022-11-16 | Complete
OCEANO 1104 | Ad Hoc Fault Indicator Installation | 2022-10-20 | 2022-11-03 | 2022-10-21 | Complete
OCEANO 1104 | Additional Detailed Patrol | 2022-10-20 | 2022-11-03 | 2022-10-21 | Complete
OCEANO 1104 | Animal Guard | 2022-10-20 | 2022-11-03 | 2023-05-26 | Complete
OCEANO 1104 | Planned Work and Opportunities | 2022-10-20 | 2022-11-03 | 2022-10-21 | Complete
OCEANO 1104 | Settings Adjustment | 2022-10-20 | 2022-11-03 | 2022-10-21 | Complete
OCEANO 1104 | Settings Review | 2022-10-20 | 2022-11-03 | 2022-10-21 | Complete
OILFIELDS 1103 | Ad Hoc Fault Indicator Installation | 2022-10-03 | 2022-10-17 | 2022-10-05 | Complete
OILFIELDS 1103 | Additional Detailed Patrol | 2022-10-03 | 2022-10-17 | 2022-10-05 | Complete
OILFIELDS 1103 | Animal Guard | 2022-10-03 | 2022-10-17 | 2023-02-14 | Complete
OILFIELDS 1103 | Planned Work and Opportunities | 2022-10-03 | 2022-10-17 | 2022-10-05 | Complete
OILFIELDS 1103 | Review CAIDI Performance | 2022-10-03 | 2022-10-17 | 2022-12-15 | Complete
OILFIELDS 1103 | Review Response Time | 2022-10-03 | 2022-10-17 | 2022-12-15 | Complete
OILFIELDS 1103 | Settings Review | 2022-10-03 | 2022-10-17 | 2022-10-05 | Complete
OLEMA 1101 | Ad Hoc Fault Indicator Installation | 2022-09-23 | 2022-10-07 | 2022-09-28 | Complete
OLEMA 1101 | Additional Detailed Patrol | 2022-09-23 | 2022-10-07 | 2022-09-28 | Complete
OLEMA 1101 | Animal Guard | 2022-09-23 | 2022-10-07 | 2022-09-26 | Complete
OLEMA 1101 | Planned Work and Opportunities | 2022-09-23 | 2022-10-07 | 2022-10-15 | Complete
OLEMA 1101 | Proactive Fault Indicator Installation | 2022-09-23 | 2022-10-31 | 2022-11-23 | Complete
OLEMA 1101 | Review CAIDI Performance | 2022-09-23 | 2022-10-07 | 2022-09-26 | Complete
OLEMA 1101 | Review Response Time | 2022-09-23 | 2022-10-07 | 2022-09-26 | Complete
OLEMA 1101 | Settings Review | 2022-09-23 | 2022-10-07 | 2022-09-28 | Complete
OLEMA 1101 | Vegetation Management Cycle Review | 2022-09-23 | 2022-11-11 | 2022-11-11 | Complete
OLETA 1102 | Planned Work and Opportunities | 2022-10-31 | 2022-11-14 | 2022-10-31 | Complete
OLETA 1102 | Settings Review | 2022-10-31 | 2022-11-14 | 2022-10-31 | Complete
OLETA 1102 | Ad Hoc Fault Indicator Installation | 2022-11-01 | 2022-11-15 | 2022-11-02 | Complete
OLETA 1102 | Additional Detailed Patrol | 2022-11-01 | 2022-11-15 | 2022-11-02 | Complete
OLETA 1102 | Animal Guard | 2022-11-01 | 2022-11-15 | 2022-11-15 | Complete
OLETA 1102 | Review CAIDI Performance | 2022-11-01 | 2022-11-15 | 2022-11-15 | Complete
PANORAMA 1102 | Ad Hoc Fault Indicator Installation | 2022-07-22 | 2022-08-05 | 2022-12-27 | Complete
PANORAMA 1102 | Additional Detailed Patrol | 2022-07-22 | 2022-08-05 | 2022-11-29 | Complete
PANORAMA 1102 | Animal Guard | 2022-07-22 | 2022-08-05 | 2022-08-03 | Complete
PANORAMA 1102 | Customer Impact | 2022-07-22 | 2022-08-05 | 2022-08-05 | Complete
PANORAMA 1102 | Planned Work and Opportunities | 2022-07-22 | 2022-08-05 | 2022-08-03 | Complete
PANORAMA 1102 | Planned Work and Opportunities | 2022-07-22 | 2022-08-05 | 2022-08-03 | Complete
PANORAMA 1102 | Proactive Fault Indicator Installation | 2022-07-22 | 2022-10-31 | 2022-10-17 | Complete
PANORAMA 1102 | Settings Review | 2022-07-22 | 2022-08-05 | 2022-08-29 | Complete
PANORAMA 1102 | Vegetation Management Cycle Review | 2022-07-22 | 2022-08-05 | 2022-08-10 | Complete
PAUL SWEET 2106 | Ad Hoc Fault Indicator Installation | 2022-08-26 | 2022-09-09 | 2022-09-15 | Complete
PAUL SWEET 2106 | Additional Detailed Patrol | 2022-08-26 | 2022-09-09 | 2022-09-15 | Complete
PAUL SWEET 2106 | Animal Guard | 2022-08-26 | 2022-09-09 | 2022-09-02 | Complete
PAUL SWEET 2106 | Planned Work and Opportunities | 2022-08-26 | 2022-09-09 | 2022-09-15 | Complete
PAUL SWEET 2106 | Proactive Fault Indicator Installation | 2022-08-26 | 2022-10-31 | 2022-10-24 | Complete
PAUL SWEET 2106 | Settings Review | 2022-08-26 | 2022-09-09 | 2022-09-15 | Complete
PENRYN 1103 | Ad Hoc Fault Indicator Installation | 2022-10-03 | 2022-10-17 | 2022-10-20 | Complete
PENRYN 1103 | Additional Detailed Patrol | 2022-10-03 | 2022-10-17 | 2022-10-20 | Complete
PENRYN 1103 | Planned Work and Opportunities | 2022-10-03 | 2022-10-17 | 2022-10-15 | Complete
PENRYN 1103 | Proactive Fault Indicator Installation | 2022-10-03 | 2022-10-17 | 2022-07-05 | Complete
PENRYN 1103 | Settings Review | 2022-10-03 | 2022-10-17 | 2022-10-11 | Complete
PENRYN 1103 | Vegetation Management Cycle Review | 2022-10-03 | 2022-11-11 | 2022-11-11 | Complete
PENRYN 1105 | Animal Guard | 2022-09-13 | 2022-09-27 | 2022-12-13 | Complete
PENRYN 1105 | Ad Hoc Fault Indicator Installation | 2022-09-14 | 2022-09-28 | 2022-10-05 | Complete
PENRYN 1105 | Additional Detailed Patrol | 2022-09-14 | 2022-09-28 | 2022-10-05 | Complete
PENRYN 1105 | Planned Work and Opportunities | 2022-09-14 | 2022-09-28 | 2022-10-07 | Complete
PENRYN 1105 | Proactive Fault Indicator Installation | 2022-09-14 | 2022-10-31 | 2022-10-14 | Complete
PENRYN 1105 | Settings Review | 2022-09-14 | 2022-09-28 | 2022-10-11 | Complete
PENRYN 1105 | Trigger Level Outage Actions | 2022-11-03 | 2022-11-17 | 2022-11-04 | Complete
PENRYN 1105 | Trigger Level Outage Actions | 2022-11-03 | 2022-11-17 | 2022-11-04 | Complete
PENRYN 1105 | Trigger Level Outage Actions | 2022-11-03 | 2022-11-17 | 2022-11-04 | Complete
PENRYN 1105 | Trigger Level Outage Actions | 2022-11-03 | 2022-11-17 | 2022-11-04 | Complete
PENRYN 1105 | Trigger Level Outage Actions | 2022-11-03 | 2022-11-17 | 2022-11-04 | Complete
PENRYN 1105 | Trigger Level Outage Actions | 2022-11-03 | 2022-11-17 | 2022-11-04 | Complete
PENRYN 1105 | Trigger Level Outage Actions | 2022-11-03 | 2022-11-17 | 2022-11-04 | Complete
PEORIA 1701 | Ad Hoc Fault Indicator Installation | 2022-09-26 | 2022-10-10 | 2022-10-06 | Complete
PEORIA 1701 | Additional Detailed Patrol | 2022-09-26 | 2022-10-10 | 2022-10-06 | Complete
PEORIA 1701 | Planned Work and Opportunities | 2022-09-26 | 2022-10-10 | 2022-10-06 | Complete
PEORIA 1701 | Settings Review | 2022-09-26 | 2022-10-10 | 2022-10-06 | Complete
PEORIA 1704 | Ad Hoc Fault Indicator Installation | 2022-10-12 | 2022-10-26 | 2022-11-01 | Complete
PEORIA 1704 | Additional Detailed Patrol | 2022-10-12 | 2022-10-26 | 2022-10-12 | Complete
PEORIA 1704 | Planned Work and Opportunities | 2022-10-12 | 2022-10-26 | 2022-10-27 | Complete
PEORIA 1704 | Review CAIDI Performance | 2022-10-12 | 2022-10-26 | 2022-10-20 | Complete
PEORIA 1705 | Ad Hoc Fault Indicator Installation | 2022-09-06 | 2022-09-20 | 2022-09-22 | Complete
PEORIA 1705 | Additional Detailed Patrol | 2022-09-06 | 2022-09-20 | 2022-09-12 | Complete
PEORIA 1705 | Animal Guard | 2022-09-06 | 2022-09-20 | 2022-09-07 | Complete
PEORIA 1705 | Planned Work and Opportunities | 2022-09-06 | 2022-09-20 | 2022-10-31 | Complete
PEORIA 1705 | Settings Review | 2022-09-06 | 2022-09-20 | 2022-09-07 | Complete
PETALUMA C 1109 | Ad Hoc Fault Indicator Installation | 2022-10-06 | 2022-10-20 | 2022-10-21 | Complete
PETALUMA C 1109 | Additional Detailed Patrol | 2022-10-06 | 2022-10-20 | 2022-10-21 | Complete
PETALUMA C 1109 | Animal Guard | 2022-10-06 | 2022-10-20 | 2022-11-01 | Complete
PETALUMA C 1109 | Planned Work and Opportunities | 2022-10-06 | 2022-10-20 | 2022-10-18 | Complete
PETALUMA C 1109 | Settings Review | 2022-10-06 | 2022-10-20 | 2022-10-31 | Complete
PETALUMA C 1109 | Vegetation Management Cycle Review | 2022-10-06 | 2022-11-11 | 2022-11-11 | Complete
PETALUMA C 1109 | Settings Adjustment | 2022-10-18 |  | 2022-10-21 | Complete
PHILO 1102 | Ad Hoc Fault Indicator Installation | 2022-11-02 | 2022-11-16 | 2022-12-07 | Complete
PHILO 1102 | Additional Detailed Patrol | 2022-11-02 | 2022-11-16 | 2022-12-07 | Complete
PHILO 1102 | Planned Work and Opportunities | 2022-11-02 | 2022-11-16 | 2022-11-18 | Complete
PHILO 1102 | Review CAIDI Performance | 2022-11-02 | 2022-11-16 | 2022-12-06 | Complete
PHILO 1102 | Review Response Time | 2022-11-02 | 2022-11-16 | 2022-12-06 | Complete
PHILO 1102 | Settings Review | 2022-11-02 | 2022-11-16 | 2022-12-06 | Complete
PHILO 1102 | Vegetation Management Cycle Review | 2022-11-02 | 2022-11-16 | 2022-11-22 | Complete
PLACERVILLE 2106 | Ad Hoc Fault Indicator Installation | 2022-09-09 | 2022-09-23 | 2022-12-27 | Complete
PLACERVILLE 2106 | Additional Detailed Patrol | 2022-09-09 | 2022-09-23 | 2022-12-13 | Complete
PLACERVILLE 2106 | Planned Work and Opportunities | 2022-09-09 | 2022-09-23 | 2022-09-27 | Complete
PLACERVILLE 2106 | Proactive Fault Indicator Installation | 2022-09-09 | 2022-10-31 | 2022-10-19 | Complete
PLACERVILLE 2106 | Settings Review | 2022-09-09 | 2022-09-23 | 2022-10-11 | Complete
PLACERVILLE 2106 | Vegetation Management Cycle Review | 2022-09-09 | 2022-09-23 | 2022-10-11 | Complete
POSO MOUNTAIN 2101 | Ad Hoc Fault Indicator Installation | 2022-06-10 | 2022-07-08 | 2022-06-24 | Complete
POSO MOUNTAIN 2101 | Animal Guard | 2022-06-10 | 2022-07-08 | 2022-06-24 | Complete
POSO MOUNTAIN 2101 | Planned Work and Opportunities | 2022-06-10 | 2022-07-08 | 2022-06-27 | Complete
POSO MOUNTAIN 2101 | Animal Guard | 2022-11-15 | 2022-11-29 | 2023-01-28 | Complete
POSO MOUNTAIN 2101 | Settings Review | 2022-11-30 | 2022-12-14 | 2022-12-22 | Complete
PUEBLO 2103 | Ad Hoc Fault Indicator Installation | 2022-09-19 | 2022-10-03 | 2022-10-05 | Complete
PUEBLO 2103 | Additional Detailed Patrol | 2022-09-19 | 2022-10-03 | 2022-10-05 | Complete
PUEBLO 2103 | Planned Work and Opportunities | 2022-09-19 | 2022-10-03 | 2022-10-07 | Complete
PUEBLO 2103 | Proactive Fault Indicator Installation | 2022-09-19 | 2022-10-31 | 2022-09-19 | Complete
PUEBLO 2103 | Settings Review | 2022-09-19 | 2022-10-03 | 2022-10-07 | Complete
PUEBLO 2104 | Ad Hoc Fault Indicator Installation | 2022-09-06 | 2022-09-20 | 2022-09-27 | Complete
PUEBLO 2104 | Additional Detailed Patrol | 2022-09-06 | 2022-09-20 | 2022-09-27 | Complete
PUEBLO 2104 | Planned Work and Opportunities | 2022-09-06 | 2022-09-20 | 2022-10-07 | Complete
PUEBLO 2104 | Settings Review | 2022-09-06 | 2022-09-20 | 2022-10-06 | Complete
PUEBLO 2104 | FuseSaver Installation | 2022-11-07 | 2022-11-21 | 2023-01-24 | Complete
PUTAH CREEK 1105 | Settings Review | 2022-05-15 | 2022-05-29 | 2022-05-24 | Complete
RED BLUFF 1104 | Ad Hoc Fault Indicator Installation | 2022-08-02 | 2022-08-16 | 2022-08-05 | Complete
RED BLUFF 1104 | Additional Detailed Patrol | 2022-08-02 | 2022-08-16 | 2022-08-05 | Complete
RED BLUFF 1104 | Customer Impact | 2022-08-02 | 2022-08-16 | 2022-08-05 | Complete
RED BLUFF 1104 | Planned Work and Opportunities | 2022-08-02 | 2022-08-16 | 2022-08-02 | Complete
RED BLUFF 1104 | Planned Work and Opportunities | 2022-08-02 | 2022-08-16 | 2022-08-03 | Complete
RED BLUFF 1104 | Settings Review | 2022-08-02 | 2022-08-16 | 2022-09-06 | Complete
RED BLUFF 1104 | Validate Ad Hoc Fault Indicators Installation | 2022-08-02 | 2022-08-16 | 2022-08-08 | Complete
RED BLUFF 1104 | Vegetation Management Cycle Review | 2022-08-02 | 2022-08-16 | 2022-08-05 | Complete
RESERVATION ROAD 1101 | Ad Hoc Fault Indicator Installation | 2022-11-04 | 2022-11-18 | 2022-11-09 | Complete
RESERVATION ROAD 1101 | Additional Detailed Patrol | 2022-11-04 | 2022-11-18 | 2022-11-09 | Complete
RESERVATION ROAD 1101 | Planned Work and Opportunities | 2022-11-04 | 2022-11-18 | 2022-11-28 | Complete
RESERVATION ROAD 1101 | Settings Review | 2022-11-04 | 2022-11-18 | 2022-11-29 | Complete
RESERVATION ROAD 1102 | Ad Hoc Fault Indicator Installation | 2022-07-19 | 2022-08-02 | 2022-09-07 | Complete
RESERVATION ROAD 1102 | Additional Detailed Patrol | 2022-07-19 | 2022-08-02 | 2022-09-07 | Complete
RESERVATION ROAD 1102 | Customer Impact | 2022-07-19 | 2022-08-02 | 2022-08-05 | Complete
RESERVATION ROAD 1102 | Planned Work and Opportunities | 2022-07-19 | 2022-08-02 | 2022-09-10 | Complete
RESERVATION ROAD 1102 | Settings Review | 2022-07-19 | 2022-08-02 | 2022-09-07 | Complete
RIO DELL 1102 | Settings Review | 2022-10-17 | 2022-10-31 | 2022-10-31 | Complete
RIO DELL 1102 | Vegetation Management Cycle Review | 2022-10-17 | 2022-11-11 | 2022-11-22 | Complete
ROB ROY 2104 | Ad Hoc Fault Indicator Installation | 2022-10-19 | 2022-11-02 | 2022-11-02 | Complete
ROB ROY 2104 | Additional Detailed Patrol | 2022-10-19 | 2022-11-02 | 2022-11-02 | Complete
ROB ROY 2104 | Planned Work and Opportunities | 2022-10-19 | 2022-11-02 | 2022-11-01 | Complete
ROB ROY 2104 | Settings Review | 2022-10-19 | 2022-11-02 | 2022-11-02 | Complete
ROB ROY 2105 | Ad Hoc Fault Indicator Installation | 2022-09-06 | 2022-09-20 | 2022-09-27 | Complete
ROB ROY 2105 | Additional Detailed Patrol | 2022-09-06 | 2022-09-20 | 2022-09-27 | Complete
ROB ROY 2105 | Animal Guard | 2022-09-06 | 2022-09-20 | 2022-09-30 | Complete
ROB ROY 2105 | Planned Work and Opportunities | 2022-09-06 | 2022-09-20 | 2022-09-27 | Complete
ROB ROY 2105 | Proactive Fault Indicator Installation | 2022-09-06 | 2022-09-20 | 2022-07-08 | Complete
ROB ROY 2105 | Settings Review | 2022-09-06 | 2022-09-20 | 2023-01-24 | Complete
ROB ROY 2105 | Vegetation Management Cycle Review | 2022-09-06 | 2022-09-20 | 2022-10-26 | Complete
ROSSMOOR 1108 | Ad Hoc Fault Indicator Installation | 2022-10-07 | 2022-10-21 | 2022-12-13 | Complete
ROSSMOOR 1108 | Additional Detailed Patrol | 2022-10-07 | 2022-10-21 | 2022-12-13 | Complete
ROSSMOOR 1108 | Animal Guard | 2022-10-07 | 2022-10-21 | 2022-11-14 | Complete
ROSSMOOR 1108 | Planned Work and Opportunities | 2022-10-07 | 2022-10-21 | 2022-10-07 | Complete
ROSSMOOR 1108 | Settings Review | 2022-10-07 | 2022-10-21 | 2022-10-11 | Complete
SAN JUSTO 1101 | Ad Hoc Fault Indicator Installation | 2022-10-06 | 2022-10-20 | 2022-10-26 | Complete
SAN JUSTO 1101 | Additional Detailed Patrol | 2022-10-06 | 2022-10-20 | 2022-10-26 | Complete
SAN JUSTO 1101 | Planned Work and Opportunities | 2022-10-06 | 2022-10-20 | 2022-10-23 | Complete
SAN JUSTO 1101 | Settings Review | 2022-10-06 | 2022-10-20 | 2022-10-28 | Complete
SAN LUIS OBISPO 1104 | Ad Hoc Fault Indicator Installation | 2022-09-21 | 2022-10-05 | 2022-09-22 | Complete
SAN LUIS OBISPO 1104 | Additional Detailed Patrol | 2022-09-21 | 2022-10-05 | 2022-09-22 | Complete
SAN LUIS OBISPO 1104 | Animal Guard | 2022-09-21 | 2022-10-05 | 2022-10-19 | Complete
SAN LUIS OBISPO 1104 | Planned Work and Opportunities | 2022-09-21 | 2022-10-05 | 2022-10-11 | Complete
SAN LUIS OBISPO 1104 | Settings Review | 2022-09-21 | 2022-10-05 | 2022-09-22 | Complete
SAN LUIS OBISPO 1107 | Ad Hoc Fault Indicator Installation | 2022-05-16 | 2022-05-23 | 2022-05-18 | Complete
SAN LUIS OBISPO 1107 | Additional Detailed Patrol | 2022-05-16 | 2022-05-23 | 2022-05-18 | Complete
SAN LUIS OBISPO 1107 | Ad Hoc Fault Indicator Installation | 2022-06-09 | 2022-07-07 | 2022-06-21 | Complete
SAN LUIS OBISPO 1107 | Vegetation Management Cycle Review | 2022-06-09 | 2022-07-07 | 2022-07-12 | Complete
SAN RAMON 2103 | Settings Review | 2022-06-13 | 2022-06-27 | 2022-06-13 | Complete
SAN RAMON 2107 | Animal Guard | 2022-10-12 | 2022-10-26 | 2022-12-08 | Complete
SAN RAMON 2107 | Planned Work and Opportunities | 2022-10-12 | 2022-10-26 | 2022-11-28 | Complete
SAND CREEK 1103 | Ad Hoc Fault Indicator Installation | 2022-09-22 | 2022-10-06 | 2022-10-13 | Complete
SAND CREEK 1103 | Additional Detailed Patrol | 2022-09-22 | 2022-10-06 | 2022-10-13 | Complete
SAND CREEK 1103 | Planned Work and Opportunities | 2022-09-22 | 2022-10-06 | 2022-11-14 | Complete
SAND CREEK 1103 | Review CAIDI Performance | 2022-09-22 | 2022-10-06 | 2022-10-06 | Complete
SAND CREEK 1103 | Review Response Time | 2022-09-22 | 2022-10-06 | 2022-10-06 | Complete
SAND CREEK 1103 | Settings Review | 2022-09-22 | 2022-10-06 | 2022-10-04 | Complete
SANTA YNEZ 1101 | Ad Hoc Fault Indicator Installation | 2022-11-15 | 2022-11-29 | 2022-11-21 | Complete
SANTA YNEZ 1101 | Additional Detailed Patrol | 2022-11-15 | 2022-11-29 | 2022-11-21 | Complete
SANTA YNEZ 1101 | Animal Guard | 2022-11-15 | 2022-11-29 | 2023-05-26 | Complete
SANTA YNEZ 1101 | Planned Work and Opportunities | 2022-11-15 | 2022-11-29 | 2022-12-01 | Complete
SANTA YNEZ 1101 | Settings Review | 2022-11-15 | 2022-11-29 | 2022-11-29 | Complete
SANTA YNEZ 1101 | Trigger Level Outage Actions | 2022-11-15 | 2022-11-29 | 2022-12-01 | Complete
SARATOGA 1103 | Ad Hoc Fault Indicator Installation | 2022-10-27 | 2022-11-10 | 2022-11-03 | Complete
SARATOGA 1103 | Additional Detailed Patrol | 2022-10-27 | 2022-11-10 | 2022-11-03 | Complete
SARATOGA 1103 | Animal Guard | 2022-10-27 | 2022-11-10 | 2022-11-16 | Complete
SARATOGA 1103 | Planned Work and Opportunities | 2022-10-27 | 2022-11-10 | 2022-11-17 | Complete
SARATOGA 1103 | Settings Review | 2022-10-27 | 2022-11-10 | 2022-11-30 | Complete
SHINGLE SPRINGS 2108 | Line Sensor Installation | 2022-05-31 | 2022-06-14 | 2022-06-08 | Complete
SHINGLE SPRINGS 2108 | Planned Work and Opportunities | 2022-05-31 | 2022-06-14 | 2022-06-08 | Complete
SHINGLE SPRINGS 2108 | Settings Review | 2022-05-31 | 2022-06-14 | 2022-06-08 | Complete
SHINGLE SPRINGS 2108 | Trigger Level Outage Actions | 2022-11-08 | 2022-11-22 | 2022-11-18 | Complete
SHINGLE SPRINGS 2108 | Trigger Level Outage Actions | 2022-11-08 | 2022-11-22 | 2022-11-18 | Complete
SHINGLE SPRINGS 2108 | Trigger Level Outage Actions | 2022-11-08 | 2022-11-22 | 2022-11-18 | Complete
SHINGLE SPRINGS 2108 | Trigger Level Outage Actions | 2022-11-08 | 2022-11-22 | 2022-11-18 | Complete
SHINGLE SPRINGS 2108 | Trigger Level Outage Actions | 2022-11-08 | 2022-11-22 | 2022-11-18 | Complete
SHINGLE SPRINGS 2109 | Ad Hoc Fault Indicator Installation | 2022-08-03 | 2022-08-17 | 2022-08-30 | Complete
SHINGLE SPRINGS 2109 | Additional Detailed Patrol | 2022-08-03 | 2022-08-17 | 2022-08-30 | Complete
SHINGLE SPRINGS 2109 | Animal Guard | 2022-08-03 | 2022-08-17 | 2022-08-22 | Complete
SHINGLE SPRINGS 2109 | Customer Impact | 2022-08-03 | 2022-08-17 | 2022-08-05 | Complete
SHINGLE SPRINGS 2109 | Planned Work and Opportunities | 2022-08-03 | 2022-08-17 | 2022-08-16 | Complete
SHINGLE SPRINGS 2109 | Planned Work and Opportunities | 2022-08-03 | 2022-08-17 | 2022-08-16 | Complete
SHINGLE SPRINGS 2109 | Settings Review | 2022-08-03 | 2022-08-17 | 2022-08-16 | Complete
SHINGLE SPRINGS 2109 | Vegetation Management Cycle Review | 2022-08-03 | 2022-08-17 | 2022-08-03 | Complete
SILVERADO 2102 | Ad Hoc Fault Indicator Installation | 2022-10-03 | 2022-10-17 | 2022-10-06 | Complete
SILVERADO 2102 | Additional Detailed Patrol | 2022-10-03 | 2022-10-17 | 2022-10-14 | Complete
SILVERADO 2102 | Planned Work and Opportunities | 2022-10-03 | 2022-10-17 | 2022-10-15 | Complete
SILVERADO 2102 | Proactive Fault Indicator Installation | 2022-10-03 | 2022-10-17 | 2022-06-10 | Complete
SILVERADO 2102 | Review CAIDI Performance | 2022-10-03 | 2022-10-17 | 2022-12-06 | Complete
SILVERADO 2102 | Settings Review | 2022-10-03 | 2022-10-17 | 2022-10-12 | Complete
SILVERADO 2102 | Vegetation Management Cycle Review | 2022-10-03 | 2022-11-11 | 2022-11-11 | Complete
SILVERADO 2103 | Ad Hoc Fault Indicator Installation | 2022-10-03 | 2022-10-17 | 2022-10-07 | Complete
SILVERADO 2103 | Additional Detailed Patrol | 2022-10-03 | 2022-10-17 | 2022-10-07 | Complete
SILVERADO 2103 | Planned Work and Opportunities | 2022-10-03 | 2022-10-17 | 2022-10-15 | Complete
SILVERADO 2103 | Settings Review | 2022-10-03 | 2022-10-17 | 2022-10-11 | Complete
SILVERADO 2103 | Vegetation Management Cycle Review | 2022-10-03 | 2022-11-11 | 2022-11-11 | Complete
SILVERADO 2104 | Ad Hoc Fault Indicator Installation | 2022-08-19 | 2022-09-02 | 2022-08-30 | Complete
SILVERADO 2104 | Additional Detailed Patrol | 2022-08-19 | 2022-09-02 | 2022-08-30 | Complete
SILVERADO 2104 | Animal Guard | 2022-08-19 | 2022-09-02 | 2022-08-24 | Complete
SILVERADO 2104 | Circuit Configuration | 2022-08-19 | 2022-09-02 | 2022-08-29 | Complete
SILVERADO 2104 | Planned Work and Opportunities | 2022-08-19 | 2022-09-02 | 2022-09-01 | Complete
SILVERADO 2104 | Proactive Fault Indicator Installation | 2022-08-19 | 2022-09-02 | 2022-06-10 | Complete
SILVERADO 2104 | Settings Review | 2022-08-19 | 2022-09-02 | 2022-09-13 | Complete
SILVERADO 2104 | Trigger Level Outage Actions | 2022-11-07 | 2022-11-21 | 2022-11-18 | Complete
SILVERADO 2104 | Trigger Level Outage Actions | 2022-11-07 | 2022-11-21 | 2022-11-18 | Complete
SILVERADO 2104 | Trigger Level Outage Actions | 2022-11-07 | 2022-11-21 | 2022-11-18 | Complete
SILVERADO 2105 | Ad Hoc Fault Indicator Installation | 2022-08-15 | 2022-08-29 | 2022-09-22 | Complete
SILVERADO 2105 | Additional Detailed Patrol | 2022-08-15 | 2022-08-29 | 2022-09-22 | Complete
SILVERADO 2105 | Planned Work and Opportunities | 2022-08-15 | 2022-08-29 | 2022-09-01 | Complete
SILVERADO 2105 | Proactive Fault Indicator Installation | 2022-08-15 | 2022-10-31 | 2022-11-01 | Complete
SILVERADO 2105 | Settings Review | 2022-08-15 | 2022-08-29 | 2022-09-01 | Complete
SISQUOC 1102 | Additional Detailed Patrol | 2022-12-01 | 2022-12-15 | 2022-12-15 | Complete
SISQUOC 1102 | Settings Review | 2022-12-01 | 2022-12-15 | 2022-12-01 | Complete
SONOMA 1102 | Ad Hoc Fault Indicator Installation | 2022-06-09 | 2022-07-07 | 2022-06-24 | Complete
SONOMA 1102 | Additional Detailed Patrol | 2022-06-09 | 2022-07-07 | 2022-06-17 | Complete
SONOMA 1102 | EC Tag Work | 2022-06-09 | 2022-07-07 | 2022-07-12 | Complete
SONOMA 1102 | Planned Work and Opportunities | 2022-06-09 | 2022-07-07 | 2022-07-12 | Complete
SONOMA 1102 | Settings Review | 2022-06-09 | 2022-07-07 | 2022-06-15 | Complete
SONOMA 1107 | Ad Hoc Fault Indicator Installation | 2022-09-14 | 2022-09-28 | 2022-09-15 | Complete
SONOMA 1107 | Additional Detailed Patrol | 2022-09-14 | 2022-09-28 | 2022-09-15 | Complete
SONOMA 1107 | Planned Work and Opportunities | 2022-09-14 | 2022-09-28 | 2022-09-15 | Complete
SONOMA 1107 | Settings Review | 2022-09-14 | 2022-09-28 | 2022-09-15 | Complete
STAFFORD 1102 | Ad Hoc Fault Indicator Installation | 2022-09-09 | 2022-09-23 | 2022-09-14 | Complete
STAFFORD 1102 | Additional Detailed Patrol | 2022-09-09 | 2022-09-23 | 2022-09-14 | Complete
STAFFORD 1102 | Animal Guard | 2022-09-09 | 2022-09-23 | 2022-09-28 | Complete
STAFFORD 1102 | Planned Work and Opportunities | 2022-09-09 | 2022-09-23 | 2022-09-23 | Complete
STAFFORD 1102 | Settings Review | 2022-09-09 | 2022-09-23 | 2022-09-14 | Complete
STANISLAUS 1701 | Ad Hoc Fault Indicator Installation | 2022-09-15 | 2022-09-29 | 2022-10-12 | Complete
STANISLAUS 1701 | Additional Detailed Patrol | 2022-09-15 | 2022-09-29 | 2022-10-12 | Complete
STANISLAUS 1701 | Planned Work and Opportunities | 2022-09-15 | 2022-09-29 | 2022-11-09 | Complete
STANISLAUS 1701 | Proactive Fault Indicator Installation | 2022-09-15 | 2022-09-29 | 2022-06-14 | Complete
STANISLAUS 1701 | Settings Review | 2022-09-15 | 2022-09-29 | 2022-09-26 | Complete
STANISLAUS 1701 | Trigger Level Outage Actions | 2022-11-07 | 2022-11-21 | 2022-11-09 | Complete
STANISLAUS 1701 | Trigger Level Outage Actions | 2022-11-07 | 2022-11-21 | 2022-11-09 | Complete
STANISLAUS 1701 | Trigger Level Outage Actions | 2022-11-07 | 2022-11-21 | 2022-11-09 | Complete
STANISLAUS 1702 | Ad Hoc Fault Indicator Installation | 2022-09-15 | 2022-09-29 | 2022-10-12 | Complete
STANISLAUS 1702 | Additional Detailed Patrol | 2022-09-15 | 2022-09-29 | 2022-10-12 | Complete
STANISLAUS 1702 | Planned Work and Opportunities | 2022-09-15 | 2022-09-29 | 2022-11-11 | Complete
STANISLAUS 1702 | Proactive Fault Indicator Installation | 2022-09-15 | 2022-09-29 | 2022-06-03 | Complete
STANISLAUS 1702 | Settings Review | 2022-09-15 | 2022-09-29 | 2022-09-20 | Complete
STONE CORRAL 1108 | Ad Hoc Fault Indicator Installation | 2022-10-12 | 2022-10-26 | 2022-10-13 | Complete
STONE CORRAL 1108 | Additional Detailed Patrol | 2022-10-12 | 2022-10-26 | 2022-10-13 | Complete
STONE CORRAL 1108 | Animal Guard | 2022-10-12 | 2022-10-26 | 2022-10-14 | Complete
STONE CORRAL 1108 | Planned Work and Opportunities | 2022-10-12 | 2022-10-26 | 2022-11-21 | Complete
STONE CORRAL 1108 | Review CAIDI Performance | 2022-10-12 | 2022-10-26 | 2022-10-14 | Complete
STONE CORRAL 1108 | Review Response Time | 2022-10-12 | 2022-10-26 | 2022-10-14 | Complete
STONE CORRAL 1108 | Settings Review | 2022-10-12 | 2022-10-26 | 2022-10-12 | Complete
SUNOL 1101 | Ad Hoc Fault Indicator Installation | 2022-09-21 | 2022-10-05 | 2022-10-27 | Complete
SUNOL 1101 | Additional Detailed Patrol | 2022-09-21 | 2022-10-05 | 2023-01-18 | Complete
SUNOL 1101 | Animal Guard | 2022-09-21 | 2022-10-05 | 2022-10-05 | Complete
SUNOL 1101 | Planned Work and Opportunities | 2022-09-21 | 2022-10-05 | 2022-10-05 | Complete
SUNOL 1101 | Review CAIDI Performance | 2022-09-21 | 2022-10-05 | 2022-10-05 | Complete
SUNOL 1101 | Settings Review | 2022-09-21 | 2022-10-05 | 2022-10-24 | Complete
SUNOL 1101 | Vegetation Management Cycle Review | 2022-09-21 | 2022-10-05 | 2022-10-11 | Complete
SWIFT 2102 | Ad Hoc Fault Indicator Installation | 2022-09-09 | 2022-09-23 | 2022-10-11 | Complete
SWIFT 2102 | Additional Detailed Patrol | 2022-09-09 | 2022-09-23 | 2022-10-11 | Complete
SWIFT 2102 | Planned Work and Opportunities | 2022-09-09 | 2022-09-23 | 2022-10-11 | Complete
SWIFT 2102 | Settings Review | 2022-09-09 | 2022-09-23 | 2022-09-28 | Complete
SWIFT 2102 | Load Transfer | 2022-09-16 |  | 2022-09-16 | Complete
TASSAJARA 2103 | Ad Hoc Fault Indicator Installation | 2022-08-29 | 2022-09-12 | 2022-09-02 | Complete
TASSAJARA 2103 | Additional Detailed Patrol | 2022-08-29 | 2022-09-12 | 2022-09-02 | Complete
TASSAJARA 2103 | Planned Work and Opportunities | 2022-08-29 | 2022-09-12 | 2022-08-25 | Complete
TASSAJARA 2103 | Settings Review | 2022-08-29 | 2022-09-12 | 2022-08-29 | Complete
TEMPLETON 2110 | Ad Hoc Fault Indicator Installation | 2022-09-26 | 2022-10-10 | 2022-10-10 | Complete
TEMPLETON 2110 | Additional Detailed Patrol | 2022-09-26 | 2022-10-10 | 2022-10-10 | Complete
TEMPLETON 2110 | Planned Work and Opportunities | 2022-09-26 | 2022-10-10 | 2022-10-23 | Complete
TEMPLETON 2110 | Proactive Fault Indicator Installation | 2022-09-26 | 2022-10-31 | 2022-10-11 | Complete
TEMPLETON 2110 | Review CAIDI Performance | 2022-09-26 | 2022-10-10 | 2022-09-24 | Complete
TEMPLETON 2110 | Settings Review | 2022-09-26 | 2022-10-10 | 2022-10-10 | Complete
TEMPLETON 2110 | Vegetation Management Cycle Review | 2022-09-26 | 2022-10-10 | 2022-10-27 | Complete
TEMPLETON 2111 | Animal Guard | 2022-09-20 | 2022-10-04 | 2023-05-26 | Complete
TEMPLETON 2113 | Ad Hoc Fault Indicator Installation | 2022-08-12 | 2022-08-26 | 2022-09-12 | Complete
TEMPLETON 2113 | Additional Detailed Patrol | 2022-08-12 | 2022-08-26 | 2022-09-12 | Complete
TEMPLETON 2113 | Planned Work and Opportunities | 2022-08-12 | 2022-08-26 | 2022-09-10 | Complete
TEMPLETON 2113 | Proactive Fault Indicator Installation | 2022-08-12 | 2022-11-05 | 2022-12-02 | Complete
TEMPLETON 2113 | Settings Review | 2022-08-12 | 2022-08-26 | 2022-09-12 | Complete
TIVY VALLEY 1107 | Ad Hoc Fault Indicator Installation | 2022-07-18 | 2022-08-01 | 2022-08-29 | Complete
TIVY VALLEY 1107 | Planned Work and Opportunities | 2022-07-18 | 2022-08-01 | 2022-08-26 | Complete
TIVY VALLEY 1107 | Planned Work and Opportunities | 2022-07-18 | 2022-08-01 | 2022-08-26 | Complete
TIVY VALLEY 1107 | Settings Review | 2022-07-18 | 2022-08-01 | 2022-09-02 | Complete
TIVY VALLEY 1107 | Vegetation Management Cycle Review | 2022-09-22 | 2022-10-06 | 2022-10-19 | Complete
TYLER 1105 | Planned Work and Opportunities | 2022-06-15 | 2022-07-11 | 2022-07-14 | Complete
TYLER 1105 | Ad Hoc Fault Indicator Installation | 2022-07-26 | 2022-08-09 | 2022-09-06 | Complete
TYLER 1105 | Additional Detailed Patrol | 2022-07-26 | 2022-08-09 | 2022-09-02 | Complete
TYLER 1105 | Customer Impact | 2022-07-26 | 2022-08-09 | 2022-08-05 | Complete
TYLER 1105 | Patrol Zones | 2022-07-26 | 2022-08-09 | 2022-09-02 | Complete
TYLER 1105 | Planned Work and Opportunities | 2022-07-26 | 2022-08-09 | 2022-08-05 | Complete
TYLER 1105 | Planned Work and Opportunities | 2022-07-26 | 2022-08-09 | 2022-08-05 | Complete
TYLER 1105 | Settings Review | 2022-07-26 | 2022-08-09 | 2022-08-26 | Complete
TYLER 1105 | Tag Prioritization | 2022-07-26 | 2022-08-09 | 2022-09-02 | Complete
TYLER 1105 | Vegetation Management Cycle Review | 2022-07-26 | 2022-08-09 | 2022-07-26 | Complete
TYLER 1106 | EC Tag Work | 2022-06-04 | 2022-07-11 | 2022-06-06 | Complete
TYLER 1107 | Additional Detailed Patrol | 2022-06-06 | 2022-07-11 | 2022-06-06 | Complete
UPPER LAKE 1101 | Trigger Level Outage Actions | 2022-11-09 | 2022-11-23 | 2022-11-18 | Complete
UPPER LAKE 1101 | Trigger Level Outage Actions | 2022-11-09 | 2022-11-23 | 2022-11-18 | Complete
UPPER LAKE 1101 | Trigger Level Outage Actions | 2022-11-09 | 2022-11-23 | 2022-11-18 | Complete
VASCO 1102 | Ad Hoc Fault Indicator Installation | 2022-11-02 | 2022-11-16 | 2022-11-30 | Complete
VASCO 1102 | Additional Detailed Patrol | 2022-11-02 | 2022-11-16 | 2022-11-30 | Complete
VASCO 1102 | Planned Work and Opportunities | 2022-11-02 | 2022-11-16 | 2022-11-15 | Complete
VASCO 1102 | Review CAIDI Performance | 2022-11-02 | 2022-11-16 | 2022-12-06 | Complete
VASCO 1102 | Settings Review | 2022-11-02 | 2022-11-16 | 2022-11-07 | Complete
VASCO 1102 | Vegetation Management Cycle Review | 2022-11-02 | 2022-11-16 | 2022-11-22 | Complete
VOLTA 1101 | Ad Hoc Fault Indicator Installation | 2022-10-03 | 2022-10-17 | 2022-10-19 | Complete
VOLTA 1101 | Additional Detailed Patrol | 2022-10-03 | 2022-10-17 | 2022-10-19 | Complete
VOLTA 1101 | Planned Work and Opportunities | 2022-10-03 | 2022-10-17 | 2022-10-15 | Complete
VOLTA 1101 | Proactive Fault Indicator Installation | 2022-10-03 | 2022-10-31 | 2022-12-02 | Complete
VOLTA 1101 | Settings Review | 2022-10-03 | 2022-10-17 | 2022-10-13 | Complete
VOLTA 1101 | Vegetation Management Cycle Review | 2022-10-03 | 2022-11-11 | 2022-11-11 | Complete
WEST POINT 1102 | Ad Hoc Fault Indicator Installation | 2022-11-03 | 2022-11-17 | 2022-11-07 | Complete
WEST POINT 1102 | Additional Detailed Patrol | 2022-11-03 | 2022-11-17 | 2022-11-07 | Complete
WEST POINT 1102 | Planned Work and Opportunities | 2022-11-03 | 2022-11-17 | 2022-11-21 | Complete
WEST POINT 1102 | Review CAIDI Performance | 2022-11-03 | 2022-11-17 | 2022-11-15 | Complete
WEST POINT 1102 | Review Outage for Cause | 2022-11-03 | 2022-11-17 | 2022-11-07 | Complete
WEST POINT 1102 | Review Response Time | 2022-11-03 | 2022-11-17 | 2022-11-15 | Complete
WEST POINT 1102 | Settings Review | 2022-11-03 | 2022-11-17 | 2022-11-08 | Complete
WHITMORE 1101 | Ad Hoc Fault Indicator Installation | 2022-08-15 | 2022-08-29 | 2022-09-14 | Complete
WHITMORE 1101 | Additional Detailed Patrol | 2022-08-15 | 2022-08-29 | 2022-09-14 | Complete
WHITMORE 1101 | Planned Work and Opportunities | 2022-08-15 | 2022-08-29 | 2022-08-16 | Complete
WHITMORE 1101 | Planned Work and Opportunities | 2022-08-15 | 2022-08-29 | 2022-08-16 | Complete
WHITMORE 1101 | Settings Review | 2022-08-15 | 2022-08-29 | 2022-09-12 | Complete
WILLITS 1103 | Ad Hoc Fault Indicator Installation | 2022-10-03 | 2022-10-17 | 2022-11-03 | Complete
WILLITS 1103 | Additional Detailed Patrol | 2022-10-03 | 2022-10-17 | 2022-11-03 | Complete
WILLITS 1103 | Planned Work and Opportunities | 2022-10-03 | 2022-10-17 | 2022-10-17 | Complete
WILLITS 1103 | Proactive Fault Indicator Installation | 2022-10-03 | 2022-10-17 | 2022-07-06 | Complete
WILLITS 1103 | Review CAIDI Performance | 2022-10-03 | 2022-10-17 | 2022-12-14 | Complete
WILLITS 1103 | Settings Review | 2022-10-03 | 2022-10-17 | 2022-10-17 | Complete
WILLITS 1103 | Vegetation Management Cycle Review | 2022-10-03 | 2022-11-11 | 2022-11-11 | Complete
WISE 1102 | Ad Hoc Fault Indicator Installation | 2022-08-15 | 2022-08-29 | 2022-08-31 | Complete
WISE 1102 | Additional Detailed Patrol | 2022-08-15 | 2022-08-29 | 2022-08-31 | Complete
WISE 1102 | Planned Work and Opportunities | 2022-08-15 | 2022-08-29 | 2022-09-07 | Complete
WISE 1102 | Proactive Fault Indicator Installation | 2022-08-15 | 2022-08-29 | 2022-07-04 | Complete
WISE 1102 | Settings Review | 2022-08-15 | 2022-08-29 | 2022-09-12 | Complete
WOODACRE 1102 | Ad Hoc Fault Indicator Installation | 2022-07-25 | 2022-08-08 | 2022-08-30 | Complete
WOODACRE 1102 | Additional Detailed Patrol | 2022-07-25 | 2022-08-08 | 2022-08-30 | Complete
WOODACRE 1102 | Animal Guard | 2022-07-25 | 2022-08-08 | 2022-08-29 | Complete
WOODACRE 1102 | Customer Impact | 2022-07-25 | 2022-08-08 | 2022-08-05 | Complete
WOODACRE 1102 | Patrol Zones | 2022-07-25 | 2022-08-08 | 2022-08-30 | Complete
WOODACRE 1102 | Planned Work and Opportunities | 2022-07-25 | 2022-08-08 | 2022-07-26 | Complete
WOODACRE 1102 | Planned Work and Opportunities | 2022-07-25 | 2022-08-08 | 2022-08-26 | Complete
WOODACRE 1102 | Settings Review | 2022-07-25 | 2022-08-08 | 2022-08-31 | Complete
WOODACRE 1102 | Vegetation Management Cycle Review | 2022-07-25 | 2022-08-08 | 2022-08-26 | Complete

## 2023 MOREs
Circuit | Device | Status
APPLE HILL 1104 | 13512 | Complete - no additional action required
APPLE HILL 2102 | 1532 | Complete - additional action(s) created
APPLE HILL 2102 | 186912 | Complete - additional action(s) created
APPLE HILL 2102 | 51792 | Complete - additional action(s) created
AVENAL 2101 | 9070 | Complete - additional action(s) created
BEN LOMOND 1101 | BL 1101 | Complete - additional action(s) created
BIG BASIN 1101 | Circuit-Level | Complete - additional action(s) created
BIG MEADOWS 2101 | 2230 | Complete - additional action(s) created
BRUNSWICK 1105 | 2100 | Complete - additional action(s) created
BRUNSWICK 1105 | 215628 | Complete - additional action(s) created
BRUNSWICK 1106 | 2104 | Complete - additional action(s) created
BRUNSWICK 1106 | 2392 | Complete - additional action(s) created
BURNS 2101 | 12868 | Complete - additional action(s) created
CALAVERAS CEMENT 1101 | 11236 | Complete - additional action(s) created
CALISTOGA 1101 | 242919 | Complete - additional action(s) created
CAMP EVERS 2103 | 11046 | Complete - additional action(s) created
CAMP EVERS 2106 | 94770 | Complete - additional action(s) created
CASTRO VALLEY 1110 | 560528 | Complete - additional action(s) created
CAYETANO 2109 | Circuit-Level | Complete - additional action(s) created
CHOLAME 2102 | X06 | Complete - additional action(s) created
CLARK ROAD 1102 | 212118 | Complete - no additional action required
CLARK ROAD 1102 | 81296 | Complete - additional action(s) created
CLARKSVILLE 2104 | 13352 | Complete - additional action(s) created
CLAY 1101 | 13442 | Complete - no additional action required
CLAYTON 2215 | Circuit-Level | Complete - additional action(s) created
CLEAR LAKE 1101 | 92870 | Complete - additional action(s) created
COARSEGOLD 2103 | 6110 | Complete - additional action(s) created
COARSEGOLD 2104 | 570682 | Complete - additional action(s) created
COARSEGOLD 2104 | 905960 | Complete - additional action(s) created
CORNING 1101 | 82846 | Complete - additional action(s) created
COTATI 1105 | 328 | Complete - additional action(s) created
CURTIS 1702 | 10940 | Complete - additional action(s) created
CURTIS 1702 | 6008 | Complete - additional action(s) created
CURTIS 1702 | Circuit-Level | Complete - additional action(s) created
CURTIS 1703 | 6064 | Complete - no additional action required
CURTIS 1703 | 84944 | Complete - additional action(s) created
CURTIS 1703 | Circuit-Level | Complete - additional action(s) created
CURTIS 1704 | 8140 | Complete - no additional action required
CURTIS 1705 | 65908 | Complete - no additional action required
DEL MONTE 2104 | 2762 | Complete - no additional action required
DRUM 1101 | CB 1101 | Complete - additional action(s) created
DUNBAR 1103 | 234 | Complete - no additional action required
DUNLAP 1102 | 7290 | Complete - no additional action required
DUNLAP 1102 | 7290 | Complete - additional action(s) created
DUNLAP 1103 | 7080 | Complete - additional action(s) created
DUNLAP 1103 | 7170 | Complete - additional action(s) created
EL DORADO PH 2101 | 6852 | Complete - additional action(s) created
EL DORADO PH 2101 | Circuit-Level | Complete - additional action(s) created
ELK CREEK 1101 | 2002 | Complete - additional action(s) created
FORESTHILL 1101 | 1802 | Complete - no additional action required
FORT ROSS 1121 | 134 | Complete - additional action(s) created
FORT ROSS 1121 | 913812 | Complete - no additional action required
FROGTOWN 1701 | 13412 | Complete - additional action(s) created
FULTON 1107 | 126742 | Complete - no additional action required
GARBERVILLE 1102 | 1510 | Complete - no additional action required
GEYSERVILLE 1101 | 166 | Complete - additional action(s) created
GONZALES 1104 | 36982 | Complete - no additional action required
GRASS VALLEY 1101 | CB 1101 | Complete - no additional action required
GRASS VALLEY 1103 | 2180 | Complete - additional action(s) created
GRASS VALLEY 1103 | CB 1101 | Complete - additional action(s) created
GREEN VALLEY 2101 | 11054 | Complete - additional action(s) created
GREEN VALLEY 2101 | 942143 | Complete - no additional action required
HARTLEY 1101 | 658 | Complete - no additional action required
HIGGINS 1104 | 1006 | Complete - additional action(s) created
HIGGINS 1109 | 594 | Complete - additional action(s) created
HOOPA 1101 | 3174 | Complete - additional action(s) created
HOOPA 1101 | 405280 | Complete - no additional action required
IONE 1101 | 510200 | Complete - additional action(s) created
JAMESON 1105 | 466348 | Complete - additional action(s) created
JESSUP 1101 | 1496 | Complete - additional action(s) created
JOLON 1102 | 7002 | Complete - additional action(s) created
JOLON 1103 | 1103/2 | Complete - additional action(s) created
JOLON 1103 | 549180 | Complete - additional action(s) created
JOLON 1103 | CB | Complete - no additional action required
KESWICK 1101 | 1590 | Complete - additional action(s) created
KONOCTI 1108 | 1278 | Complete - additional action(s) created
LAURELES 1111 | 432 | Complete - additional action(s) created
LINCOLN 1101 | 881364 | Complete - additional action(s) created
LLAGAS 2101 | 783467 | Complete - additional action(s) created
MADISON 2101 | 274974 | Complete - no additional action required
MADISON 2101 | 760730 | Complete - additional action(s) created
MADISON 2101 | 89332 | Complete - additional action(s) created
MADISON 2101 | Circuit-Level | Complete - additional action(s) created
MARIPOSA 2102 | 851902 | Complete - no additional action required
MC ARTHUR 1101 | 648698 | Complete - additional action(s) created
MIRABEL 1101 | 228 | Complete - additional action(s) created
MIWUK 1701 | 953336 | Complete - no additional action required
MIWUK 1702 | 667248 | Complete - additional action(s) created
MOLINO 1102 | 178 | Complete - no additional action required
MOLINO 1102 | Circuit-Level | Complete - additional action(s) created
MONTE RIO 1113 | 3970 | Complete - additional action(s) created
MONTICELLO 1101 | 52910 | Complete - no additional action required
MOUNTAIN QUARRIES 2101 | 51584 | Complete - additional action(s) created
NAPA 1112 | 1302 | Complete - additional action(s) created
NARROWS 2105 | 2748 | Complete - additional action(s) created
NORTH TOWER 2101 | 135318 | Complete - no additional action required
OCEANO 1104 | V38 | Complete - additional action(s) created
OILFIELDS 1103 | 7006 | Complete - additional action(s) created
OILFIELDS 1103 | 87034 | Complete - additional action(s) created
OILFIELDS 1103 | N42 | Complete - additional action(s) created
OLETA 1102 | 186326 | Complete - no additional action required
ORO LOMA 1106 | 9790 | Complete - no additional action required
OROSI 1102 | CB 1102 | Complete - no additional action required
PAUL SWEET 2106 | 974130 | Complete - no additional action required
PENRYN 1103 | 660 | Complete - additional action(s) created
PENRYN 1107 | CB 1107 | Complete - additional action(s) created
PEORIA 1704 | 59596 | Complete - no additional action required
PEORIA 1705 | 67898 | Complete - additional action(s) created
PETALUMA C 1108 | 233646 | Complete - no additional action required
PETALUMA C 1108 | 618 | Complete - additional action(s) created
PETALUMA C 1109 | 48000 | Complete - additional action(s) created
PHILO 1102 | 920 | Complete - additional action(s) created
PINE GROVE 1101 | 3170 | Complete - additional action(s) created
PINE GROVE 1102 | 3168 | Complete - no additional action required
PINE GROVE 1102 | 3172 | Complete - additional action(s) created
PLACERVILLE 2106 | 1104 | Complete - additional action(s) created
PLACERVILLE 2106 | 2224 | Complete - no additional action required
PLACERVILLE 2106 | 7522 | Complete - additional action(s) created
PLACERVILLE 2106 | 9712 | Complete - no additional action required
POSO MOUNTAIN 2101 | 2181 | Complete - additional action(s) created
POSO MOUNTAIN 2101 | 720132 | Complete - additional action(s) created
PURISIMA 1101 | Y44 | Complete - no additional action required
RACETRACK 1703 | 6014 | Complete - additional action(s) created
RACETRACK 1703 | 799924 | Complete - no additional action required
REEDLEY 1104 | 887932 | Complete - no additional action required
RIO DELL 1101 | 8768 | Complete - additional action(s) created
ROB ROY 2104 | 10960 | Complete - additional action(s) created
ROB ROY 2104 | 67520 | Complete - additional action(s) created
ROSSMOOR 1108 | 45268 | Complete - additional action(s) created
SALT SPRINGS 2101 | 1232 | Complete - additional action(s) created
SAN ARDO 1102 | 7030 | Complete - additional action(s) created
SAN BENITO 2104 | 785888 | Complete - no additional action required
SAN JUSTO 1101 | 4002 | Complete - additional action(s) created
SAN LUIS OBISPO 1104 | V46 | Complete - additional action(s) created
SANTA NELLA 1101 | 7200 | Complete - additional action(s) created
SANTA YNEZ 1101 | 277014 | Complete - additional action(s) created
SANTA YNEZ 1104 | Y04 | Complete - additional action(s) created
SARATOGA 1106 | 340986 | Complete - additional action(s) created
SHADY GLEN 1102 | 2232 | Complete - additional action(s) created
SHINGLE SPRINGS 2108 | 294550 | Complete - additional action(s) created
SHINGLE SPRINGS 2108 | Circuit-Level | Complete - no additional action required
SILVERADO 2102 | 285782 | Complete - no additional action required
SILVERADO 2104 | 37632 | Complete - no additional action required
SILVERADO 2104 | 632 | Complete - additional action(s) created
SILVERADO 2104 | 722 | Complete - additional action(s) created
SILVERADO 2105 | 768606 | Complete - no additional action required
SOBRANTE 1101 | 1101/2 | Complete - additional action(s) created
SOLEDAD 2104 | 7008 | Complete - additional action(s) created
SONOMA 1104 | Circuit-Level | Complete - additional action(s) created
STANISLAUS 1701 | 7144 | Complete - additional action(s) created
STANISLAUS 1702 | 1850 | Complete - additional action(s) created
TASSAJARA 2103 | Circuit-Level | Complete - no additional action required
TASSAJARA 2108 | CB | Complete - no additional action required
TEMPLETON 2110 | Circuit-Level | Complete - no additional action required
TEMPLETON 2111 | A66 | Complete - additional action(s) created
TEMPLETON 2113 | A70 | Complete - additional action(s) created
TIDEWATER 2106 | 57926 | Complete - additional action(s) created
TIVY VALLEY 1107 | 822606 | Complete - additional action(s) created
UKIAH 1114 | 408 | Complete - no additional action required
VALLEY SPRINGS 1101 | 11158 | Complete - no additional action required
VOLTA 1101 | 65764 | Complete - additional action(s) created
WILLOW CREEK 1103 | 7514 | Complete - no additional action required
WILLOW CREEK 1103 | CB 1103 | Complete - no additional action required
WYANDOTTE 1102 | Circuit-Level | Complete - no additional action required
ZACA 1101 | CB 1101 | Complete - additional action(s) created
ZACA 1102 | Y02 | Complete - no additional action required
ZACA 1102 | Y48 | Complete - additional action(s) created

## 2023 MORE Action Items
Circuit | Device | Action | Date Action Item Initiated | Target Completion Date of Action Item | Date Action Item Completed | Status | Tracking Platform
APPLE HILL 2102 | 1532 | MORe Investigation Request | 2023-11-07 | 2023-11-14 |  | In Progress | Digital Platform
APPLE HILL 2102 | 1532 | MORe Investigation Request | 2023-11-07 | 2023-11-21 | 2023-11-16 | Complete | Digital Platform
APPLE HILL 2102 | 51792 | Escalation: Settings Review | 2023-08-16 | 2023-08-30 | 2023-09-12 | Complete | Manual Tracker
APPLE HILL 2102 | 51792 | Escalation: Settings Review | 2023-08-22 | 2023-09-05 | 2023-09-12 | Complete | Manual Tracker
APPLE HILL 2102 | 51792 | Escalation: Veg Review | 2023-08-29 | 2023-09-13 | 2023-09-07 | Complete | Manual Tracker
APPLE HILL 2102 | 51792 | MORe Investigation Request | 2023-08-30 | 2023-09-13 | 2023-09-07 | Complete | Digital Platform
APPLE HILL 2102 | 186912 | FI Request/Installations | 2023-08-28 | 2023-09-27 | 2023-09-13 | Complete | Digital Platform
APPLE HILL 2102 | 186912 | MORe Investigation Request | 2023-08-28 | 2023-09-04 | 2023-10-12 | Complete | Digital Platform
APPLE HILL 2102 | 186912 | Escalation: Fault Indicators | 2023-08-28 | 2023-09-11 | 2023-09-11 | Complete | Manual Tracker
APPLE HILL 2102 | 186912 | Escalation: Animal Guard | 2023-08-28 | 2023-09-11 | 2023-10-13 | Complete | Manual Tracker
APPLE HILL 2102 | 186912 | MORe Investigation Request | 2023-09-06 | 2023-09-20 | 2023-09-12 | Complete | Digital Platform
APPLE HILL 2102 | 186912 | Escalation: Settings Review | 2023-09-06 | 2023-09-20 | 2023-09-12 | Complete | Manual Tracker
AVENAL 2101 | 9070 | Planning/Coordination Review | 2023-06-08 | 2023-07-08 |  | Complete | Manual Tracker
AVENAL 2101 | 9070 | Animal Guard | 2023-06-08 | 2023-09-03 |  | Complete | Manual Tracker
AVENAL 2101 | 9070 | EC/ER Tag | 2023-06-15 | 2023-06-29 | 2023-06-15 | Complete | Manual Tracker
BEN LOMOND 1101 | BL 1101 | ORT GDAT Prioritization | 2023-08-07 | 2023-08-21 |  | Past Due | Manual Tracker
BEN LOMOND 1101 | BL 1101 | Vegetation Work Assessment | 2023-08-07 | 2023-08-21 |  | Complete | Manual Tracker
BIG BASIN 1101 | Circuit-Level | Escalation: Settings Review | 2023-08-03 | 2023-08-17 | 2023-08-17 | Complete | Manual Tracker
BIG MEADOWS 2101 | 2230 | Escalation: Settings Review | 2023-09-25 | 2023-10-09 | 2023-09-28 | Complete | Manual Tracker
BIG MEADOWS 2101 | 2230 | Escalation: Cause Code | 2023-09-25 | 2023-10-09 | 2023-09-28 | Complete | Manual Tracker
BIG MEADOWS 2101 | 2230 | Investigation | 2023-09-26 | 2023-10-03 | 2023-09-28 | Complete | Digital Platform
BIG MEADOWS 2101 | 2230 | Protection/Coordination Review | 2023-09-26 | 2023-10-03 | 2023-09-28 | Complete | Digital Platform
BRUNSWICK 1105 | 2100 | ILIS Record Update | 2023-08-23 | 2023-08-30 | 2023-09-13 | Complete | Digital Platform
BRUNSWICK 1105 | 2100 | ILIS Record Update | 2023-08-23 | 2023-08-30 | 2023-09-13 | Complete | Digital Platform
BRUNSWICK 1105 | 2100 | Escalation: Cause Code | 2023-08-24 | 2023-09-07 | 2023-09-12 | Complete | Manual Tracker
BRUNSWICK 1105 | 215628 | MORe Investigation Request | 2023-11-16 | 2023-11-23 | 2023-11-16 | Complete | Digital Platform
BRUNSWICK 1106 | 2104 | Animal Mitigation Review | 2023-10-26 | 2023-11-02 | 2023-11-17 | Complete | Digital Platform
BRUNSWICK 1106 | 2392 | MORe Investigation Request | 2023-10-09 | 2023-10-23 | 2023-10-18 | Complete | Digital Platform
BRUNSWICK 1106 | 2392 | Escalation: Fault Indicators | 2023-10-09 | 2023-10-23 | 2023-10-17 | Complete | Manual Tracker
BURNS 2101 | 12868 | Outage Information Gathering | 2023-07-12 | 2023-07-26 | 2023-07-12 | Complete | Manual Tracker
CALAVERAS CEMENT 1101 | 11236 | ILIS Record Update | 2023-10-12 | 2023-10-19 | 2023-10-18 | Complete | Digital Platform
CALAVERAS CEMENT 1101 | 11236 | FI Request/Installations | 2023-10-12 | 2023-10-26 | 2023-11-01 | Complete | Digital Platform
CALAVERAS CEMENT 1101 | 11236 | Escalation: Cause Code | 2023-10-12 | 2023-10-26 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
CALAVERAS CEMENT 1101 | 11236 | Escalation: Fault Indicators | 2023-10-12 | 2023-10-26 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
CALISTOGA 1101 | 242919 | FI Request/Installations | 2023-10-24 | 2023-11-07 | 2023-10-27 | Complete | Digital Platform
CALISTOGA 1101 | 242919 | Fault Indicator Assessment | 2023-10-24 | 2023-11-07 | 2023-10-27 | Complete | Manual Tracker
CAMP EVERS 2103 | 11046 | ORT Action Item Follow Up | 2023-10-02 | 2023-10-16 |  | In Progress - Tracked in Digital Platform (Duplicate) | Manual Tracker
CAMP EVERS 2103 | 11046 | Cause Investigation | 2023-10-02 | 2023-10-16 | 2023-10-05 | Complete | Manual Tracker
CAMP EVERS 2103 | 11046 | MORe Investigation Request | 2023-10-05 | 2023-10-12 |  | In Progress | Digital Platform
CAMP EVERS 2106 | 94770 | Planning/Coordination Review | 2023-07-31 | 2023-08-14 |  | Complete | Manual Tracker
CASTRO VALLEY 1110 | 560528 | Planning/Coordination Review | 2023-07-05 | 2023-07-28 | 2023-07-25 | Complete | Manual Tracker
CASTRO VALLEY 1110 | 560528 | Additional Detailed Patrol | 2023-07-11 | 2023-07-25 | 2023-07-18 | Complete | Manual Tracker
CAYETANO 2109 | Circuit-Level | Escalation: Settings Review | 2023-08-01 | 2023-08-15 | 2023-08-10 | Complete | Manual Tracker
CHOLAME 2102 | X06 | FI Request/Installations | 2023-10-19 | 2023-10-26 | 2023-10-19 | Complete | Digital Platform
CHOLAME 2102 | X06 | Escalation: Fault Indicators | 2023-10-19 | 2023-11-02 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
CLARK ROAD 1102 | 81296 | Animal Mitigation Review | 2023-10-19 | 2023-10-26 | 2023-11-17 | Complete | Digital Platform
CLARK ROAD 1102 | 81296 | Animal Guard | 2023-10-19 | 2023-11-02 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
CLARK ROAD 1102 | 272950 | Animal Mitigation Review | 2023-10-19 | 2023-10-26 | 2023-11-17 | Complete | Digital Platform
CLARK ROAD 1102 | 514690 | Animal Mitigation Review | 2023-10-19 | 2023-10-26 | 2023-11-17 | Complete | Digital Platform
CLARKSVILLE 2104 | 13352 | ORT Patrol | 2023-08-08 | 2023-08-22 | 2023-08-18 | Complete | Manual Tracker
CLARKSVILLE 2104 | 13352 | Escalation: Settings Review | 2023-08-08 | 2023-08-22 | 2023-09-06 | Complete | Manual Tracker
CLARKSVILLE 2104 | 13352 | Vegetation Work Assessment | 2023-08-08 | 2023-08-22 | 2023-09-01 | Complete | Manual Tracker
CLARKSVILLE 2104 | 13352 | Escalation: Animal Guard | 2023-08-22 | 2023-09-05 | 2023-10-13 | Complete | Manual Tracker
CLARKSVILLE 2104 | 13352 | Escalation: Settings Review | 2023-08-22 | 2023-09-05 | 2023-09-07 | Complete | Manual Tracker
CLARKSVILLE 2104 | 13352 | Escalation: Patrol | 2023-09-05 | 2023-09-19 | 2023-08-18 | Complete | Manual Tracker
CLAYTON 2215 | Circuit-Level | Escalation: CPUC Complaint | 2023-08-02 | 2023-08-16 | 2023-08-24 | Complete | Manual Tracker
CLEAR LAKE 1101 | 92870 | Escalation: Vegetation XOC | 2023-09-29 | 2023-10-13 | 2023-10-30 | Complete | Manual Tracker
CLEAR LAKE 1101 | 92870 | Additional Detailed Patrol | 2023-09-29 | 2023-10-13 | 2023-10-10 | Complete | Manual Tracker
CLEAR LAKE 1101 | 92870 | Vegetation Work | 2023-10-06 | 2023-10-20 | 2023-10-30 | Complete | Digital Platform
CLEAR LAKE 1101 | 92870 | Patrol | 2023-10-06 | 2023-10-20 | 2023-10-09 | Complete | Digital Platform
COARSEGOLD 2103 | 6110 | Planning/Coordination Review | 2023-07-20 | 2023-08-03 |  | Complete | Manual Tracker
COARSEGOLD 2104 | 570682 | Accelerate EPSS Activation | 2023-07-31 | 2023-08-14 |  | Past Due | Manual Tracker
COARSEGOLD 2104 | 570682 | ORT Patrol | 2023-07-31 | 2023-08-14 |  | Past Due | Manual Tracker
COARSEGOLD 2104 | 905960 | Sectionalization Assessment | 2023-08-11 | 2023-08-25 |  | Past Due | Manual Tracker
CORNING 1101 | 82846 | MORe Investigation Request | 2023-08-25 | 2023-09-01 | 2023-09-01 | Complete | Digital Platform
CORNING 1101 | 82846 | Escalation: Investigation | 2023-08-25 | 2023-09-08 | 2023-09-01 | Complete | Manual Tracker
COTATI 1105 | 328 | Escalation: Project | 2023-08-10 | 2023-08-24 | 2023-08-18 | Complete | Manual Tracker
CURTIS 1702 | 6008 | Escalation: ORT Investigation | 2023-08-23 | 2023-09-06 |  | Past Due | Manual Tracker
CURTIS 1702 | 6008 | Escalation: Settings Review | 2023-09-25 | 2023-10-09 |  | Past Due | Manual Tracker
CURTIS 1702 | 6008 | Protection/Coordination Review | 2023-09-26 | 2023-10-03 | 2023-09-27 | Complete | Digital Platform
CURTIS 1702 | 6008 | Protection/Coordination Review | 2023-09-26 | 2023-10-03 | 2023-09-27 | Complete | Digital Platform
CURTIS 1702 | 6008 | Escalation: Settings Review | 2023-09-26 | 2023-10-10 |  | Past Due | Manual Tracker
CURTIS 1702 | 6008 | Escalation: Settings Review | 2023-09-26 | 2023-10-10 |  | Past Due | Manual Tracker
CURTIS 1702 | 10940 | ILIS Record Update | 2023-10-16 | 2023-10-30 | 2023-10-16 | Complete | Digital Platform
CURTIS 1702 | 10940 | FI Request/Installations | 2023-10-16 | 2023-10-23 | 2023-10-18 | Complete | Digital Platform
CURTIS 1702 | 10940 | EC/ER Tag | 2023-10-16 | 2023-10-30 | 2023-10-17 | Complete | Digital Platform
CURTIS 1702 | 10940 | Escalation: Bird Tag | 2023-10-16 | 2023-10-30 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
CURTIS 1702 | 10940 | Escalation: Fault Indicators | 2023-10-16 | 2023-10-30 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
CURTIS 1702 | 10940 | Escalation: Cause Code | 2023-10-16 | 2023-10-30 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
CURTIS 1702 | Circuit-Level | MORe Investigation Request | 2023-09-06 | 2023-09-20 | 2023-09-06 | Complete | Digital Platform
CURTIS 1702 | Circuit-Level | MORe Investigation Request | 2023-09-06 | 2023-09-20 | 2023-09-06 | Complete | Digital Platform
CURTIS 1702 | Circuit-Level | MORe Investigation Request | 2023-09-06 | 2023-09-20 | 2023-09-06 | Complete | Digital Platform
CURTIS 1702 | Circuit-Level | Escalation: Animal Guard | 2023-09-06 | 2023-09-20 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
CURTIS 1702 | Circuit-Level | Escalation: Settings Review | 2023-09-06 | 2023-09-20 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
CURTIS 1702 | Circuit-Level | Escalation: Project | 2023-09-06 | 2023-09-20 |  | Past Due | Manual Tracker
CURTIS 1702 | Circuit-Level | Escalation: Veg Review | 2023-09-06 | 2023-09-20 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
CURTIS 1702 | Circuit-Level | Protection/Coordination Review | 2023-09-26 | 2023-10-03 | 2023-10-23 | Complete | Digital Platform
CURTIS 1703 | 84944 | MORe Investigation Request | 2023-08-16 | 2023-08-23 | 2023-08-21 | Complete | Digital Platform
CURTIS 1703 | 84944 | MORe Investigation Request | 2023-08-16 | 2023-08-23 | 2023-08-18 | Complete | Digital Platform
CURTIS 1703 | 84944 | Escalation: Investigation | 2023-08-16 | 2023-08-30 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
CURTIS 1703 | 84944 | Escalation: Investigation | 2023-08-16 | 2023-08-30 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
CURTIS 1703 | 84944 | Escalation: Fault Indicators | 2023-08-16 | 2023-08-30 |  | Past Due | Manual Tracker
CURTIS 1703 | Circuit-Level | ORT Action Item Follow Up | 2023-07-27 | 2023-08-10 |  | Complete | Manual Tracker
DRUM 1101 | CB 1101 | MORe Investigation Request | 2023-10-04 | 2023-10-18 | 2023-10-06 | Complete | Digital Platform
DRUM 1101 | CB 1101 | Escalation: Settings Review | 2023-10-04 | 2023-10-18 | 2023-10-05 | Complete | Manual Tracker
DUNLAP 1102 | 7290 | Request Accelerated Project Timeline | 2023-07-17 | 2023-07-31 | 2023-07-27 | Complete | Manual Tracker
DUNLAP 1102 | 7290 | Request Accelerated Project Timeline | 2023-07-24 | 2023-09-08 |  | Past Due | Manual Tracker
DUNLAP 1102 | 7290 | Outage Information Gathering | 2023-10-02 | 2023-10-16 |  | Past Due | Manual Tracker
DUNLAP 1102 | 7290 | Escalation: Project | 2023-10-02 | 2023-10-16 |  | Past Due | Manual Tracker
DUNLAP 1102 | 7290 | ORT Action Item Follow Up | 2023-10-02 | 2023-10-16 |  | Past Due | Manual Tracker
DUNLAP 1102 | 7290 | ORT Action Item Follow Up | 2023-10-02 | 2023-10-16 |  | Past Due | Manual Tracker
DUNLAP 1102 | 7290 | MORe Investigation Request | 2023-10-17 | 2023-10-24 | 2023-10-17 | Complete | Digital Platform
DUNLAP 1102 | 7290 | MORe Investigation Request | 2023-10-17 | 2023-10-31 | 2023-11-03 | Complete | Digital Platform
DUNLAP 1102 | 7290 | FI Request/Installations | 2023-10-17 | 2023-10-31 | 2023-10-17 | Complete | Digital Platform
DUNLAP 1102 | 7290 | Planning/Coordination Review | 2023-10-17 | 2023-10-31 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
DUNLAP 1102 | 7290 | Planning/Coordination Review | 2023-10-17 | 2023-10-31 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
DUNLAP 1102 | 7290 | Fault Indicator Assessment | 2023-10-17 | 2023-10-31 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
DUNLAP 1102 | 7290 | MORe Investigation Request | 2023-11-03 | 2023-11-10 | 2023-11-10 | Complete | Digital Platform
DUNLAP 1102 | 7290 | MORe Investigation Request | 2023-11-03 | 2023-12-03 | 2023-11-10 | Complete | Digital Platform
DUNLAP 1102 | 7290 | MORe Investigation Request | 2023-11-07 | 2023-11-14 | 2023-11-10 | Complete | Digital Platform
DUNLAP 1103 | 7080 | ORT GDAT Prioritization | 2023-05-30 | 2023-06-13 | 2023-06-07 | Complete | Manual Tracker
DUNLAP 1103 | 7080 | Planning/Coordination Review | 2023-06-07 | 2023-07-14 | 2023-07-06 | Complete | Manual Tracker
DUNLAP 1103 | 7170 | Cause Investigation | 2023-05-24 | 2023-05-26 | 2023-05-31 | Complete | Manual Tracker
DUNLAP 1103 | 7170 | ORT GDAT Prioritization | 2023-05-30 | 2023-06-13 | 2023-06-07 | Complete | Manual Tracker
DUNLAP 1103 | 7170 | Escalation: Settings Review | 2023-08-03 | 2023-08-17 |  | Complete | Manual Tracker
EL DORADO PH 2101 | 6852 | MORe Investigation Request | 2023-09-08 | 2023-09-15 |  | New | Digital Platform
EL DORADO PH 2101 | 6852 | Escalation: Confirm Settings Adjustment | 2023-09-08 | 2023-09-22 |  | Complete | Manual Tracker
EL DORADO PH 2101 | Circuit-Level | Planning/Coordination Review | 2023-07-28 | 2023-08-11 |  | Complete | Manual Tracker
ELK CREEK 1101 | 2002 | Animal Mitigation Review | 2023-11-14 | 2023-11-21 | 2023-11-15 | Complete | Digital Platform
FORT ROSS 1121 | 134 | Escalation: Vegetation XOC | 2023-08-16 | 2023-08-30 | 2023-09-19 | Complete | Manual Tracker
FORT ROSS 1121 | 134 | Escalation: Settings Review | 2023-08-16 | 2023-08-30 | 2023-08-21 | Complete | Manual Tracker
FROGTOWN 1701 | 13412 | Escalation: Project | 2023-09-18 | 2023-10-02 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
FROGTOWN 1701 | 13412 | Project | 2023-09-19 | 2023-09-26 | 2023-09-22 | Complete | Digital Platform
FROGTOWN 1701 | 13412 | MORe Investigation Request | 2023-10-09 | 2023-10-23 | 2023-11-14 | Complete | Digital Platform
FROGTOWN 1701 | 13412 | Escalation: Project | 2023-10-09 | 2023-10-23 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
FROGTOWN 1701 | 13412 | MORe Investigation Request | 2023-10-26 | 2023-11-02 | 2023-11-06 | Complete | Digital Platform
FROGTOWN 1701 | 13412 | MORe Investigation Request | 2023-11-13 | 2023-12-13 | 2023-11-14 | Complete | Digital Platform
GEYSERVILLE 1101 | 166 | Escalation: Investigation | 2023-09-20 | 2023-10-04 | 2023-11-15 | Complete | Manual Tracker
GEYSERVILLE 1101 | 166 | Investigation | 2023-09-21 | 2023-09-28 | 2023-11-15 | Complete | Digital Platform
GRASS VALLEY 1103 | 2180 | ORT Action Item Follow Up | 2023-07-21 | 2023-08-04 | 2023-08-14 | Complete | Manual Tracker
GRASS VALLEY 1103 | CB 1101 | Escalation: Investigation | 2023-08-16 | 2023-08-18 | 2023-08-14 | Complete | Manual Tracker
GREEN VALLEY 2101 | 11054 | MORe Investigation Request | 2023-08-23 | 2023-08-30 | 2023-10-18 | Complete | Digital Platform
GREEN VALLEY 2101 | 11054 | FI Request/Installations | 2023-08-23 | 2023-09-22 | 2023-10-18 | Complete | Digital Platform
GREEN VALLEY 2101 | 11054 | Escalation: Bird Tag | 2023-08-24 | 2023-09-07 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
GREEN VALLEY 2101 | 11054 | Escalation: Fault Indicators | 2023-08-24 | 2023-09-07 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
HIGGINS 1104 | 1006 | Escalation: Animal Guard | 2023-08-09 | 2023-08-23 | 2023-10-13 | Complete | Manual Tracker
HIGGINS 1104 | 1006 | Escalation: Vegetation XOC | 2023-08-09 | 2023-08-23 | 2023-09-07 | Complete | Manual Tracker
HIGGINS 1104 | 1006 | MORe Investigation Request | 2023-09-06 | 2023-09-13 | 2023-09-07 | Complete | Digital Platform
HIGGINS 1104 | 1006 | MORe Investigation Request | 2023-09-06 | 2023-09-13 | 2023-10-12 | Complete | Digital Platform
HIGGINS 1104 | 1006 | Escalation: Animal Guard | 2023-09-06 | 2023-09-20 | 2023-10-13 | Complete | Manual Tracker
HIGGINS 1104 | 1006 | Escalation: Veg Review | 2023-09-06 | 2023-09-20 | 2023-09-07 | Complete | Manual Tracker
HIGGINS 1109 | 594 | ILIS Record Update | 2023-09-15 | 2023-09-22 | 2023-09-18 | Complete | Digital Platform
HIGGINS 1109 | 594 | FI Request/Installations | 2023-09-15 | 2023-09-22 | 2023-09-21 | Complete | Digital Platform
HIGGINS 1109 | 594 | Project | 2023-09-15 | 2023-09-22 | 2023-11-17 | Complete | Digital Platform
HIGGINS 1109 | 594 | Patrol | 2023-09-15 | 2023-09-22 | 2023-10-30 | Complete | Digital Platform
HIGGINS 1109 | 594 | Escalation: Patrol | 2023-09-15 | 2023-09-29 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
HIGGINS 1109 | 594 | Escalation: Fault Indicators | 2023-09-15 | 2023-09-29 | 2023-09-21 | Complete | Manual Tracker
HIGGINS 1109 | 594 | Escalation: Cause Code | 2023-09-15 | 2023-09-29 | 2023-09-18 | Complete | Manual Tracker
HIGGINS 1109 | 594 | Escalation: Project | 2023-09-15 | 2023-09-29 | 2023-11-17 | Complete | Manual Tracker
HOOPA 1101 | 3174 | Escalation: Vegetation XOC | 2023-08-22 | 2023-09-05 | 2023-09-01 | Complete | Manual Tracker
IONE 1101 | 510200 | Escalation: ORT Investigation | 2023-09-01 | 2023-09-15 |  | Past Due | Manual Tracker
JAMESON 1105 | 466348 | Animal Mitigation Review | 2023-10-24 | 2023-10-31 |  | In Progress | Digital Platform
JAMESON 1105 | 466348 | FI Request/Installations | 2023-10-24 | 2023-11-07 | 2023-11-15 | Complete | Digital Platform
JAMESON 1105 | 466348 | Fault Indicator Assessment | 2023-10-24 | 2023-11-07 | 2023-11-15 | Complete | Manual Tracker
JAMESON 1105 | 466348 | Animal Guard | 2023-10-24 | 2023-11-07 |  | In Progress | Manual Tracker
JESSUP 1101 | 1496 | Cause Investigation | 2023-07-10 | 2023-07-24 |  | Past Due | Manual Tracker
JOLON 1102 | 7002 | Escalation: Fault Indicators | 2023-10-30 | 2023-11-13 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
JOLON 1102 | 7002 | FI Request/Installations | 2023-10-31 | 2023-11-30 | 2023-11-07 | Complete | Digital Platform
JOLON 1103 | 549180 | MORe Investigation Request | 2023-09-08 | 2023-09-22 | 2023-09-13 | Complete | Digital Platform
JOLON 1103 | 549180 | FI Request/Installations | 2023-09-08 | 2023-09-22 | 2023-09-13 | Complete | Digital Platform
JOLON 1103 | 549180 | Escalation: Fault Indicators | 2023-09-08 | 2023-09-22 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
JOLON 1103 | 549180 | FI Request/Installations | 2023-09-15 | 2023-09-22 | 2023-09-14 | Complete | Digital Platform
JOLON 1103 | 549180 | Escalation: Fault Indicators | 2023-09-15 | 2023-09-29 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
JOLON 1103 | 549180 | Escalation: Settings Review | 2023-09-25 | 2023-10-09 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
JOLON 1103 | 549180 | Protection/Coordination Review | 2023-09-26 | 2023-10-03 | 2023-09-26 | Complete | Digital Platform
JOLON 1103 | 1103/2 | Escalation: Investigation | 2023-08-25 | 2023-09-08 |  | Past Due | Manual Tracker
JOLON 1103 | CB 1103 | MORe Investigation Request | 2023-08-25 | 2023-09-01 | 2023-09-01 | Complete | Digital Platform
KESWICK 1101 | 1590 | Escalation: Settings Review | 2023-08-10 | 2023-08-24 | 2023-08-15 | Complete | Manual Tracker
KESWICK 1101 | 1590 | Escalation: Settings Review | 2023-08-15 | 2023-08-29 | 2023-08-14 | Complete | Manual Tracker
KESWICK 1101 | 1590 | Investigation | 2023-09-14 | 2023-09-21 | 2023-09-21 | Complete | Digital Platform
KESWICK 1101 | 1590 | Escalation: Investigation | 2023-09-14 | 2023-09-28 |  | Complete | Manual Tracker
KESWICK 1101 | 1590 | Escalation: Investigation | 2023-09-19 | 2023-10-03 |  | Past Due | Manual Tracker
KESWICK 1101 | 1590 | Escalation: Settings Review | 2023-09-20 | 2023-10-04 | 2023-09-28 | Complete | Manual Tracker
KESWICK 1101 | 1590 | Protection/Coordination Review | 2023-09-21 | 2023-09-28 | 2023-09-28 | Complete | Digital Platform
KESWICK 1101 | 1590 | Fault Indicator Assessment | 2023-10-02 | 2023-10-16 | 2023-10-03 | Complete | Manual Tracker
KESWICK 1101 | 1590 | Escalation: Alarm Mode | 2023-10-02 | 2023-10-16 | 2023-11-16 | Complete | Manual Tracker
KESWICK 1101 | 1590 | Escalation: Patrol | 2023-10-02 | 2023-10-16 | 2023-10-10 | Complete | Manual Tracker
KESWICK 1101 | 1590 | MORe Investigation Request | 2023-10-05 | 2023-10-12 | 2023-10-09 | Complete | Digital Platform
KESWICK 1101 | 1590 | MORe Investigation Request | 2023-10-05 | 2023-10-12 | 2023-10-09 | Complete | Digital Platform
KESWICK 1101 | 1590 | MORe Investigation Request | 2023-10-06 | 2023-10-20 | 2023-11-15 | Complete | Digital Platform
KESWICK 1101 | 1590 | Escalation: Alarm Mode | 2023-10-06 | 2023-10-20 | 2023-11-16 | Complete | Manual Tracker
KONOCTI 1108 | 1278 | Planning/Coordination Review | 2023-07-03 | 2023-07-17 | 2023-07-13 | Complete | Manual Tracker
KONOCTI 1108 | 1278 | Request Accelerated Project Timeline | 2023-07-03 | 2023-07-17 | 2023-07-13 | Complete | Manual Tracker
LAURELES 1111 | 432 | Protection/Coordination Review | 2023-09-22 | 2023-09-29 | 2023-09-22 | Complete | Digital Platform
LAURELES 1111 | 432 | Patrol | 2023-09-22 | 2023-09-29 | 2023-09-22 | Complete | Digital Platform
LAURELES 1111 | 432 | Escalation: Patrol | 2023-09-22 | 2023-10-06 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
LAURELES 1111 | 432 | Escalation: Settings Review | 2023-09-22 | 2023-10-06 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
LINCOLN 1101 | 881364 | Escalation: Settings Review | 2023-09-20 | 2023-10-04 | 2023-11-15 | Complete | Manual Tracker
LINCOLN 1101 | 881364 | Escalation: Patrol | 2023-09-20 | 2023-10-04 | 2023-11-15 | Complete | Manual Tracker
LINCOLN 1101 | 881364 | Patrol | 2023-09-21 | 2023-09-28 | 2023-11-15 | Complete | Digital Platform
LINCOLN 1101 | 881364 | Protection/Coordination Review | 2023-09-21 | 2023-09-28 | 2023-11-15 | Complete | Digital Platform
LLAGAS 2101 | 783467 | MORe Investigation Request | 2023-10-13 | 2023-10-20 | 2023-10-17 | Complete | Digital Platform
MADISON 2101 | 1606 | Planning/Coordination Review | 2023-07-28 | 2023-08-11 | 2023-08-18 | Complete | Manual Tracker
MADISON 2101 | 89332 | Planning/Coordination Review | 2023-06-30 | 2023-07-14 | 2023-07-13 | Complete | Manual Tracker
MADISON 2101 | 89332 | Review CAIDI | 2023-06-30 | 2023-07-14 | 2023-07-13 | Complete | Manual Tracker
MADISON 2101 | 89332 | Animal Guard | 2023-06-30 | 2023-07-14 | 2023-07-13 | Complete | Manual Tracker
MADISON 2101 | 89332 | Planning/Coordination Review | 2023-07-31 | 2023-08-14 | 2023-08-18 | Complete | Manual Tracker
MADISON 2101 | 89332 | ORT GDAT Prioritization | 2023-08-14 | 2023-08-28 |  | Complete | Manual Tracker
MADISON 2101 | 760730 | MORe Investigation Request | 2023-09-08 | 2023-09-22 | 2023-09-25 | Complete | Digital Platform
MADISON 2101 | 760730 | MORe Investigation Request | 2023-09-08 | 2023-09-22 | 2023-09-28 | Complete | Digital Platform
MADISON 2101 | 760730 | Escalation: Investigation | 2023-09-08 | 2023-09-22 | 2023-09-25 | Complete | Manual Tracker
MADISON 2101 | 760730 | Escalation: Animal Guard | 2023-09-08 | 2023-09-22 | 2023-09-25 | Complete | Manual Tracker
MADISON 2101 | Circuit-Level | ORT Action Item Follow Up | 2023-07-28 | 2023-08-11 |  | Complete | Manual Tracker
MC ARTHUR 1101 | 648698 | Escalation: Animal Guard | 2023-09-05 | 2023-09-19 | 2023-10-13 | Complete | Manual Tracker
MC ARTHUR 1101 | 648698 | MORe Investigation Request | 2023-09-06 | 2023-09-19 | 2023-10-12 | Complete | Digital Platform
MIRABEL 1101 | 228 | MORe Investigation Request | 2023-10-05 | 2023-10-12 | 2023-10-12 | Complete | Digital Platform
MIRABEL 1101 | 228 | Escalation: Fault Indicators | 2023-10-05 | 2023-10-19 | 2023-10-13 | Complete | Manual Tracker
MIWUK 1702 | 667248 | ILIS Record Update | 2023-10-16 | 2023-10-30 | 2023-10-16 | Complete | Digital Platform
MIWUK 1702 | 667248 | Escalation: Cause Code | 2023-10-16 | 2023-10-30 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
MOLINO 1102 | Circuit-Level | Escalation: Settings Review | 2023-08-01 | 2023-08-15 | 2023-08-01 | Complete | Manual Tracker
MOLINO 1102 | Circuit-Level | Escalation: Alarm Mode | 2023-08-01 | 2023-08-15 | 2023-08-09 | Complete | Manual Tracker
MOLINO 1102 | Circuit-Level | Escalation: Veg Review | 2023-08-01 | 2023-08-15 | 2023-08-01 | Complete | Manual Tracker
MONTE RIO 1113 | 3970 | Planning/Coordination Review | 2023-07-18 | 2023-07-25 | 2023-07-19 | Complete | Manual Tracker
MONTE RIO 1113 | 3970 | Cause Investigation | 2023-07-18 | 2023-08-01 | 2023-07-19 | Complete | Manual Tracker
MONTE RIO 1113 | 3970 | Sectionalization Assessment | 2023-07-18 | 2023-08-01 | 2023-07-19 | Complete | Manual Tracker
MONTE RIO 1113 | 3970 | Fault Indicator Assessment | 2023-07-18 | 2023-08-01 | 2023-07-19 | Complete | Manual Tracker
MOUNTAIN QUARRIES 2101 | 51584 | Escalation: Animal Guard | 2023-08-15 | 2023-08-17 | 2023-09-22 | Complete | Manual Tracker
MOUNTAIN QUARRIES 2101 | 51584 | Escalation: Animal Guard | 2023-09-19 | 2023-10-03 | 2023-09-22 | Complete | Manual Tracker
MOUNTAIN QUARRIES 2101 | 51584 | EC/ER Tag | 2023-09-22 | 2023-09-29 | 2023-09-28 | Complete | Digital Platform
MOUNTAIN QUARRIES 2101 | 51584 | Escalation: Animal Guard | 2023-09-22 | 2023-10-06 | 2023-09-22 | Complete | Manual Tracker
NAPA 1112 | 1302 | MORe Investigation Request | 2023-08-25 | 2023-09-01 | 2023-09-05 | Complete | Digital Platform
NAPA 1112 | 1302 | Escalation: Investigation | 2023-08-25 | 2023-09-08 | 2023-08-28 | Complete | Manual Tracker
NAPA 1112 | 1302 | EC/ER Tag | 2023-08-28 | 2023-09-04 | 2023-08-28 | Complete | Digital Platform
NARROWS 2105 | 2748 | MORe Investigation Request | 2023-11-07 | 2023-11-14 | 2023-11-16 | Complete | Digital Platform
OCEANO 1104 | V38 | Investigation | 2023-09-26 | 2023-10-03 | 2023-10-18 | Complete | Digital Platform
OCEANO 1104 | V38 | Escalation: Investigation | 2023-09-26 | 2023-10-10 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
OILFIELDS 1103 | 7006 | MORe Investigation Request | 2023-08-31 | 2023-09-30 | 2023-09-07 | Complete | Digital Platform
OILFIELDS 1103 | 7006 | MORe Investigation Request | 2023-09-07 | 2023-09-21 | 2023-09-14 | Complete | Digital Platform
OILFIELDS 1103 | 7006 | Escalation: Settings Review | 2023-09-07 | 2023-09-21 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
OILFIELDS 1103 | 7006 | Escalation: Animal Guard | 2023-09-07 | 2023-09-21 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
OILFIELDS 1103 | 87034 | Cause Investigation | 2023-08-11 | 2023-08-25 |  | Past Due | Manual Tracker
OILFIELDS 1103 | 87034 | Escalation: Patrol | 2023-08-11 | 2023-08-25 |  | Past Due | Manual Tracker
OILFIELDS 1103 | N42 | Planning/Coordination Review | 2023-07-12 | 2023-07-26 | 2023-07-14 | Complete | Manual Tracker
OILFIELDS 1103 | N42 | Additional Detailed Patrol | 2023-07-12 | 2023-07-26 | 2023-07-14 | Complete | Manual Tracker
PENRYN 1103 | 660 | Escalation: Animal Guard | 2023-08-18 | 2023-08-20 |  | Past Due | Manual Tracker
PENRYN 1107 | CB 1107 | Escalation: XOC | 2023-08-22 | 2023-09-05 | 2023-08-30 | Complete | Manual Tracker
PENRYN 1107 | CB 1107 | Vegetation Work | 2023-08-23 | 2023-08-30 | 2023-08-30 | Complete | Digital Platform
PEORIA 1705 | 67898 | ILIS Record Update | 2023-10-24 | 2023-10-31 | 2023-11-01 | Complete | Digital Platform
PEORIA 1705 | 67898 | Escalation: Cause Code | 2023-10-24 | 2023-11-07 |  | In Progress | Manual Tracker
PETALUMA C 1108 | 618 | Escalation: Alarm Mode | 2023-09-29 | 2023-10-13 | 2023-09-29 | Complete | Manual Tracker
PETALUMA C 1108 | 618 | Escalation: DCD Settings | 2023-09-29 | 2023-10-13 |  | Past Due | Manual Tracker
PETALUMA C 1108 | 618 | Escalation: Abnormal Configuration | 2023-09-29 | 2023-10-13 |  | Past Due | Manual Tracker
PETALUMA C 1108 | 618 | Cause Investigation | 2023-09-29 | 2023-10-13 |  | Past Due | Manual Tracker
PETALUMA C 1108 | 618 | Outage Information Gathering | 2023-10-02 | 2023-10-16 | 2023-10-05 | Complete | Manual Tracker
PETALUMA C 1108 | 618 | MORe Investigation Request | 2023-10-05 | 2023-10-12 | 2023-10-19 | Complete | Digital Platform
PETALUMA C 1108 | 618 | FI Request/Installations | 2023-10-06 | 2023-10-20 | 2023-10-12 | Cancelled | Digital Platform
PETALUMA C 1108 | 636 | Escalation: Patrol | 2023-10-02 | 2023-10-16 |  | Past Due | Manual Tracker
PETALUMA C 1109 | 48000 | MORe Investigation Request | 2023-08-28 | 2023-09-04 | 2023-11-15 | Complete | Digital Platform
PETALUMA C 1109 | 48000 | FI Request/Installations | 2023-08-28 | 2023-09-04 | 2023-09-05 | Complete | Digital Platform
PETALUMA C 1109 | 48000 | Escalation: Animal Guard | 2023-08-28 | 2023-09-11 | 2023-11-15 | Complete | Manual Tracker
PETALUMA C 1109 | 48000 | Escalation: Fault Indicators | 2023-08-28 | 2023-09-11 | 2023-08-29 | Complete | Manual Tracker
PETALUMA C 1109 | 48000 | Escalation: Abnormal Configuration | 2023-08-28 | 2023-09-11 | 2023-09-06 | Complete | Manual Tracker
PHILO 1102 | 920 | Planning/Coordination Review | 2023-07-19 | 2023-08-02 | 2023-07-19 | Complete | Manual Tracker
PHILO 1102 | 920 | Planning/Coordination Review | 2023-07-26 | 2023-08-09 | 2023-07-26 | Complete | Manual Tracker
PINE GROVE 1101 | 3170 | Cause Investigation | 2023-08-21 | 2023-09-04 |  | Past Due | Manual Tracker
PINE GROVE 1101 | 3170 | MORe Investigation Request | 2023-08-30 | 2023-09-06 | 2023-08-31 | Complete | Digital Platform
PINE GROVE 1101 | 3170 | Animal Mitigation Review | 2023-08-30 | 2023-09-13 | 2023-08-31 | Complete | Digital Platform
PINE GROVE 1101 | 3170 | Escalation: Settings Review | 2023-08-30 | 2023-09-14 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
PINE GROVE 1101 | 3170 | Escalation: Animal Guard | 2023-08-30 | 2023-09-13 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
PINE GROVE 1102 | 3172 | Planning/Coordination Review | 2023-05-01 | 2023-05-31 | 2023-05-03 | Complete | Manual Tracker
PLACERVILLE 2106 | 1104 | MORe Investigation Request | 2023-08-25 | 2023-09-01 | 2023-09-13 | Complete | Digital Platform
PLACERVILLE 2106 | 1104 | Escalation: Investigation | 2023-08-25 | 2023-09-08 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
PLACERVILLE 2106 | 7522 | MORe Investigation Request | 2023-08-28 | 2023-09-04 | 2023-09-01 | Complete | Digital Platform
PLACERVILLE 2106 | 7522 | Escalation: Animal Guard | 2023-08-28 | 2023-09-11 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
POSO MOUNTAIN 2101 | 2181 | Animal Guard | 2023-06-05 | 2023-06-19 | 2023-06-09 | Complete | Manual Tracker
POSO MOUNTAIN 2101 | 2181 | ORT GDAT Prioritization | 2023-06-08 | 2023-06-22 | 2023-06-09 | Complete | Manual Tracker
POSO MOUNTAIN 2101 | 2181 | Request Accelerated Project Timeline | 2023-06-09 | 2023-07-07 | 2023-07-14 | Complete | Manual Tracker
POSO MOUNTAIN 2101 | 2181 | Project(s) | 2023-07-19 | 2023-08-18 |  | Complete | Manual Tracker
POSO MOUNTAIN 2101 | 2181 | Animal Guard | 2023-07-19 | 2023-09-15 |  | Past Due | Manual Tracker
POSO MOUNTAIN 2101 | 2181 | Proposed Project | 2023-08-14 | 2023-08-21 | 2023-09-13 | Complete | Digital Platform
POSO MOUNTAIN 2101 | 720132 | Outage Information Gathering | 2023-06-28 | 2023-07-12 | 2023-07-19 | Complete | Manual Tracker
POSO MOUNTAIN 2101 | 720132 | Planning/Coordination Review | 2023-06-28 | 2023-07-12 | 2023-07-14 | Complete | Manual Tracker
POSO MOUNTAIN 2101 | 720132 | Animal Guard | 2023-07-03 | 2023-07-17 | 2023-07-19 | Complete | Manual Tracker
POSO MOUNTAIN 2101 | 720132 | Escalation: DCD Settings | 2023-08-24 | 2023-09-07 |  | Past Due | Manual Tracker
POSO MOUNTAIN 2101 | 720132 | Outage Information Gathering | 2023-10-02 | 2023-10-16 |  | Past Due | Manual Tracker
POSO MOUNTAIN 2101 | 720132 | Planning/Coordination Review | 2023-10-02 | 2023-10-16 |  | Past Due | Manual Tracker
POSO MOUNTAIN 2101 | 720132 | Planning/Coordination Review | 2023-10-02 | 2023-10-16 |  | Past Due | Manual Tracker
POSO MOUNTAIN 2101 | 720132 | ORT Action Item Follow Up | 2023-10-02 | 2023-10-16 |  | Past Due | Manual Tracker
POSO MOUNTAIN 2101 | 720132 | ORT Action Item Follow Up | 2023-10-02 | 2023-10-16 |  | Past Due | Manual Tracker
POSO MOUNTAIN 2101 | 720132 | ORT Action Item Follow Up | 2023-10-02 | 2023-10-16 |  | Past Due | Manual Tracker
POSO MOUNTAIN 2101 | 720132 | ORT Action Item Follow Up | 2023-10-02 | 2023-10-16 |  | Past Due | Manual Tracker
RACETRACK 1703 | 6014 | Planning/Coordination Review | 2023-06-20 | 2023-07-04 | 2023-06-29 | Complete | Manual Tracker
RACETRACK 1703 | 6014 | New Tag Creation | 2023-06-20 | 2023-07-14 | 2023-06-28 | Complete | Manual Tracker
RACETRACK 1703 | 6014 | Escalation: Repair | 2023-08-01 | 2023-08-15 | 2023-08-15 | Complete | Manual Tracker
RACETRACK 1703 | 6014 | Escalation: Alarm Mode | 2023-08-01 | 2023-08-15 | 2023-08-15 | Complete | Manual Tracker
RACETRACK 1703 | 6014 | Escalation: Settings Review | 2023-08-01 | 2023-08-15 | 2023-08-15 | Complete | Manual Tracker
RACETRACK 1703 | 6014 | Cause Investigation | 2023-08-09 | 2023-08-31 |  | Past Due | Manual Tracker
RACETRACK 1703 | 6014 | Escalation: Patrol | 2023-08-15 | 2023-08-29 |  | Past Due | Manual Tracker
RACETRACK 1703 | 6014 | MORe Investigation Request | 2023-10-10 | 2023-10-24 | 2023-10-13 | Complete | Digital Platform
RIO DELL 1101 | 8768 | Escalation: Veg Review | 2023-09-01 | 2023-09-15 | 2023-09-08 | Complete | Manual Tracker
RIO DELL 1101 | 8768 | Escalation: Settings Review | 2023-09-05 | 2023-09-19 | 2023-09-11 | Complete | Manual Tracker
RIO DELL 1101 | 8768 | MORe Investigation Request | 2023-09-06 | 2023-09-13 | 2023-09-22 | Complete | Digital Platform
RIO DELL 1101 | 8768 | MORe Investigation Request | 2023-09-06 | 2023-09-19 | 2023-09-13 | Complete | Digital Platform
ROB ROY 2104 | 10960 | FI Request/Installations | 2023-10-16 | 2023-10-30 | 2023-10-16 | Complete | Digital Platform
ROB ROY 2104 | 10960 | ILIS Record Update | 2023-10-16 | 2023-10-30 | 2023-10-16 | Complete | Digital Platform
ROB ROY 2104 | 10960 | MORe Investigation Request | 2023-10-16 | 2023-10-23 | 2023-10-16 | Complete | Digital Platform
ROB ROY 2104 | 10960 | Escalation: Cause Code | 2023-10-16 | 2023-10-30 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
ROB ROY 2104 | 10960 | Escalation: Settings Review | 2023-10-16 | 2023-10-30 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
ROB ROY 2104 | 10960 | Escalation: Fault Indicators | 2023-10-16 | 2023-10-30 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
ROB ROY 2104 | 67520 | Investigation | 2023-09-15 | 2023-09-22 | 2023-09-19 | Complete | Digital Platform
ROB ROY 2104 | 67520 | Escalation: Investigation | 2023-09-15 | 2023-09-29 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
ROSSMOOR 1108 | 45268 | Planning/Coordination Review | 2023-07-21 | 2023-08-04 | 2023-07-26 | Complete | Manual Tracker
ROSSMOOR 1108 | 45268 | Sectionalization Assessment | 2023-07-21 | 2023-08-04 | 2023-07-28 | Complete | Manual Tracker
ROSSMOOR 1108 | 45268 | Request Accelerated Project Timeline | 2023-07-24 | 2023-08-07 | 2023-07-28 | Complete | Manual Tracker
ROSSMOOR 1108 | 45268 | ORT Patrol | 2023-08-04 | 2023-08-18 | 2023-08-09 | Complete | Manual Tracker
SALT SPRINGS 2101 | 1232 | Escalation: Patrol | 2023-08-14 | 2023-08-28 |  | Past Due | Manual Tracker
SAN ARDO 1102 | 7030 | EC/ER Tag | 2023-09-13 | 2023-09-20 | 2023-09-13 | Complete | Digital Platform
SAN ARDO 1102 | 7030 | Project | 2023-09-13 | 2023-09-20 | 2023-09-14 | Complete | Digital Platform
SAN ARDO 1102 | 7030 | Escalation: Animal Guard | 2023-09-13 | 2023-09-27 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
SAN ARDO 1102 | 7030 | Escalation: Project | 2023-09-13 | 2023-09-27 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
SAN JUSTO 1101 | 4002 | EC/ER Tag | 2023-09-13 | 2023-09-20 | 2023-09-13 | Complete | Digital Platform
SAN JUSTO 1101 | 4002 | Escalation: Animal Guard | 2023-09-13 | 2023-09-27 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
SAN JUSTO 1101 | 4002 | Animal Mitigation Review | 2023-10-25 | 2023-11-01 | 2023-11-03 | Complete | Digital Platform
SAN JUSTO 1101 | 4002 | MORe Investigation Request | 2023-10-25 | 2023-11-01 | 2023-11-03 | Complete | Digital Platform
SAN JUSTO 1101 | 4002 | Animal Guard | 2023-10-25 | 2023-11-08 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
SAN JUSTO 1101 | 4002 | Escalation: DCD Settings | 2023-10-25 | 2023-11-08 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
SAN LUIS OBISPO 1104 | V46 | MORe Investigation Request | 2023-10-04 | 2023-10-18 | 2023-10-06 | Complete | Digital Platform
SAN LUIS OBISPO 1104 | V46 | Escalation: Settings Review | 2023-10-04 | 2023-10-18 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
SAN LUIS OBISPO 1104 | V46 | MORe Investigation Request | 2023-10-06 | 2023-10-13 | 2023-10-18 | Complete | Digital Platform
SAN LUIS OBISPO 1104 | V46 | Escalation: Project | 2023-10-06 | 2023-10-20 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
SANTA NELLA 1101 | 7200 | EC/ER Tag | 2023-07-10 | 2023-07-24 |  | Complete | Manual Tracker
SANTA YNEZ 1101 | 277014 | Cause Investigation | 2023-09-29 | 2023-10-13 | 2023-10-05 | Complete | Manual Tracker
SANTA YNEZ 1104 | Y04 | Escalation: Settings Review | 2023-08-09 | 2023-08-23 |  | Complete | Manual Tracker
SARATOGA 1106 | 340986 | Vegetation Work Assessment | 2023-07-21 | 2023-08-04 | 2023-08-09 | Complete | Manual Tracker
SARATOGA 1106 | 340986 | Request Accelerated Patrol | 2023-07-21 | 2023-08-04 | 2023-08-09 | Complete | Manual Tracker
SHADY GLEN 1102 | 2232 | Outage Information Gathering | 2023-06-07 | 2023-06-21 | 2023-06-12 | Complete | Manual Tracker
SHADY GLEN 1102 | 2232 | Outage Information Gathering | 2023-06-07 | 2023-06-21 | 2023-06-14 | Complete | Manual Tracker
SHINGLE SPRINGS 2108 | 294550 | Escalate ORT Review | 2023-07-31 | 2023-08-14 |  | Complete | Manual Tracker
SHINGLE SPRINGS 2108 | 294550 | Sectionalization Assessment | 2023-07-31 | 2023-08-14 | 2023-07-31 | Complete | Manual Tracker
SILVERADO 2104 | 632 | Escalation: Veg Review | 2023-08-18 | 2023-08-25 | 2023-09-01 | Complete | Manual Tracker
SILVERADO 2104 | 632 | Escalation: Settings Review | 2023-08-18 | 2023-08-25 | 2023-08-29 | Complete | Manual Tracker
SILVERADO 2104 | 632 | Escalation: Project | 2023-08-18 | 2023-08-25 | 2023-09-15 | Complete | Manual Tracker
SILVERADO 2104 | 722 | MORe Investigation Request | 2023-10-05 | 2023-10-12 | 2023-10-17 | Complete | Digital Platform
SILVERADO 2104 | 722 | Escalation: ORT Investigation | 2023-10-05 | 2023-10-19 | 2023-10-17 | Complete | Manual Tracker
SOBRANTE 1101 | 1101/2 | Escalate ORT Review | 2023-07-31 | 2023-08-14 | 2023-08-24 | Complete | Manual Tracker
SOLEDAD 2104 | 7008 | MORe Investigation Request | 2023-11-07 | 2023-11-14 | 2023-11-07 | Complete | Digital Platform
SONOMA 1104 | Circuit-Level | Escalation: CAIDI Review | 2023-08-09 | 2023-08-23 |  | Past Due | Manual Tracker
STANISLAUS 1701 | 7144 | Planning/Coordination Review | 2023-07-13 | 2023-07-27 |  | Complete | Manual Tracker
STANISLAUS 1701 | 7144 | Outage Information Gathering | 2023-07-17 | 2023-07-31 |  | Complete | Manual Tracker
STANISLAUS 1701 | 7144 | MORe Investigation Request | 2023-09-08 | 2023-09-22 | 2023-09-13 | Complete | Digital Platform
STANISLAUS 1701 | 7144 | MORe Investigation Request | 2023-09-08 | 2023-09-22 | 2023-09-13 | Complete | Digital Platform
STANISLAUS 1701 | 7144 | Escalation: Investigation | 2023-09-08 | 2023-09-22 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
STANISLAUS 1701 | 7144 | Protection/Coordination Review | 2023-09-14 | 2023-09-21 | 2023-09-14 | Complete | Digital Platform
STANISLAUS 1701 | 7144 | Investigation | 2023-09-14 | 2023-09-21 | 2023-09-14 | Complete | Digital Platform
STANISLAUS 1701 | 7144 | Escalation: Settings Review | 2023-09-14 | 2023-09-28 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
STANISLAUS 1701 | 7144 | Escalation: Investigation | 2023-09-14 | 2023-09-28 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
STANISLAUS 1701 | 7144 | MORe Investigation Request | 2023-10-13 | 2023-10-27 | 2023-10-18 | Complete | Digital Platform
STANISLAUS 1701 | 7144 | MORe Investigation Request | 2023-10-16 | 2023-10-23 | 2023-10-18 | Complete | Digital Platform
STANISLAUS 1701 | 7144 | MORe Investigation Request | 2023-10-16 | 2023-10-23 | 2023-10-18 | Complete | Digital Platform
STANISLAUS 1701 | 7144 | Escalation: Settings Review | 2023-10-16 | 2023-10-30 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
STANISLAUS 1701 | 7144 | Escalation: Project | 2023-10-16 | 2023-10-30 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
STANISLAUS 1702 | 1850 | Vegetation Work | 2023-10-13 | 2023-10-20 | 2023-10-18 | Complete | Digital Platform
STANISLAUS 1702 | 1850 | ILIS Record Update | 2023-10-13 | 2023-10-27 | 2023-10-13 | Complete | Digital Platform
TEMPLETON 2111 | A66 | Escalation: Settings Review | 2023-10-11 | 2023-10-25 |  | In Progress - Tracked in Digital Platform (Duplicate) | Manual Tracker
TEMPLETON 2111 | A66 | MORe Investigation Request | 2023-10-12 | 2023-10-19 |  | In Progress | Digital Platform
TEMPLETON 2113 | A70 | Cause Investigation | 2023-10-02 | 2023-10-16 |  | Past Due | Manual Tracker
TEMPLETON 2113 | A70 | EC/ER Tag | 2023-10-02 | 2023-10-16 |  | Past Due | Manual Tracker
TIDEWATER 2106 | 57926 | Animal Mitigation Review | 2023-10-25 | 2023-11-01 | 2023-11-01 | Complete | Digital Platform
TIDEWATER 2106 | 57926 | MORe Investigation Request | 2023-10-25 | 2023-11-08 | 2023-11-15 | Complete | Digital Platform
TIDEWATER 2106 | 57926 | Animal Guard | 2023-10-25 | 2023-11-08 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
TIDEWATER 2106 | 57926 | Escalation: Settings Review | 2023-10-25 | 2023-11-08 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
TIVY VALLEY 1107 | 822606 | Investigation | 2023-09-21 | 2023-09-28 | 2023-09-22 | Complete | Digital Platform
TIVY VALLEY 1107 | 822606 | Escalation: Cause Code | 2023-09-21 | 2023-09-28 |  | Complete - Tracked in Digital Platform (Duplicate) | Manual Tracker
TIVY VALLEY 1107 | R1817 | Investigation | 2023-09-21 | 2023-09-28 | 2023-09-22 | Complete | Digital Platform
VOLTA 1101 | 65764 | MORe Investigation Request | 2023-08-30 | 2023-09-06 | 2023-09-01 | Complete | Digital Platform
VOLTA 1101 | 65764 | Escalation: Veg Review | 2023-08-30 | 2023-09-13 | 2023-09-01 | Complete | Manual Tracker
ZACA 1101 | CB 1101 | MORe Investigation Request | 2023-11-07 | 2023-11-14 | 2023-11-17 | Complete | Digital Platform
ZACA 1102 | Y48 | Planning/Coordination Review | 2023-06-27 | 2023-07-11 |  | Complete | Manual Tracker