## TABLE 9-2
TABLE 9-2:
LIST OF FREQUENTLY DE-ENERGIZED CIRCUITS
[8 empty] | ORIGINAL | UPDATED AS OF FEBRUARY 2024
Entry Number | ID or Circuit | Circuit Name | Transmission (Tx) / Distribution (Dx) | County | Date of Outages | Number of Customers Served by Circuit (as of December 1, 2022) | Number of Customers affected | Measures Taken, or Planned to be Taken, to Reduce the Need for and Impact of Future PSPS of Circuit | Measures Taken, or Planned to be Taken, to Reduce the Need for and Impact of Future PSPS of Circuit
1 | 152101101 | ALLEGHANY 1101 | Dx | SIERRA | 2019-10-09 | 1036 | 1043 | • 1 Sectionalizing device added or replaced • Temporary Generation deployed that benefited 994 customers | • 1 Sectionalizing device added or replaced - completed in Q2 2021 • Temporary Generation deployed that benefited 994 customers - completed in Q3 2023 • 0.86 miles of line removal - 0.65 completed in 2021 - 0.04 completed in Q2 2022 - 0.11 completed in Q3 2023 - 0.06 miles of line removal planned to be complete in 2024
[5 empty] | 2019-10-23 |  | 1038
[5 empty] | 2019-10-26 |  | 1037
[5 empty] | 2020-09-07 |  | 1028
[5 empty] | 2020-09-27 |  | 1032
[5 empty] | 2020-10-14 |  | 957
[5 empty] | 2020-10-25 |  | 1033
2 | 152101102 | ALLEGHANY 1102 | Dx | NEVADA | 2019-10-09 | 151 | 151 | • 0.4 miles of overhead hardening completed • Planned underground hardening | • 0.4 miles of overhead hardening - completed in Q2 2021 • Planned undergrounding hardening - 34.4 miles planned to be complete in 2025 • Planned line removal - 0.02 miles planned to be completed in 2024
[5 empty] | 2019-10-23 |  | 151
[5 empty] | 2019-10-26 |  | 152
[5 empty] | 2020-09-07 |  | 151
[5 empty] | 2020-09-27 |  | 153
[5 empty] | 2020-10-25 |  | 153
3 | 163561101 | ALPINE 1101 | Dx | ALPINE | 2019-10-09 | 278 | 278 | • 553 customer-events mitigated by PSPS protocols | • 553 customer-events mitigated by PSPS protocols - N/A – on-going
[5 empty] | 2019-10-23 |  | 278
[5 empty] | 2019-10-26 |  | 277
[5 empty] | 2020-09-07 |  | 276
[5 empty] | 2020-09-27 |  | 278
[5 empty] | 2020-10-25 |  | 278
4 | 163561102 | ALPINE 1102 | Dx | ALPINE | 2019-10-09 | 306 | 303 | • 596 customer-events mitigated by PSPS protocols | • 596 customer-events mitigated by PSPS protocols - N/A – on-going
[5 empty] | 2019-10-23 |  | 303
[5 empty] | 2019-10-26 |  | 304
[5 empty] | 2020-09-07 |  | 303
[5 empty] | 2020-09-27 |  | 303
[5 empty] | 2020-10-25 |  | 304
5 | 103261103 | ANDERSON 1103 | Dx | SHASTA | 2019-10-09 | 895 | 886 | • 3 Sectionalizing devices added or replaced • Planned overhead hardening • Planned undergrounding hardening • 2492 customer-events mitigated by PSPS protocols | • 3 Sectionalizing devices added or replaced - completed in Q3 2020 and Q3 2022 • Planned overhead hardening - 3.0 miles planned to be completed in 2025 • Planned undergrounding hardening - 3.73 miles of underground hardening completed - 0.76 completed in Q3 2023 - 2.97 completed in Q4 2023 • Planned line removal - 0.10 miles planned to be completed in 2025 • 2492 customer-events mitigated by PSPS protocols - N/A – on-going
[5 empty] | 2019-10-26 |  | 886
[5 empty] | 2019-11-20 |  | 436
[5 empty] | 2020-10-21 |  | 437
[5 empty] | 2020-10-25 |  | 438
[5 empty] | 2021-08-17 |  | 68
[5 empty] | 2021-10-11 |  | 68
6 | 42861101 | ANNAPOLIS 1101 | Dx | SONOMA | 2019-10-09 | 223 | 219 | • 445 customer-events mitigated by PSPS protocols | • 445 customer-events mitigated by PSPS protocols [N/A – on-going] • Planned line removal - 0.17 miles planned to be completed in 2024
[5 empty] | 2019-10-23 |  | 9
[5 empty] | 2019-10-26 |  | 218
[5 empty] | 2020-10-25 |  | 222
Notes: The 2019 temporary generation mitigation data does not include customers mitigated because some data such as temporary microgrid circuits was not recorded at the circuit level. Additionally, in some examples the customer count that was energized by temporary microgrids via temporary generation may have combined customer count without separate count by circuit. This table includes circuits de-energized three or more times in any calendar year from 2019-2022. For the full list of frequently de-energized circuits see Appendix F.