## PG&E UG Workplan 2023-26_Conf
PG&E 2023-2026 Undergrounding Workplan
Data as of January 3, 2023
[21 empty] | 2697.1635 | 10.6458 | 534.3408 | 588.2466 | 682.9839 | 880.9464
Order | Category | MAT Code | SAP Status | Status | WMP GH-05 10k UG (Y/N) | Division | Region | City | County | Latitude | Longitude | Applicable Risk Model | Circuit Protection Zone (CPZ) (V2) | Risk Rank (V2) | Mean Risk (V2) | Circuit Protection Zone (CPZ) (V3) | Risk Rank (V3) | Mean Risk (V3) | HFTD Tier | Feasibility Score by CPZ | Total Planned UG Miles | UG - 2022 Complete | UG - 2023 Forecast | UG - 2024 Forecast | UG - 2025 Forecast | UG - 2026 Forecast
35311627 | Base SH | 08W | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Canyon Dam | Plumas | 40.2105 | -121.1643 | WDRM v2 |  | 3328 | 4.13e-06 |  | 969 | 0.0023864 | Tier 2 | 1.9955 | 2.05 | 0 | 0 | 0 | 2.05 | 0
35374057 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SO | Region 1 - North Coast | Geyserville | Sonoma | 38.7005 | -122.9574 | WDRM v3 |  | 2170 | 0.0056711 |  | 1375 | 0.0011879 | Tier 2 | 1.6692 | 0.33996 | 0 | 0 | 0 | 0 | 0.33996
35367472 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7701 | -120.5893 | WDRM v3 |  | 2469 | 0.0020868 |  | 780 | 0.0031904 | Tier 3 | 1.0202 | 4.29 | 0 | 0 | 0 | 4.29 | 0
35373630 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8531 | -121.6056 | WDRM v3 |  | 2420 | 0.0024209 |  | 657 | 0.003959 | Tier 3 | 1.0789 | 8.5 | 0 | 0 | 0 | 0 | 8.5
35373629 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8536 | -121.6057 | WDRM v3 |  | 2420 | 0.0024209 |  | 657 | 0.003959 | Tier 3 | 1.0789 | 5.76 | 0 | 0 | 0 | 0 | 5.76
35367501 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8541 | -121.6059 | WDRM v3 |  | 2420 | 0.0024209 |  | 657 | 0.003959 | Tier 3 | 1.0789 | 4.54 | 0 | 0 | 0 | 0 | 4.54
35373626 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7585 | -120.5585 | WDRM v3 |  | 2028 | 0.0085289 |  | 625 | 0.0042306 | Tier 3 | 1.0426 | 6.2701 | 0 | 0 | 0 | 0 | 6.2701
35373625 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7594 | -120.5587 | WDRM v3 |  | 2028 | 0.0085289 |  | 625 | 0.0042306 | Tier 3 | 1.0426 | 6.2201 | 0 | 0 | 0 | 0 | 6.2201
35311626 | Base SH | 08W | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Canyon Dam | Plumas | 40.2105 | -121.1643 | WDRM v2 |  | 3328 | 4.13e-06 |  | 969 | 0.0023864 | Tier 2 | 1.9955 | 3.64 | 0 | 0 | 0 | 3.64 | 0
35311596 | Base SH | 08W | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Canyon Dam | Plumas | 40.2105 | -121.1643 | WDRM v2 |  | 3328 | 4.13e-06 |  | 969 | 0.0023864 | Tier 2 | 1.9955 | 3 | 0 | 0 | 0 | 3 | 0
35286103 | Base SH | 08W | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 3328 | 4.13e-06 |  | 969 | 0.0023864 | Tier 2 | 1.9955 | 3.0701 | 0 | 0 | 0 | 3.0701 | 0
35373624 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7597 | -120.5587 | WDRM v3 |  | 2028 | 0.0085289 |  | 625 | 0.0042306 | Tier 3 | 1.0426 | 11.9201 | 0 | 0 | 0 | 11.9201 | 0
35367473 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7467 | -120.5634 | WDRM v3 |  | 2028 | 0.0085289 |  | 625 | 0.0042306 | Tier 3 | 1.0426 | 7.2701 | 0 | 0 | 0 | 7.2701 | 0
35390389 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.508 | -119.9962 | WDRM v3 |  | 187 | 0.2644 |  | 531 | 0.0051015 | Tier 2 | 1.291 | 5.51 | 0 | 0 | 0 | 5.51 | 0
35375091 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2786 | -121.3033 | WDRM v3 |  | 1359 | 0.035805 |  | 516 | 0.0052285 | Tier 2 | 1.076 | 7.6799 | 0 | 0 | 0 | 0 | 7.6799
35364020 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2791 | -121.3034 | WDRM v3 |  | 1359 | 0.035805 |  | 516 | 0.0052285 | Tier 2 | 1.076 | 7.5 | 0 | 0 | 0 | 0 | 7.5
35376306 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5136 | -119.8722 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 2 & 3 | 1.7655 | 0.67992 | 0 | 0 | 0.67992 | 0 | 0
35376304 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5136 | -119.8722 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 3 | 1.7655 | 0.45 | 0 | 0 | 0.45 | 0 | 0
35376303 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5268 | -119.904 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 3 | 1.7655 | 0.21004 | 0 | 0 | 0.21004 | 0 | 0
35374866 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5363 | -119.833 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 3 | 1.7655 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0
35374865 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5363 | -119.833 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 3 | 1.7655 | 0.47008 | 0 | 0.47008 | 0 | 0 | 0
35374864 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5083 | -119.8773 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 3 | 1.7655 | 2.0799 | 0 | 2.0799 | 0 | 0 | 0
35374862 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5079 | -119.8466 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 3 | 1.7655 | 1.5299 | 0 | 1.5299 | 0 | 0 | 0
35374687 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5083 | -119.8773 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 2 | 1.7655 | 0.45 | 0 | 0.45 | 0 | 0 | 0
35374686 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5268 | -119.904 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 3 | 1.7655 | 1.59 | 0 | 1.59 | 0 | 0 | 0
35374685 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.517 | -119.8344 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 3 | 1.7655 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0
35374684 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.517 | -119.8344 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 2 & 3 | 1.7655 | 1.4201 | 0 | 1.4201 | 0 | 0 | 0
35374683 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.513 | -119.8444 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 2 & 3 | 1.7655 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0
35374682 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.541 | -119.9184 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 2 & 3 | 1.7655 | 2.45 | 0 | 2.45 | 0 | 0 | 0
35374559 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5087 | -119.8728 | WDRM v3 |  | 655 | 0.11849 |  | 504 | 0.00537 | Tier 2 & 3 | 1.7655 | 1.7 | 0 | 1.7 | 0 | 0 | 0
35364022 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Soledad | Monterey | 36.3482 | -121.322 | WDRM v3 |  | 2006 | 0.0089147 |  | 462 | 0.0060529 | Tier 2 | 1 | 2.4 | 0 | 0 | 0 | 2.4 | 0
35374455 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Chico | Butte | 39.8337 | -121.8445 | WDRM v3 |  | 1137 | 0.053762 |  | 434 | 0.0064305 | Tier 2 & 3 | 1.1577 | 10 | 0 | 0 | 0 | 0 | 10
35329471 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake | Lake | 38.9373 | -122.6091 | WDRM v2 |  | 3243 | 5.43e-06 |  | 1561 | 0.00090896 | Tier 2 | 1.0955 | 1.55 | 0 | 1.55 | 0 | 0 | 0
35374454 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Chico | Butte | 39.833 | -121.8444 | WDRM v3 |  | 1137 | 0.053762 |  | 434 | 0.0064305 | Tier 2 | 1.1577 | 10 | 0 | 0 | 0 | 10 | 0
35374444 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Chico | Butte | 39.8316 | -121.8443 | WDRM v3 |  | 1137 | 0.053762 |  | 434 | 0.0064305 | Tier 2 | 1.1577 | 8.66 | 0 | 0 | 0 | 8.66 | 0
35396304 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1904 | -121.0028 | WDRM v3 |  | 2157 | 0.0059169 |  | 429 | 0.0065825 | Tier 3 | 1.085 | 2.24 | 0 | 0 | 2.24 | 0 | 0
35392779 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1985 | -121.0106 | WDRM v3 |  | 2157 | 0.0059169 |  | 429 | 0.0065825 | Tier 3 | 1.085 | 3.07 | 0 | 0 | 0 | 3.07 | 0
35392778 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1989 | -121.0106 | WDRM v3 |  | 2157 | 0.0059169 |  | 429 | 0.0065825 | Tier 3 | 1.085 | 1.48 | 0 | 0 | 0 | 1.48 | 0
35373585 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1953 | -121.0108 | WDRM v3 |  | 2157 | 0.0059169 |  | 429 | 0.0065825 | Tier 3 | 1.085 | 1.44 | 0 | 1.44 | 0 | 0 | 0
35367418 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1994 | -121.0172 | WDRM v3 |  | 2157 | 0.0059169 |  | 429 | 0.0065825 | Tier 3 | 1.085 | 4.02 | 0 | 0 | 0 | 4.02 | 0
35403554 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4911 | -122.5229 | WDRM v3 |  | 2174 | 0.0056116 |  | 398 | 0.0070204 | Tier 3 | 1.1674 | 2.95 | 0 | 0 | 0 | 0 | 2.95
35403553 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4947 | -122.494 | WDRM v3 |  | 2174 | 0.0056116 |  | 398 | 0.0070204 | Tier 3 | 1.1674 | 1.5299 | 0 | 0 | 0 | 0 | 1.5299
35403552 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4944 | -122.4756 | WDRM v3 |  | 2174 | 0.0056116 |  | 398 | 0.0070204 | Tier 3 | 1.1674 | 2.31 | 0 | 0 | 0 | 0 | 2.31
35403551 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4996 | -122.4892 | WDRM v3 |  | 2174 | 0.0056116 |  | 398 | 0.0070204 | Tier 3 | 1.1674 | 1.25 | 0 | 0 | 0 | 0 | 1.25
35367518 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Saint Helena | Napa | 38.4983 | -122.4796 | WDRM v3 |  | 2174 | 0.0056116 |  | 398 | 0.0070204 | Tier 3 | 1.1674 | 8.2201 | 0 | 0 | 8.2201 | 0 | 0
35392114 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Georgetown | El Dorado | 38.9878 | -120.7412 | WDRM v3 |  | 2131 | 0.0064469 |  | 397 | 0.0070659 | Tier 3 | 1.2997 | 0.84905 | 0 | 0 | 0 | 0 | 0.84905
35355173 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9947 | -121.7415 | WDRM v3 |  | 2320 | 0.0032735 |  | 394 | 0.0070854 | Tier 2 | 1.428 | 0.52917 | 0 | 0 | 0.52917 | 0 | 0
35355171 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9849 | -121.8485 | WDRM v3 |  | 2320 | 0.0032735 |  | 394 | 0.0070854 | Tier 2 | 1.428 | 0.55814 | 0 | 0 | 0 | 0.55814 | 0
35404753 | Targeted UG | 3UG | ESTS | Estimating | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2364 | -120.3626 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 0.0073524 | Tier 3 | 1.1708 | 3.74 | 0 | 0 | 3.74 | 0 | 0
35385890 | Targeted UG | 3UG | ESTS | Estimating | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2367 | -120.3629 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 0.0073524 | Tier 3 | 1.1708 | 1.383 | 0 | 1.383 | 0 | 0 | 0
35385889 | Targeted UG | 3UG | ESTS | Estimating | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2367 | -120.3629 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 0.0073524 | Tier 3 | 1.1708 | 2.453 | 0 | 0 | 2.453 | 0 | 0
35385888 | Targeted UG | 3UG | ESTS | Estimating | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2367 | -120.3629 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 0.0073524 | Tier 3 | 1.1708 | 1.5439 | 0 | 1.5439 | 0 | 0 | 0
35376888 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2364 | -120.3626 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 0.0073524 | Tier 3 | 1.1708 | 7.2701 | 0 | 0 | 0 | 0 | 7.2701
35373705 | Targeted UG | 3UG | ESTS | Estimating | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2364 | -120.3626 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 0.0073524 | Tier 3 | 1.1708 | 5.517 | 0 | 0 | 5.517 | 0 | 0
35367520 | Targeted UG | 3UG | ESTS | Estimating | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2367 | -120.3629 | WDRM v3 |  | 2386 | 0.0026855 |  | 379 | 0.0073524 | Tier 3 | 1.1708 | 2.2869 | 0 | 2.2869 | 0 | 0 | 0
35373599 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7688 | -120.4471 | WDRM v3 |  | 1138 | 0.05356 |  | 370 | 0.0074889 | Tier 2 & 3 | 2.289 | 8.44 | 0 | 0 | 0 | 8.44 | 0
35367467 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7606 | -120.505 | WDRM v3 |  | 1138 | 0.05356 |  | 370 | 0.0074889 | Tier 2 | 2.289 | 8.75 | 0 | 0 | 0 | 0 | 8.75
35392113 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.0444 | -120.7393 | WDRM v3 |  | 1434 | 0.031693 |  | 322 | 0.0088134 | Tier 3 | 1.5426 | 1.2197 | 0 | 0 | 0 | 1.2197 | 0
35387916 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.0473 | -120.7853 | WDRM v3 |  | 1434 | 0.031693 |  | 322 | 0.0088134 | Tier 2 & 3 | 1.5426 | 7.21 | 0 | 0 | 0 | 7.21 | 0
35397456 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.174 | -120.9729 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 3.529 | 0 | 0 | 0 | 3.529 | 0
35397455 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1806 | -120.9751 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 1.312 | 0 | 0 | 0 | 1.312 | 0
35397454 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1914 | -120.9614 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 2.778 | 0 | 0 | 2.778 | 0 | 0
35397453 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1675 | -120.969 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 2 & 3 | 1.1644 | 4.302 | 0 | 0 | 4.302 | 0 | 0
35397452 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1702 | -120.972 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 2 & 3 | 1.1644 | 2.074 | 0 | 0 | 2.074 | 0 | 0
35326790 | Base SH | 08W | ESTS | Estimating | Y | SI | Region 2 - North East | Auburn | Placer | 38.8934 | -121.0677 | WDRM v2 |  | 2980 | 1.76e-05 |  | 2071 | 0.00050684 | Tier 2 | 1.5 | 0.14792 | 0 | 0.14792 | 0 | 0 | 0
35396863 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1779 | -120.9564 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 2.487 | 0 | 0 | 0 | 2.487 | 0
35396862 | Targeted UG | 3UG | ESTS | Estimating | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.188 | -120.959 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 1.798 | 0 | 0 | 0 | 1.798 | 0
35396861 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1881 | -120.9474 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 2.134 | 0 | 0 | 0 | 2.134 | 0
35396860 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1857 | -120.9735 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 2.6 | 0 | 0 | 2.6 | 0 | 0
35396779 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1902 | -120.9767 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 2.01 | 0 | 0 | 2.01 | 0 | 0
35396778 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1908 | -120.984 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 1.41 | 0 | 0 | 1.41 | 0 | 0
35396776 | Targeted UG | 3UG | ESTS | Estimating | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1909 | -120.9933 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 2.79 | 0 | 0 | 2.79 | 0 | 0
35396775 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1911 | -120.9964 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 1.71 | 0 | 0 | 0 | 1.71 | 0
35390288 | Targeted UG | 3UG | PEND | Permitting/Dependency | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1766 | -120.9772 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 0.12973 | 0 | 0 | 0 | 0 | 0.12973
35373596 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1907 | -120.9917 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 8.09 | 0 | 0 | 0 | 0 | 8.09
35373595 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1851 | -120.9719 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 3.061 | 0 | 0 | 0 | 3.061 | 0
35373594 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1841 | -120.9421 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 10.76 | 0 | 10.76 | 0 | 0 | 0
35373593 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1871 | -120.9543 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 3.081 | 0 | 3.081 | 0 | 0 | 0
35373592 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1919 | -120.9748 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 5.642 | 0 | 0 | 5.642 | 0 | 0
35373590 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1715 | -120.9736 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 2 & 3 | 1.1644 | 2.268 | 0 | 0 | 2.268 | 0 | 0
35373589 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1905 | -120.9887 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 8.1201 | 0 | 0 | 8.1201 | 0 | 0
35367462 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1912 | -120.9936 | WDRM v3 |  | 1788 | 0.014797 |  | 315 | 0.0088799 | Tier 3 | 1.1644 | 4.653 | 0 | 0 | 4.653 | 0 | 0
35382936 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Upper Lake | Lake | 39.213 | -122.9301 | WDRM v3 |  | 705 | 0.11161 |  | 309 | 0.0089653 | Tier 2 & 3 | 1.2396 | 5.26 | 0 | 0 | 0 | 5.26 | 0
35382934 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1892 | -122.9009 | WDRM v3 |  | 705 | 0.11161 |  | 309 | 0.0089653 | Tier 2 | 1.2396 | 6.04 | 0 | 0 | 0 | 6.04 | 0
35379289 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | North San Juan | Yuba | 39.4332 | -121.0753 | WDRM v3 |  | 1400 | 0.033438 |  | 301 | 0.0093855 | Tier 3 | 2.2228 | 6.74 | 0 | 0 | 0 | 0 | 6.74
35375453 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camptonville | Yuba | 39.452 | -121.0541 | WDRM v3 |  | 1400 | 0.033438 |  | 301 | 0.0093855 | Tier 3 | 2.2228 | 10.5875 | 0 | 0 | 0 | 10.5875 | 0
35385801 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Chico | Butte | 39.7911 | -121.7218 | WDRM v3 |  | 1045 | 0.061762 |  | 290 | 0.0096296 | Tier 2 & 3 | 1.2149 | 6.1 | 0 | 0 | 0 | 0 | 6.1
35401222 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7583 | -120.5159 | WDRM v3 |  | 2037 | 0.0083743 |  | 287 | 0.0097168 | Tier 3 | 1.1695 | 4.3201 | 0 | 0 | 0 | 0 | 4.3201
35401221 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7616 | -120.5345 | WDRM v3 |  | 2037 | 0.0083743 |  | 287 | 0.0097168 | Tier 3 | 1.1695 | 3.1201 | 0 | 0 | 0 | 3.1201 | 0
35401220 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7643 | -120.5577 | WDRM v3 |  | 2037 | 0.0083743 |  | 287 | 0.0097168 | Tier 3 | 1.1695 | 2.64 | 0 | 0 | 0 | 2.64 | 0
35373598 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7632 | -120.5442 | WDRM v3 |  | 2037 | 0.0083743 |  | 287 | 0.0097168 | Tier 3 | 1.1695 | 9.91 | 0 | 0 | 0 | 0 | 9.91
35367466 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7619 | -120.5592 | WDRM v3 |  | 2037 | 0.0083743 |  | 287 | 0.0097168 | Tier 3 | 1.1695 | 4.1 | 0 | 0 | 0 | 0 | 4.1
35367475 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7932 | -120.6192 | WDRM v3 |  | 2732 | 0.00051722 |  | 278 | 0.0099516 | Tier 3 | 1.1506 | 6.8875 | 0 | 0 | 0 | 0 | 6.8875
35374562 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.8847 | -121.6661 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 0.010009 | Tier 2 | 1.1479 | 8.75 | 0 | 0 | 0 | 0 | 8.75
35374561 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.8856 | -121.666 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 0.010009 | Tier 2 | 1.1479 | 8.75 | 0 | 0 | 0 | 0 | 8.75
35374459 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.8864 | -121.6657 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 0.010009 | Tier 2 | 1.1479 | 8.75 | 0 | 0 | 0 | 8.75 | 0
35374458 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.8868 | -121.6655 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 0.010009 | Tier 2 & 3 | 1.1479 | 8.75 | 0 | 0 | 0 | 8.75 | 0
35374457 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.887 | -121.6654 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 0.010009 | Tier 3 | 1.1479 | 8.75 | 0 | 0 | 8.75 | 0 | 0
35374456 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.8871 | -121.6654 | WDRM v3 |  | 2575 | 0.0013923 |  | 273 | 0.010009 | Tier 3 | 1.1479 | 10.19 | 0 | 0 | 10.19 | 0 | 0
35350039 | Fire Rebuild | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Berry Creek | Butte | 39.6626 | -121.4006 | WDRM v3 |  | 1288 | 0.040961 |  | 267 | 0.010152 | Tier 3 | 2.0187 | 0.066288 | 0 | 0.066288 | 0 | 0 | 0
35373588 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1696 | -120.993 | WDRM v3 |  | 1154 | 0.052212 |  | 266 | 0.010208 | Tier 2 & 3 | 1.3068 | 9.31 | 0 | 0 | 0 | 0 | 9.31
35373587 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1651 | -120.988 | WDRM v3 |  | 1154 | 0.052212 |  | 266 | 0.010208 | Tier 2 & 3 | 1.3068 | 9.7799 | 0 | 0 | 0 | 9.7799 | 0
35367460 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.1909 | -120.9998 | WDRM v3 |  | 1154 | 0.052212 |  | 266 | 0.010208 | Tier 2 & 3 | 1.3068 | 12.41 | 0 | 0 | 0 | 0 | 12.41
35373706 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4894 | -120.5255 | WDRM v3 |  | 2293 | 0.0035258 |  | 256 | 0.01053 | Tier 3 | 1.0208 | 12.45 | 0 | 0 | 0 | 0 | 12.45
35367522 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4868 | -120.523 | WDRM v3 |  | 2293 | 0.0035258 |  | 256 | 0.01053 | Tier 3 | 1.0208 | 12.09 | 0 | 0 | 0 | 12.09 | 0
35397961 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3465 | -122.4193 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2624 | 1.161 | 0 | 0 | 1.161 | 0 | 0
35397960 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3441 | -122.41 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2624 | 2.222 | 0 | 0 | 2.222 | 0 | 0
35396905 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.393 | -122.4421 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2624 | 0.481 | 0 | 0 | 0 | 0.481 | 0
35396904 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3909 | -122.4387 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2624 | 0.848 | 0 | 0 | 0 | 0.848 | 0
35396903 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3905 | -122.438 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2624 | 1.957 | 0 | 0 | 0 | 1.957 | 0
35396902 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3857 | -122.4324 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2624 | 2.575 | 0 | 0 | 0 | 2.575 | 0
35396900 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.382 | -122.4321 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2624 | 1.418 | 0 | 0 | 0 | 1.418 | 0
35396878 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3757 | -122.4227 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2624 | 1.74 | 0 | 0 | 0 | 1.74 | 0
35396877 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3723 | -122.4178 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2624 | 4.262 | 0 | 0 | 0 | 4.262 | 0
35396876 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3753 | -122.4221 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2624 | 1.725 | 0 | 0 | 0 | 1.725 | 0
35396875 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.363 | -122.4052 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2624 | 2.705 | 0 | 0 | 2.705 | 0 | 0
35396874 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3471 | -122.3949 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2624 | 2.965 | 0 | 0 | 2.965 | 0 | 0
35396871 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3624 | -122.4047 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2624 | 0.703 | 0 | 0 | 0.703 | 0 | 0
35396870 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3512 | -122.3815 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2624 | 1.619 | 0 | 0 | 1.619 | 0 | 0
35396869 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3395 | -122.3757 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2624 | 3.618 | 0 | 0 | 3.618 | 0 | 0
35392777 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3326 | -122.398 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 2 & 3 | 1.2624 | 1.8201 | 0 | 0 | 0 | 1.8201 | 0
35392776 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3391 | -122.3909 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2624 | 1.6201 | 0 | 0 | 0 | 1.6201 | 0
35392775 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3365 | -122.3839 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2624 | 1.76 | 0 | 0 | 0 | 1.76 | 0
35392774 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3337 | -122.3742 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2624 | 1.59 | 0 | 0 | 0 | 1.59 | 0
35392773 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3284 | -122.3536 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 2 & 3 | 1.2624 | 4.9 | 0 | 0 | 0 | 4.9 | 0
35373703 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3419 | -122.3942 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2624 | 2.4 | 0 | 0 | 2.4 | 0 | 0
35373637 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3704 | -122.4132 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2624 | 1.87 | 0 | 0 | 0 | 1.87 | 0
35373636 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3338 | -122.3727 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 3 | 1.2624 | 0.616 | 0 | 0 | 0.616 | 0 | 0
35367513 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Napa | Napa | 38.3155 | -122.342 | WDRM v3 |  | 1224 | 0.046077 |  | 255 | 0.010549 | Tier 2 | 1.2624 | 2.27 | 0 | 0 | 0 | 2.27 | 0
35373581 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.2118 | -121.0092 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 0.011407 | Tier 3 | 1.3035 | 6.7299 | 0 | 0 | 6.7299 | 0 | 0
35373580 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.212 | -121.0099 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 0.011407 | Tier 3 | 1.3035 | 8.3799 | 0 | 0 | 0 | 0 | 8.3799
35373539 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.2123 | -121.0107 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 0.011407 | Tier 3 | 1.3035 | 9.31 | 0 | 0 | 0 | 0 | 9.31
35373538 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.2125 | -121.0114 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 0.011407 | Tier 3 | 1.3035 | 8.24 | 0 | 0 | 0 | 8.24 | 0
35373537 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.2127 | -121.0121 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 0.011407 | Tier 3 | 1.3035 | 9.7 | 0 | 0 | 0 | 9.7 | 0
35373536 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.2127 | -121.0123 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 0.011407 | Tier 3 | 1.3035 | 10.3 | 0 | 0 | 10.3 | 0 | 0
35367415 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Grass Valley | Nevada | 39.2129 | -121.0128 | WDRM v3 |  | 1649 | 0.021168 |  | 234 | 0.011407 | Tier 3 | 1.3035 | 7.01 | 0 | 0 | 7.01 | 0 | 0
35396760 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4536 | -120.5299 | WDRM v3 |  | 2447 | 0.002235 |  | 233 | 0.011408 | Tier 3 | 1.1915 | 0.92992 | 0 | 0 | 0 | 0 | 0.92992
35396699 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4536 | -120.5299 | WDRM v3 |  | 2447 | 0.002235 |  | 233 | 0.011408 | Tier 3 | 1.1915 | 3.3701 | 0 | 0 | 0 | 0 | 3.3701
35396698 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4536 | -120.5299 | WDRM v3 |  | 2447 | 0.002235 |  | 233 | 0.011408 | Tier 3 | 1.1915 | 3.64 | 0 | 0 | 0 | 3.64 | 0
35367511 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4536 | -120.5299 | WDRM v3 |  | 2447 | 0.002235 |  | 233 | 0.011408 | Tier 2 & 3 | 1.1915 | 12.7701 | 0 | 0 | 0 | 12.7701 | 0
35418371 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Forest Meadows | Calaveras | 38.1699 | -120.4067 | WDRM v3 |  | 2142 | 0.0062159 |  | 231 | 0.011425 | Tier 2 | 1.4689 | 12.675 | 0 | 0 | 12.675 | 0 | 0
35376889 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4214 | -120.5494 | WDRM v3 |  | 1765 | 0.015736 |  | 218 | 0.011836 | Tier 3 | 1.6481 | 13.7 | 0 | 0 | 0 | 13.7 | 0
35367526 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4187 | -120.557 | WDRM v3 |  | 1765 | 0.015736 |  | 218 | 0.011836 | Tier 3 | 1.6481 | 13.5701 | 0 | 0 | 0 | 0 | 13.5701
35312546 | Base SH | 08W | ESTS | Estimating | Y | SI | Region 2 - North East | Auburn | Placer | 38.8933 | -121.0677 | WDRM v2 |  | 2980 | 1.76e-05 |  | 2071 | 0.00050684 | Tier 2 | 1.5 | 1.0131 | 0 | 0 | 1.0131 | 0 | 0
35373051 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Oroville | Butte | 39.574 | -121.3077 | WDRM v3 |  | 1480 | 0.029281 |  | 212 | 0.01209 | Tier 3 | 2.6372 | 0.13864 | 0 | 0.13864 | 0 | 0 | 0
35367500 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Kelseyville | Lake | 38.8267 | -122.7271 | WDRM v3 |  | 2060 | 0.0076984 |  | 211 | 0.01209 | Tier 3 | 1.137 | 1.4299 | 0 | 0 | 0 | 0 | 1.4299
35404267 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Volcano | Amador | 38.489 | -120.5889 | WDRM v3 |  | 2136 | 0.0063999 |  | 204 | 0.012447 | Tier 2 & 3 | 1.0461 | 6.192 | 0 | 0 | 0 | 6.192 | 0
35402641 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Volcano | Amador | 38.4738 | -120.6267 | WDRM v3 |  | 2136 | 0.0063999 |  | 204 | 0.012447 | Tier 2 & 3 | 1.0461 | 4.914 | 0 | 0 | 4.914 | 0 | 0
35373635 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Volcano | Amador | 38.4858 | -120.6021 | WDRM v3 |  | 2136 | 0.0063999 |  | 204 | 0.012447 | Tier 2 & 3 | 1.0461 | 4.888 | 0 | 0 | 4.888 | 0 | 0
35367510 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Volcano | Amador | 38.4738 | -120.6267 | WDRM v3 |  | 2136 | 0.0063999 |  | 204 | 0.012447 | Tier 2 & 3 | 1.0461 | 9 | 0 | 0 | 9 | 0 | 0
35403850 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5728 | -119.9924 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 0.012689 | Tier 2 | 1.3826 | 3.13 | 0 | 0 | 0 | 0 | 3.13
35403849 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5736 | -119.9769 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 0.012689 | Tier 2 | 1.3826 | 4.31 | 0 | 0 | 0 | 0 | 4.31
35403848 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5677 | -119.9692 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 0.012689 | Tier 2 | 1.3826 | 3.81 | 0 | 0 | 0 | 3.81 | 0
35403847 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5685 | -119.9677 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 0.012689 | Tier 2 | 1.3826 | 4.39 | 0 | 0 | 0 | 4.39 | 0
74001486 | Other | 30A | PEND | Permitting/Dependency | Y | EB | Region 3 - Bay Area | Berkeley | Alameda | 37.8838 | -122.2484 | WDRM v2 |  | 2792 | 0.00031068 |  | 2633 | 0.00025777 | Tier 2 & 3 | 1.3014 | 1.4576 | 0 | 0 | 1.4576 | 0 | 0
35094513 | Base SH | 08W | CONS | In-Construction | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2579 | -120.3477 | WDRM v2 |  | 2712 | 0.00058985 |  | 1583 | 0.00088659 | Tier 3 | 1.2428 | 0.053977 | 0.053977 | 0 | 0 | 0 | 0
35237937 | Other | 2BP | UNSC | Ready for Construction | Y | CC | Region 4 - Central Coast | Soquel | Santa Cruz | 37.0341 | -121.9738 | WDRM v2 |  | 2595 | 0.0012326 |  | 1319 | 0.0013011 | Tier 3 | 1.1955 | 0.015341 | 0 | 0 | 0 | 0.015341 | 0
35342333 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | CC | Region 4 - Central Coast | Santa Cruz | Santa Cruz | 37.0992 | -122.1435 | WDRM v2 |  | 2579 | 0.0013814 |  | 1120 | 0.0018854 | Tier 3 | 2.023 | 0.42576 | 0 | 0.42576 | 0 | 0 | 0
35382933 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5664 | -119.9692 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 0.012689 | Tier 2 | 1.3826 | 5.24 | 0 | 0 | 0 | 0 | 5.24
35379382 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5641 | -119.9403 | WDRM v3 |  | 700 | 0.11205 |  | 199 | 0.012689 | Tier 2 | 1.3826 | 5.28 | 0 | 0 | 0 | 5.28 | 0
35375184 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Paicines | San Benito | 36.34 | -120.7484 | WDRM v3 |  | N/A | N/A |  | 193 | 0.012994 | HFRA | 1.1703 | 8.75 | 0 | 0 | 0 | 0 | 8.75
35375183 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Paicines | San Benito | 36.3616 | -120.8504 | WDRM v3 |  | N/A | N/A |  | 193 | 0.012994 | HFRA | 1.1703 | 8.75 | 0 | 0 | 0 | 0 | 8.75
35375182 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Paicines | San Benito | 36.3871 | -120.9253 | WDRM v3 |  | N/A | N/A |  | 193 | 0.012994 | HFRA | 1.1703 | 8.75 | 0 | 0 | 0 | 8.75 | 0
35375181 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Paicines | San Benito | 36.4052 | -120.9534 | WDRM v3 |  | N/A | N/A |  | 193 | 0.012994 | HFRA | 1.1703 | 8.75 | 0 | 0 | 0 | 8.75 | 0
35375180 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Paicines | San Benito | 36.3874 | -121.0046 | WDRM v3 |  | N/A | N/A |  | 193 | 0.012994 | HFRA | 1.1703 | 12.71 | 0 | 0 | 12.71 | 0 | 0
35376642 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Dutch Flat | Placer | 39.1906 | -120.809 | WDRM v3 |  | 2087 | 0.0071702 |  | 192 | 0.013013 | Tier 3 | 1.4414 | 9.06 | 0 | 0 | 0 | 0 | 9.06
35378609 | Community Rebuild | 95F | ESTS | Estimating | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1407 | -120.9513 | N/A |  | N/A | N/A |  | 2135 | N/A | Non-HFTD | N/A | 0.7 | 0 | 0.7 | 0 | 0 | 0
35376641 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Dutch Flat | Placer | 39.2009 | -120.8105 | WDRM v3 |  | 2087 | 0.0071702 |  | 192 | 0.013013 | Tier 3 | 1.4414 | 8.2 | 0 | 0 | 0 | 8.2 | 0
35376640 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Alta | Placer | 39.2159 | -120.8055 | WDRM v3 |  | 2087 | 0.0071702 |  | 192 | 0.013013 | Tier 3 | 1.4414 | 9.5 | 0 | 0 | 0 | 9.5 | 0
35376556 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Alta | Placer | 39.2147 | -120.8091 | WDRM v3 |  | 2087 | 0.0071702 |  | 192 | 0.013013 | Tier 3 | 1.4414 | 4.7 | 0 | 0 | 4.7 | 0 | 0
35378690 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.8301 | -122.73 | WDRM v3 |  | 328 | 0.19983 |  | 182 | 0.013549 | Tier 3 | 1.2972 | 4.46 | 0 | 0 | 0 | 0 | 4.46
35378688 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.8296 | -122.7299 | WDRM v3 |  | 328 | 0.19983 |  | 182 | 0.013549 | Tier 3 | 1.2972 | 10.89 | 0 | 0 | 0 | 0 | 10.89
35378687 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.8292 | -122.7295 | WDRM v3 |  | 328 | 0.19983 |  | 182 | 0.013549 | Tier 3 | 1.2972 | 8.84 | 0 | 0 | 0 | 8.84 | 0
35377437 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.829 | -122.7294 | WDRM v3 |  | 328 | 0.19983 |  | 182 | 0.013549 | Tier 3 | 1.2972 | 7.19 | 0 | 0 | 0 | 7.19 | 0
35403556 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 38.9826 | -120.8755 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 0.013637 | Tier 3 | 1.1669 | 2.55 | 0 | 0 | 2.55 | 0 | 0
35403555 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 38.9898 | -120.8728 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 0.013637 | Tier 3 | 1.1669 | 3.172 | 0 | 0 | 3.172 | 0 | 0
35399836 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Auburn | Placer | 38.9768 | -121.1313 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 0.013637 | Tier 3 | 1.1669 | 5.387 | 0 | 0 | 0 | 0 | 5.387
35399835 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 38.9997 | -120.8545 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 0.013637 | Tier 3 | 1.1669 | 2.342 | 0 | 0 | 0 | 0 | 2.342
35399834 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.01 | -120.8465 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 0.013637 | Tier 3 | 1.1669 | 3.952 | 0 | 0 | 3.952 | 0 | 0
35373526 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 38.9828 | -120.8824 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 0.013637 | Tier 3 | 1.1669 | 2.785 | 0 | 0 | 2.785 | 0 | 0
35373525 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.0065 | -120.853 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 0.013637 | Tier 3 | 1.1669 | 2.84 | 0 | 0 | 0 | 0 | 2.84
35367476 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.0163 | -120.835 | WDRM v3 |  | 1865 | 0.012496 |  | 179 | 0.013637 | Tier 3 | 1.1669 | 4.52 | 0 | 0 | 4.52 | 0 | 0
35382858 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2698 | -121.4424 | WDRM v3 |  | 1509 | 0.027281 |  | 178 | 0.013726 | Tier 2 | 1.1351 | 7.9701 | 0 | 0 | 7.9701 | 0 | 0
35375099 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2703 | -121.439 | WDRM v3 |  | 1509 | 0.027281 |  | 178 | 0.013726 | Tier 2 | 1.1351 | 8.75 | 0 | 0 | 0 | 0 | 8.75
35375096 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2618 | -121.4162 | WDRM v3 |  | 1509 | 0.027281 |  | 178 | 0.013726 | Tier 2 | 1.1351 | 8.75 | 0 | 0 | 0 | 0 | 8.75
35375095 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2609 | -121.3708 | WDRM v3 |  | 1509 | 0.027281 |  | 178 | 0.013726 | Tier 2 | 1.1351 | 8.75 | 0 | 0 | 0 | 8.75 | 0
35375094 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Greenfield | Monterey | 36.2799 | -121.3079 | WDRM v3 |  | 1509 | 0.027281 |  | 178 | 0.013726 | Tier 2 | 1.1351 | 8.9799 | 0 | 0 | 0 | 8.9799 | 0
35373621 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7563 | -120.5981 | WDRM v3 |  | 2512 | 0.0017374 |  | 176 | 0.013848 | Tier 3 | 1.0507 | 7.31 | 0 | 0 | 0 | 0 | 7.31
35367470 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7583 | -120.5864 | WDRM v3 |  | 2512 | 0.0017374 |  | 176 | 0.013848 | Tier 3 | 1.0507 | 6.71 | 0 | 0 | 0 | 0 | 6.71
35383757 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 |  | 1206 | 0.047319 |  | 164 | 0.014654 | Tier 2 & 3 | 1.4329 | 9.1 | 0 | 0 | 0 | 0 | 9.1
35383756 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 |  | 1206 | 0.047319 |  | 164 | 0.014654 | Tier 2 & 3 | 1.4329 | 9.1 | 0 | 0 | 0 | 0 | 9.1
35383755 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 |  | 1206 | 0.047319 |  | 164 | 0.014654 | Tier 2 & 3 | 1.4329 | 9.1 | 0 | 0 | 0 | 9.1 | 0
35383754 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 |  | 1206 | 0.047319 |  | 164 | 0.014654 | Tier 2 & 3 | 1.4329 | 9.1 | 0 | 0 | 0 | 9.1 | 0
35383753 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3313 | -120.5186 | WDRM v3 |  | 1206 | 0.047319 |  | 164 | 0.014654 | Tier 2 | 1.4329 | 9.1 | 0 | 0 | 0 | 0 | 9.1
35373535 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8695 | -121.6115 | WDRM v3 |  | 2289 | 0.0035789 |  | 158 | 0.015008 | Tier 3 | 1.0309 | 6.04 | 0 | 0 | 0 | 0 | 6.04
35373534 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8701 | -121.6102 | WDRM v3 |  | 2289 | 0.0035789 |  | 158 | 0.015008 | Tier 3 | 1.0309 | 5.5701 | 0 | 0 | 0 | 5.5701 | 0
35367503 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8717 | -121.6106 | WDRM v3 |  | 2289 | 0.0035789 |  | 158 | 0.015008 | Tier 3 | 1.0309 | 7.75 | 0 | 0 | 0 | 7.75 | 0
35374203 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Chico | Butte | 39.7783 | -121.7319 | WDRM v3 |  | 73 | 0.37815 |  | 155 | 0.015172 | Tier 2 & 3 | 1.1411 | 10.6299 | 0 | 0 | 0 | 10.6299 | 0
35402643 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4069 | -120.6707 | WDRM v3 |  | 1764 | 0.015763 |  | 147 | 0.015597 | Tier 2 | 1.498 | 2.4561 | 0 | 0 | 0 | 0 | 2.4561
35396761 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4067 | -120.6708 | WDRM v3 |  | 1764 | 0.015763 |  | 147 | 0.015597 | Tier 2 | 1.498 | 4.64 | 0 | 0 | 0 | 0 | 4.64
35373707 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4067 | -120.6708 | WDRM v3 |  | 1764 | 0.015763 |  | 147 | 0.015597 | Tier 2 | 1.498 | 7.3299 | 0 | 0 | 0 | 7.3299 | 0
35372460 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4069 | -120.6707 | WDRM v3 |  | 1764 | 0.015763 |  | 147 | 0.015597 | Tier 2 | 1.498 | 7.4299 | 0 | 0 | 0 | 0 | 7.4299
35376305 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5083 | -119.8773 | WDRM v3 |  | 1809 | 0.014293 |  | 137 | 0.015939 | Tier 3 | 1.6325 | 0.61004 | 0 | 0.61004 | 0 | 0 | 0
35374863 | Fire Rebuild | 08W | ADER | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5016 | -119.8815 | WDRM v3 |  | 1809 | 0.014293 |  | 137 | 0.015939 | Tier 2 | 1.6325 | 0.46004 | 0 | 0.46004 | 0 | 0 | 0
35367515 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.323 | -120.2535 | WDRM v3 |  | 2620 | 0.0010653 |  | 133 | 0.016045 | Tier 3 | 1.7779 | 6.6799 | 0 | 0 | 0 | 0 | 6.6799
35375515 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7338 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 0.01606 | Tier 2 | 1.1366 | 7.5 | 0 | 0 | 0 | 0 | 7.5
35375514 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7343 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 0.01606 | Tier 2 & 3 | 1.1366 | 7.5 | 0 | 0 | 0 | 0 | 7.5
35375513 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7349 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 0.01606 | Tier 2 & 3 | 1.1366 | 7.5 | 0 | 0 | 0 | 7.5 | 0
35375512 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7357 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 0.01606 | Tier 2 & 3 | 1.1366 | 7.5 | 0 | 0 | 0 | 7.5 | 0
35375511 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7361 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 0.01606 | Tier 3 | 1.1366 | 7.5 | 0 | 0 | 7.5 | 0 | 0
35375510 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.737 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 0.01606 | Tier 2 & 3 | 1.1366 | 7.5 | 0 | 0 | 7.5 | 0 | 0
35375509 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7372 | -120.6759 | WDRM v3 |  | 644 | 0.12006 |  | 132 | 0.01606 | Tier 2 & 3 | 1.1366 | 6.04 | 0 | 0 | 0 | 6.04 | 0
35404716 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Volcano | Amador | 38.4612 | -120.6579 | WDRM v3 |  | 1271 | 0.042249 |  | 131 | 0.016072 | Tier 2 | 1.0944 | 6.96 | 0 | 0 | 6.96 | 0 | 0
35404715 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Volcano | Amador | 38.4612 | -120.6579 | WDRM v3 |  | 1271 | 0.042249 |  | 131 | 0.016072 | Tier 2 | 1.0944 | 8.65 | 0 | 0 | 8.65 | 0 | 0
35401013 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5474 | -119.93 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 0.016323 | Tier 2 & 3 | 1.1652 | 3.15 | 0 | 0 | 0 | 3.15 | 0
35401012 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5582 | -119.9305 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 0.016323 | Tier 2 & 3 | 1.1652 | 3.11 | 0 | 0 | 0 | 3.11 | 0
35401011 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.541 | -119.9184 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 0.016323 | Tier 2 & 3 | 1.1652 | 2.46 | 0 | 0 | 0 | 2.46 | 0
35397963 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.57 | -119.9414 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 0.016323 | Tier 2 & 3 | 1.1652 | 3.88 | 0 | 0 | 3.88 | 0 | 0
35397962 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5616 | -119.9349 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 0.016323 | Tier 2 & 3 | 1.1652 | 4.2 | 0 | 0 | 4.2 | 0 | 0
35382932 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Midpines | Mariposa | 37.5611 | -119.9354 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 0.016323 | Tier 2 & 3 | 1.1652 | 4 | 0 | 0 | 0 | 4 | 0
35379383 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5251 | -119.9182 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 0.016323 | Tier 2 & 3 | 1.1652 | 4.74 | 0 | 0 | 4.74 | 0 | 0
35375721 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5139 | -119.8384 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 0.016323 | Tier 3 | 1.1652 | 0.71004 | 0 | 0 | 0.71004 | 0 | 0
35374681 | Fire Rebuild | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5113 | -119.9076 | WDRM v3 |  | 679 | 0.11431 |  | 126 | 0.016323 | Tier 2 & 3 | 1.1652 | 0.96004 | 0 | 0.96004 | 0 | 0 | 0
35373529 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7444 | -120.6569 | WDRM v3 |  | 1284 | 0.041392 |  | 124 | 0.016427 | Tier 3 | 1.0789 | 8.75 | 0 | 0 | 0 | 8.75 | 0
35373528 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7443 | -120.6579 | WDRM v3 |  | 1284 | 0.041392 |  | 124 | 0.016427 | Tier 3 | 1.0789 | 8.75 | 0 | 0 | 8.75 | 0 | 0
35373527 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7442 | -120.6585 | WDRM v3 |  | 1284 | 0.041392 |  | 124 | 0.016427 | Tier 2 & 3 | 1.0789 | 8.75 | 0 | 0 | 8.75 | 0 | 0
35367412 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7391 | -120.668 | WDRM v3 |  | 1284 | 0.041392 |  | 124 | 0.016427 | Tier 2 & 3 | 1.0789 | 8.19 | 0 | 0 | 0 | 8.19 | 0
35374059 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.3794 | -120.6379 | WDRM v3 |  | 2349 | 0.0030208 |  | 118 | 0.016781 | Tier 2 | 1.2034 | 5.6701 | 0 | 0 | 0 | 5.6701 | 0
35377525 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camptonville | Yuba | 39.454 | -121.0327 | WDRM v3 |  | 1484 | 0.029034 |  | 116 | 0.016874 | Tier 3 | 1.9268 | 6.9701 | 0 | 0 | 0 | 0 | 6.9701
35375450 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camptonville | Yuba | 39.4528 | -121.0297 | WDRM v3 |  | 1484 | 0.029034 |  | 116 | 0.016874 | Tier 3 | 1.9268 | 10.66 | 0 | 0 | 0 | 0 | 10.66
35375449 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | North San Juan | Sierra | 39.4388 | -120.9968 | WDRM v3 |  | 1484 | 0.029034 |  | 116 | 0.016874 | Tier 3 | 1.9268 | 10.85 | 0 | 0 | 0 | 0 | 10.85
35379381 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.9245 | -121.9124 | WDRM v3 |  | 400 | 0.18021 |  | 115 | 0.016899 | Tier 2 & 3 | 1.4864 | 10.4 | 0 | 0 | 0 | 0 | 10.4
35396911 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 38.9913 | -120.8827 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 0.01695 | Tier 3 | 1.0455 | 3.13 | 0 | 0 | 3.13 | 0 | 0
35396910 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 38.9928 | -120.8828 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 0.01695 | Tier 3 | 1.0455 | 2.97 | 0 | 0 | 2.97 | 0 | 0
35396909 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 38.9917 | -120.8912 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 0.01695 | Tier 3 | 1.0455 | 3.01 | 0 | 0 | 3.01 | 0 | 0
35396908 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 38.9994 | -120.8896 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 0.01695 | Tier 3 | 1.0455 | 2.32 | 0 | 0 | 2.32 | 0 | 0
35373533 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 38.9918 | -120.883 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 0.01695 | Tier 3 | 1.0455 | 2.24 | 0 | 2.24 | 0 | 0 | 0
35367478 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.0016 | -120.8905 | WDRM v3 |  | 2270 | 0.0037622 |  | 114 | 0.01695 | Tier 3 | 1.0455 | 2.04 | 0 | 0 | 2.04 | 0 | 0
35383305 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4646 | -120.5292 | WDRM v3 |  | 2468 | 0.0020959 |  | 107 | 0.017455 | Tier 3 | 1.0276 | 4.99 | 0 | 0 | 0 | 0 | 4.99
35367524 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4678 | -120.5277 | WDRM v3 |  | 2468 | 0.0020959 |  | 107 | 0.017455 | Tier 3 | 1.0276 | 14.3201 | 0 | 0 | 0 | 0 | 14.3201
35373597 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Calistoga | Napa | 38.5951 | -122.6024 | WDRM v3 |  | 1005 | 0.066852 |  | 105 | 0.017566 | Tier 3 | 1.287 | 5.0201 | 0 | 0 | 0 | 0 | 5.0201
35367464 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Calistoga | Napa | 38.5891 | -122.6068 | WDRM v3 |  | 1005 | 0.066852 |  | 105 | 0.017566 | Tier 3 | 1.287 | 9.0299 | 0 | 0 | 0 | 0 | 9.0299
35404726 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5572 | -122.4315 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 0.018153 | Tier 3 | 1.072 | 3.88 | 0 | 0 | 3.88 | 0 | 0
35404355 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5532 | -122.4564 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 0.018153 | Tier 3 | 1.072 | 1.113 | 0 | 0 | 0 | 1.113 | 0
35404354 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5582 | -122.4502 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 0.018153 | Tier 3 | 1.072 | 0.862 | 0 | 0 | 0 | 0.862 | 0
35404353 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5587 | -122.4577 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 0.018153 | Tier 3 | 1.072 | 2.096 | 0 | 0 | 0 | 2.096 | 0
35404352 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5578 | -122.4566 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 0.018153 | Tier 3 | 1.072 | 2.029 | 0 | 0 | 2.029 | 0 | 0
35404351 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5575 | -122.452 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 0.018153 | Tier 3 | 1.072 | 1.632 | 0 | 0 | 1.632 | 0 | 0
35373704 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5653 | -122.4415 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 0.018153 | Tier 3 | 1.072 | 3.648 | 0 | 0 | 3.648 | 0 | 0
35367516 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5613 | -122.4612 | WDRM v3 |  | 1254 | 0.043133 |  | 101 | 0.018153 | Tier 3 | 1.072 | 1.358 | 0 | 0 | 0 | 1.358 | 0
35362666 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.9331 | -121.942 | WDRM v3 |  | 2561 | 0.0014894 |  | 100 | 0.018211 | Tier 2 & 3 | 1.0153 | 0.67992 | 0 | 0 | 0 | 0 | 0.67992
35409203 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7253 | -122.6191 | WDRM v3 |  | 314 | 0.20636 |  | 99 | 0.018456 | Tier 2 & 3 | 1.1512 | 1.4 | 0 | 0 | 0 | 0 | 1.4
35418379 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2465 | -120.3642 | WDRM v3 |  | 2810 | 0.00026318 |  | 98 | 0.01848 | Tier 3 | 1.0041 | 8.4875 | 0 | 0 | 0 | 8.4875 | 0
35417148 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.0198 | -120.8509 | WDRM v3 |  | 1301 | 0.040196 |  | 97 | 0.018495 | Tier 3 | 1.3267 | 8.56 | 0 | 0 | 0 | 0 | 8.56
35417144 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.0198 | -120.8509 | WDRM v3 |  | 1301 | 0.040196 |  | 97 | 0.018495 | Tier 3 | 1.3267 | 10.7 | 0 | 0 | 0 | 0 | 10.7
35417117 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.0198 | -120.8509 | WDRM v3 |  | 1301 | 0.040196 |  | 97 | 0.018495 | Tier 3 | 1.3267 | 6.04 | 0 | 0 | 0 | 6.04 | 0
35417110 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Foresthill | Placer | 39.0198 | -120.8509 | WDRM v3 |  | 1301 | 0.040196 |  | 97 | 0.018495 | Tier 3 | 1.3267 | 9.57 | 0 | 0 | 0 | 9.57 | 0
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 |  | 56 | 0.40353 |  | 95 | 0.018647 | Tier 2 & 3 | 1.4369 | 8.975 | 0 | 0 | 0 | 0 | 8.975
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 |  | 56 | 0.40353 |  | 95 | 0.018647 | Tier 2 & 3 | 1.4369 | 8.975 | 0 | 0 | 0 | 8.975 | 0
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 |  | 56 | 0.40353 |  | 95 | 0.018647 | Tier 2 & 3 | 1.4369 | 8.975 | 0 | 0 | 0 | 8.975 | 0
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 |  | 56 | 0.40353 |  | 95 | 0.018647 | Tier 2 & 3 | 1.4369 | 8.975 | 0 | 0 | 0 | 0 | 8.975
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v3 |  | 56 | 0.40353 |  | 95 | 0.018647 | Tier 2 & 3 | 1.4369 | 8.975 | 0 | 0 | 0 | 0 | 8.975
35372463 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Lakehead | Shasta | 40.8947 | -122.3807 | WDRM v3 |  | 2207 | 0.0049349 |  | 94 | 0.0187 | Tier 2 | 1.4879 | 1.99 | 0 | 0 | 0 | 0 | 1.99
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | SI | Region 2 - North East | COLFAX | Placer | 39.1444 | -120.908 | WDRM v3 |  | 2022 | 0.0086414 |  | 93 | 0.018723 | Tier 3 | 1.4369 | 10.9 | 0 | 0 | 0 | 10.9 | 0
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | SI | Region 2 - North East | COLFAX | Placer | 39.1444 | -120.908 | WDRM v3 |  | 2022 | 0.0086414 |  | 93 | 0.018723 | Tier 3 | 1.4369 | 15 | 0 | 0 | 0 | 0 | 15
35395930 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Lakehead | Shasta | 40.9052 | -122.3826 | WDRM v3 |  | 2407 | 0.002519 |  | 91 | 0.018782 | Tier 2 | 1.5 | 0.369 | 0 | 0 | 0 | 0 | 0.369
35395929 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Lakehead | Shasta | 40.905 | -122.3847 | WDRM v3 |  | 2407 | 0.002519 |  | 91 | 0.018782 | Tier 2 | 1.5 | 0.057 | 0 | 0 | 0 | 0 | 0.057
35395928 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Lakehead | Shasta | 40.9066 | -122.3834 | WDRM v3 |  | 2407 | 0.002519 |  | 91 | 0.018782 | Tier 2 | 1.5 | 1.937 | 0 | 0 | 0 | 0 | 1.937
35372464 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Lakehead | Shasta | 40.8994 | -122.3862 | WDRM v3 |  | 2407 | 0.002519 |  | 91 | 0.018782 | Tier 2 | 1.5 | 6.553 | 0 | 0 | 0 | 0 | 6.553
35418356 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | DEER PARK | Napa | 38.5431 | -122.4978 | WDRM v3 |  | 2351 | 0.0030112 |  | 90 | 0.018786 | Tier 3 | 1.5 | 0.4 | 0 | 0 | 0.4 | 0 | 0
35418366 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | COLFAX | Placer | 39.1191 | -120.9513 | WDRM v3 |  | 1378 | 0.034658 |  | 89 | 0.018876 | Tier 3 | 2.1209 | 6.062 | 0 | 0 | 0 | 6.062 | 0
35418361 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | COLFAX | Placer | 39.1191 | -120.9513 | WDRM v3 |  | 1378 | 0.034658 |  | 89 | 0.018876 | Tier 3 | 2.1209 | 6.601 | 0 | 0 | 0 | 0 | 6.601
35376559 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Saint Helena | Napa | 38.5201 | -122.5433 | WDRM v3 |  | 1361 | 0.035763 |  | 87 | 0.018978 | Tier 3 | 1.1846 | 1.21 | 0 | 0 | 0 | 0 | 1.21
35376558 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Saint Helena | Napa | 38.5071 | -122.4907 | WDRM v3 |  | 1361 | 0.035763 |  | 87 | 0.018978 | Tier 3 | 1.1846 | 10.25 | 0 | 0 | 0 | 0 | 10.25
35373620 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7646 | -120.5783 | WDRM v3 |  | 2250 | 0.0041406 |  | 81 | 0.019264 | Tier 3 | 1.2508 | 4.41 | 0 | 0 | 4.41 | 0 | 0
35367468 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7928 | -120.6194 | WDRM v3 |  | 2250 | 0.0041406 |  | 81 | 0.019264 | Tier 3 | 1.2508 | 6.65 | 0 | 0 | 6.65 | 0 | 0
35383758 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Mokelumne Hill | Calaveras | 38.3174 | -120.5211 | WDRM v3 |  | 2247 | 0.0041901 |  | 80 | 0.019265 | Tier 3 | 1.5 | 10.8 | 0 | 0 | 0 | 10.8 | 0
35409211 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | COLFAX | Placer | 39.101 | -120.9597 | WDRM v3 |  | 2201 | 0.00506 |  | 71 | 0.02023 | Tier 2 | 1.4914 | 3.3 | 0 | 0 | 3.3 | 0 | 0
35409205 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Colfax | Placer | 39.1011 | -120.9596 | WDRM v3 |  | 2201 | 0.00506 |  | 71 | 0.02023 | Tier 2 | 1.4914 | 15.2 | 0 | 0 | 0 | 0 | 15.2
35391723 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.811 | -120.8055 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 0.020612 | Tier 3 | 1.339 | 10.0799 | 0 | 0 | 0 | 0 | 10.0799
35391722 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.8089 | -120.8175 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 0.020612 | Tier 3 | 1.339 | 10.0799 | 0 | 0 | 0 | 0 | 10.0799
35391721 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.7978 | -120.8203 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 0.020612 | Tier 3 | 1.339 | 10.0799 | 0 | 0 | 0 | 10.0799 | 0
35391473 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.7837 | -120.8168 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 0.020612 | Tier 2 | 1.339 | 10.0799 | 0 | 0 | 0 | 10.0799 | 0
35391472 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.7794 | -120.8161 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 0.020612 | Tier 2 & 3 | 1.339 | 10.0799 | 0 | 0 | 10.0799 | 0 | 0
35391471 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.7716 | -120.8149 | WDRM v3 |  | 1666 | 0.020262 |  | 68 | 0.020612 | Tier 2 & 3 | 1.339 | 10.7201 | 0 | 0 | 10.7201 | 0 | 0
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | ST | Region 5 - Central Valley | Avery | Calaveras | 38.1832 | -120.3754 | WDRM v3 |  | 1412 | 0.032657 |  | 66 | 0.02064 | Tier 3 | 1.4369 | 8.788 | 0 | 0 | 0 | 8.788 | 0
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | ST | Region 5 - Central Valley | Avery | Calaveras | 38.1832 | -120.3754 | WDRM v3 |  | 1412 | 0.032657 |  | 66 | 0.02064 | Tier 3 | 1.4369 | 15 | 0 | 0 | 0 | 0 | 15
35409217 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Shasta Lake | Shasta | 40.665 | -122.3871 | WDRM v3 |  | 1773 | 0.015387 |  | 64 | 0.0208 | Tier 2 | 2.4472 | 9.7 | 0 | 0 | 0 | 0 | 9.7
35409215 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Shasta Lake | Shasta | 40.6654 | -122.3865 | WDRM v3 |  | 1773 | 0.015387 |  | 64 | 0.0208 | Tier 2 | 2.4472 | 5.1 | 0 | 0 | 0 | 0 | 5.1
35373532 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.6833 | -120.6598 | WDRM v3 |  | 1505 | 0.027532 |  | 63 | 0.020812 | Tier 3 | 1.09 | 8.4701 | 0 | 0 | 8.4701 | 0 | 0
35373530 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.683 | -120.6604 | WDRM v3 |  | 1505 | 0.027532 |  | 63 | 0.020812 | Tier 3 | 1.09 | 15.51 | 0 | 0 | 0 | 0 | 15.51
35367414 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.6829 | -120.6611 | WDRM v3 |  | 1505 | 0.027532 |  | 63 | 0.020812 | Tier 2 & 3 | 1.09 | 9.75 | 0 | 0 | 9.75 | 0 | 0
35404349 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.395 | -120.645 | WDRM v3 |  | 1548 | 0.025302 |  | 62 | 0.020861 | Tier 2 | 1.0693 | 4.47 | 0 | 0 | 0 | 0 | 4.47
35376890 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.364 | -120.6467 | WDRM v3 |  | 1548 | 0.025302 |  | 62 | 0.020861 | Tier 2 | 1.0693 | 7.09 | 0 | 0 | 0 | 0 | 7.09
35372462 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4053 | -120.6461 | WDRM v3 |  | 1548 | 0.025302 |  | 62 | 0.020861 | Tier 2 | 1.0693 | 4.85 | 0 | 0 | 0 | 0 | 4.85
35373628 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.8877 | -121.666 | WDRM v3 |  | 2763 | 0.000401 |  | 61 | 0.020869 | Tier 3 | 1.1147 | 8.7299 | 0 | 0 | 0 | 0 | 8.7299
35367504 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.8877 | -121.6655 | WDRM v3 |  | 2763 | 0.000401 |  | 61 | 0.020869 | Tier 3 | 1.1147 | 9.35 | 0 | 0 | 0 | 0 | 9.35
35418375 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2369 | -120.3646 | WDRM v3 |  | 2670 | 0.0008147 |  | 60 | 0.021109 | Tier 3 | 1.0358 | 10.3875 | 0 | 0 | 0 | 10.3875 | 0
35385804 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5742 | -122.4441 | WDRM v3 |  | 792 | 0.094959 |  | 59 | 0.021383 | Tier 3 | 1.1018 | 11.29 | 0 | 0 | 0 | 0 | 11.29
35385803 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5742 | -122.4441 | WDRM v3 |  | 792 | 0.094959 |  | 59 | 0.021383 | Tier 3 | 1.1018 | 11.29 | 0 | 0 | 0 | 11.29 | 0
35418305 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | PLACERVILLE | El Dorado | 38.7571 | -120.7681 | WDRM v3 |  | 904 | 0.079474 |  | 58 | 0.021398 | Tier 3 | 2.4503 | 8.65 | 0 | 0 | 0 | 0 | 8.65
35418255 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | PLACERVILLE | El Dorado | 38.7571 | -120.7681 | WDRM v3 |  | 904 | 0.079474 |  | 58 | 0.021398 | Tier 3 | 2.4503 | 8.65 | 0 | 0 | 0 | 8.65 | 0
35417127 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | PLACERVILLE | El Dorado | 38.7571 | -120.7681 | WDRM v3 |  | 904 | 0.079474 |  | 58 | 0.021398 | Tier 3 | 2.4503 | 4.9 | 0 | 0 | 0 | 4.9 | 0
35364784 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Chico | Butte | 39.9339 | -121.7255 | WDRM v3 |  | 2537 | 0.0016039 |  | 57 | 0.021521 | Tier 3 | 1.0403 | 7.1701 | 0 | 0 | 0 | 0 | 7.1701
35363720 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Chico | Butte | 39.9339 | -121.7255 | WDRM v3 |  | 2537 | 0.0016039 |  | 57 | 0.021521 | Tier 3 | 1.0403 | 9.59 | 0 | 0 | 0 | 9.59 | 0
35363559 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Chico | Butte | 39.9035 | -121.742 | WDRM v3 |  | 2537 | 0.0016039 |  | 57 | 0.021521 | Tier 3 | 1.0403 | 10.34 | 0 | 0 | 0 | 10.34 | 0
35409202 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7313 | -122.6233 | WDRM v3 |  | 915 | 0.078235 |  | 56 | 0.021686 | Tier 2 & 3 | 1.3284 | 1.2 | 0 | 0 | 0 | 0 | 1.2
35375452 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camptonville | Yuba | 39.4556 | -121.0536 | WDRM v3 |  | 1710 | 0.017864 |  | 52 | 0.02211 | Tier 3 | 1.4588 | 6.9201 | 0 | 0 | 0 | 6.9201 | 0
35374570 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Smartsville | Nevada | 39.2362 | -121.2665 | WDRM v3 |  | 658 | 0.11807 |  | 46 | 0.022999 | Tier 2 | 2.1181 | 7.2799 | 0 | 0 | 0 | 0 | 7.2799
35374569 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Twain | Plumas | 40.0055 | -121.249 | WDRM v3 |  | 378 | 0.1873 |  | 45 | 0.023178 | Tier 2 & 3 | 2.0328 | 0.51004 | 0 | 0 | 0 | 0 | 0.51004
35374567 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Twain | Plumas | 39.9591 | -121.2804 | WDRM v3 |  | 378 | 0.1873 |  | 45 | 0.023178 | Tier 2 & 3 | 2.0328 | 0.43996 | 0 | 0 | 0 | 0 | 0.43996
35374566 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Belden | Plumas | 39.9272 | -121.3169 | WDRM v3 |  | 378 | 0.1873 |  | 45 | 0.023178 | Tier 2 | 2.0328 | 0.11004 | 0 | 0 | 0 | 0 | 0.11004
35374564 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Twain | Plumas | 40.0158 | -121.2239 | WDRM v3 |  | 378 | 0.1873 |  | 45 | 0.023178 | Tier 2 | 2.0328 | 6.79 | 0 | 0 | 0 | 0 | 6.79
35374563 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Twain | Plumas | 40.0153 | -121.2245 | WDRM v3 |  | 378 | 0.1873 |  | 45 | 0.023178 | Tier 2 | 2.0328 | 7.21 | 0 | 0 | 0 | 0 | 7.21
35374443 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Nevada City | Nevada | 39.4367 | -120.815 | WDRM v3 |  | 1700 | 0.018204 |  | 41 | 0.023951 | Tier 3 | 1.8375 | 6.7701 | 0 | 0 | 0 | 0 | 6.7701
35374208 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Nevada City | Nevada | 39.439 | -120.8169 | WDRM v3 |  | 1700 | 0.018204 |  | 41 | 0.023951 | Tier 3 | 1.8375 | 4.89 | 0 | 0 | 0 | 0 | 4.89
35374206 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Nevada City | Nevada | 39.4393 | -120.8173 | WDRM v3 |  | 1700 | 0.018204 |  | 41 | 0.023951 | Tier 3 | 1.8375 | 9.69 | 0 | 0 | 0 | 9.69 | 0
35374205 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Alleghany | Sierra | 39.4634 | -120.843 | WDRM v3 |  | 1700 | 0.018204 |  | 41 | 0.023951 | Tier 3 | 1.8375 | 6.24 | 0 | 0 | 0 | 0 | 6.24
35374204 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Alleghany | Sierra | 39.4637 | -120.8433 | WDRM v3 |  | 1700 | 0.018204 |  | 41 | 0.023951 | Tier 3 | 1.8375 | 6.7201 | 0 | 0 | 0 | 0 | 6.7201
35377520 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Kelseyville | Lake | 38.8481 | -122.7562 | WDRM v3 |  | 328 | 0.19983 |  | 38 | 0.024501 | Tier 3 | 1.0078 | 3.9701 | 0 | 0 | 0 | 0 | 3.9701
35374202 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.839 | -121.7019 | WDRM v3 |  | 1043 | 0.062015 |  | 37 | 0.024521 | Tier 3 | 1.121 | 4.6701 | 0 | 0 | 0 | 0 | 4.6701
35374200 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Forest Ranch | Butte | 39.8389 | -121.702 | WDRM v3 |  | 1043 | 0.062015 |  | 37 | 0.024521 | Tier 3 | 1.121 | 8.04 | 0 | 0 | 0 | 0 | 8.04
35385806 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Deer Park | Napa | 38.5447 | -122.4782 | WDRM v3 |  | 1235 | 0.044601 |  | 33 | 0.025445 | Tier 3 | 1.0717 | 6.69 | 0 | 0 | 0 | 0 | 6.69
35385805 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Deer Park | Napa | 38.5447 | -122.4782 | WDRM v3 |  | 1235 | 0.044601 |  | 33 | 0.025445 | Tier 3 | 1.0717 | 10.74 | 0 | 0 | 0 | 0 | 10.74
TBD | Targeted UG | 3UG | UNSE | Pre-Scoping | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.6817 | -120.6632 | WDRM v3 |  | 178 | 0.2712 |  | 32 | 0.025831 | Tier 3 | 1.4369 | 15.1375 | 0 | 0 | 15.1375 | 0 | 0
35409213 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Camino | El Dorado | 38.7395 | -120.6766 | WDRM v3 |  | 1422 | 0.032289 |  | 30 | 0.025967 | Tier 2 | 1.0982 | 4.7299 | 0 | 0 | 4.7299 | 0 | 0
35367335 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Alta | Placer | 39.2148 | -120.8091 | WDRM v3 |  | 1526 | 0.026396 |  | 20 | 0.02949 | Tier 3 | 1.8121 | 9.7201 | 0 | 0 | 0 | 9.7201 | 0
35365064 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Dutch Flat | Placer | 39.202 | -120.8364 | WDRM v3 |  | 1526 | 0.026396 |  | 20 | 0.02949 | Tier 3 | 1.8121 | 10.34 | 0 | 0 | 0 | 0 | 10.34
35373634 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8569 | -121.6134 | WDRM v3 |  | 2451 | 0.0021922 |  | 17 | 0.031702 | Tier 3 | 1.0224 | 4.4299 | 0 | 0 | 0 | 0 | 4.4299
35373632 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8576 | -121.6133 | WDRM v3 |  | 2451 | 0.0021922 |  | 17 | 0.031702 | Tier 3 | 1.0224 | 10.2299 | 0 | 0 | 0 | 0 | 10.2299
35367508 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8583 | -121.6133 | WDRM v3 |  | 2451 | 0.0021922 |  | 17 | 0.031702 | Tier 3 | 1.0224 | 5.94 | 0 | 0 | 0 | 0 | 5.94
35367507 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Magalia | Butte | 39.8718 | -121.6107 | WDRM v3 |  | 2451 | 0.0021922 |  | 17 | 0.031702 | Tier 3 | 1.0224 | 3.04 | 0 | 0 | 0 | 0 | 3.04
35318072 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1291 | -122.1378 | WDRM v2 |  | 2435 | 0.002283 |  | 1105 | 0.0019396 | Tier 3 | 1.6206 | 0.20114 | 0 | 0.20114 | 0 | 0 | 0
35385802 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.9038 | -121.8741 | WDRM v3 |  | 377 | 0.18755 |  | 15 | 0.034099 | Tier 3 | 1.3819 | 9.6 | 0 | 0 | 0 | 0 | 9.6
35376891 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Angwin | Napa | 38.5754 | -122.4443 | WDRM v3 |  | 1235 | 0.044601 |  | 14 | 0.034265 | Tier 3 | 1.3391 | 4.4 | 0 | 0 | 0 | 0 | 4.4
35373708 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Lakehead | Shasta | 40.8928 | -122.3816 | WDRM v3 |  | 2361 | 0.0028857 |  | 11 | 0.038738 | Tier 2 | 1.4675 | 3.73 | 0 | 0 | 0 | 0 | 3.73
35372465 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Lakehead | Shasta | 40.8936 | -122.3819 | WDRM v3 |  | 2361 | 0.0028857 |  | 11 | 0.038738 | Tier 2 | 1.4675 | 11.84 | 0 | 0 | 0 | 0 | 11.84
35372258 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | El Portal | Mariposa | 37.6771 | -119.7769 | WDRM v3 |  | 555 | 0.14347 |  | 10 | 0.039297 | Tier 2 | 2.4117 | 8.892 | 0 | 0 | 0 | 0 | 8.892
35372257 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | YO | Region 5 - Central Valley | El Portal | Mariposa | 37.6651 | -119.8416 | WDRM v3 |  | 555 | 0.14347 |  | 10 | 0.039297 | Tier 2 | 2.4117 | 9.808 | 0 | 0 | 0 | 0 | 9.808
35372461 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.4492 | -120.492 | WDRM v3 |  | 1744 | 0.016801 |  | 8 | 0.040941 | Tier 2 & 3 | 1.5 | 4.42 | 0 | 0 | 4.42 | 0 | 0
35396763 | Targeted UG | 3UG | ESTS | Estimating | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4129 | -120.6605 | WDRM v3 |  | 2334 | 0.0031502 |  | 6 | 0.047261 | Tier 2 | 1.2202 | 0.88 | 0 | 0 | 0 | 0 | 0.88
35353527 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Magalia | Butte | 39.8221 | -121.5955 | N/A |  | N/A | N/A |  | 1124 | N/A | Tier 3 | N/A | 1.2 | 0 | 0 | 1.2 | 0 | 0
35353525 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Magalia | Butte | 39.8243 | -121.5994 | N/A |  | N/A | N/A |  | 159 | N/A | Tier 3 | N/A | 2.8 | 0 | 0 | 2.8 | 0 | 0
35353479 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Magalia | Butte | 39.8211 | -121.6013 | N/A |  | N/A | N/A |  | 159 | N/A | Tier 3 | N/A | 2.5 | 0 | 0 | 2.5 | 0 | 0
35353477 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Magalia | Butte | 39.8192 | -121.6024 | N/A |  | N/A | N/A |  | 159 | N/A | Tier 3 | N/A | 2.2 | 0 | 0 | 2.2 | 0 | 0
35353470 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Magalia | Butte | 39.8146 | -121.6066 | N/A |  | N/A | N/A |  | 159 | N/A | Tier 3 | N/A | 3.5 | 0 | 0 | 3.5 | 0 | 0
35353468 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Magalia | Butte | 39.8167 | -121.598 | N/A |  | N/A | N/A |  | 159 | N/A | Tier 3 | N/A | 2.5 | 0 | 0 | 2.5 | 0 | 0
35353467 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Magalia | Butte | 39.8182 | -121.5952 | N/A |  | N/A | N/A |  | 1124 | N/A | Tier 3 | N/A | 2.4 | 0 | 2.4 | 0 | 0 | 0
35353466 | Community Rebuild | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Magalia | Butte | 39.8091 | -121.5998 | N/A |  | N/A | N/A |  | 159 | N/A | Tier 3 | N/A | 2.4 | 0 | 2.4 | 0 | 0 | 0
35353463 | Community Rebuild | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Magalia | Butte | 39.8121 | -121.5914 | N/A |  | N/A | N/A |  | 302 | N/A | Tier 3 | N/A | 2.6 | 0 | 0 | 2.6 | 0 | 0
35342338 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.163 | -122.1902 | WDRM v2 |  | 2359 | 0.0029066 |  | 1314 | 0.0013052 | Tier 3 | 1.0861 | 1.24 | 0 | 0 | 0 | 1.24 | 0
35353399 | Community Rebuild | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Magalia | Butte | 39.8082 | -121.5973 | N/A |  | N/A | N/A |  | 302 | N/A | Tier 3 | N/A | 2.3 | 0 | 0 | 2.3 | 0 | 0
35352075 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7777 | -121.6077 | N/A |  | N/A | N/A |  | 809 | N/A | Tier 3 | N/A | 6.1 | 0 | 6.1 | 0 | 0 | 0
35350874 | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.7637 | -121.5732 | N/A |  | N/A | N/A |  | 1617 | N/A | Tier 3 | N/A | 2.5 | 0 | 2.5 | 0 | 0 | 0
35350582 | Community Rebuild | 95F | ESTS | Estimating | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1415 | -120.9483 | N/A |  | N/A | N/A |  | 2135 | N/A | Non-HFTD | N/A | 0.37879 | 0 | 0.37879 | 0 | 0 | 0
35350519 | Community Rebuild | 95F | ESTS | Estimating | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1415 | -120.9483 | N/A |  | N/A | N/A |  | 2135 | N/A | Non-HFTD | N/A | 0.47348 | 0 | 0.47348 | 0 | 0 | 0
35396762 | Targeted UG | 3UG | ESTS | Estimating | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4129 | -120.6605 | WDRM v3 |  | 2334 | 0.0031502 |  | 6 | 0.047261 | Tier 2 | 1.2202 | 2.91 | 0 | 0 | 0 | 0 | 2.91
35342337 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1657 | -122.2231 | WDRM v2 |  | 2359 | 0.0029066 |  | 1314 | 0.0013052 | Tier 3 | 1.0861 | 0.52008 | 0 | 0 | 0 | 0.52008 | 0
35342336 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1699 | -122.2026 | WDRM v2 |  | 2359 | 0.0029066 |  | 1314 | 0.0013052 | Tier 3 | 1.0861 | 1.1201 | 0 | 0 | 1.1201 | 0 | 0
35342335 | Fire Rebuild | 08W | ESTS | Estimating | Y | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1672 | -122.2131 | WDRM v2 |  | 2359 | 0.0029066 |  | 1314 | 0.0013052 | Tier 3 | 1.0861 | 1.5299 | 0 | 0 | 1.5299 | 0 | 0
35334541 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1443 | -122.1579 | WDRM v2 |  | 2358 | 0.002947 |  | 897 | 0.0026407 | Tier 3 | 1.0799 | 0.16629 | 0 | 0.16629 | 0 | 0 | 0
35292789 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 2342 | 0.0030704 |  | 1533 | 0.00093756 | Tier 2 | 1.0393 | 0.1 | 0 | 0.1 | 0 | 0 | 0
35292788 | Fire Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 2342 | 0.0030704 |  | 1533 | 0.00093756 | Tier 2 | 1.0393 | 1.1 | 0 | 1.1 | 0 | 0 | 0
35372259 | Targeted UG | 3UG | UNSE | Scoping/Scoped | Y | ST | Region 5 - Central Valley | Pine Grove | Amador | 38.4129 | -120.6605 | WDRM v3 |  | 2334 | 0.0031502 |  | 6 | 0.047261 | Tier 2 | 1.2202 | 2.84 | 0 | 0 | 0 | 0 | 2.84
35325226 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9868 | -121.8481 | WDRM v2 |  | 2320 | 0.0032735 |  | 394 | 0.0070854 | Tier 2 | 1.428 | 3.5241 | 0 | 0 | 0 | 3.5241 | 0
35325225 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9729 | -121.7814 | WDRM v2 |  | 2320 | 0.0032735 |  | 394 | 0.0070854 | Tier 2 | 1.428 | 3.6396 | 0 | 0 | 0 | 3.6396 | 0
35325224 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Montgomery Creek | Shasta | 41.0088 | -121.7129 | WDRM v2 |  | 2320 | 0.0032735 |  | 394 | 0.0070854 | Tier 2 | 1.428 | 3.284 | 0 | 0 | 0 | 3.284 | 0
35294730 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9685 | -121.8246 | WDRM v2 |  | 2320 | 0.0032735 |  | 394 | 0.0070854 | Tier 2 | 1.428 | 2.9066 | 0 | 0 | 2.9066 | 0 | 0
35294729 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9982 | -121.7479 | WDRM v2 |  | 2320 | 0.0032735 |  | 394 | 0.0070854 | Tier 2 | 1.428 | 3.1407 | 0 | 0 | 0 | 3.1407 | 0
35114040 | Base SH | 08W | CONS | In-Construction | Y | ST | Region 5 - Central Valley | Pioneer | Amador | 38.436 | -120.5559 | WDRM v2 |  | 2271 | 0.0037571 |  | 558 | 0.0048336 | Tier 3 | 2.0641 | 0.093561 | 0.04072 | 0.052841 | 0 | 0 | 0
35318074 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | CC | Region 4 - Central Coast | Davenport | Santa Cruz | 37.072 | -122.2298 | WDRM v2 |  | 2246 | 0.0041981 |  | 936 | 0.002497 | Tier 2 | 1.0031 | 0.29356 | 0 | 0.29356 | 0 | 0 | 0
35321894 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | CC | Region 4 - Central Coast | Davenport | Santa Cruz | 37.0773 | -122.2434 | WDRM v2 |  | 2199 | 0.0051004 |  | 2216 | 0.00042654 | Tier 2 | 1.0744 | 0.13826 | 0 | 0.13826 | 0 | 0 | 0
35297464 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | CC | Region 4 - Central Coast | Davenport | Santa Cruz | 37.0777 | -122.2439 | WDRM v2 |  | 2199 | 0.0051004 |  | 2216 | 0.00042654 | Tier 2 | 1.0744 | 1.0021 | 0 | 1.0021 | 0 | 0 | 0
35284810 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | PN | Region 3 - Bay Area | Pescadero | San Mateo | 37.2086 | -122.3251 | WDRM v2 |  | 2186 | 0.0054078 |  | 2434 | 0.00033154 | Tier 2 | 1.134 | 0.85814 | 0 | 0 | 0.85814 | 0 | 0
35219543 | Base SH | 08W | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.7293 | -120.7998 | WDRM v2 |  | 2123 | 0.0065148 |  | 1979 | 0.00055552 | Tier 2 | 1.5 | 0.24 | 0 | 0.24 | 0 | 0 | 0
35342339 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | CC | Region 4 - Central Coast | Boulder Creek | Santa Cruz | 37.1837 | -122.1598 | WDRM v2 |  | 2070 | 0.0075562 |  | 1413 | 0.0011281 | Tier 3 | 1.1797 | 0.16193 | 0 | 0.16193 | 0 | 0 | 0
35217275 | Fire Rebuild | 08W | CONS | In-Construction | Y | CC | Region 3 - Bay Area | Pescadero | San Mateo | 37.2551 | -122.3815 | WDRM v2 |  | 2055 | 0.0078448 |  | 2554 | 0.0002898 | Tier 2 | 1.1062 | 2.7439 | 0 | 2.7439 | 0 | 0 | 0
35217274 | Fire Rebuild | 08W | CONS | In-Construction | Y | PN | Region 3 - Bay Area | Pescadero | San Mateo | 37.2551 | -122.3815 | WDRM v2 |  | 2055 | 0.0078448 |  | 2554 | 0.0002898 | Tier 2 | 1.1062 | 2.5239 | 1.6411 | 0 | 0.88277 | 0 | 0
35228775 | Base SH | 08W | PEND | Permitting/Dependency | Y | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4438 | -122.602 | WDRM v2 |  | 2048 | 0.007993 |  | 3020 | 0.00012812 | Tier 2 | 1.4835 | 0.90341 | 0 | 0 | 0.90341 | 0 | 0
35228774 | Base SH | 08W | ESTS | Estimating | Y | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4438 | -122.602 | WDRM v2 |  | 2048 | 0.007993 |  | 3020 | 0.00012812 | Tier 2 | 1.4835 | 1.0008 | 0 | 0 | 1.0008 | 0 | 0
35223063 | Base SH | 08W | PEND | Permitting/Dependency | Y | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4438 | -122.602 | WDRM v2 |  | 2048 | 0.007993 |  | 3020 | 0.00012812 | Tier 2 | 1.4835 | 0.3197 | 0 | 0.3197 | 0 | 0 | 0
35285594 | Fire Rebuild | 08W | ESTS | Estimating | Y | SI | Region 2 - North East | Twin Bridges | El Dorado | 38.8075 | -120.0935 | WDRM v2 |  | 2005 | 0.0089565 |  | 2299 | 0.00038767 | Tier 2 | 2.7059 | 0.21989 | 0 | 0 | 0.21989 | 0 | 0
35109546 | Base SH | 08W | DOCC | In-Construction | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.692 | -120.6132 | WDRM v2 |  | 1946 | 0.0103 |  | 49 | 0.022482 | Tier 3 | 1.1349 | 0.44621 | 0.44621 | 0 | 0 | 0 | 0
35109541 | Base SH | 08W | CONS | In-Construction | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.6839 | -120.6354 | WDRM v2 |  | 1946 | 0.0103 |  | 49 | 0.022482 | Tier 3 | 1.1349 | 0.37955 | 0.04072 | 0.33883 | 0 | 0 | 0
35057010 | Base SH | 08W | PEND | Permitting/Dependency | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7821 | -120.6094 | WDRM v2 |  | 1946 | 0.0103 |  | 49 | 0.022482 | Tier 3 | 1.1349 | 2.2513 | 0 | 2.2513 | 0 | 0 | 0
35056733 | Base SH | 08W | CONS | In-Construction | Y | SI | Region 2 - North East | Pollock Pines | El Dorado | 38.7821 | -120.6094 | WDRM v2 |  | 1946 | 0.0103 |  | 49 | 0.022482 | Tier 3 | 1.1349 | 0.57576 | 0 | 0 | 0.57576 | 0 | 0
35320462 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.2642 | -122.1295 | WDRM v2 |  | 1848 | 0.012819 |  | 8953 |  | Tier 2 | 1.4976 | 0.34508 | 0 | 0 | 0.34508 | 0 | 0
35343741 | Base SH | 08W | ESTS | Estimating | Y | SO | Region 1 - North Coast | Sonoma | Sonoma | 38.3371 | -122.4929 | WDRM v2 |  | 1827 | 0.01369 |  | 440 | 0.0063584 | Tier 2 & 3 | 1.2699 | 0.58 | 0 | 0 | 0.58 | 0 | 0
35312542 | Base SH | 08W | ESTS | Estimating | Y | SO | Region 1 - North Coast | Glen Ellen | Sonoma | 38.3791 | -122.5192 | WDRM v2 |  | 1827 | 0.01369 |  | 440 | 0.0063584 | Tier 2 & 3 | 1.2699 | 0.77 | 0 | 0 | 0.77 | 0 | 0
35294728 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Montgomery Creek | Shasta | 40.9982 | -121.7478 | WDRM v2 |  | 1816 | 0.01407 |  | 326 | 0.0086689 | Tier 2 | 1.5 | 1.893 | 0 | 0 | 0 | 1.893 | 0
35281758 | Fire Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Twain | Plumas | 40.0222 | -121.0643 | WDRM v2 |  | 1748 | 0.016728 |  | 521 | 0.0051671 | Tier 2 | 1.5247 | 1.4 | 0 | 1.4 | 0 | 0 | 0
35145001 | Base SH | 08W | CONS | In-Construction | Y | DI | Region 3 - Bay Area | Concord | Contra Costa | 37.931 | -121.9736 | WDRM v2 |  | 1739 | 0.016935 |  | 1812 | 0.0006705 | Tier 2 & 3 | 1.08 | 1.8845 | 0 | 0 | 1.8845 | 0 | 0
35329013 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.6805 | -121.5693 | WDRM v2 |  | 1703 | 0.018088 |  | 933 | 0.0025042 | Tier 2 | 1.9074 | 1.85 | 0 | 1.85 | 0 | 0 | 0
35329012 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.6908 | -121.5733 | WDRM v2 |  | 1703 | 0.018088 |  | 1009 | 0.0022353 | Tier 2 | 1.5526 | 1.6201 | 0 | 1.6201 | 0 | 0 | 0
35299633 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Oroville | Butte | 39.6766 | -121.5675 | WDRM v2 |  | 1703 | 0.018088 |  | 1009 | 0.0022353 | Tier 2 | 1.5526 | 2.14 | 0 | 2.14 | 0 | 0 | 0
35284023 | Fire Rebuild | 08W | ESTS | Estimating | Y | SO | Region 1 - North Coast | Santa Rosa | Sonoma | 38.4361 | -122.5779 | WDRM v2 |  | 1684 | 0.019316 |  | 732 | 0.0035071 | Tier 3 | 1.5377 | 1.1699 | 0 | 0 | 1.1699 | 0 | 0
35335235 | Base SH | 08W | UNSE | Scoping/Scoped | Y | NB | Region 1 - North Coast | Saint Helena | Napa | 38.5192 | -122.4719 | WDRM v2 |  | 1648 | 0.02118 |  | 619 | 0.0043024 | Tier 3 | 1.1021 | 3.5799 | 0 | 0 | 3.5799 | 0 | 0
35280505 | Other | 30A | ESTS | Estimating | Y | NV | Region 2 - North East | Shasta | Shasta | 40.5923 | -122.4836 | WDRM v2 |  | 1614 | 0.022607 |  | 43 | 0.023649 | Tier 3 | 2.6214 | 0.37879 | 0 | 0 | 0 | 0 | 0.37879
35224856 | Other | 10K | CONS | In-Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.7352 | -121.6113 | WDRM v2 |  | 1537 | 0.025842 |  | 362 | 0.0076725 | Tier 2 & 3 | 1.036 | 2.4956 | 0 | 0 | 2.4956 | 0 | 0
35329016 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.709 | -121.5757 | WDRM v2 |  | 1535 | 0.025936 |  | 47 | 0.022808 | Tier 2 | 1.0016 | 3.54 | 0 | 3.54 | 0 | 0 | 0
35299635 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.6988 | -121.5743 | WDRM v2 |  | 1535 | 0.025936 |  | 47 | 0.022808 | Tier 2 | 1.0016 | 2.24 | 0 | 2.24 | 0 | 0 | 0
35236985 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Oroville | Butte | 39.5762 | -121.3051 | WDRM v2 |  | 1480 | 0.029281 |  | 212 | 0.01209 | Tier 3 | 2.6372 | 2.0655 | 0 | 2.0655 | 0 | 0 | 0
35334407 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.7875 | -123.4468 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0.0024804 | Tier 2 | 1.8796 | 0.089962 | 0 | 0.089962 | 0 | 0 | 0
35320466 | Base SH | 08W | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Salyer | Trinity | 40.8669 | -123.5148 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0.0024804 | Tier 2 | 1.8796 | 2 | 0 | 0 | 0 | 2 | 0
35297699 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0.0024804 | Tier 2 | 1.8796 | 1.0199 | 0 | 1.0199 | 0 | 0 | 0
35297697 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0.0024804 | Tier 2 | 1.8796 | 0.014773 | 0 | 0.014773 | 0 | 0 | 0
35297696 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0.0024804 | Tier 2 | 1.8796 | 0.78996 | 0 | 0.78996 | 0 | 0 | 0
35297695 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0.0024804 | Tier 2 | 1.8796 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0
35297694 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0.0024804 | Tier 2 | 1.8796 | 0.95 | 0 | 0.95 | 0 | 0 | 0
35297693 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0.0024804 | Tier 2 | 1.8796 | 1 | 0 | 1 | 0 | 0 | 0
35297692 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0.0024804 | Tier 2 | 1.8796 | 4.6598 | 0 | 4.6598 | 0 | 0 | 0
35281815 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Burnt Ranch | Trinity | 40.8422 | -123.485 | WDRM v2 |  | 1474 | 0.029513 |  | 938 | 0.0024804 | Tier 2 | 1.8796 | 0.45985 | 0 | 0.45985 | 0 | 0 | 0
35233996 | Base SH | 08W | CONS | In-Construction | Y | SI | Region 2 - North East | Georgetown | El Dorado | 38.9063 | -120.837 | WDRM v2 |  | 1363 | 0.035529 |  | 277 | 0.0099544 | Tier 3 | 1.2536 | 0.84962 | 0 | 0.84962 | 0 | 0 | 0
35233995 | Base SH | 08W | CONS | In-Construction | Y | SI | Region 2 - North East | Georgetown | El Dorado | 38.905 | -120.8401 | WDRM v2 |  | 1363 | 0.035529 |  | 277 | 0.0099544 | Tier 3 | 1.2536 | 0.73144 | 0 | 0.73144 | 0 | 0 | 0
35290517 | Fire Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Crescent Mills | Plumas | 40.0553 | -120.9636 | WDRM v2 |  | 1322 | 0.038702 |  | 1064 | 0.0020497 | Tier 2 | 1.7495 | 0.86989 | 0 | 0.86989 | 0 | 0 | 0
35282166 | Fire Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Crescent Mills | Plumas | 40.0604 | -120.9643 | WDRM v2 |  | 1322 | 0.038702 |  | 1064 | 0.0020497 | Tier 2 | 1.7495 | 2.5902 | 0 | 2.5902 | 0 | 0 | 0
35145540 | Base SH | 08W | PEND | Permitting/Dependency | Y | ST | Region 5 - Central Valley | Angels Camp | Calaveras | 38.0453 | -120.5253 | WDRM v2 |  | 1316 | 0.039234 |  | 1205 | 0.0016222 | Tier 3 | 2.9322 | 0.53447 | 0 | 0.53447 | 0 | 0 | 0
35241077 | Fire Rebuild | 08W | UNSC | Ready for Construction | Y | NV | Region 2 - North East | Berry Creek | Butte | 39.6348 | -121.3915 | WDRM v2 |  | 1299 | 0.040282 |  | 526 | 0.0051219 | Tier 3 | 1.4338 | 0.31004 | 0 | 0.31004 | 0 | 0 | 0
35241076 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Berry Creek | Butte | 39.6348 | -121.3915 | WDRM v2 |  | 1299 | 0.040282 |  | 526 | 0.0051219 | Tier 3 | 1.4338 | 0.11004 | 0 | 0.11004 | 0 | 0 | 0
35241075 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Berry Creek | Butte | 39.6348 | -121.3915 | WDRM v2 |  | 1299 | 0.040282 |  | 526 | 0.0051219 | Tier 3 | 1.4338 | 0.070076 | 0 | 0.070076 | 0 | 0 | 0
35237889 | Fire Rebuild | 08W | DOCC | In-Construction | Y | NV | Region 2 - North East | Berry Creek | Butte | 39.6343 | -121.4112 | WDRM v2 |  | 1299 | 0.040282 |  | 250 | 0.010796 | Tier 3 | 2.7309 | 1.8256 | 1.8193 | 0.00625 | 0 | 0 | 0
35236997 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Berry Creek | Butte | 39.6827 | -121.3105 | WDRM v2 |  | 1299 | 0.040282 |  | 526 | 0.0051219 | Tier 3 | 1.4338 | 0.28409 | 0 | 0.28409 | 0 | 0 | 0
35235675 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Berry Creek | Butte | 39.655 | -121.459 | WDRM v2 |  | 1299 | 0.040282 |  | 526 | 0.0051219 | Tier 3 | 1.4338 | 0.11364 | 0 | 0.11364 | 0 | 0 | 0
35235672 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Berry Creek | Butte | 39.5852 | -121.4309 | WDRM v2 |  | 1299 | 0.040282 |  | 526 | 0.0051219 | Tier 3 | 1.4338 | 0.30303 | 0 | 0.30303 | 0 | 0 | 0
35292791 | Fire Rebuild | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 1285 | 0.041237 |  | 2987 | 0.00013567 | Tier 2 | 1.3648 | 0.11932 | 0 | 0.11932 | 0 | 0 | 0
35279307 | Fire Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Quincy | Plumas | 40.0075 | -120.9605 | WDRM v2 |  | 1172 | 0.050559 |  | 785 | 0.0031715 | Tier 2 & 3 | 1.4657 | 2.25 | 0 | 2.25 | 0 | 0 | 0
35332870 | Base SH | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Sonora | Tuolumne | 37.9737 | -120.3714 | WDRM v2 |  | 1166 | 0.051116 |  | 1018 | 0.0021952 | Tier 2 | 2.9144 | 0.38674 | 0 | 0.38674 | 0 | 0 | 0
35332868 | Base SH | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Sonora | Tuolumne | 37.9803 | -120.337 | WDRM v2 |  | 1166 | 0.051116 |  | 1018 | 0.0021952 | Tier 2 | 2.9144 | 2.5299 | 0 | 2.5299 | 0 | 0 | 0
35312541 | Base SH | 08W | ADER | Estimating | Y | YO | Region 5 - Central Valley | Sonora | Tuolumne | 37.9777 | -120.3274 | WDRM v2 |  | 1166 | 0.051116 |  | 1018 | 0.0021952 | Tier 2 | 2.9144 | 0.42992 | 0 | 0.42992 | 0 | 0 | 0
35283938 | Base SH | 08W | PEND | Permitting/Dependency | Y | PN | Region 3 - Bay Area | Redwood City | San Mateo | 37.3845 | -122.2937 | WDRM v2 |  | 1145 | 0.05299 |  | 1026 | 0.0021738 | Tier 3 | 1.1831 | 1.1939 | 0 | 0 | 1.1939 | 0 | 0
35320444 | Base SH | 08W | UNSE | Scoping/Scoped | Y | LP | Region 4 - Central Coast | San Luis Obispo | San Luis Obispo | 35.2683 | -120.6383 | WDRM v2 |  | 1104 | 0.056447 |  | 1903 | 0.00059698 | Tier 2 | 1.0458 | 0.48 | 0 | 0 | 0.48 | 0 | 0
35338402 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4214 | -122.2578 | WDRM v2 |  | 1038 | 0.062374 |  | 3890 | 5.6461e-05 | Tier 2 | 1.4741 | 0.42008 | 0 | 0.42008 | 0 | 0 | 0
35320464 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4267 | -122.2656 | WDRM v2 |  | 1038 | 0.062374 |  | 3890 | 5.6461e-05 | Tier 2 | 1.4741 | 0.15 | 0 | 0.15 | 0 | 0 | 0
35384087 | Base SH | 08W | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Oroville | Butte | 39.6578 | -121.5657 | WDRM v2 |  | 1033 | 0.063106 |  | 711 | 0.0036217 | Tier 2 | 1.5 | 0.47992 | 0 | 0 | 0 | 0.47992 | 0
35329014 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Oroville | Butte | 39.6666 | -121.5712 | WDRM v2 |  | 1033 | 0.063106 |  | 711 | 0.0036217 | Tier 2 | 1.5 | 3.1701 | 0 | 3.1701 | 0 | 0 | 0
35299634 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Oroville | Butte | 39.6568 | -121.5763 | WDRM v2 |  | 1033 | 0.063106 |  | 711 | 0.0036217 | Tier 2 | 1.5 | 2.2799 | 0 | 2.2799 | 0 | 0 | 0
35234526 | Base SH | 08W | CONS | In-Construction | Y | ST | Region 5 - Central Valley | Sutter Creek | Amador | 38.3949 | -120.804 | WDRM v2 |  | 999 | 0.067405 |  | 2578 | 0.0002828 | Tier 2 | 1.4721 | 1.225 | 0 | 0 | 1.225 | 0 | 0
35292784 | Fire Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 995 | 0.067786 |  | 2135 | 0.00047036 | Tier 2 | 1.5572 | 3.0644 | 0 | 3.0644 | 0 | 0 | 0
35292780 | Fire Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 995 | 0.067786 |  | 2135 | 0.00047036 | Tier 2 | 1.5572 | 0.17159 | 0 | 0.17159 | 0 | 0 | 0
35290944 | Fire Rebuild | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 995 | 0.067786 |  | 2135 | 0.00047036 | Tier 2 | 1.5572 | 0.49451 | 0 | 0.49451 | 0 | 0 | 0
35290544 | Fire Rebuild | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 995 | 0.067786 |  | 2135 | 0.00047036 | Tier 2 | 1.5572 | 0.97992 | 0 | 0.97992 | 0 | 0 | 0
35290542 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 995 | 0.067786 |  | 2135 | 0.00047036 | Tier 2 | 1.5572 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0
35343397 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Oroville | Butte | 39.5082 | -121.5038 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0.00070123 | Tier 2 | 1.5 | 0.84 | 0 | 0 | 0.84 | 0 | 0
35343396 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Oroville | Butte | 39.52 | -121.4943 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0.00070123 | Tier 2 | 1.5 | 1.0822 | 0 | 1.0822 | 0 | 0 | 0
35343395 | Base SH | 08W | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Oroville | Butte | 39.5168 | -121.4943 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0.00070123 | Tier 2 | 1.5 | 1.76 | 0 | 1.76 | 0 | 0 | 0
35343394 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Oroville | Butte | 39.5152 | -121.4932 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0.00070123 | Tier 2 | 1.5 | 1.17 | 0 | 1.17 | 0 | 0 | 0
35331308 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Oroville | Butte | 39.5171 | -121.4825 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0.00070123 | Tier 2 | 1.5 | 0.82 | 0 | 0.82 | 0 | 0 | 0
35331307 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Oroville | Butte | 39.5261 | -121.4815 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0.00070123 | Tier 2 | 1.5 | 2.55 | 0 | 2.55 | 0 | 0 | 0
35331306 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Oroville | Butte | 39.5178 | -121.4854 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0.00070123 | Tier 2 | 1.5 | 2.67 | 0 | 0 | 2.67 | 0 | 0
35312560 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Oroville | Butte | 39.5054 | -121.4999 | WDRM v2 |  | 976 | 0.070566 |  | 1779 | 0.00070123 | Tier 2 | 1.5 | 3.61 | 0 | 3.61 | 0 | 0 | 0
35254947 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Paynes Creek | Tehama | 40.351 | -121.7811 | WDRM v2 |  | 966 | 0.071922 |  | 281 | 0.0099219 | Tier 2 | 1.0655 | 0.263 | 0 | 0.263 | 0 | 0 | 0
35254945 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Paynes Creek | Tehama | 40.351 | -121.7811 | WDRM v2 |  | 966 | 0.071922 |  | 281 | 0.0099219 | Tier 2 | 1.0655 | 0.51 | 0 | 0.51 | 0 | 0 | 0
35292756 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 916 | 0.077859 |  | 575 | 0.0046735 | Tier 2 | 1.5978 | 1.2786 | 0 | 1.2786 | 0 | 0 | 0
35292755 | Fire Rebuild | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 916 | 0.077859 |  | 575 | 0.0046735 | Tier 2 | 1.5978 | 2.6481 | 0 | 2.6481 | 0 | 0 | 0
35292754 | Fire Rebuild | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 916 | 0.077859 |  | 575 | 0.0046735 | Tier 2 | 1.5978 | 4.0852 | 0 | 4.0852 | 0 | 0 | 0
35290540 | Fire Rebuild | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 916 | 0.077859 |  | 575 | 0.0046735 | Tier 2 | 1.5978 | 1.2858 | 0 | 1.2858 | 0 | 0 | 0
35280493 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 916 | 0.077859 |  | 575 | 0.0046735 | Tier 2 | 1.5978 | 0.35 | 0 | 0.35 | 0 | 0 | 0
35279985 | Fire Rebuild | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Chester | Plumas | 40.2927 | -121.2429 | WDRM v2 |  | 916 | 0.077859 |  | 575 | 0.0046735 | Tier 2 | 1.5978 | 3.115 | 0 | 3.115 | 0 | 0 | 0
35280496 | Fire Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1581 | -121.081 | WDRM v2 |  | 895 | 0.080308 |  | 854 | 0.0028532 | Tier 2 | 1.363 | 0.82008 | 0 | 0.82008 | 0 | 0 | 0
35297984 | Fire Rebuild | 08W | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Redding | Shasta | 40.6951 | -122.3174 | WDRM v2 |  | 851 | 0.085979 |  | 2266 | 0.00040165 | Tier 2 | 2.7366 | 1.1201 | 0 | 0 | 0 | 0 | 1.1201
74010582 | Other | 30A | PEND | Permitting/Dependency | Y | SI | Region 2 - North East | Placerville | El Dorado | 38.726 | -120.8396 | WDRM v2 |  | 811 | 0.092281 |  | 1184 | 0.0016787 | Tier 2 | 2.0901 | 1.3299 | 0 | 0 | 1.3299 | 0 | 0
35342151 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.2491 | -122.1769 | WDRM v2 |  | 739 | 0.104 |  | 313 | 0.0089196 | Tier 2 | 1.4242 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0
35342148 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.2714 | -122.1672 | WDRM v2 |  | 739 | 0.104 |  | 313 | 0.0089196 | Tier 2 | 1.4242 | 1.19 | 0 | 1.19 | 0 | 0 | 0
35342147 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.2706 | -122.167 | WDRM v2 |  | 739 | 0.104 |  | 313 | 0.0089196 | Tier 2 | 1.4242 | 1.8259 | 0 | 1.8259 | 0 | 0 | 0
35342146 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.262 | -122.1635 | WDRM v2 |  | 739 | 0.104 |  | 313 | 0.0089196 | Tier 2 | 1.4242 | 2.397 | 0 | 2.397 | 0 | 0 | 0
35342145 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.2565 | -122.1688 | WDRM v2 |  | 739 | 0.104 |  | 313 | 0.0089196 | Tier 2 | 1.4242 | 0.16307 | 0 | 0.16307 | 0 | 0 | 0
35342144 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.2553 | -122.1615 | WDRM v2 |  | 739 | 0.104 |  | 313 | 0.0089196 | Tier 2 | 1.4242 | 1.617 | 0 | 1.617 | 0 | 0 | 0
35342143 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.2645 | -122.1722 | WDRM v2 |  | 739 | 0.104 |  | 313 | 0.0089196 | Tier 2 | 1.4242 | 3.2771 | 0 | 3.2771 | 0 | 0 | 0
35320442 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.2515 | -122.161 | WDRM v2 |  | 739 | 0.104 |  | 313 | 0.0089196 | Tier 2 | 1.4242 | 0.38693 | 0 | 0.38693 | 0 | 0 | 0
35337015 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.2533 | -122.1356 | WDRM v2 |  | 724 | 0.10731 |  | 1928 | 0.00057842 | Tier 2 | 1.4988 | 0.48996 | 0 | 0.48996 | 0 | 0 | 0
35337014 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.2525 | -122.144 | WDRM v2 |  | 724 | 0.10731 |  | 1928 | 0.00057842 | Tier 2 | 1.4988 | 0.020076 | 0 | 0.020076 | 0 | 0 | 0
35329011 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Oroville | Butte | 39.6667 | -121.5826 | WDRM v2 |  | 698 | 0.11218 |  | 1028 | 0.0021691 | Tier 2 | 1.1292 | 2.3229 | 0 | 2.3229 | 0 | 0 | 0
35329010 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Oroville | Butte | 39.6564 | -121.5838 | WDRM v2 |  | 698 | 0.11218 |  | 1028 | 0.0021691 | Tier 2 | 1.1292 | 2.814 | 0 | 2.814 | 0 | 0 | 0
35329009 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Oroville | Butte | 39.655 | -121.5839 | WDRM v2 |  | 698 | 0.11218 |  | 1028 | 0.0021691 | Tier 2 | 1.1292 | 0.94091 | 0 | 0.94091 | 0 | 0 | 0
35299631 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Oroville | Butte | 39.6474 | -121.6306 | WDRM v2 |  | 698 | 0.11218 |  | 1028 | 0.0021691 | Tier 2 | 1.1292 | 3.4299 | 0 | 3.4299 | 0 | 0 | 0
35342310 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8814 | -118.9012 | WDRM v2 |  | 691 | 0.11269 |  | 368 | 0.0075263 | Tier 2 | 2.6129 | 1.357 | 0 | 0 | 0 | 0 | 1.357
35342308 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8868 | -118.9361 | WDRM v2 |  | 691 | 0.11269 |  | 368 | 0.0075263 | Tier 2 | 2.6129 | 2.997 | 0 | 0 | 0 | 0 | 2.997
35342307 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8833 | -118.9271 | WDRM v2 |  | 691 | 0.11269 |  | 368 | 0.0075263 | Tier 2 | 2.6129 | 2.252 | 0 | 0 | 0 | 0 | 2.252
35335289 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8908 | -118.9154 | WDRM v2 |  | 691 | 0.11269 |  | 368 | 0.0075263 | Tier 2 | 2.6129 | 1.5775 | 0 | 0 | 0 | 0 | 1.5775
35335288 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.9158 | -118.9258 | WDRM v2 |  | 691 | 0.11269 |  | 368 | 0.0075263 | Tier 2 | 2.6129 | 3.6 | 0 | 0 | 0 | 3.6 | 0
35321445 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8908 | -118.9154 | WDRM v2 |  | 691 | 0.11269 |  | 368 | 0.0075263 | Tier 2 | 2.6129 | 2.958 | 0 | 0 | 0 | 2.958 | 0
35312554 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.9321 | -118.9283 | WDRM v2 |  | 691 | 0.11269 |  | 368 | 0.0075263 | Tier 2 | 2.6129 | 1.6 | 0 | 0 | 0 | 1.6 | 0
35339665 | Base SH | 08W | ESTS | Estimating | Y | SI | Region 2 - North East | Loomis | Placer | 38.767 | -121.1634 | WDRM v2 |  | 661 | 0.11734 |  | 2556 | 0.00028839 | Tier 2 | 3 | 0.75909 | 0 | 0.75909 | 0 | 0 | 0
35339664 | Base SH | 08W | ESTS | Estimating | Y | SI | Region 2 - North East | Loomis | Placer | 38.7815 | -121.1632 | WDRM v2 |  | 661 | 0.11734 |  | 2556 | 0.00028839 | Tier 2 | 3 | 0.17008 | 0 | 0.17008 | 0 | 0 | 0
35320447 | Base SH | 08W | ESTS | Estimating | Y | SI | Region 2 - North East | Granite Bay | Placer | 38.782 | -121.1456 | WDRM v2 |  | 661 | 0.11734 |  | 2556 | 0.00028839 | Tier 2 | 3 | 0.83996 | 0 | 0.83996 | 0 | 0 | 0
35335287 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8466 | -118.8987 | WDRM v2 |  | 642 | 0.12034 |  | 72 | 0.020158 | Tier 2 | 3 | 2.1799 | 0 | 0 | 2.1799 | 0 | 0
35335286 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8542 | -118.893 | WDRM v2 |  | 642 | 0.12034 |  | 72 | 0.020158 | Tier 2 | 3 | 5.21 | 0 | 0 | 5.21 | 0 | 0
35312553 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8582 | -118.8837 | WDRM v2 |  | 642 | 0.12034 |  | 72 | 0.020158 | Tier 2 | 3 | 2.39 | 0 | 0 | 2.39 | 0 | 0
35332866 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4668 | -122.3357 | WDRM v2 |  | 590 | 0.13388 |  | 2153 | 0.00046034 | Tier 2 | 1.4456 | 1.01 | 0 | 1.01 | 0 | 0 | 0
35312549 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Redding | Shasta | 40.4913 | -122.2744 | WDRM v2 |  | 590 | 0.13388 |  | 2901 | 0.00016206 | Tier 2 | 1.0306 | 0.98 | 0 | 0.98 | 0 | 0 | 0
35342318 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8363 | -118.8637 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 0.011818 | Tier 2 | 2.5465 | 4.508 | 0 | 0 | 0 | 4.508 | 0
35342317 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8295 | -118.8723 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 0.011818 | Tier 2 | 2.5465 | 2.604 | 0 | 0 | 0 | 2.604 | 0
35342316 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.837 | -118.8663 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 0.011818 | Tier 2 | 2.5465 | 2.443 | 0 | 0 | 0 | 2.443 | 0
35342315 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8407 | -118.8677 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 0.011818 | Tier 2 | 2.5465 | 1.723 | 0 | 0 | 0 | 1.723 | 0
35342314 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8594 | -118.8797 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 0.011818 | Tier 2 | 2.5465 | 0.421 | 0 | 0 | 0 | 0.421 | 0
35342313 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8582 | -118.8835 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 0.011818 | Tier 2 | 2.5465 | 2.902 | 0 | 0 | 2.902 | 0 | 0
35342312 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8726 | -118.8905 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 0.011818 | Tier 2 | 2.5465 | 1.591 | 0 | 0 | 1.591 | 0 | 0
35342311 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8765 | -118.8926 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 0.011818 | Tier 2 | 2.5465 | 2.174 | 0 | 0 | 2.174 | 0 | 0
35320607 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.846 | -118.872 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 0.011818 | Tier 2 | 2.5465 | 2.8129 | 0 | 0 | 2.8129 | 0 | 0
35312555 | Base SH | 08W | UNSE | Scoping/Scoped | Y | KE | Region 5 - Central Valley | Lebec | Kern | 34.8814 | -118.9012 | WDRM v2 |  | 583 | 0.1353 |  | 219 | 0.011818 | Tier 2 | 2.5465 | 1.979 | 0 | 0 | 1.979 | 0 | 0
35364448 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0.0036607 | Tier 2 | 1.1153 | 3.2201 | 0 | 0 | 0 | 3.2201 | 0
35364446 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0.0036607 | Tier 2 | 1.1153 | 2.5381 | 0 | 0 | 0 | 0 | 2.5381
35364442 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0.0036607 | Tier 2 | 1.1153 | 4.621 | 0 | 0 | 4.621 | 0 | 0
35364440 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0.0036607 | Tier 2 | 1.1153 | 2.8689 | 0 | 0 | 0 | 0 | 2.8689
35364339 | Base SH | 08W | UNSE | Scoping/Scoped | Y | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0.0036607 | Tier 2 | 1.1153 | 2.746 | 0 | 0 | 2.746 | 0 | 0
35364337 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0.0036607 | Tier 2 | 1.1153 | 2.5091 | 0 | 0 | 2.5091 | 0 | 0
35364336 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0.0036607 | Tier 2 | 1.1153 | 1.8561 | 0 | 0 | 0 | 0 | 1.8561
35364334 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0.0036607 | Tier 2 | 1.1153 | 2.1591 | 0 | 0 | 2.1591 | 0 | 0
35364333 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0.0036607 | Tier 2 | 1.1153 | 2.8131 | 0 | 0 | 0 | 0 | 2.8131
35364332 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paynes Creek | Tehama | 40.3452 | -121.8922 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0.0036607 | Tier 2 | 1.1153 | 2.4159 | 0 | 0 | 0 | 2.4159 | 0
35316201 | Community Rebuild | 95F | ESTS | Estimating | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1397 | -120.9389 | N/A |  | N/A | N/A |  | 2135 | N/A | Non-HFTD | N/A | 0.68314 | 0 | 0.68314 | 0 | 0 | 0
35316200 | Community Rebuild | 95F | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1413 | -120.957 | N/A |  | N/A | N/A |  | 2135 | N/A | Non-HFTD | N/A | 1.0417 | 0 | 1.0417 | 0 | 0 | 0
35316019 | Community Rebuild | 95F | ESTS | Estimating | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1435 | -120.9581 | N/A |  | N/A | N/A |  | 2135 | N/A | Non-HFTD | N/A | 1.017 | 0 | 1.017 | 0 | 0 | 0
35316018 | Community Rebuild | 95F | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1407 | -120.9513 | N/A |  | N/A | N/A |  | 2135 | N/A | Non-HFTD | N/A | 0.7197 | 0 | 0.7197 | 0 | 0 | 0
35334467 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Red Bluff | Tehama | 40.3305 | -122.0971 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0.0036607 | Tier 2 | 1.1153 | 2.014 | 0 | 0 | 2.014 | 0 | 0
35334466 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Red Bluff | Tehama | 40.3386 | -122.1218 | WDRM v2 |  | 580 | 0.13616 |  | 704 | 0.0036607 | Tier 2 | 1.1153 | 1.5951 | 0 | 0 | 1.5951 | 0 | 0
35313249 | Community Rebuild | 95F | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Greenville | Plumas | 40.1415 | -120.9483 | N/A |  | N/A | N/A |  | 2135 | N/A | Non-HFTD | N/A | 1.2871 | 0 | 1.2871 | 0 | 0 | 0
35332958 | Base SH | 08W | ADER | Estimating | Y | SI | Region 2 - North East | Lincoln | Placer | 38.9431 | -121.219 | WDRM v2 |  | 568 | 0.14111 |  | 3055 | 0.00011911 | Tier 2 | 2.3771 | 1.3701 | 0 | 1.3701 | 0 | 0 | 0
35320312 | Base SH | 08W | ESTS | Estimating | Y | SI | Region 2 - North East | Lincoln | Placer | 38.9507 | -121.219 | WDRM v2 |  | 568 | 0.14111 |  | 3055 | 0.00011911 | Tier 2 | 2.3771 | 2.04 | 0 | 2.04 | 0 | 0 | 0
35056808 | Other | 30A | PEND | Permitting/Dependency | Y | SO | Region 1 - North Coast | Sebastopol | Sonoma | 38.3734 | -122.918 | WDRM v2 |  | 534 | 0.14747 |  | 1720 | 0.00074971 | Tier 3 | 1.0903 | 1.5138 | 0 | 0 | 1.5138 | 0 | 0
35335293 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.3663 | -121.9916 | WDRM v2 |  | 500 | 0.15336 |  | 1985 | 0.00055328 | Tier 2 | 1.0572 | 2.41 | 0 | 2.41 | 0 | 0 | 0
35335292 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.3772 | -121.9918 | WDRM v2 |  | 500 | 0.15336 |  | 1985 | 0.00055328 | Tier 2 | 1.0572 | 1.8799 | 0 | 1.8799 | 0 | 0 | 0
35335291 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.3771 | -121.9968 | WDRM v2 |  | 500 | 0.15336 |  | 1985 | 0.00055328 | Tier 2 | 1.0572 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0
35320440 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.3783 | -122.0044 | WDRM v2 |  | 500 | 0.15336 |  | 1985 | 0.00055328 | Tier 2 | 1.0572 | 2.2 | 0 | 0 | 2.2 | 0 | 0
35236439 | Base SH | 08W | DOCC | In-Construction | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 0.018129 | Tier 3 | 1.2083 | 1.2508 | 1.2034 | 0.047348 | 0 | 0 | 0
35234865 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 0.018129 | Tier 3 | 1.2083 | 1.0684 | 0 | 1.0684 | 0 | 0 | 0
35234862 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 0.018129 | Tier 3 | 1.2083 | 0.12311 | 0 | 0.12311 | 0 | 0 | 0
35234758 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 0.018129 | Tier 3 | 1.2083 | 1.0267 | 0 | 1.0267 | 0 | 0 | 0
35234756 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 0.018129 | Tier 3 | 1.2083 | 2.782 | 0 | 2.782 | 0 | 0 | 0
35227025 | Base SH | 08W | CONS | In-Construction | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 0.018129 | Tier 3 | 1.2083 | 0.79413 | 0 | 0.79413 | 0 | 0 | 0
35227007 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 0.018129 | Tier 3 | 1.2083 | 2.8756 | 0 | 2.8756 | 0 | 0 | 0
35227002 | Base SH | 08W | CONS | In-Construction | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 0.018129 | Tier 3 | 1.2083 | 0.41894 | 0 | 0 | 0.41894 | 0 | 0
35227001 | Base SH | 08W | CONS | In-Construction | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 0.018129 | Tier 3 | 1.2083 | 0.85246 | 0 | 0.85246 | 0 | 0 | 0
35226878 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 0.018129 | Tier 3 | 1.2083 | 0.58883 | 0 | 0.58883 | 0 | 0 | 0
35226873 | Base SH | 08W | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 0.018129 | Tier 3 | 1.2083 | 1.0394 | 0 | 1.0394 | 0 | 0 | 0
35226857 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7577 | -122.6359 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 0.018129 | Tier 3 | 1.2083 | 1.1449 | 0 | 1.1449 | 0 | 0 | 0
35174501 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7988 | -122.7044 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 0.018129 | Tier 3 | 1.2083 | 3.8303 | 0 | 3.8303 | 0 | 0 | 0
35174478 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7576 | -122.6358 | WDRM v2 |  | 474 | 0.15935 |  | 102 | 0.018129 | Tier 3 | 1.2083 | 1.04 | 0 | 1.04 | 0 | 0 | 0
35227031 | Base SH | 08W | CONS | In-Construction | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 |  | 468 | 0.1603 |  | 13 | 0.035184 | Tier 3 | 1.1913 | 1.55 | 0 | 1.55 | 0 | 0 | 0
35227030 | Base SH | 08W | CONS | In-Construction | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 |  | 468 | 0.1603 |  | 13 | 0.035184 | Tier 3 | 1.1913 | 1.3765 | 0 | 1.3765 | 0 | 0 | 0
35226621 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7249 | -122.6186 | WDRM v2 |  | 468 | 0.1603 |  | 13 | 0.035184 | Tier 3 | 1.1913 | 1.55 | 0 | 0 | 1.55 | 0 | 0
35192282 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7241 | -122.619 | WDRM v2 |  | 468 | 0.1603 |  | 13 | 0.035184 | Tier 3 | 1.1913 | 2.04 | 0 | 0 | 2.04 | 0 | 0
35340270 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Corning | Tehama | 39.918 | -122.4709 | WDRM v2 |  | 457 | 0.16319 |  | 2905 | 0.0001615 | Tier 2 | 1.0421 | 2.34 | 0 | 2.34 | 0 | 0 | 0
35311898 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Corning | Tehama | 39.9193 | -122.4369 | WDRM v2 |  | 457 | 0.16319 |  | 2905 | 0.0001615 | Tier 2 | 1.0421 | 2 | 0 | 2 | 0 | 0 | 0
35274593 | Base SH | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5165 | -119.9716 | WDRM v2 |  | 428 | 0.17286 |  | 249 | 0.010861 | Tier 2 | 1.3062 | 2.756 | 0 | 2.756 | 0 | 0 | 0
35274589 | Base SH | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.5186 | -119.9402 | WDRM v2 |  | 428 | 0.17286 |  | 249 | 0.010861 | Tier 2 & 3 | 1.3062 | 2.132 | 0 | 2.132 | 0 | 0 | 0
35330241 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0823 | -122.6045 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 0.016255 | Tier 3 | 1.1043 | 2.8549 | 0 | 2.8549 | 0 | 0 | 0
35330219 | Base SH | 08W | ADER | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0688 | -122.6043 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 0.016255 | Tier 3 | 1.1043 | 3.1299 | 0 | 3.1299 | 0 | 0 | 0
35330217 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0506 | -122.5833 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 0.016255 | Tier 2 & 3 | 1.1043 | 0.27992 | 0 | 0.27992 | 0 | 0 | 0
35330216 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0696 | -122.585 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 0.016255 | Tier 2 & 3 | 1.1043 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0
35330215 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0669 | -122.5993 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 0.016255 | Tier 2 & 3 | 1.1043 | 3.54 | 0 | 3.54 | 0 | 0 | 0
35330213 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0448 | -122.5887 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 0.016255 | Tier 2 & 3 | 1.1043 | 5.26 | 0 | 0 | 5.26 | 0 | 0
35330211 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0287 | -122.5858 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 0.016255 | Tier 2 & 3 | 1.1043 | 1.9701 | 0 | 1.9701 | 0 | 0 | 0
35317399 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0662 | -122.6111 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 0.016255 | Tier 2 & 3 | 1.1043 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0
35312550 | Base SH | 08W | ADER | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0662 | -122.6111 | WDRM v2 |  | 423 | 0.17389 |  | 127 | 0.016255 | Tier 3 | 1.1043 | 1.54 | 0 | 1.54 | 0 | 0 | 0
35320463 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.284 | -122.128 | WDRM v2 |  | 419 | 0.17457 |  | 987 | 0.0022992 | Tier 2 | 1.5 | 0.56004 | 0 | 0.56004 | 0 | 0 | 0
35380376 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Covelo | Tehama | 39.846 | -122.5891 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0.0037456 | Tier 2 | 1.372 | 2.5799 | 0 | 2.5799 | 0 | 0 | 0
35380373 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Covelo | Tehama | 39.8466 | -122.59 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0.0037456 | Tier 2 | 1.372 | 1.79 | 0 | 1.79 | 0 | 0 | 0
35380372 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Covelo | Tehama | 39.8634 | -122.5862 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0.0037456 | Tier 2 | 1.372 | 1.74 | 0 | 1.74 | 0 | 0 | 0
35380371 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Corning | Tehama | 39.8773 | -122.5512 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0.0037456 | Tier 2 | 1.372 | 2.8299 | 0 | 2.8299 | 0 | 0 | 0
35380370 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Red Bluff | Tehama | 39.887 | -122.5361 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0.0037456 | Tier 2 | 1.372 | 3.1799 | 0 | 3.1799 | 0 | 0 | 0
35380369 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Red Bluff | Tehama | 39.8928 | -122.5171 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0.0037456 | Tier 2 | 1.372 | 2.1299 | 0 | 2.1299 | 0 | 0 | 0
35380368 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Red Bluff | Tehama | 39.9108 | -122.493 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0.0037456 | Tier 2 | 1.372 | 2.2299 | 0 | 2.2299 | 0 | 0 | 0
35380365 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Corning | Tehama | 39.9089 | -122.4786 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0.0037456 | Tier 2 | 1.372 | 3.04 | 0 | 3.04 | 0 | 0 | 0
35334229 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Covelo | Tehama | 39.8493 | -122.6179 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0.0037456 | Tier 2 | 1.372 | 3.04 | 0 | 3.04 | 0 | 0 | 0
35311897 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Corning | Tehama | 39.8685 | -122.5663 | WDRM v2 |  | 413 | 0.17544 |  | 694 | 0.0037456 | Tier 2 | 1.372 | 4.84 | 0 | 4.84 | 0 | 0 | 0
35285065 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.2968 | -123.1087 | WDRM v2 |  | 396 | 0.18107 |  | 2321 | 0.00037714 | Tier 2 | 1.381 | 0.25398 | 0 | 0.25398 | 0 | 0 | 0
35285064 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3076 | -123.1132 | WDRM v2 |  | 396 | 0.18107 |  | 2321 | 0.00037714 | Tier 2 | 1.381 | 0.79848 | 0 | 0.79848 | 0 | 0 | 0
35339293 | Base SH | 08W | ESTS | Estimating | Y | NB | Region 2 - North East | Fairfield | Solano | 38.3158 | -122.1039 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 0.0035256 | Tier 2 | 1.3834 | 1.1799 | 0 | 1.1799 | 0 | 0 | 0
35338410 | Base SH | 08W | ADER | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.2925 | -122.1292 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 0.0035256 | Tier 2 | 1.3834 | 2.21 | 0 | 2.21 | 0 | 0 | 0
35338409 | Base SH | 08W | ADER | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.2968 | -122.1356 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 0.0035256 | Tier 2 | 1.3834 | 2.35 | 0 | 2.35 | 0 | 0 | 0
35338408 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.3148 | -122.0962 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 0.0035256 | Tier 2 | 1.3834 | 1.1299 | 0 | 1.1299 | 0 | 0 | 0
35338407 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.3039 | -122.0964 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 0.0035256 | Tier 2 | 1.3834 | 0.66004 | 0 | 0.66004 | 0 | 0 | 0
35338406 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.2877 | -122.1043 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 0.0035256 | Tier 2 | 1.3834 | 1.14 | 0 | 1.14 | 0 | 0 | 0
35338405 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.2972 | -122.1262 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 0.0035256 | Tier 2 | 1.3834 | 2.24 | 0 | 2.24 | 0 | 0 | 0
35338404 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.3141 | -122.1263 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 0.0035256 | Tier 2 | 1.3834 | 1.0299 | 0 | 1.0299 | 0 | 0 | 0
35320461 | Base SH | 08W | ADER | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.299 | -122.1519 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 0.0035256 | Tier 2 | 1.3834 | 3.56 | 0 | 3.56 | 0 | 0 | 0
35320460 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Fairfield | Solano | 38.3063 | -122.1288 | WDRM v2 |  | 393 | 0.18223 |  | 728 | 0.0035256 | Tier 2 | 1.3834 | 1.7799 | 0 | 1.7799 | 0 | 0 | 0
35339289 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4493 | -122.4078 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | Tier 2 | 1.012 | 1.82 | 0 | 1.82 | 0 | 0 | 0
35339288 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4403 | -122.4075 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | Tier 2 | 1.012 | 2.25 | 0 | 2.25 | 0 | 0 | 0
35339287 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4427 | -122.3927 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | Tier 2 | 1.012 | 1.2 | 0 | 1.2 | 0 | 0 | 0
35339286 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4362 | -122.3535 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | Tier 2 | 1.012 | 2.54 | 0 | 2.54 | 0 | 0 | 0
35339285 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4359 | -122.3689 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | Tier 2 | 1.012 | 2.32 | 0 | 2.32 | 0 | 0 | 0
35339283 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4359 | -122.3689 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | Tier 2 | 1.012 | 2.96 | 0 | 2.96 | 0 | 0 | 0
35339282 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4516 | -122.3245 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | Tier 2 | 1.012 | 0.51 | 0 | 0.51 | 0 | 0 | 0
35337012 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.443 | -122.3663 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | Tier 2 | 1.012 | 4.92 | 0 | 0 | 0 | 4.92 | 0
35337011 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4406 | -122.3414 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | Tier 2 | 1.012 | 2.89 | 0 | 2.89 | 0 | 0 | 0
35337010 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4416 | -122.3258 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | Tier 2 | 1.012 | 3.82 | 0 | 3.82 | 0 | 0 | 0
35337008 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4409 | -122.3061 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | Tier 2 | 1.012 | 2.35 | 0 | 2.35 | 0 | 0 | 0
35317887 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4377 | -122.3878 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | Tier 2 | 1.012 | 0.8 | 0 | 0.8 | 0 | 0 | 0
35317480 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4488 | -122.3179 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | Tier 2 | 1.012 | 2.06 | 0 | 2.06 | 0 | 0 | 0
35312548 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4517 | -122.3081 | WDRM v2 |  | 389 | 0.18396 |  | 1853 | 0.00063997 | Tier 2 | 1.012 | 1.2 | 0 | 1.2 | 0 | 0 | 0
35280560 | Fire Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | WDRM v2 |  | 378 | 0.1873 |  | 45 | 0.023178 | Tier 2 & 3 | 2.0328 | 2.64 | 0 | 2.64 | 0 | 0 | 0
35280499 | Fire Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | WDRM v2 |  | 378 | 0.1873 |  | 45 | 0.023178 | Tier 2 & 3 | 2.0328 | 0.85 | 0 | 0.85 | 0 | 0 | 0
35279182 | Fire Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | WDRM v2 |  | 378 | 0.1873 |  | 45 | 0.023178 | Tier 2 & 3 | 2.0328 | 2.0701 | 0 | 2.0701 | 0 | 0 | 0
35279181 | Fire Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Belden | Plumas | 39.9141 | -121.3272 | WDRM v2 |  | 378 | 0.1873 |  | 45 | 0.023178 | Tier 2 & 3 | 2.0328 | 5.589 | 0 | 5.589 | 0 | 0 | 0
35192280 | Base SH | 08W | PEND | Permitting/Dependency | Y | DI | Region 3 - Bay Area | Clayton | Contra Costa | 37.8684 | -121.8574 | WDRM v2 |  | 377 | 0.18755 |  | 15 | 0.034099 | Tier 3 | 1.3819 | 1.34 | 0 | 1.34 | 0 | 0 | 0
35223030 | Base SH | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Bangor | Butte | 39.3878 | -121.4038 | WDRM v2 |  | 355 | 0.19378 |  | 2768 | 0.00020951 | Tier 2 | 1.5959 | 1.1968 | 1.1364 | 0.060417 | 0 | 0 | 0
35330249 | Base SH | 08W | ADER | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0287 | -122.6799 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 0.0038601 | Tier 2 & 3 | 1.3273 | 4 | 0 | 4 | 0 | 0 | 0
35330248 | Base SH | 08W | ADER | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0296 | -122.6802 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 0.0038601 | Tier 2 & 3 | 1.3273 | 2.4 | 0 | 0 | 2.4 | 0 | 0
35330247 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.04 | -122.6823 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 0.0038601 | Tier 2 & 3 | 1.3273 | 0.75 | 0 | 0.75 | 0 | 0 | 0
35330246 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0448 | -122.6814 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 0.0038601 | Tier 2 & 3 | 1.3273 | 1.0299 | 0 | 1.0299 | 0 | 0 | 0
35330245 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0541 | -122.6767 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 0.0038601 | Tier 2 & 3 | 1.3273 | 0.089962 | 0 | 0.089962 | 0 | 0 | 0
35330244 | Base SH | 08W | ADER | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0531 | -122.6813 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 0.0038601 | Tier 2 & 3 | 1.3273 | 0.42008 | 0 | 0.42008 | 0 | 0 | 0
35329474 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0932 | -122.6804 | WDRM v2 |  | 345 | 0.19539 |  | 375 | 0.007396 | Tier 2 & 3 | 1.0291 | 0.11004 | 0 | 0.11004 | 0 | 0 | 0
35317398 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0581 | -122.693 | WDRM v2 |  | 345 | 0.19539 |  | 375 | 0.007396 | Tier 2 & 3 | 1.0291 | 3.5201 | 0 | 0 | 3.5201 | 0 | 0
35312552 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.023 | -122.6779 | WDRM v2 |  | 345 | 0.19539 |  | 679 | 0.0038601 | Tier 2 & 3 | 1.3273 | 0.77008 | 0 | 0.77008 | 0 | 0 | 0
35349642 | Base SH | 08W | UNSE | Scoping/Scoped | Y | HB | Region 1 - North Coast | Upper Lake | Lake | 39.1699 | -123.006 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 0.024971 | Tier 2 | 1.0191 | 0.035985 | 0 | 0 | 0 | 0.035985 | 0
35285251 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Lakeport | Lake | 39.1758 | -123.0191 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 0.024971 | Tier 2 | 1.0191 | 0.65303 | 0 | 0.65303 | 0 | 0 | 0
35286270 | Community Rebuild | 95F O | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Paradise | Butte | 39.7583 | -121.6291 | N/A |  | N/A | N/A |  | 503 | N/A | Tier 3 | N/A | 1.2 | 0 | 0 | 1.2 | 0 | 0
35285249 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Lakeport | Lake | 39.1673 | -123.0087 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 0.024971 | Tier 2 | 1.0191 | 2.6288 | 0 | 2.6288 | 0 | 0 | 0
35283346 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Lakeport | Lake | 39.13 | -122.997 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 0.024971 | Tier 2 | 1.0191 | 1.6591 | 0 | 1.6591 | 0 | 0 | 0
35283343 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Lakeport | Lake | 39.1488 | -122.9992 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 0.024971 | Tier 2 | 1.0191 | 0.72614 | 0 | 0.72614 | 0 | 0 | 0
35256083 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Lakeport | Lake | 39.1434 | -123.0023 | WDRM v2 |  | 335 | 0.19794 |  | 35 | 0.024971 | Tier 2 | 1.0191 | 1.847 | 0 | 1.847 | 0 | 0 | 0
35134959 | Other | 06A | PEND | Permitting/Dependency | Y | ST | Region 5 - Central Valley | Valley Springs | Calaveras | 38.2131 | -120.7638 | WDRM v2 |  | 322 | 0.20132 |  | 1048 | 0.0020877 | Tier 2 | 1.3568 | 0.18939 | 0 | 0 | 0.18939 | 0 | 0
35332364 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Elk Creek | Glenn | 39.3944 | -122.5518 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0.0021026 | Tier 2 | 1.4457 | 0.085038 | 0 | 0.085038 | 0 | 0 | 0
35332363 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Elk Creek | Glenn | 39.4073 | -122.5471 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0.0021026 | Tier 2 | 1.4457 | 1.1299 | 0 | 1.1299 | 0 | 0 | 0
35332362 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Elk Creek | Glenn | 39.4286 | -122.5052 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0.0021026 | Tier 2 | 1.4457 | 3.8299 | 0 | 3.8299 | 0 | 0 | 0
35332360 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Willows | Glenn | 39.456 | -122.5138 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0.0021026 | Tier 2 | 1.4457 | 5.46 | 0 | 5.46 | 0 | 0 | 0
35330812 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Elk Creek | Glenn | 39.5561 | -122.5414 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0.0021026 | Tier 2 | 1.4457 | 2.49 | 0 | 2.49 | 0 | 0 | 0
35316278 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Elk Creek | Glenn | 39.4868 | -122.5188 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0.0021026 | Tier 2 | 1.4457 | 2.35 | 0 | 2.35 | 0 | 0 | 0
35312543 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Elk Creek | Glenn | 39.5896 | -122.5395 | WDRM v2 |  | 315 | 0.20473 |  | 1044 | 0.0021026 | Tier 2 | 1.4457 | 3.71 | 0 | 3.71 | 0 | 0 | 0
35329473 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0654 | -122.6333 | WDRM v2 |  | 312 | 0.20738 |  | 44 | 0.023647 | Tier 3 | 1.0205 | 4.761 | 0 | 0 | 4.761 | 0 | 0
35329472 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0748 | -122.6503 | WDRM v2 |  | 312 | 0.20738 |  | 44 | 0.023647 | Tier 3 | 1.0205 | 2.8689 | 0 | 2.8689 | 0 | 0 | 0
35312551 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Clearlake Oaks | Lake | 39.0837 | -122.66 | WDRM v2 |  | 312 | 0.20738 |  | 44 | 0.023647 | Tier 3 | 1.0205 | 3.2049 | 0 | 3.2049 | 0 | 0 | 0
35277935 | Base SH | 08W | PEND | Permitting/Dependency | Y | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0313 | -119.4396 | WDRM v2 |  | 274 | 0.22501 |  | 614 | 0.0043344 | Tier 2 | 2.2546 | 0.089394 | 0 | 0.089394 | 0 | 0 | 0
35332217 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Cottonwood | Shasta | 40.3886 | -122.3831 | WDRM v2 |  | 271 | 0.22599 |  | 2723 | 0.0002216 | Tier 2 | 1.0186 | 3.0299 | 0 | 3.0299 | 0 | 0 | 0
35332216 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Cottonwood | Shasta | 40.4042 | -122.3264 | WDRM v2 |  | 271 | 0.22599 |  | 2723 | 0.0002216 | Tier 2 | 1.0186 | 1.4299 | 0 | 1.4299 | 0 | 0 | 0
35332215 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4149 | -122.3421 | WDRM v2 |  | 271 | 0.22599 |  | 2723 | 0.0002216 | Tier 2 | 1.0186 | 2.26 | 0 | 2.26 | 0 | 0 | 0
35332214 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Cottonwood | Shasta | 40.3899 | -122.3499 | WDRM v2 |  | 271 | 0.22599 |  | 2723 | 0.0002216 | Tier 2 | 1.0186 | 4.04 | 0 | 4.04 | 0 | 0 | 0
35316569 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Cottonwood | Shasta | 40.3893 | -122.3434 | WDRM v2 |  | 271 | 0.22599 |  | 2723 | 0.0002216 | Tier 2 | 1.0186 | 4.81 | 0 | 4.81 | 0 | 0 | 0
35316567 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Cottonwood | Shasta | 40.3893 | -122.3434 | WDRM v2 |  | 271 | 0.22599 |  | 2723 | 0.0002216 | Tier 2 | 1.0186 | 3.4201 | 0 | 3.4201 | 0 | 0 | 0
35312540 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Cottonwood | Shasta | 40.3893 | -122.3434 | WDRM v2 |  | 271 | 0.22599 |  | 2723 | 0.0002216 | Tier 2 | 1.0186 | 4.8799 | 0 | 4.8799 | 0 | 0 | 0
35349649 | Base SH | 08W | UNSE | Scoping/Scoped | Y | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.6137 | -120.1537 | WDRM v2 |  | 269 | 0.22624 |  | 2607 | 0.00026962 | Tier 2 | 1.0227 | 0.25019 | 0 | 0 | 0.25019 | 0 | 0
35349648 | Base SH | 08W | UNSE | Scoping/Scoped | Y | LP | Region 4 - Central Coast | Solvang | Santa Barbara | 34.6137 | -120.1537 | WDRM v2 |  | 269 | 0.22624 |  | 2607 | 0.00026962 | Tier 2 | 1.0227 | 0.25625 | 0 | 0 | 0.25625 | 0 | 0
35329008 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Oroville | Butte | 39.6413 | -121.6413 | WDRM v2 |  | 268 | 0.22632 |  | 2491 | 0.00031072 | Tier 2 | 1 | 0.31307 | 0 | 0.31307 | 0 | 0 | 0
35299629 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Oroville | Butte | 39.654 | -121.6323 | WDRM v2 |  | 268 | 0.22632 |  | 2491 | 0.00031072 | Tier 2 | 1 | 0.89091 | 0 | 0 | 0.89091 | 0 | 0
35330815 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4792 | -122.2645 | WDRM v2 |  | 262 | 0.22913 |  | 3263 | 8.0345e-05 | Tier 2 | 1.0974 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0
35311895 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4803 | -122.2646 | WDRM v2 |  | 262 | 0.22913 |  | 3263 | 8.0345e-05 | Tier 2 | 1.0974 | 2.7799 | 0 | 2.7799 | 0 | 0 | 0
35337306 | Base SH | 08W | PEND | Permitting/Dependency | Y | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1677 | -120.3831 | WDRM v2 |  | 235 | 0.24096 |  | 54 | 0.022026 | Tier 2 & 3 | 1.3955 | 2.2667 | 0 | 2.2667 | 0 | 0 | 0
35284365 | Base SH | 08W | PEND | Permitting/Dependency | Y | ST | Region 5 - Central Valley | Arnold | Calaveras | 38.2399 | -120.3619 | WDRM v2 |  | 235 | 0.24096 |  | 54 | 0.022026 | Tier 2 & 3 | 1.3955 | 2.7547 | 0 | 2.7547 | 0 | 0 | 0
35284364 | Base SH | 08W | PEND | Permitting/Dependency | Y | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1677 | -120.3831 | WDRM v2 |  | 235 | 0.24096 |  | 54 | 0.022026 | Tier 2 & 3 | 1.3955 | 0.91742 | 0 | 0.91742 | 0 | 0 | 0
35349244 | Base SH | 08W | ADER | Estimating | Y | SI | Region 2 - North East | Lincoln | Placer | 38.9873 | -121.2542 | WDRM v2 |  | 230 | 0.24208 |  | 4147 | 5.2842e-05 | Tier 2 | 1.6327 | 0.67992 | 0 | 0.67992 | 0 | 0 | 0
35320450 | Base SH | 08W | ADER | Estimating | Y | SI | Region 2 - North East | Lincoln | Placer | 39.0041 | -121.2605 | WDRM v2 |  | 230 | 0.24208 |  | 4147 | 5.2842e-05 | Tier 2 | 1.6327 | 2.0701 | 0 | 2.0701 | 0 | 0 | 0
35223039 | Base SH | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Oroville | Butte | 39.4738 | -121.5307 | WDRM v2 |  | 218 | 0.24845 |  | 2461 | 0.00032066 | Tier 2 | 1.256 | 0.53561 | 0.40985 | 0 | 0.12576 | 0 | 0
35223615 | Base SH | 08W | PEND | Permitting/Dependency | Y | NB | Region 1 - North Coast | San Rafael | Marin | 38.0443 | -122.6155 | WDRM v2 |  | 215 | 0.25006 |  | 1267 | 0.0014262 | Tier 3 | 1.2195 | 1.3843 | 0 | 1.3843 | 0 | 0 | 0
35312544 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Elk Creek | Glenn | 39.5927 | -122.5431 | WDRM v2 |  | 206 | 0.25426 |  | 1350 | 0.0012407 | Tier 2 | 1.4822 | 0.079924 | 0 | 0.079924 | 0 | 0 | 0
35335290 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.3898 | -122.0001 | WDRM v2 |  | 190 | 0.26339 |  | 1722 | 0.00074783 | Tier 2 | 1.0225 | 2.61 | 0 | 2.61 | 0 | 0 | 0
35320441 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.3933 | -122.0146 | WDRM v2 |  | 190 | 0.26339 |  | 1722 | 0.00074783 | Tier 2 | 1.0225 | 2.14 | 0 | 2.14 | 0 | 0 | 0
35337163 | Base SH | 08W | ESTS | Estimating | Y | SI | Region 2 - North East | Lincoln | Placer | 38.97 | -121.2606 | WDRM v2 |  | 185 | 0.26526 |  | 2971 | 0.0001399 | Tier 2 | 1.5614 | 1.39 | 0 | 1.39 | 0 | 0 | 0
35320449 | Base SH | 08W | PEND | Permitting/Dependency | Y | SI | Region 2 - North East | Lincoln | Placer | 38.9755 | -121.2772 | WDRM v2 |  | 185 | 0.26526 |  | 2971 | 0.0001399 | Tier 2 | 1.5614 | 3.2375 | 0 | 3.2375 | 0 | 0 | 0
35305308 | Base SH | 08W | ESTS | Estimating | Y | SI | Region 2 - North East | Cool | El Dorado | 38.8944 | -120.9647 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 0.0069368 | Tier 2 | 1.3701 | 0.66799 | 0 | 0 | 0.66799 | 0 | 0
35305303 | Base SH | 08W | PEND | Permitting/Dependency | Y | SI | Region 2 - North East | Cool | El Dorado | 38.8972 | -120.989 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 0.0069368 | Tier 2 | 1.3701 | 1.065 | 0 | 1.065 | 0 | 0 | 0
35293670 | Base SH | 08W | PEND | Permitting/Dependency | Y | SI | Region 2 - North East | Cool | El Dorado | 38.8805 | -120.9418 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 0.0069368 | Tier 2 | 1.3701 | 0.54394 | 0 | 0.54394 | 0 | 0 | 0
35293665 | Base SH | 08W | UNSC | Ready for Construction | Y | SI | Region 2 - North East | Greenwood | El Dorado | 38.8973 | -120.9098 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 0.0069368 | Tier 2 | 1.3701 | 0.43655 | 0 | 0.43655 | 0 | 0 | 0
35293663 | Base SH | 08W | PEND | Permitting/Dependency | Y | SI | Region 2 - North East | Greenwood | El Dorado | 38.8964 | -120.922 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 0.0069368 | Tier 2 | 1.3701 | 0.98996 | 0 | 0 | 0.98996 | 0 | 0
35293662 | Base SH | 08W | PEND | Permitting/Dependency | Y | SI | Region 2 - North East | Cool | El Dorado | 38.8956 | -120.9606 | WDRM v2 |  | 169 | 0.27537 |  | 401 | 0.0069368 | Tier 2 | 1.3701 | 0.68788 | 0 | 0.68788 | 0 | 0 | 0
35278093 | Base SH | 08W | PEND | Permitting/Dependency | Y | FR | Region 5 - Central Valley | Tollhouse | Fresno | 36.9797 | -119.3677 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0.0047219 | Tier 2 | 2.0206 | 0.41496 | 0 | 0 | 0 | 0 | 0.41496
35254346 | Community Rebuild | 95F | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7484 | -121.6087 | N/A |  | N/A | N/A |  | 1178 | N/A | Non-HFTD | N/A | 0.056818 | 0 | 0 | 0.056818 | 0 | 0
35254345 | Community Rebuild | 95F | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7874 | -121.601 | N/A |  | N/A | N/A |  | 809 | N/A | Tier 3 | N/A | 0.066288 | 0 | 0 | 0.066288 | 0 | 0
35254344 | Community Rebuild | 95F | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7414 | -121.6432 | N/A |  | N/A | N/A |  | 406 | N/A | Tier 3 | N/A | 0.12027 | 0 | 0 | 0.12027 | 0 | 0
35254275 | Community Rebuild | 95F | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Paradise | Butte | 39.7704 | -121.6012 | N/A |  | N/A | N/A |  | 1618 | N/A | Tier 3 | N/A | 0.066288 | 0 | 0 | 0.066288 | 0 | 0
35254274 | Community Rebuild | 95F | UNSC | Ready for Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.7598 | -121.6341 | N/A |  | N/A | N/A |  | 503 | N/A | Tier 3 | N/A | 0.088447 | 0 | 0 | 0.088447 | 0 | 0
35277938 | Base SH | 08W | PEND | Permitting/Dependency | Y | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0125 | -119.4038 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0.0047219 | Tier 2 | 2.0206 | 0.42822 | 0 | 0.42822 | 0 | 0 | 0
35277924 | Base SH | 08W | PEND | Permitting/Dependency | Y | FR | Region 5 - Central Valley | Tollhouse | Fresno | 37.0071 | -119.4086 | WDRM v2 |  | 163 | 0.27714 |  | 569 | 0.0047219 | Tier 2 | 2.0206 | 0.10909 | 0 | 0.10909 | 0 | 0 | 0
35062376 | Base SH | 08W | CONS | In-Construction | Y | SI | Region 2 - North East | Shingle Springs | El Dorado | 38.7686 | -120.9251 | WDRM v2 |  | 159 | 0.27855 |  | 241 | 0.011098 | Tier 3 | 2.2454 | 5.0311 | 0.97178 | 4.0593 | 0 | 0 | 0
35254650 | Base SH | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Paynes Creek | Tehama | 40.4013 | -121.8752 | WDRM v2 |  | 157 | 0.27952 |  | 280 | 0.0099281 | Tier 2 | 1.1169 | 0.30436 | 0.30436 | 0 | 0 | 0 | 0
35325590 | Base SH | 08W | ESTS | Estimating | Y | SI | Region 2 - North East | Auburn | Placer | 38.8575 | -121.0758 | WDRM v2 |  | 152 | 0.28318 |  | 1508 | 0.00097924 | Tier 2 | 1.484 | 2.06 | 0 | 2.06 | 0 | 0 | 0
35325589 | Base SH | 08W | ESTS | Estimating | Y | SI | Region 2 - North East | Auburn | Placer | 38.8537 | -121.0803 | WDRM v2 |  | 152 | 0.28318 |  | 1508 | 0.00097924 | Tier 2 | 1.484 | 1.21 | 0 | 1.21 | 0 | 0 | 0
35312545 | Base SH | 08W | ESTS | Estimating | Y | SI | Region 2 - North East | Auburn | Placer | 38.8586 | -121.0805 | WDRM v2 |  | 152 | 0.28318 |  | 1508 | 0.00097924 | Tier 2 | 1.484 | 1.3299 | 0 | 1.3299 | 0 | 0 | 0
35331305 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Anderson | Shasta | 40.4699 | -122.2473 | WDRM v2 |  | 143 | 0.2889 |  | 3058 | 0.00011858 | Tier 2 | 1.1362 | 0.44508 | 0 | 0.44508 | 0 | 0 | 0
35298571 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Anderson | Shasta | 40.469 | -122.2542 | WDRM v2 |  | 143 | 0.2889 |  | 3058 | 0.00011858 | Tier 2 | 1.1362 | 0.33996 | 0 | 0.33996 | 0 | 0 | 0
35332218 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Cottonwood | Shasta | 40.3986 | -122.3143 | WDRM v2 |  | 123 | 0.31273 |  | 1675 | 0.0007912 | Tier 2 | 1.039 | 3.26 | 0 | 3.26 | 0 | 0 | 0
35332213 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Cottonwood | Shasta | 40.3892 | -122.3258 | WDRM v2 |  | 123 | 0.31273 |  | 1675 | 0.0007912 | Tier 2 | 1.039 | 2.3701 | 0 | 2.3701 | 0 | 0 | 0
35316561 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Cottonwood | Shasta | 40.3895 | -122.3067 | WDRM v2 |  | 123 | 0.31273 |  | 1675 | 0.0007912 | Tier 2 | 1.039 | 4.41 | 0 | 4.41 | 0 | 0 | 0
35311899 | Base SH | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Cottonwood | Shasta | 40.3895 | -122.3067 | WDRM v2 |  | 123 | 0.31273 |  | 1675 | 0.0007912 | Tier 2 | 1.039 | 3.44 | 0 | 3.44 | 0 | 0 | 0
35404729 | Base SH | 08W | ADER | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.4295 | -122.0489 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 0.0056058 | Tier 2 | 1.2427 | 0.95 | 0 | 0 | 0 | 0.95 | 0
35404728 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.4201 | -122.0443 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 0.0056058 | Tier 2 | 1.2427 | 0.85 | 0 | 0 | 0 | 0.85 | 0
35404727 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.4267 | -122.0475 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 0.0056058 | Tier 2 | 1.2427 | 1.1 | 0 | 0 | 0 | 1.1 | 0
35334755 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.3911 | -122.0367 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 0.0056058 | Tier 2 | 1.2427 | 1.47 | 0 | 1.47 | 0 | 0 | 0
35334754 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.4024 | -122.0318 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 0.0056058 | Tier 2 | 1.2427 | 3.93 | 0 | 3.93 | 0 | 0 | 0
35334753 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.4313 | -122.05 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 0.0056058 | Tier 2 | 1.2427 | 1.26 | 0 | 1.26 | 0 | 0 | 0
35246598 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Magalia | Butte | 39.8149 | -121.5802 | N/A |  | N/A | N/A |  | 1618 | N/A | Tier 3 | N/A | 3.5 | 0 | 0 | 3.5 | 0 | 0
35246595 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7842 | -121.5991 | N/A |  | N/A | N/A |  | 1546 | N/A | Tier 3 | N/A | 5.9 | 0 | 0 | 5.9 | 0 | 0
35246594 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7382 | -121.6208 | N/A |  | N/A | N/A |  | 497 | N/A | Tier 3 | N/A | 3.7 | 0 | 0 | 3.7 | 0 | 0
35246592 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7367 | -121.6125 | N/A |  | N/A | N/A |  | 362 | N/A | Tier 3 | N/A | 6.2 | 0 | 0 | 6.2 | 0 | 0
35246591 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7485 | -121.6086 | N/A |  | N/A | N/A |  | 1563 | N/A | Tier 3 | N/A | 4.3 | 0 | 0 | 4.3 | 0 | 0
35246590 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7696 | -121.579 | N/A |  | N/A | N/A |  | 2198 | N/A | Tier 3 | N/A | 3.3 | 0 | 0 | 3.3 | 0 | 0
35246589 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.764 | -121.5986 | N/A |  | N/A | N/A |  | 503 | N/A | Tier 3 | N/A | 0.5 | 0 | 0 | 0.5 | 0 | 0
35320339 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.4168 | -122.0381 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 0.0056058 | Tier 2 | 1.2427 | 2.2 | 0 | 2.2 | 0 | 0 | 0
35246316 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7265 | -121.6374 | N/A |  | N/A | N/A |  | 497 | N/A | Tier 3 | N/A | 3.6 | 0 | 0 | 3.6 | 0 | 0
35246309 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7752 | -121.6093 | N/A |  | N/A | N/A |  | 1546 | N/A | Non-HFTD | N/A | 1.3 | 0 | 0 | 1.3 | 0 | 0
35246308 | Community Rebuild | 95F O | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7572 | -121.5722 | N/A |  | N/A | N/A |  | 1617 | N/A | Tier 3 | N/A | 3.2 | 0 | 0 | 3.2 | 0 | 0
35320336 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.4365 | -122.0527 | WDRM v2 |  | 122 | 0.31672 |  | 491 | 0.0056058 | Tier 2 | 1.2427 | 2.3 | 0 | 0 | 2.3 | 0 | 0
35334234 | Base SH | 08W | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Auburn | Placer | 38.9781 | -121.1088 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | Tier 2 | 1.4794 | 2.3 | 0 | 0 | 2.3 | 0 | 0
35334232 | Base SH | 08W | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Auburn | Placer | 38.9855 | -121.1087 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | Tier 2 | 1.4794 | 1.01 | 0 | 0 | 1.01 | 0 | 0
35244220 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7717 | -121.6118 | N/A |  | N/A | N/A |  | 503 | N/A | Tier 3 | N/A | 2.5 | 0 | 0 | 2.5 | 0 | 0
35244027 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7285 | -121.6363 | N/A |  | N/A | N/A |  | 1618 | N/A | Tier 3 | N/A | 5.5 | 0 | 0 | 5.5 | 0 | 0
35333504 | Base SH | 08W | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Auburn | Placer | 38.9992 | -121.1363 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | Tier 2 | 1.4794 | 0.45 | 0 | 0.45 | 0 | 0 | 0
35333503 | Base SH | 08W | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Auburn | Placer | 38.9959 | -121.1355 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | Tier 2 | 1.4794 | 0.3 | 0 | 0.3 | 0 | 0 | 0
35333501 | Base SH | 08W | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Auburn | Placer | 38.9851 | -121.1296 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | Tier 2 | 1.4794 | 2.96 | 0 | 0 | 2.96 | 0 | 0
35314416 | Base SH | 08W | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Auburn | Placer | 38.9981 | -121.1168 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | Tier 2 | 1.4794 | 1.1201 | 0 | 0 | 1.1201 | 0 | 0
35314415 | Base SH | 08W | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Auburn | Placer | 38.9962 | -121.1167 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | Tier 2 | 1.4794 | 2.05 | 0 | 0 | 2.05 | 0 | 0
35311896 | Base SH | 08W | UNSE | Scoping/Scoped | Y | SI | Region 2 - North East | Auburn | Placer | 38.9961 | -121.1091 | WDRM v2 |  | 118 | 0.32016 |  | 2685 | 0.00023693 | Tier 2 | 1.4794 | 2.76 | 0 | 0 | 2.76 | 0 | 0
35259512 | Base SH | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Bella Vista | Shasta | 40.6324 | -122.2376 | WDRM v2 |  | 100 | 0.34561 |  | 2704 | 0.00022756 | Tier 2 | 1.2336 | 0.25871 | 0 | 0.25871 | 0 | 0 | 0
35254259 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Manton | Shasta | 40.4594 | -121.8662 | WDRM v2 |  | 76 | 0.37545 |  | 2202 | 0.00043332 | Tier 2 & 3 | 1.323 | 0.275 | 0 | 0.275 | 0 | 0 | 0
35240166 | Base SH | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Manton | Shasta | 40.4595 | -121.8662 | WDRM v2 |  | 76 | 0.37545 |  | 2202 | 0.00043332 | Tier 2 & 3 | 1.323 | 0.015341 | 0 | 0.015341 | 0 | 0 | 0
35293846 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.3009 | -123.0524 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 0.0046795 | Tier 2 & 3 | 1.2131 | 0.85985 | 0 | 0.85985 | 0 | 0 | 0
35290808 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Potter Valley | Mendocino | 39.2815 | -123.1027 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 0.0046795 | Tier 2 | 1.2131 | 0.27992 | 0 | 0.27992 | 0 | 0 | 0
35290508 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.1987 | -123.0496 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 0.0046795 | Tier 2 | 1.2131 | 0.62008 | 0 | 0.62008 | 0 | 0 | 0
35290504 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Ukiah | Mendocino | 39.2145 | -123.0742 | WDRM v2 |  | 75 | 0.37685 |  | 573 | 0.0046795 | Tier 2 | 1.2131 | 1.0436 | 0 | 1.0436 | 0 | 0 | 0
35301112 | Base SH | 08W | PEND | Permitting/Dependency | Y | SI | Region 2 - North East | Cool | El Dorado | 38.8641 | -120.9817 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 0.017565 | Tier 2 | 2.6372 | 0.52576 | 0 | 0.52576 | 0 | 0 | 0
35300933 | Base SH | 08W | UNSC | Ready for Construction | Y | SI | Region 2 - North East | Cool | El Dorado | 38.8775 | -120.993 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 0.017565 | Tier 2 | 2.6372 | 0.59489 | 0 | 0.59489 | 0 | 0 | 0
35227481 | Community Rebuild | 95F O | CONS | In-Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.7392 | -121.5724 | N/A |  | N/A | N/A |  | 201 | N/A | Tier 3 | N/A | 4.2 | 0 | 4.2 | 0 | 0 | 0
35227417 | Community Rebuild | 95F O | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7323 | -121.6513 | N/A |  | N/A | N/A |  | 406 | N/A | Tier 2 | N/A | 2.8 | 0 | 0 | 2.8 | 0 | 0
35227415 | Community Rebuild | 95F O | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7389 | -121.6402 | N/A |  | N/A | N/A |  | 406 | N/A | Tier 3 | N/A | 5.2 | 0 | 5.2 | 0 | 0 | 0
35227413 | Community Rebuild | 95F O | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7423 | -121.6423 | N/A |  | N/A | N/A |  | 406 | N/A | Tier 2 | N/A | 5.6 | 0 | 0 | 5.6 | 0 | 0
35227412 | Community Rebuild | 95F O | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.769 | -121.5786 | N/A |  | N/A | N/A |  | 490 | N/A | Tier 3 | N/A | 2 | 0 | 0 | 2 | 0 | 0
35227411 | Community Rebuild | 95F O | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7595 | -121.6024 | N/A |  | N/A | N/A |  | 503 | N/A | Tier 3 | N/A | 2.7 | 0 | 0 | 2.7 | 0 | 0
35227409 | Community Rebuild | 95F O | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7501 | -121.6242 | N/A |  | N/A | N/A |  | 497 | N/A | Tier 3 | N/A | 3.6 | 0 | 0 | 3.6 | 0 | 0
35227408 | Community Rebuild | 95F O | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7524 | -121.6126 | N/A |  | N/A | N/A |  | 2530 | N/A | Non-HFTD | N/A | 2.1 | 0 | 2.1 | 0 | 0 | 0
35227406 | Community Rebuild | 95F O | ADER | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7523 | -121.6185 | N/A |  | N/A | N/A |  | 2530 | N/A | Tier 3 | N/A | 4.5 | 0 | 4.5 | 0 | 0 | 0
35227405 | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.7578 | -121.6071 | N/A |  | N/A | N/A |  | 503 | N/A | Non-HFTD | N/A | 0.3 | 0 | 0.3 | 0 | 0 | 0
35227404 | Community Rebuild | 95F O | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Paradise | Butte | 39.7538 | -121.6172 | N/A |  | N/A | N/A |  | 2530 | N/A | Non-HFTD | N/A | 3.3 | 0 | 3.3 | 0 | 0 | 0
35227403 | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.7616 | -121.6079 | N/A |  | N/A | N/A |  | 503 | N/A | Non-HFTD | N/A | 2.2 | 0 | 2.2 | 0 | 0 | 0
35227402 | Community Rebuild | 95F O | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7703 | -121.6071 | N/A |  | N/A | N/A |  | 1618 | N/A | Tier 3 | N/A | 1.9 | 0 | 1.9 | 0 | 0 | 0
35227401 | Community Rebuild | 95F O | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Paradise | Butte | 39.7628 | -121.6233 | N/A |  | N/A | N/A |  | 69 | N/A | Tier 3 | N/A | 1.2 | 0 | 1.2 | 0 | 0 | 0
35227400 | Community Rebuild | 95F O | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7712 | -121.6031 | N/A |  | N/A | N/A |  | 1618 | N/A | Tier 3 | N/A | 1.9 | 0 | 0 | 1.9 | 0 | 0
35293508 | Base SH | 08W | ESTS | Estimating | Y | SI | Region 2 - North East | Cool | El Dorado | 38.8729 | -120.991 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 0.017565 | Tier 2 | 2.6372 | 0.51004 | 0 | 0.51004 | 0 | 0 | 0
35254067 | Base SH | 08W | ESTS | Estimating | Y | SI | Region 2 - North East | Cool | El Dorado | 38.9141 | -121.0189 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 0.017565 | Tier 2 | 2.6372 | 0.43996 | 0 | 0.43996 | 0 | 0 | 0
35223032 | Base SH | 08W | PEND | Permitting/Dependency | Y | SI | Region 2 - North East | Cool | El Dorado | 38.8855 | -121.0156 | WDRM v2 |  | 68 | 0.38665 |  | 106 | 0.017565 | Tier 2 | 2.6372 | 0.84924 | 0 | 0.84924 | 0 | 0 | 0
35334752 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.3655 | -122.0233 | WDRM v2 |  | 64 | 0.39138 |  | 768 | 0.0032459 | Tier 2 | 1.4579 | 1.81 | 0 | 1.81 | 0 | 0 | 0
35334750 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.3588 | -122.0245 | WDRM v2 |  | 64 | 0.39138 |  | 768 | 0.0032459 | Tier 2 | 1.4579 | 1.49 | 0 | 1.49 | 0 | 0 | 0
35320334 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.3618 | -122.0219 | WDRM v2 |  | 64 | 0.39138 |  | 768 | 0.0032459 | Tier 2 | 1.4579 | 2.5 | 0 | 2.5 | 0 | 0 | 0
35320333 | Base SH | 08W | ESTS | Estimating | Y | SA | Region 2 - North East | Vacaville | Solano | 38.344 | -122.0247 | WDRM v2 |  | 64 | 0.39138 |  | 768 | 0.0032459 | Tier 2 | 1.4579 | 2.95 | 0 | 2.95 | 0 | 0 | 0
35277925 | Base SH | 08W | CONS | In-Construction | Y | FR | Region 5 - Central Valley | Auberry | Fresno | 37.0746 | -119.4845 | WDRM v2 |  | 63 | 0.39206 |  | 2126 | 0.00047477 | Tier 2 | 1.7695 | 0.14148 | 0 | 0.14148 | 0 | 0 | 0
35283198 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Lakeport | Lake | 39.108 | -122.9558 | WDRM v2 |  | 58 | 0.39723 |  | 486 | 0.0056859 | Tier 2 | 1.331 | 0.27803 | 0 | 0.27803 | 0 | 0 | 0
35338384 | Base SH | 08W | PEND | Permitting/Dependency | Y | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v2 |  | 56 | 0.40353 |  | 95 | 0.018647 | Tier 2 & 3 | 1.4369 | 1.6 | 0 | 1.6 | 0 | 0 | 0
35279120 | Base SH | 08W | PEND | Permitting/Dependency | Y | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1831 | -120.3755 | WDRM v2 |  | 56 | 0.40353 |  | 95 | 0.018647 | Tier 2 & 3 | 1.4369 | 1.004 | 0 | 1.004 | 0 | 0 | 0
35278899 | Base SH | 08W | PEND | Permitting/Dependency | Y | ST | Region 5 - Central Valley | Murphys | Calaveras | 38.1735 | -120.3833 | WDRM v2 |  | 56 | 0.40353 |  | 95 | 0.018647 | Tier 2 & 3 | 1.4369 | 1.3449 | 0 | 1.3449 | 0 | 0 | 0
35280362 | Base SH | 08W | ESTS | Estimating | Y | YO | Region 5 - Central Valley | Mariposa | Mariposa | 37.4632 | -119.9483 | WDRM v2 |  | 50 | 0.4205 |  | 400 | 0.0069412 | Tier 2 & 3 | 2.4692 | 0.13258 | 0 | 0.13258 | 0 | 0 | 0
35316537 | Base SH | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Redding | Shasta | 40.624 | -122.3049 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0.00034131 | Tier 2 | 1.056 | 0.20152 | 0 | 0 | 0.20152 | 0 | 0
35234399 | Base SH | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0.00034131 | Tier 2 | 1.056 | 0.55985 | 0 | 0 | 0.55985 | 0 | 0
35233950 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0.00034131 | Tier 2 | 1.056 | 4.5701 | 0 | 0 | 4.5701 | 0 | 0
35233948 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0.00034131 | Tier 2 | 1.056 | 4.6722 | 0 | 0 | 4.6722 | 0 | 0
35219289 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Redding | Shasta | 40.6242 | -122.3039 | WDRM v2 |  | 49 | 0.42185 |  | 2405 | 0.00034131 | Tier 2 | 1.056 | 6.7973 | 0 | 0 | 6.7973 | 0 | 0
35227652 | Base SH | 08W | CONS | In-Construction | Y | SA | Region 2 - North East | Vacaville | Solano | 38.3423 | -122.0077 | WDRM v2 |  | 42 | 0.44642 |  | 383 | 0.0073117 | Tier 3 | 1.4991 | 0.53996 | 0 | 0.53996 | 0 | 0 | 0
35219276 | Base SH | 08W | PEND | Permitting/Dependency | Y | SA | Region 2 - North East | Vacaville | Solano | 38.3423 | -122.0077 | WDRM v2 |  | 42 | 0.44642 |  | 383 | 0.0073117 | Tier 3 | 1.4991 | 3.7282 | 0 | 3.7282 | 0 | 0 | 0
35226700 | Base SH | 08W | CONS | In-Construction | Y | NV | Region 2 - North East | Oroville | Butte | 39.4647 | -121.5189 | WDRM v2 |  | 29 | 0.52987 |  | 2717 | 0.0002242 | Tier 2 | 1.4877 | 0.4214 | 0.41477 | 0.0066288 | 0 | 0 | 0
35189987 | Community Rebuild | 95F O | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Paradise | Butte | 39.7404 | -121.5939 | N/A |  | N/A | N/A |  | 490 | N/A | Tier 3 | N/A | 2.7 | 0 | 2.7 | 0 | 0 | 0
35189984 | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.7471 | -121.6129 | N/A |  | N/A | N/A |  | 1178 | N/A | Non-HFTD | N/A | 3.3 | 0 | 3.3 | 0 | 0 | 0
35189983 | Community Rebuild | 95F O | CONS | In-Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.7484 | -121.6266 | N/A |  | N/A | N/A |  | 497 | N/A | Tier 3 | N/A | 2.1 | 0 | 0 | 2.1 | 0 | 0
35189853 | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.7681 | -121.5891 | N/A |  | N/A | N/A |  | 2198 | N/A | Non-HFTD | N/A | 1.4 | 0 | 1.4 | 0 | 0 | 0
35189792 | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.784 | -121.5864 | N/A |  | N/A | N/A |  | 1618 | N/A | Non-HFTD | N/A | 3.9 | 0 | 3.9 | 0 | 0 | 0
35189791 | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.7886 | -121.5873 | N/A |  | N/A | N/A |  | 1618 | N/A | Tier 3 | N/A | 2 | 0 | 2 | 0 | 0 | 0
35175548 | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.7619 | -121.6125 | N/A |  | N/A | N/A |  | 503 | N/A | Tier 3 | N/A | 3.2 | 0 | 3.2 | 0 | 0 | 0
35175547 | Community Rebuild | 95F O | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7886 | -121.5797 | N/A |  | N/A | N/A |  | 1618 | N/A | Non-HFTD | N/A | 4.8 | 0 | 4.8 | 0 | 0 | 0
35231621 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 |  | 27 | 0.5487 |  | 29 | 0.026126 | Tier 2 & 3 | 1.2678 | 2.8943 | 0 | 2.8943 | 0 | 0 | 0
35231620 | Base SH | 08W | PEND | Permitting/Dependency | Y | HB | Region 1 - North Coast | Clearlake | Lake | 38.9822 | -122.6031 | WDRM v2 |  | 27 | 0.5487 |  | 29 | 0.026126 | Tier 2 & 3 | 1.2678 | 2.6782 | 0 | 2.6782 | 0 | 0 | 0
35219096 | Base SH | 08W | CONS | In-Construction | Y | DI | Region 3 - Bay Area | Pittsburg | Contra Costa | 37.9907 | -121.896 | WDRM v2 |  | 21 | 0.61454 |  | 571 | 0.00471 | Tier 2 | 1.0994 | 1.8303 | 1.8019 | 0.028409 | 0 | 0 | 0
35144480 | Community Rebuild | 95F O | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Magalia | Butte | 39.8116 | -121.5956 | N/A |  | N/A | N/A |  | 302 | N/A | Tier 3 | N/A | 2.6 | 0 | 2.6 | 0 | 0 | 0
35219093 | Base SH | 08W | PEND | Permitting/Dependency | Y | DI | Region 3 - Bay Area | Concord | Contra Costa | 37.9632 | -121.9407 | WDRM v2 |  | 18 | 0.65331 |  | 448 | 0.0062529 | Tier 2 | 1.0387 | 1.14 | 0 | 1.14 | 0 | 0 | 0
35127550 | Community Rebuild | 95F CEMA | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7858 | -121.6004 | N/A |  | N/A | N/A |  | 1546 | N/A | Tier 3 | N/A | 2.9 | 0 | 0 | 2.9 | 0 | 0
35127360 | Community Rebuild | 95F O | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7461 | -121.6435 | N/A |  | N/A | N/A |  | 875 | N/A | Tier 2 | N/A | 1.3 | 0 | 0 | 1.3 | 0 | 0
35126752 | Community Rebuild | 95F O | ADER | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7333 | -121.6353 | N/A |  | N/A | N/A |  | 497 | N/A | Tier 3 | N/A | 1.9 | 0 | 0 | 1.9 | 0 | 0
35126750 | Community Rebuild | 95F O | CONS | In-Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.7741 | -121.5895 | N/A |  | N/A | N/A |  | 2198 | N/A | Tier 3 | N/A | 2.4 | 0 | 2.4 | 0 | 0 | 0
35126645 | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.7612 | -121.6342 | N/A |  | N/A | N/A |  | 503 | N/A | Tier 3 | N/A | 2.2 | 0 | 2.2 | 0 | 0 | 0
35228186 | Base SH | 08W | CONS | In-Construction | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7564 | -122.6056 | WDRM v2 |  | 14 | 0.71618 |  | 443 | 0.006302 | Tier 2 & 3 | 1.4193 | 1.49 | 0 | 1.49 | 0 | 0 | 0
35118676 | Community Rebuild | 95F O | UNSC | Ready for Construction | Y | NV | Region 2 - North East | Paradise | Butte | 39.7551 | -121.6455 | N/A |  | N/A | N/A |  | 69 | N/A | Tier 3 | N/A | 3.2 | 0 | 3.2 | 0 | 0 | 0
35118674 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Magalia | Butte | 39.8082 | -121.6017 | N/A |  | N/A | N/A |  | 302 | N/A | Tier 3 | N/A | 2.1 | 0 | 0 | 2.1 | 0 | 0
35118673 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Magalia | Butte | 39.8005 | -121.6047 | N/A |  | N/A | N/A |  | 302 | N/A | Tier 3 | N/A | 3.1 | 0 | 0 | 3.1 | 0 | 0
35117455 | Community Rebuild | 08W | ADER | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.7813 | -121.594 | N/A |  | N/A | N/A |  | 1546 | N/A | Tier 3 | N/A | 1.4 | 0 | 1.4 | 0 | 0 | 0
35227864 | Base SH | 08W | CONS | In-Construction | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7564 | -122.6056 | WDRM v2 |  | 14 | 0.71618 |  | 443 | 0.006302 | Tier 2 & 3 | 1.4193 | 1.3212 | 0.36136 | 0.95985 | 0 | 0 | 0
35220895 | Base SH | 08W | CONS | In-Construction | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7569 | -122.607 | WDRM v2 |  | 14 | 0.71618 |  | 443 | 0.006302 | Tier 2 & 3 | 1.4193 | 2.0494 | 0 | 2.0494 | 0 | 0 | 0
35112126 | Community Rebuild | 08W | ESTS | Estimating | Y | NV | Region 2 - North East | Paradise | Butte | 39.78 | -121.6092 | N/A |  | N/A | N/A |  | 1546 | N/A | Tier 3 | N/A | 2.1 | 0 | 0 | 2.1 | 0 | 0
35224713 | Fire Rebuild | 08W | UNSC | Ready for Construction | Y | NV | Region 2 - North East | Belden | Plumas | 39.9007 | -121.3594 | WDRM v2 |  | 11 | 0.73491 |  | 21 | 0.029234 | Tier 2 & 3 | 3 | 1.9095 | 0 | 1.9095 | 0 | 0 | 0
35224712 | Fire Rebuild | 08W | UNSC | Ready for Construction | Y | NV | Region 2 - North East | Belden | Plumas | 39.9101 | -121.3297 | WDRM v2 |  | 11 | 0.73491 |  | 21 | 0.029234 | Tier 2 & 3 | 3 | 2.2729 | 0 | 2.2729 | 0 | 0 | 0
35227160 | Base SH | 08W | ESTS | Estimating | Y | HB | Region 1 - North Coast | Middletown | Lake | 38.7573 | -122.606 | WDRM v2 |  | 8 | 0.91632 |  | 392 | 0.007089 | Tier 2 | 1.4753 | 1.3201 | 0 | 0 | 1.3201 | 0 | 0
35226629 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Redding | Shasta | 40.6253 | -122.4633 | WDRM v2 |  | 7 | 1.2524 |  | 48 | 0.022602 | Tier 3 | 2.481 | 4.8061 | 0 | 4.8061 | 0 | 0 | 0
35226628 | Base SH | 08W | PEND | Permitting/Dependency | Y | NV | Region 2 - North East | Redding | Shasta | 40.6253 | -122.4633 | WDRM v2 |  | 7 | 1.2524 |  | 48 | 0.022602 | Tier 3 | 2.481 | 0.85511 | 0 | 0.85511 | 0 | 0 | 0

## Definitions
Definitions
Category
Category Type | Description
Base SH | Planned projects in System Hardening program
Community Rebuild | Specific Fire Rebuild in Paradise, Magalia, Greenville Rebuilds
Fire Rebuild | System Hardening Scope as a result of fires in HFTD
Targeted UG | Projects targeted for New Program/MAT Code (specific for UG projects) to be split away from SH
Idle Facilities | Removal of Primary Conductor in HFTD
Other | Non-08W projects (New Business, WRO, Capacity, Rule 20A, etc.)
MAT Code
MAT Code | Description
06A | Feeder Projects Associated with Substation Capacity
08W | System Hardening Wildfire Resiliency Projects
10K | Electric Distribution Work Requested by Others (WRO) – New Business Underground Relocation
2BP | Maintenance Program: Undergrounding Capital Projects
30A | Rule 20A: Undergrounding Capital Projects
3UG | Targeted Undergrounding
95F | Electric Distribution Major Emergency
SAP Status and Status
SAP Status | Status
N/A | Pre-scoping
UNSE | Scoping/Scoped
ADER | Estimating
APPR | Estimating
ESTS | Estimating
PEND | Permitting/Dependency
UNSC | Ready for Construction
CONS | * In-Construction
DOCC | * Post-Construction
MAPP | Post-Construction
FICL | Post-Construction
POST | Post-Construction
PREC | Post-Construction
CLSD | Closed
*May apply to projects with pre-Construction SAP statuses with completed miles
Division
Division Acronym | Division Name
CC | Central Coast
CV | Central Valley
DA | De Anza
DI | Diablo
EB | East Bay
FR | Fresno
HB | Humboldt
KE | Kern
LP | Los Padres
NB | North Bay
NV | North Valley
PN | Peninsula
SA | Sacramento
SF | San Francisco
SI | Sierra
SJ | San Jose
SO | Sonoma
ST | Stockton
YO | Yosemite
Risk Rank | Results of the relevant risk model (e.g. WDRM v2, WDRM v3) where circuit segments are ranked on a 1 to N basis, where 1 is the highest risk circuit segment, and N is the lowest risk.
Mean Risk | Summation of the total risk of all pixels (100-meter x 100-meter cell) linked to a circuit segment, divided by the total number of pixels.
Feasibility score by CPZ | Cost multiplier indicating the difficulty of undergrounding the circuit segment (Circuit Protection Zone (CPZ)) based on presence of hard rock, water crossing, and gradient. The scale ranges from 1 to 3, with 3 being most challenging.