**SOLAR CHOICE PROGRAM:** Form of Power Purchase Agreement

**Standard contract terms and conditions shown in shaded text are those that “may not be modified” per CPUC Decisions (“D.”) 07‑11‑025; D.10-03-021, as modified by D.11-01-025; and D.13-11-024.**

**POWER PURCHASE AGREEMENT**

**Between**

**PACIFIC GAS AND ELECTRIC COMPANY**

(as “Buyer”)

and

(as “Seller”)

**POWER PURCHASE AGREEMENT**

**TABLE OF CONTENTS**

PREAMBLE

GENERAL TERMS AND CONDITIONS

ARTICLE ONE: GENERAL DEFINITIONS 1

ARTICLE TWO: GOVERNING TERMS AND TERM 23

2.1 Entire Agreement 23

2.2 Interpretation 23

2.3 Authorized Representatives 24

2.4 Separation of Functions 24

2.5 Conditions Precedent 24

2.6 Term 24

2.7 Binding Nature 25

ARTICLE THREE: OBLIGATIONS AND DELIVERIES 25

3.1 Seller’s and Buyer’s Obligations 25

3.2 Green Attributes 35

3.3 Resource Adequacy 35

3.4 Transmission and Scheduling 37

3.5 Standards of Care 39

3.6 Metering 40

3.7 Availablility and Outage Notification 40

3.8 Operations Logs and Access Rights 43

3.9 New Generation Facility 43

ARTICLE FOUR: COMPENSATION; MONTHLY PAYMENTS 47

4.1 Price 47

4.2 Excess Delivered and Deemed Delivered Energy 48

4.3 CAISO Charges 49

4.4 Additional Compensation 49

ARTICLE FIVE: EVENTS OF DEFAULT; PERFORMANCE REQUIREMENT; REMEDIES 50

5.1 Events of Default 50

5.2 Remedies 51

5.3 Calculation of Termination Payment 52

5.4 Notice of Payment of Termination Payment 52

5.5 Disputes With Respect to Termination Payment 52

5.6 Rights And Remedies Are Cumulative 53

5.7 Duty to Mitigate 53

5.8 Damage Payment for Failure to Achieve Guaranteed Dates 53

ARTICLE SIX: PAYMENT 53

6.1 Billing and Payment; Remedies 53

6.2 Disputes and Adjustments of Invoices 53

ARTICLE SEVEN: LIMITATIONS 54

7.1 Limitation of Remedies, Liability and Damages 54

ARTICLE EIGHT: CREDIT AND COLLATERAL REQUIREMENTS 54

8.1 Buyer Financial Information 54

8.2 Seller Financial Information 55

8.3 Grant of Security Interest/Remedies 55

8.4 Performance Assurance 55

8.5 Letter of Credit 57

ARTICLE NINE: GOVERNMENTAL CHARGES 58

9.1 Cooperation 58

9.2 Governmental Charges 58

ARTICLE TEN: MISCELLANEOUS 58

10.1 Recording 58

10.2 Representations and Warranties 58

10.3 Covenants 61

10.4 Title and Risk of Loss 61

10.5 Indemnities 61

10.6 Assignment 62

10.7 Confidentiality 63

10.8 RPS Confidentiality 64

10.9 Audit 64

10.10 Insurance 64

10.11 Access to Financial Information 66

10.12 Governing Law 66

10.13 General 66

10.14 Severability 66

10.15 Counterparts 66

10.16 Mobile Sierra 67

ARTICLE ELEVEN: TERMINATION EVENT 67

11.1 Force Majeure Termination Event 67

ARTICLE TWELVE: DISPUTE RESOLUTION 69

12.1 Intent of the Parties 69

12.2 Management Negotiations 69

12.3 Mediation 69

12.4 Arbitration 70

ARTICLE THIRTEEN: NOTICES 71

SIGNATURES 72

**APPENDICES**

The following Appendices constitute a part of this Agreement and are incorporated into this Agreement by reference:

Appendix I Form of Letter of Credit

Appendix II Initial Energy Delivery Date Confirmation Letter

Appendix III Form of Progress Report

Appendix IV Construction Start and Commercial Operation Certification Forms and Procedures

Appendix IV-1 Construction Start Form of Certification

Appendix IV-2 Commercial Operation Certification Procedure

Attachment A Commercial Operation Form of Certification

Appendix V GEP Damages Calculation

Appendix VI Notification Requirements for Available Capacity and Project Outages

Appendix VII Form of Financing Consent to Assignment

Attachment A Financing Consent Termination Notice

Appendix VIII Seller Documentation Condition Precedent

Appendix IX Form of Actual Availability Report

Attachment A Form of Actual Availability Report

Appendix X Telemetry Parameters for Solar Facility

Appendix XI Form of Letter of Concurrence

Appendix XII Supplier Diversity Program

Appendix XIII Project Specifications

Appendix XIV Section 3.3(e) Liquidated Damages Calculation

**POWER PURCHASE AGREEMENT**

**COVER SHEET**

This Power Purchase Agreement (“Agreement”) is entered into between Pacific Gas and Electric Company, a California corporation (“Buyer” or “PG&E”), and \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ ***[insert name of Seller]***, a \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ ***[include place of formation and business type]*** (“Seller”), as of the Execution Date. The information contained in this Cover Sheet shall be completed by Seller and incorporated into the Agreement.

**A. Transaction Type**

Seller may not modify the Transaction Type designated in this Part A of the Cover Sheet.

Project Type: □ Unreserved

□ Environmental Justice

Product: □ As-Available

Deliverability:

□ Energy Only Status

□ Partial Capacity Deliverability Status (“PCDS”)

a) If PCDS is selected, provide the Expected PCDS Date, or the date the Project received a PCDS finding if already received:\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (mm/dd/yyyy);

b) The Partial Capacity Deliverability Status Amount the Project will obtain is \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_MW.

□ Full Capacity Deliverability Status (“FCDS”)

a) If FCDS is selected, provide the Expected FCDS Date, or the date the Project received a FCDS finding if already received:\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (mm/dd/yyyy).

Transaction type pursuant to Section 3.1(b) of the Agreement: Full Buy/Sell

Seller shall elect one of the following Delivery Terms:

□ ten (10) Contract Years

□ fifteen (15) Contract Years

□ twenty (20) Contract Years

**B. Project Description Including Description of Site**

Contract Capacity: [\_\_\_\_\_\_\_\_\_\_\_] MW ***[Provide the maximum capacity to be made available to PG&E pursuant to the transaction. Note: The Total Nameplate Rated Power in Appendix XIII – Project Specifications of this Agreement may be no greater than 20 MW for Unreserved Projects and 1 MW for Environmental Justice Projects.]***

(i) Project Development:

(a) The Project is a

□ New Project

(1) The Expected Construction Start Date of the Project:

(2) The date on which the Commercial Operation Date of the Project is expected (must be no later than the Guaranteed Commercial Operation Date):

(b) The Project is:

□ Utilizing Shared Facilities

□ Not utilizing Shared Facilities

(c) Project development Milestone schedule ***[to be completed by Buyer and Seller. Insert additional rows if necessary]:***

|  |  |
| --- | --- |
| **Milestone** | **Date for Completion** |
| **Permitting completed** |  |
| **Financing completed** |  |
| **Start of construction** |  |
| **Interconnection Agreement executed** |  |
| **Commercial Operation Achieved** |  |

(ii) Supplier Diversity. For the purpose of Section 3 of the Supplier Diversity Program obligation set forth in Appendix XII of this Agreement, Seller’s supplier diversity spend target for Work supporting the construction of the Project prior to the Commercial Operation Date is \_\_\_%, and Seller’s supplier diversity spend target for Work supporting the operation and maintenance of the Project after the Initial Energy Delivery Date is \_\_\_%.

**C. Contract Price**

The Contract Price and Deemed Delivered Energy Price, for each Contract Year paid by Buyer to Seller subject to Article Four is:

| **Contract Year** | **Contract Price ($/MWh)** |
| --- | --- |
| 1 |  |
| 2 |  |
| 3 |  |
| 4 |  |
| 5 |  |
| 6 |  |
| 7 |  |
| 8 |  |
| 9 |  |
| 10 |  |
| 11 |  |
| 12 |  |
| 13 |  |
| 14 |  |
| 15 |  |
| 16 |  |
| 17 |  |
| 18 |  |
| 19 |  |
| 20 |  |

**D. Delivery Term Contract Quantity Schedule**

Length of Delivery Term (in Contract Years):

|  |  |
| --- | --- |
| **Contract Year** | **Contract Quantity (MWh)** |
| 1 |  |
| 2 |  |
| 3 |  |
| 4 |  |
| 5 |  |
| 6 |  |
| 7 |  |
| 8 |  |
| 9 |  |
| 10 |  |
| 11 |  |
| 12 |  |
| 13 |  |
| 14 |  |
| 15 |  |
| 16 |  |
| 17 |  |
| 18 |  |
| 19 |  |
| 20 |  |

**E**. **Performance Assurance *[(as described in the Solar Choice Solicitation Protocol]***

* Project Development Security ***[provide dollar amount]***

Dollar Amount: $ \_\_\_\_\_\_\_\_\_\_\_\_\_\_

* Cash, or
* Letter of Credit
* Delivery Term Security ***[provide dollar amount]***

Dollar Amount: $ \_\_\_\_\_\_\_\_\_\_\_\_\_\_

* Cash, or
* Letter of Credit
* Term Security ***[provide dollar amount] [Applies to GTSR Projects 3MW or less]***

Dollar Amount: $ \_\_\_\_\_\_\_\_\_\_\_\_\_\_

* Cash, or
* Letter of Credit

**F**. **Operational Characteristics.**

Operational characteristics of the Project are listed below.

* Maximum generation capacity (PMax of the Project): \_\_\_\_MW
* Minimum generation capacity (PMin of the Project): 0 MW
* Minimum Dispatchable Generation (DMin of the Project): \_\_\_ MW
* Ramp rate: \_\_\_\_MW/Minute
* Maximum number of Start-ups per calendar day (if any such operational limitations exist): \_\_\_\_\_\_\_

Other requirements**:**

* Start-Up Time: \_\_\_\_\_Minutes
* Minimum Run Time after Start-up (if applicable): \_\_\_\_\_Minutes
* Minimum Down Time after Shut-Down (if applicable):\_\_\_\_\_Minutes

***[Note: Sellers should enter the maximum flexibility the Project can offer given the actual physical characteristics of the technology.]***

**G. Notices List**

|  |  |
| --- | --- |
| Name: ***[Seller’s Name]***, a ***[include place of formation and business type]*** (“Seller”) | Name: Pacific Gas and Electric Company, a California corporation  (“Buyer” or “PG&E”) |
| All Notices: ***[Seller to complete]*** | All Notices: |
| Delivery Address: | Delivery Address: |
| Street: | 300 Lakeside Drive, Suite 210 |
| City: State: Zip: | Oakland, CA 94612 |
|  |  |
| Mail Address: (if different from above) | Mail Address: |
|  | P.O. Box 28209  Oakland, CA 94604 |
| Attn: | Attn: Kelly Everidge (Kelly.Everidge@pge.com)  Senior Director, Contract Mgmt, Settlements, and Reporting |
| Phone: | Phone: (415)-517-6544 |
| Email: |  |
|  |  |
| DUNS: | DUNS: |
| Federal Tax ID Number: | Federal Tax ID Number: |
|  |  |
| **Invoices:** | **Invoices:** |
| Attn: | Attn: Kelly Wong (K.Wong@pge.com) |
|  | Senior Manager, Electric Settlements |
| Phone: | Phone: (510) 220-6064 |
| Email: |  |
|  |  |
| **Scheduling:** | **Scheduling:** |
| Attn: | Attn: Day-Ahead Operations (DAEnergy@pge.com) |
| Phone: | Phone: (415) 973-1971 |
| Email: |  |
|  |  |
| **Payments:** | **Payments:** |
| Attn: | Attn: Kelly Wong (K.Wong@pge.com) |
|  | Senior Manager, Electric Settlements |
| Phone: | Phone: (510) 220-6064 |
| Email: |  |
|  |  |
| **Wire Transfer per Section 8:** | **Wire Transfer per Section 8:** |
| BNK:  ABA:  ACCT: | BNK:  ABA:  ACCT: |
|  |  |
| **Electronic funds transfer via ACH:** | **Electronic funds transfer via ACH:** |
| BNK:  ABA:  ACCT: | BNK:  ABA:  ACCT: |
|  |  |
| **Credit and Collections:** | **Credit and Collections:** |
| Attn: | Attn: PG&E Credit Risk Management |
| Phone: | Phone: (415) 636-0725 |
| Email: | Email: pgeriskcredit@pge.com |
|  |  |
| **With additional Notices of an Event of Default to Contract Manager**: | **Contract Manager:** |
| Attn: | Attn: Ryan Susanto (Ryan.Susanto@pge.com)  Senior Manager, Contract Management |
| Phone: | Phone: (650) 255-2343 |
| Email: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |  |

**PREAMBLE**

This Power Purchase Agreement, together with the Cover Sheet, appendices and any other attachments referenced herein, is made and entered into between PG&E and Seller, as of the Execution Date. Buyer and Seller hereby agree to the following:

**GENERAL TERMS AND CONDITIONS**

# **ARTICLE ONE: GENERAL DEFINITIONS**

## “Actual Availability Report” has the meaning set forth in Section 3.1(l)(i)(G).

## “Additional Extension” has the meaning set forth in Section 3.1(c)(ii).

## “Affiliate” means, with respect to any person or entity, any other person or entity (other than an individual) that (a) directly or indirectly, through one or more intermediaries, controls, or is controlled by such person or entity or (b) is under common control with such person or entity. For this purpose, “control” means the direct or indirect ownership of fifty percent (50%) or more of the outstanding capital stock or other equity interests having ordinary voting power.

## “Agreement” means this Power Purchase Agreement between Buyer and Seller, which is comprised of the Cover Sheet, Preamble, these General Terms and Conditions, and all appendices, schedules and any written supplements attached hereto and incorporated herein by references, as well as all written and signed amendments and modifications thereto. For purposes of Section 10.12, the word “agreement” shall have the meaning set forth in this definition. For purposes of Section 3.1(k)(viii), the word “contract” shall have the meaning set forth in this definition.

## “Ancillary Services” has the meaning set forth in the CAISO Tariff.

## “Arbitration” has the meaning set forth in Section 12.4.

## “As-Available Product” means a Product that is powered by a solar photovoltaic facility. Subject to the terms of this Agreement, (a) Seller is obligated to sell and deliver and (b) Buyer is obligated to purchase and receive, the Energy component of As-Available Product from the Project whenever such Energy is capable of being generated from the Project. The Seller does not control the availability of fuel supply to the Project producing As-Available Product and lacks the ability to store energy.

## “Availability Workbook” has the meaning set forth in Appendix IX.

## “Available Capacity” means the capacity from the Project, expressed in whole megawatts, that is available to generate Product.

## “Balancing Authority” has the meaning set forth in the CAISO Tariff.

## “Bankrupt” means with respect to any entity, such entity that (a) files a petition or otherwise commences, authorizes or acquiesces in the commencement of a proceeding or cause of action under any bankruptcy, insolvency, reorganization or similar Law, or has any such petition filed or commenced against it and such case filed against it is not dismissed in ninety (90) days, (b) makes an assignment or any general arrangement for the benefit of creditors, (c) otherwise becomes bankrupt or insolvent (however evidenced), (d) has a liquidator, administrator, receiver, trustee, conservator or similar official appointed with respect to it or any substantial portion of its property or assets, or (e) is generally unable to pay its debts as they fall due.

## “Bid” has the meaning set forth in the CAISO Tariff.

## “Business Day” means any day except a Saturday, Sunday, or a Federal Reserve Bank holiday and shall be between the hours of 8:00 a.m. and 5:00 p.m. local time for the relevant Party’s principal place of business where the relevant Party, in each instance unless otherwise specified, shall be the Party from whom the Notice, payment or delivery is being sent and by whom the Notice or payment or delivery is to be received.

## “Buyer” has the meaning set forth in the Cover Sheet.

## “Buyer Curtailment Order” means the instruction from Buyer to Seller to reduce generation from the Project below the CAISO final market forecast amount for the Project for the period of time set forth in such order, for reasons unrelated to a Planned Outage, Forced Outage, Force Majeure and/or Curtailment Order. Buyer Curtailment Order includes curtailment instructions during time periods that the Scheduling Coordinator either (a) submitted a CAISO final market Energy Supply Bid and such curtailment is solely a result of the CAISO implementing the Energy Supply Bid; or (b) submitted a CAISO final market Self-Schedule for less than the amount of the final market Energy forecasted to be produced from the Project. With respect to curtailments set forth in 1.15(a), curtailments implemented in the Real-Time Market shall be considered Buyer Curtailment Order if the Real-Time Price is less than the Energy Supply Bid.

## “Buyer Curtailment Period” means the period of time, as measured using current Settlement Intervals, during which Seller reduces generation from the Project pursuant to a Buyer Curtailment Order. The Buyer Curtailment Period excludes any Settlement Interval subject to a Curtailment Order and shall be inclusive of the time required for the Project to ramp down and ramp up; provided that such time periods to ramp down and ramp up shall be consistent with the Ramp Rate designated in the Cover Sheet.

## “Buyer’s Notice of First Offer Acceptance” has the meaning set forth in Section 3.9(e)(ii) or Section 11.1(b)(ii), as applicable.

## “Buyer’s WREGIS Account” has the meaning set forth in Section 3.1(k)(i).

## “CAISO” means the California Independent System Operator Corporation or any successor entity performing similar functions.

## “CAISO Exemption” means that exemption granted by the CAISO, in written form, that approves Seller’s request to install the low-side metering scheme for the Project, as such scheme is defined and required in Section 10.2.10.2 of the CAISO Tariff.

## “CAISO Global Resource ID” means the number or name assigned by the CAISO to the Project and the Project’s dedicated CAISO Revenue Meter.

## “CAISO Grid” has the same meaning as “CAISO Controlled Grid” as defined in the CAISO Tariff.

## “CAISO Metered Entity” has the meaning set forth in the CAISO Tariff.

## “CAISO Penalties” means any fees, liabilities, assessments, or similar charges assessed by the CAISO for (a) violation of the CAISO Tariff and all applicable protocols, WECC rules or CAISO operating instructions or orders or (b) as a result of a Party’s failure to follow Good Utility Practices. In either case, “CAISO Penalties” do not include the costs and charges related to scheduling and Imbalance Energy as addressed in Section 4.5(b) of this Agreement.

## “CAISO Revenue Meter” means a CAISO approved revenue quality meter, CAISO approved data processing gateway or remote intelligence gateway, telemetering equipment and data acquisition services sufficient for monitoring, recording and reporting, in real time, all electric energy produced by the Project less station use.

## “CAISO Revenues” means the net amount resulting from (a) the credits and other payments received by Buyer, as Seller’s Scheduling Coordinator, as a result of test energy from the Project delivered by Seller during the Test Period, including revenues associated with CAISO dispatches and (b) the debits, costs, penalties and interest that are directly assigned by the CAISO to the CAISO Global Resource ID for the Project for, or attributable to, scheduling and deliveries from the Project under this Agreement, which amount may result in a negative or positive value.

## “CAISO Tariff” means the California Independent System Operator Corporation, Fifth Replacement FERC Electric Tariff (Open Access Transmission Tariff), as it may be amended, supplemented or replaced (in whole or in part) from time to time.

## “California Renewables Portfolio Standard” means the renewable energy program and policies established by California State Senate Bills 1038 and 1078 as amended by Senate Bill SB1X, and codified in California Public Utilities Code Sections 399.11 through 399.31 and California Public Resources Code Sections 25740 through 25751, as such provisions are amended or supplemented from time to time.

## “Capacity Attributes” means, any and all of the following attributes:

(a) System RA Attributes,

(b) Local RA Attributes, and

(c) Other Capacity Attributes

## “CEC” means the California Energy Commission or its successor agency.

## “CEC Certification and Verification” means that the CEC has certified (or, with respect to periods before the Project has commenced commercial operation (as such term is defined by and according to the CEC), that the CEC has pre-certified) that the Project is an ERR for purposes of the California Renewables Portfolio Standard and that all Energy produced by the Project qualifies as generation from an ERR for purposes of the Project.

## “Claims” means all third party claims or actions, threatened or filed and, whether groundless, false, fraudulent or otherwise, that directly or indirectly relate to the subject matter of an indemnity, and the resulting losses, damages, expenses, attorneys’ fees and court costs, whether incurred by settlement or otherwise, and whether such claims or actions are threatened or filed prior to or after the termination or expiration of this Agreement.

## “Commercial Operation” means the Project is operating and able to produce and deliver the Product to Buyer pursuant to the terms of this Agreement.

## “Commercial Operation Date” means the date on which Seller (a) notifies Buyer that Commercial Operation has commenced, (b) notifies Buyer that all Reliability Network Upgrades identified in the Project’s Generator Interconnection Agreement have been completed, and (c) provides a certification of a Licensed Professional Engineer, substantially in the form attached hereto as Attachment A to Appendix IV-2, demonstrating satisfactory completion of the Commercial Operation Certification Procedure as provided in Appendix IV-2 hereto.

## “Condition Precedent” means each of, or one of, the conditions set forth in Section 2.5(a)(i) through (iv) and “Conditions Precedent” shall refer to all of the conditions set forth in Section 2.5(a)(i) through (iv).

## “Confidential Information” has the meaning set forth in Section 10.7(a)

## “Construction Start Date” means the later to occur of the date on which Seller delivers to Buyer (a) a copy of the Notice to Proceed that Seller has delivered to the EPC Contractor for the Project, and (b) a written Certification substantially in the form attached hereto as Appendix IV-1.

## “Contract Capacity” has the meaning set forth in Section 3.1(f).

## “Contract Capacity Commitment” means the amount of the Contract Capacity that may be constructed pursuant to the Governmental Approvals received or obtained by Seller as of, for a New Project, the Guaranteed Commercial Operation Date (as may be extended pursuant to Section 3.9(c)).

## “Contract Price” means the price in United States dollars ($U.S.) (unless otherwise provided for) to be paid by Buyer to Seller for the purchase of the Product, as specified in the Cover Sheet.

## “Contract Quantity” means the quantity of Delivered Energy expected to be delivered by Seller during each Contract Year as set forth in Section 3.1(e) and Cover Sheet Section D .

## “Contract Year” means a period of twelve (12) consecutive months. The first Contract Year shall commence on the Initial Energy Delivery Date and each subsequent Contract Year shall commence on the anniversary of the Initial Energy Delivery Date.

## “Costs” means, with respect to the Non-Defaulting Party, (a) brokerage fees, commissions and other similar third party transaction costs and expenses reasonably incurred by such Party either in terminating any arrangement pursuant to which it has hedged its obligations or in entering into new arrangements which replace the Terminated Transaction; and (b) all reasonable attorneys’ fees and expenses incurred by the Non-Defaulting Party in connection with the termination of the Transaction.

## “Cover Sheet” means the cover sheet to this Agreement, completed by Seller and incorporated into the Agreement.

## “CPUC” or “Commission” means the California Public Utilities Commission, or successor entity.

## “CPUC Approval” means a final and non-appealable order of the CPUC, without conditions or modifications unacceptable to the Parties, or either of them, which contains the following terms:

(a) approves this Agreement in its entirety, including payments to be made by the Buyer, subject to CPUC review of the Buyer’s administration of the Agreement; and

(b) finds that any procurement pursuant to this Agreement is procurement from an eligible renewable energy resource for purposes of determining Buyer’s compliance with any obligation that it may have to procure eligible renewable energy resources pursuant to the California Renewables Portfolio Standard (Public Utilities Code Section 399.11 *et seq*.), Decision 03-06-071, or other applicable law.

CPUC Approval will be deemed to have occurred on the date that a CPUC decision containing such findings becomes final and non-appealable.

For purposes of this section, a CPUC Energy Division disposition which contains such findings or deems approved an advice letter requesting such findings shall be deemed to satisfy the CPUC decision requirement.

## “CRS” means the Center for Resource Solutions or any successor entity performing similar functions.

## “Credit Rating” means, with respect to any entity, (a) the rating then assigned to such entity’s unsecured senior long-term debt obligations (not supported by third party credit enhancements) or (b) if such entity does not have a rating for its unsecured senior long-term debt obligations, then the rating assigned to such entity as an issuer rating by S&P and/or Moody’s. If the entity is rated by both S&P and Moody’s and such ratings are not equivalent, the lower of the two ratings shall determine the Credit Rating. If the entity is rated by either S&P or Moody’s, but not both, then the available rating shall determine the Credit Rating.

## “Cure” has the meaning set forth in Section 8.5(b).

## “Cured Performance Measurement Period” has the meaning set forth in Section 3.1(e)(ii)(C).

## “Cure Payment Period” has the meaning set forth in Section 3.1(e)(ii)(C)(III).

## “Curtailment Order” means any of the following:

(a) an Operating Instruction from the CAISO, Reliability Coordinator, Balancing Authority or any other entity having similar authority or performing similar functions during the Delivery Term, instructing a Party to curtail Energy deliveries, which may come in the form of a request to return to a specified Dispatch Operating Target, consistent with the CAISO Tariff, for any reason;

(b) a curtailment ordered by the Participating Transmission Owner, distribution operator (if interconnected to distribution or sub-transmission system), or any other entity having similar authority or performing similar functions during the Delivery Term, for any reason;

(c) an Operating Instruction resulting from maintenance or construction on the Participating Transmission Owner’s or distribution operator’s transmission or distribution facilities that prevents (i) Buyer from receiving or (ii) Seller from delivering Delivered Energy at the Delivery Point.

(d) a curtailment in accordance with Seller’s obligations under its Generator Interconnection Agreement with the Participating Transmission Owner or distribution operator.

## For the avoidance of doubt, if Scheduling Coordinator submits a Self-Schedule and/or an Energy Supply Bid that clears, in full, the applicable CAISO market for the full amount of Energy forecasted to be produced from the Project for any time period, any notice from the CAISO having the effect of requiring a reduction during the same time period is a Curtailment Order, not a Buyer Curtailment Order.

## “Curtailment Period” means the period of time during which Seller reduces generation from the Project, pursuant to a Curtailment Order. The Curtailment Period shall be inclusive of the time required for the Project to ramp down and ramp up.

## “Daily Delay Damages” means with respect to the Guaranteed Commercial Operation Date, an amount equal to (a) divided by (b), where (a) is $60/kW multiplied by the Contract Capacity of the Project as reflected in Section B of the Cover Sheet, and (b) is the number 180.

## “Daily Delay Damages Extension” has the meaning set forth in Section 3.9(c)(ii)(B).

## “Damage Payment” **means the dollar amount equal to the amount to be posted as Project Development Security pursuant to Section 8.4(a)(i) hereof.**

## “Day-Ahead Availability Notice” has the meaning set forth in Section 3.7(a)(iii).

## “Day-Ahead Market” has the meaning set forth in the CAISO Tariff.

## “Deemed Delivered Energy” means the amount of Energy expressed in MWh that the Project would have produced and delivered to the Delivery Point, but that is not produced by the Project and delivered to the Delivery Point during a Buyer Curtailment Period, which amount shall be equal to (a) the EIRP Forecast, expressed in MWh, applicable to the Buyer Curtailment Period, whether or not Seller is participating in EIRP during the Buyer Curtailment Period, less the amount of Delivered Energy delivered to the Delivery Point during the Buyer Curtailment Period or, (b) if there is no EIRP Forecast available, the result of the equation provided pursuant to Section 3.1(l)(i)(G) and using relevant Project availability, weather and other pertinent data for the period of time during the Buyer Curtailment Period less the amount of Delivered Energy delivered to the Delivery Point during the Buyer Curtailment Period; *provided that*, if the applicable difference calculated pursuant to (a) or (b) above is negative as compared to the amount of metered Energy at the CAISO Revenue Meter for the Project, the Deemed Delivered Energy shall be zero (0). For clarity, Deemed Delivered Energy shall not include Delivered Energy that is less than the instructed MWh for a Buyer Curtailment Order during a Buyer Curtailment Period. Deemed Delivered Energy shall be calculated as follows:

## Deemed Delivered Energy (“DDE”) = A - Max (B,C), where:

## A = EIRP Forecast, converted to MWh

## B = MWh as instructed during a Buyer Curtailment Period. For the purpose of calculating DDE, the MWh as instructed during a Buyer Curtailment Period shall be the total Expected Energy, as defined in the CAISO Tariff.

## C = Delivered Energy delivered to the Delivery Point during the Buyer Curtailment Period.

## “Deemed Delivered Energy Price” means the price in United States dollars ($U.S.) (unless otherwise provided for) to be paid by Buyer to Seller for Deemed Delivered Energy, as specified in the Cover Sheet.

## “Defaulting Party” means the Party that is subject to an Event of Default.

## “Deficient Month” has the meaning set forth in Section 3.1(k)(v).

## “Deliverability Assessment” has the meaning set forth in the CAISO Tariff.

## “Deliverability Finding Deadline” shall be two (2) calendar years after the RA Start Date. The Deliverability Finding Deadline shall be no later than December 31, 2028

## “Delivered Energy” means all Energy produced from the Project as measured in MWh at the CAISO Revenue Meter of the Project and in accordance with the CAISO Tariff, which shall include any applicable adjustments for power factor and Electrical Losses.

## “Delivery Network Upgrade” has the meaning set forth in the CAISO Tariff.

## “Delivery Point” means the point at which Buyer receives Seller’s Product, as identified in Section 3.1(d).

## “Delivery Term” has the meaning set forth in Section 3.1(c)(i) and shall be of the length specified in the Cover Sheet.

## “Delivery Term Security” means the Performance Assurance that Seller is required to maintain, as specified in Article Eight, to secure performance of its obligations during the Delivery Term.

## “Disclosing Party” has the meaning set forth in Section 10.7.

## “Dispatch Instruction” has the meaning set forth in the CAISO Tariff.

## “Dispatch Interval” has the meaning set forth in the CAISO Tariff.

## “Dispatch Operating Target” has the meaning set forth in the CAISO Tariff.

## “Distribution Loss Factor” is a multiplier factor that reduces the amount of Delivered Energy produced by a Project connecting to a distribution system to account for the electrical distribution losses, including those related to distribution and transformation, occurring between the point where the Participating Transmission Owner’s meter is physically located and the Interconnection Point.

## “Distribution Upgrades” has the meaning set forth in the CAISO Tariff.

## “DMin” or “Minimum Dispatchable Generation” is the lowest generation capacity to which the Seller can reduce generation from the Project in response to an instruction.

## “DUNS” means the Data Universal Numbering System, which is a unique nine character identification number provided by Dun & Bradstreet, Inc.

## “Early Termination Date” has the meaning set forth in Section 5.2.

## “Effective Date” means the date on which all of the Conditions Precedent set forth in Section 2.5(a) have been satisfied or waived in writing by both Parties.

## “Effective FCDS Date” means the date on which Seller provides Buyer Notice and documentation from CAISO that the Project has attained Full Capacity Deliverability Status, which Buyer subsequently finds, in its reasonable discretion, to be adequate evidence that the Project has attained Full Capacity Deliverability Status.

## “Effective PCDS Date” means the date on which Seller provides Buyer Notice and documentation from CAISO that the Project has attained Partial Capacity Deliverability Status, which Buyer subsequently finds, in its reasonable discretion, to be adequate evidence that the Project has attained Partial Capacity Deliverability Status.

## “EIRP Forecast” means the final forecast of the Energy to be produced by the Project prepared by the CAISO in accordance with the Eligible Intermittent Resources Protocol and communicated to Scheduling Coordinator for use in submitting a Schedule for the output of the Project in the Real-Time Market.

## “Electrical Losses” means all applicable losses, including the following: (a) any transmission or transformation losses between the CAISO Revenue Meter(s) and the Delivery Point; and (b) the Distribution Loss Factor, if applicable.

## “Electric System Upgrades” means any Network Upgrades, Distribution Upgrades, or Interconnection Facilities that are determined to be necessary by the CAISO or Participating Transmission Owner, as applicable, to physically and electrically interconnect the Project to the Participating Transmission Owner’s electric system for receipt of Energy at the Point of Interconnection (as defined in the CAISO Tariff) if connecting to the CAISO Grid, or the Interconnection Point, if connecting to a part of the Participating TO’s electric system that is not part of the CAISO Grid.

## “Electrician” means any person responsible for placing, installing, erecting, or connecting any electrical wires, fixtures, appliances, apparatus, raceways, conduits, solar photovoltaic cells or any part thereof, which generate, transmit, transform or utilize energy in any form or for any purpose.

## “Eligible Intermittent Resources Protocol” or “EIRP” means the Eligible Intermittent Resource Protocol, as may be amended from time to time, as set forth in the CAISO Tariff.

## “Eligible LC Bank” means either a U.S. commercial bank, or a foreign bank issuing a Letter of Credit through its U.S. branch; and in each case the issuing U.S. commercial bank or foreign bank must be acceptable to Buyer in its sole discretion and such bank must have a Credit Rating of at least: (a) “A-, with a stable designation” from S&P and “A3, with a stable designation” from Moody’s, if such bank is rated by both S&P and Moody’s; or (b) “A-, with a stable designation” from S&P or “A3, with a stable designation” from Moody’s, if such bank is rated by either S&P or Moody’s, but not both, even if such bank was rated by both S&P and Moody’s as of the date of issuance of the Letter of Credit but ceases to be rated by either, but not both of those ratings agencies.

## “Eligible Renewable Energy Resource” or “ERR” has the meaning set forth in California Public Utilities Code Section 399.12 and California Public Resources Code Section 25741, as either code provision is amended or supplemented from time to time.

## “Energy” means three-phase, 60-cycle alternating current electric energy measured in MWh and net of auxiliary loads and station electrical uses (unless otherwise specified).

## “Energy Deviation(s)” means the absolute value of the difference, in MWh, in any Settlement Interval between (a) thefinal accepted Bid submitted for the Project; and (b) Delivered Energy.

## “Energy Only Status Seller” or “EOS Seller” means a Seller that has selected Energy Only Status in the Cover Sheet. For avoidance of doubt, an EOS Seller does not have an obligation to have or obtain a Full Capacity Deliverability Status Finding.

## “Energy Supply Bid” has the meaning set forth in the CAISO Tariff.

## “Environmental Justice Project” means facilities sized up to one MW that are located in “the most impacted and disadvantaged communities” as described in California Public Utilities Code § 2833(d)(1)(A) and defined in CPUC D.15-01-051.

## “EPC Contract” means the Seller’s engineering, procurement and construction contract with the EPC Contractor.

## “EPC Contractor” means an engineering, procurement, and construction contractor, or if not utilizing an engineering, procurement and construction contractor, the entity having lead responsibility for the management of overall construction activities, selected by Seller, with substantial experience in the engineering, procurement, and construction of power plants of the same type of facility as the Seller’s; provided, however, that the Seller or the Seller’s Affiliate(s) may serve as the EPC Contractor.

## “Equitable Defenses” means any bankruptcy, insolvency, reorganization or other Laws affecting creditors’ rights generally and, with regard to equitable remedies, the discretion of the court before which proceedings may be pending to obtain same.

## “Event of Default” has the meaning set forth in Section 5.1.

## “Excess Deemed Delivered Energy” has the meaning set forth in Section 4.2(a)(i).

## “Excess Deemed Delivered Energy Price” has the meaning set forth in Section 4.2(a)(ii)(B).

## “Excess Delivered Energy” has the meaning set forth in Section 4.2(a)(i).

## “Excess Delivered Energy Price” has the meaning set forth in Section 4.2(a)(ii)(A).

## “Excess Energy” has the meaning set forth in Section 4.2(a)(i).

## “Excess Network Upgrade Costs” has the meaning set forth in Section 3.9(f)(ii).

## “Exclusivity Period” has the meaning set forth in Section 3.9(e)(i) or Section 11.1(b)(i), as applicable.

## “Execution Date” means the latest signature date found on the signature page of this Agreement.

## “Executive(s)” has the meaning set forth in Section 12.2(a).

## “Exempt Wholesale Generator” has the meaning provided in 18 C.F.R. Section 366.1.

## “Expected Construction Start Date” has the meaning set forth in the Cover Sheet.

## “Expected FCDS Date” means the date set forth in Section A of the Cover Sheet which is the date the Project is expected to achieve Full Capacity Deliverability Status.

## “Expected PCDS Date” means the date set forth in Section A of the Cover Sheet which is the date the Project is expected to achieve Partial Capacity Deliverability Status.

## “Expected Net Qualifying Capacity” means an estimate of the amount of Net Qualifying Capacity the Project would have received had it obtained deliverability according to the deliverability type selected in Section A of the Cover Sheet, as determined in accordance with Appendix XIV.

## “FERC” means the Federal Energy Regulatory Commission or any successor government agency.

## “Final True-Up” means the final payment made pursuant to this Agreement settling all invoices by the Party with an outstanding net amount due to the other Party for Product delivered prior to the end of the Delivery Term or other amounts due pursuant to this Agreement incurred prior to the end of the Delivery Term.

## “First Offer” has the meaning set forth in Section 3.9(e)(1) or Section 11.1(b)(i), as applicable.

## “Force Majeure” means any event or circumstance which wholly or partly prevents or delays the performance of any material obligation arising under this Agreement, but only if and to the extent (i) such event is not within the reasonable control, directly or indirectly, of the Party seeking to have its performance obligation(s) excused thereby, (ii) the Party seeking to have its performance obligation(s) excused thereby has taken all reasonable precautions and measures in order to prevent or avoid such event or mitigate the effect of such event on such Party’s ability to perform its obligations under this Agreement and which by the exercise of due diligence such Party could not reasonably have been expected to avoid and which by the exercise of due diligence it has been unable to overcome, and (iii) such event is not the direct or indirect result of the negligence or the failure of, or caused by, the Party seeking to have its performance obligations excused thereby.

(a) Subject to the foregoing, events that could qualify as Force Majeure include the following:

(i) flooding, lightning, landslide, earthquake, fire, drought, explosion, epidemic, quarantine, storm, hurricane, tornado, volcanic eruption, other natural disaster or unusual or extreme adverse weather-related events;

(ii) war (declared or undeclared), riot or similar civil disturbance, acts of the public enemy (including acts of terrorism), sabotage, blockade, insurrection, revolution, expropriation or confiscation;

(iii) except as set forth in subsection (b)(viii) below, strikes, work stoppage or other labor disputes (in which case the affected Party shall have no obligation to settle the strike or labor dispute on terms it deems unreasonable); or

(iv) emergencies declared by the Transmission Provider or any other authorized successor or regional transmission organization or any state or federal regulator or legislature requiring a forced curtailment of the Project or making it impossible for the Transmission Provider to transmit Energy, including Energy to be delivered pursuant to this Agreement; provided that, if a curtailment of the Project pursuant to this subsection (a)(iv) would also meet the definition of a Curtailment Period, then it shall be treated as a Curtailment Period for purposes of Section 3.1(o).

(b) Force Majeure shall not be based on:

(i) Buyer’s inability economically to use or resell the Product purchased hereunder;

(ii) Seller’s ability to sell the Product at a price greater than the price set forth in this Agreement;

(iii) Seller’s inability to obtain permits or approvals of any type for the construction, operation, or maintenance of the Project unless caused solely by an event of Force Majeure of the specific type described in any of subsections (a)(i) through (a)(iv) above;

(iv) Seller’s inability to complete interconnection or Electric System Upgrades by the Guaranteed Commercial Operation Date unless such delay is caused solely by an event of Force Majeure of the specific type described in any of subsections (a)(i) through (a)(iv) above;

(v) Seller’s inability to obtain sufficient fuel, power or materials to operate the Project, except if Seller's inability to obtain sufficient fuel, power or materials is caused solely by an event of Force Majeure of the specific type described in any of subsections (a)(i) through (a)(iv) above;

(vi) Seller’s failure to obtain additional funds, including funds authorized by a state or the federal government or agencies thereof, to supplement the payments made by Buyer pursuant to this Agreement;

(vii) a Forced Outage except where such Forced Outage is caused by an event of Force Majeure of the specific type described in any of subsections (a)(i) through (a)(iv) above;

(viii) a strike, work stoppage or labor dispute limited only to any one or more of Seller, Seller’s Affiliates, the EPC Contractor or subcontractors thereof or any other third party employed by Seller to work on the Project;

(ix) any equipment failure, including the failure of Shared Facilities, except if such failure is caused solely by an event of Force Majeure of the specific type described in any of subsections (a)(i) through (a)(iv) above;

(x) a Party’s inability to pay amounts due to the other Party under this Agreement, except if such inability is caused solely by a Force Majeure event that disables physical or electronic facilities necessary to transfer funds to the payee Party; or

(xi) any invalidation of or change to the CAISO Exemption or failure to comply with the CAISO Tariff due, in any part, to the Shared Facilities.

## “Force Majeure Extension” has the meaning set forth in Section 3.9(c)(ii)(A).

## “Force Majeure Failure” has the meaning set forth in Section 11.1(a).

## “Forced Outage” means any unplanned reduction or suspension of the electrical output from the Project or unavailability of the Product in whole or in part from a Unit in response to any control system trip or operator-initiated trip in response to an alarm or equipment malfunction; or any other unavailability of the Project or a Unit for operation, in whole or in part, for maintenance or repair that is not a Planned Outage and not the result of Force Majeure.

## “Forecasting Penalty” has the meaning set forth in Section 4.5(c)(iii), and “Forecasting Penalties” means more than one Forecasting Penalty.

## “Full Buy/Sell” is the type of transaction described in Section 3.1(b)(i).

## “Full Capacity Deliverability Status” or “FCDS” has the meaning set forth in the CAISO Tariff except that it applies to any Generating Facility (as defined in the CAISO Tariff).

## “Full Capacity Deliverability Status Finding” or “FCDS Finding” means a written confirmation from the CAISO that the Project is eligible for FCDS.

## “Full Capacity Deliverability Status Seller” or “FCDS Seller” means a Seller that selected Full Capacity Deliverability Status in the Cover Sheet and either has previously obtained, or is obligated to obtain per the terms of the Agreement, a Full Capacity Deliverability Status Finding.

## “Gains” means with respect to any Party, an amount equal to the present value of the economic benefit to it, if any (exclusive of Costs), resulting from the termination of the Transaction, determined in a commercially reasonable manner, subject to Section 5.3 hereof. Factors used in determining economic benefit may include reference to information either available to it internally or supplied by one or more third parties, including quotations (either firm or indicative) of relevant rates, prices, yields, yield curves, volatilities, spreads or other relevant market data in the relevant markets, market price referent, market prices for a comparable transaction, forward price curves based on economic analysis of the relevant markets, settlement prices for a comparable transaction at liquid trading platforms (e.g., NYMEX), all of which should be calculated for the remaining Delivery Term to determine the value of the Product.

## “Generally Accepted Accounting Principles” means the standards for accounting and preparation of financial statements established by the Federal Accounting Standards Advisory Board (or its successor agency) or any successor standards adopted pursuant to relevant SEC rule.

## “Generator Interconnection Agreement” or “GIA” means, for Projects interconnecting at the transmission level, the agreement and associated documents (or any successor agreement and associated documentation approved by FERC) by and among Seller, the Participating Transmission Owner, and the CAISO governing the terms and conditions of Seller’s interconnection with the CAISO Grid, including any description of the plan for interconnecting to the CAISO Grid. For Projects interconnecting at the distribution level, it means the agreement and associated documents (or any successor agreement and associated documentation) by and between Seller and the Participating Transmission Owner governing the terms and conditions of Seller’s interconnection with the Participating TO’s distribution system, including any description of the plan for interconnecting to Participating TO’s distribution system.

## “Generator Interconnection Process” or “GIP” means the Generator Interconnection Procedures set forth in the CAISO Tariff or Participating TO’s tariff, as applicable, and associated documents; provided that if the GIP is replaced by such other successor procedures governing interconnection (a) to the CAISO Grid or Participating TO’s distribution system, as applicable, or (b) of generating facilities with an expected net capacity equal to or greater than the Project’s Contract Capacity, the term “GIP” shall then apply to such successor procedure.

## “GEP Cure” has the meaning set forth in Section 3.1(e)(ii)(C).

## “GEP Damages” has the meaning set forth in Appendix V.

## “GEP Failure” means Seller’s failure to produce Delivered Energy plus Deemed Delivered Energy in an amount equal to or greater than the Guaranteed Energy Production amount for the applicable Performance Measurement Period.

## “GEP Shortfall” means the amount in MWh by which Seller failed to achieve the Guaranteed Energy Production in the applicable Performance Measurement Period.

## “Good Utility Practice” has the meaning provided in the CAISO Tariff.

## “Governmental Approval” means all authorizations, consents, approvals, waivers, exceptions, variances, filings, permits, orders, licenses, exemptions and declarations of or with any governmental entity and shall include those siting and operating permits and licenses, and any of the foregoing under any applicable environmental Law, that are required for the construction, use and operation of the Project.

## “Governmental Authority” means any federal, state, local or municipal government, governmental department, commission, board, bureau, agency, or instrumentality, or any judicial, regulatory or administrative body, having jurisdiction as to the matter in question.

## “Governmental Charges” has the meaning set forth in Section 9.2.

## “Green Attributes” means any and all credits, benefits, emissions reductions, offsets, and allowances, howsoever entitled, attributable to the generation from the Project, and its avoided emission of pollutants. GreenAttributes include but are not limited to Renewable Energy Credits, as well as: (a) any avoided emission of pollutants to the air, soil or water such as sulfur oxides (SOx), nitrogen oxides (NOx), carbon monoxide (CO) and other pollutants; (b) any avoided emissions of carbon dioxide (CO2), methane (CH4), nitrous oxide, hydrofluorocarbons, perfluorocarbons, sulfur hexafluorideand other greenhouse gases (GHGs) that have been determined by the United Nations Intergovernmental Panel on Climate Change, or otherwise by Law**,** to contribute to the actual or potential threat of altering the Earth’s climate by trapping heat in the atmosphere;[[1]](#footnote-2) (c) the reporting rights to these avoided emissions, such asGreen Tag Reporting Rights. Green Tag Reporting Rights are the right of a Green Tag Purchaser to report the ownership of accumulated Green Tags in compliance with federal or state Law, if applicable, and to a federal or state agency or any other party at the Green Tag Purchaser’s discretion, and include without limitation those Green Tag Reporting Rights accruing under Section 1605(b) of The Energy Policy Act of 1992 and any present or future federal, state, or local Law, regulation or bill, and international or foreign emissions trading program. Green Tags are accumulated on a MWh basis and one Green Tag represents the GreenAttributes associated with one (1) MWh of Energy. GreenAttributes do not include (i) any Energy, capacity, reliability or other power attributes from the Project, (ii) production tax credits associated with the construction or operation of the Project and other financial incentives in the form of credits, reductions, or allowances associated with the Project that are applicable to a state or federal income taxation obligation, (iii) fuel-related subsidies or “tipping fees” that may be paid to Seller to accept certain fuels, or local subsidies received by the generator for the destruction of particular preexisting pollutants or the promotion of local environmental benefits, or (iv) emission reduction credits encumbered or used by the Project for compliance with local, state, or federal operating and/or air quality permits. If the Project is a biomass or biogas facility and Seller receives any tradable GreenAttributes based on the greenhouse gas reduction benefits or other emission offsets attributed to its fuel usage, it shall provide Buyer with sufficient GreenAttributes to ensure that there are zero net emissions associated with the production of electricity from the Project.

## “Green-e® Energy Certification” means the independent certification and verification program for renewable energy and greenhouse gas emission reductions as administered by CRS.

## “GTSR Program” means the Green Tariff Shared Renewables program implemented per Senate Bill (SB) 43 (Stats. 2013, ch. 413 (Wolk)) and CPUC Decision 15-01-051.

## “GTSR Project” means a Project procured for the GTSR Program in accordance with Green-e® Energy Certification.

## “Guaranteed Commercial Operation Date” has the meaning set forth in Section 3.9(c)(i).

## “Guaranteed Energy Production” or “GEP” has the meaning set forth in Section 3.1(e)(ii).

## “Imbalance Energy” has the meaning set forth in the CAISO Tariff.

## “Initial Energy Delivery Date” has the meaning set forth in Section 3.1(c)(i).

## “Initial Extension” has the meaning set forth in Section 3.1(c)(ii).

## “Initial Negotiation End Date” has the meaning set forth in Section 12.2(a).

## “Interconnection Customer’s Interconnection Facilities” has the meaning set forth in the CAISO Tariff or Participating TO’s tariff, as applicable.

## “Interconnection Facilities” has the meaning set forth in the CAISO Tariff.

## “Interconnection Point” means the physical interconnection point of the Project as identified by Seller in the Cover Sheet.

## “Interconnection Study” means any of the studies defined in the CAISO Tariff or, if applicable, any distribution provider’s tariff that reflect the methodology and costs to interconnect the Project to the Participating Transmission Owner’s electric grid.

## “Integrated Forward Market” has the meaning set forth in the CAISO Tariff.

## “Interest Amount” means, with respect to an Interest Period, the amount of interest calculated as follows: (a) the sum of (i) the principal amount of Performance Assurance in the form of cash held by Buyer during that Interest Period, and (ii) the sum of all accrued and unpaid Interest Amounts accumulated prior to such Interest Period; (b) multiplied by the Interest Rate in effect for that Interest Period; (c) multiplied by the number of days in that Interest Period; (d) divided by 360.

## “Interest Payment Date” means the date of returning unused Performance Assurance held in the form of cash.

## “Interest Period” means the monthly period beginning on the first day of each month and ending on the last day of each month.

## “Interest Rate” means the rate per annum equal to the “Monthly” Federal Funds Rate (as reset on a monthly basis based on the latest month for which such rate is available) as reported in Federal Reserve Bank Publication H.15(519), or its successor publication.

## “JAMS” means JAMS, Inc. or its successor entity, a judicial arbitration and mediation service.

## “Law” means any statute, law, treaty, rule, regulation, CEC guidance document, ordinance, code, permit, enactment, injunction, order, writ, decision, authorization, judgment, decree or other legal or regulatory determination or restriction by a court or Governmental Authority of competent jurisdiction, including any of the foregoing that are enacted, amended, or issued after the Execution Date, and which becomes effective after the Execution Date; or any binding interpretation of the foregoing. For purposes of Sections 1.46 “CPUC Approval,” 10.2(b), “Seller Representations and Warranties” and 10.12 “Governing Law”, the term “law” shall have the meaning set forth in this definition.

## “Letter of Credit” means an irrevocable, non-transferable standby letter of credit, the form of which must be substantially as contained in Appendix I to this Agreement; provided, that, if the issuer is a U.S. branch of a foreign commercial bank, Buyer may require changes to such form; the issuer must be an Eligible LC Bank on the date of Transfer; and the issuing Letter of Credit amount may not be greater than the Maximum Issuing Amount if the total amount of collateral posted by the Seller in the form of Letter of Credit exceeds ten million dollars ($10,000,000.00) on the date of Transfer.

## “Licensed Professional Engineer” means a person acceptable to Buyer in its reasonable judgment who (a) is licensed to practice engineering in California, (b) has training and experience in the power industry specific to the technology of the Project, (c) has no economic relationship, association, or nexus with Seller or Buyer, other than to meet the obligations of Seller pursuant to this Agreement, (d) is not a representative of a consultant, engineer, contractor, designer or other individual involved in the development of the Project or of a manufacturer or supplier of any equipment installed at the Project, and (e) is licensed in an appropriate engineering discipline for the required certification being made.

## “Locational Marginal Price” or “LMP” has the meaning set forth in the CAISO Tariff.

## “Local Capacity Area” has the meaning set forth in the CAISO Tariff.

## “Local RA Attributes” means any and all resource adequacy attributes or other locational attributes related to a Local Capacity Area, as may be identified at any time during the Delivery Term by the CPUC, CAISO or other Governmental Authority having jurisdiction, associated with a physical location or point of electrical interconnection within the CAISO’s Balancing Authority, that can be counted toward Local RAR, exclusive of any Other Capacity Attributes.

## “Local RAR” means the Local Capacity Areas resource adequacy requirements established for load serving entities by the CPUC pursuant to the CPUC Decisions, or by any other Governmental Authority having jurisdiction. Local RAR may also be known as local area reliability, local resource adequacy, local resource adequacy procurement requirement, or local capacity requirement in other regulatory proceedings or legislative actions.

## “Losses” means, with respect to any Party, an amount equal to the present value of the economic loss to it, if any (exclusive of Costs), resulting from the termination of the Transaction, determined in a commercially reasonable manner, subject to Section 5.3 hereof. Factors used in determining the loss of economic benefit may include reference to information either available to it internally or supplied by one or more third parties including quotations (either firm or indicative) of relevant rates, prices, yields, yield curves, volatilities, spreads or other relevant market data in the relevant markets, market price referent, market prices for a comparable transaction, forward price curves based on economic analysis of the relevant markets, settlement prices for a comparable transaction at liquid trading platforms (e.g. NYMEX), all of which should be calculated for the remaining term of the Transaction to determine the value of the Product.

## “Low-income Residential Customer” means customers meeting the qualifications for California Alternate Rates for Energy Program (CARE) or Family Electric Rate Assistance Program (FERA).

## “Manager” has the meaning set forth in Section 12.2(a).

## “Master File” has the meaning set forth in the CAISO Tariff.

## “Maximum Issuing Amount” means the amount of a Letter of Credit to be issued by an Eligible LC Bank, which cannot exceed the lesser of (a) sixty percent (60%) of the total collateral posted by Seller in the form of Letter of Credit including the Letter of Credit to be issued or (b) twenty-five million dollars ($25,000,000.00), without Buyer’s prior written consent.

## “Milestone(s)” means the key development activities required for the construction and operation of the Project, as set forth in Section B(i)(b) of the Cover Sheet.

## “Minimum Load” has the meaning set forth in the CAISO Tariff.

## “Minimum Down Time” has the meaning set forth in the CAISO Tariff.

## “Monthly Payment for Excess Energy” has the meaning set forth in Section 4.4(b).

## “Moody’s” means Moody’s Investors Service, Inc., or its successor.

## “MW” means megawatt in alternating current or AC.

## “MWh” means megawatt-hour.

## “NERC” means the North American Electric Reliability Corporation or a successor organization that is responsible for establishing reliability criteria and protocols.

## “Net Qualifying Capacity” has the meaning set forth in the CAISO Tariff.

## “Network Upgrades” has the meaning set forth in the CAISO Tariff or the Participating TO’s tariff, as applicable.

## “New Project” is a Project that has not achieved Commercial Operation on or prior to the Execution Date.

## “NOAA” means National Oceanic and Atmospheric Administration or successor thereto.

## “Non-Defaulting Party” has the meaning set forth in Section 5.2.

## “Notice,” unless otherwise specified in the Agreement, means written communications by a Party to be delivered by hand delivery, United States mail, overnight courier service, facsimile or electronic messaging (e-mail). The Cover Sheet contains the names and addresses to be used for Notices.

## “Notice to Proceed” means the full notice to proceed, provided by Seller to the EPC Contractor following execution of the EPC Contract between Seller and such EPC Contractor and satisfaction of all conditions to performance of such contract, by which Seller authorizes such EPC Contractor to begin mobilization and construction of the Project without any delay or waiting periods.

## “Operating Instruction” has the meaning set forth in the CAISO Tariff.

## “Operational Characteristics” means the operational characteristics and other requirements set forth in Section F of the Cover Sheet.

## “Operational Deliverability Assessment” has the meaning set forth in the CAISO Tariff.

## “Other Capacity Attributes” means, exclusive of System RA Attributes and Local RA Attributes, any (a) current or future capacity characteristics or attributes, including Ancillary Services and the ability to provide Ancillary Services, generating Energy at given capacity levels, ramping up or down at a given rate, flexibility or dispatchability attributes, and locational attributes, as may be identified at any time during the Delivery Term by any applicable Law, or voluntary or mandatory program of any Governmental Authority or other Person; (b) certificate, tag, or credit, intended to commoditize or otherwise attribute value resulting from or associated with the characteristics set forth in subsection (a) of this definition; and (c) any accounting construct so that the characteristics or values set forth in subsections (a) or (b) hereof may be counted toward any compliance obligations.

## “Outage Notification Procedures” means the procedures specified in Appendix VI, attached hereto. PG&E reserves the right to revise or change the procedures upon written Notice to Seller.

## “Partial Capacity Deliverability Status” or “PCDS” has the meaning set forth in the CAISO Tariff.

## “Partial Capacity Deliverability Status Amount” means the number of MW that the Project will obtain, as stated in the Deliverability type selected in Section A of the Cover Sheet.

## “Partial Capacity Deliverability Status Finding” or “PCDS Finding” means a written confirmation from the CAISO that the Project is eligible for PCDS.

## “Participating Intermittent Resource” or “PIRP” has the meaning set forth in the CAISO Tariff.

## “Participating Transmission Owner” or “Participating TO” means an entity that (a) owns, operates and maintains transmission lines and associated facilities and/or has entitlements to use certain transmission lines and associated facilities and (b) has transferred to the CAISO operational control of such facilities and/or entitlements to be made part of the CAISO Grid.

## “Party” means the Buyer or Seller individually, and “Parties” means both collectively. For purposes of Section 10.12, Governing Law, the word “party” or “parties” shall have the meaning set forth in this definition.

## “Performance Assurance” means collateral provided by Seller to Buyer to secure Seller’s obligations hereunder and includes Project Development Security, Delivery Term Security, and Term Security, as applicable. Acceptable forms of collateral are cash or a Letter of Credit as designated in Section E of the Cover Sheet. The required form of Letter of Credit is attached hereto in Appendix I.

## “Performance Measurement Period” has the meaning set forth in Section 3.1(e)(ii).

## “Performance Tolerance Band” shall be calculated as set forth in Section 4.5(c)(ii).

## “Permit Failure” has the meaning set forth in Section 3.9(d).

## “Permitted Extensions” means extensions to the Guaranteed Commercial Operation Date due to Force Majeure Extension, or payment of Daily Delay Damages, as applicable, pursuant to Section 3.9(c).

## “Planned Outage” means the removal of equipment from service availability for inspection and/or general overhaul of one or more major equipment groups. To qualify as a Planned Outage, the maintenance (a) must actually be conducted during the Planned Outage, and in Seller’s sole discretion must be of the type that is necessary to reliably maintain the Project, (b) cannot be reasonably conducted during Project operations, and (c) causes the generation level of the Project to be reduced by 1 MW or more.

## “PMax” has the meaning set forth in the CAISO Tariff.

## “PMin” has the meaning set forth in the CAISO Tariff.

## “PNode” has the meaning set forth in the CAISO Tariff.

## “Preamble” means the paragraph that precedes Article One: General Definitions to this Agreement.

## “Product” means the Energy, capacity, Ancillary Services, and all products, services and/or attributes similar to the foregoing which are or can be produced by or associated with the Project, including renewable attributes, Renewable Energy Credits, Capacity Attributes and Green Attributes.

## “Production Tax Credit” or “PTC” means the tax credit for electricity produced from certain renewable generation resources described in Section 45 of the Internal Revenue Code of 1986, as it may be amended or supplemented from time to time.

## “Progress Report” means the report similar in form and content to that attached hereto as Appendix III.

## “Project” means all of the Unit(s) and the Site at which the generating facility is located and the other assets, tangible and intangible, that compose the generation facility, including Seller’s interests in the Shared Facilities, as applicable, and any other the assets used to connect the Unit(s) to the Interconnection Point, as more particularly described in Appendix XIII.

## “Project Development Security” is the collateral required of Seller, as specified and referred to in Section 8.4(a).

## “Project Specifications” has the meaning set forth in Appendix XIII.

## “Prolonged Outage” is any period of more than thirty (30) consecutive days during which the Project is or will be unable, for whatever reason, to provide at least sixty percent (60%) of the Contract Capacity.

## “Qualifying Facility” has the meaning provided in the Public Utility Regulatory Policies Act (“PURPA”) and in regulations of the FERC at 18 C.F.R. §§ 292.201 through 292.207.

## “RA Deficiency Amount” means the liquidated damages payment that Seller shall pay to Buyer for an applicable RA Shortfall Month as calculated in accordance with Section 3.3(e)(ii).

## “RA Shortfall Period” means the period of consecutive calendar months that starts with the calendar month in which the RA Start Date occurs and concludes with the second calendar month following the calendar month in which the Effective FCDS Date or Effective PCDS Date occurs. The RA Shortfall Period shall not exceed twenty-six (26) months.

## “RA Shortfall Month” means the applicable calendar month within the RA Shortfall Period for purposes of calculating an RA Deficiency Amount under Section 3.3(e)(ii).

## “RA Start Date” shall be the later of the Initial Energy Delivery Date or the Expected PCDS Date or FCDS Date according to the deliverability type selected in Section A of the Cover Sheet.

## “RA Value” means the value in U.S. dollars per MW of Expected Net Qualifying Capacity for each RA Shortfall Month, as set forth in Appendix XIV.

## “Ramp Rate” has the meaning set forth in the CAISO Tariff.

## “Real-Time Market” has the meaning set forth in the CAISO Tariff.

## “Real-Time Price” means the Resource-Specific Settlement Interval LMP as defined in the CAISO Tariff. If there is more than one applicable Real-Time Price for the same period of time, Real-Time Price shall mean the price associated with the smallest time interval.

## “Reductions” has the meaning set forth in Section 4.4(b).

## “Referral Date” has the meaning set forth in Section 12.2(a).

## “Reliability Coordinator” has the meaning set forth in the CAISO Tariff.

## “Reliability Network Upgrade” has the meaning set forth in the CAISO Tariff.

## “Renewable Energy Credit” has the meaning set forth in California Public Utilities Code Section 399.12(h) and CPUC Decision 08-08-028, as may be amended from time to time or as further defined or supplemented by Law.

## “Replacement Capacity Rules” means the replacement requirement for Resource Adequacy Capacity (as defined in the CAISO Tariff) associated with a Planned Outage as set forth in the CAISO Tariff or successor replacement requirements as prescribed by the CPUC, CAISO and/or other regional entity.

## “Resource Adequacy” means the procurement obligation of load serving entities, including Buyer, as such obligations are described in CPUC Decisions D.04-10-035 and D.05-10-042 and subsequent CPUC decisions addressing Resource Adequacy issues, as those obligations may be altered from time to time, and all other capacity procurement obligations established by any other entity, including the CAISO.

## “Resource Adequacy Plan” has the meaning set forth in the CAISO Tariff.

## “Resource Adequacy Requirements” has the meaning set forth in Section 3.3.

## “Resource Adequacy Availability Standards” means (a) the Program set forth in Section 40.9 of the CAISO Tariff and (b) any future program or provision under the CAISO Tariff providing for availability standards or similar standards with respect to any flexible Resource Adequacy resource, product, or procurement obligation; in the case of (a) or (b), as any such program or provision may be amended, supplemented, or replaced (in whole or in part) from time to time, setting forth certain standards regarding the desired level of availability for Resource Adequacy resources and possible changes and incentive payments for performance thereunder.

## “Resource-Specific Settlement Interval LMP” has the meaning set forth in the CAISO Tariff.

## “Revised Offer” has the meaning set forth in Section 3.9(e)(iii) or Section 11.1(b)(iii), as applicable.

## “S&P” means the Standard & Poor’s Financial Services, LLC (a subsidiary of The McGraw-Hill Companies, Inc.) or its successor.

## “Satisfaction Date” has the meaning set forth in Section 2.6.

## “Schedule” has the meaning set forth in the CAISO Tariff.

## “Scheduling Coordinator” or “SC” means an entity certified by the CAISO as qualifying as a Scheduling Coordinator pursuant to the CAISO Tariff, for the purposes of undertaking the functions specified in “Responsibilities of a Scheduling Coordinator” of the CAISO Tariff, as amended from time to time.

## “SEC” means the U.S. Securities and Exchange Commission.

## “Self-Schedule” has the meaning set forth in the CAISO Tariff.

## “Seller” has the meaning set forth in the Cover Sheet.

## “Seller Excuse Hours” means those hours during which Seller is unable to deliver Delivered Energy to Buyer as a result of (a) a Force Majeure event, (b) Buyer’s failure to perform, or (c) Curtailment Period.

## “Seller’s WREGIS Account” has the meaning set forth in Section 3.1(k)(i).

## “Settlement Amount” means the amount in US dollars equal to the sum of Losses, Gains, and Costs, which the Non-Defaulting Party incurs as a result of the termination of this Agreement.

## “Settlement Interval” has the meaning set forth in the CAISO Tariff.

## “Settlement Interval Actual Available Capacity” means the sum of the capacity, in MWs, of all generating units of the Project that were available as of the end of such Settlement Interval, as indicated by the Actual Availability Report.

## “Shared Contract Year” has the meaning set forth in section 3.1(e)(ii)(C)(I).

## “Shared Facilities” means the gentie lines, transformers, substations, or other equipment, permits, contract rights and obligations, and other assets and property (real or personal), in each case, as necessary to enable delivery of energy from Seller’s electric generating facility (which is excluded from this definition of Shared Facilities) to the Point of Interconnection that are used in common with other entities, as applicable.

## “Shared Facilities Agreement(s)” means a cotenancy or similar sharing agreement pertaining to Shared Facilities.

## “Site” means the location of the Project as described in Appendix XIII***[***.***][***, excluding that portion of real property pertaining to any other generating facility with which Seller has a Shared Facilities Agreement.***]* *[Bracketed language shall only apply to Projects that utilize Shared Facilities]***.

## “Start-up” means the action of bringing a Unit from non-operation to operation at or above the Unit’s Minimum Load, or with positive generation output if Minimum Load is zero.

## “Surplus Delivered Energy” means, in any Settlement Interval, the Delivered Energy that exceeds the product of one hundred percent (100%) of Contract Capacity multiplied by a Settlement Interval.

## “Supply Plan” has the meaning set forth in the CAISO Tariff.

## “System Emergency” has the meaning set forth in the CAISO Tariff.

## “System RA Attributes” means any and all system resource adequacy attributes, as may be identified at any time during the Delivery Term by the CPUC, CAISO or other Governmental Authority having jurisdiction that can be counted toward system resource adequacy requirements, exclusive of any Local RA Attributes and Other Capacity Attributes

## “Term” has the meaning provided in Section 2.6.

## “Term Security” means the Performance Assurance that Seller is required to maintain, as specified in Article Eight, to secure performance of its obligations during the Delivery Term. ***[“Term Security” only applies to GTSR Projects with a Contract Capacity of 3MW or less.]***

## “Terminated Transaction” means the Transaction terminated in accordance with Section 5.2 of this Agreement.

## “Termination Payment” means the payment amount equal to the sum of (a) and (b), where (a) is the Settlement Amount and (b) is the sum of all amounts owed by the Defaulting Party to the Non-Defaulting Party under this Agreement, less any amounts owed by the Non-Defaulting Party to the Defaulting Party determined as of the Early Termination Date.

## “Test Period” means the period of not more than ninety (90) consecutive days, as extended by the Initial Extension and Additional Extension according to Section 3.1(c)(ii), as applicable, which period shall commence upon the first date that the following have occurred (a) the Project is operating in parallel with the Participating Transmission Owner and the first kWh of Energy is measured by the CAISO Revenue Meter, and (b) the items in Section 3.4(a)(i)(E) have been fulfilled and implemented, and shall end upon the Initial Energy Delivery Date.

## “Third-Party SC” means a qualified third party designated by Buyer to provide the Scheduling Coordinator functions for the Project pursuant to this Agreement.

## “Total Nameplate Rated Power” shall have the meaning set forth in Appendix XIII – Project Specifications.

## “Transaction” means the particular transaction described in its entirety in Section 3.1(b) of this Agreement.

## “Transfer” with respect to Letters of Credit means the delivery of the Letter of Credit conforming to the requirements of this Agreement, by Seller or an Eligible LC Bank to Buyer or delivery of an executed amendment to such Letter of Credit (extending the term or varying the amount available to Buyer thereunder, if acceptable to Buyer) by Seller or Eligible LC Bank to Buyer.

## “Transmission Provider” means any entity or entities transmitting or transporting the Product on behalf of Seller or Buyer to or from the Delivery Point.

## “Uninstructed Imbalance Energy” shall have the meaning set forth in the CAISO Tariff.

## “Unit” means the technology used to produce the Products, which are identified in Appendix XIII for the Transaction entered into under this Agreement.

## “Unreserved Project” means any GTSR project that qualifies for the GTSR program, but excluding projects that would qualify under the Environmental Justice Project reservation or the City of Davis reservation, both as set forth in California Public Untilities Code Section 2833(d).

## “WECC” means the Western Electricity Coordinating Council or successor agency.

## “Work” means (a) work or operations performed by a Party or on a Party’s behalf, and (b) materials, parts or equipment furnished in connection with such work or operations, including (i) warranties or representations made at any time with respect to the fitness, quality, durability, performance or use of “a Party’s work”, and (ii) the providing of or failure to provide warnings or instructions.

## “WREGIS” means the Western Renewable Energy Generation Information System or any successor renewable energy tracking program.

## “WREGIS Certificate Deficit” has the meaning set forth in Section 3.1(k)(v).

## “WREGIS Certificates” has the same meaning as “Certificate” as defined in the WREGIS Operating Rules and are designated as eligible for complying with the California Renewables Portfolio Standard.

## “WREGIS Operating Rules” means those operating rules and requirements for WREGIS adopted by WECC as of January 4, 2021, as subsequently amended, supplemented or replaced (in whole or in part) from time to time.

# **ARTICLE TWO: Governing terms and term**

2.1 Entire Agreement . This Agreement, together with the Cover Sheet, Preamble and each and every appendix, attachment, amendment, schedule and any written supplements hereto, if any, between the Parties constitutes the entire, integrated agreement between the Parties.

2.2 Interpretation . The following rules of interpretation shall apply in addition to those set forth in Section 10.13:

(a) The term “month” or “Month” shall mean a calendar month unless otherwise indicated, and a “day” shall be a 24-hour period beginning at 12:00:01 a.m. Pacific Prevailing Time and ending at 12:00:00 midnight Pacific Prevailing Time; provided that a “day” may be 23 or 25 hours on those days on which daylight savings time begins and ends.

(b) Unless otherwise specified herein, all references herein to any agreement or other document of any description shall be construed to give effect to amendments, supplements, modifications or any superseding agreement or document as then existing at the applicable time to which such construction applies.

(c) Capitalized terms used in this Agreement, including the appendices hereto, shall have the meaning set forth in Article One, unless otherwise specified.

(d) Unless otherwise specified herein, references in the singular shall include references in the plural and vice versa, pronouns having masculine or feminine gender will be deemed to include the other, and words denoting natural persons shall include partnerships, firms, companies, corporations, joint ventures, trusts, associations, organizations or other entities (whether or not having a separate legal personality). Other grammatical forms of defined words or phrases have corresponding meanings.

(e) References to a particular article, section, subsection, paragraph, subparagraph, appendix or attachment shall, unless specified otherwise, be a reference to that article, section, subsection, paragraph, subparagraph, appendix or attachment in or to this Agreement.

(f) Any reference in this Agreement to any natural person, Governmental Authority, corporation, partnership or other legal entity includes its permitted successors and assigns or any natural person, Governmental Authority, corporation, partnership or other legal entity succeeding to its functions.

(g) All references to dollars are to U.S. dollars.

(h) The term “including” when used in this Agreement shall be by way of example only and shall not be considered in any way to be in limitation.

2.3 Authorized Representatives . Each Party shall provide Notice to the other Party of the persons authorized to nominate and/or agree to a Schedule or dispatch order for the delivery or acceptance of the Product or make other Notices on behalf of such Party and specify the scope of their individual authority and responsibilities, and may change its designation of such persons from time to time in its sole discretion by providing Notice.

2.4 Separation of Functions . The Parties acknowledge that this Agreement is between (a) Seller and (b) Buyer acting solely in its merchant function. The Parties further acknowledge that they have no rights against each other or obligations to each other under this Agreement with respect to any relationship between the Parties in which PG&E is acting in its capacity as Participating Transmission Owner, including orders or instructions relating to Electric System Upgrades and/or Curtailment Periods.

2.5 Conditions Precedent .

(a) Conditions Precedent. Subject to Section 2.7 hereof, the Term shall not commence until the occurrence of all of the following:

(i) this Agreement has been duly executed by the authorized representatives of each of Buyer and Seller;

(ii) CPUC Approval has been obtained for the terms, conditions and pricing of this Agreement;

(iii) the advice letter submitting this Agreement to the CPUC becomes effective in accordance with CPUC General Order 96-B or its successor order, or as otherwise provided by CPUC order; and

(iv) Buyer receives from Seller the documentation listed in Appendix VIII (Seller Documentation Condition Precedent).

(b) Failure to Meet All Conditions Precedent. If the Conditions Precedent set forth in Sections 2.5(a)(ii) and (iii) are not satisfied or waived in writing by both Parties on or before one hundred and eighty (180) days from the date on which Buyer files an advice letter submitting this Agreement to the CPUC, then either Party may terminate this Agreement effective upon receipt of Notice by the other Party. Neither Party shall have any obligation or liability to the other, including for a Termination Payment or otherwise, by reason of such termination.

2.6 Term .

(a) The term shall commence upon the satisfaction of the Conditions Precedent set forth in Section 2.5(a) of this Agreement and shall remain in effect until the conclusion of the Delivery Term unless terminated sooner pursuant to Section 2.5(b), Section 5.2 or Section 11.1 of this Agreement (the “Term”); provided that this Agreement shall thereafter remain in effect (i) until the Parties have fulfilled all obligations with respect to the Transaction, including payment in full of amounts due pursuant to the Final True-Up, the Settlement Amount, or other damages (whether directly or indirectly such as through set-off or netting) and the undrawn portion of the Project Development Security, Delivery Term Security or Term Security as applicable, is released and/or returned as applicable (the “Satisfaction Date”) or (ii) in accordance with the survival provisions set forth in subpart (b) below.

(b) Notwithstanding anything to the contrary in this Agreement, (i) all rights under Section 10.5 (“Indemnities”) and any other indemnity rights shall survive the Satisfaction Date or the end of the Term (whichever is later) for an additional twelve (12) months; (ii) all rights and obligations under Section 10.7 (“Confidentiality”) shall survive the Satisfaction Date or the end of the Term (whichever is later) for an additional two (2) years; and (iii) the right of first offer in Section 11.1(b) shall survive the Satisfaction Date for three (3) years.

2.7 Binding Nature .

(a) Upon Execution Date. This Agreement shall be effective and binding as of the Execution Date only to the extent required to give full effect to, and enforce, the rights and obligations of the Parties under:

(i) Sections 3.9(a)(vii), 5.1(a)(iv)-(v), and 5.1(b)(iv);

(ii) Section 5.1(a)(ii) only with respect to Section 10.2, and Section 5.1(a)(iii) only with respect to the Sections identified in this Section 2.7;

(iii) Sections 5.2 through 5.7;

(iv) Sections 8.3, 8.4(a)(i), 8.4(b), and 8.5;

(v) Sections 10.2, 10.6 through 10.8, and Sections 10.12 through 10.16; and

(vi) Articles One, Two, Seven, Twelve and Thirteen.

(b) Upon Effective Date. This Agreement shall be in full force and effect, enforceable and binding in all respects, upon occurrence of the Effective Date.

# **ARTICLE THREE: OBLIGATIONS AND DELIVERIES**

3.1 Seller’s and Buyer’s Obligations .

(a) Product. The Product to be delivered and sold by Seller and received and purchased by Buyer under this Agreement is set forth in the Cover Sheet. Buyer shall have exclusive rights to all Product during the Delivery Term, including the right to re-sell all or a portion of the Product purchased under this Agreement (“Resold Product”). If Buyer re-sells Product, Seller agrees to follow Buyer’s instructions with respect to providing such Resold Product to subsequent purchasers of such Resold Product to the extent such instructions are consistent with Seller’s obligations under this Agreement. Seller further agrees to take all commercially reasonable actions and execute any and all documents or instruments reasonably necessary to allow such subsequent purchasers to use such Resold Product in a manner consistent with Buyer’s rights under this Agreement. If Buyer incurs any liability to any purchaser of such Resold Product due to the failure of Seller to comply with the terms of this Agreement, then Seller shall be liable to Buyer for any liabilities Seller would have incurred under this Confirmation if Buyer had not resold the Product.

(b) Transaction. Unless specifically excused by the terms of this Agreement during the Delivery Term, Seller shall sell and deliver, or cause to be delivered, and Buyer shall purchase and receive, or cause to be received, the Product at the Delivery Point, pursuant to Seller’s election in the Cover Sheet of a Full Buy/Sell arrangement as described in paragraph 3.1(b)(i) below. Buyer shall pay Seller the Contract Price in accordance with the terms of this Agreement. In no event shall Seller have the right (1) to procure any element of the Product from sources other than the Project for sale or delivery to Buyer under this Agreement, or (2) sell Product from the Project to a third party. Buyer shall have no obligation to receive or purchase Product from Seller prior to or after the Delivery Term, except during the Test Period. Seller shall be responsible for any costs or charges imposed on or associated with the Product or its delivery of the Product up to the Delivery Point. Buyer shall be responsible for any costs or charges imposed on or associated with the Product after its receipt at and from the Delivery Point. Each Party agrees to act in good faith in the performance of its obligations under this Agreement.

(i) Full Buy/Sell. If “Full Buy/Sell” is elected on the Cover Sheet, Seller agrees to sell to Buyer the Project’s gross output of Product measured in kilowatt-hours, net of station use and transformation and transmission losses to and at the Delivery Point. Seller shall purchase all Energy required to serve the Project’s on-site load, net of station use, from Buyer or applicable retail service provider pursuant to its applicable retail rate schedule.

(c) Delivery Term.

(i) Delivery Term and Initial Energy Delivery Date. As used herein, “Delivery Term” shall mean the period of Contract Years specified on the Cover Sheet, beginning on the first date that Buyer accepts delivery of the Product from the Project in connection with this Agreement following Seller’s demonstration of satisfaction of the items listed below in this Section 3.1(c)(i) (“Initial Energy Delivery Date”) and continuing until the end of the tenth, fifteenth, or twentieth Contract Year (as applicable, based on the Cover Sheet election) unless terminated pursuant to the terms of this Agreement; provided that the Expected Initial Energy Delivery Date may be extended pursuant to Section 3.1(c)(ii). The Initial Energy Delivery Date shall be the later of the (A) date that the Buyer receives the "Initial Energy Delivery Date Confirmation Letter" attached hereto as Appendix II and (B) the date listed as the Initial Energy Delivery Date on the Initial Energy Delivery Date Confirmation Letter. The Initial Energy Delivery Date shall occur as soon as practicable once all of the following have been satisfied:

(I) Seller notifies Buyer that Commercial Operation has occurred;

(II) Buyer shall have received and accepted the Delivery Term Security or Term Security, as applicable, in accordance with the relevant provisions of Article Eight of the Agreement, as applicable;

(III) Seller shall have obtained the requisite CEC Certification and Verification for the Project and Seller shall have demonstrated submission and approval of documents and information to CRS necessary for the Project to receive an eligibility designation for Buyer’s Green-e® Energy Certification;

(IV) all of the applicable Conditions Precedent in Section 2.5(a) have been satisfied or waived in writing;

(V) for resources that are already under a contract as of the Execution Date, that existing contract must have expired by its own terms before the Initial Energy Delivery Date;

(VI) Seller shall demonstrate compliance with 3.1(p) and the ability to respond to a Buyer Curtailment Order consistent with the physical characteristics of the Project including the Operational Characteristics.

(VII) Seller shall have demonstrated satisfaction of Seller’s other obligations in this Agreement that commence prior to or as of the Delivery Term; and

(VIII) unless Seller has been directed by Buyer to not participate in the Participating Intermittent Resource Program, Buyer shall have received written notice from the CAISO that the Project is certified as a Participating Intermittent Resource to the extent the Participating Intermittent Resource Program exists for the Project’s technology type at such time as the conditions in subsections (I) through (VII) of this Section 3.1(c)(i) are satisfied.

(ii) Extensions of Test Period In the event that Seller cannot satisfy the requirements for the Initial Energy Delivery Date by the end of the Test Period, as set forth in Section 3.1(c)(i), then Seller may provide Buyer with a one-time Notice of a thirty (30) day extension of the Test Period (“Initial Extension”) along with a written explanation of the basis for the extension, no later than five (5) Business Days prior to the end of the Test Period. In the event that Seller requires an additional extension of the Test Period beyond the Initial Extension, Seller may request a further extension of the Test Period from Buyer no later than ten (10) days prior to the expiration of the Initial Extension of up to sixty (60) days by providing Notice to Buyer along with a detailed written explanation of the basis for such request (“Additional Extension”). Buyer shall provide Seller with Notice of Buyer’s acceptance or rejection, in its sole discretion, of such Notice of Additional Extension within ten (10) days of receipt of Seller’s Notice of Additional Extension. If Buyer fails to provide a Notice of Buyer’s acceptance or rejection, then Seller’s Notice of Additional Extension shall be deemed accepted. If Buyer provides Seller with Notice of Buyer’s rejection of the Additional Extension, then Seller may be subject to an Event of Default. As evidence of the Initial Energy Delivery Date, the Parties shall execute and exchange the “Initial Energy Delivery Date Confirmation Letter,” attached hereto as Appendix II, on the Initial Energy Delivery Date.

(d) Delivery Point. The Delivery Point shall be the PNode designated by the CAISO for the Project.

(e) Contract Quantity and Guaranteed Energy Production.

(i) Contract Quantity. The Contract Quantity during each Contract Year is the amount set forth in the applicable Contract Year in Section D of the Cover Sheet (“Delivery Term Contract Quantity Schedule”)**,** which amount is inclusive of outages**.**

(ii) Guaranteed Energy Production.

(A) Throughout the Delivery Term, Seller shall be required to provide to Buyer an amount of Delivered Energy plus Deemed Delivered Energy, if any, no less than the Guaranteed Energy Production over two (2) consecutive Contract Years during the Delivery Term (“Performance Measurement Period”). “Guaranteed Energy Production” is equal to the product of (x) and (y), where (x) is one hundred sixty percent (160%) of the average of the Contract Quantities applicable to the two (2) Contract Years comprising the Performance Measurement Period , and (y) is the difference between (I) and (II), with the resulting difference divided by (I), where (I) is the number of hours in the applicable Performance Measurement Period and (II) is the aggregate number of Seller Excuse Hours in the applicable Performance Measurement Period. Guaranteed Energy Production is described by the following formula:

Guaranteed Energy Production = (160% × average of the Contract Quantities in MWh in Performance Measurement Period) × [(Hrs in Performance Measurement Period – Seller Excuse Hrs in Performance Measurement Period) / Hrs in Performance Measurement Period]

(B) In no event shall any amount of Delivered Energy plus Deemed Delivered Energy in any Settlement Interval that exceeds the Contract Capacity be credited toward or added to Seller’s Guaranteed Energy Production requirement.

(C) GEP Failure, Cure, Damages.

(I) If Seller has a GEP Failure, then within forty-five (45) days after the last day of the last month of such Performance Measurement Period, Buyer shall promptly provide Notice to Seller of such failure, provided that Buyer’s failure to provide Notice shall not constitute as a waiver of Buyer’s rights to collect GEP Damages. Seller may cure the GEP Failure by providing to Buyer an amount of Delivered Energy plus Deemed Delivered Energy, if any, that is no less than ninety percent (90%) of the Contract Quantity, for the Contract Year following the GEP Failure, subject to adjustment for Seller Excuse Hours as set forth in the formula below (“GEP Cure”).

GEP Cure = (90% × Contract Quantity in MWh) × [(Hrs in next following Contract Year – Seller Excuse Hrs in next following Contract Year) / Hrs in next following Contract Year]

If Seller fails to provide sufficient Delivered Energy plus Deemed Delivered Energy, if any, as adjusted by Seller Excuse Hours, to qualify for the GEP Cure for a given Performance Measurement Period, Seller shall pay GEP Damages, calculated pursuant to Appendix V (“GEP Damages Calculation”). If Seller provides a GEP Cure or pays GEP Damages for the Contract Years in a particular Performance Measurement Period (“Cured Performance Measurement Period”), then for purposes of calculating the Guaranteed Energy Production in the following Performance Measurement Period, the amount of Delivered Energy plus Deemed Delivered Energy in the second Contract Year of the Cured Performance Measurement Period, which is also the first Contract Year of the following Performance Measurement Period (“Shared Contract Year”), shall be deemed equal to the greater of (X) the Delivered Energy plus Deemed Delivered Energy, if any, for the Shared Contract Year, subject to adjustment for Seller Excuse Hours, or (Y) eighty percent (80%) of Contract Quantity in the Shared Contract Year, where X and Y are calculated as follows:

X = (Delivered Energy + Deemed Delivered Energy in Shared Contract Year ) × [Hrs in Shared Contract Year / (Hrs in Shared Contract Year– Seller Excuse Hours in Shared Contract Year)] or;

Y = 80% × Contract Quantity in Shared Contract Year

For the avoidance of doubt, the calculation set forth above for the amount of Delivered Energy plus Deemed Delivered Energy for the Shared Contract Year shall not apply to the cumulative GEP Shortfall under Section 5.1(b)(v)(B).

(II) The Parties agree that the damages sustained by Buyer associated with Seller’s failure to achieve the Guaranteed Energy Production requirement would be difficult or impossible to determine, or that obtaining an adequate remedy would be unreasonably time consuming or expensive and therefore agree that Seller shall pay the GEP Damages to Buyer as liquidated damages. In no event shall Buyer be obligated to pay GEP Damages.

(III) After the GEP Cure period has run, if Seller has not achieved the GEP Cure, Buyer shall have forty-five (45) days to notify Seller of such failure. Within forty‑five (45) days of the end of the GEP Cure period, Buyer shall provide Notice to Seller in writing of the amount of the GEP Damages, if any, which Seller shall pay within sixty (60) days of receipt of the Notice (the “Cure Payment Period”). If Seller does not pay the GEP Damages within the Cure Payment Period, then Buyer may, at its option, declare an Event of Default pursuant to Section 5.1(b)(v)(A) within ninety (90) days following the Cure Payment Period. If Seller has failed to pay the GEP Damages, and Buyer does not (1) notify Seller of the GEP Failure or (2) declare an Event of Default pursuant to Section 5.1(b)(v) within the ninety (90) day period, then Buyer shall be deemed to have waived its right to declare an Event of Default based on Seller’s failure with respect to the Performance Measurement Period which served as the basis for the notice of GEP Failure, GEP Damages, or default, subject to the limitations set forth in Section 5.1(b)(v)(B).

(f) Contract Capacity. The generation capability designated for the Project shall be the contract capacity in MW designated in the Cover Sheet, (the “Contract Capacity”). Throughout the Delivery Term, Seller shall sell and deliver all Product produced by the Project solely to Buyer. In no event shall Buyer be obligated to receive, in any Settlement Interval, any Surplus Delivered Energy. Seller shall not receive payment for any Surplus Delivered Energy. To the extent Seller delivers Surplus Delivered Energy to the Delivery Point in a Settlement Interval in which the Real-Time Price for the applicable PNode is negative, Seller shall pay Buyer an amount equal to the Surplus Delivered Energy (in MWh) during such Settlement Interval, multiplied by the absolute value of the Real-Time Price per MWh for such Settlement Interval.

(g) Project.

(i) All Product provided by Seller pursuant to this Agreement shall be supplied from the Project only. Seller shall not make any alteration, addition, or modification to the Project without Buyer’s prior written consent. The Project Specifications are further described in Appendix XIII.

(ii) Seller shall not relinquish its possession or demonstrable exclusive right to control the Project without the prior written consent of Buyer, except under circumstances provided in Section 10.6. Seller shall be deemed to have relinquished possession of the Project if after the Commercial Operation Date Seller has ceased work on the Project or ceased production and delivery of Product for a consecutive thirty (30) day period and such cessation is not a result of a Force Majeure event or direct action of Buyer.

(h) Interconnection Facilities.

***[The following bracketed language applies to Projects that do not utilize Shared Facilities****]*

***[***(i) Seller Obligations. Seller shall (A) arrange and pay independently for any and all necessary costs under any Generator Interconnection Agreement with the Participating Transmission Owner; (B) cause the Interconnection Customer’s Interconnection Facilities, including metering facilities, to be maintained; (C) comply with the procedures set forth in the GIP and applicable agreements or procedures provided under the GIP in order to obtain the applicable Electric System Upgrades; and (D) obtain Electric System Upgrades, as needed, in order to ensure the safe and reliable delivery of Energy from the Project up to and including quantities that can be produced utilizing all of the Contract Capacity of the Project.***]***

***[The following bracketed language applies to Projects that utilize Shared Facilities.]***

***[***(i) Seller Obligations. Seller shall (A) arrange and pay independently for any and all necessary costs under any Generator Interconnection Agreement with the Participating Transmission Owner; (B) cause the Interconnection Customer’s Interconnection Facilities, including Shared Facilities and metering facilities, to be maintained; (C) comply with the procedures set forth in the GIP and applicable agreements or procedures provided under the GIP in order to obtain the applicable Electric System Upgrades; (D) obtain Electric System Upgrades, as needed, in order to ensure the safe and reliable delivery of Energy from the Project up to and including quantities that can be produced utilizing all of the Contract Capacity of the Project; and (E) ensure that Seller has sufficient interconnection capacity and rights under or through the Shared Facilities Agreements to fulfill its obligations under this Agreement.***]***

(ii) Coordination with Buyer.

(A) Seller shall (I) provide to Buyer copies of all material correspondence related to the GIA and CAISO Exemption; ; (II) provide Buyer with written reports of the status of the GIA on a monthly basis prior to the Delivery Term; and (III) obtain consent from Buyer before making any material amendment to the GIA or CAISO Exemption. The foregoing shall not preclude Seller from executing a GIA or obtaining a CAISO Exemption that it reasonably determines allows it to comply with its obligations under this Agreement and applicable Law

(B) Excess Network Upgrade Costs. Seller shall provide Buyer within ten (10) Business Days of receipt thereof, copies of any Interconnection Study or the interconnection agreement tendered to Seller by the Participating Transmission Owner that may give rise to a termination right of Buyer under Section 3.9(f)(i). Within that same period Seller shall also provide Buyer a Notice of its irrevocable election to exercise or not exercise its right to assume financial responsibility for any Excess Network Upgrade Cost pursuant to Section 3.9(f)(i), with a failure to provide such an election deemed to be an election not to exercise such rights for purposes of administration and enforcement of the terms of this Agreement.

(i) Performance Excuses.

(i) Seller Excuse. Seller shall be excused from achieving the Guaranteed Energy Production only for the applicable time period during Seller Excuse Hours.

(ii) Buyer Excuses. Buyer shall be excused from (A) receiving and paying for the Product only (I) during periods of Force Majeure, (II) by Seller’s failure to perform, (III) during Curtailment Periods and (B) receiving Product during Buyer Curtailment Periods.

(iii) Curtailment. Notwithstanding Section 3.1(b) and this Section 3.1(i), Seller shall reduce output from the Project during any Curtailment Period or Buyer Curtailment Period.

(j) Greenhouse Gas Emissions Reporting. During the Term, Seller acknowledges that a Governmental Authority may require Buyer to take certain actions with respect to greenhouse gas emissions attributable to the generation of Energy, including reporting, registering, tracking, allocating for or accounting for such emissions. Promptly following Buyer’s written request, Seller agrees to take all commercially reasonable actions and execute or provide any and all documents, information or instruments with respect to generation by the Project reasonably necessary to permit Buyer to comply with such requirements, if any. Nothing in this Section 3.1(j) shall cause Buyer to assume any liability or obligation with respect to Seller’s compliance obligations with respect to the Project under any new or existing Laws, rules, or regulations.

(k) WREGIS. Seller shall, at its sole expense, take all actions and execute all documents or instruments necessary to ensure that all WREGIS Certificates associated with all Renewable Energy Credits corresponding to all Delivered Energy are issued and tracked for purposes of satisfying the requirements of the California Renewables Portfolio Standard and transferred in a timely manner to Buyer for Buyer’s sole benefit. Seller shall transfer the Renewable Energy Credits to Buyer even if Buyer does not accept and/or pay for the underlying energy per Section 3.1(f). Seller shall comply with all Laws, including the WREGIS Operating Rules, regarding the certification and transfer of such WREGIS Certificates to Buyer and Buyer shall be given sole title to all such WREGIS Certificates. Seller shall be deemed to have satisfied the warranty in Section 3.1(k)(viii), provided that Seller fulfills its obligations under Sections 3.1(k)(i) through (vii) below. In addition:

(i) Prior to the Initial Energy Delivery Date, Seller shall register the Project with WREGIS and establish an account with WREGIS (“Seller’s WREGIS Account”), which Seller shall maintain until the end of the Delivery Term. Seller shall transfer the WREGIS Certificates using “Recurring Certificate Transfers” (as described in the WREGIS Operating Rules) from Seller’s WREGIS Account to the WREGIS account(s) of Buyer or the account(s) of a designee that Buyer identifies by Notice to Seller (“Buyer’s WREGIS Account”). Seller shall be responsible for all expenses associated with registering the Project with WREGIS, establishing and maintaining Seller’s WREGIS Account, paying WREGIS Certificate issuance and transfer fees, and transferring WREGIS Certificates from Seller’s WREGIS Account to Buyer’s WREGIS Account.

(ii) Seller shall cause Recurring Certificate Transfers to occur on a monthly basis in accordance with the certification procedure established by the WREGIS Operating Rules. Since WREGIS Certificates will only be created for whole MWh amounts of Energy generated, any fractional MWh amounts (i.e., kWh) will be carried forward until sufficient generation is accumulated for the creation of a WREGIS Certificate.

(iii) Seller shall, at its sole expense, ensure that the WREGIS Certificates for a given calendar month correspond with the Delivered Energy for such calendar month as evidenced by the Project’s metered data.

(iv) Due to the delay in the creation of WREGIS Certificates relative to the timing of invoice payment under Article 6, Buyer shall make an invoice payment for a given month in accordance with Article 6 before the WREGIS Certificates for such month are formally transferred to Buyer in accordance with the WREGIS Operating Rules and this Section 3.1(k). Notwithstanding this delay, Buyer shall have all right and title to all such WREGIS Certificates upon payment to Seller in accordance with Article 6.

(v) A “WREGIS Certificate Deficit” means any deficit or shortfall in WREGIS Certificates delivered to Buyer for a calendar month as compared to the Delivered Energy for the same calendar month (“Deficient Month”). If any WREGIS Certificate Deficit is caused, or the result of any action or inaction, by Seller, then the amount of Delivered Energy in the Deficient Month shall be reduced by the amount of the WREGIS Certificate Deficit for the purposes of calculating Buyer’s payment(s) to Seller under Article 6 and the Guaranteed Energy Production for the applicable Performance Measurement Period. Any amount owed by Seller to Buyer because of a WREGIS Certificate Deficit shall be made as an adjustment to Seller’s next monthly invoice to Buyer in accordance with Article 6, and Buyer shall net such amount against Buyer’s subsequent payment(s) to Seller pursuant to Article 6.

(vi) Without limiting Seller’s obligations under this Section 3.1(k), if a WREGIS Certificate Deficit is caused solely by an error or omission of WREGIS, the Parties shall cooperate in good faith to cause WREGIS to correct its error or omission.

(vii) If WREGIS changes the WREGIS Operating Rules after the Execution Date or applies the WREGIS Operating Rules in a manner inconsistent with this Section 3.1(k) after the Execution Date, the Parties promptly shall modify this Section 3.1(k) as reasonably required to cause and enable Seller to transfer to Buyer’s WREGIS Account a quantity of WREGIS Certificates for each given calendar month that corresponds to the Delivered Energy in the same calendar month.

(viii) Seller warrants that all necessary steps to allow the Renewable Energy Credits transferred to Buyer to be tracked in the Western Renewable Energy Generation Information System will be taken prior to the first delivery under the contract.

(ix) Buyer shall not return the Performance Assurance until all WREGIS certificates have been transferred to Buyer. In the event that there are no subsequent payment(s) to Seller under this Agreement pursuant to Article 6 and a WREGIS Certificate Deficit occurs, then one hundred and twenty (120) days after the last identified WREGIS Certificate Deficit, Buyer shall have the right to net the WREGIS Certificate Deficit in accordance with Section 3.1(k)(v) against the Performance Assurance, or Seller can pay such amount directly to Buyer in a form mutually agreeable to both Parties.

(l) Access to Data and Installation and Maintenance of Weather Station.

(i) Commencing on the first date on which the Project generates Product to be delivered to the CAISO Grid or the Delivery Point, if different, and continuing throughout the Term, Seller shall provide to Buyer, in a form reasonably acceptable to Buyer, the data set forth below on a real-time basis; provided that Seller shall agree to make and bear the cost of changes to any of the data delivery provisions below, as requested by Buyer, throughout the Term, which changes Buyer determines are necessary to forecast output from the Project, and/or comply with Law:

(A) read-only access to meteorological measurements, inverter and transformer availability, any other facility availability information, all parameters necessary for use in the equation under item (G) of this list;

(B) read-only access to energy output information collected by the supervisory control and data acquisition (SCADA) system for the Project; provided that if Buyer is unable to access the Project’s SCADA system, then upon written request from Buyer, Seller shall provide energy output information and meteorological measurements to Buyer in 1‑minute intervals in the form of a flat file to Buyer through a secure file transport protocol (FTP) system with an e-mail back up for each flat file submittal;

(C) read-only access to the Project’s CAISO Revenue Meter and all Project meter data at the Site;

(D) full, real-time access to the Project’s CAISO Outage Management System(OMS) client application, or its successor system;

(E) net plant electrical output at the CAISO Revenue Meter;

(F) instantaneous data measurements at sixty (60) second or increased frequency for the parameters set forth in Appendix X (“Telemetry Parameters for Wind or Solar Facilities”), which measurements shall be provided by Seller to Buyer in consolidated data report at least once every five minutes via flat file through a secure file transport protocol (FTP) system with an e-mail backup; and

(G) an equation, updated on an ongoing basis to reflect the potential generation of the Project as a function ofsolar insolation, temperature, wind speed, and, if applicable, wind direction. Such equation shall take into account the expected availability of the facility.

For any month in which the above information and access was not available to Buyer for longer than twenty-four (24) continuous hours, Seller shall prepare and provide to Buyer upon Buyer’s request a report with the Project’s monthly Settlement Interval Actual Available Capacity in the form set forth in Appendix IX (“Actual Availability Report”). Upon Buyer’s request, Seller shall promptly provide to Buyer any additional and supporting documentation necessary for Buyer to audit and verify any matters set forth in the Actual Availability Report. Buyer shall exercise commercially reasonable efforts to notify Seller of any deficiency by Seller in meeting the requirements of this Section 3.1(l)(i); provided that any failure by Buyer to provide such deficiency notice shall not result in any additional liability to Buyer under this Agreement.

(ii) Buyer reserves the right to validate the data provided pursuant to Section 3.1(l)(i) with information publicly available from NOAA and nearby weather stations and substitute such data for its scheduling purposes if Seller’s data is inconsistent with the publicly available data or is missing; provided that Buyer shall notify Seller promptly of Buyer’s substitution of such data.

(iii) Seller shall maintain at least a minimum of one hundred twenty (120) days’ historical data for all data required pursuant to Section 3.1(l)(i), which shall be available on a minimum time interval of one hour basis or an hourly average basis, except with respect to the meteorological measurements which shall be available on a minimum time interval of ten (10) minute basis. Seller shall provide such data to Buyer within five (5) Business Days of Buyer’s request.

(iv) Installation, Maintenance and Repair.

(A) Seller, at its own expense, shall install and maintain one (1) stand-alone meteorological station at the Site to monitor and report the meteorological data required in Section 3.1(l)(i) of this Agreement, and for wind Projects, each wind turbine must be equipped with meteorological measurement equipment (e.g. anemometers) which are individually linked to Seller’s plant information system. Seller, at its own expense, shall install and maintain a secure communication link in order to provide Buyer with access to the data required in Section 3.1(l)(i) of this Agreement.

(B) Seller shall maintain the meteorological stations, telecommunications path, hardware, and software necessary to provide accurate data to Buyer or Third-Party SC (as applicable) to enable Buyer or the Third-Party SC to meet current CAISO scheduling requirements. Seller shall promptly repair and replace as necessary such meteorological stations, telecommunications path, hardware and software and shall notify Buyer as soon as Seller learns that any such telecommunications paths, hardware and software are providing faulty or incorrect data.

(C) If Buyer notifies Seller of the need for maintenance, repair or replacement of the meteorological stations, telecommunications path, hardware or software, Seller shall maintain, repair or replace such equipment as necessary within five (5) days of receipt of such Notice.

(D) For any occurrence in which Seller’s telecommunications system is not available or does not provide quality data and Buyer notifies Seller of the deficiency or Seller becomes aware of the occurrence, Seller shall transmit data to Buyer through any alternate means of verbal or written communication, including cellular communications from onsite personnel, e-mail, or other method mutually agreed upon by the Parties, until the telecommunications link is re-established.

(v) Seller agrees and acknowledges that Buyer may seek from third parties any information relevant to its duties as SC for Seller, including from the Participating Transmission Operator or utility distribution company. Seller hereby voluntarily consents to allow the Participating Transmission Operator to share Seller’s information with Buyer in furtherance of Buyer’s duties as SC for Seller, and agrees to provide the Participating Transmission Owner with written confirmation of such voluntary consent at least ninety (90) days prior to the Initial Energy Delivery Date.

(vi) No later than ninety (90) days before the Initial Energy Delivery Date, Buyer may request and Seller shall promptly provide one (1) year, if available, but no less than six (6) months, of recorded meteorological data to Buyer in a form reasonably acceptable to Buyer from a weather station at the Site. Such weather station shall provide, via remote access to Buyer, all data relating to (A) totalglobal horizontal irradiance, plane of array or direct normal insolation as is applicable for project type, air temperature, wind speed and direction, precipitation, barometric pressure, visibility in fog areas (forward scatter sensor) and humidity at the Site, as well as time-average data including 10-minute and hourly values of irradiance or insolation, air temperature, wind speed, wind direction, standard deviation of wind direction, relative humidity, precipitation, barometric pressure ***[Include the following bracketed language only if winter season output of solar Project is an issue] [***and visibility in fog areas***]*** All data, except peak values, should be 1-second samples averaged into 10-minute periods; (B) elevation, latitude and longitude of the weather station; and (C) any other data reasonably requested by Buyer.

(m) Prevailing Wage. Seller shall use reasonable efforts to ensure that all Electricians hired by Seller, Seller’s contractors and subcontractors are paid wages at rates not less than those prevailing for Electricians performing similar work in the locality as provided by Division 2, Part 7, Chapter 1 of the California Labor Code. Nothing herein shall require Seller, its contractors and subcontractors to comply with, or assume liability created by other inapplicable provisions of the California Labor Code.

(n) Obtaining and Maintaining CEC Certification and Verification. Seller shall take all necessary steps including making or supporting timely filings with the CEC to obtain and maintain CEC Certification and Verification throughout the Term.

(o) Curtailment Requirements.

(i) Order. Seller shall reduce generation from the Project as required pursuant to a Buyer Curtailment Order or Curtailment Order, provided that a Buyer Curtailment Order or Curtailment Order shall be consistent with the Operational Characteristics. Seller agrees to reduce the Project’s generation by the amount and for the period set forth in the Buyer Curtailment Order or Curtailment Order. Buyer’s communication to Seller in advance of a Buyer Curtailment Order need not be greater than that required to support the Dispatch Interval in the Real-Time Market. The Parties agree that the Buyer Curtailment Period or Curtailment Orders shall be for unlimited hours cumulatively per Contract Year (which may or may not be consecutive). Buyer shall pay Seller for Deemed Delivered Energy associated with a Buyer Curtailment Period pursuant to Article Four.

(ii) Failure to Comply. If Seller fails to comply with a Buyer Curtailment Order or Curtailment Order provided in compliance with Section 3.1(o)(i), then, for each MWh of Delivered Energy that the Project generated in contradiction to the Buyer Curtailment Order or Curtailment Order, Seller shall pay Buyer for each such MWh at an amount equal to the sum of (A) + (B) + (C), where: (A) is the amount, if any, paid to Seller by Buyer for delivery of such MWh and, (B) is the absolute value of the Real-Time Price for the applicable PNode, if such price is negative, for the Buyer Curtailment Period or Curtailment Period and, (C) is any penalties or other charges resulting from Seller’s failure to comply with the Buyer Curtailment Order or Curtailment Order.

(iii) Operational Characteristics. Seller shall maintain the Project such that the Project is able to provide equal to or better flexibility as provided by the Operational Characteristics. Seller agrees to coordinate with Scheduling Coordinator to ensure all information provided to the CAISO regarding the operational and technical constraints in the Master File for the Project are accurate and are based on the Operational Characteristics. Upon mutual written agreement between the Parties, the Scheduling Coordinator may request that CAISO modify the Master File for the Project.

(p) Seller Equipment Required for Curtailment Instruction Communications. Seller shall acquire, install, and maintain such facilities, software, communications links and other equipment, and implement such protocols and practices, as necessary to respond and follow instructions, including an electronic signal conveying real time and intra-day Dispatch Instructions, to operate the Units as directed by the Buyer and/or a Governmental Authority, including to implement a Buyer Curtailment Order or Curtailment Order in accordance with the then-current methodology used to transmit such instructions as it may change from time to time. If at any time during the Delivery Term Seller’s facilities, communications links or other equipment, protocols or practices are not in compliance with then-current methodologies, Seller shall take the steps necessary to become compliant as soon as commercially reasonably possible. Seller shall be liable pursuant to Section 3.1(o)(ii) for failure to comply with a Buyer Curtailment Order or Curtailment Order, during the time that Seller’s facilities, communications links or other equipment, protocols or practices are not in compliance with then-current methodologies. For the avoidance of doubt, a Buyer Curtailment Order or Curtailment Order communication via such systems and facilities shall have the same force and effect on Seller as any other form of communication.

(q) Supplier Diversity Program. Seller shall comply with Buyer’s Supplier Diversity Program in accordance with Appendix XII.

(r) Green-e® Energy Certification

(i) As of the Effective Date, Seller represents and warrants that (A) the Project is eligible for Greene® Energy Certification and (B) the WREGIS Certificates associated with the Renewable Energy Credits corresponding to Delivered Energy have not been sold, separately marketed or otherwise separately represented by Seller or its Affiliates as renewable energy attributable to the Project other than to Buyer.

(ii) From the Execution Date, and for the duration of the Delivery Term, Seller covenants that it shall, at its sole expense, take all actions, including complying with all applicable registration, attestation, eligibility, auditing, and reporting requirements, and execute all documents or instruments necessary (A) to be eligible for and maintain the Green-e® Energy Certification during the Delivery Term, and (B) to enable Buyer to meet its obligation with Green-e® Energy Certification during the Delivery Term.

3.2 Green Attributes . Seller hereby provides and conveys all Green Attributes associated with all electricity generation from the Project to Buyer as part of the Product being delivered. Seller represents and warrants that Seller holds the rights to all Green Attributes from the Project, and Seller agrees to convey and hereby conveys all such Green Attributes to Buyer as included in the delivery of the Product from the Project.

3.3 Resource Adequacy .

(a) During the Delivery Term, Seller grants, pledges, assigns and otherwise commits to Buyer all of the Project’s Contract Capacity, including Capacity Attributes from the Project, to enable Buyer to meet its Resource Adequacy or successor program requirements, as the CPUC, CAISO and/or other regional entity may prescribe, including submission of a Supply Plan or Resource Adequacy Plan (“Resource Adequacy Requirements”). From the Execution Date, and for the duration of the Delivery Term, Seller shall take all commercially reasonable actions, including complying with all applicable registration and reporting requirements, and execute any and all documents or instruments necessary to enable Buyer to use all of the capacity of the Project, including Capacity Attributes, to be committed by Seller to Buyer pursuant to this Agreement to meet Buyer’s Resource Adequacy Requirements during the Delivery Term.

(b) Seller shall be responsible for all costs, charges, expenses, penalties, and obligations resulting from Resource Adequacy Standards, if applicable.

(c) Buyer shall be responsible for all costs, charges, expenses, penalties, and obligations resulting from the Replacement Capacity Rules, if applicable, provided that Seller has given Buyer Notice of the outages subject to the Replacement Capacity Rules by the earlier of ninety (90) days before the first day of the month for which the outage will occur or forty-five (45) days before Buyer’s monthly Resource Adequacy capacity showing in accordance with the CAISO Tariff or decision of the CPUC. If Seller fails to provide such Notice, then Seller shall be responsible for all costs, charges, expenses, penalties, and obligations resulting from the Replacement Capacity Rules for such outage.

(d) To the extent Seller has an exemption from the Resource Adequacy Standards or under the CAISO Tariff, Section 3.3(b) above shall not apply. To the extent Seller has an exemption from the Replacement Capacity Rules under the CAISO Tariff, Section 3.3(c) shall not apply. If Seller would like to request such an exemption for this Agreement from the CAISO, Seller shall provide to Buyer, as Seller’s Scheduling Coordinator, Notice specifically requesting that Buyer seek certification or approval of this Agreement as an exempt contract pursuant to the CAISO Tariff; provided that Buyer’s failure to obtain such exemption shall not be an Event of Default and Buyer shall not have any liability to Seller for such failure.

(e) Resource Adequacy Failure.

(i) RA Deficiency Determination. Notwithstanding Seller’s obligations set forth in Section 3.4(a)(i)(A) or anything to the contrary herein, the Parties acknowledge and agree that:

(A) if Seller is unable to obtain the deliverability type selected in Section A of the Cover Page by the RA Start Date, then Seller shall pay to Buyer the RA Deficiency Amount for each RA Shortfall Month as liquidated damages due to Buyer for the Capacity Attributes that Seller failed to convey to Buyer; and

(B) if Seller is unable to obtain the deliverability type selected in Section A of the Cover Page by the Deliverability Finding Deadline, then Seller shall be in breach of this Agreement and subject to an Event of Default under Sections 5.1(b)(vi) - (vii), regardless of Seller’s payment of any RA Deficiency Amount hereunder.

(ii) RA Deficiency Amount Calculation.

(A) Buyer shall calculate the RA Deficiency Amount for each RA Shortfall Month using the formula set forth in Section 3.3(e)(ii)(B). Buyer shall notify Seller of the RA Deficiency Amount for a given RA Shortfall Month no later than the last day of that RA Shortfall Month. The Parties agree that these liquidated damages shall be paid to Buyer for each RA Shortfall Month and constitute a reasonable approximation of the harm or loss suffered by Buyer. The Parties further agree that Buyer may use such liquidated damages for any purpose in its sole discretion. Seller shall pay the RA Deficiency Amount for a given RA Shortfall Month in the form of a deduction from the amount invoiced by Seller in such month pursuant to Section 6.1. In the event that the RA Deficiency Amount for a given RA Shortfall Month exceeds the amount invoiced pursuant to Section 6.1, Buyer shall make no payment to Seller for that month, and the difference between the invoiced amount and the RA Deficiency Amount shall be deducted from the amount(s) invoiced in the succeeding month(s) until all of the RA Deficiency Amount for such RA Shortfall Month has been deducted. Any dispute regarding Buyer’s calculation of any RA Deficiency Amount shall be resolved in accordance with Article Twelve.

(B) The RA Deficiency Amount for a given RA Shortfall Month shall be equal to the product of the RA Value and the Expected Net Qualifying Capacity, as calculated in accordance with Appendix XIV. The RA Deficiency Amount is represented by the following equation:

RA Deficiency Amount ($/Month) = RA Value ($/MW/Month) × Expected Net Qualifying Capacity (MW)

To the extent the Project obtains Net Qualifying Capacity that Seller applies towards its obligations under Section 3.3(a) before the Project obtains the deliverability type selected in Section A of the Cover Page (e.g., through the CAISO’s Operational Deliverability Assessment), then the RA Deficiency Amount calculated above for a given RA Shortfall Month shall be reduced accordingly (e.g. the RA Deficiency Amount would equal the product of (x) the RA Value and (y) the difference between the Expected Net Qualifying Capacity and the actual Net Qualifying Capacity):

RA Deficiency Amount ($/Month) = RA Value ($/MW/Month) × [Expected Net Qualifying Capacity (MW) – actual Net Qualifying Capacity (MW)].

3.4 Transmission and Scheduling .

(a) Transmission.

(i) Seller’s Transmission Service Obligations. Throughout the Term, and consistent with the terms of this Agreement, Seller shall:

(A) arrange and pay independently for any and all necessary electrical interconnection, distribution and/or transmission (and any regulatory approvals required for the foregoing), sufficient to allow Seller to deliver the Product to the Delivery Point for sale pursuant to the terms of this Agreement. Seller’s interconnection, distribution and/or transmission arrangements shall provide for the deliverability type selected in Section A of the Cover Sheet as of the RA Start Date and throughout the Delivery Term.

(B) If Seller has elected Energy Only Status on the Cover Sheet, this Section 3.4(a)(i)(B) is not applicable. An FCDS or PCDS Seller shall have either previously obtained, or is obligated to obtain per the terms of the Agreement, a FCDS or PCDS Finding. If Seller’s Project has not attained Full Capacity Deliverability Status or Partial Capacity Deliverability Status prior to the Execution Date, Seller shall take all actions necessary or appropriate to cause the Delivery Network Upgrades necessary for it to obtain Full Capacity Deliverability Status or Partial Capacity Deliverability Status to be constructed and placed into service. The cost of each Deliverability Assessment and any necessary Delivery Network Upgrades to ensure Full Capacity Deliverability Status or Partial Capacity Deliverability Status shall be borne solely by Seller. When the CAISO advises Seller that the Project has Full Capacity Deliverability Status or Partial Capacity Deliverability Status, Seller shall Notify Buyer of such status within five (5) Business Days of the date it receives notification from the CAISO of such status by providing Buyer documentation from the CAISO. The Effective FCDS Date or Effective PCDS Date must occur on or before the Deliverability Finding Deadline; a failure to do so shall constitute an Event of Default under Section 5.1(a)(iii). The Termination Payment for an Event of Default caused by Seller’s failure to achieve the Effective FCDS Date or Effective PCDS Date on or before the Deliverability Finding Deadline shall be capped at the amount of Seller’s Delivery Term Security or Term Security obligation under Section 8.4(a)(ii) or (iii), as applicable.

(C) if the Project has or obtains FCDS or PCDS, Seller shall Notify Buyer of such status as of the Execution Date, if applicable, or within five (5) Business Days of the date it receives notification from the CAISO of such status by providing Buyer documentation from the CAISO.

(D) bear all risks and costs associated with such transmission service, including any transmission outages or curtailment to the Delivery Point.

(E) fulfill all contractual, metering and applicable interconnection requirements, including those set forth in the Participating Transmission Owner’s applicable tariffs, the CAISO Tariff, including any CAISO Exemption, and implementing CAISO standards and requirements, so as to be able to deliver Energy from the Project according to the terms of this Agreement.

(ii) Buyer’s Transmission Service Obligations. As of the Test Period and during the Delivery Term,

(A) Buyer shall arrange and be responsible for transmission service at and from the Delivery Point.

(B) Buyer shall bear all risks and costs associated with such transmission service, including any transmission outages or curtailment from the Delivery Point.

(C) Buyer shall schedule or arrange for Scheduling Coordinator services with its Transmission Providers to receive the Product at the Delivery Point.

(D) Buyer shall be responsible for all CAISO costs and charges, electric transmission losses and congestion at and from the Delivery Point.

(b) EIRP Requirements. Seller shall provide Buyer with a copy of the notice from CAISO certifying the Project as a Participating Intermittent Resource as soon as practicable after Seller’s receipt of such notice of certification. As of the first date of the Test Period and until the Project receives certification as a Participating Intermittent Resource, Seller, at its sole cost, shall comply with EIRP and additional protocols issued by the CAISO for Eligible Intermittent Resources. Throughout the Delivery Term, Seller, at its sole cost, shall participate in and comply with EIRP and all additional protocols issued by the CAISO for a Participating Intermittent Resource. Throughout the Delivery Term, Seller, at its sole cost, shall participate in and comply with all other protocols issued by the CAISO for generating facilities providing energy on an intermittent basis; provided that, if multiple options exist, then Seller shall comply with any such protocols, rules or regulations as directed by Buyer. Throughout the Delivery Term, Buyer in its limited capacity as Seller’s Scheduling Coordinator shall facilitate communication with the CAISO and provide other administrative materials to CAISO as necessary to satisfy Seller’s obligations as Seller’s Scheduling Coordinator and to the extent such actions are at *de minimis* cost to Buyer.

(c) Scheduling Coordinator. Buyer shall act as the Scheduling Coordinator for the Project. In that regard, Buyer and Seller shall agree to the following:

(i) Designation as Scheduling Coordinator.

(A) At least ninety (90) days before the beginning of the Test Period Seller shall take all actions and execute and deliver to Buyer all documents necessary to authorize or designate Buyer, or Third-Party SC, as Seller’s Scheduling Coordinator, and Buyer or Third-Party SC, as applicable, shall take all actions and execute and deliver to Seller or CAISO all documents necessary to become and act as Seller’s Scheduling Coordinator. If Buyer designates a Third-Party SC, then Buyer shall give Seller Notice of such designation at least ten (10) Business Days before the Third-Party SC assumes Scheduling Coordinator duties hereunder, and Seller shall be entitled to rely on such designation until it is revoked or a new Third-Party SC is appointed by Buyer upon similar Notice. Buyer shall be fully responsible for all acts and omissions of Third-Party SC and for all cost, charges and liabilities incurred by Third-Party SC to the same extent that Buyer would be responsible under this Agreement for such acts, omissions, costs, charges and liabilities if taken, omitted or incurred by Buyer directly.

(B) Seller shall not authorize or designate any other party to act as Scheduling Coordinator, nor shall Seller perform, for its own benefit, the duties of Scheduling Coordinator during the Test Period and Delivery Term.

(ii) Buyer’s Responsibilities as Scheduling Coordinator. Buyer or Third-Party SC shall comply with all obligations as Seller’s Scheduling Coordinator under the CAISO Tariff and shall conduct all scheduling in full compliance with the terms and conditions of this Agreement, the CAISO Tariff, and all requirements of EIRP (if applicable).

(iii) Replacement of Scheduling Coordinator.

(A) At least ninety (90) days prior to the end of the Delivery Term, or as soon as practicable before the date of any termination of this Agreement prior to the end of the Delivery Term, Seller shall take all actions necessary to terminate the designation of Buyer or the Third-Party SC, as applicable, as Seller’s SC. These actions include (I) submitting to the CAISO a designation of a new SC for Seller to replace Buyer or the Third-Party SC (as applicable); (II) causing the newly-designated SC to submit a letter to the CAISO accepting the designation; and (III) informing Buyer and the Third-Party SC (if applicable) of the last date on which Buyer or the Third-Party SC (as applicable) will be Seller’s SC.

(B) Buyer shall submit, or if applicable cause the Third-Party SC to submit, a letter to the CAISO identifying the date on which Buyer (or Third-Party SC, as applicable) resigns as Seller’s SC on the first to occur of either (I) thirty (30) days prior to the end of the Delivery Term or (II) the date of any early termination of this Agreement.

3.5 Standards of Care .

(a) General Operation. Seller shall comply with all applicable requirements of Law, the CAISO, NERC and WECC relating to the Project (including those related to construction, safety, ownership and/or operation of the Project). In the event Seller requires any data or information from Buyer in order to comply with any applicable requirements of Law, including the requirements of CAISO, NERC and WECC, relating to the Project (including those related to construction, safety, ownership and/or operation of the Project), then Seller shall request in writing such data from Buyer no less than forty-five (45) calendar days prior to Seller’s requested date of Buyer’s response; provided that if Seller has less than forty-five (45) calendar days prior notice of the need for such data, Seller shall request in writing such data from Buyer as soon as reasonably practicable. Buyer shall make a good faith effort to provide such data and/or information within the timeframe specified in writing by Seller or as soon thereafter as reasonably practicable.

(b) CAISO and WECC Standards. Each Party shall perform all generation, scheduling and transmission services in compliance with all applicable (i) operating policies, criteria, rules, guidelines, tariffs and protocols of the CAISO, (ii) WECC scheduling practices and (iii) Good Utility Practices.

(c) Reliability Standard. Seller agrees to abide by (i) CPUC General Order No. 167, “Enforcement of Maintenance and Operation Standards for Electric Generating Facilities”, and (ii) all applicable requirements regarding interconnection of the Project, including the requirements of the interconnected Participating Transmission Owner.

3.6 Metering . At Seller’s expense, Seller shall install, maintain, and test all CAISO Revenue Meters to accommodate the Project pursuant to the CAISO Tariff, as a CAISO Metered Entity. ***[The following bracketed language applies to Projects that utilize a Shared Facilities.]*** ***[***Seller shall install and maintain all metering arrangements, including the CAISO Exemption as applicable, that utilize the Transformer or Line Loss Correction Factors (as such terms are defined by the CAISO Tariff) to meter the Project independently.***]*** All Delivered Energy purchased under this Agreement must be measured by the Project’s CAISO Revenue Meter to be eligible for payment under this Agreement. In addition, Seller hereby agrees to provide all meter data to Buyer in a form acceptable to Buyer, and consents to Buyer obtaining from the CAISO the CAISO meter data applicable to the Project and all inspection, testing and calibration data and reports. Seller shall grant Buyer the right to retrieve the meter reads from the CAISO Market Results Interface – Settlements (MRI-S) web and/or directly from the CAISO meter(s) at the Project site. If the CAISO makes any adjustment to any CAISO meter data for a given time period, Seller agrees that it shall submit revised monthly invoices, pursuant to Section 6.2, covering the entire applicable time period in order to conform fully such adjustments to the meter data. Seller shall submit any such revised invoice no later than thirty (30) days from the date on which the CAISO provides to Seller such binding adjustment to the meter data.

3.7 Availability and Outage Notification .

(a) Available Capacity Forecasting. Seller shall provide the Available Capacity forecasts described below. Seller’s availability forecasts below shall include Project availability and updated status of photovoltaic panels, inverters, transformers, and any other equipment that may impact availability. To avoid Forecasting Penalties set forth in Section 4.3(c)(iii), Seller shall use commercially reasonable efforts to forecast the Available Capacity of the Project accurately and to transmit such information in a format reasonably acceptable to Buyer. Buyer and Seller shall agree upon reasonable changes to the requirements and procedures set forth below from time-to-time, as necessary to comply with CAISO Tariff changes, accommodate changes to their respective generation technology and organizational structure and address changes in the operating and Scheduling procedures of Buyer, Third-Party SC (if applicable) and the CAISO, including automated forecast and outage submissions.

(i) Annual Forecast of Available Capacity. No later than (I) the earlier of July 1 of the first calendar year following the Execution Date or one hundred and eighty (180) days before the first day of the first Contract Year of the Delivery Term (“First Annual Forecast Date”), and (II) on or before July 1 for each calendar year from the First Annual Forecast Date for every subsequent Contract Year during the Delivery Term, Seller shall provide to Buyer and Third-Party SC (if applicable) a non-binding forecast of the hourly Available Capacity for each day in each month of the following calendar year in a form reasonably acceptable to Buyer.

(ii) Monthly Forecast of Available Capacity. Seller shall provide to Buyer and Third-Party SC (if applicable), pursuant to subsections (A) and (B) below, a non-binding forecast of the hourly Available Capacity for each day of the following month in a form reasonably acceptable to Buyer:

(A) by the earlier of ninety (90) days before the beginning of the Test Period or forty-five (45) days before Buyer’s monthly Resource Adequacy capacity showing in accordance with the CAISO Tariff or decision of the CPUC, and

(B) throughout the Delivery Term, by the earlier of ninety (90) days before the beginning of each month or forty-five (45) days before Buyer’s monthly Resource Adequacy capacity showing must be completed in accordance with the CAISO Tariff or decision of the CPUC.

(iii) Daily Forecast of Available Capacity. For the Initial Energy Delivery Date or Commercial Operation Date, whichever is later, and thereafter during the Delivery Term, Seller or Seller’s agent shall provide a binding day ahead forecast of Available Capacity (the “Day-Ahead Availability Notice”) to Scheduling Coordinator via Buyer’s internet site, as provided in Appendix VI, for each day no later than fourteen (14) hours before the CAISO Day-Ahead Market closes. Each Day-Ahead Availability Notice shall clearly identify, for each hour, Seller’s forecast of all amounts of Available Capacity pursuant to this Agreement. If the Available Capacity changes by at least one (1) MW as of a time that is less than fourteen (14) hours prior to the CAISO deadline for submittal of Schedules into the Day-Ahead Market then Seller must notify Buyer of such change by telephone and shall send a revised notice to Buyer’s Internet site set forth in Appendix VI.

Such Notices shall contain information regarding the beginning date and time of the event resulting in the change in Available Capacity, the expected end date and time of such event, the expected Available Capacity in MW, and any other necessary information.

If Seller fails to provide Buyer with a Day-Ahead Availability Notice as required herein, then, until Seller provides a Day-Ahead Availability Notice, Buyer may rely on the most recent Day-Ahead Forecast of Available Capacity submitted by Seller to Buyer to the extent Seller’s failure contributes to Imbalance Energy, Seller shall be subject to the Forecasting Penalties set forth in Section 4.3(c)(iii).

(iv) Real-Time Available Capacity. During the Test Period and thereafter during the Delivery Term, Seller shall notify Buyer of any changes in Available Capacity of one (1) MW or more, whether due to Forced Outage, Force Majeure or other cause, as soon as reasonably possible, but no later than one (1) hour prior to the deadline for submitting Schedules to the CAISO in accordance with the CAISO rules for participation in the Real-Time Market. If the Available Capacity changes by at least one (1) MW as of a time that is less than one (1) hour prior to the Real-Time Market deadline, but before such deadline, then Seller must likewise notify Buyer. Such Notices shall contain information regarding the beginning date and time of the event resulting in the change in Available Capacity, the expected end date and time of such event, the expected Available Capacity in MW, and any other information required by the CAISO or reasonably requested by Buyer. With respect to any Forced Outage, Seller shall use commercially reasonable efforts to notify Buyer of such outage within ten (10) minutes of the commencement of the Forced Outage. Seller shall inform Buyer of any developments that will affect either the duration of such event or the availability of the Project during or after the end of such event. These notices and changes to Available Capacity shall be communicated in a method acceptable to Buyer; provided that Buyer specifies the method no later than 60 days prior to the effective date of such requirement. In the event Buyer fails to provide Notice of an acceptable method for communications under this Section 3.7(a)(iv), then Seller shall send such communications by telephone to Buyer’s Real-Time Desk and shall be sent to Buyer’s internet site as set forth in Appendix VI.

(v) To the extent that Seller obtains, in the normal course of business, other forecasts of energy production at the Project not otherwise specified in this Section 3.7, then Seller shall grant Buyer read-only access to such forecasts.

(b) Outage Notification

(i) CAISO Approval of Outage(s). Buyer, in its capacity as Scheduling Coordinator, is responsible for securing CAISO approvals for Project outages, including securing changes in its outage schedules when CAISO disapproves Buyer’s schedules or cancels previously approved outages and for entering Project outages in the CAISO Outage Management System (“OMS”) or successor system. As Scheduling Coordinator, Buyer shall put forth commercially reasonable efforts to secure and communicate CAISO approvals for Project outages in a timely manner to Seller.

(ii) Planned Outages. During the Delivery Term, Seller shall notify Buyer of its proposed Planned Outage schedule for the Project for the following calendar year by complying with Section 3.7(a)(i), (“Annual Forecast of Available Capacity”) and Section 3.7(a)(ii), (Monthly Forecast of Available Capacity”) and implementing the notification procedures set forth in Appendix VI no later than July 1st of each year during the Delivery Term. Seller shall also notify Buyer of the proposed Planned Outage schedule for the Project by the earlier of ninety (90) days before the beginning of each month or forty-five (45) days before Buyer’s monthly Resource Adequacy capacity showing must be completed in accordance with the CAISO Tariff or decision of the CPUC. The Planned Outage schedule is subject to Buyer’s approval, which approval may not be unreasonably withheld or conditioned. Seller shall also confirm or provide updates to Buyer regarding the Planned Outage by the earlier of fourteen (14) days prior to each Planned Outage or two (2) Business Days prior to the CAISO deadline for submitting Planned Outages. Seller shall not conduct Planned Outages during the months of January, May through September, and December. During all other months, Seller shall not schedule Planned Outages without the prior written consent of Buyer, which consent may not be unreasonably withheld or conditioned. Seller shall contact Buyer with any requested changes to the Planned Outage schedule if Seller believes the Project must be shut down to conduct maintenance that cannot be delayed until the next scheduled Planned Outage consistent with Good Utility Practices. Seller shall not change its Planned Outage schedule without Buyer’s approval, not to be unreasonably withheld or conditioned. Subject to Section 3.7(b)(i), after any Planned Outage has been scheduled, at any time up to the commencement of work for the Planned Outage, Buyer may direct that Seller change its outage schedule as ordered by CAISO. For non-CAISO ordered changes to a Planned Outage schedule requested by Buyer, Seller shall notify Buyer of any incremental costs associated with such schedule change and an alternative schedule change, if any, that would entail lower incremental costs. If Buyer agrees to pay the incremental costs, Seller shall use commercially reasonable efforts to accommodate Buyer’s request.

(iii) Forced Outages. Seller shall notify Buyer of a Forced Outage as promptly as possible, but no later than ten (10) minutes after the commencement of the Forced Outage and in accordance with the notification procedures set forth in Appendix VI. Buyer shall put forth commercially reasonable efforts to submit such outages to CAISO.

(iv) Prolonged Outages. Seller shall notify Buyer of a Prolonged Outage as soon as practicable in accordance with the notification provisions in Appendix VI. Seller shall notify Buyer in writing when the Project is again capable of meeting its Contract Capacity on a *pro rata* basis also in accordance with the notification provisions in Appendix VI.

(v) Force Majeure. Within two (2) Business Days of commencement of an event of Force Majeure, the non-performing Party shall provide the other Party with oral notice of the event of Force Majeure, and within two (2) weeks of the commencement of an event of Force Majeure the non-performing Party shall provide the other Party with Notice in the form of a letter describing in detail the particulars of the occurrence giving rise to the Force Majeure claim. Failure to provide timely Notice constitutes a waiver of a Force Majeure claim. The suspension of performance due to a claim of Force Majeure must be of no greater scope and of no longer duration than is required by the Force Majeure. Buyer shall not be required to make any payments for any Products that Seller fails to deliver or provide as a result of Force Majeure during the term of a Force Majeure.

(vi) Communications with CAISO. Buyer shall be responsible for all outage coordination communications with CAISO outage coordination personnel and CAISO operations management, including submission to CAISO of updates of outage plans, submission of clearance requests, and all other outage-related communications.

(vii) Changes to Operating Procedures. Notwithstanding any language to the contrary contained in Sections 3.4, 3.6, 3.7, 3.8, or 10.13, or Appendix VI, and consistent with Section 3.5, Seller understands and acknowledges that the specified access to data and installation and maintenance of weather stations, transmission and scheduling mechanisms, metering requirements, Outage Notification Procedures and scheduling, forecast, bidding, notification and operating procedures described in the above-referenced sections are subject to change. If such changes are provided by (i) Notice from Buyer, then Seller shall implement any such changes as reasonably deemed necessary by Buyer; provided that such change does not result in an increased cost of performance to Seller hereunder other than *de minimis* amounts, or (ii) Law, then the Parties shall implement such changes as necessary for Seller and Buyer to perform their respective rights and obligations in accordance with the Law.

3.8 Operations Logs and Access Rights .

(a) Operations Logs. Seller shall maintain a complete and accurate log of all material operations and maintenance information on a daily basis. Such log shall include information on power production,efficiency, availability, maintenance performed, outages, results of inspections, manufacturer recommended services, replacements, electrical characteristics of the generators, control settings or adjustments of equipment and protective devices. Seller shall provide this information electronically to Buyer within thirty (30) days of Buyer’s request.

(b) Access Rights. Buyer, its authorized agents, employees and inspectors may, on reasonable advance notice (which no case shall be less than three (3) Business Days) visit the Project during normal business hours for purposes reasonably connected with this Agreement or the exercise of any and all rights secured to Buyer by Law, or its tariff schedules, PG&E Interconnection Handbook, Electric Rule 21, and rules on file with the CPUC. In connection with the foregoing, Buyer, its authorized agents, employees and inspectors must (i) at all times adhere to all safety and security procedures as may be required by Seller; (ii) not interfere with the operation of the Project; and (iii) unless waived in writing by Seller, be escorted by a representative of Seller. Buyer shall make reasonable efforts to coordinate its emergency activities with the Safety and Security Departments, if any, of the Project operator. Seller shall keep Buyer advised of current procedures for contacting the Project operator’s Safety and Security Departments.

3.9 New Generation Facility .

(a) Seller, at no cost to Buyer, shall be responsible to:

(i) Design and construct the Project.

(ii) Perform all studies, pay all fees, obtain all necessary approvals and execute all necessary agreements with the CAISO, the Participating Transmission Owner, and the applicable distribution provider for the Interconnection Facilities to Schedule and deliver the Product.

(iii) Acquire all permits and other approvals necessary for the construction, operation, and maintenance of the Project.

(iv) Complete all environmental impact studies necessary for the construction, operation, and maintenance of the Project.

(v) At Buyer’s request, provide to Buyer the Seller’s electrical specifications and design drawings pertaining to the Project for Buyer’s review prior to finalizing design of the Project and before beginning construction work based on such specifications and drawings. Seller shall provide to Buyer reasonable advance Notice of any changes in the Project and provide to Buyer specifications and design drawings of any such changes.

(vi) Seller shall Notify Buyer of the Construction Start Date by sending to Buyer a written Certification substantially in the form provided in Appendix IV-1 as soon as practical upon issuance of Notice to Proceed.

(vii) Within fifteen (15) days after the close of each quarter from the first quarter following the Execution Date, until the month in which the Construction Start Date has occurred, provide to Buyer a quarterly Progress Report and agree to regularly scheduled meetings between representatives of Buyer and Seller to review such quarterly reports and discuss Seller’s construction progress. The quarterly Progress Report shall indicate whether Seller is on target to meet the Guaranteed Commercial Operation Date.

(viii) Within fifteen (15) days after the close of each month following the Construction Start Date until the Commercial Operation Date, provide to Buyer a monthly Progress Report and agree to regularly scheduled meetings between representatives of Buyer and Seller to review such monthly reports and discuss Seller’s construction progress. The monthly Progress Report shall indicate whether Seller is on target to meet the Guaranteed Commercial Operation Date.

(b) Buyer shall have the right, but not the obligation, to:

(i) Notify Seller in writing of the results of the review performed pursuant to Section 3.9(a)(v) within thirty (30) days of Buyer’s receipt of all specifications for the Project, including a description of any flaws perceived by Buyer in the design.

(ii) Inspect the Project’s construction site or on-site Seller data and information pertaining to the Project during business hours upon reasonable notice.

(c) Guaranteed Commercial Operation Date.

(i) The Parties agree time is of the essence in regards to the Agreement. As such, Seller shall have demonstrated Commercial Operation per the terms of Appendix IV-2 by the date that is no later than June 30, 2024, except as such date may be extended on a day for day basis for not more than a cumulative six (6) month period for a Permitted Extension (the “Guaranteed Commercial Operation Date”).

(ii) Permitted Extensions. The Permitted Extensions to the Guaranteed Commercial Operation Date are as follows:

(A) Force Majeure Extension. The Guaranteed Commercial Operation Date may be extended on a day for day basis in the event of Force Majeure (“Force Majeure Extension”); provided that Seller works diligently to resolve the effect of the Force Majeure and provides evidence of its efforts promptly to Buyer upon Buyer’s written request.

(B) Daily Delay Damage Extension. The Guaranteed Commercial Operation Date may be extended on a day-to-day basis, corresponding to the number of days for which Seller has paid Daily Delay Damages, for a cumulative period of not more than six (6) months (“Daily Delay Damages Extension”).

(iii) Notwithstanding the foregoing, if Seller claims more than one Permitted Extension under Section 3.9(c)(ii), such extensions cannot cumulatively exceed six (6) months and all Permitted Extensions taken shall be concurrent, rather than cumulative, during any overlapping days.

(iv) Notice of Permitted Extension.

(A) In the case of a Force Majeure Extension, if sixty (60) days prior Notice is impracticable or impossible, Seller shall provide Notice as soon as possible after the occurrence of the Force Majeure event.

(B) In the case of a Daily Delay Damages Extension, Seller must, at the earliest possible time, but no later than sixty (60) Business Days before the commencement of the proposed Daily Delay Damages Extension, provide Buyer with Notice of its election to extend the Guaranteed Commercial Operation Date along with Seller’s estimate of the duration of the extension and its payment of Daily Delay Damages for the full estimated Daily Delay Damages Extension.

(v) Daily Delay Damage Payment. Daily Delay Damages payments applicable to days included in any Daily Delay Damages Extension are nonrefundable and are in addition to, and not a part of, the Project Development Security or Term Security, as applicable; provided that Seller will be entitled to a refund (without interest) of any estimated Daily Delay Damages payments paid by Seller to Buyer which exceed the amount required to cover the number of days by which the Guaranteed Commercial Operation Date was actually extended. Each Party agrees and acknowledges that the damages that Buyer would incur due to Seller’s delay in achieving the Guaranteed Commercial Operation Date would be difficult or impossible to predict with certainty and the Daily Delay Damages are an appropriate approximation of such damages.

(vi) Failure to Meet the Guaranteed Commercial Operation Date. Seller shall cause the Project to achieve the Commercial Operation Date by the Guaranteed Commercial Operation Date. If the Commercial Operation Date occurs after the Guaranteed Commercial Operation Date after giving effect to Permitted Extensions, then Buyer shall be entitled to declare an Event of Default and collect the Damage Payment pursuant to Article Five.

***[The following subsections (d) and (e) shall only apply to a New Project:]***

***[***(d) Resize of Project Due to Permit Failure.

(i) If Seller has not received or obtained by the earlier of the Expected Construction Start Date and the date that is six (6) months after the Effective Date final and non-appealable Governmental Approvals required for the construction of the Project with the Contract Capacity set forth in the Cover Sheet, after using commercially reasonable efforts to do so (including timely filings with all applicable Governmental Authorities and timely payment of any required fees) (“Permit Failure”), Seller may make a Contract Capacity Commitment on the Expected Construction Start Date (as may be extended), equal to, at a minimum, seventy percent (70%) of the Contract Capacity set forth in the Cover Sheet, provided that such amount shall also be the maximum amount of the generation capacity permitted under the final and non-appealable Governmental Approvals that Seller has received as of the Expected Construction Start Date (as may be extended), and may not be under one (1) MW, and provided further that for a period of two (2) years from any such resizing pursuant to this Section 3.9(d), Seller must offer Buyer a Right of First Offer for any Products from the Project up to the Contract Capacity set forth in the Cover Sheet as further provided in Section 3.9(e), below. Seller shall provide Notice of such Contract Capacity Commitment to Buyer no later than ten (10) Business Days following the Expected Construction Start Date.

(ii) In the event that the Contract Capacity is reduced pursuant to Section 3.9(d)(i) above, the Contract Quantity during each Contract Year set forth in the Delivery Term Contract Quantity Schedule in the Cover Sheet shall be adjusted proportionately with such reduction.

(iii) In the event that the Contract Capacity and Contract Quantity are reduced pursuant to Sections 3.9(d)(i) and (ii), the revised Contract Capacity and Contract Quantity shall be used to determine Seller’s performance under the Agreement, including the amount of Guaranteed Energy Production under Section 3.1(e) and the amount of Delivery Term Security or Term Security required under Section 8.4.

(iv) If the final Contract Capacity is less than the initial Contract Capacity due to a resize of the Project pursuant to Section 3.9(d)(i), then Seller shall forfeit a proportional share of the Project Development Security or Term Security, as applicable, on a percent-for-percent basis.

(e) Right of First Offer.

(i) If Seller resizes the Project due to Permit Failure, then for a period of three (3) years from the date on which Seller Notifies Buyer of the Contract Capacity Commitment (“Exclusivity Period”), neither Seller, its successors and assigns, nor its Affiliates shall enter into an obligation or agreement to sell or otherwise transfer any Products from the Project in excess of the Contract Capacity Commitment, up to the Contract Capacity set forth in the Cover Sheet, to any third party, unless Seller first offers, in writing, to sell to Buyer such Products from the Project on the same terms and conditions as this Agreement, subject to permitted modifications identified in subpart (ii) below, (the “First Offer”) and Buyer either accepts or rejects such First Offer in accordance with the provisions herein.

(ii) If Buyer accepts the First Offer, Buyer shall Notify Seller within thirty (30) days of receipt of the First Offer subject to Buyer’s management approval and CPUC Approval (“Buyer’s Notice of First Offer Acceptance”), and then the Parties shall have not more than ninety (90) days from the date of Buyer’s Notice to enter into a new power purchase agreement, in substantially the same form as this Agreement, or amend this Agreement, subject to CPUC Approval, if necessary; provided that the Contract Price may only be increased to reflect Seller’s documented incremental costs in overcoming the Permit Failure.

(iii) If Buyer rejects or fails to accept Seller’s First Offer within thirty (30) days of receipt of such offer, Seller shall thereafter be free to sell or otherwise transfer, and to enter into agreements to sell or otherwise transfer, any Products from the Project to any third party, so long as the material terms and conditions of such sale or transfer are not more favorable to the third party than those of the First Offer to Buyer. If, during the Exclusivity Period, Seller desires to enter into an obligation or agreement with a third party, Seller shall deliver to Buyer a certificate of an authorized officer of Seller (A) summarizing the material terms and conditions of such agreement and (B) certifying that the proposed agreement with the third party will not provide Seller with a lower rate of return than that offered in the First Offer to Buyer. If Seller is unable to deliver such a certificate to Buyer, then Seller may not sell or otherwise transfer, or enter into an agreement to sell or otherwise transfer, the Products from the Project without first offering to sell or otherwise transfer such Products to Buyer on such more favorable terms and conditions (the “Revised Offer”) in accordance with subpart (ii) above. If within thirty (30) days of receipt of Seller’s Revised Offer the Buyer rejects, or fails to accept by Notice to Seller, the Revised Offer, then Seller will thereafter be free to sell or otherwise transfer, and to enter into agreements to sell or otherwise transfer, such Products from the Project to any third party on such terms and conditions as set forth in the certificate.***]***

(f) Excess Network Upgrade Cost Termination Right.

(i) Buyer has the right to terminate this Agreement by Notice on or before the date that is sixty (60) days after Seller provides to Buyer the results of any Interconnection Study, or the GIA tendered to Seller by the Participating Transmission Owner, if such Interconnection Study or GIA as of the date of the termination Notice, estimates, includes, specifies or reflects that the maximum total cost of the Network Upgrades to Buyer, or any Participating Transmission Owner under the jurisdiction of the CAISO, including costs reimbursed to Seller by Buyer or any Participating Transmission Owner under the jurisdiction of the CAISO (“Aggregate Network Upgrade Costs”), may in the aggregate exceed one hundred and ten percent (110%) of the amount identified in the Interconnection Studies that were submitted with Seller’s original bid offer (package) so long as the exceeded dollar amount is equal to or greater than one hundred thousand dollars ($100,000.00) (“Network Upgrades Cap”), and Seller has not agreed to assume financial responsibility for Excess Network Upgrade Costs. This termination right is irrespective of any subsequent amendments of such Interconnection Study or GIA or any contingencies or assumptions upon which such Interconnection Study or GIA is based. Buyer’s Notice to terminate will be effective five (5) Business Days after such Notice is given to Seller.

(ii) Notwithstanding anything to the contrary in this Section 3.9(f)(ii), Buyer shall have no right to terminate this Agreement under Section 3.9(f)(i), if (A) Seller concurrently with its provision of the relevant Interconnection Study or GIA, as applicable, pursuant to Section 3.1(h)(ii)(B), irrevocably agrees to pay to the Participating Transmission Owner the amount by which the Aggregate Network Upgrade Costs exceed the Network Upgrades Cap (“Excess Network Upgrade Cost”) and (B) Seller enters into a GIA that states that Seller must pay all Excess Network Upgrade Costs without reimbursement from the Participating Transmission Owner. For sake of certainty, if Seller agrees to the above-described payment for the Excess Network Upgrade Costs pursuant to this Section 3.9(f)(ii), such agreement shall not independently convey to Seller any interest in or rights or title to any Network Upgrades or Congestion Revenue Rights (as defined in the CAISO Tariff) in connection with the development of the Project or the delivery of Product to Buyer pursuant to this Agreement.

(iii) Buyer shall have the right to terminate this Agreement on Notice, which will be effective five (5) Business Days after such Notice is given, (A) if Seller elects to exercise its right to pay for any Excess Network Upgrade Costs, but (B) FERC, CAISO, or any Participating Transmission Owner, as applicable, rejects Seller’s interconnection agreement, in whole or in part, or modifies Seller’s interconnection agreement in a manner that would make Seller unable to comply with Seller’s obligation pursuant to Section 3.9(f)(i). In order to be effective, Buyer’s Notice of termination must be given on or before the date that is ninety (90) days after such rejection or modification by FERC, CAISO, or any Participating Transmission Owner.

# **ARTICLE FOUR: COMPENSATION; MONTHLY PAYMENTS**

4.1 Price .

(a) Contract Price. The Contract Price for each MWh of Product as measured by Delivered Energy and Deemed Delivered Energy in each Contract Year as set forth in Section C of the Cover Sheet. For the avoidance of doubt, Seller shall not be compensated for any Surplus Delivered Energy.

(b) Test Period Payments. During the Test Period, Seller’s full compensation for Product sold to Buyer shall be the CAISO Revenues for the Delivered Energy, which revenues Buyer shall forward to Seller in accordance with the schedule described in Section 6.1.

(c) Monthly Payment of Delivered Energy and Deemed Delivered Energy = [Contract PriceSettlement Interval ×(Delivered EnergySettlement Interval +Deemed Delivered EnergySettlement Interval)] + [Excess Energy PriceSettlement Interval × (Delivered EnergySettlement Interval +Deemed Delivered EnergySettlement Interval)]

4.2 Excess Delivered and Deemed Delivered Energy .

(a) Excess Energy Price. If, at any point in any Contract Year, the amount of Delivered Energy (exclusive of Surplus Delivered Energy) plus the amount of Deemed Delivered Energy exceeds one hundred percent (100%) of the annual Contract Quantity amount, then:

(i) each MWh of additional Delivered Energy during such Contract Year shall be deemed “Excess Delivered Energy” and each MWh of additional Deemed Delivered Energy during such Contract Year shall be deemed “Excess Deemed Delivered Energy” (Excess Delivered Energy and Excess Deemed Delivered Energy, cumulatively, “Excess Energy”) and

(ii) for the remainder of such Contract Year:

(A) for every MWh of Excess Delivered Energy, the price paid to Seller shall be the lesser of (I) or (II), where (I) is fifty percent (50%) of the Contract Price for such Contract Year and (II) is the hourly Real-Time Price at the Delivery Point (the “Excess Delivered Energy Price”); and

(B) for every MWh of Excess Deemed Delivered Energy the price paid to Seller shall be the lesser of (I) or(II) where (I) is fifty percent (50%) of the Deemed Delivered Energy Price and (II) is the hourly Real-Time Price at the Delivery Point (the “Excess Deemed Delivered Energy Price”).

For the avoidance of doubt, Excess Energy shall not include any Surplus Delivered Energy; and “Delivered Energy”excludes Surplus Delivered Energy, for which Seller will receive no compensation.

(b) Monthly Payment for Excess Energy. Buyer shall pay Seller for Excess Energy (“Monthly Payment for Excess Energy”) in the amount that results from adding (i) the product of the Excess Delivered Energy Price in each applicable Settlement Interval multiplied by the Excess Delivered Energy in each Settlement Interval, plus (ii) the product of the Excess Deemed Delivered Energy Price in each applicable Settlement Interval multiplied by the Excess Deemed Delivered Energy in each Settlement Interval:

Monthly Payment for Excess Energy = [(Excess Delivered Energy PriceSettlement Interval × Excess Delivered Energy MWhSettlement Interval)] + [(Excess Deemed Delivered Energy PriceSettlement Interval × Excess Deemed Delivered Energy MWhSettlement Interval)]

n

å

Settlement Interval=1

4.3 CAISO Charges .

(a) Seller shall assume all liability and reimburse Buyer for any and all CAISO Penalties incurred by Buyer because of Seller’s failure to perform any covenant or obligation set forth in this Agreement. Buyer shall assume all liability and reimburse Seller for any and all CAISO Penalties incurred by Seller as a result of Buyer’s actions, including those resulting in a Buyer Curtailment Period.

(b) Buyer, as Scheduling Coordinator, shall (i) be responsible for all costs and charges assessed by the CAISO with respect to scheduling and Imbalance Energy, subject to Sections 4.5(a) and (c) and (ii) retain all CAISO revenues as a result of Energy from the Project throughout the Delivery Term. Seller and Buyer shall cooperate to minimize such charges and Uninstructed Imbalance Energy to the extent possible. Seller shall use commercially reasonable efforts to monitor imbalances and shall promptly notify Buyer as soon as possible after it becomes aware of any material imbalance that is occurring or has occurred. Such notification shall not alter Seller’s and Buyer’s respective responsibilities for payment for Imbalance Energy and costs and CAISO Penalties under this Agreement. Throughout the Delivery Term, Buyer shall be entitled to all Integrated Forward Market Load Uplift Obligation credits (as defined or required for MRTU under the CAISO Tariff) associated with the Energy generated from the Project.

(c) Forecasting Penalties.

(i) Subject to Force Majeure, in the event Seller does not in a given hour either (A) provide the access and information required in Section 3.1(l)(i); (B) comply with the installation, maintenance and repair requirements of Section 3.1(l)(iv); or (C) provide the forecast of Available Capacity required in Section 3.7(a), and the sum of Energy Deviations for each of the Settlement Intervals in the given hour exceeded the Performance Tolerance Band defined below, then Seller will be responsible for Forecasting Penalties as set forth below.

(ii) The Performance Tolerance Band is three percent (3%) multiplied by Contract Capacity multiplied by one (1) hour.

(iii) Forecasting Penalties. The Forecasting Penalty shall be equal to the greater of (A) one hundred fifty percent (150%) of the Contract Price or (B) the absolute value of the Real-Time Price, in each case for each MWh of Energy Deviation outside the Performance Tolerance Band, or any portion thereof, in every hour for which Seller fails to meet the requirements in Section 4.5(c)(i). Settlement of Forecasting Penalties shall occur as set forth in Section 6.1 of this Agreement.

4.4 Additional Compensation .

(a) To the extent not otherwise provided for in this Agreement, in the event that Seller is compensated by a third party for any Products produced by the Project, including compensation forResource Adequacy orGreen Attributes, Seller shall remit all such compensation directly to Buyer; provided that for avoidance of doubt, nothing herein precludes Seller from retaining credits related to Electric System Upgrades contemplated in Section 3.1(h)(i).

(b) To the extent that during the Delivery Term Seller (at a nominal or no cost to Seller) is exempt from, reimbursed for or receives any refunds, credits or benefits from CAISO for congestion charges or Congestion Revenue Rights (as defined in the CAISO Tariff), whether due to any adjustments in Congestion Revenue Rights or any Locational Marginal Price (as defined in the CAISO Tariff), market adjustments, invoice adjustments, or any other hedging instruments associated with the Product (collectively, any such refunds, credits or benefits are referred to as “Reductions”), then, at Buyer’s option, either (i) Seller shall transfer any such Reductions and their related rights to Buyer less any costs incurred by Seller in connection with such Reductions; or (ii) Buyer shall reduce payments due to Seller under this Agreement in amounts equal to the Reductions less any costs incurred by Seller in connection with such Reduction and Seller shall retain the Reductions.

# **ARTICLE FIVE: EVENTS OF DEFAULT; PERFORMANCE REQUIREMENT; REMEDIES**

5.1 Events of Default . An “Event of Default” shall mean,

(a) with respect to a Party that is subject to the Event of Default, the occurrence of any of the following:

(i) the failure to make, when due, any payment required pursuant to this Agreement if such failure is not remedied within five (5) Business Days after written Notice is received by the Party failing to make such payment;

(ii) any representation or warranty made by such Party herein (A) is false or misleading in any material respect when made or (B) with respect to Section 10.2(b), becomes false or misleading in any material respect during the Delivery Term; provided that, if a change in Law occurs after the Execution Date that causes the representation and warranty made by Seller in Section 10.2(b) to be materially false or misleading, such breach of the representation or warranty in Section 10.2(b) shall not be an Event of Default if Seller has used commercially reasonable efforts to comply with such change in Law during the Delivery Term in order to make the representation and warranty no longer false or misleading;

(iii) the failure to perform any material covenant or obligation set forth in this Agreement (except to the extent constituting a separate Event of Default), if such failure is not remedied within forty-five (45) days after Notice from the Non-Defaulting Party, which time period shall be extended if the Defaulting Party is making diligent efforts to cure such failure to perform, provided that such extended period shall not exceed forty-five (45) additional days;

(iv) such Party becomes Bankrupt; or

(v) such Party consolidates or amalgamates with, or merges with or into, or transfers all or substantially all of its assets to, another entity and, at the time of such consolidation, amalgamation, merger or transfer, the resulting, surviving or transferee entity fails to assume all the obligations of such Party under this Agreement to which it or its predecessor was a party by operation of Law or pursuant to an agreement reasonably satisfactory to the other Party;

(b) with respect to Seller as the Defaulting Party, the occurrence of any of the following:

(i) if at any time during the Term of this Agreement, Seller delivers or attempts to deliver to the Delivery Point for sale under this Agreement Energy that was not generated by the Project;

(ii) failure by Seller for any reason, other than as explicitly provided in Section 11.1(a)(i) to meet, the Guaranteed Commercial Operation Date as may be extended by Permitted Extensions;

(iii) failure by Seller to satisfy the creditworthiness/collateral requirements agreed to pursuant to Sections 8.3, 8.4, or 8.5 of this Agreement and such failure is not cured within any applicable cure period;

(iv) failure by Seller to achieve the Guaranteed Energy Production requirement as set forth in Section 3.1(e)(ii) of this Agreement as follows:

(A) after the one (1) year GEP Cure period Seller has failed to cure the GEP Failure and has failed to pay GEP Damages in the time period set forth in Section 3.1(e)(ii); or

(B) if, after any Performance Measurement Period the cumulative GEP Shortfall for all preceding Performance Measurement Periods occurring during the Delivery Term equals or exceeds two times the Contract Quantity (as may be adjusted pursuant to Sections 3.9(d) and 3.1(e)(ii)); provided, however, that if all or a portion of the GEP Shortfall during an applicable Performance Measurement Period is principally caused by a non-Force Majeure major equipment malfunction, breakdown, or failure resulting in a reduction of Energy production of the Project by at least fifty percent (50%) of the Contract Quantity in one or both years of the Performance Measurement Period, as applicable, and such malfunction, breakdown, or failure was not caused by Seller and could not have been avoided through the exercise of Good Utility Practice, such failure shall be excluded from the calculation of the cumulative GEP Shortfall for purposes of this subsection.

(v) Seller has not obtained the deliverability type selected in Section A (FCDS or PCDS) of the Cover Sheet by the Deliverability Finding Deadline.

(vi) Seller has not obtained the Partial Capacity Deliverability Status Amount identified in Section A of the Cover Sheet by the Deliverability Finding Deadline.

(vii) if the Total Nameplate Rated Power is greater than ***[Seller to specify the applicable restriction: 20 MW for Unreserved Projects and 1 MW for Environmental Justice Projects]***.

5.2 Remedies  . If an Event of Default with respect to a Defaulting Party shall have occurred and is continuing, the other Party (“Non-Defaulting Party”) shall have the following rights:

(a) send Notice, designating a day, no earlier than the day such Notice is deemed to be received and no later than twenty (20) days after such Notice is deemed to be received, as an early termination date of this Agreement (“Early Termination Date”) on which to collect the Damage Payment or Termination Payment in accordance with 5.2(c);

(b) accelerate all amounts owing between the Parties, terminate the Transaction and end the Delivery Term effective as of the Early Termination Date;

(c) (i) collect the Damage Payment (in the case of any Event of Default of Seller that arose at any time prior to the commencement of the Delivery Term), or (ii) collect the Termination Payment (in the case of any Event of Default of Seller that arose during the Delivery Term or in the case of any Event of Default of Buyer at any time);

(d) withhold any payments due to the Defaulting Party under this Agreement;

(e) suspend performance;

(f) exercise its rights pursuant to Section 8.3 to draw upon and retain Performance Assurance;

(g) demand payment for damages due to Buyer’s unexcused failure to take delivery or pay for Product; and

(h) exercise any other rights or remedies available at Law or in equity (including the collection of monetary damages) to the extent otherwise permitted under this Agreement.

Notwithstanding anything to the contrary contained herein, Seller may exercise the rights or remedies set forth in Sections 5.2(e), (g), and (h) without terminating this Agreement.

5.3 Calculation of Termination Payment .

(a) In the case where the Non-Defaulting Party is entitled to collect the Termination Payment pursuant to Section 5.2, the Non-Defaulting Party shall calculate, in a commercially reasonable manner, a Settlement Amount for the Terminated Transaction as of the Early Termination Date. Third parties supplying information for purposes of the calculation of Gains or Losses may include dealers in the relevant markets, end-users of the relevant product, information vendors and other sources of market information. If the Non-Defaulting Party uses the market price for a comparable transaction to determine the Gains or Losses, such price should be determined by using the average of market quotations provided by three (3) or more bona fide unaffiliated market participants. If the number of available quotes is three, then the average of the three quotes shall be deemed to be the market price. Where a quote is in the form of bid and ask prices, the price that is to be used in the averaging is the midpoint between the bid and ask price. The quotes shall be obtained in a commercially reasonable manner and shall be: (i) for a like amount, (ii) of the same Product, (iii) at the same Delivery Point, and (iv) for the remaining Delivery Term. Regardless of the method chosen by the Non-Defaulting Party to calculate the Settlement Amount, the Settlement Amount must still be reasonable under the circumstances.

(b) If the Non-Defaulting Party’s aggregate Gains exceed its aggregate Losses and Costs, if any, resulting from the termination of the Terminated Transaction, the Settlement Amount shall be zero.

(c) The Non-Defaulting Party shall not have to enter into replacement transactions to establish a Settlement Amount.

5.4 Notice of Payment of Termination Payment . As soon as practicable after a liquidation, Notice shall be given by the Non-Defaulting Party to the Defaulting Party of the amount of the Termination Payment and whether the Termination Payment is due to the Non-Defaulting Party. The Notice shall include a written statement explaining in reasonable detail the calculation of such amount and the sources for such calculation. The Termination Payment shall be made to the Non-Defaulting Party, as applicable, within ten (10) Business Days after such Notice is effective.

5.5 Disputes With Respect to Termination Payment . If the Defaulting Party disputes the Non-Defaulting Party’s calculation of the Termination Payment, in whole or in part, the Defaulting Party shall, within ten (10) Business Days of receipt of the Non-Defaulting Party’s calculation of the Termination Payment, provide to the Non-Defaulting Party a detailed written explanation of the basis for such dispute. Disputes regarding the Termination Payment shall be determined in accordance with Article Twelve.

5.6 Rights And Remedies Are Cumulative . The rights and remedies of a Party pursuant to this Article Five shall be cumulative and in addition to the rights of the Parties otherwise provided in this Agreement.

5.7 Duty to Mitigate . Buyer and Seller shall each have a duty to mitigate damages pursuant to this Agreement, and each shall use reasonable efforts to minimize any damages it may incur as a result of the other Party’s non-performance of this Agreement, including with respect to termination of this Agreement.

5.8 Damage Payment for Failure to Achieve Guaranteed Dates . The Parties agree that the Damage Payment to be paid by Seller for an Event of Default arising under Section 5.1(b)(ii) associated with Seller’s failure to achieve the Guaranteed Commercial Operation Date shall be considered liquidated damages and not a penalty, in accordance with Section 7.1.

# **ARTICLE SIX: PAYMENT**

6.1 Billing and Payment; Remedies . On or about the tenth (10th) day of each month beginning with the second month of either the Test Period or the first Contract Year, whichever occurs first, and every month thereafter, and continuing through and including the first month following the end of the Delivery Term, Seller shall provide to Buyer (a) records of metered data, including CAISO metering and transaction data sufficient to document and verify the generation of Product by the Project for any CAISO settlement time interval during the preceding months, (b) access to any records, including invoices or settlement data from the CAISO, necessary to verify the accuracy or amount of any Reductions; and (c) an invoice, in the format specified by Buyer, covering the services provided in the preceding month determined in accordance with the applicable provisions of Article Four. Seller shall continue to provide to Buyer an invoice of CAISO charges, net any sums Buyer owes Seller under this Agreement, on or about the tenth (10th) day of each month until the date of the Final True-Up. Buyer shall pay the undisputed amount of such invoices less the amount of any RA Deficiency Amount and the amount of any Forecasting Penalties, as applicable on or before the later of the twenty-fifth (25th) day of each month and fifteen (15) days after receipt of the invoice. If either the invoice date or payment date is not a Business Day, then such invoice or payment shall be provided on the next following Business Day. During the Test Period, and for twelve (12) months following the Test Period only, Buyer shall provide to Seller a statement of the CAISO Revenues and any true-ups of CAISO Revenues from prior months and Buyer shall forward to Seller the CAISO Revenues from such statement, according to the invoice and payment schedules described in this Section 6.1. Each Party will make payments by electronic funds transfer via ACH, to the account designated by the other Party. Any undisputed amounts not paid by the due date will be deemed delinquent and will accrue interest at the Interest Rate, such interest to be calculated from and including the due date to but excluding the date the delinquent amount is paid in full. Invoices may be sent by facsimile or e-mail.

6.2 Disputes and Adjustments of Invoices . In the event an invoice or portion thereof or any other claim or adjustment arising hereunder, is disputed, payment of the undisputed portion of the invoice shall be required to be made when due, with Notice of the objection given to the other Party. Any invoice dispute or invoice adjustment shall be in writing and shall state the basis for the dispute or adjustment. Payment of the disputed amount shall not be required until the dispute is resolved. Subject to Section 3.6, in the event adjustments to payments are required, Buyer shall use corrected measurements to recompute the amount due from Buyer to Seller for the Product delivered under the Transaction during the period of adjustment. The Parties agree to use good faith efforts to resolve the dispute or identify the adjustment as soon as possible. Upon resolution of the dispute or calculation of the adjustment, any required payment shall be made on the next invoice after such resolution along with interest accrued at the Interest Rate from and including the due date, but excluding the date paid. Inadvertent overpayments shall be returned upon request or deducted by the Party receiving such overpayment from subsequent payments, with interest accrued at the Interest Rate from and including the date of such overpayment, but excluding the date repaid or deducted by the Party receiving such overpayment. Any dispute with respect to an invoice is waived unless the other Party is notified in accordance with this Section 6.2 within twelve (12) months after the invoice is rendered or any specific adjustment to the invoice is made; provided that, such waiver shall not apply to any adjustment or dispute related to Seller’s performance under any applicable RMR Contract; and provided further that, any disputes with respect to a statement of CAISO Revenues is waived unless Seller notifies Buyer in accordance with this Section 6.2 within one (1) month after the last statement of CAISO Revenues is provided. If an invoice is not rendered within twelve (12) months after the close of the month during which performance under the Transaction occurred, the right to payment for such performance is waived.

# **ARTICLE SEVEN: LIMITATIONS**

7.1 Limitation of Remedies, Liability and Damages . EXCEPT AS MAY OTHERWISE BE EXPRESSLY PROVIDED IN THIS AGREEMENT, THERE IS NO WARRANTY OF MERCHANTABILITY OR FITNESS FOR A PARTICULAR PURPOSE, AND ANY AND ALL IMPLIED WARRANTIES ARE DISCLAIMED. LIABILITY SHALL BE LIMITED TO DIRECT ACTUAL DAMAGES ONLY, SUCH DIRECT ACTUAL DAMAGES SHALL BE THE SOLE AND EXCLUSIVE REMEDY AND ALL OTHER REMEDIES OR DAMAGES AT LAW OR IN EQUITY ARE WAIVED UNLESS EXPRESSLY HEREIN PROVIDED. NEITHER PARTY SHALL BE LIABLE FOR CONSEQUENTIAL, INCIDENTAL, PUNITIVE, EXEMPLARY OR INDIRECT DAMAGES, LOST PROFITS OR OTHER BUSINESS INTERRUPTION DAMAGES, BY STATUTE, IN TORT OR CONTRACT, UNDER ANY INDEMNITY PROVISION OR OTHERWISE. UNLESS EXPRESSLY HEREIN PROVIDED, AND SUBJECT TO THE PROVISIONS OF SECTION 10.5 (“INDEMNITIES”), IT IS THE INTENT OF THE PARTIES THAT THE LIMITATIONS HEREIN IMPOSED ON REMEDIES AND THE MEASURE OF DAMAGES BE WITHOUT REGARD TO THE CAUSE OR CAUSES RELATED THERETO, INCLUDING THE NEGLIGENCE OF ANY PARTY, WHETHER SUCH NEGLIGENCE BE SOLE, JOINT OR CONCURRENT, OR ACTIVE OR PASSIVE.

THE PARTIES CONFIRM THAT THE EXPRESS REMEDIES AND MEASURES OF DAMAGES PROVIDED IN THIS AGREEMENT SATISFY THE ESSENTIAL PURPOSES HEREOF.

TO THE EXTENT ANY DAMAGES REQUIRED TO BE PAID HEREUNDER ARE LIQUIDATED, THE PARTIES ACKNOWLEDGE THAT THE DAMAGES ARE DIFFICULT OR IMPOSSIBLE TO DETERMINE, OR OTHERWISE OBTAINING AN ADEQUATE REMEDY IS INCONVENIENT AND THE DAMAGES CALCULATED HEREUNDER CONSTITUTE A REASONABLE APPROXIMATION OF THE HARM OR LOSS.

# **ARTICLE EIGHT: CREDIT AND COLLATERAL REQUIREMENTS**

8.1 Buyer Financial Information . If requested by Seller, Buyer shall deliver to Seller (a) within one hundred twenty (120) days after the end of each fiscal year with respect to Buyer, a copy of Buyers’s annual report containing audited consolidated financial statements for such fiscal year and (b) within sixty (60) days after the end of each of Buyer’s first three fiscal quarters of each fiscal year, a copy of Buyers’s quarterly report containing unaudited consolidated financial statements for each accounting period prepared in accordance with Generally Accepted Accounting Principles. Buyer shall be deemed to have satisfied such delivery requirement if the applicable report is publicly available on Buyer’s website or on the SEC EDGAR information retrieval system; provided however, that should such statements not be available on a timely basis due to a delay in preparation or certification, such delay shall not be an Event of Default, so long as such statements are provided to Seller upon their completion and filing with the SEC.

8.2 Seller Financial Information . If requested by Buyer, Seller shall deliver to Buyer (a) within one hundred twenty (120) days following the end of each fiscal year, a copy of Seller’s or Seller’s guarantor’s, if applicable, annual report containing unaudited consolidated financial statements for such fiscal year (or audited consolidated financial statements for such fiscal year if otherwise available) and (b) within sixty (60) days after the end of each of its first three fiscal quarters of each fiscal year, a copy of such Party’s quarterly report containing unaudited consolidated financial statements for such fiscal quarter. In all cases the statements shall be for the most recent accounting period and shall be prepared in accordance with Generally Accepted Accounting Principles; provided, however, that should any such statements not be available on a timely basis due to a delay in preparation or certification, such delay shall not be an Event of Default so long as such Party diligently pursues the preparation, certification and delivery of the statements.

8.3 Grant of Security Interest/Remedies . To secure its obligations under this Agreement and to the extent Seller delivers the Project Development Security, Delivery Term Security, or Term Security, as applicable, hereunder, Seller hereby grants to Buyer, as the secured party, a first priority security interest in, and lien on (and right of setoff against), and assignment of, all such Performance Assurance posted with Buyer in the form of cash collateral and cash equivalent collateral and any and all proceeds resulting therefrom or the liquidation thereof, whether now or hereafter held by, on behalf of, or for the benefit of, Buyer. Within thirty (30) days of the delivery of the Project Development Security, Delivery Term Security, or Term Security, as applicable, Seller agrees to take such action as Buyer reasonably requires in order to perfect a first-priority security interest in, and lien on (and right of setoff against), such Performance Assurance and any and all proceeds resulting therefrom or from the liquidation thereof. Upon or any time after the occurrence or deemed occurrence and during the continuation of an Event of Default or an Early Termination Date, Buyer, as the Non-Defaulting Party, may do any one or more of the following: (a) exercise any of the rights and remedies of a secured party with respect to all Project Development Security, Delivery Term Security, or Term Security, as applicable, including any such rights and remedies under the Law then in effect; (b) exercise its rights of setoff against any and all property of Seller, as the Defaulting Party, in the possession of the Buyer or Buyer’s agent; (c) draw on any outstanding Letter of Credit issued for its benefit; and (d) liquidate all Project Development Security, Delivery Term Security, or Term Security, as applicable, then held by or for the benefit of Buyer free from any claim or right of any nature whatsoever of Seller, including any equity or right of purchase or redemption by Seller. Buyer shall apply the proceeds of the collateral realized upon the exercise of any such rights or remedies to reduce Seller’s obligations under the Agreement (Seller remaining liable for any amounts owing to Buyer after such application), subject to the Buyer’s obligation to return any surplus proceeds remaining after such obligations are satisfied in full.

8.4 Performance Assurance .

(a) Security. Seller agrees to deliver to Buyer collateral to secure its obligations under this Agreement, which Seller shall maintain in full force and effect for the period posted with Buyer, as follows:

(i) Project Development Security: Project Development Security pursuant to this Section 8.4(a)(i) in the amount of $60/kW multiplied by the Contract Capacity of the Project as reflected in the Cover Sheet, within thirty (30) days following the Effective Date of this Agreement until Seller posts Delivery Term Security pursuant to Section 8.4(a)(ii) below with Buyer.

(ii) Delivery Term Security: Delivery Term Security pursuant to this Section 8.4(a)(ii) in the amount of five percent (5%) of expected total Project revenues from the date required pursuant to Section 3.1(c)(i) as a condition precedent to the Initial Energy Delivery Date, until the end of the Term; provided that, with Buyer’s consent, Seller may elect to apply the Project Development Security posted pursuant to Section 8.4(a)(i) toward the Delivery Term Security posted pursuant to this Section 8.4(a)(ii) and deliver or cause to be delivered to Buyer the difference between the posted Project Development Security and the required Delivery Term Security.

***[For purposes of Section 8.4(a), GTSR Projects 3 MWs or less only need to comply with the following bracketed language.]***

***[***(iii) Term Security: Term Security pursuant to this Section 8.4(a)(iii) in the amount of $20/kW for GTSR Projects with Contract Capacity of three (3) MW and under multiplied by the capacity of the Project as reflected in Section B of the Cover Sheet, within thirty (30) days following the Effective Date of this Agreement until the end of the Term.***]***

The amount of Performance Assurance required under this Agreement shall not be deemed a limitation of damages. Except as specifically provided for in this Section 8.4(a), Buyer acknowledges that Seller shall not be required to post any additional security.

(b) Use of Project Development Security or Term Security. Buyer shall be entitled to draw upon the Project Development Security or Term Security for any damages arising upon Buyer’s declaration of an Early Termination Date.

(c) Termination of Project Development Security. If after the Initial Energy Delivery Date no damages are due and owing to Buyer under this Agreement, then Seller shall no longer be required to maintain theProject Development Security, and Buyer shall return to Seller the Project Development Security, less the amounts drawn in accordance with Section 8.4(b). The Project Development Security(or portion thereof) due to Seller shall be returned to Seller within five (5) Business Days of Seller’s provision of the Delivery Term Security, as applicable unless, with Buyer’s consent, Seller elects to apply the Project Development Security posted pursuant to Section 8.4(a)(i) toward the Delivery Term Security posted pursuant to Section 8.4(a)(ii), as applicable. ***[Section 8.4(c) does not apply to GTSR Projects 3 MW or less.]***

(d) Payment and Transfer of Interest. Buyer shall pay interest on cash held as Project Development Security, Delivery Term Security or Term Security, as applicable, at the Interest Rate; provided that, the interest on Project Development Security shall be retained by Buyer until Seller posts the Delivery Term Security pursuant to Section 8.4(a)(ii). Upon Seller’s posting of the Delivery Term Security, all accrued interest on the unused portion of Project Development Security shall be transferred from Buyer to Seller in the form of cash by wire transfer to the bank account specified under “Wire Transfer” in the Cover Sheet (Notices List). After Seller posts the Delivery Term Security or Term Security, Buyer shall transfer (as described in the preceding sentence) on or before each Interest Payment Date the Interest Amount due to Seller for such Delivery Term Security or Term Security.

(e) Return of Performance Assurance. Buyer shall return the unused portion of Project Development Security, Delivery Term Security, or Term Security, as applicable, including the payment of any interest due thereon, pursuant to Section 8.4(d) above, to Seller promptly after the following has occurred: (i) the Term of the Agreement has ended, or subject to Section 8.3, an Early Termination Date has occurred, as applicable; (ii) all payment obligations of the Seller arising under this Agreement, including payments pursuant to Section 4.3 (“CAISO Charges”), Termination Payment, indemnification payments or other damages are paid in full (whether directly or indirectly such as through set-off or netting); and (iii) all WREGIS Certificates have been transferred to Buyer’s WREGIS Account.

(f) Adjustment of Security Amounts for Project Resizing. The required amount of Delivery Term Security or Term Security, as applicable, shall be proportionally and automatically adjusted in connection with any resizing of the Project under Section 3.9(d), and Buyer shall promptly return to Seller the unused portion of Delivery Term Security or Term Security in connection with any such adjustment.

8.5 Letter of Credit . Performance Assurance provided in the form of a Letter of Credit shall be subject to the following provisions:

(a) If Seller has provided a Letter of Credit pursuant to any of the applicable provisions in this Article Eight, then Seller shall renew or cause the renewal of each outstanding Letter of Credit on a timely basis in accordance with this Agreement.

(b) In the event the issuer of such Letter of Credit at any time (i) fails to maintain the requirements of an Eligible LC Bank or Letter of Credit, (ii) indicates its intent not to renew such Letter of Credit, or (iii) fails to honor Buyer’s properly documented request to draw on such Letter of Credit, Seller shall cure such occurrence by complying with either (A) or (B) below in an amount equal to the outstanding Letter of Credit, and by completing the action within five (5) Business Days after the date of Buyer’s Notice to Seller of an occurrence listed in this subsection (Seller’s compliance with either (A) or (B) below is considered the “Cure”):

(A) providing a substitute Letter of Credit that is issued by an Eligible LC Bank, other than the bank which is the subject of Buyer’s Notice to Seller in Section 8.5(b) above, or

(B) posting cash.

If Seller fails to Cure or if such Letter of Credit expires or terminates without a full draw thereon by Buyer, or fails or ceases to be in full force and effect at any time that such Letter of Credit is required pursuant to the terms of this Agreement, then Seller shall have failed to meet the creditworthiness or collateral requirements of Article Eight.

(c) Notwithstanding the foregoing in Section 8.5(b), if, at any time, the issuer of such Letter of Credit has a Credit Rating on “credit watch” negative or developing by S&P, or is on Moody’s “watch list” under review for downgrade or uncertain ratings action (either a “Watch”), then Buyer may make a demand to Seller by Notice (“LC Notice”) to provide a substitute Letter of Credit that is issued by an Eligible LC Bank, other than the bank on a Watch (“Substitute Letter of Credit”). The Parties shall have thirty (30) Business Days from the LC Notice to negotiate a Substitute Letter of Credit (“Substitute Bank Period”).

(i) If the Parties do not agree to a Substitute Letter of Credit by the end of the Substitute Bank Period, then Buyer shall provide Seller with Notice within five (5) Business Days following the expiration of the Substitute Bank Period (“Ineligible LC Bank Notice Period”) that either:

(A) Buyer agrees to continue accepting the then currently outstanding Letter of Credit from the bank that is the subject of the LC Notice, but such bank shall no longer be an Eligible LC Bank (“Ineligible LC Bank”) and Buyer will not accept future or renewals of Letters of Credit from the Ineligible LC Bank; or

(B) the bank that is the subject of the LC Notice is an Ineligible LC Bank and Seller shall then have thirty (30) days from the date of Buyer’s Notice to Cure pursuant to Section 8.5(b) and, if Seller fails to Cure, then the last paragraph in Section 8.5(b) shall apply to Seller.

(ii) If the Parties have not agreed to a Substitute Letter of Credit and Buyer fails to provide a Notice during the Ineligible LC Bank Notice Period above, then Seller may continue providing the Letter of Credit posted immediately prior to the LC Notice.

(d) In all cases, the reasonable costs and expenses of establishing, renewing, substituting, canceling, increasing, reducing, or otherwise administering the Letter of Credit shall be borne by Seller.

# **ARTICLE NINE: GOVERNMENTAL CHARGES**

9.1 Cooperation . Each Party shall use reasonable efforts to implement the provisions of and to administer this Agreement in accordance with the intent of the Parties to minimize all taxes, so long as neither Party is materially adversely affected by such efforts.

9.2 Governmental Charges . Seller shall pay or cause to be paid all taxes imposed by any Governmental Authority (“Governmental Charges”) on or with respect to the Product or the Transaction arising at the Delivery Point, including ad valorem taxes and other taxes attributable to the Project, land, land rights or interests in land for the Project. Buyer shall pay or cause to be paid all Governmental Charges on or with respect to the Product or the Transaction from the Delivery Point. In the event Seller is required by Law or regulation to remit or pay Governmental Charges which are Buyer’s responsibility hereunder, Buyer shall promptly reimburse Seller for such Governmental Charges. If Buyer is required by Law or regulation to remit or pay Governmental Charges which are Seller’s responsibility hereunder, Buyer may deduct such amounts from payments to Seller with respect to payments under the Agreement; if Buyer elects not to deduct such amounts from Seller’s payments, Seller shall promptly reimburse Buyer for such amounts upon request. Nothing shall obligate or cause a Party to pay or be liable to pay any Governmental Charges for which it is exempt under the Law. A Party that is exempt at any time and for any reason from one or more Governmental Charges bears the risk that such exemption shall be lost or the benefit of such exemption reduced; and thus, in the event a Party’s exemption is lost or reduced, each Party’s responsibility with respect to such Governmental Charge shall be in accordance with the first four sentences of this Section.

# **ARTICLE TEN: MISCELLANEOUS**

10.1 Recording . Unless a Party expressly objects to a recording at the beginning of a telephone conversation, each Party consents to the creation of a tape or electronic recording of all telephone conversations between Buyer’s employees or representatives performing a Scheduling Coordinator function as provided in Section 3.4(c) and any representative of Seller. The Parties agree that any such recordings will be retained in confidence, secured from improper access, and may be submitted in evidence in any proceeding or action relating to this Agreement. Each Party waives any further notice of such monitoring or recording, and agrees to notify its officers and employees of such monitoring or recording and to obtain any necessary consent of such officers and employees.

10.2 Representations and Warranties .

(a) Seller General Representations and Warranties. On the Execution Date, Seller represents and warrants to Buyer that:

(i) it is duly organized, validly existing and in good standing under the Laws of the jurisdiction of its formation;

(ii) it has all regulatory authorizations necessary for it to perform its obligations under this Agreement, except for all permits necessary to install, operate and maintain the Project;

(iii) it is a “forward contract merchant” within the meaning of the United States Bankruptcy Code (as in effect as of the Execution Date of this Agreement);

(iv) the execution, delivery and performance of this Agreement are within its powers, have been duly authorized by all necessary action and do not violate any of the terms and conditions in its governing documents, any contracts to which it is a party or any Laws applicable to it;

(v) this Agreement and each other document executed and delivered in accordance with this Agreement constitutes a legally valid and binding obligation enforceable against it in accordance with its terms, subject to any Equitable Defenses;

(vi) it is not Bankrupt and there are no proceedings pending or being contemplated by it or, to its knowledge, threatened against it which would result in it being or becoming Bankrupt;

(vii) there is not pending or, to its knowledge, threatened against it or any of its Affiliates, any legal proceedings that could materially adversely affect its ability to perform its obligations under this Agreement;

(viii) no Event of Default with respect to it has occurred and is continuing and no such event or circumstance would occur as a result of its entering into or performing its obligations under this Agreement;

(ix) it is acting for its own account, has made its own independent decision to enter into this Agreement and as to whether this Agreement is appropriate or proper for it based upon its own judgment, is not relying upon the advice or recommendations of Buyer in so doing, and is capable of assessing the merits of and understanding, and understands and accepts, the terms, conditions and risks of this Agreement; ***[***and***]***

(x) it has entered into this Agreement in connection with the conduct of its business and it has the capacity or the ability to make delivery of the Product as provided in this Agreement***[***.***][****; and*

(xi) it has considered long-term climate risk with respect to the Project, consistent with CPUC Decision 20-08-046 (including, without limitation, the risks described in Ordering Paragraph (9)(11)(a)-(e).***] [Section 10.2(a)(xi) shall ONLY apply for Agreements with a Delivery Term of fifteen or more Contract Years.]***

(b) Seller Representations and Warranties. Seller, and, if applicable, its successors, represents and warrants that throughout the Delivery Term of this Agreement that: (i) the Project qualifies and is certified by the CEC as an Eligible Renewable Energy Resource (“ERR”) as such term is defined in Public Utilities Code Section 399.12 or Section 399.16; and (ii) the Project’s output delivered to Buyer qualifies under the requirements of the California Renewables Portfolio Standard. To the extent a change in law occurs after execution of this Agreement that causes this representation and warranty to be materially false or misleading, it shall not be an Event of Default if Seller has used commercially reasonable efforts to comply with such change in law.

Seller and, if applicable, its successors, represents and warrants that throughout the Delivery Term of this Agreement the Renewable Energy Credits transferred to Buyer conform to the definition and attributes required for compliance with the California Renewables Portfolio Standard, as set forth in California Public Utilities Commission Decision 08-08-028, and as may be modified by subsequent decision of the California Public Utilities Commission or by subsequent legislation. To the extent a change in law occurs after execution of this Agreement that causes this representation and warranty to be materially false or misleading, it shall not be an Event of Default if Seller has used commercially reasonable efforts to comply with such change in law.

***[The following bracketed language shall only be applicable to Projects that utilize Shared Facilities.]*** ***[***The term “change in law” as used in Section 10.2(b) does not include an invalidation, rescission or modification of the CAISO Exemption nor any disapproval, disallowance, or other change by WREGIS, the CEC or the CPUC with regards to the RECs as a result Seller’s Shared Facilities***]***

(c) Buyer General Representations and Warranties. On the Execution Date, Buyer represents and warrants to Seller that:

(i) it is duly organized, validly existing and in good standing under the Laws of the jurisdiction of its formation and is qualified to transact business in the State of California;

(ii) it has all regulatory authorizations necessary for it to perform its obligations under this Agreement, except for CPUC Approval;

(iii) it is a “forward contract merchant” within the meaning of the United States Bankruptcy Code (as in effect as of the Execution Date of this Agreement);

(iv) the execution, delivery and performance of this Agreement are within its powers, have been duly authorized by all necessary action and do not violate any of the terms and conditions in its governing documents, any contracts to which it is a party or any Laws applicable to it;

(v) this Agreement and each other document executed and delivered in accordance with this Agreement constitutes a legally valid and binding obligation enforceable against it in accordance with its terms, subject to any Equitable Defenses;

(vi) no Event of Default with respect to it has occurred and is continuing and no such event or circumstance would occur as a result of its entering into or performing its obligations under this Agreement;

(vii) it is acting for its own account, has made its own independent decision to enter into this Agreement and as to whether this Agreement is appropriate or proper for it based upon its own judgment, is not relying upon the advice or recommendations of Seller in so doing, and is capable of assessing the merits of and understanding, and understands and accepts, the terms, conditions and risks of this Agreement; and

(viii) it has entered into this Agreement in connection with the conduct of its business and it has the capacity or the ability to take delivery of the Product as provided in this Agreement.

10.3 Covenants .

(a) General Covenants. Each Party covenants throughout the Delivery Term as follows:

(i) it shall continue to be duly organized, validly existing and in good standing under the Laws of the jurisdiction of its formation;

(ii) it shall maintain (or obtain from time to time as required, including through renewal, as applicable) all regulatory authorizations necessary for it to legally perform its obligations under this Agreement and the Transaction; and

(iii) it shall perform its obligations under this Agreement and the Transaction in a manner that does not violate any of the terms and conditions in its governing documents, any contracts to which it is a party or any Law, rule, regulation, order or the like applicable to it.

(b) Seller Covenants.

(i) Seller covenants throughout the Delivery Term that it will take no action or permit any other person or entity (other than Buyer) to take any action that would impair in any way Buyer’s ability to rely on the Project in order to satisfy its Resource Adequacy Requirements; and

(ii) Seller covenants that it shall comply with all CAISO Tariff requirements and/or Participating TO tariff requirements, as applicable, that are applicable to an Interconnection Customer (as defined in the CAISO Tariff or Participating TO’s tariff, as applicable) and shall take any other necessary action, including payment of fees and submission of requests, applications or other documentation, to promote the completion of the Electric System Upgrades prior to the RA Start Date.

10.4 Title and Risk of Loss . Title to and risk of loss related to the Product shall transfer from Seller to Buyer at the Delivery Point. Seller warrants that it will deliver to Buyer the Product free and clear of all liens, security interests, Claims and encumbrances or any interest therein or thereto by any person or entity arising prior to or at the Delivery Point.

10.5 Indemnities .

(a) Indemnity by Seller. Seller shall release, indemnify and hold harmless Buyer or Buyers’ respective directors, officers, agents, and representatives against and from any and all loss, Claims, actions or suits, including costs and attorney’s fees resulting from, or arising out of or in any way connected with (i) the Product delivered under this Agreement to the Delivery Point, [or] (ii) Seller’s operation and/or maintenance of the Project, including any loss, Claim, action or suit, for or on account of injury to, bodily or otherwise, or death of persons, or for damage to or destruction of property belonging to Buyer, Seller, or others, excepting only such loss, Claim, action or suit as may be caused solely by the willful misconduct or gross negligence of Buyer, its Affiliates, or Buyers’ and Affiliates’ respective agents, employees, directors, or officers.***[***, or (iii) any penalties, sanctions or fines imposed by the CAISO or any other any Governmental Authority with respect to the Shared Facilities or as a result of the inaccuracy or recalibration of the CAISO Approved Meter(s).***]*** ***[The bracketed language shall only be applicable to projects that utilize Shared Facilities.]***

(b) Indemnity by Buyer. Buyer shall release, indemnify and hold harmless Seller, its directors, officers, agents, and representatives against and from any and all loss, Claims, actions or suits, including costs and attorney’s fees resulting from, or arising out of or in any way connected with the Product delivered by Seller under this Agreement after the Delivery Point, including any loss, Claim, action or suit, for or on account of injury to, bodily or otherwise, or death of persons, or for damage to or destruction of property belonging to Buyer, Seller, or others, excepting only such loss, Claim, action or suit as may be caused solely by the willful misconduct or gross negligence of Seller, its Affiliates, or Seller’s and Affiliates’ respective agents, employees, directors or officers.

(c) No Dedication. Without limitation of each Party’s obligations under Sections 10.5(a) and 10.5(b) herein, nothing in this Agreement shall be construed to create any duty to, any standard of care with reference to, or any liability to any person or entity not a Party to this Agreement. No undertaking by one Party to the other under any provision of this Agreement shall constitute the dedication of that Party’s system or any portion thereof to the other Party or the public, nor affect the status of Buyer as an independent public utility corporation or Seller as an independent individual or entity.

10.6 Assignment .

(a) General Assignment. Except as provided in Sections 10.6 (b) and (c), neither Party shall assign this Agreement or its rights hereunder without the prior written consent of the other Party, which consent shall not be unreasonably withheld so long as among other things (i) the assignee assumes the transferring Party’s payment and performance obligations under this Agreement, (ii) the assignee agrees in writing to be bound by the terms and conditions hereof, (iii) the transferring Party delivers evidence satisfactory to the non-transferring Party of the proposed assignee’s technical and financial capability to fulfill the assigning Party’s obligations hereunder and (iv) the transferring Party delivers such tax and enforceability assurance as the other Party may reasonably request. Notwithstanding the foregoing and except as provided in Section 10.6(b), consent shall not be required for an assignment of this Agreement where the assigning Party remains subject to liability or obligation under this Agreement, provided that (i) the assignee assumes the assigning Party’s payment and performance obligations under this Agreement, (ii) the assignee agrees in writing to be bound by the terms and conditions hereof, and (iii) the assigning Party provides the other Party hereto with at least thirty (30) days’ prior written notice of the assignment.

(b) Assignment to Financing Providers. Seller shall be permitted to assign this Agreement as collateral for any financing or refinancing of the Project with the prior written consent of the Buyer, which consent shall not be unreasonably withheld. If Buyer gives its consent, then such consent shall be in a form substantially similar to the Form of Consent to Assignment attached hereto as Appendix VII provided that (i) Buyer shall not be required to consent to any additional terms or conditions beyond those contained in Appendix VII, including extension of any cure periods or additional remedies for financing providers, and (ii) Seller shall be responsible at Buyer’s request for Buyer’s reasonable costs associated with the review, negotiation, execution and delivery of documents in connection with such assignment, attorneys’ fees.

(c) Notice of Change in Control. Except in connection with public market transactions of the equity interests or capital stock of Seller or Seller’s Affiliates’, Seller shall provide Buyer notice of any direct change of control of Seller (whether voluntary or by operation of Law).

(d) Unauthorized Assignment. Any assignment or purported assignment in violation of this Section 10.6 is void.

10.7 Confidentiality .

(a) Neither Party shall disclose the non-public terms or conditions of this Agreement (the “Confidential Information”) to a third party, other than as follows:

(i) to the Party’s Affiliates, the Party’s or its Affiliates’ respective employees, lenders, investors, counsel, accountants or advisors who have a need to know such information and have agreed to keep such terms confidential,

(ii) for disclosure to Buyer’s Procurement Review Group, as defined in CPUC Decision D. 02-08-071, subject to a confidentiality agreement,

(iii) to the CPUC under seal for purposes of review,

(iv) for disclosure of those certain terms specified in and pursuant to Section 10.8 of this Agreement;

(v) in order to comply with any applicable Law, regulation, or any exchange, control area or CAISO rule, or order issued by a court or entity with competent jurisdiction over the disclosing Party (“Disclosing Party”), other than to those entities set forth in subsection (vi);

(vi) in order to comply with any applicable regulation, rule, or order of the CPUC, CEC, or the FERC;

(vii) to the extent necessary for Buyer to exercise its exclusive rights to the Product during the Delivery Term, including its rights to resell any or all portions of the Product as set forth in Section 3.1(a), other than the Contract Price;

(viii) for disclosure by Buyer to publicly release generation information of GTSR Projects, in the aggregate with three or more GTSR or RPS eligible Projects on an annual basis; or

(ix) for disclosure by Buyer to CRS in connection with Buyer’s Green-e® Energy Certification.

(b) If a Party is required to disclose Confidential Information in order to satisfy an obligation pursuant to subsection 10.7(a)(v) above (“Disclosure Order”) each Party shall, to the extent practicable, use reasonable efforts: (i) to notify the other Party prior to disclosing the Confidential Information and (ii) prevent or limit such disclosure. After using such reasonable efforts, the Disclosing Party shall not be: (y) prohibited from complying with a Disclosure Order or (z) liable to the other Party for monetary or other damages incurred in connection with the disclosure of the Confidential Information. Except as provided in the preceding sentence, the Parties shall be entitled to all remedies available at Law or in equity to enforce, or seek relief in connection with, this confidentiality obligation.

(c) Notwithstanding the provisions in Section 10.7(a), the Parties are permitted to disclose information related to the bidding and negotiation process as follows: (i) to Buyer’s Procurement Review Group, as defined in CPUC Decision (D) 02-08-071, subject to a confidentiality agreement, (ii) to the CPUC (including CPUC staff) under seal for purposes of review (if such seal is applicable to the nature of the Confidential Information), and (iii) to the Independent Evaluator, as defined and specified in the PG&E’s Solicitation Protocol (“Protocol”).

(d) The Parties agree that the confidentiality provisions under this Section 10.7 are separate from, and shall not impair or modify any other confidentiality agreements that may be in place between the Parties or their Affiliates; provided however, that the confidentiality provisions of this Section 10.7 shall govern confidential treatment of all non-public information exchanged between the Parties related directly or indirectly to this Agreement as of and after the Effective Date.

10.8 RPS Confidentiality .

(a) Notwithstanding Section 10.7(a) of this Agreement, at any time on or after the date on which the Buyer makes its advice filing letter seeking CPUC Approval of this Agreement, either Party shall be permitted to disclose the following terms with respect to such Transaction: Party names, the number of bids per company, Project size, resource type, Delivery Term, Project location, Capacity Factor and Contract Capacity, Commercial Operation Date, Expected Initial Energy Delivery Date, Contract Quantity, Delivery Point, and the achievement of Project development Milestones.

(b) Seller acknowledges and agrees that pursuant to CPUC Decision D.06-06-066, which implements Senate Bill (SB) No. 1488 (2004 Cal. Stats., Ch. 690 (Sept. 22, 2004)), this Agreement may be publicly available three (3) years from the Commercial Operation Date stated herein. Seller further acknowledges that the CPUC’s rules regarding confidential treatment of this Agreement is subject to change and therefore the timing and extent of disclosure is subject to amendment per CPUC order, rule or regulation.

10.9 Audit . Each Party has the right, at its sole expense and during normal working hours, after reasonable Notice, to examine the records of the other Party to the extent reasonably necessary to verify the accuracy of any statement, charge or computation made pursuant to this Agreement including amounts of Delivered Energy. If any such examination reveals any inaccuracy in any statement, the necessary adjustments in such statement and the payments thereof will be made promptly and shall bear interest calculated at the Interest Rate from the date the overpayment or underpayment was made until paid; provided, however, that no adjustment for any statement or payment will be made unless objection to the accuracy thereof was made prior to the lapse of twelve (12) months from the rendition thereof, and thereafter any objection shall be deemed waived.

10.10 Insurance . Throughout the Term, Seller shall, at its sole cost and expense, obtain and maintain the following insurance coverages and be responsible for its subcontractors, including Seller’s EPC Contractors, maintaining sufficient limits of the appropriate insurance coverage. The obligations of the Seller in this Section 10.10 constitute material obligations of the Agreement.

(a) Workers’ Compensation and Employers’ Liability.

(i) Workers’ Compensation insurance indicating compliance with any applicable labor codes, acts, Laws or statutes, state or federal, where Seller performs Work.

(ii) Employers’ Liability insurance shall not be less than one million dollars ($1,000,000.00) for injury or death occurring as a result of each accident.

(b) Commercial General Liability.

(i) Coverage shall be at least as broad as the Insurance Services Office Commercial General Liability Coverage “occurrence” form, with no alterations to the coverage form.

(ii) The limit shall not be less than three million dollars ($3,000,000.00) each occurrence for bodily injury, property damage, personal injury and products/completed operations. Defense costs shall be provided as an additional benefit and not included within the limits of liability. Coverage limits may be satisfied using an umbrella or excess liability policy or an Owners Contractors Protective (OPC) policy. Limits shall be on a per project basis.

(iii) Coverage shall:

(A) by “Additional Insured” endorsement add as insureds PG&E, its directors, officers, agents and employees with respect to liability arising out of the Work performed by or for the Seller. In the event the Commercial General Liability policy includes a “blanket endorsement by contract,” the following language added to the certificate of insurance will satisfy Buyer’s requirement: “PG&E, its directors, officers, agents and employees with respect to liability arising out of the Work performed by or for the Seller has been endorsed by blanket endorsement;”

(B) be endorsed (blanket or otherwise) to specify that the Seller's insurance is primary and that any insurance or self-insurance maintained by PG&E shall not contribute with it; and

(C) include a severability of interest clause.

(c) Business Auto.

(i) Coverage shall be at least as broad as the Insurance Services Office Business Auto Coverage form covering Automobile Liability, code 1 “any auto”.

(ii) The limit shall not be less than one million dollars ($1,000,000.00) each accident for bodily injury and property damage.

(iii) If scope of Work involves hauling hazardous materials, coverage shall be endorsed in accordance with Section 30 of the Motor Carrier Act of 1980 (Category 2) and the CA 99 48 endorsement.

(d) All Risk Property Insurance.

(i) During construction, an All Risk Property insurance policy including earthquake and flood (with sublimits as appropriate) shall be maintained during the course of Work being performed and include Start-up and testing for installed equipment and delayed opening coverage. Such policy shall include coverage for materials and equipment while under the care, custody and control of the Seller during the course of Work, at the Site, offsite or while in transit to the Site.

(e) Additional Insurance Requirements.

(i) Upon Buyer’s request, Seller shall furnish Buyer with certificates of insurance and endorsements of all required insurance for Seller.

(ii) The insurance documentation shall state that coverage shall not be cancelled except after thirty (30) days prior written Notice has been given to Buyer.

(f) Form And Content.

All policies or binders with respect to insurance maintained by Seller shall waive any right of subrogation of the insurers hereunder against Buyer, its officers, directors, employees, agents and representatives of each of them, and any right of the insurers to any setoff or counterclaim or any other deduction, whether by attachment or otherwise, in respect of any liability of any such person insured under such policy.

10.11 Access to Financial Information . The Parties agree that Generally Accepted Accounting Principles and SEC rules require Buyer to evaluate if Buyer must consolidate Seller’s financial information. Buyer will require access to financial records and personnel to determine if consolidated financial reporting is required. If Buyer determines that consolidation is required, Buyer shall require the following during every calendar quarter for the Term:

(a) complete financial statements and notes to financial statements; and

(b) financial schedules underlying the financial statements, all within fifteen (15) days after the end of each fiscal quarter.

Any information provided to Buyer pursuant to this Section 10.11 shall be considered confidential in accordance with the terms of this Agreement and shall only be disclosed on an aggregate basis with other similar entities for which Buyer has power purchase agreements. The information will only be used for financial statement purposes and shall not be otherwise shared with internal or external parties.

10.12 Governing Law . This agreement and the rights and duties of the parties hereunder shall be governed by and construed, enforced and performed in accordance with the laws of the state of California, without regard to principles of conflicts of law. To the extent enforceable at such time, each party waives its respective right to any jury trial with respect to any litigation arising under or in connection with this agreement.

10.13 General . Except to the extent provided for, no amendment or modification to this Agreement shall be enforceable unless reduced to writing and executed by both Parties. The Parties acknowledge and agree that this Agreement is a “forward contract” (within the meaning of the Bankruptcy Code, as in effect as of the Execution Date). This Agreement shall not impart any rights enforceable by any third party (other than a permitted successor or assignee bound to this Agreement). Waiver by a Party of any default by the other Party shall not be construed as a waiver of any other default. The headings used herein are for convenience and reference purposes only. Electronic transmission will be the same as delivery of an original document; provided that at the request of either Party, the other Party will confirm electronic signatures by signing and delivering an original document; provided, however, that the execution and delivery of this Agreement and its counterparts shall be subject to Section 10.15. This Agreement shall be binding on each Party’s successors and permitted assigns.

10.14 Severability . If any provision in this Agreement is determined to be invalid, void or unenforceable by any court having jurisdiction, such determination shall not invalidate, void, or make unenforceable any other provision, agreement or covenant of this Agreement and the Parties shall use their best efforts to modify this Agreement to give effect to the original intention of the Parties.

10.15 Counterparts . This Agreement may be executed in one or more counterparts each of which shall be deemed an original and all of which shall be deemed one and the same Agreement. Delivery of an executed counterpart of this Agreement by fax will be deemed as effective as delivery of an originally executed counterpart. Any Party delivering an executed counterpart of this Agreement by email will also deliver an originally executed counterpart, but the failure of any Party to deliver an originally executed counterpart of this Agreement will not affect the validity or effectiveness of this Agreement.

10.16 Mobile Sierra . Notwithstanding any provision of this Agreement, neither Party shall seek, nor shall they support any third party seeking, to prospectively or retroactively revise the rates, terms or conditions of service of this Agreement through application or complaint to the FERC pursuant to the provisions of the Federal Power Act, absent prior written agreement of the Parties. Further, absent the prior written agreement in writing by both Parties, the standard of review for changes to the rates, terms or conditions of service of this Agreement proposed by a Party, a non-Party, or the FERC acting *sua sponte* shall be the “public interest” standard of review set forth in *United States Gas Pipe Line Co. v. Mobile Gas Service Corp., 350 U.S. 332 (1956) and Federal Power Commission v. Sierra Pacific Power Co., 350 U.S. 348 (1956)*.

# **ARTICLE ELEVEN: Termination event**

11.1 Force Majeure Termination Event.

(a) Force Majeure Failure. Buyer shall have the right, but not the obligation, to terminate this Agreement after the occurrence of any of the following: (each constituting a “Force Majeure Failure”):

(i) If prior to the Delivery Term, Seller is unable, due solely to a Force Majeure event, to achieve the Commercial Operation Date or place the Project into Commercial Operation by the Guaranteed Commercial Operation Date, after applicable extensions or cure periods have run, as set forth in Section 3.9(c); provided that if a Force Majeure event is caused by a catastrophic natural disaster, then upon Buyer’s written request to Seller, Seller shall have not more than ninety (90) days from the date of such Force Majeure event to obtain a report from an independent, third party engineer stating whether the Project is capable of being repaired or replaced within such twenty-four (24) month period and Seller shall provide Buyer a copy of the engineer’s report, at no cost to Buyer; provided further that if such engineer’s report concludes that the Project is capable of being repaired or replaced within twenty-four (24) months from the date of the Seller provides the engineer’s report to Buyer and Seller undertakes and continues such repair or replacement with due diligence, then Buyer shall not have the right to terminate this Agreement pursuant to this Section 11.1(a) until the expiration of the repair or replacement period deemed necessary by the engineer’s report (which shall not exceed twenty-four (24) months), after which time, Buyer may terminate this Agreement unless the Project has been repaired or replaced, as applicable, and Seller has resumed and is satisfying its obligations under this Agreement.

(ii) If during the Delivery Term:

(A) the Project fails to deliver at least forty percent (40%) of the Contract Quantity to the Delivery Point for a period of twelve (12) consecutive rolling months following a Force Majeure event that materially and adversely impacts the Project and Buyer has provided Notice to Seller of such failure; provided that, if Seller within forty-five (45) days of receipt of Notice from Buyer, presents Buyer with a plan for mitigation of the effect of the Force Majeure within a period not to exceed six (6) months from the above-mentioned Notice date, which plan is commercially reasonable and satisfactory to Buyer, as evidenced by Buyer’s written acknowledgement of such plan, then Buyer shall not have the right to terminate this Agreement pursuant to this Section 11.1(a) until the expiration of the mitigation period deemed necessary by Seller to repair the Project (which shall not exceed six (6) months); provided that Seller diligently pursues such mitigation plan throughout the mitigation period, and after which time Buyer may terminate this Agreement unless the Project has been repaired, and the Seller has resumed and is satisfying all of its obligations under this Agreement; or

(B) the Project is destroyed or rendered inoperable by a Force Majeure event caused by a catastrophic natural disaster; provided that Seller shall have up to ninety (90) days following such Force Majeure event to obtain a report from an independent, third party engineer stating whether the Project is capable of being repaired or replaced no later than twenty-four (24) months from the date of the report and Seller shall provide Buyer with a copy of the engineer’s report, at no cost to Buyer; provided further that if such engineer’s report concludes that the Project is capable of being repaired or replaced within such twenty-four (24) month period and Seller undertakes and continues such repair or replacement with due diligence, then Buyer shall not have the right to terminate this Agreement pursuant to this Section 11.1(a) until the expiration of the period deemed necessary by the engineer’s report (which shall not exceed twenty-four (24) months), after which time, Buyer may terminate this Agreement unless the Project has been repaired or replaced, as applicable, and the Seller has resumed and is satisfying all of its obligations under this Agreement.

(b) Termination and Right of First Offer.

(i) If Buyer exercises its termination right in connection with the Force Majeure Failure, then the Agreement shall terminate without further liability of either Party to the other, effective upon the date set forth in Buyer’s Notice of termination, subject to each Party’s satisfaction of all of the final payment and survival obligations set forth in Sections 2.6(a) and (b). The Parties agree that for a period of three (3) years from the date on which Buyer Notifies Seller of termination due to the Force Majeure Failure (“Exclusivity Period”), neither Seller, its successors and assigns, nor its Affiliates shall enter into an obligation or agreement to sell or otherwise transfer any Products from the Project to any third party, unless Seller first offers, in writing, to sell to Buyer such Products from the Project on the same terms and conditions as this Agreement, subject to permitted modifications identified in subpart (ii) below, (the “First Offer”) and Buyer either accepts or rejects such First Offer in accordance with the provisions herein.

(ii) If Buyer accepts the First Offer, Buyer shall Notify Seller within thirty (30) days of receipt of the First Offer subject to Buyer’s management approval and CPUC Approval (“Buyer’s Notice of First Offer Acceptance”), and then the Parties shall have not more than ninety (90) days from the date of Buyer’s Notice of First Offer Acceptance to enter into a new power purchase agreement, in substantially the same form as this Agreement, or amend this Agreement, subject to CPUC Approval, if necessary; provided that the Contract Price may only be increased to reflect Seller’s documented incremental costs in overcoming the Force Majeure event.

(iii) If Buyer rejects or fails to accept Seller’s First Offer within thirty (30) days of receipt of such offer, Seller shall thereafter be free to sell or otherwise transfer, and to enter into agreements to sell or otherwise transfer, any Products from the Project to any third party, so long as the material terms and conditions of such sale or transfer are not more favorable to the third party than those of the First Offer to Buyer. If, during the Exclusivity Period, Seller desires to enter into an obligation or agreement with a third party, Seller shall deliver to Buyer a certificate of an authorized officer of Seller (A) summarizing the material terms and conditions of such agreement and (B) certifying that the proposed agreement with the third party will not provide Seller with a lower rate of return than that offered in the First Offer to Buyer. If Seller is unable to deliver such a certificate to Buyer, then Seller may not sell or otherwise transfer, or enter into an agreement to sell or otherwise transfer, the Products from the Project without first offering to sell or otherwise transfer such Products to Buyer on such more favorable terms and conditions (the “Revised Offer”) in accordance with subpart (ii) above. If within thirty (30) days of receipt of Seller’s Revised Offer the Buyer rejects, or fails to accept by Notice to Seller, the Revised Offer, then Seller will thereafter be free to sell or otherwise transfer, and to enter into agreements to sell or otherwise transfer, such Products from the Project to any third party on such terms and conditions as set forth in the certificate.

# **ARTICLE TWELVE: DISPUTE RESOLUTION**

12.1 Intent of the Parties . Except as provided in the next sentence, the sole procedure to resolve any claim arising out of or relating to this Agreement is the dispute resolution procedure set forth in this Article Twelve. The lone exception to the foregoing is that either Party may seek an injunction in Superior Court in Alameda County, California if such action is necessary to prevent irreparable harm, in which case both Parties nonetheless will continue to pursue resolution of all other aspects of the dispute by means of this procedure.

12.2 Management Negotiations .

(a) The Parties will attempt in good faith to resolve any controversy or claim arising out of or relating to this Agreement by prompt negotiations between each Party’s Authorized Representative, or such other person designated in writing as a representative of the Party (each a “Manager”). Either Manager may request a meeting, to be held in person or telephonically, to initiate negotiations to be held within ten (10) Business Days of the other Party’s receipt of such request, at a mutually agreed time and place. If the matter is not resolved within fifteen (15) Business Days of their first meeting (“Initial Negotiation End Date”), the Managers shall refer the matter to the designated senior officers of their respective companies (“Executive(s)”), who shall have authority to settle the dispute. Within five (5) Business Days of the Initial Negotiation End Date (“Referral Date”), each Party shall provide one another written Notice confirming the referral and identifying the name and title of the Executive who will represent the Party.

(b) Within five (5) Business Days of the Referral Date, the Executives shall establish a mutually acceptable location and date to meet, which date shall not be greater than thirty (30) days from the Referral Date. After the initial meeting date, the Executives shall meet, as often as they reasonably deem necessary, to exchange relevant information and to attempt to resolve the dispute.

(c) All communication and writing exchanged between the Parties in connection with these negotiations shall be deemed confidential and subject to the confidentiality provisions of this Agreement. All such communication and writing shall be inadmissible as evidence such that it cannot be used or referred to in any subsequent binding adjudicatory process between the Parties, whether with respect to this dispute or any other.

(d) If the matter is not resolved within forty-five (45) days of the Referral Date, or if the Party receiving the written request to meet, pursuant to Section 12.2(a), refuses or does not meet within the ten (10) Business Day period specified in Section 12.2(a), either Party may initiate mediation of the controversy or claim according to the terms of the following Section 12.3.

12.3 Mediation . If the dispute cannot be resolved by negotiation as set forth in Section 12.2 above, then either Party may initiate mediation, the first-step of a two-step dispute resolution process, which JAMS shall administer. As the first step, the Parties agree to mediate any controversy before a commercial mediator from the JAMS panel, pursuant to JAMS’s then-applicable commercial mediation rules, in Alameda County, California. Either Party may initiate such a mediation by serving a written demand for mediation. The mediator shall not have the authority to require, and neither Party may be compelled to engage in, any form of discovery prior to or in connection with the mediation. If within sixty (60) days after service of a written demand for mediation, or as extended by mutual agreement of the Parties, the mediation does not result in resolution of the dispute, then the Parties shall resolve such controversy through Arbitration by one retired judge or justice from the JAMS panel, which Arbitration shall take place in Alameda County, California, and which the arbitrator shall administer by and in accordance with JAMS’s Commercial Arbitration Rules (“Arbitration”). If the Parties cannot mutually agree on the arbitrator who will adjudicate the dispute, then JAMS shall provide the Parties with an arbitrator pursuant to its then-applicable Commercial Arbitration Rules. The period commencing from the date of the written demand for mediation until the appointment of a mediator shall be included within the sixty (60) day mediation period. Any mediator(s) and arbitrator(s) shall have no affiliation with, financial or other interest in, or prior employment with either Party and shall be knowledgeable in the field of the dispute. Either Party may initiate Arbitration by filing with the JAMS a notice of intent to arbitrate within sixty (60) days of service of the written demand for mediation.

12.4 Arbitration  . At the request of a Party, the arbitrator shall have the discretion to order depositions of witnesses to the extent the arbitrator deems such discovery relevant and appropriate. Depositions shall be limited to a maximum of three (3) per Party and shall be held within thirty (30) days of the making of a request. Additional depositions may be scheduled only with the permission of the arbitrator, and for good cause shown. Each deposition shall be limited to a maximum of six (6) hours duration unless otherwise permitted by the arbitrator for good cause shown. All objections are reserved for the Arbitration hearing except for objections based on privilege and proprietary and Confidential Information. The arbitrator shall also have discretion to order the Parties to exchange relevant documents. The arbitrator shall also have discretion to order the Parties to answer interrogatories, upon good cause shown.

(a) Each of the Parties shall submit to the arbitrator, in accordance with a schedule set by the arbitrator, offers in the form of the award it considers the arbitrator should make. If the arbitrator requires the Parties to submit more than one such offer, the arbitrator shall designate a deadline by which time the Parties shall submit their last and best offer. In such proceedings the arbitrator shall be limited to awarding only one of the two “last and best” offers submitted, and shall not determine an alternative or compromise remedy.

(b) The arbitrator shall have no authority to award punitive or exemplary damages or any other damages other than direct and actual damages and the other remedies contemplated by this Agreement.

(c) The arbitrator’s award shall be made within nine (9) months of the filing of the notice of intention to arbitrate (demand) and the arbitrator shall agree to comply with this schedule before accepting appointment. However, this time limit may be extended by agreement of the Parties or by the arbitrator, if necessary. The California Superior Court of the County of Alameda may enter judgment upon any award rendered by the arbitrator. The Parties are aware of the decision in Advanced Micro Devices, Inc. v. Intel Corp., 9 Cal. 4th 362 (1994) and, except as modified by this Agreement, intend to limit the power of the arbitrator to that of a Superior Court judge enforcing California Law.

(d) The prevailing Party in this dispute resolution process is entitled to recover its costs and reasonable attorneys’ fees.

(e) The arbitrator shall have the authority to grant dispositive motions prior to the commencement of or following the completion of discovery if the arbitrator concludes that there is no material issue of fact pending before him or her.

(f) Except as may be required by Law, neither a Party nor an arbitrator may disclose the existence, content, or results of any Arbitration hereunder without the prior written consent of both Parties.

# **ARTICLE THIRTEEN: NOTICES**

Whenever this Agreement requires or permits delivery of a “Notice” (or requires a Party to “notify”), the Party with such right or obligation shall provide a written communication in the manner specified herein; provided, however, that notices of Outages or other Scheduling or dispatch information or requests, as provided in Appendix VI, shall be provided in accordance with the terms set forth in the relevant section of this Agreement. Notices may be sent by e-mail. A Notice sent by e-mail will be recognized and shall be deemed received on the Business Day on which such Notice was transmitted if received before 5:00 p.m. (and if received after 5:00 p.m., on the next Business Day) and a Notice of overnight mail or courier shall be deemed to have been received two (2) Business Days after it was sent or such earlier time as is confirmed by the receiving Party. Either Party may periodically change any address, phone number, e-mail, website, or contact, including such information in Appendix VI and the “Notices List” in the Cover Sheet, to which Notice is to be given it by providing Notice of such change to the other Party.

*[Remainder of Page Intentionally Left Blank]*

# **SIGNATURES**

**Agreement Execution**

IN WITNESS WHEREOF, each Party has caused this Agreement to be duly executed by its authorized representative as of the dates provided below:

|  |  |  |  |
| --- | --- | --- | --- |
| [**SELLER, a (*include place of formation and business type*)**] | | **PACIFIC GAS AND ELECTRIC COMPANY, a California corporation** | |
| Signature: |  | Signature: |  |
| Name: |  | Name: |  |
| Title: |  | Title: |  |
| Date: |  | Date: |  |

**APPENDIX I**

**FORM OF LETTER OF CREDIT**

***Issuing Bank Letterhead and Address***

**STANDBY LETTER OF CREDIT NO.** XXXXXXXX

**Date:** ***[insert issue date]***

|  |  |  |  |
| --- | --- | --- | --- |
| **Beneficiary:** | Pacific Gas and Electric Company  300 Lakeside Drive, Suite 210 | **Applicant:** | [Insert name and address of Applicant] |
|  | Oakland, CA 94612 |  |  |
|  | Attention: Credit Risk Management |  |  |

**Letter of Credit Amount: *[Insert the amount]***

**Expiry Date: *[Insert the expiry date]***

Ladies and Gentlemen:

By order of ***[Insert the name of Applicant]*** (“Applicant”), we hereby issue in favor of Pacific Gas and Electric Company (the “Beneficiary”) our irrevocable standby letter of credit No. ***[Insert the letter of credit number]*** (“Letter of Credit”), for the account of Applicant, for drawings up to but not to exceed the aggregate sum of U.S. $ ***[Insert amount in figures followed by (amount in words)]*** (“Letter of Credit Amount”). This Letter of Credit is available with ***[Insert the name of issuing bank, and the city and state in which it is located]*** by sight payment, at our offices located at the address stated below, effective immediately, and it will expire at our close of business on ***[Insert the expiry date]*** (the “Expiry Date”).

Funds under this Letter of Credit are available to the Beneficiary against presentation of the following documents (which may be presented by physical delivery or by facsimile, e-mail or other electronic transmission):

1. Beneficiary’s signed and dated sight draft in the form of Exhibit A hereto, referencing this Letter of Credit No. ***[Insert the Letter of Credit number]*** and stating the amount of the demand; and

2. One of the following statements signed by an authorized representative or officer of Beneficiary:

A. “Pursuant to the terms of that certain ***[Insert the name of the Agreement]*** (the “Agreement”), dated ***[Insert the date of the Agreement]***, between Beneficiary and ***[Insert the name of Seller under the Agreement]*,** Beneficiary is entitled to draw under Letter of Credit No. ***[Insert the Letter of Credit number]*** amounts owed by ***[Insert the name of Seller under the Agreement]*** under the Agreement; or

B. “Letter of Credit No. ***[Insert the Letter of Credit number]*** will expire in thirty (30) days or earlier and ***[Insert the name of Seller under the Agreement]*** has not provided replacement security acceptable to Beneficiary.

Special Conditions:

1. Partial and multiple drawings under this Letter of Credit are allowed;

2. All banking charges associated with this Letter of Credit are for the account of the Applicant;

3. This Letter of Credit is not transferable; and

4. The Expiry Date of this Letter of Credit shall be automatically extended, without a written amendment, for a period of one (1) year, and it shall also be so extended on each successive Expiry Date, unless at least sixty (60) days before the then current Expiry Date we notify you by registered mail or courier that we elect not to extend the Expiry Date of this Letter of Credit for such an additional period.

We engage with you that drafts drawn under and in compliance with the terms of this Letter of Credit will be duly honored upon presentation, on or before the Expiry Date (or after the Expiry Date in case of an interruption of our business as stated below), at our offices located at ***[Insert issuing bank’s address for drawings]***.

All demands for payment shall be made by presentation of copies or original documents, or by facsimile, e-mail, or other electronic transmission of documents to [Insert fax number, email or other electronic transmission], Attention: [Insert name of bank’s receiving department] or [Insert e-mail or other electronic transmission address]. If a demand is made by facsimile, e-mail or other electronic transmission, the originals or copies of documents must follow by overnight mail, and you may contact us at [Insert phone number(s)] to confirm our receipt of the transmission. Your failure to seek such a telephone confirmation does not affect our obligation to honor such a presentation.

Our payments against complying presentations under this Letter of Credit will be made no later than on the sixth (6th) banking day following a complying presentation.

Except as stated herein, this Letter of Credit is not subject to any condition or qualification. It is our individual obligation, which is not contingent upon reimbursement and is not affected by any agreement, document, or instrument between us and the Applicant or between the Beneficiary and the Applicant or any other party.

Except as otherwise specifically stated herein, this Letter of Credit is subject to and governed by the *Uniform Customs and Practice for Documentary Credits, 2007 Revision,* International Chamber of Commerce (ICC) Publication No. 600 (the “UCP 600”); provided that, if this Letter of Credit expires during an interruption of our business as described in Article 36 of the UCP 600, we will honor drafts presented in compliance with this Letter of Credit, if they are presented within thirty (30) days after the resumption of our business, and we will effect payment accordingly.

The electronic copy of this Letter of Credit shall be the operative instrument until such time as the original is received. This Letter of credit can be amended or terminated by facsimile, e-mail or other electronic transmission.

The law of the State of New York shall apply to any matters not covered by the UCP 600.

For telephone assistance regarding this Letter of Credit, please contact us at ***[insert number and any other necessary details]***.

Very truly yours,

|  |  |
| --- | --- |
| ***[insert name of issuing bank]*** | |
| By: |  |
|  | Authorized Signature |
| Name: | ***[print or type name]*** |
| Title: | ***[print or type title]*** |

***[Note: All pages must contain the Letter of Credit number and page number for identification purposes.]***

**Exhibit A SIGHT DRAFT**

TO

[INSERT NAME AND ADDRESS OF PAYING BANK]

AMOUNT: $\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ DATE: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

AT SIGHT OF THIS DEMAND PAY TO THE ORDER OF PACIFIC GAS AND ELECTRIC COMPANY THE AMOUNT OF U.S.$\_\_\_\_\_\_\_\_(\_\_\_\_\_\_\_\_\_\_\_\_\_\_ U.S. DOLLARS)

DRAWN UNDER [INSERT NAME OF ISSUING BANK] LETTER OF CREDIT NO. XXXXXX.

REMIT FUNDS AS FOLLOWS:

[INSERT PAYMENT INSTRUCTIONS]

DRAWER

BY: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

NAME AND TITLE

**APPENDIX II**

**INITIAL ENERGY DELIVERY DATE CONFIRMATION LETTER**

In accordance with the terms of that certain Power Purchase Agreement dated \_\_\_\_\_\_\_ (“Agreement”) by and between \_\_\_\_\_\_\_\_\_\_\_(“Buyer”) and \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (“Seller”), this letter (“Initial Energy Delivery Date Confirmation Letter”) serves to document the Parties’ further agreement that (i) the Conditions Precedent to the occurrence of the Initial Energy Delivery Date have been satisfied, and (ii) Buyer has accepted delivery of the Product, as specified in the Agreement, as of this \_\_\_\_\_ day of \_\_\_\_\_\_, \_\_\_\_\_\_ (the “Initial Energy Delivery Date”). All capitalized terms not defined herein shall have the meaning set forth in the Agreement.

Seller represents to Buyer that it has been granted status as an [Exempt Wholesale Generator] [Qualifying Facility]. Additionally Seller provides the following FERC Tariff information for reference purposes only:

Tariff: Dated: Docket Number:

IN WITNESS WHEREOF, each Party has caused this Initial Energy Delivery Date Confirmation Letter to be duly executed by its authorized representative as of the date of last signature provided below:

|  |  |  |  |
| --- | --- | --- | --- |
| [**SELLER, a (*include place of formation and business type*)**] | | **PACIFIC GAS AND ELECTRIC COMPANY, a California corporation** | |
| Signature: |  | Signature: |  |
| Name: |  | Name: |  |
| Title: |  | Title: |  |
| Date: |  | Date: |  |

**Appendix III**

**FORM OF PROGRESS REPORT**

Progress Report

of

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

(“Seller”)

provided to

Pacific Gas and Electric Company

(“Buyer”)

[Date]

**Instructions**.

Any capitalized terms used in this report which are not defined herein shall have the meaning ascribed to them in the Power Purchase Agreement by and between , (“Seller”) and Pacific Gas and Electric Company dated \_\_\_\_\_\_\_\_\_\_\_\_, (the “Agreement”).

Seller shall review the status of each Milestone of the construction schedule for the Project and Seller shall identify such matters referenced in clauses (i)-(v) below as known to Seller and which in Seller’s reasonable judgment are expected to adversely affect the schedule, and with respect to any such matters, shall state the actions which Seller intends to take to ensure that the Milestones will be attained by their required dates. Such matters may include, but shall not be limited to:

(i) Any material matter or issue arising in connection with a Governmental Approval, or compliance therewith, with respect to which there is an actual or threatened dispute over the interpretation of a Law, actual or threatened opposition to the granting of a necessary Governmental Approval, any organized public opposition, any action or expenditure required for compliance or obtaining approval that Seller is unwilling to take or make, or in each case which could reasonably be expected to materially threaten or prevent financing of the Units or related Project, attaining any Milestone, or obtaining any contemplated agreements with other parties which are necessary for attaining any Milestone or which otherwise reasonably could be expected to materially threaten Seller’s ability to attain any Milestone.

(ii) Any development or event in the financial markets or the independent power industry, any change in taxation or accounting standards or practices or in Seller’s business or prospects which reasonably could be expected to materially threaten financing of the Project, attainment of any Milestone or materially threaten any contemplated agreements with other parties which are necessary for attaining any Milestone or could otherwise reasonably be expected to materially threaten Seller’s ability to attain any Milestone;

(iii) A change in, or discovery by Seller of, any legal or regulatory requirement which would reasonably be expected to materially threaten Seller’s ability to attain any Milestone;

(iv) Any material change in the Seller’s schedule for initiating or completing any material aspect of Project;

(v) The status of any matter or issue identified as outstanding in any prior Progress Report and any material change in the Seller’s proposed actions to remedy or overcome such matter or issue.

For guidance, each “overview” subsection shall include a summary of the status and progress of major activities associated with that section, whether planned, in progress, or completed, including relevant dates. Each “recent activities” subsection shall include details of activities during the previous month. Each “expected activities” subsection shall include a brief list of major activities planned for the current month.

Seller shall complete, certify, and deliver this form of Progress Report to [\_\_\_\_\_\_\_\_\_\_\_\_], together with all attachments and exhibits, with copies of this report delivered to GCMTGroup@pge.com and [\_\_\_\_\_\_\_\_\_\_\_\_].

1. **Executive Summary**

Please provide an overview of the Project, including technology, size, location, and ownership.

Please provide a brief chronological cumulative summary of the **major** activities completed for each of the following aspects of the Project. Include the date each item was added to the summary (*e.g., in Milestone section “January 2012 – notice of Construction Start Date milestone achieved was reported to PG&E on January 15, 2012” and in Construction section “January 2012 - Notice to Proceed was issued to EPC contractor on January 10, 2012”* ):

* 1. **Milestones**
  2. **Governmental Approvals**
  3. **Financing**
  4. **Property Acquisition**
  5. **Design and Engineering**
  6. **Major Equipment procurement**
  7. **Construction**
  8. **Interconnection**
  9. **Startup**

1. **Milestones**

In this section, please include information on each Milestone listed in the Cover Sheet, plus any additional significant milestones related to the project.

* 1. **Milestone schedule**

Please state the status and progress of each Milestone. Provide the date of completion of completed Milestone(s) and the expected date of completion of uncompleted Milestone(s). The expected date is the current best estimate, and may change from time to time as better information becomes available.

* 1. **Remedial Action Plan (applicable if Seller fails to achieve a Milestone by the Milestone Date)**

Please describe in detail any delays (actual or anticipated) beyond the scheduled Milestone dates. Describe the cause of the delay (e.g., governmental approvals, financing, property acquisition, design activities, equipment procurement, project construction, interconnection, or any other factor). Describe Seller’s Remedial Action Plan which shall include detailed plans to achieve the missed Milestone and subsequent Milestones.

1. **Governmental Approvals**

In this section, please include information on each of the Governmental Approvals required for the construction of the Units and the status thereof. List the applicable government agency, the type of application/approval requested, and the dates (expected or actual) of significant activity. Significant activity includes, but is not limited to, application submission, notice of complete application, notice of preparation, public hearing or comment period, draft documents and/or approvals, final documents and/or approvals, notice of determination, and/or issuance of permit. If the government agency maintains a website with information on the approval process for the Project, please provide a link.

* 1. **Environmental Impact Report/Statement (EIR/EIS)**

Please describe the environmental review process and each of the Governmental Approval(s) to be obtained for the Project. Provide the status and completion date (expected or actual) of each significant activity in the process.

* 1. **Other Governmental Approvals**

Please describe each of the other Governmental Approvals to be obtained for the Project. Provide the status and completion date (expected or actual) of each significant activity.

* 1. **Recent Governmental Approval activities**

Please describe in detail the Governmental Approval activities that occurred during the previous calendar month.

* 1. **Expected Governmental Approval activities**

Please list all Governmental Approval activities that are expected to be performed during the current calendar month.

* 1. **Governmental Approval Notices received**

Please attach to this Progress Report copies of any Notices related to Governmental Approval activities received during the previous calendar month.

1. **Financing Activities**

In this section, please include information on each separate phase of financing for the Project. Include information on debt, equity, and/or federal or state loans or grants.

* 1. **Overview of financing activities**

Please provide a summary of the status and progress of each major financing activity, including the date of execution of significant documents, and information on the expected timing of future significant activities.

* 1. **Recent financing activities**

Please describe in detail the financing activities that occurred during the previous calendar month.

* 1. **Expected financing activities**

Please list the financing activities that are expected to be performed during the current calendar month.

1. **Property Acquisition Activities**

In this section, please include information on property acquisition or site control activities for the Project.

* 1. **Overview of property acquisition activities**

Please provide a summary of the status and progress of each major property acquisition activity, including the date of execution of significant documents, and information on the expected timing of future significant activities.

* 1. **Recent property acquisition activities**

Please describe in detail the property acquisition activities that occurred during the previous calendar month.

* 1. **Expected property acquisition activities**

Please list the property acquisition activities that are expected to be performed during the current calendar month.

1. **Design and Engineering Activities**

In this section, please include information on the status of design and engineering for the Project.

* 1. **Overview of design activities**

Please provide a summary of the status and progress of each major design or engineering activity, including dates of completion of significant activities and expected timing of future activities.

* 1. **Recent design activities**

Please describe in detail the design activities that occurred during the previous calendar month.

* 1. **Expected design activities**

Please list the design activities that are expected to be performed during the current calendar month.

1. **Major Equipment Procurement**

In this section, please include information on all major equipment to be procured for all portions of the Project to be completed by Seller, including switchyards, substations and any other interconnection equipment, in addition to generating and auxiliary equipment.

* 1. **Overview of major equipment procurement activities**

For each type of equipment, list the number of each major item to be procured, the manufacturer, model number (if applicable), and rating. List the delivery schedule (expected or actual as applicable), breaking out the number of each item (to be) procured or delivered in each month.

* 1. **Recent major equipment procurement activities**

Please describe in detail the major equipment procurement activities that occurred during the previous calendar month.

* 1. **Expected major equipment procurement activities**

Please list the major equipment procurement activities that are expected to be performed during the current calendar month.

1. **Construction Activities**

In this section, please include information on the status of any construction-related factors that may affect the ability of the Project to deliver Product to the Buyer. Include information on the Project infrastructure, generating equipment, and major auxiliary equipment. Also include information on the substations, switchyards, gen-ties, telecommunications equipment or other interconnection facilities that are the direct responsibility of the Project.

* 1. **Overview of major construction activities**

Please provide a summary of the status and progress of each major construction activity for all portions of the Project, including a schedule showing expected or actual dates as applicable. Provide the name of the EPC Contractor, the date of execution of the EPC Contract, and the date of issuance of a full Notice to Proceed (or equivalent). For each major type of equipment, break out the number of each item (to be) installed and/or commissioned in each month.

* 1. **Recent construction activities**

Please describe in detail the construction activities that occurred during the previous calendar month.

* 1. **Expected construction activities**

Please list the interconnection activities that are expected to be performed during the current calendar month.

* 1. **EPC Contractor Progress Report**

Please attach a copy of the Progress Reports received during the previous calendar month from the EPC Contractor pursuant to the construction contract between Seller and EPC Contractor, certified by the EPC Contractor as being true and correct as of the date issued.

* 1. **Look-ahead construction schedule**

Please provide a look-ahead construction schedule covering at least three months.

* 1. **OSHA Recordables**

Please list all OSHA recordables from the previous calendar month.

* 1. **Work stoppages**

Please describe any work stoppage from the previous calendar month and its effect on the construction schedule.

1. **Interconnection Activities**

In this section, please include information on interconnection-related factors that may affect the ability of the Project to deliver Product to the Buyer. Include information on the status of interconnection studies, Interconnection Agreements including Shared Facilities Agreements as applicable, design and construction of Interconnection Facilities (e.g., substations, switchyards, gen-ties, system protection schemes, telecommunications equipment to the extent not already covered in the Project construction information in Section 8), Shared Facilities as applicable, Network Upgrades, and grid outage and/or interconnection schedules.

* 1. **Overview of interconnection activities**

Please provide a summary of the status and progress of each major interconnection activity including dates of completion of significant activities and expected timing of future activities.

* 1. **Recent interconnection activities**

Please describe in detail the interconnection activities that occurred during the previous calendar month.

* 1. **Expected interconnection activities**

Please list the interconnection activities that are expected to be performed during the current calendar month.

1. **Startup**

In this section, please include information on the status of activities related to preparation for Commercial Operation, including equipment testing, commissioning, release to operations, requirements of the grid operator, and any other activities that must be conducted before the Project may deliver Energy to the grid and/or declare Commercial Operation.

* 1. **Overview of startup activities**

Please provide a summary of the status and progress of each major startup activity including dates of completion of significant activities and expected timing of future activities.

* 1. **Recent startup activities**

Please describe in detail the startup activities that occurred during the previous calendar month.

* 1. **Expected startup activities**

Please list the startup activities that are expected to be performed during the current calendar month.

I, \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, on behalf of and as an authorized representative of \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_, do hereby certify that any and all information contained in this Seller’s Progress Report is true and accurate, and reflects, to the best of my knowledge, the current status of the construction of the Project as of the date specified below.

By:\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Name:\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Title:\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Date:\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**APPENDIX IV**

**CONSTRUCTION START AND COMMERCIAL OPERATION**

**CERTIFICATION FORMS AND PROCEDURES**

Appendix IV-1: CONSTRUCTION START FORM OF CERTIFICATION

Appendix IV-2: COMMERCIAL OPERATION CERTIFICATION PROCEDURE

Attachment A Commercial Operation Form of Certification

**APPENDIX IV–1**

**CONSTRUCTION START**

**FORM OF CERTIFICATION**

\_\_(Date)\_\_\_

Director Contract Management and Settlements

Pacific Gas and Electric Company

300 Lakeside Drive, Suite 210

Oakland, CA 94612

Re: Construction Start Date

This certification (“Certification”) of the Construction Start Date is delivered by \_\_\_\_\_\_\_\_\_\_\_ (“Seller”) to Pacific Gas and Electric Company (“Buyer”) in accordance with the terms of that certain Power Purchase Agreement dated \_\_\_\_\_\_\_\_ (“Agreement”) by and between Seller and Buyer. All capitalized terms used in this Certification but not otherwise defined herein shall have the respective meanings assigned to such terms in the Agreement. Seller hereby certifies and represents to Buyer all of the following:

a) the EPC Contract related to the Project was executed on \_\_\_\_\_\_\_\_\_\_;

b) [permitting agency name] \_ issued grading permits to the Seller on \_\_\_\_\_\_\_\_\_\_; and

c) the Notice to Proceed was issued on \_\_\_\_\_\_\_\_\_\_\_\_\_\_ (attached), and.

d) mobilization at the Project Site commenced on \_\_\_\_\_\_\_\_\_\_.

IN WITNESS WHEREOF, the undersigned has executed this certificate on behalf of the Seller as of the \_\_\_ day of \_\_\_\_\_\_\_\_.

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

(Seller)

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

(Name)

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

(Position)

[LICENSED PROFESSIONAL ENGINEER]

By: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Name: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Title: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Date: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**APPENDIX IV–2**

**COMMERCIAL OPERATION CERTIFICATION PROCEDURE**

In accordance with the terms of that certain Power Purchase Agreement dated \_\_\_\_\_\_\_\_, 20\_\_ by and between Pacific Gas and Electric Company (“Buyer”) and \_\_\_\_\_\_\_\_\_\_\_\_ (“Seller”) to declare and recognize the Commercial Operation Date of the Project, Seller shall provide all of the documents set forth herein to Buyer as of the Commercial Operation Date. All terms not defined herein shall have the meaning set forth in the Agreement.

(1) A certification from an authorized officer of Seller, substantially in the form of Attachment A to this Appendix IV-2, dated as of the Commercial Operation Date; and

(2) A certificate or report from a Licensed Professional Engineer containing all of the following:

(a) A statement that the Project has achieved Mechanical Completion and the date on which it was achieved;

(b) A statement that the Project has successfully completed Project Testing and the dates on which Seller has accepted the test results; and

(c) A statement that the Project has achieved Substantial Completion and the date on which it was achieved.

(3) Seller has provided to Buyer all documents which demonstrate that Seller has satisfied all of the CAISO agreement, interconnection agreement, and metering requirements in Sections 3.4 and 3.6 and has enabled Buyer to schedule the Facility with the CAISO for the Facility’s full unrestricted output.

(4) Definitions.

(a) “Mechanical Completion” means that (i) all components and systems of the Project have been properly constructed, installed and functionally tested according to EPC Contract requirements in a safe and prudent manner that does not void any equipment or system warranties or violate any permits, approvals or Laws; (ii) the Project is ready for startup testing and commissioning; (iii) Seller has provided written acceptance to the EPC Contractor of mechanical completion as that term is specifically defined in the EPC Contract.

(b) “Project Testing Completion” means the written acceptance to the EPC Contractor of the completion of startup testing / commissioning, emissions testing (as applicable), and performance / acceptance / warranty testing (all such testing shall be collectively referred to as “Project Testing”) as required under the EPC Contract. The objectives of the tests shall be generally (i) to verify that the Project has been properly designed and constructed to meet the performance and operating requirements of the EPC Contract; (ii) to assure warranty coverage for equipment and systems over their warranty periods.

(c) “Substantial Completion” means when the following has occurred: (i) the Project is sufficiently complete, in accordance with the EPC Contract, that Seller has full and unrestricted use and benefit of the Project in the use for which it is intended; (ii) the Project has achieved Mechanical Completion; (iii) utilities are fully connected and operating normally; (iv) all necessary permits have been issued; (v) the Project is fully and properly interconnected and synchronized with the electrical grid and is capable of producing electricity in accordance with the EPC Contract; (vi) the operating manual has been approved by Seller; (vii) all work other than incidental corrective and incidental punch list work is complete; and (viii) Seller has provided written acceptance to the EPC Contractor of substantial completion as that term is specifically defined in the EPC Contract.

**APPENDIX IV–2 –Attachment A**

**COMMERCIAL OPERATION**

**FORM OF CERTIFICATION**

This certification (“Certification”) of Commercial Operation is delivered by \_\_\_\_\_\_\_(“Seller”) to Pacific Gas and Electric Company (“Buyer”) in accordance with the terms of that certain Power Purchase Agreement dated \_\_\_\_\_\_\_ (“Agreement”) by and between Seller and Buyer. All capitalized terms used in this Certification but not otherwise defined herein shall have the respective meanings assigned to such terms in the Agreement.

Seller hereby certifies and represents to Buyer the following:

(1) Mechanical Completion of the Project was achieved on \_\_\_\_[DATE]\_\_\_\_.

(2) Project Testing Completion successfully occurred on:

***[Seller to indicate each type of Project Testing and date completed]***

(a) NAME OF TEST [DATE]

(b) NAME OF TEST [DATE]

(c) NAME OF TEST [DATE]

(3) Substantial Completion of the Project was achieved on \_\_\_\_[DATE]\_\_\_\_

(4) Pre-parallel inspection of the Project was successfully completed on \_\_[DATE]\_\_

(5) Authorization to parallel the Project was obtained on \_\_\_\_[DATE]\_\_\_\_

(6) Telemetering / SCADA visibility with PTO and CAISO grid control and power dispatch centers was obtained for the Project on \_\_\_\_[DATE]\_\_\_\_

(7) Reliability Network Upgrades (as defined in the CAISO Tariff) were completed on the Project on \_\_\_\_[DATE]\_\_\_\_

(8) Power system stabilizer testing and calibration was obtained for the Project on \_\_\_\_\_[DATE]\_\_\_\_ or, □ was not required

(9) Full Capacity Deliverability Status Finding from CAISO was obtained for the Project on \_\_\_\_[DATE]\_\_\_\_ or, □ was not required because the Project is Energy Only.

(10) The Participating Transmission Provider or Distribution Provider has provided documentation supporting full unrestricted release for Commercial Operation by [Name of Participating Transmission Owner as appropriate] on \_\_\_\_\_\_\_[DATE]\_\_\_\_\_.

(11) The CAISO has provided notification supporting Commercial Operation, in accordance with the CAISO Tariff on \_\_\_\_\_\_\_[DATE]\_\_\_\_\_.

***[The following shall only apply to Projects that utilize Shared Facilities]***

(12) The CAISO has provided approval of the CAISO Exemption in accordance with the CAISO Tariff on \_\_\_\_\_\_\_[DATE]\_\_\_\_\_.

A certified statement of the Licensed Professional Engineer, attached hereto, has been provided as evidence of Commercial Operation of the Project to provide Product and meet, at a minimum, the requirements indicated herein.

EXECUTED by SELLER this \_\_\_\_\_\_\_\_ day of \_\_\_\_\_\_\_\_\_\_\_\_\_, 20\_\_.

|  |  |  |  |
| --- | --- | --- | --- |
|  | | **[Licensed Professional Engineer]** | |
| Signature: |  | Signature: |  |
| Name: |  | Name: |  |
| Title: |  | Title: |  |
|  |  | Date: |  |

|  |  |  |
| --- | --- | --- |
|  | License Number and LPE Stamp: |  |

**APPENDIX V**

**GEP DAMAGES CALCULATION**

In accordance with the provisions in Section 3.1(e)(ii), GEP Damages means the liquidated damages payment due by Seller to Buyer, calculated as follows:

[(A-B) × (C-D)]

Where:

A = the Guaranteed Energy Production for the Performance Measurement Period, in MWh

B = Sum of Delivered Energy plus Deemed Delivered Energy, if any, over the Performance Measurement Period, in MWh

C= Replacement price for the Performance Measurement Period, in $/MWh, which is the sum of (a) the simple average of the Integrated Forward Market hourly price for all the hours in the Performance Measurement Period, as published by the CAISO, for the Existing Zone Generation Trading Hub (as defined in the CAISO Tariff), in which the PNode resides, plus (b) $50/MWh

D = the unweighted Contract Price specified in the Cover Sheet for the Performance Measurement Period, in $/MWh

The Parties agree that in the above calculation of GEP Damages, the result of “(C-D)” is less than $20/MWh, the “(C-D)” will be replaced with $20/MWh.

**APPENDIX VI**

**NOTIFICATION REQUIREMENTS FOR AVAILABLE CAPACITY AND PROJECT OUTAGES**

**A. NOTIFICATION REQUIREMENTS for ROUTINE start-up and shutdownS**

Prior to paralleling or after disconnecting from the electric system, ALWAYS follow your balancing authority rules and notify the applicable Participating Transmission Owner’s (PTO) switching center

* Call the applicable Participating Transmission Owner’s (PTO) switching center and Buyer’s Real-Time Desk to advise of the intent to parallel before any Start-up.

1. Call the applicable Participating Transmission Owner’s (PTO) switching center and Buyer’s Real-Time Desk after the unit has been paralleled and report the parallel time and intended unit output.
2. Call the applicable Participant Transmission Owner’s (PTO) switching center and Buyer’s Real-Time Desk after any routine separation and report the separation time as well as the date and time estimate for return to service.

**B. submission of AVAILABLE CAPACITY AND Planned outages**

1. Submit information by posting to PG&E’s approved web-based system, which is located at www.pge.com under “Business to Business,” or alternative website designated by PG&E (both, “PG&E’s Website”). Once directed to the appropriate page, enter the username and password assigned by PG&E’s Bilateral Settlements Group. If PG&E’s Website is unavailable, implement the procedures set forth below:

* 1. **For all email correspondence, enter the following in the email subject field: Delivery Date Range, Company Name, Contract Name, Email Purpose, Date Range(For example: “dd/mm/yyyy through dd/mm/yyyy, XYZ Company Project #2, Daily Forecast of Available Capacity,”)**
  2. For Annual Forecasts of Available Capacity, email to DAenergy@pge.com and Bilat\_Settlements@pge.com.
  3. For Monthly and Daily Forecasts of Available Capacity, email to DAenergy@pge.com.
  4. For Daily Forecasts of Available Capacity after fourteen (14) hours before the close of the CAISO Day-Ahead Market, but before the CAISO deadline for submitting Schedules into the Day-Ahead Market, call primary phone (415) 973-1971 or backup phone (415) 973-4500. Also send email to DAenergy@pge.com.
  5. For Hourly Forecasts of Available Capacity, call PG&E’s Real Time Desk at (415) 973-4500 and email to RealTime@pge.com.
  6. For Planned Outages and Prolonged Outages, complete the specifics below and submit by email to ESMOutageCoordinator@pge.com, DAenergy@pge.com, and Bilat\_Settlements@pge.com.
     1. ***Email subject field*: Company Name, Contract Name, Email Purpose, Date Range(For example: “dd/mm/yyyy through dd/mm/yyyy, XYZ Company Project #2, Daily Forecast of Available Capacity”)**
     2. ***Email body:***
        1. ***Type of Outage: Planned Outage or Prolonged Outage***
        2. ***Start Date and Start Time***
        3. ***Estimated or Actual End Date and End Time for Outage***
        4. ***Date and time when reported to PG&E and name(s) of PG&E representative(s) contacted***
        5. ***Text description of additional information as needed, including, but not limited to, changes to a Planned Outage or Prolonged Outage.***
        6. ***Contact name: first and last name of the individual at the Unit to contact regarding the outage(s) at issue in the email.***

**C. Forced Outage reporting**

1. Forced Outages – Seller shall notify PG&E merchant generation desk verbally at (415) 973-4500 within ten (10) minutes of event or as soon as reasonably possible, after the safety of all personnel and securing of all facility equipment.
2. Seller will be responsible for reporting the following information when reporting Forced Outages to the PG&E merchant generation desk:
   1. Operator Name
   2. Specific Issue: outage or derate due to XXX.
   3. Total Plant Availability: the current MW value the plant can generate
   4. Estimated Time of Return (“ETR”): Date (MMDDYYYY) and time (HH:MM) in 24H format.
3. After verbally notifying PG&E Merchant Generation desk of the forced outage,  submit the following information via email to Bilat\_Settlements@pge.com.
4. ***Email subject field*: Company Name, Contract Name, Email Purpose, Date Range(For example: “dd/mm/yyyy through dd/mm/yyyy, XYZ Company Project #2, Daily Forecast of Available Capacity”)**
5. ***Email body:***
6. ***Type of Outage: Forced Outage***
7. ***Start Date and Start Time***
8. ***Estimated or Actual End Date and End Time***
9. ***Date and time when reported to PG&E and name(s) of PG&E representative(s) contacted.***
10. ***Text description of additional information as needed.***
11. ***Primary and secondary causes of Forced Outage, including a detailed description of specific equipment involved and the nature of the problem or condition.***
12. ***Equipment description and nature of work being performed. For generation outages, include NERC Generation Availability Data System (GADS) numbers (as available) that identify the specific equipment and type of work that affect restrictions. Include additional equipment designations as available.***
13. ***Text description of additional information as needed, including, but not limited to, changes to a previously scheduled Outage, links/cross-references to related outage cards and log entries, outage classifications per the CAISO Tariff, etc.***
14. ***Associated events, e.g. operation of Special Protection Schemes.***
15. ***Impact on CAISO-controlled Grid.***

**APPENDIX VII**

**FORM OF FINANCING CONSENT TO ASSIGNMENT**

**FINANCING CONSENT AND AGREEMENT**

This CONSENT AND AGREEMENT (“Consent and Agreement”) is entered into as of **[\_\_\_\_\_\_\_ \_\_, 2\_\_\_]**, between PACIFIC GAS AND ELECTRIC COMPANY, a California corporation (“PG&E”), and **[\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_]**, ***[include place of formation and business type]*** as collateral agent (in such capacity, “Financing Provider”), for the benefit of various financial institutions (collectively, the “Secured Parties”) providing financing to [\_\_\_\_\_\_\_] (“Seller”). PG&E, Seller, and the Financing Provider shall each individually be referred to as a “Party” and collectively as the “Parties”.

**Recitals**

A. Pursuant to that certain Power Purchase Agreement dated as of \_\_\_\_\_\_\_\_\_\_\_\_\_, 2\_\_\_ (as amended, modified, supplemented or restated from time to time, as including all related agreements, instruments and documents, collectively, the “Assigned Agreement”) between PG&E and Seller, PG&E has agreed to purchase Energy from Seller.

B. The Secured Parties have provided, or have agreed to provide, to Seller financing (including, but not limited to a financing lease) pursuant to one or more agreements (the “Financing Documents”), and require that Financing Provider be provided certain rights with respect to the “Assigned Agreement” and the “Assigned Agreement Accounts,” each as defined below, in connection with such financing.

C. In consideration for the execution and delivery of the Assigned Agreement, PG&E has agreed to enter into this Consent and Agreement for the benefit of Seller.

**Agreement**

1. Definitions. Any capitalized term used but not defined herein shall have the meaning specified for such term in the Assigned Agreement.

2. Consent. Subject to the terms and conditions below, PG&E consents to and approves the pledge and assignment by Seller to Financing Provider pursuant to the Financing Documentsof (a) the Assigned Agreement, and (b) the accounts, revenues and proceeds of the Assigned Agreement (collectively, the “Assigned Agreement Accounts”).

3. Limitations on Assignment.

3.1 Limitations. Financing Provider acknowledges and confirms that, notwithstanding any provision to the contrary under applicable law or in any Financing Document executed by Seller, Financing Provider shall not assume, sell or otherwise dispose of the Assigned Agreement (whether by foreclosure sale, conveyance in lieu of foreclosure or otherwise) unless, on or before the date of any such assumption, sale or disposition, Financing Provider or any third party designated by Financing Provider, as the case may be, assuming, purchasing or otherwise acquiring the Assigned Agreement is a Permitted Transferee (as defined below). Financing Provider further acknowledges that this assignment of the Assigned Agreement and the Assigned Agreement Accounts is for security purposes only and that Financing Provider has no rights under the Assigned Agreement or the Assigned Agreement Accounts to enforce the provisions of the Assigned Agreement or the Assigned Agreement Accounts unless and until an event of default has occurred and is continuing under the Financing Documents between Seller and Financing Provider (a “Financing Default”), in which case Financing Provider shall be entitled to designate a Permitted Transferee, after completing the process of obtaining PG&E’s acceptance in accordance with Section 3.2(a), to assume all of the rights and benefits and be subject to all of the obligations which Seller then has or may have under the Assigned Agreement to the same extent and in the same manner as if the Permitted Transferee were an original party to the Assigned Agreement.

3.2 Permitted Transferee

(a) A Permitted Transferee is a person or entity that (i) cures any and all defaults of Seller under the Assigned Agreement which are “Capable of Being Cured” as defined in Section 3.2(b); (ii) executes and delivers to PG&E a written assumption of all of Seller’s rights and obligations under the Assigned Agreement in form and substance reasonably satisfactory to PG&E, (iii) otherwise satisfies and complies with all requirements of the Assigned Agreement, including credit and collateral requirements; (iv) if requested by PG&E, provides (A) tax and enforceability assurance as PG&E may reasonably request to ensure PG&E does not incur any costs or loss any benefits by such assignment; (B) documentation to demonstrate the Permitted Transferee’s safety record and ability to meet applicable safety obligations; and (C) its ability to construct (if applicable), operate, and maintain the Project, and evidence that the Permitted Transferee has operated other energy storage facilities with a similar technology and operating profile; and (v) is reasonably acceptable to PG&E.

(b) “Capable of Being Cured” means that the Assigned Agreement specifies that a cure is available to Seller for a default(s), whether such cure is financial or by performance, and the terms of the cure as specified in the Assigned Agreement remain unfulfilled and available as set forth in the Assigned Agreement without modification. If the Assigned Agreement does not specify that a cure is available for a default(s), or a cure is specified but is no longer available as a cure (due to the passage of time or for any other reason), then the default(s) shall not be “Capable of Being Cured”. An incurable (default by Seller shall be cause for termination by PG&E of the Assigned Agreement and the Assigned Agreement will not be available for assignment to a Permitted Transferee.

(c) Financing Provider shall, following the occurrence of a Financing Default, Notify PG&E of the identity of a proposed transferee of the Assigned Agreement, which proposed transferee may include Financing Provider, in connection with the enforcement of Financing Provider’s rights under the Financing Documents, and PG&E shall, within thirty (30) Business Days of its receipt of such Notice, confirm to Financing Provider whether or not such proposed transferee is a Permitted Transferee (together with a written statement of the reason(s) for any negative determination) it being understood that if PG&E shall fail to so respond within such thirty (30) Business Day period such proposed transferee shall be deemed to be a Permitted Transferee.

4. Cure Rights.

4.1 Notice to Financing Provider by PG&E. Concurrently with the delivery to Seller of any Notice of an event of default under the Assigned Agreement (each, an “Event of Default”) (and a “Default Notice”), PG&E shall provide a copy of such Default Notice to Financing Provider pursuant to Section 9.1 of this Consent and Agreement. In addition, Seller shall provide a copy of the Default Notice to Financing Provider the next Business Day after receipt from PG&E, independent of any agreement of PG&E to deliver such Default Notice.

4.2 Cure Period Available to Financing Provider Prior to Any Termination by PG&E. Upon the occurrence of an Event of Default, but only if the default is curable, PG&E agrees not to terminate the Assigned Agreement unless it or Seller first provides Financing Provider with Notice of the Event of Default and PG&E affords Financing Provider an additional cure period of ten (10) calendar days for the financial cure or thirty (30) calendar days for a non-financial cure.

4.3 Failure to Deliver Default Notice. If neither PG&E nor Seller delivers a Default Notice to Financing Provider as provided in Section 4.1, then the Financing Provider’s applicable cure period shall begin on the date on which Notice of an Event of Default is delivered to Financing Provider by either PG&E or Seller, whichever is received first. Except for a delay in the commencement of the cure period for Financing Provider and a delay in PG&E’s ability to terminate the Assigned Agreement (in each case only if both PG&E and Seller fail to deliver Notice of an Event of Default to Financing Provider), failure of PG&E to deliver any Default Notice shall not waive PG&E’s right to take any action under the Assigned Agreement and will not subject PG&E to any damages or liability for failure to provide such Notice.

4.4 Extension for Foreclosure Proceedings. If (a) it is necessary for the Financing Provider to have possession of the Project (as defined in the Assigned Agreement) in order for Financing Provider to cure an Event of Default which is Capable of Being Cured, as defined in Section 3.2(b), and (b) and Financing Provider commences foreclosure proceedings against Seller within thirty (30) calendar days of receiving Notice of an Event of Default from PG&E or Seller, whichever is received first, then Financing Provider shall be allowed an additional period to complete such foreclosure proceedings, such period not to exceed ninety (90) calendar days; provided, however, that Financing Provider shall provide a written Notice to PG&E that it intends to commence foreclosure proceedings with respect to Seller within ten (10) calendar days of receiving a Notice of such Event of Default from PG&E or Seller, whichever is received first. In the event Financing Provider or its designated Permitted Transferee succeeds to Seller’s interest in the Project as a result of foreclosure proceedings, the Financing Provider or Permitted Transferee shall be subject to the requirements of Section 3 of this Consent and Agreement.

5. Setoffs and Deductions. Each of Seller and Financing Provider agrees that PG&E shall have the right to set off or deduct from payments due to Seller each and every amount due PG&E from Seller whether or not arising out of or in connection with the Assigned Agreement. Financing Provider further agrees that it takes the assignment for security purposes of the Assigned Agreement and the Assigned Agreement Accounts subject to any defenses or causes of action PG&E may have against Seller.

6. No Representation or Warranty. Seller and Financing Provider each recognizes and acknowledges that PG&E makes no representation or warranty, express or implied, that Seller has any right, title, or interest in the Assigned Agreement or as to the priority of the assignment for security purposes of the Assigned Agreement or the Assigned Agreement Accounts. Financing Provider is responsible for satisfying itself as to the existence and extent of Seller’s right, title, and interest in the Assigned Agreement, and Financing Provider releases PG&E from any liability resulting from the assignment for security purposes of the Assigned Agreement and the Assigned Agreement Accounts.

7. Amendment to Assigned Agreement. Financing Provider acknowledges and agrees that PG&E may agree with Seller to modify or amend the Assigned Agreement, and that PG&E is not obligated to Notify Financing Provider of any such amendment or modification to the Assigned Agreement. Financing Provider hereby releases PG&E from all liability arising out of or in connection with the making of any amendment or modification to the Assigned Agreement.

8. Payments under Assigned Agreement. PG&E shall make all payments due to Seller under the Assigned Agreement from and after the date hereof to [\_\_\_\_\_\_\_\_\_\_], as depositary agent, to ABA No. [\_\_\_\_\_\_\_\_\_\_], Account No. [\_\_\_\_\_\_\_\_\_\_], and Seller hereby irrevocably consents to any and all such payments being made in such manner. Each of Seller, PG&E and Financing Provider agrees that each such payment by PG&E to such depositary agent of amounts due to Seller from PG&E under the Assigned Agreement shall satisfy PG&E’s corresponding payment obligation under the Assigned Agreement.

9. Miscellaneous.

9.1 Notices. All Notices given or requirements of a Party to Notify hereunder shall be in writing, receipt of which shall be deemed complete (i) at the close of business of the date of receipt, if delivered by hand or by electronic means, or (ii) when signed for by recipient, if sent registered or certified mail, postage prepaid, provided such Notice was properly addressed to the appropriate address set forth below or to such other address that a Party may designate by prior Notice to the other Parties:

|  |  |
| --- | --- |
| To Financing Provider: |  |
| Attn: | \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |
| Department | \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |
| Street Address: | \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |
|  | \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |
| Telephone: | \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |
| Email: | \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |

|  |  |
| --- | --- |
| To PG&E: | \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |
| Attn: | \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |
| Department | \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |
| Street Address: | \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |
|  | \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |
| Telephone: | \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |
| Email: | \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |

9.2 No Assignment. This Consent and Agreement shall be binding upon and shall inure to the benefit of the successors and assigns of PG&E, and shall be binding on and inure to the benefit of the Financing Provider, the Secured Parties and their respective successors and Permitted Transferees and assigns under theFinancing Documents.

9.3 No Modification. This Consent and Agreement is neither a modification of nor an amendment to the Assigned Agreement.

9.4 Choice of Law. The Parties hereto agree that this Consent and Agreement shall be construed and interpreted in accordance with the laws of the State of California, excluding any choice of law rules which may direct the application of the laws of another jurisdiction.

9.5 No Waiver. No term, covenant or condition hereof shall be deemed waived and no breach excused unless such waiver or excuse shall be in writing and signed by the Party claimed to have so waived or excused.

9.6 Counterparts. This Consent and Agreement may be executed in one or more duplicate counterparts, and when executed and delivered by all the Parties listed below, shall constitute a single binding agreement.

9.7 No Third Party Beneficiaries. There are no third party beneficiaries to this Consent and Agreement.

9.8 Severability. The invalidity or unenforceability of any provision of this Consent and Agreement shall not affect the validity or enforceability of any other provision of this Consent and Agreement, which shall remain in full force and effect.

9.9 Amendments and Termination. This Consent and Agreement may be modified, amended, or rescinded only by writing expressly referring to this Consent and Agreement and signed by all Parties hereto. Notwithstanding the foregoing, Seller and Financing Provider may terminate this Consent by delivering a signed notice to PG&E in substantially the form of Attachment A, attached hereto and made a part hereof.

IN WITNESS WHEREOF, each of PG&E and Financing Provider has duly executed this Consent and Agreement as of the date first written above.

|  |  |  |  |
| --- | --- | --- | --- |
| **PACIFIC GAS AND ELECTRIC COMPANY, a California corporation** | | ***[FINANCING PROVIDER*, a *(include place of formation and business type)], as collateral agent*** | |
| Signature: |  | Signature: |  |
| Name: |  | Name: |  |
| Title: |  | Title: |  |
| Date: |  | Date: |  |

**ACKNOWLEDGEMENT**

The undersigned hereby acknowledges the Consent and Agreement set forth above, makes the agreements set forth therein as applicable to Seller, including the obligation of Seller to provide a copy of any Default Notice it receives from PG&E to Financing Provider the next Business Day after receipt by Seller, and confirms that the Financing Provider identified above and the Secured Parties have provided or are providing financing to the undersigned Seller.

|  |  |
| --- | --- |
| *[***SELLER, a *(include place of formation and business type)]*** | |
| Signature: |  |
| Name: |  |
| Title: |  |
| Date: |  |

**APPENDIX VII -- Attachment A**

**FINANCING CONSENT TERMINATION NOTICE**

[Date]

VIA E-MAIL

Pacific Gas and Electric Company

300 Lakeside Drive, Suite 210

Oakland, CA 94612

Attention: [Kelly Everidge, Senior Director Contract Management, Settlements, and Reporting]

Re: Termination of Financing Consent to Assignment

Dear [Ms. Everidge]:

Pacific Gas and Electric Company (“PG&E”) and [\_\_\_\_\_\_\_\_\_\_\_\_\_\_] (“Seller”) are parties to a Power Purchase Agreement (“Agreement”) dated as of [\_\_\_\_\_\_\_\_\_\_\_\_\_\_] for the Facility described as the [\_\_\_\_\_\_\_\_\_\_\_\_\_\_] Project (PG&E Log No. [\_\_\_\_\_\_\_\_\_\_\_\_\_\_]). All capitalized terms used but not defined herein shall have the meanings provided to them in the Agreement or Consent described below.

Subsequent to the execution of the Agreement, Seller and PG&E entered into a Financing Consent and Agreement dated as of [\_\_\_\_\_\_\_\_\_\_\_\_\_\_] with [\_\_\_\_\_\_\_\_\_\_\_\_\_\_] as Financing Provider, with respect to the Agreement (“Consent”). Pursuant to Section 9.9 of the Consent, Seller and Financing Provider are hereby providing Notice that effective as of [\_\_\_\_\_\_\_\_\_\_\_\_\_\_] (the “Termination Date”), they now wish to terminate the Consent.

As of the Termination Date, PG&E is hereby instructed to make all payments due Seller under the Agreement directly to Seller as provided therein.

|  |  |  |  |
| --- | --- | --- | --- |
| [**SELLER, a (*include place of formation and business type*)**] | | ***[FINANCING PROVIDER*, a *(include place of formation and business type)], as collateral agent*** | |
| Signature: |  | Signature: |  |
| Name: |  | Name: |  |
| Title: |  | Title: |  |
| Date: |  | Date: |  |

**APPENDIX VIII**

**SELLER DOCUMENTATION CONDITION PRECEDENT**

Seller shall provide to Buyer all of the following documentation prior to the Execution Date:

1. A copy of each of (A) the articles of incorporation, certificate of incorporation, operating agreement or similar applicable organizational document of Seller and (B) the by-laws or other similar document of Seller (collectively, “Charter Documents”) as in effect, or anticipated to be in effect, on the Execution Date.

2. A certificate signed by an authorized officer of Seller (who must be a different person than the officers listed in clause (C) below), dated no earlier than ten (10) Business Days prior to the Execution Date, certifying (A) that attached thereto is a true and complete copy of the Charter Documents of the Seller, as in effect at all times from the date on which the resolutions referred to in clause (B) below were adopted to and including the date of such certificate; (B) that attached thereto is a true and complete copy of resolutions duly adopted by the board of directors (or other equivalent body) or evidence of all corporate or limited liability company action, as the case may be, of Seller, authorizing the execution, delivery and performance of this Agreement, and that such resolutions have not been modified, rescinded or amended and are in full force and effect, and (C) as to the name, incumbency and specimen signature of each officer of Seller executing this Agreement.

3. A certificate from the jurisdiction of Seller’s incorporation or organization certifying that Seller is duly organized, validly existing and in good standing under the laws of such jurisdiction.

4. Evidence of Site control (e.g. memorandum of lease or lease with redacted price terms, an option to lease or purchase, or proof of ownership), satisfactory to Buyer, covering the entire Term of the PPA. PG&E will not accept a “Memorandum of Option Agreement” as filed with a County Recorder because it is a summary of a transaction and lacks the actual terms of the option.

5. Evidence of CEC Certification and Verification (pre-certification) satisfactory to Buyer.

6. A copy of the most recent financial statements (which may be unaudited) from Seller together with a certificate from the Chief Financial or equivalent officer of Seller, dated no earlier than ten (10) Business Days prior to the Execution Date, to the effect that, to the best of such officer’s knowledge, (A) such financial statements are true, complete and correct in all material respects and (B) there has been no material adverse change in the financial condition, operations, Properties, business or prospects of Seller since the date of such financial statements.

7. An executed Letter of Concurrence substantially in the form specified in Appendix XI.

**APPENDIX IX**

**FORM OF ACTUAL AVAILABILITY REPORT**

Pursuant to Section 3.1(l)(i), Seller shall prepare an Actual Availability Report in accordance with the procedures described in this Appendix IX.

(a) Availability Workbook. Seller shall (i) collect the measurement data, listed in (b) below, in one (1) or more Microsoft Excel Workbooks (the “Availability Workbook”) provided in a form and naming convention approved by Buyer and (ii) electronically send the Availability Workbook to an address provided by Buyer. The Actual Availability Report shall reflect the sum of the Settlement Interval Actual Available Capacity of all generators as measured by such generator’s internal turbine controller.

(b) Log of Availability. The Availability Workbook shall be created on a single, dedicated Excel worksheet and shall be in the form of Attachment A to this Appendix IX.

**APPENDIX IX**

**Attachment A**

**Form of Actual Availability Report**

**Seller’s Actual Availability Report**

*All amounts are in MWs*

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Settlement Interval No.** | **Date** | **HE1** | **HE2** | **HE3** | **HE4** | **HE5** | **HE6** | **HE7** | **HE8** | **HE9** | **HE10** | **HE11** | **HE12** | **HE13** | **HE14** | **HE15** | **HE16** | **HE17** | **HE18** | **HE19** | **HE20** | **HE21** | **HE22** | **HE23** | **HE24** |
| 1 | mm/dd/yyyy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | mm/dd/yyyy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | mm/dd/yyyy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | mm/dd/yyyy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | mm/dd/yyyy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 | mm/dd/yyyy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | mm/dd/yyyy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | mm/dd/yyyy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | mm/dd/yyyy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | mm/dd/yyyy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | mm/dd/yyyy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 | mm/dd/yyyy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | mm/dd/yyyy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | mm/dd/yyyy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | mm/dd/yyyy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | mm/dd/yyyy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | mm/dd/yyyy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 | mm/dd/yyyy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Date/Time of Submittal

**APPENDIX X**

**TELEMETRY PARAMETERS FOR SOLAR FACILITY**

|  |  |  |
| --- | --- | --- |
| **Technology Type** | **Telemetry Parameters** | **Units** |
| **Solar Photovoltaic** | Back Panel Temperature | ˚C |
|  | Global Horizontal Irradiance | W/m2 |
|  | Plane of Array Irradiance (If PV is fixed)  Direct Normal Irradiance (If PV is Tracking) | W/m2 |
|  | Wind Speed | m/s |
|  | Peak Wind Speed (Within 1 minute) | m/s |
|  | Wind Direction | Degrees |
|  | Ambient Air Temperature | ˚C |
|  | Dewpoint Air Temperature or Relative Humidity | ˚C |
|  | Horizontal Visibility | m |
|  | Precipitation (Rain Rate) | mm/hr |
|  | Precipitation (Running 30 day total) | mm |
|  | Barometric Pressure | Millibars or  Hecto Pascals (HPa) |

**APPENDIX XI**

**FORM OF LETTER OF CONCURRENCE**

[Date]

[Name]

[Position]

[Company]

[Address]

Re: Letter of Concurrence Regarding Control of [Name] Facility

This letter sets forth the understanding of the degree of control exercised by Pacific Gas and Electric Company (“PG&E”) and [Company Name] with respect to [Facility Name (the “Facility”)] for the purposes of facilitating compliance with the requirements of the Federal Energy Regulatory Commission’s (“Commission”) Order No. 697.[[2]](#footnote-3) Specifically, Order No. 697 requires that sellers filing an application for market-based rates, an updated market power analysis, or a required change in status report with regard to generation specify the party or parties they believe have control of the generation facility and extent to which each party holds control.[[3]](#footnote-4) The Commission further requires that “a seller making such an affirmative statement seek a ‘letter of concurrence’ from other affected parties identifying the degree to which each party controls a facility and submit these letters with its filing.”[[4]](#footnote-5)

PG&E and [Company Name] have executed a [power purchase and sale agreement (the “Agreement”)] with regard to the Facility. The Facility is a [XX] MW [description] facility located in [County, State]. Pursuant to the Agreement, [Company Name] maintains sole control of the Facility. [Company Name] agrees to provide subsequent Letters of Concurrence as may be necessary should any of the information provided herein change after the execution date of this letter.

If you concur with the statements made in this letter, please countersign the letter and send a copy to me.

Best regards,

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

[Author]

[Position]

Pacific Gas and Electric Company

**Concurring Statement**

On behalf of [Company Name], I am authorized to countersign this letter in concurrence with its content.

By: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

[Name]

[Company Position]

[Company Name]

**APPENDIX XII**

**SUPPLIER DIVERSITY PROGRAM**

1. Seller agrees as follows:

a. Seller shall use good faith efforts in meeting the requirements of this Appendix XII which efforts shall be material obligations.

b. Seller shall provide a copy of this Appendix to each prospective Subcontractor.

c. Seller shall provide Women-, Minority-, and service-Disabled Veteran-, and Lesbian, Gay, Bisexual and/or Transgender-owned Business Enterprises, as verified pursuant to the procedures prescribed in Section 2 of CPUC General Order 156 (“WMDVLGBTBE”), the maximum practicable opportunity to participate in the performance of Work supporting Seller’s construction, operation, and maintenance of the Project. General Order 156 can be found linked from https://www.cpuc.ca.gov/supplierdiversity/

2. In order for Subcontractors to qualify as a WMDVLGBTBE, they must be certified as follows:

a. Small Businesses Enterprises must be registered as a small business with a state or federal agency (e.g. Department of General Services or Small Business Administration);

b. Women- and minority-owned businesses must be certified by the California Public Utilities Commission’s Supplier Clearinghouse;

c. Service disabled veteran-owned businesses must be certified by the Department of General Services;

d. Lesbian, Gay, Bisexual and Transgender-owned businesses must be certified by the National Gay and Lesbian Chamber of Commerce (NGLCC®).

3. Targets

a. Seller’s supplier diversity spending target for Work supporting the construction of the Project prior to the expected Commercial Operation Date is: ***[insert percentage]*** percent (\_\_\_\_***%***) as measured relative to Seller’s total expenditures on construction of the Project prior to the expected Commercial Operation Date.

b. Seller’s annual supplier diversity spending target for Work supporting the operation and maintenance of the Project after the Initial Energy Delivery Date is: ***[insert percentage]*** percent (\_\_\_\_***%***) as measured relative to the net payments made by Buyer to Seller in each calendar year.

4. Reporting

a. Upon request from Buyer, Seller shall provide a separate “Supplier Plan” consisting of a specific list of suppliers that may participate in the performance of the Work supporting the construction of the Project prior to the Commercial Operation Date and operation and maintenance of the Project after the Initial Energy Delivery Date, and a statement setting forth any additional efforts Seller will employ to increase the participation of WMDVLGBTBE suppliers supporting the construction, operation and maintenance of the Project.

b. Upon request from Buyer, but no less than once per 365-day period of time between the Execution Date and the end of the Delivery Term, Seller shall report its spending with WMDVLGBTBE suppliers per instructions to be provided by PG&E.

c. Seller will be expected to report payments made to small, diverse businesses to support the Project upon request but no less than annually.

Status of Seller ***(Select one)***:

***[Seller is not a WMDVLGBTBE]***

***[Seller is a WMDVLGBTBE, as certified by \_\_\_\_\_\_\_\_\_\_\_\_\_ [please identify the certifying agency].***

**APPENDIX XIII**

**PROJECT SPECIFICATIONS**

**I. PROJECT SPECIFICATIONS**

“MVA” means megavolt ampere, the unit of apparent power.

“Nameplate Rated Output” means, with respect to an inverter or electric generator, the MVA that the manufacturer of the inverter or generator has designed such equipment to produce under normal operating conditions as specified by such manufacturer.

“Designated Power Factor” means, with respect to an inverter or electric generator, the power factor required to satisfy the portion of the Project’s reactive power requirements that are specified in ***[please identify the applicable source, such as the PTO’s Interconnection Handbook, the CAISO’s Phase II Study, or the Generator Interconnection Agreement for the Project]*** and are not being satisfied by other sources of reactive power within the Project.

“Nameplate Rated Power” means, with respect to an inverter or electric generator, the multiplication product of the Nameplate Rated Output and the Designated Power Factor for such inverter or generator, in MWs.

“Total Nameplate Rated Power” means ***[Seller to insert total MW from table]***, as set forth in the table entitled Table 1: Description of Nameplate Information in this Appendix XIII below, which shall be no greater than ***[Seller to specify the applicable restriction: 20 MW for Unreserved Projects and 1 MW for Environmental Justice Projects]***.

The project specifications shall consist of the following items (each item of which shall be a “Project Specification”). As provided in Section 3.1(g), Seller shall not make any change or modification to any Project Specification without Buyer’s prior written consent.

1. Project name:

2. Project Site name:

3. Project physical address:

4. Latitude and longitude at the centroid of the Project Site:

5. Assessor Parcel Number(s) (APN):

6. Total number of Units at the Project:

7. Technology Type:

8. Interconnection Point of Project:

9. Service Territory of Project:

10. Substation:

11. Description of Units:

a. For each type of inverter in the Project, specify in the table below the type, the number of inverters, the Nameplate Rated Output, the total Nameplate Rated Output, the Designated Power Factor, the Nameplate Rated Power and the Total Nameplate Rated Power. ***[add rows as needed]***

**Table 1: Description of the Nameplate Information**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  |  |  |  |  |
| **Inverter Type** | **Number of Inverters** | **Nameplate Rated Output (MVA)** | **Designated Power Factor** | **Nameplate Rated Power (MW)** |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | **Per Inverter** | **Total** |  | **Per Inverter** | **Total** |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
| Total |  | N/A |  |  | N/A |  |

b. For each type of panel technology (e.g., multi-crystalline silicon, mono-crystalline silicon, thin-film CdTe, multi-junction, bifacial, concentrating, etc.) and each type of panel orientation (e.g., fixed-mount, tilt-angle, azimuth, single-axis tracker, double axis tracker, etc.) specify in the table below the technology, the type of orientation and the total DC rating at Standard Test Conditions: ***[add rows as needed]***

**Table 2: DC Rating for Panel Technology Types and Orientation**

|  |  |  |
| --- | --- | --- |
| **Panel Technology** | **Orientation** | **DC Rating at STC (MWDC)** |
|  |  |  |
|  |  |  |
| Total | N/A |  |

“Standard Test Conditions” means, with respect to determining the nameplate DC rating of a solar PV panel in a factory flash test, an irradiance of 1,000 W/m2, a panel temperature of 25°C, and an air mass of 1.5.

12. Legal Description of Land:

The legal descripton of the land is as shown below, and shall correspond to the Project Site identified on the topographical map included in Section 14 below. The legal description of the land means the metes and bounds of the entire Project Site (or equivalent description acceptable to Buyer) and must match the legal description shown on the deed, lease, or option to lease. :

***[Insert Legal Description of Land]***

13. Description of Interconnection Facilities and metering:

The Project will use the following Interconnection Facilities, Shared Facilities, as applicable,and metering configuration as identified in this one-line diagram included in this Appendix XIII:

***[Insert One-Line Diagram for Interconnection Facilities, Shared Facilities as applicable, and Metering*** ***using a high-quality image format]***

***[NOTE: Because this PPA will be provided to third parties and eventually made public, please ensure there are NO confidentiality or proprietary engineering firm notices on the diagrams that prevent duplication or sharing. Alternatively, provide written consent for disclosure with the Diagram or on the Diagram]***

14. Description of Shared Facilities: [if applicable]

15. Maps: The Site is identified in the following topographical map:

***[INSERT MAP - it must include boundary lines corresponding to the legal description of the Project Site, street names/highway numbers, APN and latitude/longitude and should match any other locational information included in this Appendix XIII; PG&E will not accept a map that does not include these identifiable location notations]***

**APPENDIX XIV**

**SECTION 3.3(e) LIQUIDATED DAMAGES CALCULATION**

I. Equation and Formulas for Calculating RA Deficiency Amount

As provided in Section 3.3(e)(ii)(B), the formula for calculating the RA Deficiency Amount in a given RA Shortfall Month is:

RA Deficiency Amount ($/Month) = RA Value ($/MW/Month) × Expected Net Qualifying Capacity (MW)

Where the:

A. RA Value shall be $4,010/MW/Month in calendar year 2017 and shall escalate at 2.5% per year for each succeeding calendar year; **[*PG&E may update to 2020 as base year*]** and

B. Expected Net Qualifying Capacity for projects that selected Full Capacity Deliverability Status shall be the product of the Contract Capacity and the applicable monthly Qualifying Capacity factor in the table below; or

C. Expected Net Qualifying Capacity for Projects seeking Partial Capacity Deliverability Status shall be the product of the Partial Capacity Deliverability Status Amount and the applicable monthly Qualifying Capacity factor in the table below..

**Table XIV-1 Monthly Qualifying Capacity Factor**

|  |  |
| --- | --- |
| Month | Solar |
| Jan | 0.0% |
| Feb | 2.4% |
| March | 10.4% |
| April | 33.2% |
| May | 30.5% |
| June | 44.8% |
| July | 41.7% |
| Aug | 41.0% |
| Sept | 33.4% |
| Oct | 29.4% |
| Nov | 4.1% |
| Dec | 0.0% |

II. Example of Calculation of the RA Deficiency Amount (for illustrative purposes only) if:

* RA Shortfall Month is June 2020
* Project is a solar system
* Contract Capacity is 20 MW
* RA Start Date is based on the Expected FCDS Date, which is January 1, 2020
* FCDS is achieved on August 14, 2020

**RA Value ($/MW/Month)** = $4,010.00, escalated at 2.5% per year for 3 years, from 2017 to 2020 **[*PG&E may update to 2020 as base year*]**

$4,010 × (1.025)3 = $4,318/MW/Month.

**Monthly Qualifying Capacity factor** for a solar project in June is 44.8% (from table above).

**Expected Net Qualifying Capacity** =

Contract Capacity (MW) × monthly Qualifying Capacity factor =

20 MW × 44.8% = 8.96 MW

**RA Deficiency Amount ($/Month) =**

RA Value ($/MW/Month) × Expected Net Qualifying Capacity (MW) =

$4,318/MW/Month × 8.96 MW = $38,689.28

In this example, the RA Shortfall Period is from January through October 2020. The calculations above would be performed and the result applied for each month in this RA Shortfall Period.

1. Avoided emissions may or may not have any value for GHG compliance purposes. Although avoided emissions are included in the list of Green Attributes, this inclusion does not create any right to use those avoided emissions to comply with any GHG regulatory program. [↑](#footnote-ref-2)
2. *Market-Based Rates for Wholesale Sales of Electric Energy, Capacity and Ancillary Services by Public Utilities*, Order No. 697 at P 186-187, FERC Stats. & Regs. ¶ 31,252, *clarified*, 121 FERC ¶ 61,260 (2007), *order on reh’g*, Order No. 697-A, FERC Stats. & Regs. ¶ 31,268 (2008), *clarified*, 124 FERC ¶ 61,055 (2008), *order on reh’g*, Order No. 697-B, FERC Stats. & Regs. ¶ 31,285 (2008), *order on reh’g*, Order No. 697-C, FERC Stats. & Regs. ¶ 31,291 (2009), *order on reh’g*, Order No. 697-D, FERC Stats. & Regs. ¶ 31,305 (2010). [↑](#footnote-ref-3)
3. Order No. 697 at P 186. [↑](#footnote-ref-4)
4. Order No. 697 at P 187. [↑](#footnote-ref-5)