## Class B Action PGE-24 Atch 1
2021 WMP Class B Action PGE-24 Attachment 1
Responses to B-24 - Progress Tracking
Table # | ID | Line ID | Table Name | Sub-Category (if applicable) | Year Range | Risk Assessment and Mapping Maturity Timeline | Define what "continue" or "increase" means | Is the benchmark quantitative? (Yes/No) | Benchmark or Tracking Method
4 | 23 | 4.23 | Risk Assessment and Mapping Maturity Timeline | NA | 2020-2024 | Increase granularity of ignition risk reduction to below the circuit level. | Transitioning the granularity of ignition risk reduction to the circuit segment or individual asset level. | No | Track assessed level of ignition risk reduction (e.g., circuit segment, entire circuit, or at some other level)
4 | 24 | 4.24 | Risk Assessment and Mapping Maturity Timeline | NA | 2020-2024 | Increase granularity of ignition risk reduction to below the circuit level, including integration of fire spread consequences. | Developing the fire spread consequence at a circuit segment or asset level | No | Models will be updated so that fire spread consequence data can be produced at the circuit segment or asset level.
4 | 25 | 4.25 | Risk Assessment and Mapping Maturity Timeline | NA | 2025-2027 | Continue partial automation of risk reduction and RSE tools. | RSE tools are currently manually fed in by pre-structured data analysis. In order to update RSE calculation, information needs to be pre-calculated and inputted into the data input sheets for model calculation. In the future, it would be ideal for the dataset to be refreshed and built into a calculated report to feed into the models. This would allow up to date risk analysis, as well as risk reduction and RSE calculation, if various systems of records are connected | No | What automation steps are taken in risk tools (e.g., automated the consolidation of input from various risk models into a central risk database)
4 | 26 | 4.26 | Risk Assessment and Mapping Maturity Timeline | NA | 2025-2027 | Increase granularity of ignition risk reduction models including integration of a full-cycle of inspection data for some assets. | Integration of inspection data for assets means that asset level ignition risk values are determined based on data that includes inspection data specific to individual assets | No | When ignition risk model output is available at the asset level so that inspection data regarding the asset can be updated.
5 | 14 | 5.14 | Situational Awareness | NA | 2020-2022 | Continue deploying weather stations and expand the number of weather variables being measured that impact ignition probability. | Increase the number of weather stations beyond what is currently in the field to 1300. | Yes | We will measure and track the number of incremental weather stations deployed.
5 | 15 | 5.15 | Situational Awareness | NA | 2020-2022 | Continue to increase the geographic granularity of weather prediction. | Increasing the granularity of the weather model, if possible, in the future. The weather model PG&E uses, at 2 x 2 km resolution, is more granular than weather data availble from the federal government and NOAA | No | None. This is explorative in nature.
5 | 16 | 5.16 | Situational Awareness | NA | 2023-2027 | Continue deployment of cameras to cover remaining high-risk areas and evaluate further deployment based on current HFTD maps. | Increase the number of cameras beyond those currently in the field by 135, which will bring lifetime installations up to 468 by EOY 2021. | Yes | We will track number of camera installations weekly/monthly toward the 2021 EOY goal of an additional 135 cameras.
5 | 17 | 5.17 | Situational Awareness | NA | 2023-2027 | Continue to validate POMMS against historical weather data to refine prediction accuracy. | Validation of the POMMS weather model output versus actuals observed from weather stations. This validation will be used to inform future versions of the weather model. | Yes | We will track this via error statistics such as mean absolute error, which measures the errors between model output and actual observed values.
6 | 1 | 6.1 | Grid Design and System Hardening | Community Microgrid Enablement Program | 2030 | • Continue to enhance the CMEP based upon lessons learned from Phase 2. | A new program was adopted by the CPUC in D.20-06-017 and PG&E is currently awaiting CPUC approval of Advice Letter 5918-E concerning implementation. PG&E intends to incorporate lessons learned from early implementations of the program to inform any subsequent request to the CPUC for program changes, also in light of the newly adopted Microgrid Incentive Program in D.21-01-018. | No | PG&E will provide an initial program evaluation of CMEP in the 2023 General Rate Case, which will include an evaluation of the program's design elements such as eligibility requirements, capacity cap, and application process. PG&E will use lessons learned from early implementations to inform any subsequent request to update or enhance the program.
6 | 4 | 6.4 | Grid Design and System Hardening | Grid Hardening | 2027-2029 | • Continue to harden at-risk infrastructure consistent with evolving risk prioritization and strategies. | The target is to continue hardening between 450 and 500 of the highest risk miles annually starting in 2024. | Yes | We will track system hardening miles completed per year.
6 | 5 | 6.5 | Grid Design and System Hardening | Grid Hardening | 2027-2029 | • Increase the application of higher risk reduction measures such as remote grid and undergrounding. | Increase the percentage of undergrounding and removals to 10% of the miles hardened annually. | Yes | Count of remote grid solutions installed, calculation of miles undergrounded for system hardening divided by total miles hardened.
6 | 11 | 6.11 | Grid Design and System Hardening | Grid Hardening | 2030 | • Continue to Harden next highest risk infrastructure consistent with evolving risk prioritization and strategies. | The target is to continue hardening between 450 and 500 of the highest risk miles annually | Yes | We will track system hardening miles completed per year
6 | 14 | 6.14 | Grid Design and System Hardening | Grid Hardening | 2020-2026 | • Continue to harden at-risk infrastructure consistent with evolving risk prioritization and strategies. | The target is to continue hardening between 450 and 500 of the highest risk miles annually, | Yes | We will track system hardening miles completed per year
6 | 17 | 6.17 | Grid Design and System Hardening | Grid Hardening | 2020-2026 | • Identify opportunities to pilot new products or construction methods to reduce cost or increase fire resiliency | Continuous improvement of PG&E's wildfire hardening standards by reviewing industry trends and developments. | No | This will depend on trends and developments in the electric industry. As new products or construction methods become available, and are proven within the industry, PG&E will update its standards to reflect these changes. A benchmark for this is the active monitoring of industry trends and developments.
6 | 33 | 6.33 | Grid Design and System Hardening | Temporary Microgrid – Substation | 2020-2026 | • Continue to design energization plans and install make-ready infrastructure at relevant substations. | As models (such as meteorology and transmission operability) improve, continually analyze 10-year historical PSPS lookback information to identify de-energized substations with high frequency of impact and no other near-term PSPS mitigation solution. Develop energization plans for those substations. Rent or permanently install infrastrucutre to interconnect generation at those locations. | Yes | Number of substations with energization plans developed to support interconnection of temporary generation. Number of substations with temporary or permanent infrastrucutre installed to support the interconnection of temporary or permanent generation.
6 | 34 | 6.34 | Grid Design and System Hardening | Temporary Microgrid – Substation | 2020-2026 | • Continue to convert temporary generation configurations to permanent. | As models (such as meteorology and transmission operability) improve, continually analyze 10-year hisotrical PSPS lookback information to identify de-energized substations with high frequency of impact and no other near-term PSPS mitigation solution. Determine whether a permanent generation solution could support other needs at this substation (e.g., winter storm resiliency). Compare potential permenet generation solutions against cost of energizing the substation with temporary generation over a given time horizon. Run a solicitation for permanent generation solutions at these substations. Partner with appropriate vendors and community leaders in designing any perment substation generation solutions. | Yes | Number of substations analyzed for potential permanent generation solution. Number of substations identified as potentially viable for a permanent generation solution based on results of analytics. Number of locations where a permanent generation solution is pursued based on results of analytics.
6 | 35 | 6.35 | Grid Design and System Hardening | Permanent Microgrids – Substation | 2027-2029 | • Continue to partner with vendors and local communities in solution design. | In locations where possible permanent generation solutions have been identified, partner with vendors and local communities in the site-specific design elements. | Yes | Number of locations where a permanent generation solution is pursued based on results of analytics.Outreach to vendors and local communities.
6 | 36 | 6.36 | Grid Design and System Hardening | Community Microgrid Enablement Program | 2027-2029 | • Continue to enhance the CMEP based upon lessons learned from Phase 1. | A new program was adopted by the CPUC in D.20-06-017 and PG&E is currently awaiting CPUC approval of Advice Letter 5918-E concerning implementation. PG&E intends to incorporate lessons learned from early implementations of the program to inform any subsequent request to the CPUC for program changes, also in light of the newly adopted Microgrid Incentive Program in D.21-01-018. | No | PG&E will provide an initial program evaluation of CMEP in the 2023 General Rate Case, which will include an evaluation of the program's design elements such as eligibility requirements, capacity cap, and application process. PG&E will use lessons learned from early implementations to inform any subsequent request to update or enhance the program.
7 | 1 | 7.1 | Asset Management and Inspections | NA | 2020-2023 | • Increase granularity of asset inventory data to include inspection and repair history. | Moving from multiple platforms to a single platform will increase granularity. Asset data is stored and mainly viewable in separate applications. Asset inventory data is stored and is primarily visible in EDGIS and ETGIS. Most GO 165 inspection records for Distribution (and I think Transmission) are indexed off support structure ID # and stored in SAP. Granularity of the inspection and repair history can be partnered in one platform via Palantir/Foundry. In this platform, pertinent asset data along with inspection and repair history can be viewed along photographs in one repository. | Yes | For each pole or support structure ID# verify that there is an associated Inspect App entry in Foundry. 2021 is the second year of Inspect App implementation so anticipate matching entries in 2021 to be 25-40%. As full cycles of inspections complete by 2025 expect performance to be 95-100%
7 | 2 | 7.2 | Asset Management and Inspections | NA | 2020-2023 | • Increase frequency of condition assessment updates to quarterly | Distribution - As part of GO 165 inspection tags, EC tags are generated for maintenance items. For each EC tag an FDA assestment is performed by inspectors. F stands for Facility, D for Damage, and A for Activity required. PG&E proposes quarterly tracking the quantity of repair and replacing of key facility types. Transmission- condition assessments are already updated weekly (or daily during PSPS events) with latest inspection and repair data in the Transmission OA Model. | Yes | For key Distribution facility types: poles, crossarms, and transformers, provide a quarterly EC tag count of each that needs repair or replacing partnered with key asset parameters such as age and division to assess trends and asset conditions.
7 | 3 | 7.3 | Asset Management and Inspections | NA | 2024-2027 | • Continue refining risk informed inspection protocols. | Distribution - For key asset facility types where high failure trends are more prevalent, incorporate this into risk-based circuit inspection guidance. If there are pockets of increased failure trends, these would be targeted for more inspection scrutiny. Transmission - In addition to what is written above, inspection methodology may also be customized to the trended failure modes for effective inspections. | No | This is not possible yet because quarterly trends for key facility type failures are not routinely generated. We will look into quarterly trends for key facility type failures (WIP effort to routinely generate) as a proxy benchmark.
7 | 4 | 7.4 | Asset Management and Inspections | NA | 2028-2030 | • Increase ability to identify asset problems before they result in failure. | Distribution - Maturity of technology at PG&E is anticipated to enable crews to capture key failure attributes of asset failures. For instance if a cross-arm or transformer fails, little information is currently captured by crews to assess if the failure was a systemic problem or normal wear on an asset. Utilizing the trends enabled by this technology will allow more informed decisions to proactively replace assets prior to failure. This will be especially useful in assessing potential problems with transformers and switches prior to failure. Transmission- Use of threat modeling (using inspection data as one of many inputs - either in engineering or AI-based models) and degradation rate analysis will help pinpoint areas to catch failures before the occur. | Yes | Visbility of EC tags associated with all equipment ID# should be available in Foundry. Expect 90-100% compliance that every EC tag that generates an asset to be replaced by 2028 will have at least a photo of the retired asset along with its original installation date, manufacturer, and mode of failure. Transmission - AI "computer vision" models have been developed to catch some issues within aerial captured photos (e.g. worn C-Hooks)
8 | 13 | 8.13 | Vegetation Management and Inspections | Vegetation Inventory and Inspection Planning | 2020-2026 | • Increase fuel reduction programs and assess the benefits of these efforts. | Increase means to further develop PG&E's new fuel reduction program for implementation in 2021 , as described in Section 7.3.5.5 of the 2021 WMP. | No | PG&E cannot track the progress of this using quantitative data at this time because the framework for fuel reduction work is still being developed. However, it is our goal to use incoming data in 2021 to determine the program's effectiveness and to identify the risk spend efficiency of an effective fuel reduction program.
8 | 14 | 8.14 | Vegetation Management and Inspections | Program Execution | 2020-2026 | • Establish a California-based training program to increase population of trained Pre-Inspectors. | Grow the amount of training courses offered to Pre-inspectors to support certification efforts of PG&E contractors and employees. | Yes | In order to increase the population of trained Pre-Inspectors, PG&E has created the Structured Learning Path ("SLP") and has partnered with a community college to establish a training program designed to provide the skills and knowledge necessary to perform tree crew work safely and competently.
8 | 15 | 8.15 | Vegetation Management and Inspections | Program Execution | 2020-2026 | • Establish a California-based training program to increase population of trained tree crew personnel. | Grow the amount of training courses offered to tree crew personnel to support certification efforts of PG&E contractors and employees. | Yes | In order to increase the population of trained tree crew, PG&E has created the Structured Learning Path ("SLP") and has partnered with a community college to establish a training program designed to provide the skills and knowledge necessary to perform tree crew work safely and competently.
8 | 16 | 8.16 | Vegetation Management and Inspections | Program Execution | 2020-2026 | • Improve routine program administration structure to increase resource efficiency and customer satisfaction. | Improve worker knowledge and qualifications to ensure proper work completion on the first attempt. | Yes | PG&E will track this effort by monitoring work verification inspection pass rates. Pass rates are assessed on a monthly basis.
8 | 17 | 8.17 | Vegetation Management and Inspections | Vegetation Inventory and Inspection Planning | 2027-2029 | • Continue to expand the ROWs of higher risk transmission lines with the goal of increasing separation between vegetation and transmission assets. | Expand VM work around assets in High Fire Threat Districts (HFTD). This includes addressing vegetation that poses a higher potential for wildfire risk in high fire-threat areas by removing vegetation to widen existing 60 kV/70/kV115/kV ET corridors in Tier 2 and Tier 3 HFTD areas. | Yes | We will measure ROW expansion work completed in HFTDs.
8 | 18 | 8.18 | Vegetation Management and Inspections | Program Execution | 2027-2029 | • Continue outreach with communities to educate about the VM Program, with the goal of reducing overall refusals and creating increased partnership on powerline safety and wildfire risk reduction. | Work with the community through outreach programs to build trust in the community for PG&E. Increased or improved community trust will lead to additional partnerships within the community to support powerline safety and wildfire risk reduction. | Yes | Processed refusals obtained from community members will be tracked and evaluated. All community communication will be shared on the PG&E community outreach website for continued awareness, in addition to separate communication via mail and email.
8 | 19 | 8.19 | Vegetation Management and Inspections | Program Execution | 2027-2029 | • Continue to evaluate new technologies for ways to improve efficiency and effectiveness. | Continue means to find additional methods to ensure our vegetation inventory and condition database is advancing along with VM conditions in HFTDs. | Yes | We will measure efficiency and effectiveness of our inventory system by the ability of field employees to quickly utilize mobile devices and software to collect vegetation data that is traceable, verifiiable, accurate, and complete.
9 | 1 | 9.1 | Grid Operations Protocols | PSPS Event Execution | 2020-2025 | • Increase PSPS notifications to greater than 95 percent of customers and virtually 100 percent of known medical baseline customers. | Make additional efforts to deliver PSPS outage notifications to more than 95% of known general customers who are impacted by a PSPS event and close to 100% of known medical baseline customers who are impacted by a PSPS event. | Yes | PG&E aggregates PSPS event notification data at the end of each year. We will review the notification percentage data for general and known medical baseline customers at that time.
9 | 2 | 9.2 | Grid Operations Protocols | PSPS Event Execution | 2020-2025 | • Increase and maintain fleet of 65 exclusive-use helicopters for patrol. | Implement and maintain helicopters which can be avaliable for use during the peak PSPS season to aid in patrols.* *PG&E previously had a goal to increase the size of its helicopter fleet to 65 for patrols only but no longer intends to do so because it is unecessary to increase every year. The current plan is to maintain the previous year's fleet size of 65 and annually evaluate the business needs. | No | PG&E will execute exclusive use contracts for helicopters used for patrols.
9 | 3 | 9.3 | Grid Operations Protocols | PSPS Event Execution | 2026-2028 | • Continue refining use of drones. | Track technology and laws related to drones in order to potentially leverage this technology for patrols during PSPS. We currently do not use drones for PSPS inspections as they require a flight path beyond visual line of sight (BVLOS). Drones are presently used for detailed isolated, not out of visual sight, asset inspections. We will continue to explore BVLOS operations for PSPS and other enterprise initiatives. | No | PG&E has benchmarked with various energy companies as we seek operational experience to develop and implement drone utilization for PSPS. We will monitor our progress as we look into issues like appropriate organizational structures, the use of drones in utility environments to support asset inspections, and the use of drones for PSPS and BVLOS operations. We will use this information to further develop our current and future aviation operations strategy.
9 | 4 | 9.4 | Grid Operations Protocols | PSPS Event Execution | 2029-2030 | • Continue refining use of drones. | Track technology and laws related to drones in order to potentially leverage this technology for patrols during PSPS. We currently do not use drones for PSPS inspections as they require a flight path beyond visual line of sight (BVLOS). Drones are presently used for detailed isolated, not out of visual sight, asset inspections. We will continue to explore BVLOS operations for PSPS and other enterprise initiatives. | No | PG&E has benchmarked with various energy companies as we seek operational experience to develop and implement drone utilization for PSPS. We will monitor our progress as we look into issues like appropriate organizational structures, the use of drones in utility environments to support asset inspections, and the use of drones for PSPS and BVLOS operations. We will use this information to further develop our current and future aviation operations strategy.
9 | 27 | 9.27 | Grid Operations Protocols | Clean Temporary Generation | 2026-2028 | • Continue supporting market development and partnering with clean temporary generation technology vendors. | Develop clear operational and testing criteria; launch diesel alternative temporary generation RFI and solicitation; procure technologies as needed to support generation-based PSPS mitigation workstreams; and test new diesel-alternative temporary generation technologies. | Yes | PG&E will monitor this effort by tracking the number of (1) technologies tested, (2) technologies/vendors contracted, and (3) MWs contracted.
9 | 29 | 9.29 | Grid Operations Protocols | PSPS Event Execution | 2026-2028 | • Continue Identifying program enhancements based on after-action reviews from exercises and events. | Use our continuous improvement process to identify opportunities to improve PSPS event execution. The continuous improvement process starts with the completion of the post-incident hot wash to identify strengths and opportunities for improvement. Opportunities are then formated into corrective actions. An event specfic Corrective Action Program (CAP) item is created and the respective corrective actions are included with specific action owners and due dates. These corrective actions are then tracked by our CAP team through to completion. A quality check on the completion is also completed to validate the corrective action has been addressed. | Yes | Corrective actions confirmed to be opportunities are logged through CAP with assigned due dates and owners. These actions are managed with visibility in the CAP application.
9 | 31 | 9.31 | Grid Operations Protocols | PSPS Event Execution | 2026-2028 | • Continue refining PSPS restoration collateral (segment guides, maps). | Update segment guides used for restoration as system changes occur and enhance GIS data to improve mapping capabilities. | No | System changes are incorporated into PSPS segment guides and maps as part of the mapping process. PSPS map creation has been automated based on data pulled from the segment guides.
9 | 32 | 9.32 | Grid Operations Protocols | PSPS Event Execution | 2026-2028 | • Continue tracking and validating restoration timeliness performance, identify constraints, and develop solutions. | Track restoration progress in PSPS events and identify opportunities for enhancements in restoration and implement improvements. Restoration times are tracked for each PSPS event at the circuit, subcircuit, and customer level. | Yes | Internal PSPS data management systems (Foundry) is used to track data for PSPS event restoration for reporting purposes.
9 | 33 | 9.33 | Grid Operations Protocols | PSPS Event Execution | 2026-2028 | • Continue ETOR refinement processes. | Refine the processes used for updating estimated and updated ETORs in the PSPS process. | No | Consistent with 2020 ETOR improvement planning, 2021 ETOR improvements are led by a Project Manager in EP&R Field Operations. These forecasted improvements were created based on an ETOR analysis of 2020 PSPS events. Solutions for these improvements will be incorporated into process documents and training upon finalization of the improvements.
9 | 36 | 9.36 | Grid Operations Protocols | PSPS Event Execution | 2026-2028 | • Continue updating training collateral based on after-action reviews from exercises and events. | Refine training to improve clarity for EOC roles that contribute to executing PSPS events. After action reviews (AAR) are completed after each PSPS event to identify new improvement opportunities. The AARs are led by the Emergency Preparedness and Response team. | No | Training documents produced annually for EOC roles and updated for the season and for in-season changes when required.
9 | 37 | 9.37 | Grid Operations Protocols | PSPS Event Execution | 2029-2030 | • Continue identifying program enhancements based on after-action reviews from exercises and events. | Use our continuous improvement process to identify opportunities to improve PSPS event execution. The continuous improvement process starts with the completion of the post-incident hot wash to identify strengths and opportunities for improvement. Opportunities are then formated into corrective actions. An event specfic CAP item is created and the respective corrective actions are included with specific action owners and due dates. These corrective actions are then tracked by our CAP team through to completion. A quality check on the completion is also completed to validate the corrective action has been addressed. | Yes | Corrective actions confirmed to be opportunities are logged through CAP with assigned due dates and owners. These actions are managed with visibility in the CAP application.
9 | 38 | 9.38 | Grid Operations Protocols | PSPS Event Execution | 2029-2030 | • Continue refining PSPS restoration collateral (e.g., segment guides, maps). | Update segment guides used for restoration as system changes occur and enhance GIS data to improve mapping capabilities. | No | System changes are incorporated into PSPS segment guides and maps as part of the mapping process. PSPS map creation has been automated based on data pulled from the segment guides
9 | 39 | 9.39 | Grid Operations Protocols | PSPS Event Execution | 2029-2030 | • Continue ETOR refinement processes. | Refine the processes used for updating estimated and updated ETORs in the PSPS process | No | Consistent with 2020 ETOR improvement planning, 2021 ETOR improvements are led by a Project Manager in EP&R Field Operations. These forecasted improvements were created based on an ETOR analysis of 2020 PSPS events. Solutions for these improvements will be incorporated into process documents and training upon finalization of the improvements.
9 | 40 | 9.40 | Grid Operations Protocols | PSPS Event Execution | 2029-2030 | • Continue updating training collateral based on after-action reviews from exercises and events. | Refine training to improve clarity for EOC roles that contribute to executing PSPS events. After action reviews (AAR) are completed after each PSPS event to identify new improvement opportunities. The AARs are led by the Emergency Preparedness and Response team. | No | Training documents are produced annually for EOC roles and updated for the season and for in-season changes when required.
10 | 1 | 10.1 | Data Governance | NA | 2020-2024 | • Continue execution of improvements to data quality and related business processes, including: corrections to customer contact information, grid topology, and asset information. | Develop EO PMO to intake, investigate, resolve/triage and measure data quality issues and related business processes across EO. | No | PG&E will track this effort by documenting when the following events take place: Development of EO Data Quality PMO Charter, development of procedures for data quality monitoring, evaluation and prioritization, creation or adoption of tools to enable data quality management, and development of KPIs for data quality measurement
10 | 2 | 10.2 | Data Governance | NA | 2025-2027 | • Continue to grow and enable a Data Stewards community, including establishing a board of Data Owners and outlining the board’s role in data governance and retention decisions. | Create a forum of data quality and metadata stewards who can collaborate to share process knowledge, data quality functional expertise, and address the fundamental causes for data quality issues. | No | PG&E will track this by documenting when the following events take place: development of EO Stewardship Program charter with roles and responsibilities defined, development of training and onboarding materials for Data Stewards, delivery of training to first cohort of Data Stewards, and development of a full roster of EO Data Stewards and commitments to support data quality efforts.
10 | 3 | 10.3 | Data Governance | NA | 2025-2027 | • Execute data architecture activities, including the rationalization and retirement of databases to increase database integration. | Identify and integrate critical data not currently stored Tier 1 or Tier 2 systems of record into these systems to improve controls, consistency, and access to data. | No | We will inventory critical business terms and the associated data systems and data elements. PG&E will then track the number of Tier 3 data systems and the associated data elements that are migrated to Tier 2 and Tier 3 systems.
10 | 4 | 10.4 | Data Governance | NA | 2025-2027 | • Continue to improve and document business processes that generate data. | Annual aligment with EO leadership to review, revise, and approve critical business processes. | No | We have an inventory of critical business processes. We will track the number of processes reviewed, revised, and approved each year as we seek to improve and document business processes that generate data.
10 | 5 | 10.5 | Data Governance | NA | 2028-2030 | • Develop data access Application Programming Interfaces to enable increased partnerships and transparency with researchers, regulators, and state and local governments. | Develop a portal to share data regarding Microgrids as required by the microgrid OIR, and create a way of sharing PSPS historical and planning data with customers and other external stakeholders. This will provide transparency for our stakeholders and allow them to work more efficiently with PG&E or to make better decisions. | No | PG&E will establish an external data sharing product road map. For individual projects/products, we will track according to the specific project plans or the advice letter filed in response to the Microgrid OIR.
11 | 1 | 11.1 | Resource Allocation Methodology | NA | 2020-2023 | • Increase granularity of scenario projections and RSE down to the circuit level. | Risk analysis to be aggregated to the circuit level based on the Wildfire Distribution Risk Model results. This is to be developed in 2021. | No | Display circuit level risk scores with cost projections to represent circuit level RSEs
11 | 2 | 11.2 | Resource Allocation Methodology | NA | 2020-2023 | • Increase the detail and geographic granularity of RSE down to the circuit level. | Risk analysis to be aggregated to the circuit level based on the Wildfire Distribution Risk Model results. This is to be developed in 2021. | No | Display circuit level risk scores with cost projections to represent circuit level RSEs
11 | 11 | 11.11 | Resource Allocation Methodology | NA | 2028-2030 | • Continue improving end-to-end work management processes. | PG&E will implement the EO E2E Work Management Process Improvement Program. This program will streamline both upstream and downstream processes to ensure alignment and visibility across seven key process areas: Plan, Inspect, Design & Estimate, Dependency Management, Schedule, Execute, and Close. | No | PG&E will track the progress by tracking key milestones of the E2E Work Management Process Improvement Program. These milestones include completion of current state process mapping, future state process mapping, technology portfolio management integration, process piloting, initial process rollout, and post-deployment adoption and support.
12 | 1 | 12.1 | Emergency Planning and Preparedness | NA | 2023-2025 | • Continue incorporating enhancements based on after-action review, exercises, and event response. | Use our continuous improvement process to identify opportunities to improve PSPS event execution. The continuous improvement process starts with the completion of the post-incident hot wash to identify strengths and opportunities for improvement. Opportunities are then formated into corrective actions. An event specfic CAP item is created and the respective corrective actions are included with specific action owners and due dates. These corrective actions are then tracked by our CAP team through to completion. A quality check on the completion is also completed to validate the corrective action has been addressed. | No | Corrective actions confirmed to be opportunities are logged through CAP with assigned due dates and owners. These actions are managed with visibility in the CAP application.
12 | 2 | 12.2 | Emergency Planning and Preparedness | NA | 2026-2030 | • Continue to integrate the WMP with disaster and emergency plans. | As WMP initiatives are completed and change our emergency response processes, situational awareness, or other tools, we will operationalize them in the Community Emergency Response Plan or its annexes, as well as PG&E's standards or procedures. | No | We will track through an annual WMP initiative review or develop a process to tag initiatives that should be operationalized in our emergency response plans.
12 | 3 | 12.3 | Emergency Planning and Preparedness | NA | 2026-2030 | • Continue incorporating enhancements based on after-action review, exercises, and event response. | Use our continuous improvement process to identify opportunities to improve PSPS event execution. The continuous improvement process starts with the completion of the post incident hot wash to identify strengths and opportunities for improvement. Opportunities are then formated into corrective actions. An Event specfic CAP item is created and the respective corrective actions are included with specific action owners and due dates. These corrective actions are then tracked by our CAP team thru to completion and also perform a quality check on the completion to validate the corrective action has been addressed. | No | Corrective actions confirmed to be opportunities are logged through the Corrective Action Program with assigned due dates and owners. These actions are managed with visibility in the CAP application.
13 | 1 | 13.1 | Stakeholder Cooperation and Community Engagement | NA | 2020-2022 | • Increase coordination with fire suppression crews including fire detection and fire propagation. | PG&E will continue to work closely with local and state agencies as appropriate and look for opportunities to support when invited to do so. | No | This is not quantitative. PG&E will lend aid when invited to do so by the authority having jurisdiction.
13 | 2 | 13.2 | Stakeholder Cooperation and Community Engagement | NA | 2023-2026 | • Continue to gather and incorporate feedback from community partners and first responders. | Following key external engagement activities, we summarize the agency’s feedback and identify action items. When action items are identified and logged in meeting summary sheets, we assign an internal owner to drive the action to resolution, and we communicate the status back to agencies. PG&E also meets internally to discuss the agency’s feedback and determine feasibility. If deemed feasible and appropriate, PG&E incorporates the feedback into processes and procedures. | No | We track the feedback and action items provided by the agency. Each initiative is given an internal owner to drive the action.
13 | 3 | 13.3 | Stakeholder Cooperation and Community Engagement | NA | 2027-2030 | • Continue to improve stakeholders’ outreach and education efforts. | Action items captured from key agency engagements related to agency outreach and education for their communities are identified and tracked in meeting summary sheets and resolved in the manner described above. Any follow-up needed is performed in subsequent recurring meetings or on an ad-hoc basis if time-sensitive. | No | We track the feedback and action items provided by the agency. Each initiative is given an internal owner to drive the action.

## WSD Full Table (hidden)
[12 empty] | Responses to B-24 - Progress Tracking |  |  |  | FOR PMO USE >>>
| Table # | ID | Line ID | Table Name | Sub-Category (if applicable) | Section Responsible Director - 2021 | Section Lead Drafter - 2021 | Addt'l SME - 2021 | Contains "Continue" or "Increase" | Year Range | Risk Assessment and Mapping Maturity Timeline | Define what "continue" or "increase" means | Is the benchmark quantitative? (Yes/No) | Benchmark or Tracking Method | NOTES/SUGGESTIONS | STATUS | SME Response / Drafting in Progress | SME First Draft Submitted | PMO QC1 Approval | Legal Approval | PG&E Director Approval | Approval (1/2) | Approval (2/2) | Final Draft Completed
| 4 | 1 | 4.1 | Risk Assessment and Mapping Maturity Timeline | NA |  |  |  | FALSE | 2020-2024 | Incorporate future climate change into risk models. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 4 | 2 | 4.2 | Risk Assessment and Mapping Maturity Timeline | NA |  |  |  | FALSE | 2020-2024 | Independent expert assessment of risk reduction impact. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 4 | 3 | 4.3 | Risk Assessment and Mapping Maturity Timeline | NA |  |  |  | FALSE | 2020-2024 | Explore climate factors that affect risk over time into risk models (i.e., sea-level rise, extreme heat conditions, erratic wind patterns). | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 4 | 4 | 4.4 | Risk Assessment and Mapping Maturity Timeline | NA |  |  |  | FALSE | 2020-2024 | Partial automation of risk assessment processes (i.e., automation of data refreshes for risk monitoring). | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 4 | 5 | 4.5 | Risk Assessment and Mapping Maturity Timeline | NA |  |  |  | FALSE | 2020-2024 | Incorporate near-miss data (e.g., non-reportable ignitions, unplanned outages, electric faults), and pilot technologies to support utilizing this information. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 4 | 6 | 4.6 | Risk Assessment and Mapping Maturity Timeline | NA |  |  |  | FALSE | 2025-2027 | Full automation of current risk assessment processes and tools, including risk performance (i.e., projected risk vs realized risk) | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 4 | 7 | 4.7 | Risk Assessment and Mapping Maturity Timeline | NA |  |  |  | FALSE | 2025-2027 | Risk reduction impacts measured by models, with confidence intervals, and reviewed by independent experts. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 4 | 8 | 4.8 | Risk Assessment and Mapping Maturity Timeline | NA |  |  |  | FALSE | 2025-2027 | Incorporate long-term climate factors (dependent on climate modeling maturity) into risk models. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 4 | 9 | 4.9 | Risk Assessment and Mapping Maturity Timeline | NA |  |  |  | FALSE | 2025-2027 | Facilitate information sharing for intra- and inter-industry risk assessment/reduction methodology developments. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 4 | 10 | 4.10 | Risk Assessment and Mapping Maturity Timeline | NA |  |  |  | FALSE | 2025-2027 | Enable forward predictive ignition risk models, including integration of more robust consequence modeling (i.e., fire spread at varying hours). | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 4 | 11 | 4.11 | Risk Assessment and Mapping Maturity Timeline | NA |  |  |  | FALSE | 2025-2027 | Incorporate pilot technologies’ effectiveness for impacting near miss and ignition incidents. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 4 | 12 | 4.12 | Risk Assessment and Mapping Maturity Timeline | NA |  |  |  | FALSE | 2028-2030 | Incorporate industry and research advances in risk modeling, wildfire science and geographic risk mapping as learnings are identified. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 4 | 13 | 4.13 | Risk Assessment and Mapping Maturity Timeline | NA |  |  |  | FALSE | 2028-2030 | Leverage real time data and specific asset failure modes as modeling inputs. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 4 | 14 | 4.14 | Risk Assessment and Mapping Maturity Timeline | NA |  |  |  | FALSE | 2028-2030 | Expand consequence modeling to include factors such as population, buildings, and environmental considerations. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 4 | 15 | 4.15 | Risk Assessment and Mapping Maturity Timeline | NA |  |  |  | FALSE | 2028-2030 | Incorporate independent third-party assessment of risk modeling methods and scenarios. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 4 | 16 | 4.16 | Risk Assessment and Mapping Maturity Timeline | NA |  |  |  | FALSE | 2028-2030 | Improve asset data collection practices (e.g., asset condition, failure modes) and consider granular wind patterns and temperature effects. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 4 | 17 | 4.17 | Risk Assessment and Mapping Maturity Timeline | NA |  |  |  | FALSE | 2028-2030 | Automate the flow of data inputs and information between analytical tools and platforms. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 4 | 18 | 4.18 | Risk Assessment and Mapping Maturity Timeline | NA |  |  |  | FALSE | 2028-2030 | Full automation of current risk level, reduction, and RSE tools. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 4 | 19 | 4.19 | Risk Assessment and Mapping Maturity Timeline | NA |  |  |  | FALSE | 2028-2030 | Climate integration fully developed into real-time and long-term asset planning and design standards. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 4 | 20 | 4.20 | Risk Assessment and Mapping Maturity Timeline | NA |  |  |  | FALSE | 2028-2030 | Real time reporting of risk performance. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 4 | 21 | 4.21 | Risk Assessment and Mapping Maturity Timeline | NA |  |  |  | FALSE | 2028-2030 | Develop “real-time” risk models that incorporate condition of asset, environmental factors, weather conditions, and potential fire spread. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 4 | 22 | 4.22 | Risk Assessment and Mapping Maturity Timeline | NA |  |  |  | FALSE | 2028-2030 | Integration of tools for risk models and levels of risk actively allow for real-time situational awareness shared with stakeholder agencies and communities. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 4 | 23 | 4.23 | Risk Assessment and Mapping Maturity Timeline | NA | Paul McGregor | Jon Eric Thalman |  | TRUE | 2020-2024 | Increase granularity of ignition risk reduction to below the circuit level. | "Increasing the granularity of ignition risk reduction to below the circuit level" means transitioning the granularity of ignition risk reduction to the circuit segment or individual asset level. | No | Assessed level of ignition risk reduction (e.g., circuit segment, entire circuit, or at some other level |  |  | Yes | Yes | Yes | No | No | No | No | No
| 4 | 24 | 4.24 | Risk Assessment and Mapping Maturity Timeline | NA | Paul McGregor | Jon Eric Thalman |  | TRUE | 2020-2024 | Increase granularity of ignition risk reduction to below the circuit level, including integration of fire spread consequences. | [5 empty] | No | No | Pending | No | No | No | No | No
| 4 | 25 | 4.25 | Risk Assessment and Mapping Maturity Timeline | NA | Paul McGregor | Benson Wong |  | TRUE | 2025-2027 | Continue partial automation of risk reduction and RSE tools. |  | No | What automation steps are taken in risk tools (e.g., automated the consolidation of input from various risk models into a central risk database) | is there a number? Evaluate the effectiveness and needed based on continued reduction in psps scope size |  | No | No | Pending | No | No | No | No | No
| 4 | 26 | 4.26 | Risk Assessment and Mapping Maturity Timeline | NA | Paul McGregor | Jon Eric Thalman |  | TRUE | 2025-2027 | Increase granularity of ignition risk reduction models including integration of a full-cycle of inspection data for some assets. | [5 empty] | No | No | Pending | No | No | No | No | No
| 5 | 1 | 5.1 | Situational Awareness | NA |  |  |  | FALSE | 2020-2022 | Deploy cameras to cover approximately 90 percent of the high fire-risk areas. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 5 | 2 | 5.2 | Situational Awareness | NA |  |  |  | FALSE | 2020-2022 | Complete the evaluation of the usefulness of satellite data in situational awareness. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 5 | 3 | 5.3 | Situational Awareness | NA |  |  |  | FALSE | 2020-2022 | Finalize validation of the operational application of the PG&E Operational Mesoscale Modeling System (POMMS) high-resolution weather model. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 5 | 4 | 5.4 | Situational Awareness | NA |  |  |  | FALSE | 2020-2022 | Partially automate the forecasting processes. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 5 | 5 | 5.5 | Situational Awareness | NA |  |  |  | FALSE | 2020-2022 | Deploy Smart Meter devices for enhanced wire down detection in HFTD. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 5 | 6 | 5.6 | Situational Awareness | NA |  |  |  | FALSE | 2023-2027 | Evaluate weather station needs to support desired forecasting granularity and deploy additional stations as needed. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 5 | 7 | 5.7 | Situational Awareness | NA |  |  |  | FALSE | 2023-2027 | Evaluate results of automation of forecasting process and expand as appropriate. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 5 | 8 | 5.8 | Situational Awareness | NA |  |  |  | FALSE | 2023-2027 | Complete evaluation of enhanced wire down detection to guide additional Smart Meter deployment. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 5 | 9 | 5.9 | Situational Awareness | NA |  |  |  | FALSE | 2028-2030 | Fully automate forecasting process, subject to favorable results in Phase II, supported by an extensive camera and weather station network. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 5 | 10 | 5.10 | Situational Awareness | NA |  |  |  | FALSE | 2028-2030 | Achieve state of the art level in geographic granularity of weather prediction. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 5 | 11 | 5.11 | Situational Awareness | NA |  |  |  | FALSE | 2028-2030 | Incorporate external sources and partner with academic institutions to support achieving the desired level of automation, forecasting granularity and forecasting accuracy. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 5 | 12 | 5.12 | Situational Awareness | NA |  |  |  | FALSE | 2028-2030 | Further automate fire detection via intelligence from our extensive network of cameras and weather stations. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 5 | 13 | 5.13 | Situational Awareness | NA |  |  |  | FALSE | 2028-2030 | Complete deployment of Smart Meter devices for enhanced wire down detection. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 5 | 14 | 5.14 | Situational Awareness | NA | Rod Robinson | Scott Strenfel |  | TRUE | 2020-2022 | Continue deploying weather stations and expand the number of weather variables being measured that impact ignition probability. | "Continue deploying weather stations" means to increase the number of weather stations beyond what is currently in the field to XY. | Yes | Number of incremental weather stations deployed | Need to complete response |  | Yes | No | Pending | No | No | No | No | No
| 5 | 15 | 5.15 | Situational Awareness | NA | Rod Robinson | Scott Strenfel |  | TRUE | 2020-2022 | Continue to increase the geographic granularity of weather prediction. | [5 empty] | No | No | Pending | No | No | No | No | No
| 5 | 16 | 5.16 | Situational Awareness | NA | Rod Robinson | Scott Strenfel |  | TRUE | 2023-2027 | Continue deployment of cameras to cover remaining high-risk areas and evaluate further deployment based on current HFTD maps. | [5 empty] | No | No | Pending | No | No | No | No | No
| 5 | 17 | 5.17 | Situational Awareness | NA | Rod Robinson | Scott Strenfel |  | TRUE | 2023-2027 | Continue to validate POMMS against historical weather data to refine prediction accuracy. | [5 empty] | No | No | Pending | No | No | No | No | No
| 6 | 1 | 6.1 | Grid Design and System Hardening | Remote Grid | Jan Berman | Molly Hoyt |  | TRUE | 2030 | • Continue to enhance the CMEP based upon lessons learned from Phase 2. | As a new program adopted in D.20-06-017 and awaiting CPUC approval of AL 5918-E, PG&E intends to incorporate lessons learned from early implementations of the program to inform any subsequent request to the CPUC for program changes, also in light of the newly adopted Microgrid Incentive Program in D.21-01-018. | No | PG&E may file a subsequent request to the CPUC for enhancements to the CMEP. |  |  | Yes | Yes | Pending | No | No | No | No | No
| 6 | 2 | 6.2 | Grid Design and System Hardening | Remote Grid |  |  |  | FALSE | 2020-2026 | • Pilot remote grids to develop a standardized product for installation, operations, and maintenance. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 6 | 3 | 6.3 | Grid Design and System Hardening | Remote Grid |  |  |  | FALSE | 2020-2026 | • Formalize remote grid site selection framework for future opportunities. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 6 | 4 | 6.4 | Grid Design and System Hardening | Grid Hardening | Jeff Borders | Brad Koelling |  | TRUE | 2027-2029 | • Continue to harden at-risk infrastructure consistent with evolving risk prioritization and strategies. | 2021-2023 target is to harden 1,127 miles of the high risk miles (as defined in 7.3.3.17.1) | Yes | Miles completed per year | Wrong timeframe - should list the 450 to 500 miles per year after 2024? |  | Yes | Yes | No | No | No | No | No | No
| 6 | 5 | 6.5 | Grid Design and System Hardening | Grid Hardening | Jeff Borders | Brad Koelling |  | TRUE | 2027-2029 | • Increase the application of higher risk reduction measures such as remote grid and undergrounding. | Continuous improvement of the wildfire hardening standard | No | Document changes to the standards associated with Tier 2 and Tier 3 construction. | How to achieve these increases? Current initiatives in place? New technologies to explore? |  | Yes | Yes | No | No | No | No | No | No
| 6 | 6 | 6.6 | Grid Design and System Hardening | Permanent Microgrids – Substation |  |  |  | FALSE | 2020-2026 | • Advance framework for determining which substations are best suited to leverage permanent generation in support of cost-effective PSPS mitigation. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 6 | 7 | 6.7 | Grid Design and System Hardening | Permanent Microgrids – Substation |  |  |  | FALSE | 2020-2026 | • Test clean permanent generation technologies in controlled and field environment and work with vendors to address any operational concerns and ensure scalability of technology and any fueling/refueling logistics. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 6 | 8 | 6.8 | Grid Design and System Hardening | Permanent Microgrids – Substation |  |  |  | FALSE | 2020-2026 | • Develop best practices for designing multi-faceted solutions that pair permanent in front of the meter generation with other resources (e.g., demand response (DR), behind-the-meter (BTM) resources, etc.). | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 6 | 9 | 6.9 | Grid Design and System Hardening | Permanent Microgrids – Substation |  |  |  | FALSE | 2020-2026 | • Partner with relevant external stakeholders to ensure envisioned solutions meet local communities' needs. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 6 | 10 | 6.10 | Grid Design and System Hardening | Community Microgrid Enablement Program (CMEP) |  |  |  | FALSE | 2020-2026 | • Develop and implement program framework based on Microgrid Order Instituting Rulemaking (OIR) Phase 2 decision. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 6 | 11 | 6.11 | Grid Design and System Hardening | Grid Hardening | Jeff Borders | Brad Koelling |  | TRUE | 2030 | • Continue to Harden next highest risk infrastructure consistent with evolving risk prioritization and strategies. | Duplicate |  |  |  |  | Yes | Yes | No | No | No | No | No | No
| 6 | 12 | 6.12 | Grid Design and System Hardening | Grid Hardening |  |  |  | FALSE | 2020-2026 | • Further development of hardening strategies to support PSPS, Fire Rebuild, deteriorated conductor, and other work optimization opportunities. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 6 | 13 | 6.13 | Grid Design and System Hardening | Grid Hardening |  |  |  | FALSE | 2020-2026 | • Monitor and assess system performance once hardened to help inform future scoping decisions. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 6 | 14 | 6.14 | Grid Design and System Hardening | Grid Hardening | Jeff Borders | Brad Koelling |  | TRUE | 2020-2026 | • Continue to harden at-risk infrastructure consistent with evolving risk prioritization and strategies. | Increase the percentage of undergrounding and removals to 10% of the miles hardened in 2021-2023; install remote grid solutions in 2021-2023. | Yes | Count of remote grid solutions installed, calculation of miles undergrounded for system hardening divided by total miles hardened. |  |  | Yes | Yes | Pending | No | No | No | No | No
| 6 | 15 | 6.15 | Grid Design and System Hardening | Remote Grid |  |  |  | FALSE | 2027-2029 | • Full-scale implementation and operations of remote grids based upon site selection framework. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 6 | 16 | 6.16 | Grid Design and System Hardening | Permanent Microgrids – Substation |  |  |  | FALSE | 2027-2029 | • Complete construction of multiple permanent generation solutions at relevant substations. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 6 | 17 | 6.17 | Grid Design and System Hardening | Grid Hardening | Jeff Borders | Brad Koelling |  | TRUE | 2020-2026 | • Identify opportunities to pilot new products or construction methods to reduce cost or increase fire resiliency | Duplicate |  |  |  |  | Yes | Yes | Pending | No | No | No | No | No
| 6 | 18 | 6.18 | Grid Design and System Hardening | Permanent Microgrids – Substation |  |  |  | FALSE | 2027-2029 | • Scale penetration of clean technologies in permanent generation portfolio. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 6 | 19 | 6.19 | Grid Design and System Hardening | Grid Hardening |  |  |  | FALSE | 2027-2029 | • Optimize opportunities with other programs to align system hardening with programs such as reliability and capacity. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 6 | 20 | 6.20 | Grid Design and System Hardening | Grid Hardening |  |  |  | FALSE | 2027-2029 | • Incorporate hardened system performance with weather data to inform design decisions and standard design requirements. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 6 | 21 | 6.21 | Grid Design and System Hardening | Grid Hardening |  |  |  | FALSE | 2027-2029 | • Develop criteria for alternate hardening levels to become more targeted in wildfire risk reduction measures. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 6 | 22 | 6.22 | Grid Design and System Hardening | Remote Grid |  |  |  | FALSE | 2030 | • Enhance remote grid capabilities based upon technology innovations and cost reductions. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 6 | 23 | 6.23 | Grid Design and System Hardening | Remote Grid |  |  |  | FALSE | 2030 | • Community Microgrid Enablement Program | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 6 | 24 | 6.24 | Grid Design and System Hardening | Remote Grid |  |  |  | FALSE | 2030 | • Deploy microgrids and back-up power solutions where appropriate. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 6 | 25 | 6.25 | Grid Design and System Hardening | Remote Grid |  |  |  | FALSE | 2030 | • Leverage resilience planning criterion to optimize mitigation measures (e.g., grid hardening, non-wires alternatives). | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 6 | 26 | 6.26 | Grid Design and System Hardening | Remote Grid |  |  |  | FALSE | 2030 | • Deploy innovations in engineering and protection for overhead electrical infrastructure. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 6 | 27 | 6.27 | Grid Design and System Hardening | Grid Hardening |  |  |  | FALSE | 2030 | • Capture, analyze, and use data on asset condition and the interactions between assets and vegetation to inform long-term asset management approaches. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 6 | 28 | 6.28 | Grid Design and System Hardening | Grid Hardening |  |  |  | FALSE | 2030 | • Complete hardening of highest risk distribution circuits and eliminate all non-exempt equipment. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 6 | 29 | 6.29 | Grid Design and System Hardening | Grid Hardening |  |  |  | FALSE | 2030 | • Improve material and design standards based on risk modeling. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 6 | 30 | 6.30 | Grid Design and System Hardening | Grid Hardening |  |  |  | FALSE | 2030 | • Operationalize asset condition information by improving field tools and resources. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 6 | 31 | 6.31 | Grid Design and System Hardening | Grid Hardening |  |  |  | FALSE | 2030 | • Test and deploy innovative technologies to reduce ignition risk | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 6 | 32 | 6.32 | Grid Design and System Hardening | Grid Hardening |  |  |  | FALSE | 2030 | • Develop a robust field scoping process for all work done in HFTD areas, not just system hardening, to maximize fire resiliency effectiveness of all maintenance and asset work in HFTDs. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 6 | 33 | 6.33 | Grid Design and System Hardening | Temporary Microgrid – Substation | Quinn Nakayama | Claire Halbrook |  | TRUE | 2020-2026 | • Continue to design energization plans and install make-ready infrastructure at relevant substations. | [5 empty] | No | No | Pending | No | No | No | No | No
| 6 | 34 | 6.34 | Grid Design and System Hardening | Temporary Microgrid – Substation | Quinn Nakayama | Claire Halbrook |  | TRUE | 2020-2026 | • Continue to convert temporary generation configurations to permanent. | [5 empty] | No | No | Pending | No | No | No | No | No
| 6 | 35 | 6.35 | Grid Design and System Hardening | Permanent Microgrids – Substation | Quinn Nakayama | Claire Halbrook |  | TRUE | 2027-2029 | • Continue to partner with vendors and local communities in solution design. | [5 empty] | No | No | Pending | No | No | No | No | No
| 6 | 36 | 6.36 | Grid Design and System Hardening | Community Microgrid Enablement Program | Quinn Nakayama | Claire Halbrook |  | TRUE | 2027-2029 | • Continue to enhance the CMEP based upon lessons learned from Phase 1. | [5 empty] | No | No | Pending | No | No | No | No | No
| 7 | 1 | 7.1 | Asset Management and Inspections | NA | Jeff Borders / Maria Ly | Jeff Thomas Michelle Sakamoto |  | TRUE | 2020-2023 | • Increase granularity of asset inventory data to include inspection and repair history. | Moving from multiple platforms to a single platform will increase granularity. Asset data is stored and mainly viewable in separate applications. Asset inventory data is stored and is primarily visible in EDGIS and ETGIS. Most GO 165 inspection records for Distribution (and I think Transmission) are indexed off support structure ID # and stored in SAP. Granularity of the inspection and repair history can be partnered in one platform via Palantir/Foundry. In this platform, pertinent asset data along with inspection and repair history can be viewed along photographs in one repository. | Yes | For each pole or support structure ID# verify that there is an associated Inspect Ap entry in Foundry. 2021 is the second year of Inspect Ap implementation so anticipate matching entries in 2021 to be 25-40%. As full cycles of inspections complete by 2025 expect performance to be 95-100% |  |  | Yes | Yes | Yes | No | No | No | No | No
| 7 | 2 | 7.2 | Asset Management and Inspections | NA | Jeff Borders / Maria Ly | Jeff Thomas Michelle Sakamoto |  | TRUE | 2020-2023 | • Increase frequency of condition assessment updates to quarterly | As part of GO 165 inspection tags, EC tags are generated for maintenance items. For each EC tag an FDA assestment is performed by inspectors. F stands for Facility, D for Damage, and A for Activity required. PG&E proposes quarterly tracking the quantity of repair and replacing of key facility types. | Yes | For key Distribution facility types: poles, crossarms, and transformers, provide a quarterly EC tag count of each that needs repair or replacing partnered with key asset parameters such as age and division to assess trends and asset conditions | same as above, but latter years. Don't know if have different benchmark |  | Yes | Yes | Yes | No | No | No | No | No
| 7 | 3 | 7.3 | Asset Management and Inspections | NA | Jeff Borders / Maria Ly | Jeff Thomas Michelle Sakamoto |  | TRUE | 2024-2027 | • Continue refining risk informed inspection protocols. | For key asset facility types where high failure trends are more prevalent, incorporate this into risk-based circuit inspection guidance. If there are pockets of increased failure trends, these would be targeted for more inspection scrutiny. | No | This is not possible yet because quarterly trends for key facility type failures are not routinely generated yet. | Proposed benchmarks response: Quarterly trends for key facility type failures (WIP effort to routinely generate) |  | Yes | Yes | Pending | No | No | No | No | No
| 7 | 4 | 7.4 | Asset Management and Inspections | NA | Jeff Borders / Maria Ly | Jeff Thomas Michelle Sakamoto |  | TRUE | 2028-2030 | • Increase ability to identify asset problems before they result in failure. | Maturity of technology at PG&E is anticipated to enable crews to capture key failure attributes of asset failures. For instance if a cross-arm or transformer fails, little information is currently captured by crews to assess if the failure was a systemic problem or normal wear on an asset. Utilizing the trends enabled by this technology will allow more informed decisions to proactively replace assets prior to failure. This will be especially useful in assessing potential problems with transformers and switches prior to failure. | Yes | Visbility of EC tags associated with all euipment ID# should be available in Foundry. Expect 90-100% compliance that every EC tag that generates an asset to be replaced by 2028 will have at least a photo of the retired asset along with its original installation date, manufacturer, and mode of failure. |  |  | Yes | Yes | Yes | No | No | No | No | No
| 7 | 5 | 7.5 | Asset Management and Inspections | NA |  |  |  | FALSE | 2020-2023 | • Move all patrol and inspection activities to digital data platforms. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 7 | 6 | 7.6 | Asset Management and Inspections | NA |  |  |  | FALSE | 2020-2023 | • Evaluate consolidation of distribution and transmission inspection tools, methods, and personnel. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 7 | 7 | 7.7 | Asset Management and Inspections | NA |  |  |  | FALSE | 2020-2023 | • Move towards risk informed inspection protocols. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 7 | 8 | 7.8 | Asset Management and Inspections | NA |  |  |  | FALSE | 2024-2027 | • Mine inspection data to better target at-risk assets. | Maturity of technology at PG&E is anticipated to enable crews to capture key failure attributes of asset failures. For instance if a cross-arm or transformer fails, little information is currently captured by crews to assess if the failure was a systemic problem or normal wear on an asset. Utilizing the trends enabled by this technology will allow more informed decisions to proactively replace assets prior to failure. This will be especially useful in assessing potential problems with transformers and switches prior to failure. | yes | Visbility of EC tags associated with all euipment ID# should be available in Foundry. Expect 90-100% compliance that every EC tag that generates an asset to be replaced by 2028 will have at least a photo of the retired asset along with its original installation date, manufacturer, and mode of failure. |  |  | NA | NA | NA | NA | NA | NA | NA | NA
| 7 | 9 | 7.9 | Asset Management and Inspections | NA |  |  |  | FALSE | 2024-2027 | • Develop a more comprehensive list of asset failure modes. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 7 | 10 | 7.10 | Asset Management and Inspections | NA |  |  |  | FALSE | 2024-2027 | • Research methods for detecting and preventing asset failures. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 7 | 11 | 7.11 | Asset Management and Inspections | NA |  |  |  | FALSE | 2028-2030 | • Complete the transition to and widespread integration of a risk-informed and data-driven inspection process. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 7 | 12 | 7.12 | Asset Management and Inspections | NA |  |  |  | FALSE | 2028-2030 | • Refine risk data for more targeted inspections. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 7 | 13 | 7.13 | Asset Management and Inspections | NA |  |  |  | FALSE | 2028-2030 | • Gain deeper insight into asset condition through advanced technologies, data management, and analytical capabilities | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 8 | 1 | 8.1 | Vegetation Management and Inspections | Vegetation Inventory and Inspection Planning |  |  |  | FALSE | 2020-2026 | • Incorporate risk considerations into inspection frequency. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 8 | 2 | 8.2 | Vegetation Management and Inspections | Vegetation Inventory and Inspection Planning |  |  |  | FALSE | 2020-2026 | • Expand software tools to manage inspection process. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 8 | 3 | 8.3 | Vegetation Management and Inspections | Vegetation Inventory and Inspection Planning |  |  |  | FALSE | 2020-2026 | • Evaluate EVM scope to focus on higher risk trees with the goals of improving overall RSE and achieving a greater overall risk reduction in the short term. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 8 | 4 | 8.4 | Vegetation Management and Inspections | Vegetation Inventory and Inspection Planning |  |  |  | FALSE | 2020-2026 | • Incorporate the EVM radial clearance and overhang removal scope into our routine work procedure. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 8 | 5 | 8.5 | Vegetation Management and Inspections | Vegetation Inventory and Inspection Planning |  |  |  | FALSE | 2020-2026 | • Establish an integrated work management system and database for all of PG&E’s VM programs. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 8 | 6 | 8.6 | Vegetation Management and Inspections | Program Execution |  |  |  | FALSE | 2020-2026 | • Standup inspection team to oversee PI and tree crew work as it is being implemented. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 8 | 7 | 8.7 | Vegetation Management and Inspections | Vegetation Inventory and Inspection Planning |  |  |  | FALSE | 2027-2029 | • Perform a systemwide species inventory of all trees with strike potential of PG&E Distribution Assets. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 8 | 8 | 8.8 | Vegetation Management and Inspections | Vegetation Inventory and Inspection Planning |  |  |  | FALSE | 2027-2029 | • Improve RSE outlook for the program overall and incorporate into decision making. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 8 | 9 | 8.9 | Vegetation Management and Inspections | Program Execution |  |  |  | FALSE | 2027-2029 | • Enhance work management systems with automation to improve reporting capabilities and timeliness to internal and external parties. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 8 | 10 | 8.10 | Vegetation Management and Inspections | Vegetation Inventory and Inspection Planning |  |  |  | FALSE | 2030 | • Extend EVM to most distribution line miles in Tier 2 and Tier 3 HFTDs. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 8 | 11 | 8.11 | Vegetation Management and Inspections | Vegetation Inventory and Inspection Planning |  |  |  | FALSE | 2030 | • Leverage risk modeling advancements to inform inspection processes, vegetation clearances, and trim cycles. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 8 | 12 | 8.12 | Vegetation Management and Inspections | Vegetation Inventory and Inspection Planning |  |  |  | FALSE | 2030 | • Explore Targeted tree species removal of trees with high fail rates in high risk areas. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 8 | 13 | 8.13 | Vegetation Management and Inspections | Vegetation Inventory and Inspection Planning | Steven Fisher | Joey Perez Jr. |  | TRUE | 2020-2026 | • Increase fuel reduction programs and assess the benefits of these efforts. | [5 empty] | No | No | Pending | No | No | No | No | No
| 8 | 14 | 8.14 | Vegetation Management and Inspections | Program Execution | Steven Fisher | Joey Perez Jr. |  | TRUE | 2020-2026 | • Establish a California-based training program to increase population of trained Pre-Inspectors. | [5 empty] | No | No | Pending | No | No | No | No | No
| 8 | 15 | 8.15 | Vegetation Management and Inspections | Program Execution | Steven Fisher | Joey Perez Jr. |  | TRUE | 2020-2026 | • Establish a California-based training program to increase population of trained tree crew personnel. | [5 empty] | No | No | Pending | No | No | No | No | No
| 8 | 16 | 8.16 | Vegetation Management and Inspections | Program Execution | Steven Fisher | Joey Perez Jr. |  | TRUE | 2020-2026 | • Improve routine program administration structure to increase resource efficiency and customer satisfaction. | [5 empty] | No | No | Pending | No | No | No | No | No
| 8 | 17 | 8.17 | Vegetation Management and Inspections | Vegetation Inventory and Inspection Planning | Steven Fisher | Joey Perez Jr. |  | TRUE | 2027-2029 | • Continue to expand the ROWs of higher risk transmission lines with the goal of increasing separation between vegetation and transmission assets. | [5 empty] | No | No | Pending | No | No | No | No | No
| 8 | 18 | 8.18 | Vegetation Management and Inspections | Program Execution | Steven Fisher | Joey Perez Jr. |  | TRUE | 2027-2029 | • Continue outreach with communities to educate about the VM Program, with the goal of reducing overall refusals and creating increased partnership on powerline safety and wildfire risk reduction. | [5 empty] | No | No | Pending | No | No | No | No | No
| 8 | 19 | 8.19 | Vegetation Management and Inspections | Program Execution | Steven Fisher | Joey Perez Jr. |  | TRUE | 2027-2029 | • Continue to evaluate new technologies for ways to improve efficiency and effectiveness. | [5 empty] | No | No | Pending | No | No | No | No | No
| 9 | 1 | 9.1 | Grid Operations Protocols | PSPS Event Execution | David Schoenberg | Meghan Dewey/Vanessa Bryan |  | TRUE | 2020-2025 | • Increase PSPS notifications to greater than 95 percent of customers and virtually 100 percent of known medical baseline customers. | Increase means that we will make efforts to deliver PSPS outage notifications to more than 95% of known general customers who are impacted by a PSPS event, and close to 100% of known medical baseline customers who are impacted by a PSPS event. | Yes | Annual aggregated PSPS event notifications data for known general and known medical baseline customers |  |  | Yes | Yes | Yes | Include? | No | No | No | No
| 9 | 2 | 9.2 | Grid Operations Protocols | PSPS Event Execution | Jim Kent | Aja Lodigiani |  | TRUE | 2020-2025 | • Increase and maintain fleet of 65 exclusive-use helicopters for patrol. | "Increase and maintain fleet of 65 exclusive-use helicopters for patrol" means to implement and maintain helicopters which can be avaliable for use during the peak PSPS season to aid in patrols There is no current plan to increase the helicopter fleet for PSPS patrolling. Please remove the language to increase. The current plan is to maintain the previous year's fleet size and evaluate the business needs. | No | Exclusive use contracts for helicopters |  |  | Yes | Yes | Yes | No | No | No | No | No
| 9 | 3 | 9.3 | Grid Operations Protocols | PSPS Event Execution | Jim Kent | Aja Lodigiani |  | TRUE | 2026-2028 | • Continue refining use of drones. | "Continue refining use of drones" means to track technology and laws related to drones in order to potentially leverage this technology for patrols during PSPS We currently do not use drones for PSPS inspections as they require a flight path beyond visual line of sight (BVLOS). Drones are presently utilized for detailed isolated, not out of visual sight, asset inspections. We will continue to explore BVLOS operations for PSPS and other enterprise initiatives over the next two years. | No |  | Okay to include if this bullet was supposed to reference 2026 through 2028? Would that change the response as well? How would you theoretically track extent of drone usage in the future? |  | Yes | Yes | No | No | No | No | No | No
| 9 | 4 | 9.4 | Grid Operations Protocols | PSPS Event Execution | Jim Kent | Aja Lodigiani |  | TRUE | 2029-2030 | • Continue refining use of drones. | "Continue refining use of drones" means to track technology and laws related to drones in order to potentially leverage this technology for patrols during PSPS We currently do not use drones for PSPS inspections as they require a flight path beyond visual line of sight (BVLOS). Drones are presently utilized for detailed isolated, not out of visual sight, asset inspections. We will continue to explore BVLOS operations for PSPS and other enterprise initiatives over the next two years. | No |  | Is there any difference in this strategy between 2026-2028 and 2029-2030? How would you theoretically track extent of drone usage in the future? |  | Yes | Yes | No | No | No | No | No | No
| 9 | 5 | 9.5 | Grid Operations Protocols | Load Management and BTM for Microgrids |  |  |  | FALSE | 2020-2025 | • Partner with key external stakeholders for DR and BTM Program design (e.g., California Energy Commission (CEC)). | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 9 | 6 | 9.6 | Grid Operations Protocols | Load Management and BTM for Microgrids |  |  |  | FALSE | 2020-2025 | • Identify candidate substations for piloting DR and BTM programs to support load management during PSPS events. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 9 | 7 | 9.7 | Grid Operations Protocols | Load Management and BTM for Microgrids |  |  |  | FALSE | 2020-2025 | • Pilot DR and BTM program(s) and document lessons learned, including which generation technologies can best pair with DR. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 9 | 8 | 9.8 | Grid Operations Protocols | Load Management and BTM for Microgrids |  |  |  | FALSE | 2020-2025 | • Propose DR and BTM program(s) for full-scale rollout. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 9 | 9 | 9.9 | Grid Operations Protocols | Clean Temporary Generation |  |  |  | FALSE | 2020-2025 | • Test and pilot clean temporary generation technologies in controlled and field environment. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 9 | 10 | 9.10 | Grid Operations Protocols | Clean Temporary Generation |  |  |  | FALSE | 2020-2025 | • Partner with vendors to address any operational concerns and ensure scalability of technology and any fueling/refueling logistics. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 9 | 11 | 9.11 | Grid Operations Protocols | Clean Temporary Generation |  |  |  | FALSE | 2020-2025 | • Embed clean temporary generation in procurement framework for PSPS mitigation. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 9 | 12 | 9.12 | Grid Operations Protocols | PSPS Event Execution |  |  |  | FALSE | 2020-2025 | • Reduce average grid re-energization time to 12 hours after all clear from a PSPS event. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 9 | 13 | 9.13 | Grid Operations Protocols | PSPS Event Execution |  |  |  | FALSE | 2020-2025 | • Track and validate restoration timeliness performance, identify constraints, and develop continuous improvement solutions. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 9 | 14 | 9.14 | Grid Operations Protocols | PSPS Event Execution |  |  |  | FALSE | 2020-2025 | • Partially automate the re-inspection process prior to re-energization following a PSPS event. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 9 | 15 | 9.15 | Grid Operations Protocols | PSPS Event Execution |  |  |  | FALSE | 2020-2025 | • Acquire two fixed wing aircraft with MX15 camera systems to enable night patrol of transmission circuits. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 9 | 16 | 9.16 | Grid Operations Protocols | PSPS Event Execution |  |  |  | FALSE | 2020-2025 | • Develop, test, and operationalize drone use for patrol. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 9 | 17 | 9.17 | Grid Operations Protocols | PSPS Event Execution |  |  |  | FALSE | 2020-2025 | • Conduct pre-flights of all potential PSPS circuits to identify patrol method and incorporate into mapping. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 9 | 18 | 9.18 | Grid Operations Protocols | PSPS Event Execution |  |  |  | FALSE | 2020-2025 | • Identify PSPS enhancements based on after-action reviews from exercises and events. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 9 | 19 | 9.19 | Grid Operations Protocols | PSPS Event Execution |  |  |  | FALSE | 2020-2025 | • Develop updated training materials and refine cadence based on after-action reviews, process updates, and PSPS exercises and events. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 9 | 20 | 9.20 | Grid Operations Protocols | PSPS Event Execution |  |  |  | FALSE | 2020-2025 | • Redevelop circuit segmentation guides and restoration maps by circuit, incorporating and prioritizing critical and essential customer restoration. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 9 | 21 | 9.21 | Grid Operations Protocols | PSPS Event Execution |  |  |  | FALSE | 2020-2025 | • Automate PSPS map creation in GIS. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 9 | 22 | 9.22 | Grid Operations Protocols | PSPS Event Execution |  |  |  | FALSE | 2020-2025 | • Incorporate Estimated Time of Restoration (ETOR) management at the Operations Emergency Center-level post-weather event for more granular and accurate ETOR management. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 9 | 23 | 9.23 | Grid Operations Protocols | PSPS Event Execution |  |  |  | FALSE | 2020-2025 | • Expand the fidelity of modeling for PSPS decision support to include historical data and expert evaluation. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 9 | 24 | 9.24 | Grid Operations Protocols | Load Management and BTM for Microgrids |  |  |  | FALSE | 2026-2028 | • Deploy DR and BTM programs at multiple substations in combination with temporary and/or permanent generation technologies. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 9 | 25 | 9.25 | Grid Operations Protocols | Clean Temporary Generation |  |  |  | FALSE | 2026-2028 | • Scale penetration of clean technologies in temporary generation portfolio. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
Pinto | 9 | 26 | 9.26 | Grid Operations Protocols | PSPS Event Execution |  |  |  | FALSE | 2026-2028 | • Evaluate exclusive use helicopter quantities based on risk and historical use. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 9 | 27 | 9.27 | Grid Operations Protocols | Clean Temporary Generation | Quinn Nakayama | Claire Halbrook |  | TRUE | 2026-2028 | • Continue supporting market development and partnering with clean temporary generation technology vendors. | [5 empty] | No | No | Pending | No | No | No | No | No
| 9 | 28 | 9.28 | Grid Operations Protocols | PSPS Event Execution |  |  |  | FALSE | 2026-2028 | • Identify opportunities to partially automate PSPS patrols (e.g., LiDAR, satellite). | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 9 | 29 | 9.29 | Grid Operations Protocols | PSPS Event Execution | Rod Robinson | Angie Gibson |  | TRUE | 2026-2028 | • Continue Identifying program enhancements based on after-action reviews from exercises and events. | "Continue identifying program enhancments" means to use or continuous improvement process to identify opportunities to improve | Yes | Number of corrective actions identified in our after action reviews | Definition - More detail on what "continuous improvement process" might include Tracking / benchmarking - What about corrective actions implemented and not just ID'ed? |  | Yes | Yes | No | No | No | No | No | No
| 9 | 30 | 9.30 | Grid Operations Protocols | PSPS Event Execution |  |  |  | FALSE | 2029-2030 | • Target smaller and less frequent PSPS events through better system and weather modeling. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 9 | 31 | 9.31 | Grid Operations Protocols | PSPS Event Execution | Rod Robinson | Robert Cupp |  | TRUE | 2026-2028 | • Continue refining PSPS restoration collateral (segment guides, maps). | "Continue refining PSPS restoration collateral" means to update segment guides used for restoration as system changes occur and enhance data in GIS to improve mapping capabilities | No | Segment guide and maps updates produced for PSPS restoration | Instead of the quantitative benchmark, I suggest we include language on how to track (e.g. # of segment guides up to date, process for capturing current data) |  | Yes | Yes | No | No | No | No | No | No
| 9 | 32 | 9.32 | Grid Operations Protocols | PSPS Event Execution | Rod Robinson | Shawn Holder |  | TRUE | 2026-2028 | • Continue tracking and validating restoration timeliness performance, identify constraints, and develop solutions. | "Continue tracking and validating restoration timeliness performance, identify constraints, and develop solutions" means to track restoration progress in PSPS events, identify opportunities for enhancements in restoration and implement improvements | No | Internal PSPS data management systems (Foundry) | Instead of the quantitative benchmark, I suggest we include language on how to track. |  | Yes | Yes | Pending | No | No | No | No | No
| 9 | 33 | 9.33 | Grid Operations Protocols | PSPS Event Execution | Rod Robinson | Robert Cupp |  | TRUE | 2026-2028 | • Continue ETOR refinement processes. | "Continue ETOR refinement processes" means to continue to refine process for updating estimating and updating ETORs in the PSPS process | No | Process Maps, job aids, other collateral |  |  | Yes | Yes | Pending | No | No | No | No | No
| 9 | 34 | 9.34 | Grid Operations Protocols | PSPS Event Execution |  |  |  | FALSE | 2029-2030 | • Identify program enhancements based on after-action reviews from exercises and events. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 9 | 35 | 9.35 | Grid Operations Protocols | PSPS Event Execution |  |  |  | FALSE | 2029-2030 | • Track and validate restoration timeliness performance, identify constraints, and develop solutions. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 9 | 36 | 9.36 | Grid Operations Protocols | PSPS Event Execution | Rod Robinson | Shawn Holder |  | TRUE | 2026-2028 | • Continue updating training collateral based on after-action reviews from exercises and events. | "Continue updating training collateral based on after-action reviews from exercises and events" means to refine training and improve for clarify to EOC roles who contribute to executing on PSPS events | No | Training documents produced for EOC roles for the PSPS season |  |  | Yes | Yes | Pending | No | No | No | No | No
| 9 | 37 | 9.37 | Grid Operations Protocols | PSPS Event Execution | Rod Robinson | Angie Gibson |  | TRUE | 2029-2030 | • Continue identifying program enhancements based on after-action reviews from exercises and events. | "Continue identifying program enhancments" means to use or continuous improvement process to identify opportunities to improve | Yes | Number of corrective actions identified in our after action reviews |  |  | Yes | Yes | Pending | No | No | No | No | No
| 9 | 38 | 9.38 | Grid Operations Protocols | PSPS Event Execution | Rod Robinson | Robert Cupp |  | TRUE | 2029-2030 | • Continue refining PSPS restoration collateral (e.g., segment guides, maps). | "Continue refining PSPS restoration collateral" means to update segment guides used for restoration as system changes occur and enhance data in GIS to improve mapping capabilities | No | Segment guide and maps updates produced for PSPS restoration |  |  | Yes | Yes | Pending | No | No | No | No | No
| 9 | 39 | 9.39 | Grid Operations Protocols | PSPS Event Execution | Rod Robinson | Robert Cupp |  | TRUE | 2029-2030 | • Continue ETOR refinement processes. | "Continue ETOR refinement processes" means to continue to refine process for updating estimating and updating ETORs in the PSPS process | No | Process Maps, job aids, other collateral |  |  | Yes | Yes | Pending | No | No | No | No | No
| 9 | 40 | 9.40 | Grid Operations Protocols | PSPS Event Execution | Rod Robinson | Shawn Holder |  | TRUE | 2029-2030 | • Continue updating training collateral based on after-action reviews from exercises and events. | "Continue updating training collateral based on after-action reviews from exercises and events" means to refine training and improve for clarify to EOC roles who contribute to executing on PSPS events | No | Training documents produced for EOC roles for the PSPS season |  |  | Yes | Yes | Pending | No | No | No | No | No
| 10 | 1 | 10.1 | Data Governance | NA | Ali Moazed | Jeanette Walters |  | TRUE | 2020-2024 | • Continue execution of improvements to data quality and related business processes, including: corrections to customer contact information, grid topology, and asset information. | Develop EO PMO to intake, investigate, resolve/triage and measure data quality issues across EO. | Yes | 1. PMO in place 2. PMO documented procedures in place 3. Data quality rules in place 4. PMO implementation tools in place 5. PMO KPI's to track and measure incoming data quality issues and progress in Foundry in place | Brief - needs to address business processes, more description on what the PMO does |  | Yes | Yes | No | No | No | No | No | No
| 10 | 2 | 10.2 | Data Governance | NA | Ali Moazed | Jeanette Walters |  | TRUE | 2025-2027 | • Continue to grow and enable a Data Stewards community, including establishing a board of Data Owners and outlining the board’s role in data governance and retention decisions. | Create a forum of data quality and metadata stewards who can collaborate to share process knowledge, data quality functional expertise and address the fundamental causes for data quality issues | Yes | 1. Forum in place 2. Forum has an agreed charter including the roles of metadata stewards in place 3. Number of assigned EO stewards committed to monitor and manage our data quality |  |  | Yes | Yes | Yes | No | No | No | No | No
| 10 | 3 | 10.3 | Data Governance | NA | Ali Moazed | Eugene Gorokhov |  | TRUE | 2025-2027 | • Execute data architecture activities, including the rationalization and retirement of databases to increase database integration. | Incorporate complimentary (not existing in current SOR) data sources into existing systems of records | Yes | 1. Inventory of systems exists. 2. Number of “complementary” data sources 3. Number of “complementary” data sources integrated / retired | Need more detail on types of data sources in mind, other high-level data architecture activities to increase integration |  | Yes | Yes | Yes | No | No | No | No | No
| 10 | 4 | 10.4 | Data Governance | NA | Ali Moazed | Jeanette Walters |  | TRUE | 2025-2027 | • Continue to improve and document business processes that generate data. | Inventory of EO critical business process Review, revised & approve critical business processes. | Yes | 1. Inventory of Critical Business Processes exists 2. Number of critical business processes reviewed, revised & approved | What's the method for review? Through a CI team? |  | Yes | Yes | No | No | No | No | No | No
| 10 | 5 | 10.5 | Data Governance | NA | Ali Moazed | Jason Bright |  | TRUE | 2028-2030 | • Develop data access Application Programming Interfaces to enable increased partnerships and transparency with researchers, regulators, and state and local governments. | Develop a portal in order to share data regarding Microgrids as required by the microgrid OIR, as well as create a way of sharing PSPS historical and planning data with customers and other external stakeholders. This will provide transparency to our stakeholders, and allow them to work more efficiently with PG&E, or to make better decisions. | No | 1. External data sharing product roadmap in place 2. For individual projects/products, track according to the project plans and whether PG&E is tracking to the advice letter filed in response to the Microgrid OIR. |  |  | Yes | Yes | Yes | No | No | No | No | No
| 10 | 6 | 10.6 | Data Governance | NA |  |  |  | FALSE | 2020-2024 | • Develop an Enterprise Data Management Program, enterprise strategy, enterprise governance and operating model, Electric Operations’ implementation plan, and key performance indicators to track progress against said plan. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 10 | 7 | 10.7 | Data Governance | NA |  |  |  | FALSE | 2020-2024 | • Develop a catalog/inventory of data sources including profiling of databases for duplicity and utilization. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 10 | 8 | 10.8 | Data Governance | NA |  |  |  | FALSE | 2020-2024 | • Develop a catalog/inventory of critical business terms and other relevant metadata. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 10 | 9 | 10.9 | Data Governance | NA |  |  |  | FALSE | 2020-2024 | • Create data literacy educational materials/curriculum customized to key personnel to improve data collection, quality, and utilization processes, | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 10 | 10 | 10.10 | Data Governance | NA |  |  |  | FALSE | 2025-2027 | • Scaled execution against Electric Operations’ implementation plan, resulting in the improvement or creation of data products that enable business processes focused on risk reduction and operational excellence. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 10 | 11 | 10.11 | Data Governance | NA |  |  |  | FALSE | 2025-2027 | • Development and initial execution of a cloud migration approach, including data selection criteria, prioritization of databases to be migrated and a roadmap of required activities, including change management plan. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 10 | 12 | 10.12 | Data Governance | NA |  |  |  | FALSE | 2028-2030 | • Rationalize and align business intelligence dashboards and reports, including profiling for duplicity and utilization. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 10 | 13 | 10.13 | Data Governance | NA |  |  |  | FALSE | 2028-2030 | • Establish and enforce comprehensive governance patterns for the collection and storage of new data. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 10 | 14 | 10.14 | Data Governance | NA |  |  |  | FALSE | 2028-2030 | • Refine analytics operating model and organization structure to further develop high-quality predictive and prescriptive analytics for risk informed decision making. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 10 | 15 | 10.15 | Data Governance | NA |  |  |  | FALSE | 2028-2030 | • Continuously evaluate tools, technology, and performance against industry best practices to adjust the plan as appropriate. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 11 | 1 | 11.1 | Resource Allocation Methodology | NA | Paul McGregor | Benson Wong |  | TRUE | 2020-2023 | • Increase granularity of scenario projections and RSE down to the circuit level. | [5 empty] | No | No | Pending | No | No | No | No | No
| 11 | 2 | 11.2 | Resource Allocation Methodology | NA | Paul McGregor | Benson Wong |  | TRUE | 2020-2023 | • Increase the detail and geographic granularity of RSE down to the circuit level. | [5 empty] | No | No | Pending | No | No | No | No | No
| 11 | 3 | 11.3 | Resource Allocation Methodology | NA |  |  |  | FALSE | 2020-2023 | • Move to a circuit-based approach to planning to achieve higher risk reduction through coordination, such as planning system hardening and VM work to be executed concurrently. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 11 | 4 | 11.4 | Resource Allocation Methodology | NA |  |  |  | FALSE | 2020-2023 | • Incorporate scenarios and associated risk reduction potential into plans for initiatives. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 11 | 5 | 11.5 | Resource Allocation Methodology | NA |  |  |  | FALSE | 2020-2023 | • Develop RSEs across a broad range of initiatives. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 11 | 6 | 11.6 | Resource Allocation Methodology | NA |  |  |  | FALSE | 2020-2023 | • Incorporate RSE into capital allocation process. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 11 | 7 | 11.7 | Resource Allocation Methodology | NA |  |  |  | FALSE | 2024-2027 | • Risk effectiveness by mitigation is deeply embedded into the resource allocation process guiding the prioritization and tradeoff analysis. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 11 | 8 | 11.8 | Resource Allocation Methodology | NA |  |  |  | FALSE | 2028-2030 | • Refine use of investment decision optimization tools. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 11 | 9 | 11.9 | Resource Allocation Methodology | NA |  |  |  | FALSE | 2028-2030 | • Leverage a more comprehensive analysis framework. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 11 | 10 | 11.10 | Resource Allocation Methodology | NA |  |  |  | FALSE | 2028-2030 | • Improve staff competencies with risk and investment modeling tools | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 11 | 11 | 11.11 | Resource Allocation Methodology | NA | Todd Mintzer | Stephen Mayer |  | TRUE | 2028-2030 | • Continue improving end-to-end work management processes. | Continue the end-to-end work management processes via the implementation of the EO E2E Work Management Process Improvement program, through streamlining both upstream and downstream processes to ensure visibility and alignment across seven key process areas: Plan (includes Manage Assets, Work & Resource Planning, and Investment Planning), Inspect, Design & Estimate, Dependency Management, Schedule, Execute, and Close. Key milestones include completion of current state process mapping, future state process mapping, technology portfolio management integration, process piloting, initial process rollout, and post-deployment adoption and support. | No | Tracking Key milestones. |  |  | Yes | Yes | Pending | No | No | No | No | No
| 12 | 1 | 12.1 | Emergency Planning and Preparedness | NA | Rod Robinson | Angie Gibson |  | TRUE | 2023-2025 | • Continue incorporating enhancements based on after-action review, exercises, and event response. | "Continue identifying program enhancments" means to use or continuous improvement process to identify opportunities to improve | Yes | Number of corrective actions identified in our after action reviews |  |  | Yes | Yes | No | No | No | No | No | No
| 12 | 2 | 12.2 | Emergency Planning and Preparedness | NA | Rod Robinson | Angie Gibson |  | TRUE | 2026-2030 | • Continue to integrate the WMP with disaster and emergency plans. | [5 empty] | No | No | Pending | No | No | No | No | No
| 12 | 3 | 12.3 | Emergency Planning and Preparedness | NA | Rod Robinson | Angie Gibson |  | TRUE | 2026-2030 | • Continue incorporating enhancements based on after-action review, exercises, and event response. | "Continue identifying program enhancments" means to use or continuous improvement process to identify opportunities to improve | Yes | Number of corrective actions identified in our after action reviews |  |  | Yes | Yes | No | No | No | No | No | No
| 12 | 4 | 12.4 | Emergency Planning and Preparedness | NA |  |  |  | FALSE | 2020-2022 | • Incorporation of drills to audit viability and execution of wildfire plans. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 12 | 5 | 12.5 | Emergency Planning and Preparedness | NA |  |  |  | FALSE | 2020-2022 | • Evolution of wildfire plan to incorporate confounding and simultaneous disasters. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 12 | 6 | 12.6 | Emergency Planning and Preparedness | NA |  |  |  | FALSE | 2020-2022 | • Taking a leading role in the integration of PG&E’s wildfire plan with the plans of other stakeholders. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 12 | 7 | 12.7 | Emergency Planning and Preparedness | NA |  |  |  | FALSE | 2020-2022 | • Refine inventory of resources available for repairs to those with high RSEs. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 12 | 8 | 12.8 | Emergency Planning and Preparedness | NA |  |  |  | FALSE | 2020-2022 | • >99 percent of PSPS-affected customers and virtually 100 percent of PSPS-affected Medical Baseline customers receiving complete information. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 12 | 9 | 12.9 | Emergency Planning and Preparedness | NA |  |  |  | FALSE | 2020-2022 | • Develop an After-Action Review Standard and After-Action Procedures that outline the execution steps of the After-Action Review process. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 12 | 10 | 12.10 | Emergency Planning and Preparedness | NA |  |  |  | FALSE | 2020-2022 | • Develop After-Action Procedures that outline the execution steps of the After-Action Review process. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 12 | 11 | 12.11 | Emergency Planning and Preparedness | NA |  |  |  | FALSE | 2020-2022 | • Develop Wildfire Annex and enhancements based on after-action reviews from exercises and events. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 12 | 12 | 12.12 | Emergency Planning and Preparedness | NA |  |  |  | FALSE | 2020-2022 | • Conduct enhanced wildfire exercise in 2021 and begin developing progressively complex exercises including the use of drills, seminar, table-tops, and functional exercises. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 12 | 13 | 12.13 | Emergency Planning and Preparedness | NA |  |  |  | FALSE | 2020-2022 | • Include public sector agencies as planners and players | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 12 | 14 | 12.14 | Emergency Planning and Preparedness | NA |  |  |  | FALSE | 2023-2025 | • Evaluate After-action Standard and Procedures for continuous improvement. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 12 | 15 | 12.15 | Emergency Planning and Preparedness | NA |  |  |  | FALSE | 2023-2025 | • Include Wildfire exercises in PG&E's Multi-Year Training and Exercise plan, and begin to incorporate concurrent hazard response from the additional Hazard Specific Annexes to the Company Emergency Response Plan. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 12 | 16 | 12.16 | Emergency Planning and Preparedness | NA |  |  |  | FALSE | 2023-2025 | • Expand the inclusion of public sector agencies as both exercise planners and participants in a PG&E exercise. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 12 | 17 | 12.17 | Emergency Planning and Preparedness | NA |  |  |  | FALSE | 2026-2030 | • Update service restoration workforce training from after-action reviews. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 12 | 18 | 12.18 | Emergency Planning and Preparedness | NA |  |  |  | FALSE | 2026-2030 | • Identify program enhancements based on after-action reviews from exercises and events. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 12 | 19 | 12.19 | Emergency Planning and Preparedness | NA |  |  |  | FALSE | 2026-2030 | • Expand inclusion to the public sector agencies in a collaboratively led full-scale wildfire exercise. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 13 | 1 | 13.1 | Stakeholder Cooperation and Community Engagement | NA | Ben Almario | Jeff Millar |  | TRUE | 2020-2022 | • Increase coordination with fire suppression crews including fire detection and fire propagation. | PG&E will continue to work closely with local and state agencies as appropriate and look for opportunities to support when invited to do so. | No | This is not quantitative PG&E can lend aid when invited to do so by the Authority Having Jurisdiction | Sounds more like status quo - are there going to be more channels of communication, etc.? |  | Yes | Yes | No | No | No | No | No | No
| 13 | 2 | 13.2 | Stakeholder Cooperation and Community Engagement | NA | Mary Ellen Ittner | Elise Hunter |  | TRUE | 2023-2026 | • Continue to gather and incorporate feedback from community partners and first responders. | Following key external engagement activities, we summarize the agency’s feedback and identify action items. When action items are identified, we assign an internal owner to drive the action to resolution and we communicate the status back to agencies. PG&E also meets internally to discuss the agency’s feedback and determine feasibility. If deemed feasible and appropriate, PG&E incorporates the feedback into processes and procedures. | No | No quantitative benchmark. | Missing tracking method Is there a process to follow-up afterwards to make sure that the feedback has been incorporated? |  | Yes | Yes | No | No | No | No | No | No
| 13 | 3 | 13.3 | Stakeholder Cooperation and Community Engagement | NA | Mary Ellen Ittner | Elise Hunter |  | TRUE | 2027-2030 | • Continue to improve stakeholders’ outreach and education efforts. | Action items captured from key agency engagements related to agency outreach and education to their communities are identified, tracked and resolved in the manner described above. | No | No quantitative benchmark. | Missing tracking method Is there a process to follow-up afterwards to make sure that the feedback has been incorporated? |  | Yes | Yes | No | No | No | No | No | No
| 13 | 4 | 13.4 | Stakeholder Cooperation and Community Engagement | NA |  |  |  | FALSE | 2020-2022 | • Incorporate benchmarking and best practices from other utilities. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 13 | 5 | 13.5 | Stakeholder Cooperation and Community Engagement | NA |  |  |  | FALSE | 2020-2022 | • Formalize processes to incorporate lessons learned from other utilities. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 13 | 6 | 13.6 | Stakeholder Cooperation and Community Engagement | NA |  |  |  | FALSE | 2020-2022 | • Improve cooperative relationships with communities in HFTD. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 13 | 7 | 13.7 | Stakeholder Cooperation and Community Engagement | NA |  |  |  | FALSE | 2020-2022 | • Implement annually-updated plans to further reduce wildfire and PSPS risk to LEP and AFN communities, among other critical constituencies. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 13 | 8 | 13.8 | Stakeholder Cooperation and Community Engagement | NA |  |  |  | FALSE | 2020-2022 | • Further gather, evaluate, and incorporate feedback from community partners and first responders to improve collaboration and processes. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 13 | 9 | 13.9 | Stakeholder Cooperation and Community Engagement | NA |  |  |  | FALSE | 2023-2026 | • Incorporate technology such as integrated communications and data sharing platforms to support better partnership with fire suppression and first responder agencies. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 13 | 10 | 13.10 | Stakeholder Cooperation and Community Engagement | NA |  |  |  | FALSE | 2023-2026 | • Deepen community outreach programs and relationships with property owners. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 13 | 11 | 13.11 | Stakeholder Cooperation and Community Engagement | NA |  |  |  | FALSE | 2023-2026 | • Develop new partnerships within and outside California to identify and incorporate risk-reduction best practices. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 13 | 12 | 13.12 | Stakeholder Cooperation and Community Engagement | NA |  |  |  | FALSE | 2027-2030 | • Lead collaborative partnerships to identify and incorporate best practices to reduce risk. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 13 | 13 | 13.13 | Stakeholder Cooperation and Community Engagement | NA |  |  |  | FALSE | 2027-2030 | • Complete buildout of integrated operations and communications structures to support true collaboration with communities and customer groups. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA
| 13 | 14 | 13.14 | Stakeholder Cooperation and Community Engagement | NA |  |  |  | FALSE | 2027-2030 | • Final maturation of processes to seamlessly share information with industry peers, researchers, scientists, and other inside and outside California. | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA