## Instructions
California Public Utilties Commission
Annual Report Electric Rule 20 Programs (A-D)
GENERAL
BACKGROUND: As directed in Decision 21-06-013, electric utilities shall annually report to the Commission information about all of the projects, expenditures, and work credit balances for all communities in their service territories. This annual report template is designed for reporting all Rule 20A, 20B, 20C, and 20D projects in the reporting period. The first sheet is for project level data and the second sheet is for community level data. The utilities shall meet with Energy Division upon request to further refine the template prior to the submission deadline of April 1, 2022. Therefore, this template may be subject to change. INSTRUCTIONS: Complete the spreadsheet, listing all Electric Rule 20 programs' project and community level data from January 1, 2019 to December 31, 2021. Please include all projects from planning phase to close out phase. The annual report is split into three tranches in order of importance of the data. Staff requests that the utilities make data available as they complete each tranche. Data provided should include everything up to December 31st, 2021 (i.e., data recorded after this data should NOT be included in this year's report). Do not leave cells blank; if a column is not applicable to a specific project please indicate this using "N/A" and if a value for a column is unknown indicate this using "Unknown." Additionally, the utilities shall work with staff regarding the availability of project files in GIS format. GIS data should be provided in a shape file and should include project boundary, path of overhead infrastructure to be converted to underground, and path of trench where underground equipment is to be placed. The attribute table for each project should include all data in the project tab. If the report contains confidential information, provide two separate versions via through KiteWorks: a redacted version for public distribution and an unredacted version. The files must be searchable and filterable. If you have questions, contact Jessica Tse at Jessica.Tse@cpuc.ca.gov and Julian Enis at Julian.Enis@cpuc.ca.gov. This is the current template as of 03/10/2021.
DEFINITIONS
Definitions of urban areas, urban clusters, and rural areas are per the US Census Bureau's 2010 definitions, which can be found here: https://www.census.gov/programs-surveys/geography/guidance/geo-areas/urban-rural/2010-urban-rural.html Urban Area: Areas meeting minimum population density requirements and encompassing more than 50,000 people. Urban Cluster: Areas meeting minimum population density requirements and encompassing more than 2,500 people and less than 50,000 people. Rural Area: All areas not defined as either urban areas or urban clusters.

## Project - By Tranche
PG&E Rule 20 Project Data
Note: The data provided in the conversion report is now being reported in the new annual report. Cancelled projects will only include project description information.
Tranche 1 (High Priority) | [23 empty] | Tranche 2 |  |  |  |  | Tranche 3 (Lower Priority)
Project Sponsor | Other Project Sponsors | County | City | Utility Undergrounding District | Project Name/Identifier | Project Address (Street, City, ZIP Code) | R20 Project Type (A/B/C/D) | Applicant Type | Project Status (Active/Hold/Cancelled) | Project Stage | Project Completion Date (PCD) | PCD, Forecast or Actual? | Trench Length (ft) | Length, Estimated or Design? | Project Cost (Actual, Non-Adjusted) | Actual Cost/ Current Estimated At Completion (EAC)* | Current/ Actual Cost/ Ft | Explanation for Outlier Costs | Centerline Footage of Primary OH Line Converted | Line Footage of Primary UG Circuit | Number of Meters Converted to UG Service | Project Spend to Date | Project Spend, Report Year | Joint Trench Participants? | Public Interest Criteria Met By Project (Rule 20A Only) | Is this project being performed in top 25% DAC per CalEnviroScreen 4.0? | Environmental Mitigations required? | Storm Water Pollution Prevention Plan (SWPPP) required? | Project in Urban/Urban Cluster/Rural (Defined in the American Community Survey) | # of Poles Removed as Part of Project Scope | Projected/Final Cost to Non-Ratepayers | Non-Ratepayer Funding Source
SANTA CLARA COUNTY | MILPITAS | SANTA CLARA | MILPITAS | MONTAGUE EXPWY | MONTAGUE EXPWY MILPITAS R20A ¦ 16-43000-01 ¦ 31330811 | MONTAGUE EXPWY, SOUTH MILPITAS BLVD, GLADDING CT & WATSON CT, MILPITAS, 95035 | A | Government Agency | Active | Closed | 2020-06-10 | Actual | 186 | Design | 528738.35 | Actual | 4737.7988 | Minimal trenching required due to use of existing pre-installed conduit | 1798.2805 | 1279.31 | 0 | 528738.348 | 8282.682 | No | Arterial Street or Major Collector | No | TBD | No | Urban | 6 | TBD | TBD
MILPITAS | SANTA CLARA COUNTY | SANTA CLARA | MILPITAS | MONTAGUE EXPWY | MONTAGUE EXPWY MILPITAS R20A ¦ 16-43000-01 ¦ 31330811 | MONTAGUE EXPWY, SOUTH MILPITAS BLVD, GLADDING CT & WATSON CT, MILPITAS, 95035 | A | Government Agency | Active | Closed | 2020-06-10 | Actual | see 1st sponsor | Design | 352492.23 | Actual | see 1st sponsor | see 1st sponsor | see 1st sponsor | see 1st sponsor | see 1st sponsor | 352492.232 | 5521.788 | No | Arterial Street or Major Collector | No | TBD | No | Urban | see 1st sponsor | TBD | TBD
MERCED COUNTY | None | MERCED | UNINCORPORATED | LOBO AVE, UUD# 11 | EP LOBO AVE MERCED COUNTY R20A ¦ 14-24000-01 ¦ 74001558 | LOBO AVE, SUNRISE AVE & DRAKE AVE, MERCED COUNTY, MERCED, 95348 | A | Government Agency | Active | Closed | 2020-01-24 | Actual | 10245 | Design | 5124510.54 | Actual | 500.1962 | Not Outlier | 4901.3726 | 11348.0607 | 29 | 5141866.54 | 0 | Yes | Civic/Scenic/Historical/Other Interest to General Public | Yes | TBD | No | Urban | 36 | TBD | TBD
FORTUNA | None | HUMBOLDT | FORTUNA | 12TH ST | 12TH STREET FORTUNA R20A ¦ 13-12018-01 ¦ 74004300 | 12TH ST, L ST & NEWBERG, FORTUNA, 95540 | A | Government Agency | Active | Closed | 2020-01-31 | Actual | 8005 | Design | 3939197.67 | Actual | 492.0922 | Not Outlier | 2894.5155 | 6826.1172 | 47 | 3861811.67 | 0 | Yes | Arterial Street or Major Collector | No | No | No | Urban Cluster | 45 | TBD | TBD
SUTTER COUNTY | None | SUTTER | UNINCORPORATED | BARRY RD | ECEIR2Z EP BARRY ROAD SUTTER COUNTY R20A ¦ 16-51000-01 ¦ 31242522 | BARRY RD, HWY 99, SUTTER COUNTY, YUBA CITY, 95991 | A | Government Agency | Active | Closing | 2020-08-12 | Actual | 2291 | Design | 1970980.55 | EAC | 860.3145 | Not Outlier | 954.6346 | 2705.2255 | 8 | 1933479.55 | 543.95 | Yes | Civic/Scenic/Historical/Other Interest to General Public | No | TBD | No | Rural | 14 | TBD | TBD
SANTA CLARA COUNTY | None | SANTA CLARA | LOS ALTOS | LINCOLN PARK | LINCOLN PARK LOS ALTOS R20A ¦ 17-43000-01 ¦ 35029458 | UNIVERSITY AVE & LINCOLN AVE, EDITH AVE & SHERMAN ST, LOS ALTOS, 94022 | A | Government Agency | Active | Closing | 2020-12-17 | Actual | 5946 | Design | 3479161.22 | EAC | 585.1263 | Not Outlier | 3305.696 | 6754.9724 | 6 | 3465380.22 | 0 | Yes | Civic/Scenic/Historical/Other Interest to General Public | No | TBD | No | Urban | 9 | TBD | TBD
ALAMEDA COUNTY | None | ALAMEDA | UNINCORPORATED | HESPERIAN BLVD, UUD# 19 | HESPERIAN BLVD ALAMEDA CNTY R20A ¦ 09-01000-01 ¦ 74001557 | HESPERIAN BLVD BETWEEN HWY 238 TO GRAND AVE AND WEST A ST TO GOLF COURSE RD, HAYWARD, ALAMEDA COUNTY, 94541 | A | Government Agency | Active | Closing | 2020-03-06 | Actual | 4620 | Design | 4542867.99 | EAC | 983.3048 | Not Outlier | 2098.8742 | 5519.7848 | 3 | 4554005.99 | 0 | Yes | Arterial Street or Major Collector | No | TBD | No | Urban | 13 | TBD | TBD
REDWOOD CITY | None | SAN MATEO | REDWOOD CITY | MIDDLEFIELD RD, UUD# 2011-1 | R1 MIDDLEFIELD ROAD REDWOOD CITY R20A ¦ 12-41024-01 ¦ 74001642 | MIDDLEFIELD RD, MAIN ST & MANZANITA ST, REDWOOD CITY, 94063 | A | Government Agency | Active | Closed | 2020-07-28 | Actual | 9140 | Design | 8368718.63 | Actual | 915.6147 | Not Outlier | 5734.3214 | 10265.8482 | 106 | 8292356.63 | 0 | Yes | Arterial Street or Major Collector | No | No | No | Urban | 0 | TBD | TBD
MCFARLAND | None | KERN | MCFARLAND | GARZOLI AVE | EP GARZOLI AVE MC FARLAND R20A ¦ 15-15032-01 ¦ 74003981 | GARZOLI AVE, KYRA AVE TO W. PERKINS AVE, MCFARLAND, 93250 | A | Government Agency | Active | Closing | 2020-09-18 | Actual | 8470 | Design | 2741393.96 | EAC | 323.6593 | Not Outlier | 5323.3767 | 4548.448 | 21 | 2824246.96 | 0 | Yes | Arterial Street or Major Collector | Yes | TBD | No | Rural | 25 | TBD | TBD
MONTEREY COUNTY | None | MONTEREY | UNINCORPORATED | MOSS LANDING RD, MONTEREY COUNTY | EP MOSS LANDING RD MOSS LANDING R20A ¦ 05-27000-01 ¦ 74004303 | MOSS LANDING RD, POTRERO RD & SANDHOLDT RD, MONTEREY COUNTY, 95039 | A | Government Agency | Active | Closing | 2020-12-04 | Actual | 14347 | Design | 6726105.01 | EAC | 468.8161 | Not Outlier | 8342.5151 | 17755.2765 | 55 | 6565674.01 | 8800 | Yes | Civic/Scenic/Historical/Other Interest to General Public | No | No | No | Rural | 58 | TBD | TBD
PARADISE | None | BUTTE | PARADISE | ALMOND ST | ALMOND ST PARADISE R20A ¦ 16-04017-01 ¦ 74010581 | ALMOND ST, PEARSON RD & ELLIOTT RD, PARADISE, 95969 | A | Government Agency | Active | Closing | 2020-04-01 | Actual | 14381 | Design | 3955906.84 | EAC | 275.0787 | Not Outlier | 3257.0879 | 9830.7782 | 112 | 4129714.84 | -14095.45 | Yes | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | No | No | Urban Cluster | 55 | TBD | TBD
LIVE OAK | None | SUTTER | LIVE OAK | LIVE OAK BLVD | R6 LIVE OAK BLVD LIVE OAK R20A ¦ 17-51003-01 ¦ 74015720 | LIVE OAK BLVD, ASH ST & RAMSDELL DR, LIVE OAK, 95953 | A | Government Agency | Active | Closing | 2020-05-08 | Actual | 9125 | Design | 4832399.04 | EAC | 529.578 | Not Outlier | 6367.336 | 11913.0076 | 58 | 5737324.05 | -6538.62 | Yes | Arterial Street or Major Collector | No | TBD | No | Urban Cluster | 65 | TBD | TBD
LOS GATOS | None | SANTA CLARA | LOS GATOS | LOS GATOS BLVD | EP LOS GATOS BLVD LOS GATOS ¦ 16-43014-01 ¦ 35155286 | LOS GATOS BLVD, LARK AVE & CHIRCO DR, LOS GATOS, 95032 | A | Government Agency | Active | Closing | 2021-09-30 | Actual | 5330 | Design | 5076499.33 | EAC | 952.4389 | Not Outlier | 3250.3251 | 6201.19 | 5 | 5039484.44 | 517884.11 | Yes | Arterial Street or Major Collector | No | No | No | Urban | 20 | 0 | N/A
CONTRA COSTA COUNTY | None | CONTRA COSTA | UNINCORPORATED | WILLOW PASS RD/BAILEY RD, BAY POINT AREA, UUD# 31 | EP BAILEY RD CONTRA COSTA CNTY R20A ¦ 13-07000-01 ¦ 74001485 | BAILEY RD, CANAL RD & WILLOW PASS RD, WILLOW PASS RD, BAILEY RD & CRIVELLO AVE, BAY POINT, CONTRA COSTA COUNTY, 94565 | A | Government Agency | Active | Closing | 2021-10-04 | Actual | 11212 | Design | 9142659.5 | EAC | 815.4352 | Not Outlier | 6814.4016 | 11476.0362 | 40 | 9054694.5 | 146098.3 | Yes | Arterial Street or Major Collector | Yes | TBD | No | Urban | 50 | 0 | N/A
CHICO | None | BUTTE | CHICO | WARNER ST DIST 18 | WARNER ST CHICO R20 ¦ 16-04005-03 ¦ 74010864 | WARNER ST, SACRAMENTO AVE & 1ST W ST, CHICO, 95926 | A | Government Agency | Active | Closing | 2021-06-24 | Actual | 6795 | Design | 5238108.64 | EAC | 770.8769 | Not Outlier | 7261.6934 | 11396.8294 | 9 | 5265312.64 | 81028.4 | Yes | Arterial Street or Major Collector | No | No | No | Urban | 44 | 0 | N/A
EUREKA | None | HUMBOLDT | EUREKA | 4TH ST | 4TH ST EUREKA R20A ¦ 17-12013-01 ¦ 74014380 | 4TH ST, O ST & Y ST, EUREKA, 95501 | A | Government Agency | Active | Closing | 2021-08-09 | Actual | 8773 | Design | 7883983.44 | EAC | 898.6645 | Not Outlier | 3895.4261 | 12547.2184 | 38 | 7679955.26 | 281073.46 | Yes | Arterial Street or Major Collector | No | No | Yes | Urban Cluster | 56 | 0 | N/A
SANTA BARBARA COUNTY | None | SANTA BARBARA | UNINCORPORATED | BRADLEY RD | BRADLEY RD SANTA MARIA/S.B. CNTY R20A ¦ 09-42000-01 ¦ 74009862 | BRADLEY RD, AMETHYST DR & LARCH AVE, SANTA MARIA, 93455 | A | Government Agency | Active | Closing | 2021-08-08 | Actual | 9886 | Design | 6775926.46 | EAC | 685.4063 | Not Outlier | 6030.3408 | 14306.8354 | 1 | 6720830.46 | 9742.37 | Yes | Arterial Street or Major Collector | No | No | No | Urban | 32 | 0 | N/A
PITTSBURG | None | CONTRA COSTA | PITTSBURG | WEST LELAND RD | R1 WEST LELAND RD PITTSBURG R20A ¦ 09-07028-01 ¦ 30754659 | WEST LELAND RD, RAILROAD AVE TO CRESTVIEW DR, PITTSBURG, 94565 | A | Government Agency | Active | Closing | 2021-04-15 | Actual | 4140 | Design | 3714973.5 | EAC | 897.3366 | Not Outlier | 1879.3455 | 4501.5193 | 88 | 3683152.5 | 3500.78 | Yes | Arterial Street or Major Collector | No | TBD | No | Urban | 13 | 0 | N/A
ROHNERT PARK | None | SONOMA | ROHNERT PARK | E COTATI AVE | R20A - E COTATI AVE ROHNERT PARK ¦ 18-49032-01 ¦ 35051448 | ALONG PORTION OF E COTATI AVE, ROHNERT PARK, 94928 | A | Government Agency | Active | Closing | 2021-02-24 | Actual | 2270 | Design | 1919094.67 | EAC | 845.4162 | Not Outlier | 2109.4969 | 2927.0171 | 0 | 1916841.67 | 54964.09 | Yes | Arterial Street or Major Collector | No | No | No | Urban | 9 | 0 | N/A
SANTA ROSA | SONOMA COUNTY | SONOMA | SANTA ROSA | FULTON RD | R20A - FULTON RD SANTA ROSA ¦ 17-49034-01 ¦ 74013528 | FULTON RD, GUERNEVILLE RD & PINER RD, SANTA ROSA, 95403 | A | Government Agency | Active | Closing | 2021-06-08 | Actual | 9444 | Design | 5139134.87 | EAC | 618.3742 | Not Outlier | 7143.9639 | 10252.1923 | 19 | 5094525.03 | 4040.1416 | Yes | Arterial Street or Major Collector | No | No | No | Urban | 52 | 0 | N/A
SONOMA COUNTY | SANTA ROSA | SONOMA | SANTA ROSA | FULTON RD | R20A - FULTON RD SANTA ROSA ¦ 17-49034-01 ¦ 74013528 | FULTON RD, GUERNEVILLE RD & PINER RD, SANTA ROSA, 95403 | A | Government Agency | Active | Closing | 2021-06-08 | Actual | see 1st sponsor | Design | 700791.12 | EAC | see 1st sponsor | see 1st sponsor | see 1st sponsor | see 1st sponsor | see 1st sponsor | 694707.96 | 550.9284 | Yes | Arterial Street or Major Collector | No | No | No | Urban | see 1st sponsor | 0 | N/A
SAN LEANDRO | None | ALAMEDA | SAN LEANDRO | BAYFAIR PH 2 | R1 RULE 20A E14TH ST N/O BAYFAIR, SL ¦ 03-01026-03 ¦ 30616108 | E 14TH ST, 150TH & THORNTON AVE, SAN LEANDRO, 94578 | A | Government Agency | Active | Estimating/Design | 2024-07-29 | Forecast | TBD | Design | 6554955.58 | EAC | TBD | TBD | TBD | TBD | TBD | 667738.56 | 45830.22 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
BERKELEY | None | ALAMEDA | BERKELEY | GRIZZLY PEAK BLVD, UUD# 48 | GRIZZLY PEAK BLVD BERKELEY R20A ¦ 93-01005-01 ¦ 74001486 | GRIZZLY PEAK BLVD, HILL RD, SUMMIT RD, SUMMIT LN, SENIOR AVE, HARVARD CIR, FAIRLAWN & AVENIDA DR, BERKELEY, 94708 | A | Government Agency | Active | Estimating/Design | 2027-01-18 | Forecast | TBD | Design | 18287744.68 | EAC | TBD | TBD | TBD | 8837.7658 | TBD | 2822502.08 | 551577.23 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
SANTA MARIA | None | SANTA BARBARA | SANTA MARIA | CIVIC CENTER | EP CIVIC CENTER SANTA MARIA R20A ¦ 14-42020-01 ¦ 74005712 | MANILA AVE BTW RICHMOND ST & SAN PABLO AVE, KEARNEY ST BTW MANILA AVE & SCHMIDT LN, SANTA MARIA, 93454 | A | Government Agency | Active | Estimating/Design | 2024-10-14 | Forecast | TBD | Design | 4373885.13 | EAC | TBD | TBD | TBD | TBD | TBD | 167917.16 | 38870.23 | TBD | Civic/Scenic/Historical/Other Interest to General Public | No | TBD | TBD | Urban | TBD | TBD | TBD
MILPITAS | None | SANTA CLARA | MILPITAS | SOUTH MAIN ST | SOUTH MAIN ST MILPITAS R20A ¦ 17-43015-01 ¦ 74010862 | SOUTH MAIN ST, CORNING AVE & CURTIS AVE, MILPITAS, 95035 | A | Government Agency | Active | Estimating/Design | 2024-02-29 | Forecast | TBD | Design | 5228428.8 | EAC | TBD | TBD | TBD | TBD | TBD | 658294.79 | 52459.79 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
CAPITOLA | None | SANTA CRUZ | CAPITOLA | MONTEREY AVE & BAY AVE | BAY AVE CAPITOLA R20A ¦ 00-44007-01 ¦ 74013860 | BAY AVE BETWEEN OAK & BURLINGAME & CAPITOLA BETWEEN PLUM & BEVERLY, 95010 | A | Government Agency | Active | Estimating/Design | 2024-06-24 | Forecast | TBD | Design | 3082725.84 | EAC | TBD | TBD | TBD | TBD | TBD | 460991.15 | 255145.04 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
LINCOLN | None | PLACER | LINCOLN | CIVIC CENTER PLAZA | R20A - CIVIC CENTER PLAZA LINCOLN ¦ 17-31016-01 ¦ 74015721 | ALLEY BETWEEN 5TH ST & 6TH ST, LINCOLN BLVD, LINCOLN, 95648 | A | Government Agency | Active | Estimating/Design | 2024-06-17 | Forecast | TBD | Design | 1763070.82 | EAC | TBD | TBD | TBD | TBD | TBD | 295720.14 | 30144.71 | TBD | Civic/Scenic/Historical/Other Interest to General Public | No | TBD | TBD | Urban | TBD | TBD | TBD
SUNNYVALE | None | SANTA CLARA | SUNNYVALE | WOLFE RD, SUNNYVALE | WOLFE RD SUNNYVALE R20A PHASE I ¦ 09-43032-02 ¦ 74001551 | WOLFE RD, OLD SAN FRANCISCO RD & HOMESTEAD RD, SUNNYVALE, 94087 | A | Government Agency | Active | Construction | 2023-09-15 | Forecast | TBD | Design | 8952084.14 | EAC | TBD | TBD | TBD | 9570.8905 | TBD | 2692777.04 | 1520169.4 | Yes | Arterial Street or Major Collector | No | No | No | Urban | TBD | TBD | TBD
EL DORADO COUNTY | None | EL DORADO | UNINCORPORATED | PLEASANT VALLEY RD, DIAMOND SPRINGS | DIAMOND SPRINGS 1A-EL DORADO CTY R20A ¦ 14-09000-01 ¦ 31066255 | HWY 49, BRADLEY DR & PLEASANT VALLEY RD, EL DORADO COUNTY, 95619 | A | Government Agency | Active | Closing | 2022-04-01 | Actual | 7477 | Design | 4996584.11 | EAC | 668.2605 | Not Outlier | 4894.8818 | 8678.2771 | 20 | 4979853.11 | 133578.64 | Yes | Arterial Street or Major Collector | No | No | No | Urban Cluster | 30 | 0 | N/A
PINOLE | None | CONTRA COSTA | PINOLE | PINOLE VALLEY RD | R7 EP PINOLE VALLEY RD PINOLE R20A ¦ 16-07027-01 ¦ 31269303 | PINOLE VALLEY RD, RAMONA & HELENA, PINOLE, 94564 | A | Government Agency | Active | Closing | 2022-03-21 | Actual | 3260 | Design | 2945446.22 | EAC | 903.5111 | Not Outlier | 1605.3098 | 4416.328 | 12 | 2907511.22 | -305.77 | Yes | Arterial Street or Major Collector | No | No | No | Urban | 14 | 0 | N/A
STOCKTON | None | SAN JOAQUIN | STOCKTON | MINER AVE, STOCKTON | DOWNTOWN STOCKTON PH 1 R20A ¦ 17-39016-01 ¦ 35029720 | MINER AVE, AURORA ST, WEBER AVE, STANISLAUS, STOCKTON, 95202 | A | Government Agency | Active | Construction | 2023-03-31 | Forecast | TBD | Design | 7139974.3 | EAC | TBD | TBD | TBD | 7712.0959 | TBD | 6965736.3 | 1162216.33 | No | Civic/Scenic/Historical/Other Interest to General Public | Yes | TBD | No | Urban | TBD | TBD | TBD
STOCKTON | None | SAN JOAQUIN | STOCKTON | MINER AVE, CALIFORNIA, WEBER AVE, STOCKTON | DOWNTOWN STOCKTON PH 3 R20A ¦ 17-39016-03 ¦ 35218376 | MINER AVE, CALIFORNIA, WEBER AVE, STOCKTON, 95202 | A | Government Agency | Active | Construction | 2023-03-31 | Forecast | TBD | Design | 3052346.23 | EAC | TBD | TBD | TBD | 2149.4709 | TBD | 2886988.23 | 1895432.84 | No | Civic/Scenic/Historical/Other Interest to General Public | Yes | TBD | No | Urban | TBD | TBD | TBD
FRESNO | None | FRESNO | FRESNO | BLACKSTONE AVE & ABBY ST | BLACKSTONE AVE & ABBY ST FRESNO R20A ¦ 07-10023-03 ¦ 74009342 | BLACKSTONE AVE & ABBY ST, SHEILDS TO BELMONT & BELMONT TO HEDGES, FRESNO, 93703 | A | Government Agency | Active | Construction | 2023-04-26 | Forecast | TBD | Design | 11235802.91 | EAC | TBD | TBD | TBD | 20931.8931 | TBD | 8899618.67 | 7250861.01 | Yes | Arterial Street or Major Collector | Yes | No | No | Urban | TBD | TBD | TBD
EL DORADO COUNTY | None | EL DORADO | UNINCORPORATED | DIAMOND SPRINGS 1C | DIAMOND SPRINGS 1C-EL DORADO CTY R20A ¦ 14-09000-02 ¦ 74013925 | MISSOURI FLAT RD, EL DORADO TRAIL & OLD DEPOT RD, EL DORADO COUNTY, DIAMOND SPRINGS, 95619 | A | Government Agency | Active | Closing | 2021-10-23 | Actual | 2882 | Design | 1643059.11 | EAC | 570.1107 | Not Outlier | 1332.7096 | 3405.3082 | 6 | 1700252.11 | 631.37 | Yes | Civic/Scenic/Historical/Other Interest to General Public | No | No | No | Urban Cluster | 12 | 0 | N/A
SONOMA COUNTY | None | SONOMA | UNINCORPORATED | FREESTONE, UUD# 1 | R20A - FREESTONE SONOMA COUNTY ¦ 99-49000-02 ¦ 35056808 | BOHEMIAN HWY, FREESTONE ST & EL CAMINO BODEGA, FREESTONE, SONOMA COUNTY, 95465 | A | Government Agency | Active | Estimating/Design | 2024-07-12 | Forecast | TBD | Design | 5353246.91 | EAC | TBD | TBD | TBD | TBD | TBD | 514893.87 | 78467.03 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Rural | TBD | TBD | TBD
FRESNO | None | FRESNO | FRESNO | FRE-96 | CHURCH AVE FRESNO R20A ¦ 18-10023-01 ¦ 35067381 | CHURCH AVE BETWEEN WALNUT & MARTIN LUTHER KING BLVD, WALNUT AVE BETWEEN CHURCH AVE & GROVE AVE AND MARTIN LUTHER KING BLVD BETWEEN CHURCH AVE & GROVE AVE, FRESNO, 93706 | A | Government Agency | Active | Estimating/Design | 2024-03-15 | Forecast | TBD | Design | 2903744.84 | EAC | TBD | TBD | TBD | TBD | TBD | 314453.61 | 59500.72 | TBD | Arterial Street or Major Collector | Yes | No | TBD | Urban | TBD | TBD | TBD
CALAVERAS COUNTY | None | CALAVERAS | UNINCORPORATED | MOUNTAIN RANCH RD PH 1, UUD# 8 | MTN RANCH RD PH1 CALAVERAS COUNTY R20A ¦ 05-05000-01 ¦ 35067384 | MOUNTAIN RANCH RD, PARK DR & POPE ST, CALAVERAS COUNTY, 95249 | A | Government Agency | Active | Estimating/Design | TBD | TBD | TBD | Design | 1200138 | EAC | TBD | TBD | TBD | TBD | TBD | 87.92 | 5.46 | TBD | Civic/Scenic/Historical/Other Interest to General Public | No | TBD | TBD | Rural | TBD | TBD | TBD
NOVATO | None | MARIN | NOVATO | NOVATO BLVD, UUD# 16 | NOVATO BLVD NOVATO R20A ¦ 11-21019-01 ¦ 35076132 | NOVATO BLVD, DIABLO AVE & BOULEVARD TERRACE, NOVATO, 94947 | A | Government Agency | Active | Construction | 2025-04-17 | Forecast | TBD | Design | 4988146.79 | EAC | TBD | TBD | TBD | 3367.8411 | TBD | 317475.21 | 49264.93 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
SOUTH SAN FRANCISCO | None | SAN MATEO | SOUTH SAN FRANCISCO | MISSION RD UUD (CIP PROJECT ST1904) | MISSION RD SOUTH SAN FRANCISCO R20A ¦ 18-41029-01 ¦ 35118760 | ALONG MISSION RD FROM GRAND AVE TO THE SOUTHERN BART STATION ENTRANCE, SOUTH SAN FRANCISCO, 94080 | A | Government Agency | Active | Estimating/Design | 2024-06-19 | Forecast | TBD | Design | 2780516.03 | EAC | TBD | TBD | TBD | TBD | TBD | 118783.96 | 64656.5 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
YUBA CITY | None | SUTTER | YUBA CITY | BRIDGE ST, YUBA CITY | BRIDGE ST PH1 YUBA CITY R20A ¦ 18-51011-01 ¦ 35131205 | BRIDGE ST BETWEEN STATE ROUTE 99 & SECOND ST, YUBA CITY, 95991 | A | Government Agency | Active | Estimating/Design | 2025-01-09 | Forecast | TBD | Design | 2831972.43 | EAC | TBD | TBD | TBD | TBD | TBD | 271223.34 | 167236.06 | TBD | Arterial Street or Major Collector | Yes | TBD | TBD | Urban | TBD | TBD | TBD
TEHAMA COUNTY | None | TEHAMA | UNINCORPORATED | HIGHWAY 99E LOS MOLINOS UUD# 6 | HWY 99 E LOS MOLINOS TEHAMA CNTY R20A ¦ 18-52000-01 ¦ 35148904 | HIGHWAY 99E, MAREK RD & TEHAMA VINA RD, LOS MOLINOS, TEHAMA COUNTY, 96055 | A | Government Agency | Active | Estimating/Design | TBD | TBD | TBD | Design | 4412974.19 | EAC | TBD | TBD | TBD | TBD | TBD | 320683.21 | 62651.83 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban Cluster | TBD | TBD | TBD
SAN JOSE | None | SANTA CLARA | SAN JOSE | MONTEREY HWY, WILLOW ST TO CURTNER AVE | MONTEREY RD SAN JOSE R20A ¦ 89-43026-02 ¦ 35170365 | MONTEREY HWY, WILLOW ST TO CURTNER AVE, SAN JOSE, 95112 | A | Government Agency | Active | Estimating/Design | 2025-01-15 | Forecast | TBD | Design | 6283348.93 | EAC | TBD | TBD | TBD | TBD | TBD | 1728593.6 | 500703.85 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
MOUNTAIN VIEW | None | SANTA CLARA | MOUNTAIN VIEW | CALIFORNIA ST | EP CALIFORNIA ST MOUNTAIN VIEW ¦ 13-43021-01 ¦ 35175476 | CALIFORNIA ST, ESCUELA AVE & MARIPOSA AVE, MOUNTAIN VIEW, 94041 | A | Government Agency | Active | Estimating/Design | 2025-06-30 | Forecast | TBD | Design | 2560489.81 | EAC | TBD | TBD | TBD | TBD | TBD | 588842.22 | 75231.72 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
MARIN COUNTY | None | MARIN | UNINCORPORATED | REDWOOD HWY | R20A - REDWOOD HWY MARIN CNTY ¦ 20-21000-02 ¦ 35179157 | REDWOOD HWY, BELVEDERE DR & SEMINARY DR, MARIN COUNTY, 94941 | A | Government Agency | Active | Estimating/Design | 2024-10-17 | Forecast | TBD | Design | 4676303.75 | EAC | TBD | TBD | TBD | TBD | TBD | 107010.27 | 41765.71 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
CLOVIS | None | FRESNO | CLOVIS | UUD NO. 8 | BULLARD AVE CLOVIS 20A ¦ 19-10012-01 ¦ 35201154 | BULLARD AVE BETWEEN MINNEWAWA AVE & WOODWORTH AVE, CLOVIS, 93612 | A | Government Agency | Active | Estimating/Design | 2024-12-11 | Forecast | TBD | Design | 1940536.38 | EAC | TBD | TBD | TBD | TBD | TBD | 280087.75 | 111356.25 | TBD | Civic/Scenic/Historical/Other Interest to General Public | Yes | TBD | TBD | Urban | TBD | TBD | TBD
SUNNYVALE | None | SANTA CLARA | SUNNYVALE | WOLFE ROAD PH 2 | WOLFE RD PH 2 SUNNYVALE 20A ¦ 09-43032-03 ¦ 35297575 | WOLFE RD FROM EL CAMINO REAL TO OLD SAN FRANCISCO, SUNNYVALE, 94086 | A | Government Agency | Hold | Estimating/Design | 2025-07-24 | Forecast | TBD | Design | 4966573.54 | EAC | TBD | TBD | TBD | TBD | TBD | 372338.48 | 204564.77 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
LAKE COUNTY | None | LAKE | UNINCORPORATED | SOUTH MAIN ST - SODA BAY RD, LAKEPORT AREA, COUNTY OF LAKE | R7 R20A - MAIN ST, SODA BAY ¦ 01-17000-01 ¦ 74001800 | PHASE 1: SODA BAY RD & SOUTH MAIN ST, SYLVA LN, LAKEPORT, LAKE COUNTY, 95453 | A | Government Agency | Active | Estimating/Design | 2024-11-25 | Forecast | TBD | Design | 5623718 | EAC | TBD | TBD | TBD | TBD | TBD | 648006.68 | 48224.52 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Rural | TBD | TBD | TBD
SOLVANG | None | SANTA BARBARA | SOLVANG | MISSION DR/5TH ST | EP MISSION AND FIFTH SOLVANG R20A ¦ 13-42023-01 ¦ 31056750 | MISSION & 5TH, 5TH & COPENHAGEN, SOLVANG, 93463 | A | Government Agency | Hold | Estimating/Design | TBD | TBD | TBD | Design | 2503980.09 | EAC | TBD | TBD | TBD | TBD | TBD | 245685.66 | 15455.41 | TBD | Civic/Scenic/Historical/Other Interest to General Public | No | TBD | TBD | Urban Cluster | TBD | TBD | TBD
AMERICAN CANYON | None | NAPA | AMERICAN CANYON | GREEN ISLAND RD | GREEN ISLAND DR AMERICAN CANYON R20A ¦ 17-28001-01 ¦ 31363065 | GREEN ISLAND RD, COMMERCE BLVD & PAOLI LOOP, AMERICAN CANYON, 94503 | A | Government Agency | Active | Estimating/Design | 2023-08-04 | Forecast | TBD | Design | 841419.32 | EAC | TBD | TBD | TBD | 1153.0059 | TBD | 55316.53 | 10569.01 | TBD | Arterial Street or Major Collector | No | No | TBD | Urban | TBD | TBD | TBD
LARKSPUR | None | MARIN | LARKSPUR | DOHERTY DR, UUD# 2017-01 | DOHERTY DR LARKSPUR R20A ¦ 17-21014-01 ¦ 35029457 | DOHERTY DR, MAGNOLIA AVE & LUCKY DR, LARKSPUR, 94939 | A | Government Agency | Active | Closing | 2022-09-24 | Actual | 2691 | Design | 2705638.23 | EAC | 1005.4397 | Not Outlier | 5549.6275 | 2826.524 | 0 | 2714418.37 | 2318005.55 | Yes | Arterial Street or Major Collector | No | No | Yes | Urban | 13 | 0 | N/A
EL DORADO COUNTY | None | EL DORADO | UNINCORPORATED | MISSOURI FLAT RD WITHIN DIAMOND SPRINGS & EL DORADO UUD | MISSOURI FLAT RD EL DORADO CNTY R20A ¦ 18-09000-01 ¦ 35047931 | MISSOURI FLAT RD BETWEEN PLEASANT VALLEY RD & CHINA GARDEN RD, EL DORADO COUNTY, 95619 | A | Government Agency | Active | Closing | 2022-10-01 | Actual | 6200 | Design | 4633095.33 | EAC | 747.2734 | Not Outlier | 3195.6888 | 11379.7421 | 17 | 4073425.19 | 3753569.74 | Yes | Arterial Street or Major Collector | No | No | No | Urban Cluster | 27 | 0 | N/A
WINTERS | None | YOLO | WINTERS | FIRST ST AND ABBEY, WINTERS | R20A - NEWT'S EXPRESSWAY WINTERS ¦ 18-57015-01 ¦ 35051251 | ALLEY BETWEEN FIRST & RAILROAD AND BETWEEN ABBEY & MAIN, WINTERS, 95694 | A | Government Agency | Active | Closing | 2022-10-24 | Actual | 734 | Design | 1094862.11 | EAC | 1491.6378 | Not Outlier | 158.6018 | 514.7532 | 7 | 1065740.11 | 943437.71 | Yes | Civic/Scenic/Historical/Other Interest to General Public | No | No | No | Urban Cluster | 6 | 0 | N/A
STOCKTON | None | SAN JOAQUIN | STOCKTON | MINER AVE, AMERICAN, CALIFORNIA, STOCKTON | DOWNTOWN STOCKTON PH 2 R20A ¦ 17-39016-02 ¦ 35218375 | MINER AVE, AMERICAN, CALIFORNIA, STOCKTON, 95202 | A | Government Agency | Active | Construction | 2023-03-31 | Forecast | TBD | Design | 374573.72 | EAC | TBD | TBD | TBD | TBD | TBD | 374573.72 | 39980.64 | No | Civic/Scenic/Historical/Other Interest to General Public | Yes | TBD | No | Urban | TBD | TBD | TBD
NAPA | None | NAPA | NAPA | JEFFERSON ST | EP JEFFERSON ST. NAPA R20A ¦ 14-28006-01 ¦ 74003533 | JEFFERSON ST, LINCOLN AVE & TRANCAS ST, NAPA, 94558 | A | Government Agency | Active | Estimating/Design | 2025-07-15 | Forecast | TBD | Design | 9865051 | EAC | TBD | TBD | TBD | TBD | TBD | 625784.29 | 49977.19 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
SAN MATEO COUNTY | None | SAN MATEO | UNINCORPORATED | MIDDLEFIELD RD PH 2 | R7 MIDDLEFIELD RD PH2 S.MATEO CNTY R20A0 ¦ 02-41000-01 ¦ 74004302 | MIDDLEFIELD RD, FIFTH AVE & MACARTHUR AVE, REDWOOD CITY, SAN MATEO COUNTY, 94063 | A | Government Agency | Active | Estimating/Design | 2023-07-03 | Forecast | TBD | Design | 7671128.79 | EAC | TBD | TBD | TBD | 12493.2768 | TBD | 1696302.06 | 551289.35 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
EL DORADO COUNTY | None | EL DORADO | UNINCORPORATED | GREEN VALLEY RD | GREEN VALLEY RD EL DORADO CNTY R20A ¦ 16-09000-01 ¦ 74010582 | GREEN VALLEY RD, POODLE LN & MORTARA CIR, EL DORADO COUNTY, PLACERVILLE, 95667 | A | Government Agency | Active | Estimating/Design | 2024-12-09 | Forecast | TBD | Design | 2467784.9 | EAC | TBD | TBD | TBD | TBD | TBD | 309341.14 | 30165.45 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Rural | TBD | TBD | TBD
BAKERSFIELD | None | KERN | BAKERSFIELD | 34TH ST | 34TH STREET BAKERSFIELD R20A ¦ 14-15002-02 ¦ 74012450 | 34TH ST, CHESTER AVE TO UNION AVE, BAKERSFIELD, 93301 | A | Government Agency | Active | Estimating/Design | 2024-11-13 | Forecast | TBD | Design | 7357564.99 | EAC | TBD | TBD | TBD | TBD | TBD | 568599.97 | 51657.5 | TBD | Arterial Street or Major Collector | Yes | TBD | TBD | Urban | TBD | TBD | TBD
LOOMIS | None | PLACER | LOOMIS | SIERRA COLLEGE BLVD, LOOMIS | R20A: SIERRA COLLEGE BLVD, LOOMIS ¦ 17-31017-01 ¦ 74017840 | SIERRA COLLEGE BLVD, BRACE RD & GRANITE DR, LOOMIS, 95650 | A | Government Agency | Active | Estimating/Design | 2023-09-30 | Forecast | TBD | Design | 1119265.4 | EAC | TBD | TBD | TBD | TBD | TBD | 136900.33 | 11058.03 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
WALNUT CREEK | None | CONTRA COSTA | WALNUT CREEK | BONANZA ST, UUD# 15-1 | BONANZA ST WALNUT CREEK R20A ¦ 16-07039-01 ¦ 35029459 | BONANZA ST, CALIFORNIA BLVD & MT DIABLO BLVD, WALNUT CREEK, 94596 | A | Government Agency | Active | Construction | 2023-03-31 | Forecast | TBD | Design | 2754052.93 | EAC | TBD | TBD | TBD | 1925.6644 | TBD | 2884820.5 | 2416199.92 | Yes | Arterial Street or Major Collector | No | No | No | Urban | TBD | TBD | TBD
PARADISE | None | BUTTE | PARADISE | SKYWAY | BR-09-01A SKYWAY PARADISE R20A ¦ 16-04017-02 ¦ 35176012 | SKYWAY, JEWELL RD & VISTA WAY, PARADISE, 95969 | A | Government Agency | Active | Closing | 2022-07-11 | Actual | 1530 | Design | 2346432.46 | EAC | 1533.616 | Not Outlier | 1301.139 | 1681.2957 | 16 | 2290007.46 | 1259392.09 | Yes | Arterial Street or Major Collector | No | No | Yes | Urban Cluster | 8 | 0 | N/A
NEVADA CITY | None | NEVADA | NEVADA CITY | BROAD ST | 1B BROAD ST NEVADA CITY R20A ¦ 17-29006-01 ¦ 74013926 | BROAD ST, COTTAGE ST & BENNETS RD, NEVADA CITY, 95959 | A | Government Agency | Active | Closing | 2022-04-08 | Actual | 1189 | Design | 843738.34 | EAC | 709.6201 | Not Outlier | 619.2169 | 792.1712 | 12 | 965710.02 | 860778.63 | Yes | Arterial Street or Major Collector | No | No | No | Urban Cluster | 10 | 0 | N/A
PORTOLA VALLEY | None | SAN MATEO | PORTOLA VALLEY | ALPINE RD | 1B R1 ALPINE RD PORTOLA VALLEY R20A ¦ 13-41023-01 ¦ 30992944 | ALPINE RD, NATHHORST AVE & HILLBROOK DR, PORTOLA VALLEY, 94028 | A | Government Agency | Hold | Estimating/Design | TBD | TBD | TBD | Design | 641475.85 | EAC | TBD | TBD | TBD | TBD | TBD | 81304.05 | 5051.49 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Rural | TBD | TBD | TBD
TIBURON | None | MARIN | TIBURON | TIBURON BLVD | *CANC* -TIBURON BLVD, TIBURON - R20A ¦ 14-21030-01 ¦ 31172652 | TIBURON BLVD, LYFORD DR & NED'S WY, TIBURON, 94920 | A | Government Agency | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KERN COUNTY | None | KERN | UNINCORPORATED | STATE ROUTE 43 | *CANC*STATE ROUTE 43 KERN CNTY R20A ¦ 18-15000-01 ¦ 35040079 | STATE ROUTE 43 BETWEEN STATE ROUTE 119 & I-5, KERN COUNTY, 93276 | A | Government Agency | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ROHNERT PARK | None | SONOMA | ROHNERT PARK | ADRIAN DR, PH 2, UUD# 6 | *CANC*R7 ADRIAN DR PH2 ROHNERT PARK R20A ¦ 02-49032-01 ¦ 30247819 | ADRIAN DR, BRUCE AVE & E COTATI AVE, ROHNERT PARK, 94928 | A | Government Agency | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEWMAN | None | STANISLAUS | NEWMAN | KERN ST & MERCED ST PH 2, UUD# 5-A & 5-B | *CANC*R2 EP NEWMAN RULE 20A PHASE 2 ¦ 03-50000-03 ¦ 30657421 | MARIPOSA ST, N ST, TULARE ST, MAIN ST & FRESNO ST, N ST, MERCED ST, MAIN ST, NEWMAN, 95360 | A | Government Agency | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHOWCHILLA | None | MADERA | CHOWCHILLA | 2ND-6TH ST DIST 5 | *CANC*R2Z DISTRICT 5 CHOWCHILLA R20A 2N ¦ 03-20003-02 ¦ 30675657 | 2ND-6TH ST, ROBERTSON BLVD & TRINITY AVE, CHOWCHILLA, 93610 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 692195.42 | EAC | TBD | TBD | TBD | TBD | TBD | 692195.42 | 11422.61 | TBD | Civic/Scenic/Historical/Other Interest to General Public | No | TBD | TBD | Urban Cluster | TBD | TBD | TBD
NEWMAN | None | STANISLAUS | NEWMAN | KERN ST & MERCED ST PH 3, UUD# 5-C | *CANC*E NEWMAN PH3 R20A ¦ 03-50000-04 ¦ 30709856 | KERN ST, MAIN ST, MERCED ST, P ST, NEWMAN, 95360 | A | Government Agency | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FAIRFIELD | None | SOLANO | FAIRFIELD | TRAVIS BLVD, FAIRFIELD | *CANC* R6 TRAVIS BLVD FAIRFIELD R20A ¦ 06-48006-01 ¦ 30674762 | TRAVIS BLVD, FAIRFIELD, 94534 | A | Government Agency | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ARROYO GRANDE | None | SAN LUIS OBISPO | ARROYO GRANDE | EAST GRAND AVE, UUD# 6 | GRAND-HALCYON TO ELM ARROYO GRANDE R20A ¦ 05-40002-01 ¦ 30485630 | EAST GRAND AVE, ELM & HALCYON, ARROYO GRANDE, 93420 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 7222898.52 | EAC | TBD | TBD | TBD | TBD | TBD | 17220.09 | 1069.92 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
MARINA | None | MONTEREY | MARINA | RESERVATION RD, UUD# 2008-1 | RESERVATION RD MARINA R20A ¦ 08-27019-01 ¦ 30649669 | RESERVATION RD, DE FOREST AVE & CALIFORNIA AVE, MARINA, 93933 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 3166620.31 | EAC | TBD | TBD | TBD | TBD | TBD | 7600.67 | 472.26 | TBD | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | TBD | TBD | Urban | TBD | TBD | TBD
FRESNO | None | FRESNO | FRESNO | VENTURA AVE, UUD# FRE-85 | VENTURA AVE FRESNO R20A ¦ 07-10023-01 ¦ 30676932 | VENTURA AVE, M ST & STATE RT 99, FRESNO, 93721 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 2248406.87 | EAC | TBD | TBD | TBD | TBD | TBD | 8315.28 | 516.65 | TBD | Arterial Street or Major Collector | Yes | TBD | TBD | Urban | TBD | TBD | TBD
CALAVERAS COUNTY | None | CALAVERAS | UNINCORPORATED | MOUNTAIN RANCH RD PH 2, UUD# 8 | MTN RANCH RD PH2 CALAVERAS COUNTY R20A ¦ 05-05000-02 ¦ 30695568 | MOUNTAIN RANCH RD, E ST CHARLES ST & MARSHALL AVE, CALAVERAS COUNTY, 95249 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 1699467.86 | EAC | TBD | TBD | TBD | TBD | TBD | 347344.94 | 22520.36 | TBD | Civic/Scenic/Historical/Other Interest to General Public | No | TBD | TBD | Rural | TBD | TBD | TBD
PETALUMA | None | SONOMA | PETALUMA | BODEGA AVE PH 2 | R7 BODEGA AVE PH2 PETALUMA R20A ¦ 04-49030-02 ¦ 30762469 | BODEGA AVE, NORTH WEBSTER ST & KEOKUK ST, PETALUMA, 94952 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 3905638.96 | EAC | TBD | TBD | TBD | TBD | TBD | 28748.45 | 1785.87 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
SONOMA COUNTY | None | SONOMA | UNINCORPORATED | GRATON RD | R7 GRATON RD SONOMA CNTY R20A ¦ 99-49000-03 ¦ 30766668 | GRATON RD, RAILROAD AVE & S BRUSH ST, GRATON, SONOMA COUNTY, 95444 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 2056175.32 | EAC | TBD | TBD | TBD | TBD | TBD | 12275.6 | 762.47 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban Cluster | TBD | TBD | TBD
SANTA CLARA COUNTY | None | SANTA CLARA | SAN JOSE | ALMADEN EXPWY, SANTA CLARA COUNTY, UUD# 2 | R7 ALMADEN EXPWY SANTA CLARA CNTY R20A ¦ 07-43000-01 ¦ 30767366 | ALMADEN EXPWY, COLEMAN AVE & MESA DR, SAN JOSE, 95118 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 2792025.57 | EAC | TBD | TBD | TBD | TBD | TBD | 20186.84 | 1404.53 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
KINGSBURG | None | FRESNO | KINGSBURG | 10TH ST (ROOSEVELT SCHOOL) | 10TH AVE ROOSEVELT SCHOOL KINGSBURG R20A ¦ 04-10000-01 ¦ 30768527 | 10TH ST (ROOSEVELT SCHOOL), NEVADA & KERN, KINGSBURG, 93631 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 1285866.95 | EAC | TBD | TBD | TBD | TBD | TBD | 13443.63 | 835.27 | TBD | Arterial Street or Major Collector | Yes | TBD | TBD | Urban Cluster | TBD | TBD | TBD
SAN JOSE | None | SANTA CLARA | SAN JOSE | COLEMAN AVE PH 2, SAN JOSE | COLEMAN AVE PH 2 SAN JOSE R20A ¦ 09-43026-03 ¦ 30776258 | COLEMAN AVE, WEST HEDDING ST & SPRING ST , SAN JOSE, 95110 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 3268151.78 | EAC | TBD | TBD | TBD | TBD | TBD | 5078.02 | 315.49 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
CALAVERAS COUNTY | None | CALAVERAS | UNINCORPORATED | ST CHARLES ST, HWY 49, UUD# 9 | ST CHARLES (HWY 49) SAN ANDREAS R20A ¦ 99-05000-01 ¦ 30780266 | ST CHARLES ST, HWY 49, SAN ANDREAS, 95249 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 4307758 | EAC | TBD | TBD | TBD | TBD | TBD | 566457.2 | 36455.36 | TBD | Civic/Scenic/Historical/Other Interest to General Public | No | TBD | TBD | Rural | TBD | TBD | TBD
BERKELEY | None | ALAMEDA | BERKELEY | VISATMONT AVE, UUD# 35A | VISTAMONT AVE BERKELEY R20A ¦ 92-01005-02 ¦ 30817976 | VISTAMONT AVE, WILD CAT CANYON RD, MY WAY, ROCHDALE WAY, ROSEMONT AVE, BERKELEY, 94708 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 11412260 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Civic/Scenic/Historical/Other Interest to General Public | No | TBD | TBD | Urban | TBD | TBD | TBD
OROVILLE | None | BUTTE | OROVILLE | MYERS ST | MYERS ST OROVILLE R20A ¦ 11-04015-01 ¦ 30938105 | MYERS ST, ORO DAM BLVD & LINCOLN BLVD, OROVILLE, 95966 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 6559353 | EAC | TBD | TBD | TBD | TBD | TBD | 76.65 | 4.73 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban Cluster | TBD | TBD | TBD
DINUBA | None | TULARE | DINUBA | TRANSIT CENTER | DINUBA TRANSIT CENTER R20A ¦ 11-54007-01 ¦ 30959525 | L ST & M ST, FRESNO ST & MARIPOSA ST, DINUBA, 93618 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 988342.16 | EAC | TBD | TBD | TBD | TBD | TBD | 88050.2 | 5466.91 | TBD | Heavy Volume of Vehicular/Pedestrian/Other Traffic | Yes | TBD | TBD | Urban Cluster | TBD | TBD | TBD
SAN JOSE | None | SANTA CLARA | SAN JOSE | LINCOLN AVE | EP LINCOLN AVE SAN JOSE ¦ 10-43026-01 ¦ 35332988 | LINCOLN AVE, WEST SAN CARLOS ST & COE AVE, SAN JOSE, 95126 | A | Government Agency | Active | Planning | 2025-07-10 | Forecast | TBD | Preliminary | 5039288 | EAC | TBD | TBD | TBD | TBD | TBD | 94083.67 | 15117.79 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
SAN JOSE | None | SANTA CLARA | SAN JOSE | KIRK PARK | EP KIRK PARK SAN JOSE R20A ¦ 11-43026-01 ¦ 31085931 | FOXWORTHY AVE, YUCCA AVE & BRIARWOOD AVE, SAN JOSE, 95118 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 2379941.81 | EAC | TBD | TBD | TBD | TBD | TBD | 46928.91 | 2992.25 | TBD | Civic/Scenic/Historical/Other Interest to General Public | No | TBD | TBD | Urban | TBD | TBD | TBD
SANTA CRUZ | None | SANTA CRUZ | SANTA CRUZ | RIVERSIDE AVE | R2Z AD EP RIVERSIDE AVE SANTA CRUZ R20A ¦ 15-44017-01 ¦ 31218473 | RIVERSIDE AVE, 10TH ST & 24TH ST, SANTA CRUZ, 95060 | A | Government Agency | Active | Planning | 2024-07-18 | Forecast | TBD | Preliminary | 1596746.24 | EAC | TBD | TBD | TBD | TBD | TBD | 475722.36 | 28433.35 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
ORANGE COVE | None | FRESNO | ORANGE COVE | ANCHOR AVE | EP ANCHOR AVE ORANGE COVE R20A ¦ 16-10039-01 ¦ 31221681 | ACHOR AVE, NORTH OF PARK BLVD TO MARTINEZ ST, ORANGE COVE, 93646 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 2695948.62 | EAC | TBD | TBD | TBD | TBD | TBD | 1552.04 | 741.5 | TBD | Arterial Street or Major Collector | Yes | TBD | TBD | Urban Cluster | TBD | TBD | TBD
DALY CITY | None | SAN MATEO | DALY CITY | GENEVA AVE PH 2 | R7 GENEVA AVE PH2 DALY CITY R20A ¦ 05-41006-04 ¦ 35067382 | GENEVA AVE, SCHERWIN ST & BAYSHORE BLVD, DALY CITY, 94014 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 5695981 | EAC | TBD | TBD | TBD | TBD | TBD | 7420.5 | 616.07 | TBD | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | TBD | TBD | Urban | TBD | TBD | TBD
REEDLEY | None | FRESNO | REEDLEY | DINUBA AVE, UUD# 1 | REEDLEY SPORTS PARK, DINUBA AVE R20A ¦ 08-10000-03 ¦ 35067383 | DINUBA AVE, BUTTONWILLOW & TRAVER CHANNEL, REEDLEY, 93654 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 4844494.56 | EAC | TBD | TBD | TBD | TBD | TBD | 20099.76 | 2175.81 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Rural | TBD | TBD | TBD
FREMONT | None | ALAMEDA | FREMONT | UUD# 38 | FREMONT BLVD FREMONT R20A ¦ 18-01013-02 ¦ 35148903 | FREMONT BLVD BETWEEN ALDER AVE & THORNTON AVE, FREMONT, 94536 | A | Government Agency | Active | Planning | 2028-08-03 | Forecast | TBD | Preliminary | 2340170.67 | EAC | TBD | TBD | TBD | TBD | TBD | 53644.56 | 3332.99 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
FREMONT | None | ALAMEDA | FREMONT | UUD 37 | PERALTA BLVD FREMONT R20A ¦ 18-01013-01 ¦ 35148906 | PERALTA BLVD FROM FREMONT BLVD TO SEQUOIA RD, FREMONT, 94536 | A | Government Agency | Active | Planning | 2024-09-30 | Forecast | TBD | Preliminary | 1908369.45 | EAC | TBD | TBD | TBD | TBD | TBD | 75192.17 | 7686.48 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
CONCORD | None | CONTRA COSTA | CONCORD | MARKET ST | MARKET ST CONCORD R20A ¦ 10-07009-01 ¦ 35158246 | MARKET ST, WILLOW PASS RD & 1945 MARKET ST, CONCORD, 94520 | A | Government Agency | Active | Planning | 2026-03-26 | Forecast | TBD | Preliminary | 1021717.1 | EAC | TBD | TBD | TBD | TBD | TBD | 30572.24 | 2042.31 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
MARIN COUNTY | None | MARIN | UNINCORPORATED | NICASIO VALLEY RD | NICASIO VALLEY RD MARIN CNTY R20A ¦ 20-21000-01 ¦ 35179155 | NICASIO VALLEY RD, SOUTH OF TOWN CENTER & LUCAS VALLEY RD, MARIN COUNTY, 94946 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 3588124.2 | EAC | TBD | TBD | TBD | TBD | TBD | 119.19 | 7.41 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Rural | TBD | TBD | TBD
SALINAS | None | MONTEREY | SALINAS | WILLIAMS RD, PH 1, UUD# 24 | WILLIAMS RD SALINAS PH I R20A ¦ 13-27029-01 ¦ 35201155 | WILLIAMS RD, ALISAL ST & BARDIN RD, SALINAS, 93905 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 4750456.5 | EAC | TBD | TBD | TBD | TBD | TBD | 54887.34 | 26642.7 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
BURLINGAME | None | SAN MATEO | BURLINGAME | EL CAMINO REAL | EL CAMINO REAL BURLINGAME R20A ¦ 19-41004-01 ¦ 35246683 | EL CAMINO REAL, DAVIS D & BARROILHET AVE, BURLINGAME, 94010 | A | Government Agency | Active | Planning | 2025-05-19 | Forecast | TBD | Preliminary | 11294989.72 | EAC | TBD | TBD | TBD | TBD | TBD | 250094.44 | 108748.63 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
OAKLAND | None | ALAMEDA | OAKLAND | PIEDMONT PINES PH 2 | PIEDMONT PINES PH 2 OAKLAND R20A ¦ 00-01023-02 ¦ 35248565 | CHELTON DR, SKYLINE BLVD & SCARBOROUGH DR, OAKLAND, 94611 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 20163567 | EAC | TBD | TBD | TBD | TBD | TBD | 134250.34 | 25263.64 | TBD | Tariff Deviation Approved by CPUC | No | TBD | TBD | Urban | TBD | TBD | TBD
CHICO | None | BUTTE | CHICO | NORTH ESPLANADE DIST 17 | NORTH ESPLANADE CHICO R20A ¦ 16-04005-02 ¦ 35249254 | NORTH ESPLANADE, EATON RD & LEORA CT, CHICO, 95973 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 4722835.48 | EAC | TBD | TBD | TBD | TBD | TBD | 105675.41 | 11950.73 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
FAIRFAX | None | MARIN | FAIRFAX | BANK ST UUD #7 | BANK ST FAIRFAX R20A ¦ 19-21005-01 ¦ 35253350 | BANK ST, BROADWAY, BOLINAS RD & MONO AVE, FAIRFAX, 94930 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 622821.95 | EAC | TBD | TBD | TBD | TBD | TBD | 380.74 | 23.65 | TBD | Civic/Scenic/Historical/Other Interest to General Public | No | TBD | TBD | Urban | TBD | TBD | TBD
SAN MATEO | None | SAN MATEO | SAN MATEO | 25TH AVE PH 2, SAN MATEO, UUD# 87-2 | 25TH AVE PH 2 SAN MATEO R20A ¦ 87-41028-02 ¦ 35263904 | E 25TH AVE, SOUTH DELAWARE ST & S EL CAMINO REAL, SAN MATEO, 94403 | A | Government Agency | Active | Planning | 2024-10-01 | Forecast | TBD | Preliminary | 1456634.69 | EAC | TBD | TBD | TBD | TBD | TBD | 67837.23 | 16156.35 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
FERNDALE | None | HUMBOLDT | FERNDALE | FRANCIS ST | FRANCIS ST FERNDALE R20A ¦ 19-12015-01 ¦ 35277392 | FRANCIS ST BTW OCEAN AVE & END OF FRANCIS ST, FERNDALE, 95536 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 1542384.48 | EAC | TBD | TBD | TBD | TBD | TBD | 97.61 | 6.08 | TBD | Civic/Scenic/Historical/Other Interest to General Public | No | TBD | TBD | Rural | TBD | TBD | TBD
SHASTA COUNTY | None | SHASTA | UNINCORPORATED | HWY 299 | HWY 299 SHASTA R20A ¦ 20-45000-01 ¦ 35280505 | HWY 299, SECOND ST, MIDDLE CREEK RD, SHASTA COUNTY, 96087 | A | Government Agency | Active | Estimating/Design | TBD | TBD | TBD | Design | 1963510.4 | EAC | TBD | TBD | TBD | TBD | TBD | 177341.41 | 174006.18 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Rural | TBD | TBD | TBD
LOS ALTOS HILLS | None | SANTA CLARA | LOS ALTOS HILLS | EL MONTE RD | EL MONTE RD LOS ALTOS HILLS R20A ¦ 19-43013-01 ¦ 35300013 | EL MONTE RD & MOODY, GREEN HILL CT & EL MONTE FIRE STATION, LOS ALTOS HILLS, 94022 | A | Government Agency | Active | Estimating/Design | 2025-07-24 | Forecast | TBD | Design | 3672798.4 | EAC | TBD | TBD | TBD | TBD | TBD | 10324.4 | 10324.4 | TBD | Civic/Scenic/Historical/Other Interest to General Public | No | TBD | TBD | Urban | TBD | TBD | TBD
SANTA CRUZ | None | SANTA CRUZ | SANTA CRUZ | MISSION ST, PH 3, SANTA CRUZ | MISSION ST PH 3 SANTA CRUZ R20A ¦ 01-44017-02 ¦ 35316022 | MISSION ST, CENTER ST & CHESTNUT ST, SANTA CRUZ, 95060 | A | Government Agency | Active | Planning | 2025-09-26 | Forecast | TBD | Preliminary | 2120856.99 | EAC | TBD | TBD | TBD | TBD | TBD | 131474.4 | 10294.33 | TBD | Civic/Scenic/Historical/Other Interest to General Public | No | TBD | TBD | Urban | TBD | TBD | TBD
MERCED COUNTY | None | MERCED | UNINCORPORATED | DAN WARD RD, MERCED COUNTY | EP DAN WARD RD MERCED COUNTY R20A ¦ 15-24000-01 ¦ 74003380 | DAN WARD RD, FRANKLIN RD & BEACHWOOD DR, MERCED COUNTY, 95348 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 6190418 | EAC | TBD | TBD | TBD | TBD | TBD | 4735.3 | 294.2 | TBD | Civic/Scenic/Historical/Other Interest to General Public | Yes | TBD | TBD | Urban | TBD | TBD | TBD
SOUTH SAN FRANCISCO | None | SAN MATEO | SOUTH SAN FRANCISCO | SPRUCE AVE | SPRUCE AVE SOUTH SAN FRANCISCO ¦ 16-41029-01 ¦ 74009301 | SPRUCE AVE, LUX AVE & RAILROAD AVE, SOUTH SAN FRANCISCO, 94080 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 4216667.44 | EAC | TBD | TBD | TBD | TBD | TBD | 793.43 | 49.25 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
COALINGA | None | FRESNO | COALINGA | ELM AVE | ELM AVE COALINGA R20A ¦ 11-10013-01 ¦ 74013924 | ELM AVE, CHERRY LN TO LOS GATOS CREEK BRIDGE, COALINGA, 93210 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 1657344.98 | EAC | TBD | TBD | TBD | TBD | TBD | 679.48 | 42.21 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban Cluster | TBD | TBD | TBD
RIPON | None | SAN JOAQUIN | RIPON | STOCKTON AVE AND 5TH ST, RIPON | STOCKTON AVE, RIPON ¦ 05-39014-01 ¦ NO ORDER | STOCKTON AVE BTW FIFTH ST & MAIN ST, RIPON, 95366 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 3084183 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
SAN JOAQUIN COUNTY | None | SAN JOAQUIN | UNINCORPORATED | COUNTRY CLUB BLVD AND PERSHING AVE, STOCKTON | COUNTRY CLUB BLVD, SAN JOAQUIN COUNTY ¦ 21-39000-01 ¦ NO ORDER | COUNTRY CLUB BLVD BETWEEN FRANKLIN AVE AND PERSHING AVE, STOCKTON, 95204 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 4957326.05 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
STOCKTON | None | SAN JOAQUIN | STOCKTON | FREMONT ST, STOCKTON | FREMONT ST PH 2, STOCKTON ¦ 03-39016-02 ¦ NO ORDER | FREMONT ST, STOCKTON, 95202 | A | Government Agency | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STOCKTON | None | SAN JOAQUIN | STOCKTON | SOUTHSHORE, STOCKTON | SOUTHSHORE PH 2, STOCKTON ¦ 86-39016-02 ¦ NO ORDER | SOUTHSHORE, STOCKTON, 95207 | A | Government Agency | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRACY | None | SAN JOAQUIN | TRACY | VALPICO RD AND CORRAL HOLLOW RD, TRACY | VALPICO RD, TRACY ¦ 21-39018-01 ¦ NO ORDER | VALPICO RD FROM CORRAL HOLLOW RD TO CAGNEY WAY, TRACY, 95377 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 3362812.41 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
ATWATER | None | MERCED | ATWATER | BELLEVUE RD AND 13TH, ATWATER | BELLEVUE RD PH 2, ATWATER ¦ 09-24001-01 ¦ NO ORDER | BELLEVUE RD AND 13TH, ATWATER, 95302 | A | Government Agency | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DOS PALOS | None | MERCED | DOS PALOS | BLOSSOM ST, DOS PALOS | BLOSSOM ST, DOS PALOS ¦ 19-24006-01 ¦ NO ORDER | BLOSSOM ST, DOS PALOS, 93620 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 1808696 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | Yes | TBD | TBD | Urban Cluster | TBD | TBD | TBD
ESCALON | None | SAN JOAQUIN | ESCALON | FIRST STREET | FIRST STREET, ESCALON ¦ 19-39004-01 ¦ NO ORDER | FIRST STREET BTW STATE ROUTE 120 & MCHENRY AVE, ESCALON, 95320 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 2150178.89 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban Cluster | TBD | TBD | TBD
LOS BANOS | None | MERCED | LOS BANOS | H ST LOS BANOS | H STREET, LOS BANOS ¦ 20-24012-01 ¦ NO ORDER | H ST BTWN 2ND AND 6TH ST, LOS BANOS, 93635 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 2277810.91 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | Yes | TBD | TBD | Urban Cluster | TBD | TBD | TBD
NEWMAN | None | STANISLAUS | NEWMAN | MAIN AND MARIPOSA ST, NEWMAN | MAIN ST 5-A, NEWMAN ¦ 06-50012-01 ¦ NO ORDER | ALLEY BETWEEN MAIN ST & HWY 33 BETWEEN MARIPOSA ST AND TULARE ST, NEWMAN, 95360 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 1534562 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban Cluster | TBD | TBD | TBD
TUOLUMNE COUNTY | None | TUOLUMNE | UNINCORPORATED | TUOLUMNE CITY UUD | TUOLUMNE TOWNSITE, TUOLUMNE COUNTY ¦ 19-55000-01 ¦ NO ORDER | WILLOW AVE & PASSED ROZIER ST BETWEEN CHERRY LOOP & PASSED CARTER ST, TUOLUMNE COUNTY, 95379 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 5667279.63 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Civic/Scenic/Historical/Other Interest to General Public | No | TBD | TBD | Rural | TBD | TBD | TBD
DIXON | None | SOLANO | DIXON | EAST A STREET DIXON R20A UUD | EAST A STREET, DIXON ¦ 19-48004-01 ¦ NO ORDER | EAST A STREET BTW N. 2ND ST AND DOYLE LN, DIXON, 95620 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 2790534.48 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban Cluster | TBD | TBD | TBD
FAIRFIELD | None | SOLANO | FAIRFIELD | WEBSTER AND EMPIRE ST, FAIRFIELD | WEBSTER ST/EMPIRE ST, FAIRFIELD ¦ 20-48006-01 ¦ NO ORDER | WEBSTER AND EMPIRE ST, FAIRFIELD, 94533 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 2784003.15 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | Yes | TBD | TBD | Urban | TBD | TBD | TBD
ISLETON | None | SACRAMENTO | ISLETON | JACKSON BLVD | JACKSON BLVD, ISLETON ¦ 19-34014-01 ¦ NO ORDER | JACKSON BLVD FROM SECOND ST TO FOURTH ST, ISLETON, 95641 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 606570 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Civic/Scenic/Historical/Other Interest to General Public | No | TBD | TBD | Rural | TBD | TBD | TBD
RIO VISTA | None | SOLANO | RIO VISTA | MAIN ST PH 2 | MAIN ST PH 2, RIO VISTA ¦ 19-48010-01 ¦ NO ORDER | MAIN ST FROM 4TH ST TO HWY 12, RIO VISTA, 94571 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 2405502 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | Yes | TBD | TBD | Urban Cluster | TBD | TBD | TBD
WEST SACRAMENTO | None | YOLO | WEST SACRAMENTO | F ST, WEST SACRAMENTO | F STREET, WEST SACRAMENTO ¦ 20-57014-01 ¦ NO ORDER | F STREET, WEST SACRAMENTO, 95605 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 1412483.34 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | Yes | TBD | TBD | Urban | TBD | TBD | TBD
EL DORADO COUNTY | None | EL DORADO | UNINCORPORATED | PONDEROSA RD. SHINGLE SPRINGS | SHINGLE SPRINGS, EL DORADO COUNTY ¦ 19-09000-01 ¦ NO ORDER | PONDEROSA RD. SHINGLE SPRINGS, 95682 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 4262045.52 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
GRASS VALLEY | None | NEVADA | GRASS VALLEY | E MAIN ST | E. MAIN ST, GRASS VALLEY ¦ 18-29004-01 ¦ NO ORDER | E MAIN ST BETWEEN RICHARDSON ST & PASSED EUREKA ST, GRASS VALLEY, 95945 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 2071110 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban Cluster | TBD | TBD | TBD
MARYSVILLE | None | YUBA | MARYSVILLE | HWY 70 AND 12TH ST, MARYSVILLE | HWY 70, MARYSVILLE ¦ 20-58010-01 ¦ NO ORDER | HWY 70 12TH ST TO 15TH ST AND 14TH ST FROM D ST TO END AT RAILROAD TRACKS, MARYSVILLE, 95901 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 1250651.44 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | Yes | TBD | TBD | Urban | TBD | TBD | TBD
PLACER COUNTY | None | PLACER | NEWCASTLE | MAIN ST , NEWCASTLE | MAIN ST, NEWCASTLE ¦ 98-31000-01 ¦ NO ORDER | MAIN ST , NEWCASTLE, 95658 | A | Government Agency | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLACER COUNTY | None | PLACER | AUBURN | ATWOOD RD, AUBURN | ATWOOD RD, AUBURN ¦ 98-31000-02 ¦ NO ORDER | ATWOOD RD, AUBURN, 95603 | A | Government Agency | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLACER COUNTY | None | PLACER | AUBURN | BOWMAN RD, AUBURN | BOWMAN RD PH 1, AUBURN ¦ 98-31000-03 ¦ NO ORDER | BOWMAN RD, AUBURN, 95603 | A | Government Agency | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLACER COUNTY | None | PLACER | AUBURN | BOWMAN RD, AUBURN | BOWMAN RD PH 2, AUBURN ¦ 98-31000-04 ¦ NO ORDER | BOWMAN RD, AUBURN, 95603 | A | Government Agency | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SIERRA COUNTY | None | SIERRA | UNINCORPORATED | THE SIERRA CITY MAIN STREET PROJECT AND UUD | MAIN STREET, SIERRA CITY ¦ 19-46000-01 ¦ NO ORDER | MAIN ST SIERRA CITY, SIERRA CITY, 96125 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 7165277 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Rural | TBD | TBD | TBD
GREENFIELD | None | MONTEREY | GREENFIELD | EL CAMINO REAL | EL CAMINO REAL, GREENFIELD ¦ 19-27014-01 ¦ NO ORDER | EL CAMINO REAL BETWEEN THORNE RD & CHERRY AVE, GREENFIELD, 93927 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 2326381.53 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | TBD | TBD | Urban Cluster | TBD | TBD | TBD
KINGS COUNTY | None | KINGS | UNINCORPORATED | GENERAL PETROLEUM KETTLEMAN CITY | GENERAL PETROLEUM KETTLEMAN CITY, KINGS COUNTY ¦ 20-16000-01 ¦ NO ORDER | GENERAL PETROLEUM, 6TH STREET TO 9TH STREET, KETTLEMAN CITY, 93239 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 1540841.43 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Civic/Scenic/Historical/Other Interest to General Public | Yes | TBD | TBD | Rural | TBD | TBD | TBD
MONTEREY | None | MONTEREY | MONTEREY | NORTH FREMONT | NORTH FREMONT, MONTEREY ¦ 20-27020-01 ¦ NO ORDER | NORTH FREMONT, PALO VERDE AVE & CANYON DEL REY, MONTEREY, 93940 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 5301888.75 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
MONTEREY COUNTY | None | MONTEREY | UNINCORPORATED | CARMEL VALLEY AREA, UUD# 15 | CARMEL VALLEY RD PH 2, MONTEREY COUNTY ¦ 13-27000-01 ¦ NO ORDER | CARMEL VALLEY RD, PILOT RD & OAK MEADOW LN, CARMEL VALLEY, 93924 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 19304129 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban Cluster | TBD | TBD | TBD
MONTEREY COUNTY | None | MONTEREY | UNINCORPORATED | CARMEL HIGHLANDS AREA UUD 16 | CARMEL HIGHLANDS AREA UUD 16, MONTEREY COUNTY ¦ 18-27000-01 ¦ NO ORDER | STATE ROUTE 1, RIO RD & MAL PASO CREEK, CARMEL, 93923 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 10000000 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Rural | TBD | TBD | TBD
PACIFIC GROVE | None | MONTEREY | PACIFIC GROVE | CENTRAL AVE | CENTRAL AVE DISTRICT, PACIFIC GROVE ¦ 19-27022-01 ¦ NO ORDER | CENTRAL AVE, FOUNTAIN TO 2ND, PACIFIC GROVE, 93950 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 3144489.6 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
SAN BENITO COUNTY | None | SAN BENITO | UNINCORPORATED | HIGHWAY 156 | HIGHWAY 156, SAN BENITO COUNTY ¦ 19-35000-01 ¦ NO ORDER | 100 YARDS ON EITHER SIDE OF HWY 156 BTW UNION RD & BREEN RD, HOLLISTER, 95045 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 24811514.81 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Rural | TBD | TBD | TBD
SAND CITY | None | MONTEREY | SAND CITY | CALIFORNIA ST | CALIFORNIA ST, SAND CITY ¦ 75-27032-01 ¦ NO ORDER | CALIFORNIA AVE, HICKORY ST & ORLAND AVE, SAND CITY, 93955 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 1851638.96 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
SANTA CRUZ COUNTY | None | SANTA CRUZ | UNINCORPORATED | SOQUEL SAN JOSE RD DIST. 20 | SOQUEL SAN JOSE RD STA CRUZ CNTY 20 R20A ¦ 21-44000-01 ¦ 35322308 | SOQUEL SAN JOSE RD, LAUREL GLEN RD TO OLIVE SPRINGS RD, SOQUEL, 95073 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 8599556 | EAC | TBD | TBD | TBD | TBD | TBD | 203.54 | 203.54 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Rural | TBD | TBD | TBD
SANTA CRUZ COUNTY | None | SANTA CRUZ | UNINCORPORATED | SOQUEL SAN JOSE RD DIST. 21 | SOQUEL SAN JOSE RD DIST. 21, SANTA CRUZ COUNTY ¦ 21-44000-02 ¦ NO ORDER | SOQUEL SAN JOSE RD, OLIVE SPRINGS RD TO HOOVER RD, SOQUEL, 95073 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 5014768.03 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Rural | TBD | TBD | TBD
SANTA CRUZ COUNTY | None | SANTA CRUZ | UNINCORPORATED | SOQUEL SAN JOSE RD DIST. 22 | SOQUEL SAN JOSE RD DIST. 22, SANTA CRUZ COUNTY ¦ 21-44000-03 ¦ NO ORDER | SOQUEL SAN JOSE RD, HOOVER RD TO AMAYA RIDGE RD, SOQUEL, 95073 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 8310166.33 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Rural | TBD | TBD | TBD
SANTA CRUZ COUNTY | None | SANTA CRUZ | UNINCORPORATED | EMPIRE GRADE DIST. 23 | EMPIRE GRADE DIST. 23, SANTA CRUZ COUNTY ¦ 21-44000-04 ¦ NO ORDER | EMPIRE GRADE, PINE FLAT RD TO ALBA RD, SANTA CRUZ, 95060 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 14535872.72 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Rural | TBD | TBD | TBD
SANTA CRUZ COUNTY | None | SANTA CRUZ | UNINCORPORATED | BEAR CREEK RD DIST. 24 | BEAR CREEK RD DIST. 24, SANTA CRUZ COUNTY ¦ 21-44000-05 ¦ NO ORDER | BEAR CREEK RD, HARMON GULCH RD TO STARR CREEK RD, BOULDER CREEK, 95006 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 12742538.25 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Rural | TBD | TBD | TBD
SANTA CRUZ COUNTY | None | SANTA CRUZ | UNINCORPORATED | TROUT GULCH & VALENCIA RD DIST. 25 | TROUT GULCH & VALENCIA RD DIST. 25, SANTA CRUZ COUNTY ¦ 21-44000-06 ¦ NO ORDER | TROUT GULC/VALENCIA RD, QUAL RUN RD TO MARTHAS WAY, APTOS, 95003 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 10597537.15 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
SOLEDAD | None | MONTEREY | SOLEDAD | MONTEREY ST, | MONTEREY ST, SOLEDAD ¦ 20-27034-01 ¦ NO ORDER | MONTEREY ST, MAIN & SOLEDAD, SOLEDAD, 93960 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 620689.96 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban Cluster | TBD | TBD | TBD
WATSONVILLE | None | SANTA CRUZ | WATSONVILLE | LAKE AVE, UUD# 21 | LAKE AVE, WATSONVILLE ¦ 14-44021-01 ¦ NO ORDER | LAKE AVE, RODRIGUEZ ST & BRENNAN ST & UNION ST, WATSONVILLE, 95076 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 2386616 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | Yes | TBD | TBD | Urban | TBD | TBD | TBD
CUPERTINO | None | SANTA CLARA | CUPERTINO | STEVENS CREEK BLVD, UUD# 16 | STEVENS CREEK BLVD DIST 16, CUPERTINO ¦ 99-43008-01 ¦ NO ORDER | STEVENS CREEK BLVD, PHAR LAP DR & JANICE AVE, CUPERTINO, 95014 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 2700000 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
BUELLTON | None | SANTA BARBARA | BUELLTON | CENTRAL AVE | CENTRAL AVE, BUELLTON ¦ 20-42003-01 ¦ NO ORDER | CENTRAL AVE, OAKSIDE LANE & FIRST ST, BUELLTON 93427 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 5198696.27 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban Cluster | TBD | TBD | TBD
GUADALUPE | None | SANTA BARBARA | GUADALUPE | E. 11TH ST | E. 11TH ST, GUADALUPE ¦ 20-42010-01 ¦ NO ORDER | 11TH, PERALTA ST & ESCALANTE ST, GUADALUPE, 93434 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 1183704.2 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | Yes | TBD | TBD | Urban Cluster | TBD | TBD | TBD
MORRO BAY | None | SAN LUIS OBISPO | MORRO BAY | MORRO BAY BLVD | MORRO BAY BLVD, MORRO BAY ¦ 98-40017-01 ¦ NO ORDER | MORRO BAY BLVD, S MAIN TO BERNARDO AVE, MORRO BAY, 93443 | A | Government Agency | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAN LUIS OBISPO COUNTY | None | SAN LUIS OBISPO | UNINCORPORATED | SAN LUIS DR, UUD# 31 | SAN LUIS DRIVE, AVILA BEACH ¦ 14-40000-01 ¦ NO ORDER | SAN LUIS DR, SAN RAFAEL ST & FIRST ST, AVILA BEACH, 93424 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 2163186 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Civic/Scenic/Historical/Other Interest to General Public | No | TBD | TBD | Urban | TBD | TBD | TBD
GILROY | None | SANTA CLARA | GILROY | MONTEREY RD | MONTEREY RD, GILROY ¦ 20-43009-01 ¦ NO ORDER | MONTEREY RD, W EIGHTH & W TENTH, GILROY, 95020 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 2085065 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | Yes | TBD | TBD | Urban | TBD | TBD | TBD
HURON | None | FRESNO | HURON | LASSEN AVE PH 3 | LASSEN AVE PH 3, HURON ¦ 19-10030-01 ¦ NO ORDER | LASSEN AVE BTW 9TH ST & PALMER AVE, HURON, 93234 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 3226138.04 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | Yes | TBD | TBD | Urban Cluster | TBD | TBD | TBD
SAN JOAQUIN | None | FRESNO | SAN JOAQUIN | COLORADO AVE | COLORADO AVE, SAN JOAQUIN ¦ 20-10047-01 ¦ NO ORDER | COLORADO AVE, 11TH TO 9TH, SAN JOAQUIN, 93660 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 1191343.23 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | Yes | TBD | TBD | Urban Cluster | TBD | TBD | TBD
SELMA | None | FRESNO | SELMA | MCCALL AVE | MCCALL AVE, SELMA ¦ 20-10049-01 ¦ NO ORDER | MCCALL AVE, E. DINUBA & FLORAL AVE, SELMA, 93662 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 7949336.91 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | Yes | TBD | TBD | Urban Cluster | TBD | TBD | TBD
SELMA | None | FRESNO | SELMA | DINUBA AVE | DINUBA AVE, SELMA ¦ 20-10049-02 ¦ NO ORDER | DINUBA AVE, MITCHELL AVE & WRIGHT STREET, SELMA, 93662 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 5458812.77 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | Yes | TBD | TBD | Urban Cluster | TBD | TBD | TBD
SELMA | None | FRESNO | SELMA | FLORAL AVE | FLORAL AVE, SELMA ¦ 20-10049-03 ¦ NO ORDER | FLORAL AVE, C STREET & DOCKERY AVE, SELMA, 93662 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 2362310.52 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | Yes | TBD | TBD | Urban Cluster | TBD | TBD | TBD
SELMA | None | FRESNO | SELMA | NEBRASKA AVE | NEBRASKA AVE, SELMA ¦ 20-10049-04 ¦ NO ORDER | NEBRASKA AVE, HIGHLAND AVE & 2ND STREET, SELMA, 93662 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 4484226.07 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | Yes | TBD | TBD | Urban Cluster | TBD | TBD | TBD
SELMA | None | FRESNO | SELMA | SECOND ST | SECOND ST, SELMA ¦ 20-10049-05 ¦ NO ORDER | SECOND ST, NEBRASKA AVE & HIGHWAY 99, SELMA, 93662 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 2034621.16 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | Yes | TBD | TBD | Urban Cluster | TBD | TBD | TBD
ARVIN | None | KERN | ARVIN | UUD #1 | VARSITY RD, ARVIN ¦ 19-15001-01 ¦ NO ORDER | VARSITY RD BTW COMANCHE DR & CAMPUS DR, ARVIN, 93203 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 3025242.88 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | Yes | TBD | TBD | Rural | TBD | TBD | TBD
KERN COUNTY | None | KERN | UNINCORPORATED | BELLE TERRACE | BELLE TERRACE, KERN COUNTY ¦ 20-15000-01 ¦ NO ORDER | BELLE TERRACE, STINE & H STREET, BAKERSFIELD, 93304 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 14866602.67 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | Yes | TBD | TBD | Urban | TBD | TBD | TBD
SHAFTER | None | KERN | SHAFTER | SOUTH SHAFTER AVE | SOUTH SHAFTER AVE, SHAFTER ¦ 20-15048-01 ¦ NO ORDER | SOUTH SHAFTER AVE, LERDO HWY & LOS ANGELES AVE, SHAFTER, 93263 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 3911056.3 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | Yes | TBD | TBD | Urban Cluster | TBD | TBD | TBD
CLAYTON | None | CONTRA COSTA | CLAYTON | MARSH CREEK RD | MARSH CREEK RD, CLAYTON ¦ 20-07008-01 ¦ NO ORDER | MARSH CREEK RD, HIGH ST & STRANAHAN CR, CLAYTON, 94517 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 818336.43 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
DANVILLE | None | CONTRA COSTA | DANVILLE | CAMINO TASSAJARA PH 2 | CAMINO TASSAJARA PH 2, DANVILLE ¦ 03-07011-02 ¦ NO ORDER | CAMINO TASSAJARA, WOODSIDE DR & CROW CANYON RD, DANVILLE, 94506 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 9537435.12 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
ORINDA | None | CONTRA COSTA | ORINDA | CAMINO PABLO | CAMINO PABLO, ORINDA ¦ 20-07025-01 ¦ NO ORDER | CAMINO PABLO,CAMINO SOBRANTE & EL TOYONAL, ORINDA, 94563 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 1548780.67 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
EL CERRITO | None | CONTRA COSTA | EL CERRITO | CIVIC CENTER | CIVIC CENTER, EL CERRITO ¦ 19-07014-01 ¦ NO ORDER | MANILA AVE BTW RICHMOND ST & SAN PABLO AVE, KEARNEY ST BTW MANILA AVE & SCHMIDT LN, EL CERRITO, 94530 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 3266321.05 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
EMERYVILLE | None | ALAMEDA | EMERYVILLE | HOLLIS ST | HOLLIS ST, EMERYVILLE ¦ 20-01012-01 ¦ NO ORDER | HOLLIS ST, 59TH ST & 67TH ST, EMERYVILLE, 94608 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 5932663 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
OAKLAND | None | ALAMEDA | OAKLAND | PIEDMONT PINES AREA, UUD# 232 | PIEDMONT PINES PH 3, OAKLAND ¦ 00-01023-03 ¦ NO ORDER | CASTLE DR/SKYLINE BLVD FROM MOUNTAINGATE WAY TO ASCOT DR, OAKLAND, 94611 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 14847768.29 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
CORTE MADERA | None | MARIN | CORTE MADERA | REDWOOD AVE | REDWOOD AVE, CORTE MADERA ¦ 21-21003-01 ¦ NO ORDER | REDWOOD AVE, CORTE MADERA AVE, EDISON AVE & PORTOLA WAY, CORTE MADERA, 94925 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 1447172.49 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
ROSS | None | MARIN | ROSS | SIR FRANCIS DRAKE BLVD - TOWN ADMINISTRATION UUD NO. 1 | SIR FRANCIS DRAKE BLVD, ROSS ¦ 19-21022-01 ¦ NO ORDER | SIR FRANCIS DRAKE BLVD BETWEEN PRIOR LAGUNITAS RD & PASSED LAUREL GROVE AVE, ROSS, 94957 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 1237411.59 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Civic/Scenic/Historical/Other Interest to General Public | No | TBD | TBD | Urban | TBD | TBD | TBD
SAN RAFAEL | None | MARIN | SAN RAFAEL | MANUAL T. FREITAS PARKWAY | FREITAS PARKWAY, SAN RAFAEL ¦ 19-21026-01 ¦ NO ORDER | MANUAL T. FREITAS PARKWAY FROM HWY 101 TO LAS GALLINAS AVE, SAN RAFAEL, 94903 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 4553946.87 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
TIBURON | None | MARIN | TIBURON | TIBURON BLVD | TIBURON BLVD, TIBURON ¦ 20-21030-01 ¦ NO ORDER | TIBURON BLVD, NED'S WAY & LYFORD DR, TIBURON, 94920 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 1683564 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
VALLEJO | None | SOLANO | VALLEJO | UUD NO. 19-1 | SACRAMENTO ST, VALLEJO ¦ 19-48014-01 ¦ NO ORDER | SACRAMENTO ST BTW PIKE ST & FRISBIE ST, VALLEJO, 94590 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 5681452.83 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
YOUNTVILLE | None | NAPA | YOUNTVILLE | YOUNTVILLE PARK UNDERGROUND UTILITY ZONE | YOUNTVILLE PARK, YOUNTVILLE ¦ 19-28014-01 ¦ NO ORDER | YOUNTVILLE PARK BETWEEN YOUNT MILL RD & PASSED WASHINGTON ST, YOUNTVILLE, 94599 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 1571431.98 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Civic/Scenic/Historical/Other Interest to General Public | No | TBD | TBD | Urban Cluster | TBD | TBD | TBD
HAYWARD | None | ALAMEDA | HAYWARD | MISSION BLVD DISTRICT 29 HAYWARD | MISSION BLVD DIST 29, HAYWARD ¦ 10-01015-01 ¦ NO ORDER | MISSION BLVD, ROSE ST & A ST, HAYWARD, 94541 | A | Government Agency | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NEWARK | None | ALAMEDA | NEWARK | NEWARK UNDERGROUND DISTRICT NO. 15 | NEWARK BLVD, NEWARK ¦ 19-01022-01 ¦ NO ORDER | NEWARK BLVD BTW FAIR AVE & BELLHAVEN AVE, NEWARK, 94560 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 1748975.56 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
SAN LEANDRO | None | ALAMEDA | OAKLAND | EDEN RD | EDEN RD, SAN LEANDRO ¦ 11-01026-01 ¦ NO ORDER | EDEN RD, DOOLITTLE DR & DAVIS ST, SAN LEANDRO, 94603 | A | Government Agency | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BRISBANE | None | SAN MATEO | BRISBANE | CENTRAL BRISBANE | CENTRAL BRISBANE, BRISBANE ¦ 20-41003-01 ¦ NO ORDER | SAN BRUNO AVE, SAN FRANCISCO AVE & WILLIAMS AVE, BRISBANE, 94005 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 7995647.65 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
COLMA | None | SAN MATEO | COLMA | COLLINS AVE | COLLINS AVE, COLMA ¦ 20-41005-01 ¦ NO ORDER | COLLINS AVE, EL CAMINO REAL & JUNIPERO SERRA BLVD, COLMA, 94014 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 1132273 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Heavy Volume of Vehicular/Pedestrian/Other Traffic | No | TBD | TBD | Urban | TBD | TBD | TBD
MENLO PARK | None | SAN MATEO | MENLO PARK | ALMA ST | ALMA ST, MENLO PARK ¦ 20-41017-01 ¦ NO ORDER | ALMA ST, BURGESS PARK & BURGESS DR, MENLO PARK, 94025 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 1320451.45 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Civic/Scenic/Historical/Other Interest to General Public | No | TBD | TBD | Urban | TBD | TBD | TBD
MENLO PARK | None | SAN MATEO | MENLO PARK | MENLO AVE | MENLO AVE, MENLO PARK ¦ 20-41017-02 ¦ NO ORDER | MENLO AVE, UNIVERSITY DR & EL CAMINO REAL, MENLO PARK, 94025 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 5127768.48 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
MENLO PARK | None | SAN MATEO | MENLO PARK | MIDDLEFIELD RD | MIDDLEFIELD RD, MENLO PARK ¦ 20-41017-03 ¦ NO ORDER | MIDDLEFIELD RD, RAVENSWOOD AVE & WILLOW RD, MENLO PARK, 94025 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 6304944.8 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
MILLBRAE | None | SAN MATEO | MILLBRAE | MILLBRAE AVE | MILLBRAE AVE, MILLBRAE ¦ 20-41018-01 ¦ NO ORDER | MILLBRAE AVE, MINORCA WAY & MAGNOLIA AVE, MILLBRAE, 94030 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 5395797.04 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
SAN BRUNO | None | SAN MATEO | SAN BRUNO | CRYSTAL SPRINGS RD PH 1 | CRYSTAL SPRINGS RD PH 1, SAN BRUNO ¦ 20-41025-01 ¦ NO ORDER | CRYSTAL SPRINGS RD, PALOMAR CT & NILES AVE, SAN BRUNO, 94066 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 4698569 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
ARCATA | None | HUMBOLDT | ARCATA | DISTRICT 8 PH 1 | DISTRICT 8, ARCATA ¦ 20-12003-01 ¦ NO ORDER | H ST, 11TH ST & 13TH ST, G ST, 11TH ST & 13TH ST, ARCATA, 95521 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 2792265.66 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban Cluster | TBD | TBD | TBD
FERNDALE | None | HUMBOLDT | FERNDALE | SHAW TO HERBERT | MAIN ST, FERNDALE ¦ 19-12015-02 ¦ NO ORDER | MAIN ST, SHAW AVE & HERBERT ST, FERNDALE, 95536 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 3194539.05 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Rural | TBD | TBD | TBD
HUMBOLDT COUNTY | None | HUMBOLDT | UNINCORPORATED | TOWN SQUARE UUD | GARBERVILLE TOWN SQUARE, GARBERVILLE ¦ 19-12000-01 ¦ NO ORDER | SECOND ST BTW CHURCH ST & CONGER ST AND ON CHURCH ST BTW LOCUST ST & REDWOOD DR, GARBERVILLE, 95542 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 2000000 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Civic/Scenic/Historical/Other Interest to General Public | No | TBD | TBD | Rural | TBD | TBD | TBD
LAKEPORT | None | LAKE | LAKEPORT | 11TH ST | 11 ST, LAKEPORT ¦ 19-17010-01 ¦ NO ORDER | 11TH ST, MAIN ST & CENTRAL PARK AVE, LAKEPORT, 95453 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 8617739.26 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban Cluster | TBD | TBD | TBD
POINT ARENA | None | MENDOCINO | POINT ARENA | SCHOOL ST | SCHOOL ST, POINT ARENA ¦ 19-23021-01 ¦ NO ORDER | SCHOOL ST & PASSED LAKE ST, POINT ARENA, 95468 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 4061766.96 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Rural | TBD | TBD | TBD
RIO DELL | None | HUMBOLDT | RIO DELL | UUD NO. 2 | WILDWOOD AVE PH 2, RIO DELL ¦ 95-12040-01 ¦ NO ORDER | WILDWOOD AVE FROM ASH ST TO WEST BRIDGE/EAST BRIDGE STREETS, RIO DELL, 95562 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 434994.86 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban Cluster | TBD | TBD | TBD
WILLITS | None | MENDOCINO | WILLITS | SNIDER PARK | SNIDER PARK, WILLITS ¦ 19-23028-01 ¦ NO ORDER | SNIDER PARK ALONG STATE ST, MARIN ST, HUMBOLDT ST, E. COMMERCIAL ST, WILLITS, 95490 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 2348039.11 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Civic/Scenic/Historical/Other Interest to General Public | No | TBD | TBD | Urban Cluster | TBD | TBD | TBD
CORNING | None | TEHAMA | CORNING | CORNING CITY PLAZA | CITY PLAZA, CORNING ¦ 19-52001-01 ¦ NO ORDER | SOLANO ST & MARIN ST BETWEEN 3RD ST & 4TH ST, CORNING, 96021 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 649711.63 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Civic/Scenic/Historical/Other Interest to General Public | No | TBD | TBD | Urban Cluster | TBD | TBD | TBD
ORLAND | None | GLENN | ORLAND | PAPST AVE | PAPST AVE, ORLAND ¦ 19-11007-01 ¦ NO ORDER | PAPST AVE BTW SOUTH ST & E. SWIFT ST, ORLAND, 95963 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 2700000 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban Cluster | TBD | TBD | TBD
TEHAMA | None | TEHAMA | TEHAMA | 5TH STREET | 5TH STREET, TEHAMA ¦ 19-52013-01 ¦ NO ORDER | 5TH STREET BETWEEN C AND I STREETS, TEHAMA, 96021 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 1636421.42 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban Cluster | TBD | TBD | TBD
COTATI | None | SONOMA | COTATI | CHARLES ST | CHARLES ST, COTATI ¦ 20-49010-01 ¦ NO ORDER | CHARLES ST, OLD REDWOOD HWY & E. COTATI AVE, COTATI, 94931 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 975907.35 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
ROHNERT PARK | None | SONOMA | UNINCORPORATED | SNYDER LN | SNYDER LANE, ROHNERT PARK ¦ 21-49032-01 ¦ NO ORDER | SNYDER LN, KEISER AVE & CRANE CREEK, ROHNERT PARK, 95404 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 837479.3 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Rural | TBD | TBD | TBD
SONOMA COUNTY | None | SONOMA | UNINCORPORATED | SALMON CREEK, UUD# 1 | SALMON CREEK, SONOMA COUNTY ¦ 97-49000-01 ¦ NO ORDER | HIGHWAY 1, BEAN AVE, OCEAN VIEW & CHURCHILL ST, BODEGA BAY, SONOMA COUNTY, 94923 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 1280000 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Civic/Scenic/Historical/Other Interest to General Public | No | TBD | TBD | Rural | TBD | TBD | TBD
WINDSOR | None | SONOMA | WINDSOR | WINDSOR RD | WINDSOR RD PH 1, WINDSOR ¦ 20-49043-01 ¦ NO ORDER | WINDSOR RD, PLANT RD & REIMAN LN, WINDSOR, 95492 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 1000000 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
FORT BRAGG | None | MENDOCINO | FORT BRAGG | CHESTNUT ST | CHESTNUT ST PH1, FORT BRAGG ¦ 21-23011-01 ¦ NO ORDER | CHESTNUT ST, MAIN ST & EBBING WAY, FORT BRAGG, 95437 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 2369156.24 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban Cluster | TBD | TBD | TBD
YUBA CITY | None | SUTTER | YUBA CITY | SECOND ST, YUBA CITY | *CANC* SECOND ST YUBA CITY PH II R20A ¦ 12-51011-02 ¦ 74010531 | SECOND ST, YUBA CITY, 95991 | A | Government Agency | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CONTRA COSTA COUNTY | None | CONTRA COSTA | UNINCORPORATED | UNDERGROUND UTILITY DISTRICT NO. 32 | APPIAN WAY, CONTRA COSTA COUNTY ¦ 22-07000-01 ¦ NO ORDER | APPIAN WAY BTWN ARGYLE ROAD & ALLVIEW AVE, CONTRA COSTA COUNTY, 94803 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 4844842.96 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
RICHMOND | None | CONTRA COSTA | RICHMOND | PIERCE ST & SAN MATEO ST | PIERCE ST & SAN MATEO ST, RICHMOND ¦ 22-07033-01 ¦ NO ORDER | PIERCE ST & SAN MATEO ST, RICHMOND, 94804 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | 1455032.67 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
CUPERTINO | None | SANTA CLARA | CUPERTINO | DISTRICT NO. 15, STEVENS CREEK BLVD | STEVENS CREEK BLVD DIST 15, CUPERTINO ¦ 99-43008-02 ¦ NO ORDER | DISTRICT NO. 15, STEVENS CREEK BLVD BETWEEN ROUTE 85 AND BYRNE AVE, 95014 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 4061198.38 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Urban | TBD | TBD | TBD
MORRO BAY | SAN LUIS OBISPO COUNTY | SAN LUIS OBISPO | UNINCORPORATED | SOUTH BAY BLVD | SOUTH BAY BLVD, MORRO BAY/SLO COUNTY ¦ 14-40000-02 ¦ NO ORDER | SOUTH BAY BLVD, CHORRO CREEK BRIDGE TO TURRI RD, MORRO BAY, 93442 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | TBD | EAC | TBD | TBD | TBD | TBD | see 1st sponsor | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Rural | see 1st sponsor | TBD | TBD
SAN LUIS OBISPO COUNTY | MORRO BAY | SAN LUIS OBISPO | UNINCORPORATED | SOUTH BAY BLVD | SOUTH BAY BLVD, MORRO BAY/SLO COUNTY ¦ 14-40000-02 ¦ NO ORDER | SOUTH BAY BLVD, CHORRO CREEK BRIDGE TO TURRI RD, MORRO BAY, 93442 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | TBD | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Rural | TBD | TBD | TBD
ALAMEDA COUNTY | None | ALAMEDA | UNINCORPORATED | UNDERGROUND UTILITY DISTRICT NO. 20 | TESLA RD, ALAMEDA COUNTY ¦ 22-01000-01 ¦ NO ORDER | TESLA RD & S LIVERMORE AVE BTWN GREENVILLE RD & BEFORE CONCANNON BLVD, ALAMEDA COUNTY, 94550 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | 17705345.47 | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Arterial Street or Major Collector | No | TBD | TBD | Rural | TBD | TBD | TBD
MANTECA | None | SAN JOAQUIN | MANTECA | MCKINLEY AVE UNDERGROUND UTILITY DISTRICT | MCKINLEY AVE, MANTECA ¦ 21-39013-01 ¦ NO ORDER | MCKINLEY AVE BETWEEN BRONZAN RD AND W WOODARD AVE, MANTECA, 95337 | A | Government Agency | Active | Planning | TBD | TBD | TBD | Preliminary | TBD | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Pending CPUC acceptance of project qualification variance | Yes | TBD | TBD | Urban | TBD | TBD | TBD
EL DORADO COUNTY | None | EL DORADO | UNINCORPORATED | DIAMOND SPRINGS PKWY UNDERGROUND UTILITY DISTRICT | DIAMOND SPRINGS PH 1B, EL DORADO COUNTY ¦ 14-09000-03 ¦ NO ORDER | DIAMOND SPRINGS PKWY MISSOURI FLAT RD TO HWY 49, EL DORADO COUNTY, PLACERVILLE, 95667 | A | Government Agency | Hold | Planning | TBD | TBD | TBD | Preliminary | TBD | EAC | TBD | TBD | TBD | TBD | TBD | 0 | 0 | TBD | Project does not meet public interest criteria. El Dorado County to execute project as Rule 20B. | No | TBD | TBD | Urban Cluster | TBD | TBD | TBD
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | SANTA CLARA | SUNNYVALE | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2022-02-12 | Actual | N/A | N/A | 448747.57 | Actual | N/A | N/A | 1379 | 410.9004 | 4 | 448747.57 | 235319.99 | No | N/A | No | N/A | N/A | Urban | 10 | 152242.2 | REDACTED
REDACTED | N/A | SAN MATEO | REDWOOD CITY | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1614.22 | EAC | TBD | N/A | TBD | TBD | TBD | 1614.22 | 122.28 | TBD | N/A | Yes | N/A | N/A | Urban | TBD | 560937.36 | REDACTED
REDACTED | N/A | SAN MATEO | REDWOOD CITY | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-09-18 | Actual | 4489.0187 | Design | 1091761.71 | Actual | 243.2072 | Not Outlier | 12864 | 1742.4065 | 1 | 1091761.71 | 128765.22 | No | N/A | Yes | No | No | Urban | 16 | -73257.55 | REDACTED
REDACTED | N/A | SAN MATEO | REDWOOD CITY | N/A | REDACTED | REDACTED | B | Business | Active | Construction | 2023-04-07 | Forecast | TBD | TBD | 399303.35 | EAC | TBD | N/A | TBD | 829.1934 | TBD | 399303.35 | 397949.47 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 63886.07 | REDACTED
REDACTED | N/A | SAN MATEO | SOUTH SAN FRANCISCO | N/A | REDACTED | REDACTED | B | Business | Active | Construction | 2023-03-31 | Forecast | TBD | TBD | 195046.84 | EAC | TBD | N/A | TBD | TBD | TBD | 195046.84 | 185583.17 | Unknown | N/A | Yes | N/A | N/A | Urban | TBD | 56964.23 | REDACTED
REDACTED | N/A | SAN MATEO | WOODSIDE | N/A | REDACTED | REDACTED | B | Business | Active | Construction | 2023-06-23 | Forecast | TBD | TBD | 25830.59 | EAC | TBD | N/A | TBD | TBD | TBD | 25830.59 | 6625.09 | Unknown | N/A | No | N/A | N/A | Rural | TBD | 289618.21 | REDACTED
REDACTED | N/A | SAN MATEO | REDWOOD CITY | N/A | REDACTED | REDACTED | B | Business | Active | Construction | TBD | TBD | TBD | TBD | 24260.49 | EAC | TBD | N/A | TBD | TBD | TBD | 24260.49 | 22598.52 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 126979.39 | REDACTED
REDACTED | N/A | SAN MATEO | SAN CARLOS | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 13795.1 | EAC | TBD | N/A | TBD | TBD | TBD | 13795.1 | 10978.77 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | SAN MATEO | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Government Agency | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1494.09 | EAC | TBD | N/A | TBD | TBD | TBD | 1494.09 | 1494.09 | TBD | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | SAN MATEO | SOUTH SAN FRANCISCO | N/A | REDACTED | REDACTED | B | Business | Active | Planning | TBD | TBD | TBD | TBD | 1145.68 | EAC | TBD | N/A | TBD | TBD | TBD | 1145.68 | 1145.68 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | CONTRA COSTA | MARTINEZ | N/A | REDACTED | REDACTED | B | Business | Active | Construction | TBD | TBD | TBD | TBD | 139594.08 | EAC | TBD | N/A | TBD | 742.3762 | TBD | 139594.08 | 133117.71 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 96688.05 | REDACTED
REDACTED | N/A | CONTRA COSTA | PLEASANT HILL | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2022-01-19 | Actual | N/A | N/A | 986447.93 | Actual | N/A | N/A | 3953 | 899.0121 | 0 | 986447.93 | -265373.12 | No | N/A | No | N/A | N/A | Urban | 14 | 106064.45 | REDACTED
REDACTED | N/A | CONTRA COSTA | PLEASANT HILL | N/A | REDACTED | REDACTED | B | Government Agency | Active | Closing | 2021-02-14 | Actual | N/A | N/A | 93290.27 | Actual | N/A | N/A | 2018 | 1072.2564 | 1 | 93290.27 | 0 | No | N/A | No | N/A | N/A | Urban | 8 | 24427.6 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | CONTRA COSTA | PITTSBURG | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 47692.04 | EAC | TBD | N/A | TBD | TBD | TBD | 47692.04 | 5823.86 | TBD | N/A | No | N/A | N/A | Urban | TBD | 272409.28 | REDACTED
REDACTED | N/A | CONTRA COSTA | PLEASANT HILL | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 42755.65 | EAC | TBD | N/A | TBD | TBD | TBD | 42755.65 | 38604.41 | TBD | N/A | No | No | No | Urban | TBD | 87973.61 | REDACTED
REDACTED | N/A | CONTRA COSTA | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 25469.55 | EAC | TBD | N/A | TBD | TBD | TBD | 25469.55 | 21578.03 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | CONTRA COSTA | ANTIOCH | N/A | REDACTED | REDACTED | B | Business | Active | Planning | 2023-03-19 | Forecast | TBD | TBD | 12624.26 | EAC | TBD | N/A | TBD | TBD | TBD | 12624.26 | 12624.26 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | ALAMEDA | OAKLAND | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | 2023-04-07 | Forecast | TBD | TBD | 21925.59 | EAC | TBD | N/A | TBD | TBD | TBD | 21925.59 | 16623.9 | TBD | N/A | Yes | N/A | N/A | Urban | TBD | 93745.47 | REDACTED
REDACTED | N/A | ALAMEDA | EMERYVILLE | N/A | REDACTED | REDACTED | B | Business | Active | Construction | TBD | TBD | TBD | TBD | 1019910.98 | EAC | TBD | N/A | TBD | TBD | TBD | 1019910.98 | 987922.05 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 178710.24 | REDACTED
REDACTED | N/A | ALAMEDA | OAKLAND | N/A | REDACTED | REDACTED | B | Business | Active | Planning | 2023-03-14 | Forecast | TBD | TBD | 4614.7 | EAC | TBD | N/A | TBD | TBD | TBD | 4614.7 | 4072.64 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | ALAMEDA | BERKELEY | N/A | REDACTED | REDACTED | B | Government Agency | Active | Planning | TBD | TBD | TBD | TBD | 1125.52 | EAC | TBD | N/A | TBD | TBD | TBD | 1125.52 | 1125.52 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | CONTRA COSTA | RICHMOND | N/A | REDACTED | REDACTED | B | Business | Active | Planning | TBD | TBD | TBD | TBD | 1222.99 | EAC | TBD | N/A | TBD | TBD | TBD | 1222.99 | 1222.99 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | ALAMEDA | DUBLIN | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2022-03-27 | Actual | N/A | N/A | 550448.93 | Actual | N/A | N/A | 741.7282 | 741.7282 | Not Available | 550448.93 | 333935.65 | No | N/A | No | N/A | N/A | Urban | 1 | 155244.94 | REDACTED
REDACTED | N/A | ALAMEDA | DUBLIN | N/A | REDACTED | REDACTED | B | Business | Active | Construction | TBD | TBD | TBD | TBD | 60808.2 | EAC | TBD | N/A | TBD | TBD | TBD | 60808.2 | 22399.42 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 63823.89 | REDACTED
REDACTED | N/A | ALAMEDA | DUBLIN | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-11-17 | Actual | N/A | N/A | 199945.72 | Actual | N/A | N/A | 2307.61 | 1053.4767 | Not Available | 199945.72 | 7953.61 | No | N/A | No | N/A | N/A | Urban | 5 | 29132.21 | REDACTED
REDACTED | N/A | ALAMEDA | NEWARK | N/A | REDACTED | REDACTED | B | Business | Active | Planning | TBD | TBD | TBD | TBD | 2134.03 | EAC | TBD | N/A | TBD | TBD | TBD | 2134.03 | 1587.92 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | ALAMEDA | HAYWARD | N/A | REDACTED | REDACTED | B | Business | Active | Planning | 2023-03-16 | Forecast | TBD | TBD | 3738.98 | EAC | TBD | N/A | TBD | TBD | TBD | 3738.98 | 3738.98 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | ALAMEDA | DUBLIN | N/A | REDACTED | REDACTED | B | Business | Active | Planning | TBD | TBD | TBD | TBD | 314.94 | EAC | TBD | N/A | TBD | TBD | TBD | 314.94 | 314.94 | TBD | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | MONTEREY | SALINAS | N/A | REDACTED | REDACTED | B | Business | Active | Construction | TBD | TBD | TBD | TBD | 336299.78 | EAC | TBD | N/A | TBD | 1284.2432 | TBD | 336299.78 | 9.57 | Unknown | N/A | No | N/A | N/A | Rural | TBD | 62329.44 | REDACTED
REDACTED | N/A | SANTA CRUZ | SANTA CRUZ | N/A | REDACTED | REDACTED | B | Business | Active | Construction | TBD | TBD | TBD | TBD | 779306.18 | EAC | TBD | N/A | TBD | 783.7955 | TBD | 779306.18 | 682306.88 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 294318.84 | REDACTED
REDACTED | N/A | MONTEREY | MARINA | N/A | REDACTED | REDACTED | B | Business | Active | Construction | TBD | TBD | TBD | TBD | 334625.9 | EAC | TBD | N/A | TBD | 2832.9681 | TBD | 334625.9 | 297845.2 | Unknown | N/A | No | N/A | N/A | Urban | TBD | -5114.42 | REDACTED
REDACTED | N/A | SAN BENITO | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Individual | Active | Planning | TBD | TBD | TBD | TBD | 1805.97 | EAC | TBD | N/A | TBD | TBD | TBD | 1805.97 | 1805.97 | TBD | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | SAN BENITO | HOLLISTER | N/A | REDACTED | REDACTED | B | Business | Active | Planning | TBD | TBD | TBD | TBD | 214.76 | EAC | TBD | N/A | TBD | TBD | TBD | 214.76 | 214.76 | TBD | N/A | No | N/A | N/A | Urban Cluster | TBD | 0 | REDACTED
REDACTED | N/A | MONTEREY | MARINA | N/A | REDACTED | REDACTED | B | Individual | Active | Planning | TBD | TBD | TBD | TBD | 1061.04 | EAC | TBD | N/A | TBD | TBD | TBD | 1061.04 | 1061.04 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SANTA CLARA | MOUNTAIN VIEW | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-11-16 | Actual | N/A | N/A | 620778.9 | Actual | N/A | N/A | 4999 | 1749.0751 | 0 | 620778.9 | -25572.84 | No | N/A | No | N/A | N/A | Urban | 26 | 177031.68 | REDACTED
REDACTED | N/A | SANTA CLARA | LOS ALTOS | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 11793.27 | EAC | TBD | N/A | TBD | TBD | TBD | 11793.27 | 8519.32 | TBD | N/A | No | N/A | N/A | Urban | TBD | -9102.86 | REDACTED
REDACTED | N/A | SANTA CLARA | SUNNYVALE | N/A | REDACTED | REDACTED | B | Business | Active | Planning | TBD | TBD | TBD | TBD | 1836.21 | EAC | TBD | N/A | TBD | TBD | TBD | 1836.21 | 1836.21 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SANTA CLARA | MORGAN HILL | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-08-19 | Actual | N/A | N/A | 77283.39 | Actual | N/A | N/A | 752.25 | 311.3357 | Not Available | 77283.39 | 1017.48 | No | N/A | No | N/A | N/A | Urban | 3 | 7577.88 | REDACTED
REDACTED | N/A | SANTA CLARA | SAN JOSE | N/A | REDACTED | REDACTED | B | Government Agency | Active | Estimating/Design | 2023-04-20 | Forecast | TBD | TBD | 1344430.48 | EAC | TBD | N/A | TBD | 2177.9364 | TBD | 1344430.48 | 1246807.79 | TBD | N/A | No | N/A | N/A | Urban | TBD | -70735.09 | REDACTED
REDACTED | N/A | SANTA CLARA | SAN JOSE | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-06-15 | Actual | N/A | N/A | 534558.29 | Actual | N/A | N/A | 1147 | 793.1487 | 0 | 534558.29 | 961.11 | No | N/A | No | N/A | N/A | Urban | 15 | 265533.05 | REDACTED
REDACTED | N/A | SANTA CLARA | SANTA CLARA | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | 2023-05-05 | Forecast | TBD | TBD | 77484.19 | EAC | TBD | N/A | TBD | TBD | TBD | 77484.19 | 73557.28 | TBD | N/A | No | N/A | N/A | Urban | TBD | 211586.58 | REDACTED
REDACTED | N/A | SANTA CLARA | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Business | Active | Planning | TBD | TBD | TBD | TBD | 4680.28 | EAC | TBD | N/A | TBD | TBD | TBD | 4680.28 | 2986.28 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | FRESNO | CLOVIS | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-02-27 | Actual | N/A | N/A | 347650.73 | Actual | N/A | N/A | 1533.47 | 940.1498 | Not Available | 347650.73 | 196028.78 | No | N/A | No | N/A | N/A | Rural | 6 | 107655.58 | REDACTED
REDACTED | N/A | FRESNO | REEDLEY | N/A | REDACTED | REDACTED | B | Business | Active | Closed | 2021-05-14 | Actual | N/A | N/A | 543071.49 | Actual | N/A | N/A | 8592 | 1762.3636 | 4 | 543071.49 | 276291.28 | No | N/A | Yes | N/A | N/A | Urban Cluster | 4 | 609.72 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-04-12 | Actual | N/A | N/A | 161857.28 | Actual | N/A | N/A | 2917 | 1435.3974 | 0 | 161857.28 | 83094.48 | No | N/A | No | N/A | N/A | Urban | 15 | 61462.98 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2022-01-29 | Actual | N/A | N/A | 559294.36 | Actual | N/A | N/A | 3968 | 1355.0093 | 5 | 559294.36 | 338176.8 | No | N/A | Yes | N/A | N/A | Urban | 11 | 70732.06 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 19168.52 | EAC | TBD | N/A | TBD | TBD | TBD | 19168.52 | 18176.72 | TBD | N/A | No | N/A | N/A | Urban | TBD | 152523.59 | REDACTED
REDACTED | N/A | FRESNO | KERMAN | N/A | REDACTED | REDACTED | B | Individual | Active | Closing | 2022-07-13 | Actual | N/A | N/A | 279109.57 | Actual | N/A | N/A | 2241 | 1618.2646 | 0 | 279109.57 | 268050.49 | No | N/A | Yes | N/A | N/A | Urban Cluster | 7 | -2235.26 | REDACTED
REDACTED | N/A | FRESNO | REEDLEY | N/A | REDACTED | REDACTED | B | Contractor | Active | Closing | 2022-04-11 | Actual | N/A | N/A | 890225.74 | Actual | N/A | N/A | 1510 | 1211.1572 | 0 | 890225.74 | 875423.95 | No | N/A | Yes | N/A | N/A | Urban Cluster | 7 | 51826.38 | REDACTED
REDACTED | N/A | FRESNO | FOWLER | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2022-02-03 | Actual | N/A | N/A | 313044.02 | Actual | N/A | N/A | 1412 | 749.1196 | 0 | 313044.02 | 125225.48 | No | N/A | Yes | N/A | N/A | Urban Cluster | 5 | 72634.19 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 17124.7 | EAC | TBD | N/A | TBD | TBD | TBD | 17124.7 | 7340.88 | TBD | N/A | No | N/A | N/A | Rural | TBD | 86321.27 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | 2023-03-02 | Forecast | TBD | TBD | 4497.15 | EAC | TBD | N/A | TBD | TBD | TBD | 4497.15 | 2988.28 | TBD | N/A | No | N/A | N/A | Rural | TBD | 173612.62 | REDACTED
REDACTED | N/A | FRESNO | CLOVIS | N/A | REDACTED | REDACTED | B | Government Agency | Active | Estimating/Design | TBD | TBD | TBD | TBD | 15928.02 | EAC | TBD | N/A | TBD | TBD | TBD | 15928.02 | 4383.81 | TBD | N/A | No | N/A | N/A | Urban | TBD | 874687.9 | REDACTED
REDACTED | N/A | FRESNO | CLOVIS | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 4650.38 | EAC | TBD | N/A | TBD | TBD | TBD | 4650.38 | 2256.51 | TBD | N/A | No | N/A | N/A | Rural | TBD | 93836.35 | REDACTED
REDACTED | N/A | KINGS | CORCORAN | N/A | REDACTED | REDACTED | B | Contractor | Active | Estimating/Design | TBD | TBD | TBD | TBD | 23353.14 | EAC | TBD | N/A | TBD | TBD | TBD | 23353.14 | 21993.51 | TBD | N/A | Yes | N/A | N/A | Urban Cluster | TBD | 0 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 6270.17 | EAC | TBD | N/A | TBD | TBD | TBD | 6270.17 | 5855.49 | TBD | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | FRESNO | KERMAN | N/A | REDACTED | REDACTED | B | Government Agency | Active | Planning | TBD | TBD | TBD | TBD | 5411.57 | EAC | TBD | N/A | TBD | TBD | TBD | 5411.57 | 2467.76 | TBD | N/A | Yes | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | FRESNO | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Contractor | Active | Planning | 2023-02-12 | Forecast | TBD | TBD | 3019.52 | EAC | TBD | N/A | TBD | TBD | TBD | 3019.52 | 3019.52 | TBD | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | TULARE | DINUBA | N/A | REDACTED | REDACTED | B | Business | Active | Planning | TBD | TBD | TBD | TBD | 4351.04 | EAC | TBD | N/A | TBD | TBD | TBD | 4351.04 | 4351.04 | TBD | N/A | Yes | N/A | N/A | Urban Cluster | TBD | 0 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | B | Business | Active | Planning | TBD | TBD | TBD | TBD | 427.17 | EAC | TBD | N/A | TBD | TBD | TBD | 427.17 | 427.17 | TBD | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | TULARE | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Government Agency | Active | Planning | TBD | TBD | TBD | TBD | 2615.6 | EAC | TBD | N/A | TBD | TBD | TBD | 2615.6 | 2615.6 | TBD | N/A | Yes | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | B | Business | Active | Planning | TBD | TBD | TBD | TBD | 1353.04 | EAC | TBD | N/A | TBD | TBD | TBD | 1353.04 | 1353.04 | TBD | N/A | Yes | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | FRESNO | CLOVIS | N/A | REDACTED | REDACTED | B | Individual | Active | Planning | TBD | TBD | TBD | TBD | 1514.03 | EAC | TBD | N/A | TBD | TBD | TBD | 1514.03 | 1514.03 | TBD | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | KERN | SHAFTER | N/A | REDACTED | REDACTED | B | Business | Active | Construction | TBD | TBD | TBD | TBD | 569784.97 | EAC | TBD | N/A | TBD | 1330.4429 | TBD | 569784.97 | 552650.98 | Unknown | N/A | No | N/A | N/A | Urban Cluster | TBD | 38600.13 | REDACTED
REDACTED | N/A | KERN | BAKERSFIELD | N/A | REDACTED | REDACTED | B | Government Agency | Active | Closing | 2022-04-20 | Actual | N/A | N/A | 904992.97 | Actual | N/A | N/A | 19637 | 3873.4783 | 2 | 904992.97 | 837455.72 | No | N/A | Yes | N/A | N/A | Rural | 26 | 171249.3 | REDACTED
REDACTED | N/A | KERN | BAKERSFIELD | N/A | REDACTED | REDACTED | B | Contractor | Active | Closing | 2022-02-03 | Actual | N/A | N/A | 385536.57 | Actual | N/A | N/A | 2545 | 1360.9832 | 0 | 385536.57 | 94224.74 | No | N/A | No | N/A | N/A | Urban | 4 | 50604.18 | REDACTED
REDACTED | N/A | KERN | SHAFTER | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2022-03-10 | Actual | 3483.1396 | Design | 519268.94 | Actual | 149.0807 | Not Outlier | 4217 | 3382.5761 | 0 | 519268.94 | 131595.8 | No | N/A | Yes | No | No | Rural | 21 | 256985.36 | REDACTED
REDACTED | N/A | KERN | BAKERSFIELD | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2022-07-07 | Actual | N/A | N/A | 191800.07 | Actual | N/A | N/A | 2263 | 2304.9235 | 0 | 191800.07 | 183729.03 | No | N/A | Yes | N/A | N/A | Rural | 9 | 80415.74 | REDACTED
REDACTED | N/A | KERN | BAKERSFIELD | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1067.28 | EAC | TBD | N/A | TBD | TBD | TBD | 1067.28 | 1067.28 | TBD | N/A | No | N/A | N/A | Urban | TBD | 108096.25 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2022-08-22 | Actual | N/A | N/A | 583487.36 | Actual | N/A | N/A | 2741.22 | 919 | Not Available | 583487.36 | 582736.99 | Yes | N/A | No | N/A | N/A | Rural | Not Available | 159881.53 | REDACTED
REDACTED | N/A | SANTA BARBARA | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 3415.11 | EAC | TBD | N/A | TBD | TBD | TBD | 3415.11 | 2808.96 | TBD | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | SAN JOAQUIN | LATHROP | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2022-02-18 | Actual | N/A | N/A | 211354.4 | Actual | N/A | N/A | 3946 | 1340.0133 | 0 | 211354.4 | 127976.24 | No | N/A | Yes | N/A | N/A | Urban | 10 | 136618.75 | REDACTED
REDACTED | N/A | SAN JOAQUIN | TRACY | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2022-09-12 | Actual | N/A | N/A | 272486.35 | Actual | N/A | N/A | 7557 | Not Available | 0 | 272486.35 | 272043.67 | No | N/A | No | N/A | N/A | Rural | 16 | 65821.21 | REDACTED
REDACTED | N/A | SAN JOAQUIN | LATHROP | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 6208.27 | EAC | TBD | N/A | TBD | TBD | TBD | 6208.27 | 6208.27 | TBD | N/A | Yes | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | SAN JOAQUIN | MANTECA | N/A | REDACTED | REDACTED | B | Business | Active | Planning | TBD | TBD | TBD | TBD | 767.6 | EAC | TBD | N/A | TBD | TBD | TBD | 767.6 | 767.6 | TBD | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | MADERA | MADERA | N/A | REDACTED | REDACTED | B | Business | Active | Construction | 2023-02-03 | Forecast | TBD | TBD | 277758.03 | EAC | TBD | N/A | TBD | 954.7054 | TBD | 277758.03 | 263992.54 | Unknown | N/A | Yes | N/A | N/A | Urban | TBD | 173650.68 | REDACTED
REDACTED | N/A | STANISLAUS | NEWMAN | N/A | REDACTED | REDACTED | B | Business | Active | Planning | TBD | TBD | TBD | TBD | 4440.5 | EAC | TBD | N/A | TBD | TBD | TBD | 4440.5 | 402.19 | TBD | N/A | No | N/A | N/A | Urban Cluster | TBD | 0 | REDACTED
REDACTED | N/A | MADERA | MADERA | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | 2023-04-28 | Forecast | TBD | TBD | 10049.18 | EAC | TBD | N/A | TBD | TBD | TBD | 10049.18 | 10049.18 | TBD | N/A | Yes | N/A | N/A | Rural | TBD | 280022.44 | REDACTED
REDACTED | N/A | PLACER | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 7798.33 | EAC | TBD | N/A | TBD | TBD | TBD | 7798.33 | 0 | TBD | N/A | No | N/A | N/A | Rural | TBD | 8000 | REDACTED
REDACTED | N/A | YOLO | WINTERS | N/A | REDACTED | REDACTED | B | Business | Active | Closed | 2021-01-25 | Actual | N/A | N/A | 315079.93 | Actual | N/A | N/A | 544.41 | 1128.2882 | Not Available | 315079.93 | 200.24 | No | N/A | No | N/A | N/A | Urban Cluster | 6 | 1620.32 | REDACTED
REDACTED | N/A | SOLANO | VACAVILLE | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-04-08 | Actual | N/A | N/A | 466755.29 | Actual | N/A | N/A | 1130 | 807.7556 | 0 | 466755.29 | 16426.63 | No | N/A | No | N/A | N/A | Urban | 4 | 14691.57 | REDACTED
REDACTED | N/A | SOLANO | RIO VISTA | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2022-06-30 | Actual | N/A | N/A | 61123.76 | Actual | N/A | N/A | 1375 | 757.8793 | 0 | 61123.76 | 48405.44 | No | N/A | Yes | N/A | N/A | Urban Cluster | 7 | 54463.67 | REDACTED
REDACTED | N/A | YOLO | WEST SACRAMENTO | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2022-10-28 | Actual | N/A | N/A | 211676.74 | Actual | N/A | N/A | 5400 | 2641.6322 | 0 | 211676.74 | 199257.86 | No | N/A | No | N/A | N/A | Urban | 20 | 57866.45 | REDACTED
REDACTED | N/A | SOLANO | VACAVILLE | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 5390.31 | EAC | TBD | N/A | TBD | TBD | TBD | 5390.31 | 4340.22 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SOLANO | VACAVILLE | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 4892.78 | EAC | TBD | N/A | TBD | TBD | TBD | 4892.78 | 4232.84 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | YOLO | WEST SACRAMENTO | N/A | REDACTED | REDACTED | B | Business | Active | Construction | 2022-07-15 | Actual | N/A | N/A | 56752.04 | Actual | N/A | N/A | 854 | Not Available | 0 | 56752.04 | 56752.04 | No | N/A | No | N/A | N/A | Urban | 4 | 32508.46 | REDACTED
REDACTED | N/A | PLACER | LINCOLN | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-03-24 | Actual | N/A | N/A | 283554.21 | Actual | N/A | N/A | 167 | 515.5725 | Not Available | 283554.21 | 17205.34 | Yes | N/A | No | N/A | N/A | Urban | 2 | 45794.59 | REDACTED
REDACTED | N/A | PLACER | LINCOLN | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2022-04-05 | Actual | N/A | N/A | 252726.96 | Actual | N/A | N/A | 963.827 | 963.827 | Not Available | 252726.96 | 250857.8 | No | N/A | No | N/A | N/A | Urban | 2 | 88648.69 | REDACTED
REDACTED | N/A | PLACER | LINCOLN | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-12-01 | Actual | N/A | N/A | 435199.12 | Actual | N/A | N/A | 166.86 | 3989.2262 | Not Available | 435199.12 | 28337.86 | No | N/A | No | N/A | N/A | Urban | 20 | -44346.16 | REDACTED
REDACTED | N/A | PLACER | LINCOLN | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-04-10 | Actual | N/A | N/A | 1002950.68 | Actual | N/A | N/A | 8770 | 3449.9151 | 0 | 1002950.68 | 338517.36 | No | N/A | No | N/A | N/A | Urban | 8 | -5193.64 | REDACTED
REDACTED | N/A | SONOMA | SANTA ROSA | N/A | REDACTED | REDACTED | B | Business | Active | Construction | TBD | TBD | TBD | TBD | 19661.16 | EAC | TBD | N/A | TBD | TBD | TBD | 19661.16 | 19281.16 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 78299.31 | REDACTED
REDACTED | N/A | SAN FRANCISCO | SAN FRANCISCO | N/A | REDACTED | REDACTED | B | Government Agency | Active | Construction | 2023-09-29 | Forecast | TBD | TBD | 5910094.25 | EAC | TBD | N/A | TBD | 1321.0668 | TBD | 5422919.17 | 167139.91 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 2496673.02 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | CONTRA COSTA | PITTSBURG | N/A | REDACTED | REDACTED | B | Business | Active | Construction | TBD | TBD | TBD | TBD | 4438.7 | EAC | TBD | N/A | TBD | TBD | TBD | 4438.7 | 2226.92 | Unknown | N/A | Yes | N/A | N/A | Urban | TBD | 285385.21 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | CONTRA COSTA | OAKLEY | N/A | REDACTED | REDACTED | B | Business | Active | Construction | 2023-03-31 | Forecast | TBD | TBD | 241132.97 | EAC | TBD | N/A | TBD | 179.0238 | TBD | 241132.97 | 232573.1 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 150684.13 | REDACTED
REDACTED | N/A | ALAMEDA | BERKELEY | N/A | REDACTED | REDACTED | B | Government Agency | Active | Closing | 2022-03-29 | Actual | 3423.4817 | Design | 5580587.02 | Actual | 1630.0911 | Not Outlier | 698.67 | 1868.8489 | Not Available | 5580587.02 | 1221900.82 | No | N/A | No | No | No | Urban | 13 | 4993170.83 | REDACTED
REDACTED | N/A | ALAMEDA | OAKLAND | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-12-22 | Actual | N/A | N/A | 729553.99 | Actual | N/A | N/A | 694.31 | 406.4939 | 2 | 729553.99 | 124931.95 | No | N/A | No | N/A | N/A | Urban | 6 | 318071.62 | REDACTED
REDACTED | N/A | CONTRA COSTA | RICHMOND | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-09-30 | Actual | N/A | N/A | 781388.7 | Actual | N/A | N/A | 1855 | 1153.5295 | 2 | 781388.7 | 2788.21 | No | N/A | Yes | N/A | N/A | Urban | 15 | 218544.25 | REDACTED
REDACTED | N/A | CONTRA COSTA | RICHMOND | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | 2023-05-23 | Forecast | TBD | TBD | 46288.58 | EAC | TBD | N/A | TBD | TBD | TBD | 46288.58 | 43513.62 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | CONTRA COSTA | PINOLE | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | 2023-04-30 | Forecast | TBD | TBD | 3991.26 | EAC | TBD | N/A | TBD | TBD | TBD | 3991.26 | 3991.26 | TBD | N/A | No | N/A | N/A | Urban | TBD | 85137.18 | REDACTED
REDACTED | N/A | ALAMEDA | SAN LEANDRO | N/A | REDACTED | REDACTED | B | Government Agency | Active | Estimating/Design | 2024-12-02 | Forecast | TBD | TBD | 1282895.46 | EAC | TBD | N/A | TBD | TBD | TBD | 88062.07 | 11455.89 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | ALAMEDA | DUBLIN | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-02-06 | Actual | N/A | N/A | 373205.77 | Actual | N/A | N/A | 1856.831 | 1856.831 | Not Available | 373205.77 | 0 | No | N/A | No | N/A | N/A | Rural | 7 | -16037.48 | REDACTED
REDACTED | N/A | ALAMEDA | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Government Agency | Active | Construction | 2025-01-14 | Forecast | TBD | TBD | 3215215.36 | EAC | TBD | N/A | TBD | TBD | TBD | 215821.39 | 161818.56 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 878555.52 | REDACTED
REDACTED | N/A | ALAMEDA | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Government Agency | Active | Estimating/Design | 2023-12-31 | Forecast | TBD | TBD | 7129669 | EAC | TBD | N/A | TBD | TBD | TBD | 550497.57 | 487980.26 | TBD | N/A | No | N/A | N/A | Urban | TBD | 2516442.72 | REDACTED
REDACTED | N/A | SANTA CRUZ | SANTA CRUZ | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-07-27 | Actual | N/A | N/A | 355708 | Actual | N/A | N/A | 789.92 | 909.8883 | 6 | 355708 | 8210.65 | Yes | N/A | No | N/A | N/A | Urban | 11 | 128229.72 | REDACTED
REDACTED | N/A | SAN BENITO | HOLLISTER | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2022-03-04 | Actual | N/A | N/A | 619556.81 | Actual | N/A | N/A | 281.32 | 1221.6643 | Not Available | 619556.81 | -11115.13 | No | N/A | No | N/A | N/A | Urban Cluster | 7 | 184410.44 | REDACTED
REDACTED | N/A | SANTA CRUZ | SCOTTS VALLEY | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-01-14 | Actual | N/A | N/A | 61546.18 | Actual | N/A | N/A | 267.09 | 315.2267 | Not Available | 61546.18 | 6051.21 | No | N/A | No | N/A | N/A | Urban | 3 | 4209.32 | REDACTED
REDACTED | N/A | MONTEREY | SAND CITY | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 87533.31 | EAC | TBD | N/A | TBD | TBD | TBD | 87533.31 | 49543.44 | TBD | N/A | No | N/A | N/A | Urban | TBD | 259653.77 | REDACTED
REDACTED | N/A | MONTEREY | PEBBLE BEACH | N/A | REDACTED | REDACTED | B | Business | Active | Construction | 2023-06-08 | Forecast | TBD | TBD | 9489109.88 | EAC | TBD | N/A | TBD | TBD | TBD | 2199000.14 | 1889942.31 | Unknown | N/A | No | N/A | N/A | Rural | TBD | 2183610.39 | REDACTED
REDACTED | N/A | SAN BENITO | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Business | Active | Planning | TBD | TBD | TBD | TBD | 4169.26 | EAC | TBD | N/A | TBD | TBD | TBD | 4169.26 | 3974.48 | TBD | N/A | No | N/A | N/A | Urban Cluster | TBD | 0 | REDACTED
REDACTED | N/A | SAN BENITO | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Government Agency | Active | Estimating/Design | TBD | TBD | TBD | TBD | 6054.99 | EAC | TBD | N/A | TBD | TBD | TBD | 6054.99 | 2911.17 | TBD | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | MONTEREY | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1172.92 | EAC | TBD | N/A | TBD | TBD | TBD | 1172.92 | 1172.92 | TBD | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | MONTEREY | GREENFIELD | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 379.88 | EAC | TBD | N/A | TBD | TBD | TBD | 379.88 | 379.88 | TBD | N/A | No | N/A | N/A | Urban Cluster | TBD | 0 | REDACTED
REDACTED | N/A | SANTA CLARA | SUNNYVALE | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-12-04 | Actual | N/A | N/A | 325528.78 | Actual | N/A | N/A | 369.65 | 617.6362 | Not Available | 325528.78 | 0 | No | N/A | No | N/A | N/A | Urban | 4 | -4669 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | SANTA CLARA | MOUNTAIN VIEW | N/A | REDACTED | REDACTED | B | Individual | Active | Planning | TBD | TBD | TBD | TBD | 1766.57 | EAC | TBD | N/A | TBD | TBD | TBD | 1766.57 | 1766.57 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SANTA CLARA | SAN JOSE | N/A | REDACTED | REDACTED | B | Government Agency | Active | Construction | 2023-05-01 | Forecast | TBD | TBD | 2517249.31 | EAC | TBD | N/A | TBD | 1360.6982 | TBD | 2206580.6 | 1453902.59 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 457907.79 | REDACTED
REDACTED | N/A | SANTA CLARA | GILROY | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-06-25 | Actual | N/A | N/A | 531715.14 | Actual | N/A | N/A | 2296.24 | 1065.7722 | 2 | 531715.14 | 2032.21 | No | N/A | No | N/A | N/A | Urban | 5 | 118133.4 | REDACTED
REDACTED | N/A | SANTA CLARA | SAN JOSE | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-03-30 | Actual | N/A | N/A | 512480.89 | Actual | N/A | N/A | 702.26 | 1479.1516 | 1 | 512480.89 | -4327.87 | Yes | N/A | Yes | N/A | N/A | Urban | 12 | 58268.72 | REDACTED
REDACTED | N/A | SANTA CLARA | MORGAN HILL | N/A | REDACTED | REDACTED | B | Government Agency | Active | Construction | TBD | TBD | TBD | TBD | 668467.29 | EAC | TBD | N/A | TBD | 1061.5495 | TBD | 668467.29 | 658441.44 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 253915.46 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | SANTA CLARA | MORGAN HILL | N/A | REDACTED | REDACTED | B | Government Agency | Active | Estimating/Design | TBD | TBD | TBD | TBD | 2083.22 | EAC | TBD | N/A | TBD | TBD | TBD | 2083.22 | 2008.57 | TBD | N/A | No | N/A | N/A | Urban | TBD | 397382.08 | REDACTED
REDACTED | N/A | SANTA CLARA | SAN JOSE | N/A | REDACTED | REDACTED | B | Government Agency | Active | Estimating/Design | TBD | TBD | TBD | TBD | 106783.93 | EAC | TBD | N/A | TBD | TBD | TBD | 106783.93 | 106783.93 | TBD | N/A | Yes | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SANTA CLARA | GILROY | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 2980.2 | EAC | TBD | N/A | TBD | TBD | TBD | 2980.2 | 2762.9 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SANTA CLARA | SAN JOSE | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 20762.15 | EAC | TBD | N/A | TBD | TBD | TBD | 20762.15 | 20762.15 | TBD | N/A | No | No | No | Urban | TBD | 0 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 6972.02 | EAC | TBD | N/A | TBD | TBD | TBD | 6972.02 | 34.17 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | FRESNO | CLOVIS | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 27054 | EAC | TBD | N/A | TBD | TBD | TBD | 27054 | 33497.77 | TBD | N/A | No | N/A | N/A | Urban | TBD | 76080.21 | REDACTED
REDACTED | N/A | FRESNO | CLOVIS | N/A | REDACTED | REDACTED | B | Business | Active | Planning | TBD | TBD | TBD | TBD | 647.82 | EAC | TBD | N/A | TBD | TBD | TBD | 647.82 | 647.82 | TBD | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | FRESNO | CLOVIS | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-11-18 | Actual | N/A | N/A | 317375.42 | Actual | N/A | N/A | 525 | 851.8327 | 0 | 317375.42 | 0 | No | N/A | No | N/A | N/A | Rural | 5 | 72419.41 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2022-02-23 | Actual | N/A | N/A | 651343.9 | Actual | N/A | N/A | 1828 | 583.5837 | 0 | 651343.9 | 465189.8 | Yes | N/A | No | N/A | N/A | Urban | 5 | 196824.63 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2022-01-19 | Actual | N/A | N/A | 351511.32 | Actual | N/A | N/A | 4037 | 1409.2246 | 0 | 351511.32 | 5925.84 | Yes | N/A | Yes | N/A | N/A | Rural | 14 | 82507.14 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-07-20 | Actual | N/A | N/A | 590960.47 | Actual | N/A | N/A | 1750 | 674.8675 | 2 | 590960.47 | -4857.92 | Yes | N/A | No | N/A | N/A | Urban | 6 | 235705.76 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-11-23 | Actual | N/A | N/A | 385828.76 | Actual | N/A | N/A | 1444 | 873.4046 | 0 | 385828.76 | -7599.06 | No | N/A | No | N/A | N/A | Urban | 9 | 85235.37 | REDACTED
REDACTED | N/A | FRESNO | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 5863.92 | EAC | TBD | N/A | TBD | TBD | TBD | 5863.92 | 60.01 | TBD | N/A | No | N/A | N/A | Rural | TBD | 385497.45 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | B | Business | Active | Construction | TBD | TBD | TBD | TBD | 4108.48 | EAC | TBD | N/A | TBD | TBD | TBD | 4108.48 | 1288.73 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 7001.76 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-06-17 | Actual | 781.2588 | Design | 405821.75 | Actual | 519.446 | Not Outlier | 1937 | 772.8032 | 0 | 405821.75 | -3188.16 | Yes | N/A | No | No | No | Urban | 4 | 141351.2 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 12784.78 | EAC | TBD | N/A | TBD | TBD | TBD | 12784.78 | 4823.36 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | KINGS | LEMOORE | N/A | REDACTED | REDACTED | B | Government Agency | Active | Closing | 2021-07-22 | Actual | N/A | N/A | 376101.89 | Actual | N/A | N/A | 1578 | 1093.5435 | 0 | 376101.89 | -5359.46 | Yes | N/A | No | N/A | N/A | Urban | 7 | 152168.87 | REDACTED
REDACTED | N/A | FRESNO | FOWLER | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-05-08 | Actual | N/A | N/A | 383768.34 | Actual | N/A | N/A | 986 | 723.3841 | 0 | 383768.34 | 172350.3 | No | N/A | Yes | N/A | N/A | Rural | 10 | 151781.65 | REDACTED
REDACTED | N/A | FRESNO | CLOVIS | N/A | REDACTED | REDACTED | B | Government Agency | Active | Construction | 2023-02-10 | Forecast | TBD | TBD | 475768.89 | EAC | TBD | N/A | TBD | 1707.5295 | TBD | 475768.89 | 466665.93 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 228706.31 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | 2023-04-01 | Forecast | TBD | TBD | 61146.74 | EAC | TBD | N/A | TBD | TBD | TBD | 61146.74 | 42739.3 | TBD | N/A | No | N/A | N/A | Rural | TBD | 70827.68 | REDACTED
REDACTED | N/A | FRESNO | CLOVIS | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 43109.5 | EAC | TBD | N/A | TBD | TBD | TBD | 43109.5 | 42782.98 | TBD | N/A | No | N/A | N/A | Urban | TBD | 37811.25 | REDACTED
REDACTED | N/A | FRESNO | SANGER | N/A | REDACTED | REDACTED | B | Business | Active | Construction | 2023-05-26 | Forecast | TBD | TBD | 320358.99 | EAC | TBD | N/A | TBD | 1467.9859 | TBD | 320358.99 | 303361.11 | Unknown | N/A | Yes | N/A | N/A | Urban Cluster | TBD | 66582.63 | REDACTED
REDACTED | N/A | FRESNO | CLOVIS | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 3163.28 | EAC | TBD | N/A | TBD | TBD | TBD | 3163.28 | 29.56 | TBD | N/A | No | N/A | N/A | Urban | TBD | 19843.3 | REDACTED
REDACTED | N/A | FRESNO | CLOVIS | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2022-07-25 | Actual | N/A | N/A | 238420.94 | Actual | N/A | N/A | 1154 | 565.2363 | 2 | 238420.94 | 235892.24 | No | N/A | No | N/A | N/A | Urban | 6 | 66012.61 | REDACTED
REDACTED | N/A | FRESNO | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Business | Active | Construction | 2023-04-26 | Forecast | TBD | TBD | 10029.24 | EAC | TBD | N/A | TBD | TBD | TBD | 10029.24 | 10029.24 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 155845.36 | REDACTED
REDACTED | N/A | FRESNO | CLOVIS | N/A | REDACTED | REDACTED | B | Business | Active | Planning | 2023-05-17 | Forecast | TBD | TBD | 5087.79 | EAC | TBD | N/A | TBD | TBD | TBD | 5087.79 | 1995.71 | TBD | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | MADERA | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | 2023-04-26 | Forecast | TBD | TBD | 914.61 | EAC | TBD | N/A | TBD | TBD | TBD | 914.61 | 914.61 | TBD | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | B | Government Agency | Active | Construction | 2023-04-14 | Forecast | TBD | TBD | 130379.44 | EAC | TBD | N/A | TBD | TBD | TBD | 130379.44 | 129121.35 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 430609.5 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 22085.76 | EAC | TBD | N/A | TBD | TBD | TBD | 22085.76 | 19163.98 | TBD | N/A | No | N/A | N/A | Rural | TBD | 118188.94 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | B | Business | Active | Construction | TBD | TBD | TBD | TBD | 122877.43 | EAC | TBD | N/A | TBD | TBD | TBD | 122877.43 | 122877.43 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 235268.47 | REDACTED
REDACTED | N/A | FRESNO | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Business | Active | Planning | TBD | TBD | TBD | TBD | 635.95 | EAC | TBD | N/A | TBD | TBD | TBD | 635.95 | 635.95 | TBD | N/A | No | N/A | N/A | Urban Cluster | TBD | 0 | REDACTED
REDACTED | N/A | FRESNO | CLOVIS | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 6521.5 | EAC | TBD | N/A | TBD | TBD | TBD | 6521.5 | 6521.5 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | FRESNO | CLOVIS | N/A | REDACTED | REDACTED | B | Business | Active | Planning | 2023-03-30 | Forecast | TBD | TBD | 404.76 | EAC | TBD | N/A | TBD | TBD | TBD | 404.76 | 404.76 | TBD | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | FRESNO | SAN JOAQUIN | N/A | REDACTED | REDACTED | B | Business | Active | Planning | TBD | TBD | TBD | TBD | 214.83 | EAC | TBD | N/A | TBD | TBD | TBD | 214.83 | 214.83 | TBD | N/A | Yes | N/A | N/A | Urban Cluster | TBD | 0 | REDACTED
REDACTED | N/A | FRESNO | CLOVIS | N/A | REDACTED | REDACTED | B | Business | Active | Planning | TBD | TBD | TBD | TBD | 5264.17 | EAC | TBD | N/A | TBD | TBD | TBD | 5264.17 | 5264.17 | TBD | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | KERN | BAKERSFIELD | N/A | REDACTED | REDACTED | B | Government Agency | Active | Closing | 2022-04-20 | Actual | N/A | N/A | 720668.05 | Actual | N/A | N/A | 1980 | 1514.3448 | 0 | 720668.05 | 710623.3 | No | N/A | Yes | N/A | N/A | Rural | 4 | 333841.23 | REDACTED
REDACTED | N/A | KERN | MC FARLAND | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 19030.48 | EAC | TBD | N/A | TBD | TBD | TBD | 19030.48 | 17844.28 | TBD | N/A | Yes | N/A | N/A | Urban Cluster | TBD | 0 | REDACTED
REDACTED | N/A | KERN | SHAFTER | N/A | REDACTED | REDACTED | B | Contractor | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1693.59 | EAC | TBD | N/A | TBD | TBD | TBD | 1693.59 | 1693.59 | TBD | N/A | No | N/A | N/A | Urban Cluster | TBD | 0 | REDACTED
REDACTED | N/A | KERN | BAKERSFIELD | N/A | REDACTED | REDACTED | B | Business | Active | Construction | 2023-04-28 | Forecast | TBD | TBD | 17542.8 | EAC | TBD | N/A | TBD | TBD | TBD | 17542.8 | 17542.8 | Unknown | N/A | No | N/A | N/A | Rural | TBD | 92305.33 | REDACTED
REDACTED | N/A | KERN | BAKERSFIELD | N/A | REDACTED | REDACTED | B | Contractor | Active | Estimating/Design | 2023-03-10 | Forecast | TBD | TBD | 1329.49 | EAC | TBD | N/A | TBD | TBD | TBD | 1329.49 | 1329.49 | TBD | N/A | Yes | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | SAN LUIS OBISPO | N/A | REDACTED | REDACTED | B | Business | Active | Construction | 2023-02-08 | Forecast | TBD | TBD | 1888943.57 | EAC | TBD | N/A | TBD | 4619.659 | TBD | 1888943.57 | 8527.12 | Unknown | N/A | No | No | No | Urban | TBD | 754142.41 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | SAN LUIS OBISPO | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-02-25 | Actual | N/A | N/A | 563690.98 | Actual | N/A | N/A | 1027.7 | 1420.2499 | 1 | 563690.98 | 0 | No | N/A | No | N/A | N/A | Urban | 5 | 157031.6 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | PASO ROBLES | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-10-08 | Actual | N/A | N/A | 540624.65 | Actual | N/A | N/A | 10236 | 2922.2282 | 8 | 540624.65 | 12143.61 | Yes | N/A | No | N/A | N/A | Rural | 13 | 135743.91 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | TEMPLETON | N/A | REDACTED | REDACTED | B | Business | Active | Construction | TBD | TBD | TBD | TBD | 45581.99 | EAC | TBD | N/A | TBD | 253.3153 | TBD | 45581.99 | 40770.37 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 37671.71 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | PASO ROBLES | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-06-26 | Actual | N/A | N/A | 377432.25 | Actual | N/A | N/A | 1735 | 1929.9652 | 0 | 377432.25 | 229352.66 | No | N/A | No | N/A | N/A | Rural | 5 | 155894.91 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 6246.61 | EAC | TBD | N/A | TBD | TBD | TBD | 6246.61 | 1233.43 | TBD | N/A | No | N/A | N/A | Urban Cluster | TBD | 0 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Business | Active | Construction | TBD | TBD | TBD | TBD | 1190.23 | EAC | TBD | N/A | TBD | TBD | TBD | 1190.23 | 406.27 | Unknown | N/A | No | N/A | N/A | Urban Cluster | TBD | 42970.8 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | EL PASO DE ROBLES | N/A | REDACTED | REDACTED | B | Business | Active | Construction | 2023-02-04 | Forecast | TBD | TBD | 5786.95 | EAC | TBD | N/A | TBD | TBD | TBD | 5786.95 | 5786.95 | Unknown | N/A | No | N/A | N/A | Rural | TBD | 83222.56 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | EL PASO DE ROBLES | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 688.04 | EAC | TBD | N/A | TBD | TBD | TBD | 688.04 | 688.04 | TBD | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | SAN JOAQUIN | LODI | N/A | REDACTED | REDACTED | B | Business | Active | Construction | TBD | TBD | TBD | TBD | 38935.31 | EAC | TBD | N/A | TBD | TBD | TBD | 38935.31 | 34372.38 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 56431.5 | REDACTED
REDACTED | N/A | SAN JOAQUIN | TRACY | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-11-15 | Actual | N/A | N/A | 1111774.78 | Actual | N/A | N/A | 4579 | 3306.6788 | 1 | 1111774.78 | 2123.14 | Yes | N/A | No | N/A | N/A | Rural | 18 | 655718.28 | REDACTED
REDACTED | N/A | SAN JOAQUIN | TRACY | N/A | REDACTED | REDACTED | B | Business | Active | Closed | 2021-02-27 | Actual | N/A | N/A | 464181.39 | Actual | N/A | N/A | 977 | 932.1268 | 2 | 464181.39 | 35408.78 | No | N/A | No | N/A | N/A | Urban | 5 | 160602.83 | REDACTED
REDACTED | N/A | SAN JOAQUIN | TRACY | N/A | REDACTED | REDACTED | B | Business | Active | Construction | TBD | TBD | TBD | TBD | 626250.94 | EAC | TBD | N/A | TBD | 1363.8569 | TBD | 626250.94 | 149302.59 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 192027.62 | REDACTED
REDACTED | N/A | SAN JOAQUIN | TRACY | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1344.45 | EAC | TBD | N/A | TBD | TBD | TBD | 1344.45 | 0 | TBD | N/A | No | N/A | N/A | Rural | TBD | 230452.98 | REDACTED
REDACTED | N/A | SAN JOAQUIN | STOCKTON | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-09-12 | Actual | N/A | N/A | 314718.52 | Actual | N/A | N/A | 690 | 792.9223 | 1 | 314718.52 | 43382.31 | No | N/A | Yes | N/A | N/A | Urban | 9 | -9686.45 | REDACTED
REDACTED | N/A | SAN JOAQUIN | LODI | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2022-08-30 | Actual | N/A | N/A | 503357.85 | Actual | N/A | N/A | 4302 | 2573.1232 | 0 | 503357.85 | 486758.6 | No | N/A | No | N/A | N/A | Urban | 21 | 104683.99 | REDACTED
REDACTED | N/A | SAN JOAQUIN | TRACY | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2022-02-03 | Actual | N/A | N/A | 422973.15 | Actual | N/A | N/A | 1287.5211 | 1287.5211 | 0 | 422973.15 | 185088.2 | No | N/A | No | N/A | N/A | Rural | 7 | 287200.85 | REDACTED
REDACTED | N/A | SAN JOAQUIN | LATHROP | N/A | REDACTED | REDACTED | B | Government Agency | Active | Estimating/Design | TBD | TBD | TBD | TBD | 13569.14 | EAC | TBD | N/A | TBD | TBD | TBD | 13569.14 | 13440.47 | TBD | N/A | Yes | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SAN JOAQUIN | MANTECA | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | 2023-06-30 | Forecast | TBD | TBD | 7249.12 | EAC | TBD | N/A | TBD | TBD | TBD | 7249.12 | 6863.4 | TBD | N/A | No | N/A | N/A | Rural | TBD | 117689.86 | REDACTED
REDACTED | N/A | SAN JOAQUIN | TRACY | N/A | REDACTED | REDACTED | B | Business | Active | Construction | 2023-06-30 | Forecast | TBD | TBD | 24328.55 | EAC | TBD | N/A | TBD | TBD | TBD | 24328.55 | 22120.34 | Unknown | N/A | No | N/A | N/A | Rural | TBD | 102172.66 | REDACTED
REDACTED | N/A | SAN JOAQUIN | STOCKTON | N/A | REDACTED | REDACTED | B | Business | Active | Construction | TBD | TBD | TBD | TBD | 1063276.51 | EAC | TBD | N/A | TBD | 2027.8125 | TBD | 1063276.51 | 1061820.55 | Unknown | N/A | Yes | N/A | N/A | Rural | TBD | 426298.52 | REDACTED
REDACTED | N/A | SAN JOAQUIN | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 648.29 | EAC | TBD | N/A | TBD | TBD | TBD | 648.29 | 648.29 | TBD | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | SAN JOAQUIN | MANTECA | N/A | REDACTED | REDACTED | B | Contractor | Active | Estimating/Design | TBD | TBD | TBD | TBD | 5926.99 | EAC | TBD | N/A | TBD | TBD | TBD | 5926.99 | 5926.99 | TBD | N/A | Yes | N/A | N/A | Rural | TBD | 69743.14 | REDACTED
REDACTED | N/A | SAN JOAQUIN | TRACY | N/A | REDACTED | REDACTED | B | Business | Active | Planning | 2023-02-26 | Forecast | TBD | TBD | 7176.3 | EAC | TBD | N/A | TBD | TBD | TBD | 7176.3 | 7176.3 | TBD | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | SAN JOAQUIN | MANTECA | N/A | REDACTED | REDACTED | B | Contractor | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1347.71 | EAC | TBD | N/A | TBD | TBD | TBD | 1347.71 | 1347.71 | TBD | N/A | Yes | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | SAN JOAQUIN | LODI | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 2640.11 | EAC | TBD | N/A | TBD | TBD | TBD | 2640.11 | 2640.11 | TBD | N/A | No | N/A | N/A | Rural | TBD | 62416.36 | REDACTED
REDACTED | N/A | SAN JOAQUIN | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Business | Active | Planning | TBD | TBD | TBD | TBD | 295.87 | EAC | TBD | N/A | TBD | TBD | TBD | 295.87 | 295.87 | TBD | N/A | Yes | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SAN JOAQUIN | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Individual | Active | Planning | TBD | TBD | TBD | TBD | 430.22 | EAC | TBD | N/A | TBD | TBD | TBD | 430.22 | 430.22 | TBD | N/A | Yes | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SAN JOAQUIN | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Business | Active | Planning | TBD | TBD | TBD | TBD | 352.09 | EAC | TBD | N/A | TBD | TBD | TBD | 352.09 | 352.09 | TBD | N/A | Yes | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | MADERA | MADERA | N/A | REDACTED | REDACTED | B | Government Agency | Active | Construction | 2023-06-12 | Forecast | TBD | TBD | 838224.05 | EAC | TBD | N/A | TBD | TBD | TBD | 838224.05 | 457782.69 | Unknown | N/A | Yes | No | No | Urban | TBD | 475383.11 | REDACTED
REDACTED | N/A | MADERA | MADERA | N/A | REDACTED | REDACTED | B | Individual | Active | Closing | 2020-06-22 | Actual | N/A | N/A | 278744.08 | Actual | N/A | N/A | 1554 | 925.655 | 1 | 278744.08 | 0 | No | N/A | Yes | N/A | N/A | Urban | 8 | 80987.61 | REDACTED
REDACTED | N/A | STANISLAUS | RIVERBANK | N/A | REDACTED | REDACTED | B | Individual | Active | Construction | 2023-03-27 | Forecast | TBD | TBD | 162021.26 | EAC | TBD | N/A | TBD | 745.578 | TBD | 162021.26 | 160944.61 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 65457.51 | REDACTED
REDACTED | N/A | MADERA | MADERA | N/A | REDACTED | REDACTED | B | Individual | Active | Planning | 2023-05-16 | Forecast | TBD | TBD | 2637.6 | EAC | TBD | N/A | TBD | TBD | TBD | 2637.6 | 2637.6 | TBD | N/A | Yes | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | TEHAMA | MINERAL | N/A | REDACTED | REDACTED | B | Government Agency | Active | Closing | 2022-05-13 | Actual | N/A | N/A | 649583.35 | Actual | N/A | N/A | 15870 | 3624.7856 | 0 | 649583.35 | 222645.95 | No | N/A | No | N/A | N/A | Rural | 78 | 0 | REDACTED
REDACTED | N/A | SHASTA | ANDERSON | N/A | REDACTED | REDACTED | B | Business | Active | Construction | TBD | TBD | TBD | TBD | 249964.39 | EAC | TBD | N/A | TBD | 1982.2706 | TBD | 249964.39 | 14397.69 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 84842.51 | REDACTED
REDACTED | N/A | GLENN | ORLAND | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 2309.64 | EAC | TBD | N/A | TBD | TBD | TBD | 2309.64 | 2309.64 | TBD | N/A | No | N/A | N/A | Urban Cluster | TBD | 0 | REDACTED
REDACTED | N/A | SHASTA | ANDERSON | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1915.4 | EAC | TBD | N/A | TBD | TBD | TBD | 1915.4 | 1915.4 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | GLENN | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Individual | Active | Estimating/Design | TBD | TBD | TBD | TBD | 768.79 | EAC | TBD | N/A | TBD | TBD | TBD | 768.79 | 768.79 | TBD | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | SOLANO | VACAVILLE | N/A | REDACTED | REDACTED | B | Business | Active | Closed | 2021-11-06 | Actual | N/A | N/A | 213621.64 | Actual | N/A | N/A | 685.37 | 1240.6941 | Not Available | 213621.64 | -643.04 | No | N/A | No | N/A | N/A | Urban | 8 | 33757.97 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | SOLANO | DIXON | N/A | REDACTED | REDACTED | B | Contractor | Active | Closing | 2022-04-20 | Actual | N/A | N/A | 164393.58 | Actual | N/A | N/A | 1875 | 1905.1854 | 0 | 164393.58 | 157030.24 | No | N/A | No | N/A | N/A | Urban Cluster | 6 | 13104.61 | REDACTED
REDACTED | N/A | SOLANO | DIXON | N/A | REDACTED | REDACTED | B | Contractor | Active | Closing | 2022-02-26 | Actual | N/A | N/A | 786019.53 | Actual | N/A | N/A | 2314 | 1834.3564 | 4 | 786019.53 | 740557.55 | No | N/A | No | N/A | N/A | Urban Cluster | 10 | 79589.99 | REDACTED
REDACTED | N/A | SOLANO | DIXON | N/A | REDACTED | REDACTED | B | Contractor | Active | Construction | TBD | TBD | TBD | TBD | 129351.57 | EAC | TBD | N/A | TBD | 874.308 | TBD | 129351.57 | 99802.75 | Unknown | N/A | No | N/A | N/A | Urban Cluster | TBD | 14941.32 | REDACTED
REDACTED | N/A | SOLANO | FAIRFIELD | N/A | REDACTED | REDACTED | B | Business | Active | Construction | 2023-06-30 | Forecast | TBD | TBD | 285892.39 | EAC | TBD | N/A | TBD | 1169.7093 | TBD | 285892.39 | 279531.82 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 91091.16 | REDACTED
REDACTED | N/A | SOLANO | FAIRFIELD | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2022-04-13 | Actual | N/A | N/A | 260240.74 | Actual | N/A | N/A | 1820 | 955.4966 | 0 | 260240.74 | 244107.11 | Yes | N/A | No | N/A | N/A | Urban | 5 | 38812.77 | REDACTED
REDACTED | N/A | SOLANO | DIXON | N/A | REDACTED | REDACTED | B | Contractor | Hold | Estimating/Design | TBD | TBD | TBD | TBD | 8130.54 | EAC | TBD | N/A | TBD | TBD | TBD | 8130.54 | 3479.71 | TBD | N/A | No | N/A | N/A | Urban Cluster | TBD | 0 | REDACTED
REDACTED | N/A | SOLANO | DIXON | N/A | REDACTED | REDACTED | B | Contractor | Active | Construction | TBD | TBD | TBD | TBD | 31203.85 | EAC | TBD | N/A | TBD | 1790.0843 | TBD | 31203.85 | 27264.84 | Unknown | N/A | No | N/A | N/A | Urban Cluster | TBD | 43790.13 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | YOLO | WEST SACRAMENTO | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1292.95 | EAC | TBD | N/A | TBD | TBD | TBD | 1292.95 | 521.27 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SOLANO | FAIRFIELD | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 16775.36 | EAC | TBD | N/A | TBD | TBD | TBD | 16775.36 | 14211.25 | TBD | N/A | Yes | N/A | N/A | Rural | TBD | 236470.41 | REDACTED
REDACTED | N/A | YOLO | WOODLAND | N/A | REDACTED | REDACTED | B | Business | Active | Construction | 2023-04-30 | Forecast | TBD | TBD | 14726.56 | EAC | TBD | N/A | TBD | TBD | TBD | 14726.56 | 7426.68 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 303989.75 | REDACTED
REDACTED | N/A | SOLANO | VACAVILLE | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | 2023-03-15 | Forecast | TBD | TBD | 4141.58 | EAC | TBD | N/A | TBD | TBD | TBD | 4141.58 | 3481.64 | TBD | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | SOLANO | FAIRFIELD | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 22129.62 | EAC | TBD | N/A | TBD | TBD | TBD | 22129.62 | 21801.76 | TBD | N/A | Yes | N/A | N/A | Urban | TBD | 163978.94 | REDACTED
REDACTED | N/A | YOLO | WEST SACRAMENTO | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 309.98 | EAC | TBD | N/A | TBD | TBD | TBD | 309.98 | 309.98 | TBD | N/A | Yes | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SOLANO | SUISUN CITY | N/A | REDACTED | REDACTED | B | Business | Active | Planning | 2023-03-17 | Forecast | TBD | TBD | 2664.48 | EAC | TBD | N/A | TBD | TBD | TBD | 2664.48 | 2664.48 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SOLANO | VACAVILLE | N/A | REDACTED | REDACTED | B | Business | Active | Planning | TBD | TBD | TBD | TBD | 734.78 | EAC | TBD | N/A | TBD | TBD | TBD | 734.78 | 734.78 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SOLANO | VACAVILLE | N/A | REDACTED | REDACTED | B | Business | Active | Planning | 2023-03-19 | Forecast | TBD | TBD | 439.97 | EAC | TBD | N/A | TBD | TBD | TBD | 439.97 | 439.97 | TBD | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | PLACER | LINCOLN | N/A | REDACTED | REDACTED | B | Contractor | Active | Estimating/Design | 2022-09-03 | Actual | N/A | N/A | 661347.54 | Actual | N/A | N/A | 1752 | 950.9932 | 0 | 661347.54 | 647251.26 | Yes | N/A | No | N/A | N/A | Urban | 6 | 142123.95 | REDACTED
REDACTED | N/A | EL DORADO | RESCUE | N/A | REDACTED | REDACTED | B | Individual | Active | Estimating/Design | TBD | TBD | TBD | TBD | 8051.13 | EAC | TBD | N/A | TBD | TBD | TBD | 8051.13 | 7189.42 | TBD | N/A | No | N/A | N/A | Rural | TBD | 81615.61 | REDACTED
REDACTED | N/A | PLACER | ROSEVILLE | N/A | REDACTED | REDACTED | B | Government Agency | Active | Closing | 2022-02-28 | Actual | N/A | N/A | 573967.82 | Actual | N/A | N/A | 2780 | 2136.0436 | 0 | 573967.82 | 541527.08 | No | N/A | No | N/A | N/A | Urban | 7 | 160179.73 | REDACTED
REDACTED | N/A | PLACER | AUBURN | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-11-24 | Actual | N/A | N/A | 374464.3 | Actual | N/A | N/A | 2545 | 1492.809 | 1 | 374464.3 | 63841.69 | No | N/A | No | N/A | N/A | Urban Cluster | 7 | 95889.32 | REDACTED
REDACTED | N/A | PLACER | ROCKLIN | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2022-02-20 | Actual | N/A | N/A | 439880.06 | Actual | N/A | N/A | 1774 | 981.4628 | 1 | 439880.06 | 421123.2 | No | N/A | No | N/A | N/A | Urban | 7 | 352887.33 | REDACTED
REDACTED | N/A | EL DORADO | EL DORADO HILLS | N/A | REDACTED | REDACTED | B | Business | Active | Construction | TBD | TBD | TBD | TBD | 160707.97 | EAC | TBD | N/A | TBD | TBD | TBD | 160707.97 | 8997.09 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 210187.18 | REDACTED
REDACTED | N/A | PLACER | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 6178.03 | EAC | TBD | N/A | TBD | TBD | TBD | 6178.03 | 6178.03 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | MARIN | BELVEDERE | N/A | REDACTED | REDACTED | B | Government Agency | Active | Closing | 2020-11-23 | Actual | N/A | N/A | 1666711.67 | Actual | N/A | N/A | 6304.06 | 2795.4918 | Not Available | 1666711.67 | 1403.51 | Yes | N/A | No | N/A | N/A | Urban | 30 | 932486 | REDACTED
REDACTED | N/A | MARIN | TIBURON | N/A | REDACTED | REDACTED | B | Government Agency | Active | Construction | 2023-06-27 | Forecast | TBD | TBD | 4662577.11 | EAC | TBD | N/A | TBD | TBD | TBD | 1800184.9 | 1048224.54 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 1240474.32 | REDACTED
REDACTED | N/A | MARIN | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Contractor | Active | Estimating/Design | TBD | TBD | TBD | TBD | 7308.26 | EAC | TBD | N/A | TBD | TBD | TBD | 7308.26 | 6778.07 | TBD | N/A | No | N/A | N/A | Rural | TBD | 81996.09 | REDACTED
REDACTED | N/A | MARIN | BELVEDERE | N/A | REDACTED | REDACTED | B | Government Agency | Active | Construction | TBD | TBD | TBD | TBD | 718651.39 | EAC | TBD | N/A | TBD | 413.6833 | TBD | 718651.39 | 423013.48 | Unknown | N/A | No | N/A | N/A | Urban | TBD | -12585.17 | REDACTED
REDACTED | N/A | MARIN | SAN RAFAEL | N/A | REDACTED | REDACTED | B | Contractor | Active | Closing | 2022-08-13 | Actual | N/A | N/A | 981941.59 | Actual | N/A | N/A | 2071 | 1150.4624 | 3 | 981941.59 | 973491.24 | No | N/A | No | N/A | N/A | Urban | 8 | 310409.49 | REDACTED
REDACTED | N/A | MARIN | ROSS | N/A | REDACTED | REDACTED | B | Government Agency | Active | Estimating/Design | 2025-02-26 | Forecast | TBD | TBD | 6681297.77 | EAC | TBD | N/A | TBD | TBD | TBD | 254537.93 | 252791.59 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | MARIN | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Individual | Active | Estimating/Design | TBD | TBD | TBD | TBD | 308.89 | EAC | TBD | N/A | TBD | TBD | TBD | 308.89 | 308.89 | TBD | N/A | No | N/A | N/A | Rural | TBD | TBD | REDACTED
REDACTED | N/A | SONOMA | SANTA ROSA | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-03-02 | Actual | N/A | N/A | 231315.34 | Actual | N/A | N/A | 630.8529 | 630.8529 | Not Available | 231315.34 | 119.9 | No | N/A | No | N/A | N/A | Urban | 3 | 63672.64 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | SONOMA | PETALUMA | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2022-04-08 | Actual | N/A | N/A | 390634.74 | Actual | N/A | N/A | 1560 | 713.9761 | 6 | 390634.74 | 372938.91 | No | N/A | No | N/A | N/A | Urban | 4 | 118940.48 | REDACTED
REDACTED | N/A | SONOMA | HEALDSBURG | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-11-12 | Actual | N/A | N/A | 498374.98 | Actual | N/A | N/A | 1718 | 1662.309 | 0 | 498374.98 | 12684.59 | No | N/A | No | N/A | N/A | Urban | 8 | 31253.2 | REDACTED
REDACTED | N/A | SONOMA | WINDSOR | N/A | REDACTED | REDACTED | B | Business | Active | Planning | TBD | TBD | TBD | TBD | 840.74 | EAC | TBD | N/A | TBD | TBD | TBD | 840.74 | 840.74 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SONOMA | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Government Agency | Active | Planning | 2025-11-21 | Forecast | TBD | TBD | 4825856.6 | EAC | TBD | N/A | TBD | TBD | TBD | 7092.63 | 7092.63 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SONOMA | CLOVERDALE | N/A | REDACTED | REDACTED | B | Government Agency | Active | Planning | TBD | TBD | TBD | TBD | 185.96 | EAC | TBD | N/A | TBD | TBD | TBD | 185.96 | 185.96 | TBD | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | SAN FRANCISCO | SAN FRANCISCO | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-10-27 | Actual | N/A | N/A | 1390412.76 | Actual | N/A | N/A | 3011 | 1021.8512 | 0 | 1390412.76 | 1654.24 | Yes | N/A | No | N/A | N/A | Urban | 11 | 427625.62 | REDACTED
REDACTED | N/A | MONTEREY | BIG SUR | N/A | REDACTED | REDACTED | B | Government Agency | Active | Estimating/Design | TBD | TBD | TBD | TBD | 30534.36 | EAC | TBD | N/A | TBD | TBD | TBD | 30534.36 | 2973.6 | TBD | N/A | No | No | No | Rural | TBD | TBD | REDACTED
REDACTED | N/A | FRESNO | HURON | N/A | REDACTED | REDACTED | B | Government Agency | Active | Estimating/Design | TBD | TBD | TBD | TBD | 2596.25 | EAC | TBD | N/A | TBD | TBD | TBD | 2596.25 | 265.97 | TBD | N/A | Yes | N/A | N/A | Urban Cluster | TBD | 10000 | REDACTED
REDACTED | N/A | FRESNO | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Individual | Active | Planning | TBD | TBD | TBD | TBD | 176.56 | EAC | TBD | N/A | TBD | TBD | TBD | 176.56 | 176.56 | TBD | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | SAN MATEO | SOUTH SAN FRANCISCO | N/A | REDACTED | REDACTED | B | Individual | Active | Planning | TBD | TBD | TBD | TBD | 1356.48 | EAC | TBD | N/A | TBD | TBD | TBD | 1356.48 | 1356.48 | TBD | N/A | Yes | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SAN MATEO | REDWOOD CITY | N/A | REDACTED | REDACTED | C | Individual | Active | Planning | TBD | TBD | TBD | TBD | 360.54 | EAC | TBD | N/A | TBD | TBD | TBD | 360.54 | 360.54 | TBD | N/A | Yes | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | NAPA | AMERICAN CANYON | N/A | REDACTED | REDACTED | B | Government Agency | Active | Estimating/Design | 2023-09-19 | Forecast | TBD | TBD | 2663228.78 | EAC | TBD | N/A | TBD | TBD | TBD | 185855.17 | 31865.78 | TBD | N/A | No | N/A | N/A | Urban | TBD | 942067.72 | REDACTED
REDACTED | N/A | ALAMEDA | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Government Agency | Active | Estimating/Design | 2023-12-31 | Forecast | TBD | TBD | 3744570.63 | EAC | TBD | N/A | TBD | TBD | TBD | 567600.48 | 447109.07 | TBD | N/A | No | N/A | N/A | Urban | TBD | 1565208.86 | REDACTED
REDACTED | N/A | ALAMEDA | HAYWARD | N/A | REDACTED | REDACTED | B | Government Agency | Active | Estimating/Design | 2024-12-31 | Forecast | TBD | TBD | 4842187.65 | EAC | TBD | N/A | TBD | TBD | TBD | 430398.13 | 57325 | TBD | N/A | No | N/A | N/A | Urban | TBD | 1250352.91 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | SANTA CLARA | CAMPBELL | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 2130.03 | EAC | TBD | N/A | TBD | TBD | TBD | 2130.03 | 2130.03 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SAN MATEO | ATHERTON | N/A | REDACTED | REDACTED | C | Individual | Active | Closing | 2020-11-02 | Actual | N/A | N/A | 142093.77 | Actual | N/A | N/A | 461.5 | 293.2803 | 1 | 142093.77 | 0 | Yes | N/A | No | N/A | N/A | Urban | 3 | 123342.95 | REDACTED
REDACTED | N/A | SAN MATEO | MILLBRAE | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 123984.07 | EAC | TBD | N/A | TBD | TBD | TBD | 123984.07 | 68960.27 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 159279.94 | REDACTED
REDACTED | N/A | SAN MATEO | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 5456.85 | EAC | TBD | N/A | TBD | TBD | TBD | 5456.85 | 1587.73 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 32841.6 | REDACTED
REDACTED | N/A | SAN MATEO | SAN MATEO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-02-23 | Actual | N/A | N/A | 100153.3 | Actual | N/A | N/A | 187.6 | 180 | 1 | 100153.3 | 98154.37 | No | N/A | No | N/A | N/A | Urban | 2 | 30199.86 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | SAN MATEO | SOUTH SAN FRANCISCO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-06-26 | Actual | N/A | N/A | 1819886.44 | Actual | N/A | N/A | 12877.09 | 3558.1023 | Not Available | 1819886.44 | 1510613.05 | No | N/A | Yes | N/A | N/A | Urban | 8 | 631350.5 | REDACTED
REDACTED | N/A | SAN MATEO | EAST PALO ALTO | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | 2023-04-24 | Forecast | TBD | TBD | 89770.85 | EAC | TBD | N/A | TBD | TBD | TBD | 89770.85 | 78470.3 | TBD | N/A | Yes | N/A | N/A | Urban | TBD | 283982.81 | REDACTED
REDACTED | N/A | SAN MATEO | SOUTH SAN FRANCISCO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-03-25 | Actual | N/A | N/A | 358721.51 | Actual | N/A | N/A | 1130.99 | 366.7461 | Not Available | 358721.51 | 357735.83 | No | N/A | No | N/A | N/A | Urban | 3 | 115450.45 | REDACTED
REDACTED | N/A | SAN MATEO | SOUTH SAN FRANCISCO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-08-28 | Actual | N/A | N/A | 445929.97 | Actual | N/A | N/A | 1804.7 | 584.6302 | Not Available | 445929.97 | 6332.47 | No | N/A | No | N/A | N/A | Urban | 3 | 192447.37 | REDACTED
REDACTED | N/A | SAN MATEO | REDWOOD CITY | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-06-14 | Actual | N/A | N/A | 364534.06 | Actual | N/A | N/A | 439.43 | 192.0493 | 1 | 364534.06 | 363960.67 | No | N/A | No | N/A | N/A | Urban | 2 | 143899.72 | REDACTED
REDACTED | N/A | SAN MATEO | MENLO PARK | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 15662.01 | EAC | TBD | N/A | TBD | TBD | TBD | 15662.01 | 13060.22 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SAN MATEO | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1855.36 | EAC | TBD | N/A | TBD | TBD | TBD | 1855.36 | 1855.36 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | SAN MATEO | REDWOOD CITY | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-07-13 | Actual | N/A | N/A | 230439.4 | Actual | N/A | N/A | Not Available | 298 | Not Available | 230439.4 | 230439.4 | Yes | N/A | No | N/A | N/A | Urban | 1 | 62916.66 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | SAN MATEO | MENLO PARK | N/A | REDACTED | REDACTED | C | Business | Active | Planning | TBD | TBD | TBD | TBD | 1334.03 | EAC | TBD | N/A | TBD | TBD | TBD | 1334.03 | 542.93 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SAN MATEO | WOODSIDE | N/A | REDACTED | REDACTED | C | Individual | Active | Estimating/Design | 2023-04-10 | Forecast | TBD | TBD | 29835.96 | EAC | TBD | N/A | TBD | TBD | TBD | 29835.96 | 29835.96 | TBD | N/A | No | N/A | N/A | Urban | TBD | 241809.88 | REDACTED
REDACTED | N/A | SAN MATEO | DALY CITY | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 2779.48 | EAC | TBD | N/A | TBD | TBD | TBD | 2779.48 | 2371.59 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SAN MATEO | ATHERTON | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-08-09 | Actual | N/A | N/A | 83369.28 | Actual | N/A | N/A | 230 | 128.614 | 0 | 83369.28 | 2014.18 | Yes | N/A | No | N/A | N/A | Urban | 2 | 13290.87 | REDACTED
REDACTED | N/A | SAN MATEO | REDWOOD CITY | N/A | REDACTED | REDACTED | C | Contractor | Active | Closing | 2021-09-13 | Actual | N/A | N/A | 476269.2 | Actual | N/A | N/A | 1508 | 419.4135 | 0 | 476269.2 | 402367.59 | Yes | N/A | No | N/A | N/A | Rural | 1 | 122030.37 | REDACTED
REDACTED | N/A | SAN MATEO | DALY CITY | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-02-22 | Actual | N/A | N/A | 122601.52 | Actual | N/A | N/A | 505 | 115.4937 | 0 | 122601.52 | 107227.88 | No | N/A | No | N/A | N/A | Urban | 4 | 54198.25 | REDACTED
REDACTED | N/A | SAN MATEO | BELMONT | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-09-22 | Actual | N/A | N/A | 225789.37 | Actual | N/A | N/A | 870 | 287 | 4 | 225789.37 | 222924.5 | No | N/A | No | N/A | N/A | Urban | 1 | 125736.14 | REDACTED
REDACTED | N/A | SAN MATEO | MENLO PARK | N/A | REDACTED | REDACTED | C | Individual | Active | Estimating/Design | TBD | TBD | TBD | TBD | 11110.3 | EAC | TBD | N/A | TBD | TBD | TBD | 11110.3 | 4363.78 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SAN MATEO | REDWOOD CITY | N/A | REDACTED | REDACTED | C | Government Agency | Active | Construction | TBD | TBD | TBD | TBD | 327344.08 | EAC | TBD | N/A | TBD | 258.088 | TBD | 327344.08 | 4442 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 178300.58 | REDACTED
REDACTED | N/A | SAN MATEO | WOODSIDE | N/A | REDACTED | REDACTED | C | Individual | Active | Estimating/Design | TBD | TBD | TBD | TBD | 181.82 | EAC | TBD | N/A | TBD | TBD | TBD | 181.82 | 181.82 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | SAN MATEO | HILLSBOROUGH | N/A | REDACTED | REDACTED | C | Individual | Active | Estimating/Design | 2023-07-26 | Forecast | TBD | TBD | 2090.49 | EAC | TBD | N/A | TBD | TBD | TBD | 2090.49 | 2090.49 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SAN MATEO | PORTOLA VALLEY | N/A | REDACTED | REDACTED | C | Individual | Active | Estimating/Design | TBD | TBD | TBD | TBD | 2274.68 | EAC | TBD | N/A | TBD | TBD | TBD | 2274.68 | 2274.68 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SAN MATEO | MENLO PARK | N/A | REDACTED | REDACTED | C | Individual | Active | Estimating/Design | 2023-03-31 | Forecast | TBD | TBD | 1971.62 | EAC | TBD | N/A | TBD | TBD | TBD | 1971.62 | 1971.62 | TBD | N/A | No | N/A | N/A | Urban | TBD | 23057.66 | REDACTED
REDACTED | N/A | SAN MATEO | MENLO PARK | N/A | REDACTED | REDACTED | C | Business | Active | Planning | TBD | TBD | TBD | TBD | 2331.76 | EAC | TBD | N/A | TBD | TBD | TBD | 2331.76 | 2331.76 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SAN MATEO | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Business | Active | Planning | TBD | TBD | TBD | TBD | 121.81 | EAC | TBD | N/A | TBD | TBD | TBD | 121.81 | 121.81 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SAN MATEO | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Business | Active | Planning | 2023-05-09 | Forecast | TBD | TBD | 3774.86 | EAC | TBD | N/A | TBD | TBD | TBD | 3774.86 | 3774.86 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SAN MATEO | MENLO PARK | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 7445.25 | EAC | TBD | N/A | TBD | TBD | TBD | 7445.25 | 7445.25 | TBD | N/A | No | N/A | N/A | Urban | TBD | 147017.13 | REDACTED
REDACTED | N/A | SAN MATEO | MENLO PARK | N/A | REDACTED | REDACTED | C | Business | Active | Construction | 2023-04-05 | Forecast | TBD | TBD | 73907.87 | EAC | TBD | N/A | TBD | TBD | TBD | 73907.87 | 73907.87 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 94083.74 | REDACTED
REDACTED | N/A | SAN MATEO | MENLO PARK | N/A | REDACTED | REDACTED | C | Government Agency | Active | Estimating/Design | TBD | TBD | TBD | TBD | 6459.22 | EAC | TBD | N/A | TBD | TBD | TBD | 6459.22 | 6459.22 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SAN MATEO | PORTOLA VALLEY | N/A | REDACTED | REDACTED | C | Business | Active | Planning | TBD | TBD | TBD | TBD | 678.24 | EAC | TBD | N/A | TBD | TBD | TBD | 678.24 | 678.24 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SAN MATEO | MENLO PARK | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 320.98 | EAC | TBD | N/A | TBD | TBD | TBD | 320.98 | 320.98 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SAN FRANCISCO | SAN FRANCISCO | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 4103.4 | EAC | TBD | N/A | TBD | TBD | TBD | 4103.4 | 104.97 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SAN FRANCISCO | SAN FRANCISCO | N/A | REDACTED | REDACTED | C | Business | Active | Construction | 2023-04-14 | Forecast | TBD | TBD | 575858.05 | EAC | TBD | N/A | TBD | TBD | TBD | 575858.05 | 547518.59 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 687285.58 | REDACTED
REDACTED | N/A | CONTRA COSTA | ANTIOCH | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 289388.65 | EAC | TBD | N/A | TBD | 611.4763 | TBD | 289388.65 | 18280.37 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 195954.5 | REDACTED
REDACTED | N/A | CONTRA COSTA | CONCORD | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-12-02 | Actual | N/A | N/A | 272822.87 | Actual | N/A | N/A | 229.82 | 763.952 | Not Available | 272822.87 | 9422.32 | No | N/A | Yes | N/A | N/A | Rural | 5 | 169784.66 | REDACTED
REDACTED | N/A | CONTRA COSTA | CANYON | N/A | REDACTED | REDACTED | C | Government Agency | Active | Estimating/Design | 2023-04-30 | Forecast | TBD | TBD | 49449.15 | EAC | TBD | N/A | TBD | TBD | TBD | 49449.15 | 32458.43 | TBD | N/A | No | N/A | N/A | Rural | TBD | 106554.99 | REDACTED
REDACTED | N/A | CONTRA COSTA | CONCORD | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-07-13 | Actual | N/A | N/A | 169471.16 | Actual | N/A | N/A | 417.9 | 378.4699 | Not Available | 169471.16 | 160820.89 | No | N/A | No | N/A | N/A | Urban | 3 | 40244.44 | REDACTED
REDACTED | N/A | CONTRA COSTA | CONCORD | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-01-29 | Actual | N/A | N/A | 77753.14 | Actual | N/A | N/A | 163.19 | 450.1532 | Not Available | 77753.14 | 62003.75 | No | N/A | No | N/A | N/A | Urban | 3 | 60427.76 | REDACTED
REDACTED | N/A | CONTRA COSTA | BRENTWOOD | N/A | REDACTED | REDACTED | C | Individual | Active | Estimating/Design | TBD | TBD | TBD | TBD | 2565.33 | EAC | TBD | N/A | TBD | TBD | TBD | 2565.33 | 1087.93 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | CONTRA COSTA | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | 2023-05-11 | Forecast | TBD | TBD | 1743.81 | EAC | TBD | N/A | TBD | TBD | TBD | 1743.81 | 837.48 | TBD | N/A | No | No | No | Urban | TBD | TBD | REDACTED
REDACTED | N/A | CONTRA COSTA | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Contractor | Active | Estimating/Design | TBD | TBD | TBD | TBD | 7300.02 | EAC | TBD | N/A | TBD | TBD | TBD | 7300.02 | 5493.83 | TBD | N/A | No | N/A | N/A | Urban | TBD | 87587.76 | REDACTED
REDACTED | N/A | CONTRA COSTA | BRENTWOOD | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 3423.89 | EAC | TBD | N/A | TBD | TBD | TBD | 3423.89 | 2063.06 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 80260.75 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | CONTRA COSTA | BRENTWOOD | N/A | REDACTED | REDACTED | C | Individual | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1235.82 | EAC | TBD | N/A | TBD | TBD | TBD | 1235.82 | 535.58 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | CONTRA COSTA | BRENTWOOD | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | 2023-03-30 | Forecast | TBD | TBD | 65417.05 | EAC | TBD | N/A | TBD | TBD | TBD | 65417.05 | 46830.83 | TBD | N/A | No | N/A | N/A | Urban | TBD | 762734.48 | REDACTED
REDACTED | N/A | CONTRA COSTA | OAKLEY | N/A | REDACTED | REDACTED | C | Business | Active | Planning | TBD | TBD | TBD | TBD | 1872.04 | EAC | TBD | N/A | TBD | TBD | TBD | 1872.04 | 1872.04 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | CONTRA COSTA | OAKLEY | N/A | REDACTED | REDACTED | C | Business | Active | Planning | TBD | TBD | TBD | TBD | 879.65 | EAC | TBD | N/A | TBD | TBD | TBD | 879.65 | 879.65 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | CONTRA COSTA | DANVILLE | N/A | REDACTED | REDACTED | C | Business | Active | Planning | TBD | TBD | TBD | TBD | 6584.76 | EAC | TBD | N/A | TBD | TBD | TBD | 6584.76 | 6584.76 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | CONTRA COSTA | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 2403.43 | EAC | TBD | N/A | TBD | TBD | TBD | 2403.43 | 2403.43 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | CONTRA COSTA | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Individual | Active | Estimating/Design | TBD | TBD | TBD | TBD | 2930.62 | EAC | TBD | N/A | TBD | TBD | TBD | 2930.62 | 2930.62 | TBD | N/A | No | N/A | N/A | Rural | TBD | TBD | REDACTED
REDACTED | N/A | ALAMEDA | OAKLAND | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-07-19 | Actual | N/A | N/A | 226725.16 | Actual | N/A | N/A | 694.36 | 86.2236 | Not Available | 226725.16 | 0 | No | N/A | Yes | N/A | N/A | Urban | 2 | 39071.18 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | CONTRA COSTA | PINOLE | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 5061.22 | EAC | TBD | N/A | TBD | TBD | TBD | 5061.22 | 2888.1 | TBD | N/A | No | N/A | N/A | Urban | TBD | 75163.21 | REDACTED
REDACTED | N/A | ALAMEDA | OAKLAND | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 4093.09 | EAC | TBD | N/A | TBD | TBD | TBD | 4093.09 | 3685.15 | TBD | N/A | No | N/A | N/A | Urban | TBD | 106143.71 | REDACTED
REDACTED | N/A | ALAMEDA | BERKELEY | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-05-02 | Actual | N/A | N/A | 174009.14 | Actual | N/A | N/A | Not Available | 306 | Not Available | 174009.14 | 173086.61 | No | N/A | No | N/A | N/A | Urban | 2 | 80594.76 | REDACTED
REDACTED | N/A | ALAMEDA | EMERYVILLE | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 8270.1 | EAC | TBD | N/A | TBD | TBD | TBD | 8270.1 | 4826.51 | TBD | N/A | No | N/A | N/A | Urban | TBD | 458224.66 | REDACTED
REDACTED | N/A | ALAMEDA | BERKELEY | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | 2023-04-14 | Forecast | TBD | TBD | 11675.63 | EAC | TBD | N/A | TBD | TBD | TBD | 11675.63 | 9289.79 | TBD | N/A | No | N/A | N/A | Urban | TBD | 98465.73 | REDACTED
REDACTED | N/A | ALAMEDA | BERKELEY | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1839.92 | EAC | TBD | N/A | TBD | TBD | TBD | 1839.92 | 234.21 | TBD | N/A | No | N/A | N/A | Urban | TBD | 19432.46 | REDACTED
REDACTED | N/A | ALAMEDA | OAKLAND | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | 2023-04-28 | Forecast | TBD | TBD | 2553.53 | EAC | TBD | N/A | TBD | TBD | TBD | 2553.53 | 1080.99 | TBD | N/A | Yes | N/A | N/A | Urban | TBD | 49666.85 | REDACTED
REDACTED | N/A | CONTRA COSTA | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 5132.19 | EAC | TBD | N/A | TBD | TBD | TBD | 5132.19 | 3875.26 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | ALAMEDA | OAKLAND | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 499.23 | EAC | TBD | N/A | TBD | TBD | TBD | 499.23 | 251.47 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | CONTRA COSTA | RICHMOND | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 4262.45 | EAC | TBD | N/A | TBD | TBD | TBD | 4262.45 | 4262.45 | TBD | N/A | Yes | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | ALAMEDA | BERKELEY | N/A | REDACTED | REDACTED | C | Business | Active | Planning | TBD | TBD | TBD | TBD | 5535.38 | EAC | TBD | N/A | TBD | TBD | TBD | 5535.38 | 5535.38 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | ALAMEDA | OAKLAND | N/A | REDACTED | REDACTED | C | Individual | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1679.64 | EAC | TBD | N/A | TBD | TBD | TBD | 1679.64 | 1679.64 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | ALAMEDA | EMERYVILLE | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | 2023-02-06 | Forecast | TBD | TBD | 419.92 | EAC | TBD | N/A | TBD | TBD | TBD | 419.92 | 419.92 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | ALAMEDA | BERKELEY | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | 2023-04-28 | Forecast | TBD | TBD | 415.83 | EAC | TBD | N/A | TBD | TBD | TBD | 415.83 | 415.83 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | ALAMEDA | OAKLAND | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | 2023-03-09 | Forecast | TBD | TBD | 388.97 | EAC | TBD | N/A | TBD | TBD | TBD | 388.97 | 388.97 | TBD | N/A | Yes | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | CONTRA COSTA | EL CERRITO | N/A | REDACTED | REDACTED | C | Individual | Active | Planning | TBD | TBD | TBD | TBD | 371.97 | EAC | TBD | N/A | TBD | TBD | TBD | 371.97 | 371.97 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | ALAMEDA | HAYWARD | N/A | REDACTED | REDACTED | C | Contractor | Active | Construction | TBD | TBD | TBD | TBD | 40064.56 | EAC | TBD | N/A | TBD | 180.0711 | TBD | 40064.56 | 37537.14 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 65489.3 | REDACTED
REDACTED | N/A | ALAMEDA | NEWARK | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 3291.19 | EAC | TBD | N/A | TBD | TBD | TBD | 3291.19 | 1842.6 | TBD | N/A | No | N/A | N/A | Urban | TBD | 63225.51 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | ALAMEDA | FREMONT | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 3904.02 | EAC | TBD | N/A | TBD | TBD | TBD | 3904.02 | 360.54 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | ALAMEDA | NEWARK | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-11-11 | Actual | N/A | N/A | 322401.5 | Actual | N/A | N/A | 687.63 | 260.5327 | Not Available | 322401.5 | 208525.74 | No | N/A | No | N/A | N/A | Urban | 5 | 69509.54 | REDACTED
REDACTED | N/A | ALAMEDA | FREMONT | N/A | REDACTED | REDACTED | C | Business | Active | Construction | 2023-02-03 | Forecast | TBD | TBD | 603843.29 | EAC | TBD | N/A | TBD | 505.872 | TBD | 603843.29 | 424855.76 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 250772.83 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | ALAMEDA | FREMONT | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 2746.2 | EAC | TBD | N/A | TBD | TBD | TBD | 2746.2 | 818.13 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | ALAMEDA | HAYWARD | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-06-23 | Actual | N/A | N/A | 286576.62 | Actual | N/A | N/A | 243.0318 | 243.0318 | Not Available | 286576.62 | 264912.47 | No | N/A | No | N/A | N/A | Urban | 2 | 64253.37 | REDACTED
REDACTED | N/A | ALAMEDA | HAYWARD | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-10-08 | Actual | N/A | N/A | 234572.71 | Actual | N/A | N/A | 177.35 | Not Available | Not Available | 234572.71 | 234341.2 | No | N/A | No | N/A | N/A | Urban | 3 | 152251.76 | REDACTED
REDACTED | N/A | ALAMEDA | LIVERMORE | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | 2023-05-23 | Forecast | TBD | TBD | 1482.73 | EAC | TBD | N/A | TBD | TBD | TBD | 1482.73 | 162.06 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | ALAMEDA | HAYWARD | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 3078.72 | EAC | TBD | N/A | TBD | TBD | TBD | 3078.72 | 3078.72 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | ALAMEDA | FREMONT | N/A | REDACTED | REDACTED | C | Business | Active | Construction | 2023-04-01 | Forecast | TBD | TBD | 44996.38 | EAC | TBD | N/A | TBD | TBD | TBD | 44996.38 | 44996.38 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 98842.89 | REDACTED
REDACTED | N/A | ALAMEDA | HAYWARD | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 6267.73 | EAC | TBD | N/A | TBD | TBD | TBD | 6267.73 | 6267.73 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | ALAMEDA | UNION CITY | N/A | REDACTED | REDACTED | C | Business | Active | Planning | 2023-04-13 | Forecast | TBD | TBD | 2389.4 | EAC | TBD | N/A | TBD | TBD | TBD | 2389.4 | 2389.4 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | ALAMEDA | NEWARK | N/A | REDACTED | REDACTED | C | Individual | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1771.57 | EAC | TBD | N/A | TBD | TBD | TBD | 1771.57 | 1771.57 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SANTA CRUZ | SANTA CRUZ | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 181655.14 | EAC | TBD | N/A | TBD | 177.5574 | TBD | 181655.14 | 79315.53 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 37526.53 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | MONTEREY | SALINAS | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1374.86 | EAC | TBD | N/A | TBD | TBD | TBD | 1374.86 | 69.61 | TBD | N/A | No | N/A | N/A | Rural | TBD | TBD | REDACTED
REDACTED | N/A | SAN BENITO | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 56912.97 | EAC | TBD | N/A | TBD | TBD | TBD | 56912.97 | 55086.25 | Unknown | N/A | No | N/A | N/A | Urban Cluster | TBD | 42307.51 | REDACTED
REDACTED | N/A | MONTEREY | KING CITY | N/A | REDACTED | REDACTED | C | Business | Active | Planning | TBD | TBD | TBD | TBD | 10057.24 | EAC | TBD | N/A | TBD | TBD | TBD | 10057.24 | 9013.08 | TBD | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | SAN BENITO | HOLLISTER | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 23521.74 | EAC | TBD | N/A | TBD | TBD | TBD | 23521.74 | 22690.37 | TBD | N/A | No | N/A | N/A | Rural | TBD | 150958.97 | REDACTED
REDACTED | N/A | MONTEREY | MARINA | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-05-19 | Actual | N/A | N/A | 150798.99 | Actual | N/A | N/A | 1035 | 242.8356 | 0 | 150798.99 | 20463.32 | No | N/A | No | N/A | N/A | Urban | 0 | 56594.42 | REDACTED
REDACTED | N/A | MONTEREY | GREENFIELD | N/A | REDACTED | REDACTED | C | Contractor | Active | Planning | 2023-03-07 | Forecast | TBD | TBD | 218.32 | EAC | TBD | N/A | TBD | TBD | TBD | 218.32 | 218.32 | TBD | N/A | No | N/A | N/A | Urban Cluster | TBD | 0 | REDACTED
REDACTED | N/A | MONTEREY | KING CITY | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1619.72 | EAC | TBD | N/A | TBD | TBD | TBD | 1619.72 | 1619.72 | TBD | N/A | No | N/A | N/A | Rural | TBD | 83410.62 | REDACTED
REDACTED | N/A | SAN BENITO | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 5276.94 | EAC | TBD | N/A | TBD | TBD | TBD | 5276.94 | 5276.94 | TBD | N/A | No | N/A | N/A | Rural | TBD | 176766.66 | REDACTED
REDACTED | N/A | SANTA CRUZ | SANTA CRUZ | N/A | REDACTED | REDACTED | C | Contractor | Active | Planning | TBD | TBD | TBD | TBD | 611.17 | EAC | TBD | N/A | TBD | TBD | TBD | 611.17 | 611.17 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | MONTEREY | MARINA | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 6869.22 | EAC | TBD | N/A | TBD | TBD | TBD | 6869.22 | 6869.22 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 76693.27 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | SANTA CLARA | MOUNTAIN VIEW | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 14054.22 | EAC | TBD | N/A | TBD | TBD | TBD | 14054.22 | 12656.54 | TBD | N/A | No | N/A | N/A | Urban | TBD | 52250.06 | REDACTED
REDACTED | N/A | SANTA CLARA | MOUNTAIN VIEW | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-03-16 | Actual | N/A | N/A | 323072.73 | Actual | N/A | N/A | 486.11 | 504.4996 | Not Available | 323072.73 | 189429.57 | No | N/A | No | N/A | N/A | Urban | 1 | 157996.32 | REDACTED
REDACTED | N/A | SANTA CLARA | SUNNYVALE | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-12-14 | Actual | N/A | N/A | 218036.75 | Actual | N/A | N/A | 255.57 | 232.4313 | Not Available | 218036.75 | 0 | No | N/A | No | N/A | N/A | Urban | 1 | 138813.5 | REDACTED
REDACTED | N/A | SANTA CLARA | MOUNTAIN VIEW | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-01-15 | Actual | N/A | N/A | 291365.06 | Actual | N/A | N/A | 791.88 | 297.1231 | Not Available | 291365.06 | 93744.16 | No | N/A | No | N/A | N/A | Urban | 1 | 61968.2 | REDACTED
REDACTED | N/A | SANTA CLARA | SUNNYVALE | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 51401.99 | EAC | TBD | N/A | TBD | TBD | TBD | 51401.99 | 23320.37 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 25141.3 | REDACTED
REDACTED | N/A | SANTA CLARA | LOS GATOS | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-08-06 | Actual | N/A | N/A | 223454.03 | Actual | N/A | N/A | 937.97 | 280.2726 | Not Available | 223454.03 | 375.92 | No | N/A | No | N/A | N/A | Urban | 3 | 72821.93 | REDACTED
REDACTED | N/A | SANTA CLARA | SAN JOSE | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-03-20 | Actual | N/A | N/A | 420532.53 | Actual | N/A | N/A | 776.88 | 425.184 | Not Available | 420532.53 | 331061.98 | No | N/A | No | N/A | N/A | Urban | Not Available | 107862.47 | REDACTED
REDACTED | N/A | SANTA CLARA | SUNNYVALE | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 13789.64 | EAC | TBD | N/A | TBD | TBD | TBD | 13789.64 | 12054.36 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SANTA CLARA | MOUNTAIN VIEW | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 3628.62 | EAC | TBD | N/A | TBD | TBD | TBD | 3628.62 | 3205.14 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SANTA CLARA | MOUNTAIN VIEW | N/A | REDACTED | REDACTED | C | Business | Active | Planning | TBD | TBD | TBD | TBD | 948.18 | EAC | TBD | N/A | TBD | TBD | TBD | 948.18 | 216.09 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SANTA CLARA | MOUNTAIN VIEW | N/A | REDACTED | REDACTED | C | Individual | Active | Planning | TBD | TBD | TBD | TBD | 1305.42 | EAC | TBD | N/A | TBD | TBD | TBD | 1305.42 | 1088.12 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SANTA CLARA | CAMPBELL | N/A | REDACTED | REDACTED | C | Business | Active | Planning | TBD | TBD | TBD | TBD | 360.52 | EAC | TBD | N/A | TBD | TBD | TBD | 360.52 | 360.52 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SANTA CLARA | CUPERTINO | N/A | REDACTED | REDACTED | C | Business | Active | Planning | TBD | TBD | TBD | TBD | 3325.79 | EAC | TBD | N/A | TBD | TBD | TBD | 3325.79 | 1087.12 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | SANTA CLARA | LOS ALTOS | N/A | REDACTED | REDACTED | C | Individual | Active | Estimating/Design | TBD | TBD | TBD | TBD | 12139.18 | EAC | TBD | N/A | TBD | TBD | TBD | 12139.18 | 11891.42 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SANTA CLARA | SAN JOSE | N/A | REDACTED | REDACTED | C | Business | Active | Planning | TBD | TBD | TBD | TBD | 962.68 | EAC | TBD | N/A | TBD | TBD | TBD | 962.68 | 962.68 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SANTA CLARA | MOUNTAIN VIEW | N/A | REDACTED | REDACTED | C | Individual | Active | Planning | 2023-03-01 | Forecast | TBD | TBD | 481.18 | EAC | TBD | N/A | TBD | TBD | TBD | 481.18 | 481.18 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SANTA CLARA | SUNNYVALE | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 118.25 | EAC | TBD | N/A | TBD | TBD | TBD | 118.25 | 118.25 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 105398.56 | REDACTED
REDACTED | N/A | SANTA CLARA | SAN JOSE | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 158207.97 | EAC | TBD | N/A | TBD | TBD | TBD | 158207.97 | -2733.49 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 111977.3 | REDACTED
REDACTED | N/A | SANTA CLARA | MORGAN HILL | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 295126.12 | EAC | TBD | N/A | TBD | 418.2574 | TBD | 295126.12 | 611 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 142229.56 | REDACTED
REDACTED | N/A | SANTA CLARA | MORGAN HILL | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-03-02 | Actual | N/A | N/A | 305866.46 | Actual | N/A | N/A | 1853.1 | 811.3217 | Not Available | 305866.46 | 641.55 | No | N/A | No | N/A | N/A | Urban | 2 | 128074.35 | REDACTED
REDACTED | N/A | SANTA CLARA | SAN JOSE | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 5880.95 | EAC | TBD | N/A | TBD | TBD | TBD | 5880.95 | 2342.78 | TBD | N/A | No | N/A | N/A | Urban | TBD | 199641.01 | REDACTED
REDACTED | N/A | SANTA CLARA | SAN JOSE | N/A | REDACTED | REDACTED | C | Individual | Active | Closing | 2021-08-12 | Actual | 331.0903 | Design | 102512.79 | Actual | 309.6218 | Not Outlier | 358.0695 | 358.0695 | Not Available | 102512.79 | 375.93 | Yes | N/A | No | No | No | Urban | 1 | 40510.09 | REDACTED
REDACTED | N/A | SANTA CLARA | MORGAN HILL | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 16895.73 | EAC | TBD | N/A | TBD | TBD | TBD | 16895.73 | 10753.71 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 318738.65 | REDACTED
REDACTED | N/A | SANTA CLARA | SAN JOSE | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-09-14 | Actual | N/A | N/A | 80431.41 | Actual | N/A | N/A | 177 | Not Available | Not Available | 80431.41 | 73342.92 | No | N/A | No | N/A | N/A | Urban | Not Available | 30751.53 | REDACTED
REDACTED | N/A | SANTA CLARA | MORGAN HILL | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1299.92 | EAC | TBD | N/A | TBD | TBD | TBD | 1299.92 | 834.46 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SANTA CLARA | MORGAN HILL | N/A | REDACTED | REDACTED | C | Government Agency | Active | Planning | TBD | TBD | TBD | TBD | 9081.9 | EAC | TBD | N/A | TBD | TBD | TBD | 9081.9 | 6114.76 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SANTA CLARA | SAN JOSE | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-03-18 | Actual | N/A | N/A | 230581.61 | Actual | N/A | N/A | 562.4 | 301.7538 | Not Available | 230581.61 | 228273.91 | No | N/A | No | N/A | N/A | Urban | 3 | 69918.85 | REDACTED
REDACTED | N/A | SANTA CLARA | MORGAN HILL | N/A | REDACTED | REDACTED | C | Contractor | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1030.28 | EAC | TBD | N/A | TBD | TBD | TBD | 1030.28 | 727.24 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | SANTA CLARA | SAN JOSE | N/A | REDACTED | REDACTED | C | Business | Active | Planning | 2023-03-19 | Forecast | TBD | TBD | 18245.23 | EAC | TBD | N/A | TBD | TBD | TBD | 18245.23 | 15060.05 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SANTA CLARA | MORGAN HILL | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 5975.41 | EAC | TBD | N/A | TBD | TBD | TBD | 5975.41 | 5975.41 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SANTA CLARA | MORGAN HILL | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | 2023-05-19 | Forecast | TBD | TBD | 1289.44 | EAC | TBD | N/A | TBD | TBD | TBD | 1289.44 | 1289.44 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SANTA CLARA | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Individual | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1123.08 | EAC | TBD | N/A | TBD | TBD | TBD | 1123.08 | 1123.08 | TBD | N/A | No | No | No | Rural | TBD | TBD | REDACTED
REDACTED | N/A | SANTA CLARA | MORGAN HILL | N/A | REDACTED | REDACTED | C | Contractor | Active | Estimating/Design | TBD | TBD | TBD | TBD | 2181.72 | EAC | TBD | N/A | TBD | TBD | TBD | 2181.72 | 2181.72 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SANTA CLARA | MORGAN HILL | N/A | REDACTED | REDACTED | C | Government Agency | Active | Estimating/Design | TBD | TBD | TBD | TBD | 194.64 | EAC | TBD | N/A | TBD | TBD | TBD | 194.64 | 194.64 | TBD | N/A | No | No | No | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SANTA CLARA | SAN JOSE | N/A | REDACTED | REDACTED | C | Business | Active | Planning | TBD | TBD | TBD | TBD | 205.03 | EAC | TBD | N/A | TBD | TBD | TBD | 205.03 | 205.03 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SANTA CLARA | MORGAN HILL | N/A | REDACTED | REDACTED | C | Business | Active | Planning | 2023-03-17 | Forecast | TBD | TBD | 555.91 | EAC | TBD | N/A | TBD | TBD | TBD | 555.91 | 555.91 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SANTA CLARA | SAN JOSE | N/A | REDACTED | REDACTED | C | Business | Active | Planning | TBD | TBD | TBD | TBD | 176.03 | EAC | TBD | N/A | TBD | TBD | TBD | 176.03 | 176.03 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SANTA CLARA | GILROY | N/A | REDACTED | REDACTED | C | Individual | Active | Planning | TBD | TBD | TBD | TBD | 176.03 | EAC | TBD | N/A | TBD | TBD | TBD | 176.03 | 176.03 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SANTA CLARA | SAN JOSE | N/A | REDACTED | REDACTED | C | Business | Active | Planning | TBD | TBD | TBD | TBD | 880.19 | EAC | TBD | N/A | TBD | TBD | TBD | 880.19 | 880.19 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | FRESNO | CLOVIS | N/A | REDACTED | REDACTED | C | Government Agency | Active | Closing | 2022-07-27 | Actual | N/A | N/A | 396701.72 | Actual | N/A | N/A | 764.3432 | 764.3432 | Not Available | 396701.72 | 357386.47 | No | N/A | No | N/A | N/A | Rural | 1 | 0 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Business | Active | Construction | 2023-05-24 | Forecast | TBD | TBD | 83962.22 | EAC | TBD | N/A | TBD | TBD | TBD | 83962.22 | 65664.04 | Unknown | N/A | Yes | N/A | N/A | Urban | TBD | 103911.35 | REDACTED
REDACTED | N/A | FRESNO | KINGSBURG | N/A | REDACTED | REDACTED | C | Government Agency | Active | Closing | 2022-02-07 | Actual | N/A | N/A | 549309.04 | Actual | N/A | N/A | 559.3353 | 559.3353 | Not Available | 549309.04 | 320105.6 | No | N/A | No | N/A | N/A | Urban Cluster | 3 | 179476.35 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-03-26 | Actual | N/A | N/A | 57326.38 | Actual | N/A | N/A | 690.36 | 246.702 | Not Available | 57326.38 | 53352.28 | No | N/A | No | N/A | N/A | Urban | 2 | 61118.21 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-01-29 | Actual | N/A | N/A | 286326.68 | Actual | N/A | N/A | 635.2618 | 635.2618 | Not Available | 286326.68 | 259336.81 | No | N/A | No | N/A | N/A | Urban | 3 | 93311.65 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-09-08 | Actual | N/A | N/A | 341942.01 | Actual | N/A | N/A | 867.5458 | 867.5458 | Not Available | 341942.01 | -10878.58 | No | N/A | No | N/A | N/A | Rural | 2 | 113419.61 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-04-13 | Actual | N/A | N/A | 554374.88 | Actual | N/A | N/A | 238.51 | 421.2555 | Not Available | 554374.88 | 534944.53 | No | N/A | Yes | N/A | N/A | Urban | 3 | 189494.35 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-03-12 | Actual | N/A | N/A | 200046.46 | Actual | N/A | N/A | 208.32 | 442.8465 | Not Available | 200046.46 | 162290.27 | No | N/A | No | N/A | N/A | Urban | 2 | 94272.39 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 8994.86 | EAC | TBD | N/A | TBD | TBD | TBD | 8994.86 | 8297.1 | TBD | N/A | Yes | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-10-10 | Actual | N/A | N/A | 87872.64 | Actual | N/A | N/A | Not Available | 199 | Not Available | 87872.64 | 87872.64 | Yes | N/A | Yes | N/A | N/A | Urban | 1 | 72042.69 | REDACTED
REDACTED | N/A | FRESNO | CLOVIS | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 8599.86 | EAC | TBD | N/A | TBD | TBD | TBD | 8599.86 | 651.43 | TBD | N/A | No | N/A | N/A | Urban | TBD | 161827.68 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 969.93 | EAC | TBD | N/A | TBD | TBD | TBD | 969.93 | 969.93 | TBD | N/A | Yes | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | 2023-08-18 | Forecast | TBD | TBD | 5743.92 | EAC | TBD | N/A | TBD | TBD | TBD | 5743.92 | 5743.92 | TBD | N/A | No | N/A | N/A | Rural | TBD | 26117.6 | REDACTED
REDACTED | N/A | FRESNO | CLOVIS | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 4871.03 | EAC | TBD | N/A | TBD | TBD | TBD | 4871.03 | 4871.03 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 85467.96 | REDACTED
REDACTED | N/A | FRESNO | KERMAN | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1342.2 | EAC | TBD | N/A | TBD | TBD | TBD | 1342.2 | 1342.2 | TBD | N/A | Yes | N/A | N/A | Urban Cluster | TBD | TBD | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | ARROYO GRANDE | N/A | REDACTED | REDACTED | C | Individual | Active | Closing | 2021-12-06 | Actual | N/A | N/A | 196599.96 | Actual | N/A | N/A | 485.9499 | 485.9499 | Not Available | 196599.96 | 140827.68 | No | N/A | No | N/A | N/A | Rural | 1 | 111740.05 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | PISMO BEACH | N/A | REDACTED | REDACTED | C | Individual | Active | Closing | 2022-03-31 | Actual | N/A | N/A | 54820.23 | Actual | N/A | N/A | Not Available | 103 | 3 | 54820.23 | 51208.14 | Yes | N/A | No | N/A | N/A | Urban | Not Available | 27269.72 | REDACTED
REDACTED | N/A | SANTA BARBARA | SANTA MARIA | N/A | REDACTED | REDACTED | C | Contractor | Active | Estimating/Design | TBD | TBD | TBD | TBD | 12744.97 | EAC | TBD | N/A | TBD | TBD | TBD | 12744.97 | 7548.66 | TBD | N/A | No | N/A | N/A | Urban | TBD | 211567 | REDACTED
REDACTED | N/A | SANTA BARBARA | SANTA YNEZ | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-09-02 | Actual | N/A | N/A | 106091.62 | Actual | N/A | N/A | 770 | 679.6398 | 0 | 106091.62 | 101600.83 | Yes | N/A | No | N/A | N/A | Urban Cluster | 2 | 66522.05 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | SAN SIMEON | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 15493.66 | EAC | TBD | N/A | TBD | TBD | TBD | 15493.66 | 11626.4 | Unknown | N/A | No | N/A | N/A | Rural | TBD | 68405.06 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | EL PASO DE ROBLES | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 2414.13 | EAC | TBD | N/A | TBD | TBD | TBD | 2414.13 | 2196.83 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Government Agency | Active | Construction | 2023-03-04 | Forecast | TBD | TBD | 8040.41 | EAC | TBD | N/A | TBD | TBD | TBD | 8040.41 | 8040.41 | Unknown | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | SAN LUIS OBISPO | N/A | REDACTED | REDACTED | C | Government Agency | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1553.42 | EAC | TBD | N/A | TBD | TBD | TBD | 1553.42 | 1553.42 | TBD | N/A | No | N/A | N/A | Urban | TBD | 115748.37 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 2347.34 | EAC | TBD | N/A | TBD | TBD | TBD | 2347.34 | 2347.34 | TBD | N/A | No | N/A | N/A | Rural | TBD | TBD | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Government Agency | Active | Construction | 2023-03-31 | Forecast | TBD | TBD | 4373.47 | EAC | TBD | N/A | TBD | TBD | TBD | 4373.47 | 4373.47 | Unknown | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 3918.57 | EAC | TBD | N/A | TBD | TBD | TBD | 3918.57 | 3918.57 | TBD | N/A | No | N/A | N/A | Rural | TBD | TBD | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Contractor | Active | Planning | 2023-05-11 | Forecast | TBD | TBD | 379.88 | EAC | TBD | N/A | TBD | TBD | TBD | 379.88 | 379.88 | TBD | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | SAN JOAQUIN | STOCKTON | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-06-26 | Actual | N/A | N/A | 658792.75 | Actual | N/A | N/A | 403.1641 | 403.1641 | Not Available | 658792.75 | 646618.28 | No | N/A | Yes | N/A | N/A | Urban | 2 | 78416.51 | REDACTED
REDACTED | N/A | SAN JOAQUIN | TRACY | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-07-19 | Actual | N/A | N/A | 144091.5 | Actual | N/A | N/A | 301.92 | 250.5898 | Not Available | 144091.5 | 135820.49 | No | N/A | No | N/A | N/A | Urban | 4 | 73217.63 | REDACTED
REDACTED | N/A | SAN JOAQUIN | LATHROP | N/A | REDACTED | REDACTED | C | Contractor | Active | Closing | 2022-09-06 | Actual | N/A | N/A | 136077.89 | Actual | N/A | N/A | 174 | 195.2687 | 1 | 136077.89 | 91438.95 | No | N/A | Yes | N/A | N/A | Urban | 2 | 112877.47 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | SAN JOAQUIN | TRACY | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 2020.94 | EAC | TBD | N/A | TBD | TBD | TBD | 2020.94 | 2020.94 | TBD | N/A | No | No | No | Urban | TBD | 526955.13 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | SAN JOAQUIN | MANTECA | N/A | REDACTED | REDACTED | C | Individual | Active | Planning | 2023-03-13 | Forecast | TBD | TBD | 180.3 | EAC | TBD | N/A | TBD | TBD | TBD | 180.3 | 180.3 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SAN JOAQUIN | RIPON | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 548.62 | EAC | TBD | N/A | TBD | TBD | TBD | 548.62 | 548.62 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SAN JOAQUIN | MANTECA | N/A | REDACTED | REDACTED | C | Business | Active | Planning | TBD | TBD | TBD | TBD | 911.08 | EAC | TBD | N/A | TBD | TBD | TBD | 911.08 | 911.08 | TBD | N/A | Yes | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | MERCED | LOS BANOS | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-09-21 | Actual | N/A | N/A | 210207.95 | Actual | N/A | N/A | 191.1426 | 191.1426 | Not Available | 210207.95 | 91783.54 | No | N/A | Yes | N/A | N/A | Urban Cluster | 3 | 105997.09 | REDACTED
REDACTED | N/A | MERCED | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Contractor | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1075.09 | EAC | TBD | N/A | TBD | TBD | TBD | 1075.09 | 468.44 | TBD | N/A | No | N/A | N/A | Urban | TBD | 67730.15 | REDACTED
REDACTED | N/A | STANISLAUS | RIVERBANK | N/A | REDACTED | REDACTED | C | Individual | Active | Planning | TBD | TBD | TBD | TBD | 4388.44 | EAC | TBD | N/A | TBD | TBD | TBD | 4388.44 | 4388.44 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | BUTTE | CHICO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-09-01 | Actual | N/A | N/A | 308732.59 | Actual | N/A | N/A | 182 | 283.7618 | 0 | 308732.59 | 308166.12 | No | N/A | No | N/A | N/A | Urban | 1 | 75695.12 | REDACTED
REDACTED | N/A | SOLANO | FAIRFIELD | N/A | REDACTED | REDACTED | C | Business | Active | Construction | 2023-02-10 | Forecast | TBD | TBD | 8957.88 | EAC | TBD | N/A | TBD | TBD | TBD | 8957.88 | 961.75 | Unknown | N/A | No | N/A | N/A | Rural | TBD | 58165.37 | REDACTED
REDACTED | N/A | SOLANO | VACAVILLE | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 4239.91 | EAC | TBD | N/A | TBD | TBD | TBD | 4239.91 | 1027.24 | TBD | N/A | No | N/A | N/A | Urban | TBD | 107036.99 | REDACTED
REDACTED | N/A | SUTTER | YUBA CITY | N/A | REDACTED | REDACTED | C | Business | Active | Closed | 2021-06-15 | Actual | N/A | N/A | 174509.71 | Actual | N/A | N/A | 580.02 | 226.4608 | Not Available | 174509.71 | 98830.71 | No | N/A | Yes | N/A | N/A | Urban | 2 | 71787.8 | REDACTED
REDACTED | N/A | PLACER | LOOMIS | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 585.74 | EAC | TBD | N/A | TBD | TBD | TBD | 585.74 | 585.74 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | NAPA | NAPA | N/A | REDACTED | REDACTED | C | Business | Active | Construction | 2023-04-19 | Forecast | TBD | TBD | 455922.21 | EAC | TBD | N/A | TBD | TBD | TBD | 455922.21 | 417125 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 105510.22 | REDACTED
REDACTED | N/A | NAPA | SAINT HELENA | N/A | REDACTED | REDACTED | C | Individual | Active | Construction | TBD | TBD | TBD | TBD | 459098.4 | EAC | TBD | N/A | TBD | 889.1841 | TBD | 459098.4 | 77904.64 | Unknown | N/A | No | N/A | N/A | Rural | TBD | 190960.59 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | MARIN | NOVATO | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 9107.49 | EAC | TBD | N/A | TBD | TBD | TBD | 9107.49 | 8330.72 | TBD | N/A | No | N/A | N/A | Urban | TBD | 97000.86 | REDACTED
REDACTED | N/A | SOLANO | VALLEJO | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 554625.79 | EAC | TBD | N/A | TBD | 462.1668 | TBD | 554625.79 | 552782.28 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 187247.46 | REDACTED
REDACTED | N/A | NAPA | AMERICAN CANYON | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 10012.29 | EAC | TBD | N/A | TBD | TBD | TBD | 10012.29 | 10012.29 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | MARIN | TIBURON | N/A | REDACTED | REDACTED | C | Individual | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1552.98 | EAC | TBD | N/A | TBD | TBD | TBD | 1552.98 | 1552.98 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | MARIN | FAIRFAX | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | 2023-05-11 | Forecast | TBD | TBD | 419.92 | EAC | TBD | N/A | TBD | TBD | TBD | 419.92 | 419.92 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | NAPA | NAPA | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 15921.3 | EAC | TBD | N/A | TBD | TBD | TBD | 15921.3 | 15921.3 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | MARIN | TIBURON | N/A | REDACTED | REDACTED | C | Individual | Active | Planning | 2023-05-29 | Forecast | TBD | TBD | 1382.73 | EAC | TBD | N/A | TBD | TBD | TBD | 1382.73 | 1382.73 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SONOMA | SANTA ROSA | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 3300.55 | EAC | TBD | N/A | TBD | TBD | TBD | 3300.55 | 3034 | TBD | N/A | No | N/A | N/A | Urban | TBD | 19418.85 | REDACTED
REDACTED | N/A | SONOMA | SANTA ROSA | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-10-06 | Actual | N/A | N/A | 30732.88 | Actual | N/A | N/A | 183.2 | Not Available | 1 | 30732.88 | 26954.66 | No | N/A | Yes | N/A | N/A | Urban | 1 | 26527.03 | REDACTED
REDACTED | N/A | SONOMA | SANTA ROSA | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1414.96 | EAC | TBD | N/A | TBD | TBD | TBD | 1414.96 | 226.35 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SONOMA | WINDSOR | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-08-17 | Actual | N/A | N/A | 156770.9 | Actual | N/A | N/A | 174.2 | Not Available | Not Available | 156770.9 | 155455.82 | No | N/A | No | N/A | N/A | Rural | 1 | 94662.16 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | SONOMA | PETALUMA | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | 2023-04-14 | Forecast | TBD | TBD | 10277.01 | EAC | TBD | N/A | TBD | TBD | TBD | 10277.01 | 10277.01 | TBD | N/A | No | N/A | N/A | Urban | TBD | 60396.86 | REDACTED
REDACTED | N/A | SONOMA | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 180.23 | EAC | TBD | N/A | TBD | TBD | TBD | 180.23 | 180.23 | TBD | N/A | No | N/A | N/A | Rural | TBD | TBD | REDACTED
REDACTED | N/A | SONOMA | SANTA ROSA | N/A | REDACTED | REDACTED | C | Individual | Active | Planning | TBD | TBD | TBD | TBD | 731.48 | EAC | TBD | N/A | TBD | TBD | TBD | 731.48 | 731.48 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SONOMA | SANTA ROSA | N/A | REDACTED | REDACTED | C | Individual | Active | Planning | TBD | TBD | TBD | TBD | 360.54 | EAC | TBD | N/A | TBD | TBD | TBD | 360.54 | 360.54 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SAN FRANCISCO | SAN FRANCISCO | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | 2023-04-30 | Forecast | TBD | TBD | 1345966.72 | EAC | TBD | N/A | TBD | TBD | TBD | 1345966.72 | 1343236.44 | TBD | N/A | No | N/A | N/A | Urban | TBD | 782842.53 | REDACTED
REDACTED | N/A | SAN FRANCISCO | SAN FRANCISCO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-05-11 | Actual | N/A | N/A | 579134.22 | Actual | N/A | N/A | 538.57 | 205 | Not Available | 579134.22 | 579134.22 | No | N/A | No | N/A | N/A | Urban | 2 | 91969.69 | REDACTED
REDACTED | N/A | SAN FRANCISCO | SAN FRANCISCO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-02-22 | Actual | N/A | N/A | 782349.55 | Actual | N/A | N/A | 827 | 297.1492 | 0 | 782349.55 | 768577.54 | No | N/A | No | N/A | N/A | Urban | 6 | 267001.29 | REDACTED
REDACTED | N/A | CONTRA COSTA | WALNUT CREEK | N/A | REDACTED | REDACTED | C | Government Agency | Active | Construction | TBD | TBD | TBD | TBD | 1130125.75 | EAC | TBD | N/A | TBD | TBD | TBD | 1130125.75 | 3165.43 | Unknown | N/A | No | No | No | Urban | TBD | 297618.27 | REDACTED
REDACTED | N/A | CONTRA COSTA | LAFAYETTE | N/A | REDACTED | REDACTED | C | Business | Active | Construction | 2023-04-08 | Forecast | TBD | TBD | 62556.81 | EAC | TBD | N/A | TBD | TBD | TBD | 62556.81 | 46922.18 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 47893.66 | REDACTED
REDACTED | N/A | CONTRA COSTA | LAFAYETTE | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-04-23 | Actual | N/A | N/A | 186943.52 | Actual | N/A | N/A | 154.31 | 297.0817 | Not Available | 186943.52 | 172993.09 | No | N/A | No | N/A | N/A | Urban | 1 | 40738.71 | REDACTED
REDACTED | N/A | CONTRA COSTA | OAKLEY | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-07-07 | Actual | N/A | N/A | 227866.26 | Actual | N/A | N/A | 242.8104 | 242.8104 | Not Available | 227866.26 | 7314.36 | No | N/A | No | N/A | N/A | Urban | 3 | 172093.9 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | CONTRA COSTA | OAKLEY | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | 2023-04-28 | Forecast | TBD | TBD | 6092.71 | EAC | TBD | N/A | TBD | TBD | TBD | 6092.71 | 2715.74 | TBD | N/A | No | N/A | N/A | Urban | TBD | 101739.81 | REDACTED
REDACTED | N/A | CONTRA COSTA | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | 2023-04-14 | Forecast | TBD | TBD | 797.67 | EAC | TBD | N/A | TBD | TBD | TBD | 797.67 | 797.67 | TBD | N/A | Yes | N/A | N/A | Urban | TBD | 45643.79 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | CONTRA COSTA | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Individual | Active | Planning | TBD | TBD | TBD | TBD | 5041.21 | EAC | TBD | N/A | TBD | TBD | TBD | 5041.21 | 5041.21 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | CONTRA COSTA | BRENTWOOD | N/A | REDACTED | REDACTED | C | Individual | Active | Estimating/Design | TBD | TBD | TBD | TBD | 489.96 | EAC | TBD | N/A | TBD | TBD | TBD | 489.96 | 489.96 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | CONTRA COSTA | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Business | Active | Construction | 2023-06-30 | Forecast | TBD | TBD | 371.97 | EAC | TBD | N/A | TBD | TBD | TBD | 371.97 | 371.97 | Unknown | N/A | No | No | No | Urban | TBD | 142554.94 | REDACTED
REDACTED | N/A | ALAMEDA | EMERYVILLE | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-11-13 | Actual | N/A | N/A | 245322.61 | Actual | N/A | N/A | 464.9885 | 464.9885 | Not Available | 245322.61 | -62656.02 | No | N/A | Yes | N/A | N/A | Urban | 2 | 151239.95 | REDACTED
REDACTED | N/A | ALAMEDA | BERKELEY | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 59520.23 | EAC | TBD | N/A | TBD | 285.012 | TBD | 59520.23 | 119.9 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 56732.13 | REDACTED
REDACTED | N/A | ALAMEDA | EMERYVILLE | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-03-12 | Actual | N/A | N/A | 343852.8 | Actual | N/A | N/A | 807.37 | 608.5177 | Not Available | 343852.8 | 2272.51 | No | N/A | Yes | N/A | N/A | Urban | 3 | 160305.97 | REDACTED
REDACTED | N/A | ALAMEDA | OAKLAND | N/A | REDACTED | REDACTED | C | Contractor | Active | Estimating/Design | TBD | TBD | TBD | TBD | 545.09 | EAC | TBD | N/A | TBD | TBD | TBD | 545.09 | 545.09 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | ALAMEDA | OAKLAND | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-08-13 | Actual | N/A | N/A | 89310.77 | Actual | N/A | N/A | 303.94 | Not Available | Not Available | 89310.77 | 87690.63 | No | N/A | Yes | N/A | N/A | Urban | 1 | 38356.07 | REDACTED
REDACTED | N/A | ALAMEDA | EMERYVILLE | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 471.27 | EAC | TBD | N/A | TBD | TBD | TBD | 471.27 | 471.27 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 147499.4 | REDACTED
REDACTED | N/A | ALAMEDA | OAKLAND | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 216.07 | EAC | TBD | N/A | TBD | TBD | TBD | 216.07 | 216.07 | TBD | N/A | No | N/A | N/A | Urban | TBD | 54108.62 | REDACTED
REDACTED | N/A | ALAMEDA | OAKLAND | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 11407.47 | EAC | TBD | N/A | TBD | TBD | TBD | 11407.47 | 11407.47 | Unknown | N/A | Yes | N/A | N/A | Urban | TBD | 146406.84 | REDACTED
REDACTED | N/A | ALAMEDA | OAKLAND | N/A | REDACTED | REDACTED | C | Business | Active | Planning | TBD | TBD | TBD | TBD | 972.4 | EAC | TBD | N/A | TBD | TBD | TBD | 972.4 | 972.4 | TBD | N/A | Yes | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | ALAMEDA | NEWARK | N/A | REDACTED | REDACTED | C | Contractor | Active | Estimating/Design | TBD | TBD | TBD | TBD | 3218.97 | EAC | TBD | N/A | TBD | TBD | TBD | 3218.97 | 120.29 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | ALAMEDA | DUBLIN | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-05-17 | Actual | 355.7015 | Design | 478552.12 | Actual | 1345.3758 | Not Outlier | 287.2 | 353.4027 | 1 | 478552.12 | 207.77 | No | N/A | No | No | No | Urban | 1 | 172805.97 | REDACTED
REDACTED | N/A | ALAMEDA | PLEASANTON | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-04-11 | Actual | N/A | N/A | 21380.55 | Actual | N/A | N/A | 420.05 | 521.344 | Not Available | 21380.55 | 19508.58 | No | N/A | No | N/A | N/A | Rural | 2 | 32815.31 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | ALAMEDA | PLEASANTON | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-04-13 | Actual | N/A | N/A | 46042.15 | Actual | N/A | N/A | 1183.128 | 1183.128 | Not Available | 46042.15 | 5475.31 | No | N/A | No | N/A | N/A | Urban | Not Available | 54254.17 | REDACTED
REDACTED | N/A | ALAMEDA | HAYWARD | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-11-10 | Actual | N/A | N/A | 1359586.37 | Actual | N/A | N/A | 237 | 531.5087 | Not Available | 1359586.37 | 1184504.54 | No | N/A | No | N/A | N/A | Urban | 4 | 641569.8 | REDACTED
REDACTED | N/A | ALAMEDA | HAYWARD | N/A | REDACTED | REDACTED | C | Business | Active | Planning | TBD | TBD | TBD | TBD | 2649.41 | EAC | TBD | N/A | TBD | TBD | TBD | 2649.41 | 1767.91 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | ALAMEDA | NEWARK | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-12-20 | Actual | N/A | N/A | 373498.48 | Actual | N/A | N/A | 18452.4 | Not Available | Not Available | 373498.48 | 367239.53 | Yes | N/A | No | N/A | N/A | Urban | 3 | 290581.69 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | ALAMEDA | HAYWARD | N/A | REDACTED | REDACTED | C | Business | Active | Planning | 2023-05-03 | Forecast | TBD | TBD | 3414.06 | EAC | TBD | N/A | TBD | TBD | TBD | 3414.06 | 3414.06 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | MONTEREY | PEBBLE BEACH | N/A | REDACTED | REDACTED | C | Individual | Active | Estimating/Design | TBD | TBD | TBD | TBD | 14604.37 | EAC | TBD | N/A | TBD | TBD | TBD | 14604.37 | 5343.6 | TBD | N/A | No | N/A | N/A | Rural | TBD | 85508.93 | REDACTED
REDACTED | N/A | SAN BENITO | SAN JUAN BAUTISTA | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-06-26 | Actual | N/A | N/A | 416265.29 | Actual | N/A | N/A | 1624.2959 | 1624.2959 | 1 | 416265.29 | 0 | No | N/A | No | N/A | N/A | Rural | 9 | 241046.11 | REDACTED
REDACTED | N/A | SANTA CRUZ | WATSONVILLE | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-08-23 | Actual | N/A | N/A | 116717.54 | Actual | N/A | N/A | 560.8661 | 560.8661 | Not Available | 116717.54 | 5913.55 | No | N/A | Yes | N/A | N/A | Urban | 4 | 35967.86 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | MONTEREY | SAND CITY | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 31917.46 | EAC | TBD | N/A | TBD | TBD | TBD | 31917.46 | 27576 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 233176.65 | REDACTED
REDACTED | N/A | MONTEREY | CARMEL-BY-THE-SEA | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-07-09 | Actual | N/A | N/A | 167859.19 | Actual | N/A | N/A | 211.05 | 236 | Not Available | 167859.19 | 0 | Yes | N/A | No | N/A | N/A | Urban | 4 | 78915.19 | REDACTED
REDACTED | N/A | MONTEREY | KING CITY | N/A | REDACTED | REDACTED | C | Business | Active | Construction | 2023-02-26 | Forecast | TBD | TBD | 69431.72 | EAC | TBD | N/A | TBD | 366.4042 | TBD | 69431.72 | 67036.51 | Unknown | N/A | No | N/A | N/A | Urban Cluster | TBD | 75610 | REDACTED
REDACTED | N/A | MONTEREY | SEASIDE | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 2043.43 | EAC | TBD | N/A | TBD | TBD | TBD | 2043.43 | 519.64 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SANTA CRUZ | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Individual | Active | Estimating/Design | TBD | TBD | TBD | TBD | 470.91 | EAC | TBD | N/A | TBD | TBD | TBD | 470.91 | 470.91 | TBD | N/A | No | N/A | N/A | Rural | TBD | TBD | REDACTED
REDACTED | N/A | MONTEREY | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Government Agency | Active | Estimating/Design | 2023-04-07 | Forecast | TBD | TBD | 568.66 | EAC | TBD | N/A | TBD | TBD | TBD | 568.66 | 568.66 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | MONTEREY | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Contractor | Active | Estimating/Design | TBD | TBD | TBD | TBD | 472.18 | EAC | TBD | N/A | TBD | TBD | TBD | 472.18 | 472.18 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | MONTEREY | SOLEDAD | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 201.08 | EAC | TBD | N/A | TBD | TBD | TBD | 201.08 | 201.08 | TBD | N/A | No | N/A | N/A | Urban Cluster | TBD | TBD | REDACTED
REDACTED | N/A | MONTEREY | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Contractor | Active | Planning | 2023-06-18 | Forecast | TBD | TBD | 205.03 | EAC | TBD | N/A | TBD | TBD | TBD | 205.03 | 205.03 | TBD | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | SANTA CLARA | MOUNTAIN VIEW | N/A | REDACTED | REDACTED | C | Business | Active | Construction | 2023-04-30 | Forecast | TBD | TBD | 112570.92 | EAC | TBD | N/A | TBD | TBD | TBD | 112570.92 | 111187.63 | Unknown | N/A | No | No | No | Urban | TBD | 348810.97 | REDACTED
REDACTED | N/A | SANTA CLARA | SAN JOSE | N/A | REDACTED | REDACTED | C | Individual | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1001.03 | EAC | TBD | N/A | TBD | TBD | TBD | 1001.03 | 1001.03 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SANTA CLARA | LOS ALTOS HILLS | N/A | REDACTED | REDACTED | C | Individual | Active | Construction | 2023-07-25 | Forecast | TBD | TBD | 515.48 | EAC | TBD | N/A | TBD | TBD | TBD | 515.48 | 391.57 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 21590.4 | REDACTED
REDACTED | N/A | SANTA CLARA | SAN JOSE | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1382.84 | EAC | TBD | N/A | TBD | TBD | TBD | 1382.84 | 118.88 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SANTA CLARA | SAN JOSE | N/A | REDACTED | REDACTED | C | Individual | Active | Estimating/Design | TBD | TBD | TBD | TBD | 5522.36 | EAC | TBD | N/A | TBD | TBD | TBD | 5522.36 | 947.42 | TBD | N/A | No | No | No | Urban | TBD | 81114.69 | REDACTED
REDACTED | N/A | SANTA CLARA | MORGAN HILL | N/A | REDACTED | REDACTED | C | Government Agency | Active | Closing | 2022-08-19 | Actual | N/A | N/A | 650255.54 | Actual | N/A | N/A | 594.3 | 498.8034 | Not Available | 650255.54 | 583299.38 | Yes | N/A | No | N/A | N/A | Urban | 3 | 120785.89 | REDACTED
REDACTED | N/A | SANTA CLARA | MILPITAS | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1726.97 | EAC | TBD | N/A | TBD | TBD | TBD | 1726.97 | 580.59 | TBD | N/A | No | No | No | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SANTA CLARA | SAN JOSE | N/A | REDACTED | REDACTED | C | Contractor | Active | Closing | 2022-03-07 | Actual | N/A | N/A | 174227.32 | Actual | N/A | N/A | 123.786 | 123.786 | 1 | 174227.32 | 149256.86 | Yes | N/A | Yes | N/A | N/A | Urban | 1 | 30906.96 | REDACTED
REDACTED | N/A | SANTA CLARA | MORGAN HILL | N/A | REDACTED | REDACTED | C | Individual | Active | Estimating/Design | TBD | TBD | TBD | TBD | 759.7 | EAC | TBD | N/A | TBD | TBD | TBD | 759.7 | 759.7 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 8757.14 | EAC | TBD | N/A | TBD | TBD | TBD | 8757.14 | 1320.14 | TBD | N/A | No | N/A | N/A | Rural | TBD | 36655.97 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-09-23 | Actual | N/A | N/A | 245081.82 | Actual | N/A | N/A | 217.47 | 230.7577 | 1 | 245081.82 | 56.11 | No | N/A | Yes | N/A | N/A | Urban | Not Available | 76320.37 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-08-03 | Actual | N/A | N/A | 146083.72 | Actual | N/A | N/A | 314.8919 | 314.8919 | Not Available | 146083.72 | 142846.29 | No | N/A | No | N/A | N/A | Urban | 2 | 38735.66 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 9681.94 | EAC | TBD | N/A | TBD | TBD | TBD | 9681.94 | 9004.02 | Unknown | N/A | Yes | N/A | N/A | Rural | TBD | 101481.6 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Individual | Active | Estimating/Design | TBD | TBD | TBD | TBD | 330.65 | EAC | TBD | N/A | TBD | TBD | TBD | 330.65 | 113.35 | TBD | N/A | Yes | No | No | Urban | TBD | TBD | REDACTED
REDACTED | N/A | FRESNO | REEDLEY | N/A | REDACTED | REDACTED | C | Government Agency | Active | Closing | 2021-04-03 | Actual | N/A | N/A | 477483.99 | Actual | N/A | N/A | 518 | 429.2948 | 0 | 477483.99 | 328309 | No | N/A | No | N/A | N/A | Urban Cluster | 7 | 168606.34 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Business | Active | Closed | 2021-04-08 | Actual | N/A | N/A | 399887.53 | Actual | N/A | N/A | 701 | 240.5508 | 1 | 399887.53 | -8066.7 | No | N/A | Yes | N/A | N/A | Urban | 3 | 137247.3 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-08-18 | Actual | N/A | N/A | 1612891.98 | Actual | N/A | N/A | 1050 | 424.9382 | 0 | 1612891.98 | 50800.85 | Yes | N/A | Yes | N/A | N/A | Urban | 4 | 476317.39 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-04-09 | Actual | N/A | N/A | 282777.34 | Actual | N/A | N/A | 446 | 378.3505 | 0 | 282777.34 | 276266.24 | No | N/A | No | N/A | N/A | Urban | 3 | 106979.6 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1813.9 | EAC | TBD | N/A | TBD | TBD | TBD | 1813.9 | 1813.9 | TBD | N/A | Yes | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 2015.02 | EAC | TBD | N/A | TBD | TBD | TBD | 2015.02 | 2015.02 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Business | Active | Planning | TBD | TBD | TBD | TBD | 214.83 | EAC | TBD | N/A | TBD | TBD | TBD | 214.83 | 214.83 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Business | Active | Construction | 2023-04-07 | Forecast | TBD | TBD | 3597.29 | EAC | TBD | N/A | TBD | TBD | TBD | 3597.29 | 3597.29 | Unknown | N/A | Yes | No | No | Urban | TBD | 191672 | REDACTED
REDACTED | N/A | KERN | LOST HILLS | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-07-26 | Actual | N/A | N/A | 128813.25 | Actual | N/A | N/A | 359.3716 | 359.3716 | Not Available | 128813.25 | 125184.86 | No | N/A | Yes | N/A | N/A | Rural | 3 | 141768.47 | REDACTED
REDACTED | N/A | KERN | BAKERSFIELD | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-01-25 | Actual | N/A | N/A | 243549.39 | Actual | N/A | N/A | 181.99 | 287.6393 | Not Available | 243549.39 | 114161.78 | No | N/A | No | N/A | N/A | Urban | 2 | 89856.78 | REDACTED
REDACTED | N/A | KERN | MCFARLAND | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 896.75 | EAC | TBD | N/A | TBD | TBD | TBD | 896.75 | 389.26 | TBD | N/A | Yes | N/A | N/A | Urban Cluster | TBD | TBD | REDACTED
REDACTED | N/A | KERN | BAKERSFIELD | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-09-02 | Actual | 1530.5334 | Design | 810086.7 | Actual | 529.2839 | Not Outlier | 1403.73 | 1431.3926 | 2 | 810086.7 | 605603.88 | No | N/A | Yes | No | No | Rural | 9 | 295508.48 | REDACTED
REDACTED | N/A | KERN | BAKERSFIELD | N/A | REDACTED | REDACTED | C | Business | Active | Construction | 2023-04-15 | Forecast | TBD | TBD | 137983.33 | EAC | TBD | N/A | TBD | TBD | TBD | 137983.33 | 137983.33 | Unknown | N/A | No | N/A | N/A | Rural | TBD | 151619.01 | REDACTED
REDACTED | N/A | KERN | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | 2023-02-02 | Forecast | TBD | TBD | 3405.25 | EAC | TBD | N/A | TBD | TBD | TBD | 3405.25 | 3405.25 | TBD | N/A | No | N/A | N/A | Rural | TBD | TBD | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | PASO ROBLES | N/A | REDACTED | REDACTED | C | Contractor | Active | Closed | 2021-02-18 | Actual | N/A | N/A | 154442.35 | Actual | N/A | N/A | 440.1177 | 440.1177 | Not Available | 154442.35 | 1879.69 | No | N/A | No | N/A | N/A | Urban | 1 | 84677.51 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | SAN LUIS OBISPO | N/A | REDACTED | REDACTED | C | Contractor | Active | Closing | 2021-09-26 | Actual | N/A | N/A | 449467.27 | Actual | N/A | N/A | 227.4782 | 227.4782 | Not Available | 449467.27 | 98941.49 | No | N/A | No | N/A | N/A | Urban | 2 | 91063.75 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | ARROYO GRANDE | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 2531.75 | EAC | TBD | N/A | TBD | TBD | TBD | 2531.75 | 1647.68 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | SAN LUIS OBISPO | N/A | REDACTED | REDACTED | C | Government Agency | Active | Planning | TBD | TBD | TBD | TBD | 11449.99 | EAC | TBD | N/A | TBD | TBD | TBD | 11449.99 | 8169.67 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | EL PASO DE ROBLES | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 387314.86 | EAC | TBD | N/A | TBD | TBD | TBD | 387314.86 | 385684.36 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 228352.42 | REDACTED
REDACTED | N/A | SANTA BARBARA | SANTA MARIA | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-02-26 | Actual | N/A | N/A | 228231.46 | Actual | N/A | N/A | 679.1269 | 679.1269 | Not Available | 228231.46 | 3623.87 | Yes | N/A | No | N/A | N/A | Urban | 3 | 180107.92 | REDACTED
REDACTED | N/A | SANTA BARBARA | GUADALUPE | N/A | REDACTED | REDACTED | C | Government Agency | Active | Estimating/Design | TBD | TBD | TBD | TBD | 4889.36 | EAC | TBD | N/A | TBD | TBD | TBD | 4889.36 | 935.26 | TBD | N/A | Yes | N/A | N/A | Urban Cluster | TBD | 191094.47 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | SAN LUIS OBISPO | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1176.41 | EAC | TBD | N/A | TBD | TBD | TBD | 1176.41 | 113.35 | TBD | N/A | No | N/A | N/A | Urban | TBD | 74864.48 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | EL PASO DE ROBLES | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1527.15 | EAC | TBD | N/A | TBD | TBD | TBD | 1527.15 | 1527.15 | TBD | N/A | No | N/A | N/A | Urban | TBD | 111613.37 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | EL PASO DE ROBLES | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | 2023-04-28 | Forecast | TBD | TBD | 1129.98 | EAC | TBD | N/A | TBD | TBD | TBD | 1129.98 | 1129.98 | TBD | N/A | No | N/A | N/A | Urban | TBD | 57542.19 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | PISMO BEACH | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 205.03 | EAC | TBD | N/A | TBD | TBD | TBD | 205.03 | 205.03 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | SAN LUIS OBISPO | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 205.03 | EAC | TBD | N/A | TBD | TBD | TBD | 205.03 | 205.03 | TBD | N/A | No | N/A | N/A | Rural | TBD | TBD | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | ARROYO GRANDE | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | 2023-01-12 | Forecast | TBD | TBD | 176.03 | EAC | TBD | N/A | TBD | TBD | TBD | 176.03 | 176.03 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SAN JOAQUIN | TRACY | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 83142.64 | EAC | TBD | N/A | TBD | 691.8837 | TBD | 83142.64 | 1343.73 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 82499.5 | REDACTED
REDACTED | N/A | SAN JOAQUIN | RIPON | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 3644.32 | EAC | TBD | N/A | TBD | TBD | TBD | 3644.32 | 759.32 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 107200.01 | REDACTED
REDACTED | N/A | SAN JOAQUIN | STOCKTON | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 105314.19 | EAC | TBD | N/A | TBD | 396.093 | TBD | 105314.19 | 101124.5 | Unknown | N/A | Yes | N/A | N/A | Urban | TBD | 78387.09 | REDACTED
REDACTED | N/A | SAN JOAQUIN | TRACY | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 16728.5 | EAC | TBD | N/A | TBD | TBD | TBD | 16728.5 | 795.53 | TBD | N/A | No | N/A | N/A | Rural | TBD | 61036.05 | REDACTED
REDACTED | N/A | SAN JOAQUIN | RIPON | N/A | REDACTED | REDACTED | C | Individual | Active | Planning | TBD | TBD | TBD | TBD | 2689.43 | EAC | TBD | N/A | TBD | TBD | TBD | 2689.43 | 2689.43 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SAN JOAQUIN | TRACY | N/A | REDACTED | REDACTED | C | Contractor | Active | Estimating/Design | TBD | TBD | TBD | TBD | 236.51 | EAC | TBD | N/A | TBD | TBD | TBD | 236.51 | 236.51 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | MADERA | MADERA | N/A | REDACTED | REDACTED | C | Government Agency | Active | Closing | 2020-04-17 | Actual | N/A | N/A | 323519.39 | Actual | N/A | N/A | 474.9 | 685.2592 | Not Available | 323519.39 | 0 | No | N/A | Yes | N/A | N/A | Urban | 3 | 172783.72 | REDACTED
REDACTED | N/A | STANISLAUS | OAKDALE | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 656701.34 | EAC | TBD | N/A | TBD | 847.0537 | TBD | 656701.34 | 651235.73 | Unknown | N/A | Yes | N/A | N/A | Urban | TBD | 463056.86 | REDACTED
REDACTED | N/A | STANISLAUS | RIVERBANK | N/A | REDACTED | REDACTED | C | Individual | Active | Estimating/Design | 2023-03-24 | Forecast | TBD | TBD | 9317.8 | EAC | TBD | N/A | TBD | TBD | TBD | 9317.8 | 9317.8 | TBD | N/A | No | N/A | N/A | Urban | TBD | 99812.11 | REDACTED
REDACTED | N/A | STANISLAUS | RIVERBANK | N/A | REDACTED | REDACTED | C | Individual | Active | Planning | TBD | TBD | TBD | TBD | 634.23 | EAC | TBD | N/A | TBD | TBD | TBD | 634.23 | 634.23 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | STANISLAUS | OAKDALE | N/A | REDACTED | REDACTED | C | Individual | Active | Planning | TBD | TBD | TBD | TBD | 202.32 | EAC | TBD | N/A | TBD | TBD | TBD | 202.32 | 202.32 | TBD | N/A | Yes | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SHASTA | REDDING | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-10-04 | Actual | N/A | N/A | 212211.37 | Actual | N/A | N/A | 893.0949 | 893.0949 | Not Available | 212211.37 | 207972.27 | No | N/A | No | N/A | N/A | Rural | 4 | 123535.17 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | YOLO | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Individual | Active | Closing | 2022-03-24 | Actual | 114 | Design | 124706.44 | Actual | 1093.9161 | Not Outlier | 232.92 | 114 | 1 | 124706.44 | 114206.69 | Yes | N/A | No | No | No | Urban | 3 | 17486.22 | REDACTED
REDACTED | N/A | SOLANO | FAIRFIELD | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 7398.12 | EAC | TBD | N/A | TBD | TBD | TBD | 7398.12 | 6533.45 | TBD | N/A | No | No | No | Urban | TBD | 138787.4 | REDACTED
REDACTED | N/A | YOLO | WOODLAND | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-05-25 | Actual | 291.1866 | Design | 177643.25 | Actual | 610.0667 | Not Outlier | 317.2082 | 317.2082 | Not Available | 177643.25 | 177032.63 | No | N/A | No | No | No | Rural | Not Available | 73836.36 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | SOLANO | FAIRFIELD | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 865.96 | EAC | TBD | N/A | TBD | TBD | TBD | 865.96 | 865.96 | TBD | N/A | No | N/A | N/A | Rural | TBD | TBD | REDACTED
REDACTED | N/A | SOLANO | FAIRFIELD | N/A | REDACTED | REDACTED | C | Business | Active | Construction | 2023-05-31 | Forecast | TBD | TBD | 686.01 | EAC | TBD | N/A | TBD | TBD | TBD | 686.01 | 686.01 | Unknown | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | SOLANO | FAIRFIELD | N/A | REDACTED | REDACTED | C | Individual | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1349.85 | EAC | TBD | N/A | TBD | TBD | TBD | 1349.85 | 1349.85 | TBD | N/A | No | No | No | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SOLANO | FAIRFIELD | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1005.36 | EAC | TBD | N/A | TBD | TBD | TBD | 1005.36 | 1005.36 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | EL DORADO | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 87917.35 | EAC | TBD | N/A | TBD | TBD | TBD | 87917.35 | 82974.75 | Unknown | N/A | No | N/A | N/A | Rural | TBD | 31441.63 | REDACTED
REDACTED | N/A | PLACER | LINCOLN | N/A | REDACTED | REDACTED | C | Contractor | Active | Closing | 2022-02-15 | Actual | N/A | N/A | 172749.56 | Actual | N/A | N/A | 225.9847 | 225.9847 | Not Available | 172749.56 | 166249.31 | No | N/A | No | N/A | N/A | Rural | 1 | 23619.83 | REDACTED
REDACTED | N/A | PLACER | GRANITE BAY | N/A | REDACTED | REDACTED | C | Business | Hold | Construction | TBD | TBD | TBD | TBD | 164772.72 | EAC | TBD | N/A | TBD | 270.9567 | TBD | 164772.72 | 85907.96 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 80966.02 | REDACTED
REDACTED | N/A | PLACER | LINCOLN | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-06-28 | Actual | N/A | N/A | 89614.64 | Actual | N/A | N/A | 656.3032 | 656.3032 | 1 | 89614.64 | 57228.65 | No | N/A | No | N/A | N/A | Rural | 3 | 56622.95 | REDACTED
REDACTED | N/A | PLACER | ROSEVILLE | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-10-09 | Actual | N/A | N/A | 140553.59 | Actual | N/A | N/A | 747.1773 | 747.1773 | Not Available | 140553.59 | 139427.88 | Yes | N/A | No | N/A | N/A | Urban | 2 | 86762.35 | REDACTED
REDACTED | N/A | COLUSA | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-07-02 | Actual | N/A | N/A | 220265.74 | Actual | N/A | N/A | Not Available | 524 | Not Available | 220265.74 | 220265.74 | No | N/A | No | N/A | N/A | Rural | 2 | 57039.62 | REDACTED
REDACTED | N/A | NEVADA | GRASS VALLEY | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-06-21 | Actual | N/A | N/A | 77287.88 | Actual | N/A | N/A | 746.4728 | 746.4728 | Not Available | 77287.88 | 76957.89 | No | N/A | No | N/A | N/A | Rural | 1 | 47420.03 | REDACTED
REDACTED | N/A | SUTTER | LIVE OAK | N/A | REDACTED | REDACTED | C | Business | Active | Construction | 2023-04-06 | Forecast | TBD | TBD | 2179.65 | EAC | TBD | N/A | TBD | TBD | TBD | 2179.65 | 728.65 | Unknown | N/A | No | N/A | N/A | Urban Cluster | TBD | 47745.19 | REDACTED
REDACTED | N/A | EL DORADO | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Individual | Active | Estimating/Design | TBD | TBD | TBD | TBD | 341.75 | EAC | TBD | N/A | TBD | TBD | TBD | 341.75 | 341.75 | TBD | N/A | No | N/A | N/A | Rural | TBD | 6043.27 | REDACTED
REDACTED | N/A | PLACER | ROSEVILLE | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-12-03 | Actual | N/A | N/A | 89692.32 | Actual | N/A | N/A | 971 | 1043.1941 | 0 | 89692.32 | 0 | Yes | N/A | No | N/A | N/A | Urban | 3 | 67351.15 | REDACTED
REDACTED | N/A | PLACER | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Contractor | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1551.19 | EAC | TBD | N/A | TBD | TBD | TBD | 1551.19 | 1551.19 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | PLACER | ROSEVILLE | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 535.94 | EAC | TBD | N/A | TBD | TBD | TBD | 535.94 | 535.94 | TBD | N/A | No | N/A | N/A | Rural | TBD | TBD | REDACTED
REDACTED | N/A | MARIN | SAN RAFAEL | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-03-09 | Actual | N/A | N/A | 217258.41 | Actual | N/A | N/A | 520.98 | 214.9238 | 2 | 217258.41 | 4771.77 | No | N/A | No | N/A | N/A | Urban | 1 | 143277.87 | REDACTED
REDACTED | N/A | SONOMA | CALISTOGA | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-07-16 | Actual | N/A | N/A | 133234.36 | Actual | N/A | N/A | 1033.069 | 1033.069 | Not Available | 133234.36 | 1368.83 | No | N/A | No | N/A | N/A | Rural | Not Available | 73037.23 | REDACTED
REDACTED | N/A | SOLANO | VALLEJO | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 124980.1 | EAC | TBD | N/A | TBD | 472.8638 | TBD | 124980.1 | 11609.61 | Unknown | N/A | Yes | N/A | N/A | Urban | TBD | 78190.73 | REDACTED
REDACTED | N/A | NAPA | SAINT HELENA | N/A | REDACTED | REDACTED | C | Contractor | Active | Closing | 2022-04-28 | Actual | N/A | N/A | 99388.67 | Actual | N/A | N/A | 549.63 | 769.3173 | Not Available | 99388.67 | 98592.14 | No | N/A | No | N/A | N/A | Rural | 2 | 77058.74 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | MARIN | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Individual | Active | Estimating/Design | TBD | TBD | TBD | TBD | 4506.24 | EAC | TBD | N/A | TBD | TBD | TBD | 4506.24 | 4325.48 | TBD | N/A | No | N/A | N/A | Urban | TBD | 21198.25 | REDACTED
REDACTED | N/A | MARIN | TIBURON | N/A | REDACTED | REDACTED | C | Individual | Active | Construction | 2023-03-29 | Forecast | TBD | TBD | 9747.33 | EAC | TBD | N/A | TBD | TBD | TBD | 9747.33 | 8053.79 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 63164.93 | REDACTED
REDACTED | N/A | MARIN | NOVATO | N/A | REDACTED | REDACTED | C | Contractor | Active | Construction | TBD | TBD | TBD | TBD | 38362.41 | EAC | TBD | N/A | TBD | TBD | TBD | 38362.41 | 33209.12 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 47761.38 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | NAPA | CALISTOGA | N/A | REDACTED | REDACTED | C | Contractor | Active | Closing | 2022-09-02 | Actual | N/A | N/A | 201695.05 | Actual | N/A | N/A | Not Available | 320 | Not Available | 201695.05 | 199653.01 | No | N/A | No | N/A | N/A | Rural | 1 | 61287.36 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | NAPA | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1069.58 | EAC | TBD | N/A | TBD | TBD | TBD | 1069.58 | 739.59 | TBD | N/A | No | N/A | N/A | Rural | TBD | TBD | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | NAPA | NAPA | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-03-07 | Actual | N/A | N/A | 350741.19 | Actual | N/A | N/A | 1920 | 2175.2832 | 2 | 350741.19 | 335490.41 | Yes | N/A | No | N/A | N/A | Rural | 10 | 200225.11 | REDACTED
REDACTED | N/A | NAPA | AMERICAN CANYON | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 5396.62 | EAC | TBD | N/A | TBD | TBD | TBD | 5396.62 | 5396.62 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | NAPA | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Contractor | Active | Estimating/Design | TBD | TBD | TBD | TBD | 23680.29 | EAC | TBD | N/A | TBD | TBD | TBD | 23680.29 | 23680.29 | TBD | N/A | No | N/A | N/A | Rural | TBD | 207098.61 | REDACTED
REDACTED | N/A | NAPA | SAINT HELENA | N/A | REDACTED | REDACTED | C | Government Agency | Active | Estimating/Design | TBD | TBD | TBD | TBD | 5403.47 | EAC | TBD | N/A | TBD | TBD | TBD | 5403.47 | 5403.47 | TBD | N/A | No | N/A | N/A | Urban Cluster | TBD | TBD | REDACTED
REDACTED | N/A | MARIN | CORTE MADERA | N/A | REDACTED | REDACTED | C | Contractor | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1841.72 | EAC | TBD | N/A | TBD | TBD | TBD | 1841.72 | 1841.72 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | NAPA | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Individual | Active | Estimating/Design | TBD | TBD | TBD | TBD | 899.24 | EAC | TBD | N/A | TBD | TBD | TBD | 899.24 | 899.24 | TBD | N/A | No | N/A | N/A | Rural | TBD | TBD | REDACTED
REDACTED | N/A | NAPA | NAPA | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | 2023-03-23 | Forecast | TBD | TBD | 6056.62 | EAC | TBD | N/A | TBD | TBD | TBD | 6056.62 | 6056.62 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | NAPA | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 562.19 | EAC | TBD | N/A | TBD | TBD | TBD | 562.19 | 562.19 | TBD | N/A | No | N/A | N/A | Rural | TBD | TBD | REDACTED
REDACTED | N/A | MARIN | CORTE MADERA | N/A | REDACTED | REDACTED | C | Business | Active | Planning | TBD | TBD | TBD | TBD | 514.81 | EAC | TBD | N/A | TBD | TBD | TBD | 514.81 | 514.81 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SONOMA | SANTA ROSA | N/A | REDACTED | REDACTED | C | Business | Active | Construction | 2023-06-30 | Forecast | TBD | TBD | 54915.86 | EAC | TBD | N/A | TBD | TBD | TBD | 54915.86 | 49801.96 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 84265.86 | REDACTED
REDACTED | N/A | SONOMA | PETALUMA | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-10-10 | Actual | N/A | N/A | 354514.39 | Actual | N/A | N/A | 330.5832 | 330.5832 | Not Available | 354514.39 | -1371.73 | No | N/A | No | N/A | N/A | Urban | 3 | 116825.52 | REDACTED
REDACTED | N/A | SONOMA | CAZADERO | N/A | REDACTED | REDACTED | C | Contractor | Active | Closing | 2022-02-14 | Actual | N/A | N/A | 122902.38 | Actual | N/A | N/A | 326.2164 | 326.2164 | Not Available | 122902.38 | 116714.24 | No | N/A | No | N/A | N/A | Rural | Not Available | 41169.46 | REDACTED
REDACTED | N/A | SONOMA | SANTA ROSA | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | 2023-06-30 | Forecast | TBD | TBD | 10664.49 | EAC | TBD | N/A | TBD | TBD | TBD | 10664.49 | 10664.49 | TBD | N/A | No | N/A | N/A | Urban | TBD | 315975.5 | REDACTED
REDACTED | N/A | SONOMA | SANTA ROSA | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 546.5 | EAC | TBD | N/A | TBD | TBD | TBD | 546.5 | 546.5 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SONOMA | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Contractor | Active | Estimating/Design | TBD | TBD | TBD | TBD | 800.5 | EAC | TBD | N/A | TBD | TBD | TBD | 800.5 | 800.5 | TBD | N/A | No | N/A | N/A | Rural | TBD | 95908.98 | REDACTED
REDACTED | N/A | SANTA CLARA | SUNNYVALE | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 16558.2 | EAC | TBD | N/A | TBD | TBD | TBD | 16558.2 | 1795.56 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Contractor | Active | Closing | 2022-12-09 | Actual | N/A | N/A | 11429.57 | Actual | N/A | N/A | 830 | 1077 | 2 | 11429.57 | 11429.57 | Yes | N/A | Yes | N/A | N/A | Urban | 6 | 0 | REDACTED
REDACTED | N/A | FRESNO | CLOVIS | N/A | REDACTED | REDACTED | C | Business | Active | Planning | TBD | TBD | TBD | TBD | 357.66 | EAC | TBD | N/A | TBD | TBD | TBD | 357.66 | 357.66 | TBD | N/A | No | N/A | N/A | Rural | TBD | 0 | REDACTED
REDACTED | N/A | FRESNO | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Individual | Active | Planning | TBD | TBD | TBD | TBD | 176.03 | EAC | TBD | N/A | TBD | TBD | TBD | 176.03 | 176.03 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SOLANO | VALLEJO | N/A | REDACTED | REDACTED | C | Government Agency | Active | Closing | 2021-09-14 | Actual | N/A | N/A | 484714.77 | Actual | N/A | N/A | 1266.57 | 290.3135 | Not Available | 484714.77 | 0 | No | N/A | Yes | N/A | N/A | Urban | 3 | 177652.73 | REDACTED
REDACTED | N/A | HUMBOLDT | FORTUNA | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1306.23 | EAC | TBD | N/A | TBD | TBD | TBD | 1306.23 | 447.12 | TBD | N/A | No | N/A | N/A | Urban Cluster | TBD | TBD | REDACTED
REDACTED | N/A | HUMBOLDT | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Individual | Active | Construction | TBD | TBD | TBD | TBD | 2103.85 | EAC | TBD | N/A | TBD | TBD | TBD | 2103.85 | 2103.85 | Unknown | N/A | No | N/A | N/A | Rural | TBD | 19164.18 | REDACTED
REDACTED | N/A | YOLO | WEST SACRAMENTO | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | 2023-04-21 | Forecast | TBD | TBD | 4797.53 | EAC | TBD | N/A | TBD | TBD | TBD | 4797.53 | 4797.53 | TBD | N/A | Yes | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SAN MATEO | SOUTH SAN FRANCISCO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-03-29 | Actual | N/A | N/A | 305233.51 | Actual | N/A | N/A | 278.05 | 325.4085 | Not Available | 305233.51 | 235187.15 | Yes | N/A | Yes | N/A | N/A | Urban | 3 | 176276.69 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | SAN FRANCISCO | SAN FRANCISCO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-10-14 | Actual | N/A | N/A | 245345.3 | Actual | N/A | N/A | 310 | 262.3321 | 0 | 245345.3 | 96.25 | No | N/A | No | N/A | N/A | Urban | 1 | 114298.69 | REDACTED
REDACTED | N/A | SAN MATEO | REDWOOD CITY | N/A | REDACTED | REDACTED | C | Individual | Active | Construction | TBD | TBD | TBD | TBD | 75892.84 | EAC | TBD | N/A | TBD | TBD | TBD | 75892.84 | 75336.62 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 70687.47 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | SAN MATEO | HILLSBOROUGH | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 3108.3 | EAC | TBD | N/A | TBD | TBD | TBD | 3108.3 | 3108.3 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 24784.63 | REDACTED
REDACTED | N/A | PLACER | ROSEVILLE | N/A | REDACTED | REDACTED | B | Business | Active | Closed | 2020-02-12 | Actual | N/A | N/A | 358532.63 | Actual | N/A | N/A | 2646.7023 | 2609.608 | Not Available | 358532.63 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 8 | 141327.87 | REDACTED
REDACTED | N/A | FRESNO | REEDLEY | N/A | REDACTED | REDACTED | B | Contractor | Active | Closed | 2020-01-15 | Actual | N/A | N/A | 325618.07 | Actual | N/A | N/A | 2568 | 908.1066 | 0 | 325618.07 | 0 | Unknown | N/A | Yes | N/A | N/A | Urban Cluster | 3 | 68888.73 | REDACTED
REDACTED | N/A | NAPA | CALISTOGA | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-05-16 | Actual | N/A | N/A | 344530.99 | Actual | N/A | N/A | 835.14 | 2382.4963 | Not Available | 344530.99 | 0 | Unknown | N/A | No | N/A | N/A | Urban Cluster | 15 | -3497.99 | REDACTED
REDACTED | N/A | SAN MATEO | DALY CITY | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-08-02 | Actual | N/A | N/A | 493270.22 | Actual | N/A | N/A | 802.65 | 1109.0213 | Not Available | 493270.22 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 4 | 57182.42 | REDACTED
REDACTED | N/A | ALAMEDA | FREMONT | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-01-23 | Actual | N/A | N/A | 335618.41 | Actual | N/A | N/A | 152.3 | 2381.7895 | Not Available | 335618.41 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 10 | 46948.09 | REDACTED
REDACTED | N/A | SANTA CLARA | MILPITAS | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-02-06 | Actual | N/A | N/A | 563580.17 | Actual | N/A | N/A | 224.16 | 1798.1778 | Not Available | 563580.17 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 7 | -27342.81 | REDACTED
REDACTED | N/A | SOLANO | VACAVILLE | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-03-04 | Actual | N/A | N/A | 602901.22 | Actual | N/A | N/A | 120 | 1402.5832 | Not Available | 602901.22 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 6 | 69861.88 | REDACTED
REDACTED | N/A | CONTRA COSTA | ANTIOCH | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-03-11 | Actual | N/A | N/A | 185808.9 | Actual | N/A | N/A | 60 | 1773.8776 | Not Available | 185808.9 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 6 | 11518.89 | REDACTED
REDACTED | N/A | ALAMEDA | OAKLAND | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-01-29 | Actual | N/A | N/A | 204829.88 | Actual | N/A | N/A | 1218.9 | 1302.5159 | Not Available | 204829.88 | 0 | Unknown | N/A | Yes | N/A | N/A | Urban | 7 | 19801.98 | REDACTED
REDACTED | N/A | SANTA CLARA | MOUNTAIN VIEW | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-05-15 | Actual | N/A | N/A | 698897.89 | Actual | N/A | N/A | 834.91 | 1602.1356 | Not Available | 698897.89 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 6 | 233695.7 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-06-11 | Actual | N/A | N/A | 328298.07 | Actual | N/A | N/A | 1742.66 | 2104.1155 | 1 | 328298.07 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 6 | 72431.5 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | B | Government Agency | Active | Closing | 2020-05-19 | Actual | N/A | N/A | 602252.46 | Actual | N/A | N/A | 590.97 | 3921.99 | Not Available | 602252.46 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 13 | 277476.39 | REDACTED
REDACTED | N/A | ALAMEDA | FREMONT | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-02-19 | Actual | N/A | N/A | 373695.35 | Actual | N/A | N/A | 406.76 | 988.2935 | Not Available | 373695.35 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 7 | 144147.67 | REDACTED
REDACTED | N/A | SOLANO | FAIRFIELD | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-03-04 | Actual | N/A | N/A | 1156884.5 | Actual | N/A | N/A | 917 | 2920.0221 | Not Available | 1156884.5 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 9 | 194868.07 | REDACTED
REDACTED | N/A | FRESNO | CLOVIS | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-08-15 | Actual | N/A | N/A | 984645.22 | Actual | N/A | N/A | 6794.91 | 2714.62 | Not Available | 984645.22 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 7 | 328167.43 | REDACTED
REDACTED | N/A | ALAMEDA | OAKLAND | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-01-30 | Actual | N/A | N/A | 365087.77 | Actual | N/A | N/A | 520.81 | 749.161 | 1 | 365087.77 | 0 | Unknown | N/A | Yes | N/A | N/A | Urban | 1 | 82700.13 | REDACTED
REDACTED | N/A | CONTRA COSTA | SAN RAMON | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-05-19 | Actual | N/A | N/A | 204272.42 | Actual | N/A | N/A | 77.11 | 849.1929 | Not Available | 204272.42 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 1 | 68896.45 | REDACTED
REDACTED | N/A | NAPA | NAPA | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-01-26 | Actual | N/A | N/A | 578380.12 | Actual | N/A | N/A | 143.26 | 465.9497 | Not Available | 578380.12 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 5 | 152244.4 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | SAN LUIS OBISPO | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-10-09 | Actual | N/A | N/A | 1173428.99 | Actual | N/A | N/A | 1809.38 | 4031.063 | Not Available | 1173428.99 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 14 | 504442.66 | REDACTED
REDACTED | N/A | SAN JOAQUIN | TRACY | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-06-28 | Actual | N/A | N/A | 180507.47 | Actual | N/A | N/A | 95 | 2725.389 | Not Available | 180507.47 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 8 | 146726.72 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | TEMPLETON | N/A | REDACTED | REDACTED | B | Individual | Active | Closing | 2020-08-03 | Actual | N/A | N/A | 904729.23 | Actual | N/A | N/A | 1728.16 | 2507.2523 | Not Available | 904729.23 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 5 | 281419.56 | REDACTED
REDACTED | N/A | SOLANO | VACAVILLE | N/A | REDACTED | REDACTED | B | Business | Active | Closed | 2020-11-13 | Actual | N/A | N/A | 446587.36 | Actual | N/A | N/A | 139 | 6501.5034 | Not Available | 446587.36 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 11 | 77642.7 | REDACTED
REDACTED | N/A | SANTA CLARA | STANFORD | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-03-22 | Actual | N/A | N/A | 219650.71 | Actual | N/A | N/A | 839.83 | 217.183 | Not Available | 219650.71 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 8 | 5657.89 | REDACTED
REDACTED | N/A | FRESNO | FRIANT | N/A | REDACTED | REDACTED | B | Government Agency | Active | Closing | 2021-02-18 | Actual | N/A | N/A | 841528.06 | Actual | N/A | N/A | 775.92 | 5705.5557 | Not Available | 841528.06 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 16 | 297471.56 | REDACTED
REDACTED | N/A | CONTRA COSTA | OAKLEY | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-07-10 | Actual | N/A | N/A | 412551.53 | Actual | N/A | N/A | 77.38 | 809.1717 | Not Available | 412551.53 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 3 | 144300.33 | REDACTED
REDACTED | N/A | SAN MATEO | SAN CARLOS | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-06-20 | Actual | N/A | N/A | 150526.03 | Actual | N/A | N/A | 939.25 | 790.7851 | 1 | 150526.03 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 6 | 41054.59 | REDACTED
REDACTED | N/A | MONTEREY | GREENFIELD | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-03-03 | Actual | N/A | N/A | 235132.46 | Actual | N/A | N/A | 446.08 | 939.3416 | Not Available | 235132.46 | 0 | Unknown | N/A | No | N/A | N/A | Urban Cluster | 4 | 40196.03 | REDACTED
REDACTED | N/A | SONOMA | COTATI | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-07-10 | Actual | N/A | N/A | 151873.35 | Actual | N/A | N/A | 240.58 | 1120.5735 | Not Available | 151873.35 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 3 | 52661.47 | REDACTED
REDACTED | N/A | SONOMA | SANTA ROSA | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-05-22 | Actual | N/A | N/A | 427750.83 | Actual | N/A | N/A | 414.5 | 1437.8731 | 1 | 427750.83 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 7 | 164975.55 | REDACTED
REDACTED | N/A | PLACER | LINCOLN | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-03-09 | Actual | N/A | N/A | 1089423.99 | Actual | N/A | N/A | 175 | 853.4973 | Not Available | 1089423.99 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 3 | 199548.24 | REDACTED
REDACTED | N/A | SONOMA | SANTA ROSA | N/A | REDACTED | REDACTED | B | Government Agency | Active | Closing | 2021-01-26 | Actual | N/A | N/A | 481950.33 | Actual | N/A | N/A | 1000.59 | 2168.3826 | 4 | 481950.33 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 6 | 42185.13 | REDACTED
REDACTED | N/A | SAN JOAQUIN | TRACY | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-06-30 | Actual | N/A | N/A | 162993.89 | Actual | N/A | N/A | 1426.2 | 2040.504 | 1 | 162993.89 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 10 | 53121.52 | REDACTED
REDACTED | N/A | ALAMEDA | FREMONT | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-05-17 | Actual | N/A | N/A | 524381.01 | Actual | N/A | N/A | 1282.51 | 953.3181 | Not Available | 524381.01 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 4 | 107153.68 | REDACTED
REDACTED | N/A | ALAMEDA | OAKLAND | N/A | REDACTED | REDACTED | B | Contractor | Active | Closing | 2020-12-14 | Actual | N/A | N/A | 517203.03 | Actual | N/A | N/A | 269.07 | 602.7702 | Not Available | 517203.03 | 0 | Unknown | N/A | Yes | N/A | N/A | Urban | 5 | 129609.22 | REDACTED
REDACTED | N/A | ALAMEDA | DUBLIN | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-03-07 | Actual | N/A | N/A | 424341.64 | Actual | N/A | N/A | 4874.25 | 2207.7312 | Not Available | 424341.64 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 17 | 34891.22 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-12-30 | Actual | N/A | N/A | 331497.57 | Actual | N/A | N/A | 400.03 | 3097.3838 | Not Available | 331497.57 | 0 | Unknown | N/A | No | N/A | N/A | Rural | Not Available | 23388.83 | REDACTED
REDACTED | N/A | MARIN | TIBURON | N/A | REDACTED | REDACTED | B | Government Agency | Active | Closing | 2020-09-08 | Actual | N/A | N/A | 419902.93 | Actual | N/A | N/A | 4975 | 582.024 | 20 | 419902.93 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 0 | 47635.47 | REDACTED
REDACTED | N/A | SANTA CLARA | SUNNYVALE | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-03-03 | Actual | N/A | N/A | 362486.71 | Actual | N/A | N/A | 4047 | 1369.7741 | 0 | 362486.71 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 8 | 42849.91 | REDACTED
REDACTED | N/A | KERN | BAKERSFIELD | N/A | REDACTED | REDACTED | B | Business | Active | Closed | 2021-01-20 | Actual | N/A | N/A | 151072.63 | Actual | N/A | N/A | 2817 | 770.7621 | 0 | 151072.63 | 0 | Unknown | N/A | Yes | N/A | N/A | Rural | 0 | 87594.58 | REDACTED
REDACTED | N/A | SHASTA | REDDING | N/A | REDACTED | REDACTED | B | Individual | Active | Closed | 2020-11-15 | Actual | N/A | N/A | 333615.47 | Actual | N/A | N/A | 2265 | 828.2229 | 0 | 333615.47 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 0 | 92699.98 | REDACTED
REDACTED | N/A | ALAMEDA | OAKLAND | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-10-06 | Actual | N/A | N/A | 282754.17 | Actual | N/A | N/A | 3314 | 593.8358 | 0 | 282754.17 | 0 | Unknown | N/A | Yes | N/A | N/A | Urban | 5 | 38584.11 | REDACTED
REDACTED | N/A | SOLANO | DIXON | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-11-18 | Actual | N/A | N/A | 544605.22 | Actual | N/A | N/A | 9071 | 4009.4632 | 0 | 544605.22 | 0 | Unknown | N/A | No | N/A | N/A | Urban Cluster | 4 | 39406.08 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | B | Government Agency | Active | Closing | 2020-06-12 | Actual | N/A | N/A | 376433.79 | Actual | N/A | N/A | 3516 | 1828.3881 | 0 | 376433.79 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 3 | 231025.56 | REDACTED
REDACTED | N/A | SONOMA | SANTA ROSA | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-01-26 | Actual | N/A | N/A | 747461.71 | Actual | N/A | N/A | 3061 | 1499.3225 | 2 | 747461.71 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 7 | 79330.02 | REDACTED
REDACTED | N/A | SAN MATEO | REDWOOD CITY | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-05-26 | Actual | N/A | N/A | 203853.97 | Actual | N/A | N/A | 1809 | 302.7346 | 0 | 203853.97 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 3 | 32528.46 | REDACTED
REDACTED | N/A | PLACER | ROSEVILLE | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-09-16 | Actual | N/A | N/A | 557612.11 | Actual | N/A | N/A | 3294 | 3866.3344 | 0 | 557612.11 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 0 | 129921.57 | REDACTED
REDACTED | N/A | SAN BENITO | HOLLISTER | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-02-27 | Actual | N/A | N/A | 218461.83 | Actual | N/A | N/A | 4210 | 1779.9275 | 0 | 218461.83 | 0 | Unknown | N/A | No | N/A | N/A | Urban Cluster | 2 | 66445.58 | REDACTED
REDACTED | N/A | ALAMEDA | NEWARK | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-03-18 | Actual | N/A | N/A | 189773.17 | Actual | N/A | N/A | 3311 | 1894.6224 | 0 | 189773.17 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 0 | -27342.45 | REDACTED
REDACTED | N/A | SAN BENITO | HOLLISTER | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-04-15 | Actual | N/A | N/A | 48712.31 | Actual | N/A | N/A | 1711 | 1198.3764 | 3 | 48712.31 | 0 | Unknown | N/A | No | N/A | N/A | Urban Cluster | 5 | 0 | REDACTED
REDACTED | N/A | FRESNO | KINGSBURG | N/A | REDACTED | REDACTED | B | Contractor | Active | Closing | 2020-04-17 | Actual | N/A | N/A | 835138.2 | Actual | N/A | N/A | 1458 | 1394.3792 | 0 | 835138.2 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 1 | 178755.25 | REDACTED
REDACTED | N/A | SANTA CRUZ | WATSONVILLE | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-10-04 | Actual | N/A | N/A | 617478.23 | Actual | N/A | N/A | 1545 | 2355.7521 | 0 | 617478.23 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 7 | 166162.78 | REDACTED
REDACTED | N/A | SAN JOAQUIN | TRACY | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-07-31 | Actual | N/A | N/A | 157970.02 | Actual | N/A | N/A | 651 | 633.0964 | 0 | 157970.02 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 3 | 61141.14 | REDACTED
REDACTED | N/A | FRESNO | CLOVIS | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-06-16 | Actual | N/A | N/A | 69318.47 | Actual | N/A | N/A | 2028 | 708.8868 | 0 | 69318.47 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 0 | -24627.52 | REDACTED
REDACTED | N/A | FRESNO | CLOVIS | N/A | REDACTED | REDACTED | B | Government Agency | Active | Closing | 2021-02-27 | Actual | N/A | N/A | 750275.71 | Actual | N/A | N/A | 868 | 1365.6032 | 0 | 750275.71 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 0 | 112769.27 | REDACTED
REDACTED | N/A | SAN JOAQUIN | LODI | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-07-29 | Actual | N/A | N/A | 66001.52 | Actual | N/A | N/A | 1229 | 1206.9479 | 0 | 66001.52 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 0 | 66032.98 | REDACTED
REDACTED | N/A | SHASTA | REDDING | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-09-16 | Actual | N/A | N/A | 54208.96 | Actual | N/A | N/A | 382 | 478.9766 | 0 | 54208.96 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 0 | 7738.01 | REDACTED
REDACTED | N/A | CONTRA COSTA | BRENTWOOD | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-09-01 | Actual | N/A | N/A | 88378.83 | Actual | N/A | N/A | 1380 | 1510.3776 | 0 | 88378.83 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 3 | 20207.99 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | PISMO BEACH | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-11-10 | Actual | N/A | N/A | 543437.67 | Actual | N/A | N/A | 954 | 928.8434 | 1 | 543437.67 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 3 | 118818.91 | REDACTED
REDACTED | N/A | MADERA | MADERA | N/A | REDACTED | REDACTED | B | Business | Active | Closed | 2020-10-05 | Actual | N/A | N/A | 114547.32 | Actual | N/A | N/A | 1240 | 765.9692 | 0 | 114547.32 | 0 | Unknown | N/A | Yes | N/A | N/A | Rural | 0 | 64017.25 | REDACTED
REDACTED | N/A | FRESNO | CLOVIS | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2020-12-10 | Actual | N/A | N/A | 237221.66 | Actual | N/A | N/A | 1452 | 2637.4838 | 0 | 237221.66 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 4 | 50649.07 | REDACTED
REDACTED | N/A | SAN JOAQUIN | MANTECA | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-02-23 | Actual | N/A | N/A | 289195.57 | Actual | N/A | N/A | 1750 | 742.6802 | 3 | 289195.57 | 0 | Unknown | N/A | Yes | N/A | N/A | Urban | 5 | 93758.96 | REDACTED
REDACTED | N/A | SAN JOAQUIN | MANTECA | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-08-16 | Actual | N/A | N/A | 753695.29 | Actual | N/A | N/A | 3877 | 4414.006 | 0 | 753695.29 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 12 | 472169.43 | REDACTED
REDACTED | N/A | NAPA | AMERICAN CANYON | N/A | REDACTED | REDACTED | B | Government Agency | Active | Closing | 2021-04-06 | Actual | N/A | N/A | 300966.54 | Actual | N/A | N/A | 1160 | 1461.8508 | 0 | 300966.54 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 0 | 67991.92 | REDACTED
REDACTED | N/A | SAN MATEO | BELMONT | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-04-09 | Actual | N/A | N/A | 146088.24 | Actual | N/A | N/A | 1260 | 523.8431 | 0 | 146088.24 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 5 | 5870.91 | REDACTED
REDACTED | N/A | FRESNO | REEDLEY | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-05-13 | Actual | N/A | N/A | 200036.19 | Actual | N/A | N/A | 726 | 839.7809 | 0 | 200036.19 | 0 | Unknown | N/A | Yes | N/A | N/A | Urban Cluster | 3 | 54307.87 | REDACTED
REDACTED | N/A | FRESNO | KINGSBURG | N/A | REDACTED | REDACTED | B | Contractor | Active | Closing | 2021-11-04 | Actual | N/A | N/A | 166714.76 | Actual | N/A | N/A | 992 | 1334.7219 | 0 | 166714.76 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 1 | 0 | REDACTED
REDACTED | N/A | FRESNO | KINGSBURG | N/A | REDACTED | REDACTED | B | Contractor | Active | Closing | 2021-11-05 | Actual | N/A | N/A | 112088.53 | Actual | N/A | N/A | 837 | 1008.7963 | 0 | 112088.53 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 5 | -42034.99 | REDACTED
REDACTED | N/A | FRESNO | FOWLER | N/A | REDACTED | REDACTED | B | Business | Active | Closing | 2021-10-01 | Actual | N/A | N/A | 92119.89 | Actual | N/A | N/A | 622 | 705.7776 | 0 | 92119.89 | 0 | Unknown | N/A | Yes | N/A | N/A | Urban Cluster | 3 | 22250.68 | REDACTED
REDACTED | N/A | YUBA | UNINCORPORATED | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1726.82 | EAC | TBD | N/A | TBD | TBD | TBD | 1726.82 | 0 | TBD | N/A | No | N/A | N/A | Urban Cluster | TBD | TBD | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | B | Government Agency | Active | Estimating/Design | TBD | TBD | TBD | TBD | 15256.67 | EAC | TBD | N/A | TBD | TBD | TBD | 15256.67 | 0 | TBD | N/A | No | N/A | N/A | Urban | TBD | 166041.22 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | SANTA CLARA | ALVISO | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | 2020-10-15 | Actual | N/A | N/A | 341489.36 | Actual | N/A | N/A | 4564 | 3744.488 | 0 | 341489.36 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 13 | -9598.73 | REDACTED
REDACTED | N/A | SANTA CLARA | MOUNTAIN VIEW | N/A | REDACTED | REDACTED | B | Business | Active | Planning | TBD | TBD | TBD | TBD | 3663.76 | EAC | TBD | N/A | TBD | TBD | TBD | 3663.76 | 0 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SANTA CLARA | MORGAN HILL | N/A | REDACTED | REDACTED | B | Contractor | Active | Estimating/Design | 2023-06-15 | Forecast | TBD | TBD | 284.31 | EAC | TBD | N/A | TBD | TBD | TBD | 284.31 | 0 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | ALAMEDA | EMERYVILLE | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 3356.61 | EAC | TBD | N/A | TBD | TBD | TBD | 3356.61 | 0 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | ALAMEDA | EMERYVILLE | N/A | REDACTED | REDACTED | B | Business | Active | Planning | TBD | TBD | TBD | TBD | 2558.82 | EAC | TBD | N/A | TBD | TBD | TBD | 2558.82 | 0 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | ALAMEDA | LIVERMORE | N/A | REDACTED | REDACTED | B | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1456.56 | EAC | TBD | N/A | TBD | TBD | TBD | 1456.56 | 0 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | B | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | MONTEREY | PEBBLE BEACH | N/A | REDACTED | REDACTED | C | Business | Active | Closed | 2020-02-18 | Actual | N/A | N/A | 210999.5 | Actual | N/A | N/A | 75 | 921.1816 | Not Available | 210999.5 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 3 | 102665.32 | REDACTED
REDACTED | N/A | TUOLUMNE | GROVELAND | N/A | REDACTED | REDACTED | C | Business | Active | Closed | 2020-04-01 | Actual | N/A | N/A | 375981.65 | Actual | N/A | N/A | 856.85 | 2986.9788 | 4 | 375981.65 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 7 | 215586.57 | REDACTED
REDACTED | N/A | SAN FRANCISCO | SAN FRANCISCO | N/A | REDACTED | REDACTED | C | Business | Active | Closed | 2020-01-04 | Actual | N/A | N/A | 144616.14 | Actual | N/A | N/A | 355 | Not Available | 0 | 144616.14 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 0 | 86901.83 | REDACTED
REDACTED | N/A | SOLANO | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Business | Active | Closed | 2020-11-03 | Actual | N/A | N/A | 19998.95 | Actual | N/A | N/A | 112 | Not Available | 1 | 19998.95 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 0 | 6137.98 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | SAN LUIS OBISPO | N/A | REDACTED | REDACTED | C | Individual | Active | Closed | 2020-08-18 | Actual | N/A | N/A | 248252.29 | Actual | N/A | N/A | 468.19 | 1381.2606 | 2 | 248252.29 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 3 | 146587.62 | REDACTED
REDACTED | N/A | CONTRA COSTA | ALAMO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-01-14 | Actual | 905 | Design | 643000.93 | Actual | 710.4983 | Not Outlier | 131.09 | 429.0597 | 3 | 643000.93 | 0 | Unknown | N/A | No | No | No | Urban | 2 | 0 | REDACTED
REDACTED | N/A | SANTA BARBARA | SANTA YNEZ | N/A | REDACTED | REDACTED | C | Government Agency | Active | Closing | 2021-05-26 | Actual | N/A | N/A | 378618.54 | Actual | N/A | N/A | 664.28 | 356.7817 | Not Available | 378618.54 | 0 | Unknown | N/A | No | N/A | N/A | Urban Cluster | 4 | 119739.83 | REDACTED
REDACTED | N/A | SANTA CLARA | MOUNTAIN VIEW | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-01-29 | Actual | N/A | N/A | 124768.73 | Actual | N/A | N/A | 54.9 | 98.916 | Not Available | 124768.73 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 2 | 30686.53 | REDACTED
REDACTED | N/A | SONOMA | SANTA ROSA | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-01-22 | Actual | N/A | N/A | 52330.68 | Actual | N/A | N/A | 119 | 770.6296 | Not Available | 52330.68 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 2 | 49617.69 | REDACTED
REDACTED | N/A | SONOMA | HEALDSBURG | N/A | REDACTED | REDACTED | C | Contractor | Active | Closing | 2020-01-10 | Actual | N/A | N/A | 128503.9 | Actual | N/A | N/A | 155.7 | 582.1388 | Not Available | 128503.9 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 2 | 126388.32 | REDACTED
REDACTED | N/A | STANISLAUS | RIVERBANK | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-11-06 | Actual | N/A | N/A | 48422.74 | Actual | N/A | N/A | Not Available | 367.3472 | Not Available | 48422.74 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 2 | 41462.26 | REDACTED
REDACTED | N/A | CONTRA COSTA | LAFAYETTE | N/A | REDACTED | REDACTED | C | Individual | Active | Closed | 2021-02-16 | Actual | N/A | N/A | 29755.7 | Actual | N/A | N/A | 152.75 | Not Available | 1 | 29755.7 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 1 | 19852.31 | REDACTED
REDACTED | N/A | SANTA CLARA | MOUNTAIN VIEW | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-06-12 | Actual | N/A | N/A | 301560.37 | Actual | N/A | N/A | 175.71 | 877.0954 | Not Available | 301560.37 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 5 | 112776.98 | REDACTED
REDACTED | N/A | SANTA CLARA | MOUNTAIN VIEW | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-01-29 | Actual | N/A | N/A | 144467.34 | Actual | N/A | N/A | 356.3 | 434.0837 | Not Available | 144467.34 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 3 | 53962.01 | REDACTED
REDACTED | N/A | ALAMEDA | FREMONT | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-02-04 | Actual | N/A | N/A | 138982.96 | Actual | N/A | N/A | 326.55 | 274.3376 | Not Available | 138982.96 | 0 | Unknown | N/A | No | N/A | N/A | Urban | Not Available | 53008.32 | REDACTED
REDACTED | N/A | SAN FRANCISCO | SAN FRANCISCO | N/A | REDACTED | REDACTED | C | Individual | Active | Closed | 2021-05-24 | Actual | N/A | N/A | 34620.58 | Actual | N/A | N/A | 157.5 | Not Available | 1 | 34620.58 | 0 | Unknown | N/A | No | N/A | N/A | Urban | Not Available | 31317.48 | REDACTED
REDACTED | N/A | CONTRA COSTA | EL CERRITO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-06-29 | Actual | N/A | N/A | 102988.2 | Actual | N/A | N/A | 586.33 | 296.8185 | Not Available | 102988.2 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 1 | 35227.16 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-02-22 | Actual | 584 | Design | 451728.97 | Actual | 773.5085 | Not Outlier | 522.9958 | 483.1464 | Not Available | 451728.97 | 0 | Unknown | N/A | Yes | No | No | Urban | Not Available | 117980.76 | REDACTED
REDACTED | N/A | MONTEREY | SALINAS | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-10-15 | Actual | N/A | N/A | 110991.77 | Actual | N/A | N/A | 45 | 973.3557 | Not Available | 110991.77 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 2 | 48188.91 | REDACTED
REDACTED | N/A | SAN FRANCISCO | SAN FRANCISCO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-05-13 | Actual | N/A | N/A | 660731.38 | Actual | N/A | N/A | 130 | 1207.4179 | Not Available | 660731.38 | 0 | Unknown | N/A | Yes | N/A | N/A | Urban | 9 | 491723.38 | REDACTED
REDACTED | N/A | CONTRA COSTA | EL CERRITO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-07-10 | Actual | N/A | N/A | 158174.6 | Actual | N/A | N/A | 570.6 | Not Available | Not Available | 158174.6 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 1 | 47086.58 | REDACTED
REDACTED | N/A | MONTEREY | PEBBLE BEACH | N/A | REDACTED | REDACTED | C | Individual | Active | Closing | 2020-08-28 | Actual | N/A | N/A | 206000.53 | Actual | N/A | N/A | 358.16 | 235.3416 | Not Available | 206000.53 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 1 | 89656.61 | REDACTED
REDACTED | N/A | SANTA CLARA | MOUNTAIN VIEW | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-11-14 | Actual | N/A | N/A | 204895.76 | Actual | N/A | N/A | 173.35 | 237.2274 | Not Available | 204895.76 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 1 | 85112.59 | REDACTED
REDACTED | N/A | YOLO | WINTERS | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-08-05 | Actual | N/A | N/A | 176173.2 | Actual | N/A | N/A | 266.71 | 637.8348 | Not Available | 176173.2 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 3 | 149236.62 | REDACTED
REDACTED | N/A | SAN MATEO | BURLINGAME | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-03-01 | Actual | N/A | N/A | 63300.49 | Actual | N/A | N/A | 286.6 | 259.721 | Not Available | 63300.49 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 2 | 63447.92 | REDACTED
REDACTED | N/A | CONTRA COSTA | WALNUT CREEK | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-10-07 | Actual | N/A | N/A | 147760.33 | Actual | N/A | N/A | 345.75 | 171.0791 | Not Available | 147760.33 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 1 | 63690.6 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-04-16 | Actual | N/A | N/A | 12025.63 | Actual | N/A | N/A | 59.9 | 44.732 | Not Available | 12025.63 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 2 | 22269.33 | REDACTED
REDACTED | N/A | MARIN | NOVATO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-10-02 | Actual | N/A | N/A | 281845.52 | Actual | N/A | N/A | 1144.34 | 770.9674 | Not Available | 281845.52 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 4 | 123912.68 | REDACTED
REDACTED | N/A | ALAMEDA | CASTRO VALLEY | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-06-13 | Actual | N/A | N/A | 238568.16 | Actual | N/A | N/A | 237.26 | 320.3523 | Not Available | 238568.16 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 2 | 54350.83 | REDACTED
REDACTED | N/A | ALAMEDA | HAYWARD | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-01-31 | Actual | N/A | N/A | 219353.43 | Actual | N/A | N/A | 613.05 | 894.4627 | Not Available | 219353.43 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 3 | 131460 | REDACTED
REDACTED | N/A | ALAMEDA | HAYWARD | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-02-03 | Actual | N/A | N/A | 285985.23 | Actual | N/A | N/A | 266.61 | 953.5802 | Not Available | 285985.23 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 4 | 131343.56 | REDACTED
REDACTED | N/A | SAN MATEO | DALY CITY | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-03-13 | Actual | N/A | N/A | 288253.46 | Actual | N/A | N/A | 388.12 | 622.139 | Not Available | 288253.46 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 3 | 92885.17 | REDACTED
REDACTED | N/A | HUMBOLDT | EUREKA | N/A | REDACTED | REDACTED | C | Government Agency | Active | Closing | 2020-07-01 | Actual | N/A | N/A | 107197.23 | Actual | N/A | N/A | 175.75 | 284.9812 | Not Available | 107197.23 | 0 | Unknown | N/A | No | N/A | N/A | Urban Cluster | 3 | 74429.06 | REDACTED
REDACTED | N/A | SANTA CLARA | GILROY | N/A | REDACTED | REDACTED | C | Contractor | Active | Closing | 2020-04-04 | Actual | N/A | N/A | 467673.97 | Actual | N/A | N/A | 194.5 | 989.5243 | Not Available | 467673.97 | 0 | Unknown | N/A | Yes | N/A | N/A | Urban | 2 | 237437.14 | REDACTED
REDACTED | N/A | SANTA CLARA | MILPITAS | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-02-23 | Actual | N/A | N/A | 293185.78 | Actual | N/A | N/A | 2023.14 | 860.6418 | Not Available | 293185.78 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 3 | 61794.69 | REDACTED
REDACTED | N/A | SAN MATEO | SOUTH SAN FRANCISCO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-01-11 | Actual | N/A | N/A | 545909.37 | Actual | N/A | N/A | 1380.16 | 1051.4337 | Not Available | 545909.37 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 5 | 231306.61 | REDACTED
REDACTED | N/A | SANTA BARBARA | GUADALUPE | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-08-05 | Actual | N/A | N/A | 114093.42 | Actual | N/A | N/A | 743.89 | 502.1034 | 1 | 114093.42 | 0 | Unknown | N/A | Yes | N/A | N/A | Urban Cluster | 3 | 102952.43 | REDACTED
REDACTED | N/A | SAN MATEO | REDWOOD CITY | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-04-08 | Actual | N/A | N/A | 182426.16 | Actual | N/A | N/A | 298.1 | 681.5342 | 1 | 182426.16 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 6 | 79105.25 | REDACTED
REDACTED | N/A | ALAMEDA | HAYWARD | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-02-28 | Actual | N/A | N/A | 217357.39 | Actual | N/A | N/A | 229.6 | 139.2248 | Not Available | 217357.39 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 1 | 102384.16 | REDACTED
REDACTED | N/A | SAN BENITO | HOLLISTER | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-07-01 | Actual | N/A | N/A | 167600.12 | Actual | N/A | N/A | 288.92 | 1876.7918 | Not Available | 167600.12 | 0 | Unknown | N/A | No | N/A | N/A | Urban Cluster | 6 | 140992.65 | REDACTED
REDACTED | N/A | SANTA CLARA | MOUNTAIN VIEW | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-05-12 | Actual | N/A | N/A | 290166.88 | Actual | N/A | N/A | 143.16 | 366.1968 | Not Available | 290166.88 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 2 | 144007.92 | REDACTED
REDACTED | N/A | STANISLAUS | OAKDALE | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-07-20 | Actual | N/A | N/A | 36378.56 | Actual | N/A | N/A | 370.11 | 159.9762 | Not Available | 36378.56 | 0 | Unknown | N/A | Yes | N/A | N/A | Urban | 3 | 30624.38 | REDACTED
REDACTED | N/A | FRESNO | FIREBAUGH | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-11-13 | Actual | N/A | N/A | 155249.57 | Actual | N/A | N/A | 51.5 | 192.6092 | Not Available | 155249.57 | 0 | Unknown | N/A | Yes | N/A | N/A | Urban Cluster | 2 | 79337.99 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | PASO ROBLES | N/A | REDACTED | REDACTED | C | Contractor | Active | Closed | 2020-09-25 | Actual | N/A | N/A | 354008.39 | Actual | N/A | N/A | 60 | 583.0068 | Not Available | 354008.39 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 3 | 254036.38 | REDACTED
REDACTED | N/A | SAN FRANCISCO | SAN FRANCISCO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-05-29 | Actual | N/A | N/A | 763919.19 | Actual | N/A | N/A | 780.7 | 936.5614 | Not Available | 763919.19 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 3 | 702028.19 | REDACTED
REDACTED | N/A | MADERA | MADERA | N/A | REDACTED | REDACTED | C | Contractor | Active | Closing | 2020-05-26 | Actual | N/A | N/A | 118752.84 | Actual | N/A | N/A | 964.47 | 437.061 | Not Available | 118752.84 | 0 | Unknown | N/A | Yes | N/A | N/A | Urban | 3 | 51611.79 | REDACTED
REDACTED | N/A | ALAMEDA | OAKLAND | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-08-01 | Actual | N/A | N/A | 175530.84 | Actual | N/A | N/A | 473.3 | 143.1683 | Not Available | 175530.84 | 0 | Unknown | N/A | Yes | N/A | N/A | Urban | 1 | 46060.73 | REDACTED
REDACTED | N/A | SAN MATEO | PORTOLA VALLEY | N/A | REDACTED | REDACTED | C | Individual | Active | Closing | 2020-12-05 | Actual | N/A | N/A | 37488.01 | Actual | N/A | N/A | 179.56 | Not Available | 2 | 37488.01 | 0 | Unknown | N/A | No | N/A | N/A | Urban | Not Available | 22967.95 | REDACTED
REDACTED | N/A | SAN MATEO | REDWOOD CITY | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-11-21 | Actual | N/A | N/A | 1123894.9 | Actual | N/A | N/A | 636.5 | 1600.4138 | 1 | 1123894.9 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 6 | 330841.39 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | SAN LUIS OBISPO | N/A | REDACTED | REDACTED | C | Business | Active | Closed | 2021-02-16 | Actual | N/A | N/A | 108703.11 | Actual | N/A | N/A | 743.04 | 445.0476 | Not Available | 108703.11 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 3 | 99345.97 | REDACTED
REDACTED | N/A | SONOMA | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Individual | Active | Closing | 2020-01-09 | Actual | N/A | N/A | 60939.33 | Actual | N/A | N/A | Not Available | Not Available | Not Available | 60939.33 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 1 | 25785.07 | REDACTED
REDACTED | N/A | SOLANO | VACAVILLE | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-06-04 | Actual | N/A | N/A | 365116.66 | Actual | N/A | N/A | 963.26 | 1117.7075 | Not Available | 365116.66 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 8 | 207185.27 | REDACTED
REDACTED | N/A | SANTA CLARA | MOUNTAIN VIEW | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-02-12 | Actual | N/A | N/A | 88417.48 | Actual | N/A | N/A | 60 | 257.1305 | Not Available | 88417.48 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 2 | 37237.62 | REDACTED
REDACTED | N/A | MARIN | SAN RAFAEL | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-05-15 | Actual | N/A | N/A | 234305.91 | Actual | N/A | N/A | 192.75 | 694.227 | Not Available | 234305.91 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 2 | 78640.1 | REDACTED
REDACTED | N/A | YOLO | DAVIS | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-03-09 | Actual | N/A | N/A | 250636.45 | Actual | N/A | N/A | 334.5358 | 287.1271 | Not Available | 250636.45 | 0 | Unknown | N/A | No | N/A | N/A | Urban | Not Available | 143644.57 | REDACTED
REDACTED | N/A | SAN MATEO | HALF MOON BAY | N/A | REDACTED | REDACTED | C | Individual | Active | Closing | 2020-06-14 | Actual | 281 | Design | 810624.33 | Actual | 2884.7841 | Crossing Hwy 1 required project to be bored instead of open trench | 165.5928 | 121.5815 | Not Available | 810624.33 | 0 | Unknown | N/A | No | No | No | Urban Cluster | 2 | 383338.18 | REDACTED
REDACTED | N/A | FRESNO | FIREBAUGH | N/A | REDACTED | REDACTED | C | Government Agency | Active | Closing | 2020-08-12 | Actual | N/A | N/A | 354341.48 | Actual | N/A | N/A | 641.66 | 830.0017 | Not Available | 354341.48 | 0 | Unknown | N/A | Yes | N/A | N/A | Urban Cluster | 3 | 132753.18 | REDACTED
REDACTED | N/A | ALAMEDA | BERKELEY | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-02-03 | Actual | N/A | N/A | 238790.14 | Actual | N/A | N/A | 115.8 | 273.1454 | 2 | 238790.14 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 2 | 150627.93 | REDACTED
REDACTED | N/A | HUMBOLDT | SAMOA | N/A | REDACTED | REDACTED | C | Business | Active | Closed | 2020-07-25 | Actual | N/A | N/A | 182348.47 | Actual | N/A | N/A | 15 | 659.3557 | Not Available | 182348.47 | 0 | Unknown | N/A | No | N/A | N/A | Urban Cluster | 2 | 72442.2 | REDACTED
REDACTED | N/A | SONOMA | WINDSOR | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-03-31 | Actual | N/A | N/A | 79702.5 | Actual | N/A | N/A | 135.95 | 480.4648 | Not Available | 79702.5 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 3 | 45634.27 | REDACTED
REDACTED | N/A | CONTRA COSTA | ALAMO | N/A | REDACTED | REDACTED | C | Contractor | Active | Closing | 2020-07-22 | Actual | N/A | N/A | 147264.39 | Actual | N/A | N/A | 450.01 | 22.6184 | 2 | 147264.39 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 4 | 80850.05 | REDACTED
REDACTED | N/A | SAN MATEO | ATHERTON | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-04-21 | Actual | N/A | N/A | 105269.39 | Actual | N/A | N/A | 430.67 | Not Available | Not Available | 105269.39 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 2 | 85676.37 | REDACTED
REDACTED | N/A | NAPA | NAPA | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-06-12 | Actual | N/A | N/A | 114229.4 | Actual | N/A | N/A | 41.2 | 597.6398 | 1 | 114229.4 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 2 | 58535.5 | REDACTED
REDACTED | N/A | SANTA CLARA | SAN JOSE | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-02-21 | Actual | N/A | N/A | 379681.3 | Actual | N/A | N/A | 280.51 | 333.4093 | Not Available | 379681.3 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 3 | 199946.7 | REDACTED
REDACTED | N/A | ALAMEDA | LIVERMORE | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-10-22 | Actual | N/A | N/A | 74471.28 | Actual | N/A | N/A | 93 | 135.1838 | Not Available | 74471.28 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 3 | 43199.84 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-08-13 | Actual | N/A | N/A | 92764.2 | Actual | N/A | N/A | 64 | 519.373 | Not Available | 92764.2 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 2 | 50749.28 | REDACTED
REDACTED | N/A | CONTRA COSTA | EL CERRITO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-11-13 | Actual | N/A | N/A | 104584.57 | Actual | N/A | N/A | 885.44 | 433.4284 | Not Available | 104584.57 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 6 | 87910.67 | REDACTED
REDACTED | N/A | FRESNO | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Business | Active | Closed | 2021-06-10 | Actual | N/A | N/A | 13890.45 | Actual | N/A | N/A | 116.98 | Not Available | Not Available | 13890.45 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 1 | 10669.56 | REDACTED
REDACTED | N/A | MADERA | MADERA | N/A | REDACTED | REDACTED | C | Business | Active | Closed | 2021-05-26 | Actual | N/A | N/A | 99522.46 | Actual | N/A | N/A | 238.06 | 537.6582 | Not Available | 99522.46 | 0 | Unknown | N/A | Yes | N/A | N/A | Urban | 3 | 89989.23 | REDACTED
REDACTED | N/A | SHASTA | REDDING | N/A | REDACTED | REDACTED | C | Business | Active | Closed | 2020-07-30 | Actual | N/A | N/A | 72880.47 | Actual | N/A | N/A | 75 | 329.8633 | Not Available | 72880.47 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 2 | 75453.03 | REDACTED
REDACTED | N/A | SANTA BARBARA | SANTA YNEZ | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-09-15 | Actual | N/A | N/A | 186271.96 | Actual | N/A | N/A | 665.07 | 3132.497 | Not Available | 186271.96 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 12 | 215301.66 | REDACTED
REDACTED | N/A | CONTRA COSTA | OAKLEY | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-10-28 | Actual | N/A | N/A | 84584.96 | Actual | N/A | N/A | 50 | 267.9362 | Not Available | 84584.96 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 2 | 82769.25 | REDACTED
REDACTED | N/A | MARIN | SAN RAFAEL | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-07-15 | Actual | N/A | N/A | 471649.97 | Actual | N/A | N/A | 450.7 | 1885.8875 | 1 | 471649.97 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 10 | 214245.52 | REDACTED
REDACTED | N/A | MERCED | LOS BANOS | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-07-29 | Actual | N/A | N/A | 111002.63 | Actual | N/A | N/A | 45 | 409.1069 | Not Available | 111002.63 | 0 | Unknown | N/A | No | N/A | N/A | Urban Cluster | 2 | 70700.38 | REDACTED
REDACTED | N/A | SOLANO | VACAVILLE | N/A | REDACTED | REDACTED | C | Business | Active | Closed | 2021-05-23 | Actual | N/A | N/A | 212169.32 | Actual | N/A | N/A | 40 | 326.4655 | Not Available | 212169.32 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 2 | 93013.99 | REDACTED
REDACTED | N/A | SOLANO | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Business | Active | Closed | 2021-06-04 | Actual | N/A | N/A | 12561.69 | Actual | N/A | N/A | 200.13 | Not Available | 1 | 12561.69 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 1 | 4941.8 | REDACTED
REDACTED | N/A | SOLANO | VACAVILLE | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-11-15 | Actual | N/A | N/A | 9534.4 | Actual | N/A | N/A | 180.25 | Not Available | 1 | 9534.4 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 1 | 6957.58 | REDACTED
REDACTED | N/A | SAN MATEO | ATHERTON | N/A | REDACTED | REDACTED | C | Business | Active | Closed | 2021-02-17 | Actual | N/A | N/A | 30949.6 | Actual | N/A | N/A | 188 | Not Available | Not Available | 30949.6 | 0 | Unknown | N/A | No | N/A | N/A | Urban | Not Available | 36589.55 | REDACTED
REDACTED | N/A | SANTA BARBARA | SANTA MARIA | N/A | REDACTED | REDACTED | C | Business | Active | Closed | 2021-05-15 | Actual | N/A | N/A | 40214.77 | Actual | N/A | N/A | 106.6 | 313.0935 | 1 | 40214.77 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 2 | 30559.44 | REDACTED
REDACTED | N/A | SONOMA | SANTA ROSA | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-09-28 | Actual | N/A | N/A | 94148.55 | Actual | N/A | N/A | 30 | 375.2145 | Not Available | 94148.55 | 0 | Unknown | N/A | No | N/A | N/A | Urban | Not Available | 72023.43 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-07-26 | Actual | N/A | N/A | 372380.85 | Actual | N/A | N/A | 1557 | 770.262 | 0 | 372380.85 | 0 | Unknown | N/A | Yes | N/A | N/A | Urban | 2 | 207468.06 | REDACTED
REDACTED | N/A | ALAMEDA | HAYWARD | N/A | REDACTED | REDACTED | C | Contractor | Active | Closing | 2021-02-16 | Actual | N/A | N/A | 318185.07 | Actual | N/A | N/A | 1809 | 493.6743 | 0 | 318185.07 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 5 | 122168.41 | REDACTED
REDACTED | N/A | SAN MATEO | BURLINGAME | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-10-21 | Actual | N/A | N/A | 265276.75 | Actual | N/A | N/A | 915 | 639.7324 | 0 | 265276.75 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 0 | 137542.68 | REDACTED
REDACTED | N/A | SAN MATEO | PORTOLA VALLEY | N/A | REDACTED | REDACTED | C | Individual | Active | Closing | 2021-01-06 | Actual | 395 | Design | 83677.7 | Actual | 211.8423 | Not Outlier | 700 | 353.4372 | 0 | 83677.7 | 0 | Unknown | N/A | No | No | No | Rural | 2 | 55342.45 | REDACTED
REDACTED | N/A | EL DORADO | EL DORADO HILLS | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-10-22 | Actual | N/A | N/A | 40106.7 | Actual | N/A | N/A | 540 | 207.2471 | 0 | 40106.7 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 2 | 31997.13 | REDACTED
REDACTED | N/A | EL DORADO | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-01-23 | Actual | N/A | N/A | 213333.62 | Actual | N/A | N/A | 2012 | Not Available | 0 | 213333.62 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 0 | 35663.87 | REDACTED
REDACTED | N/A | MADERA | MADERA | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-09-18 | Actual | N/A | N/A | 200128.79 | Actual | N/A | N/A | 2139 | 704.6271 | 0 | 200128.79 | 0 | Unknown | N/A | Yes | N/A | N/A | Urban | 0 | 196891.21 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | SAN LUIS OBISPO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-04-28 | Actual | N/A | N/A | 263534.68 | Actual | N/A | N/A | 4816 | 836.3633 | 0 | 263534.68 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 0 | 94476.33 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Contractor | Active | Closing | 2020-07-12 | Actual | N/A | N/A | 144103.99 | Actual | N/A | N/A | 135 | 229.9202 | 0 | 144103.99 | 0 | Unknown | N/A | Yes | N/A | N/A | Urban | 0 | 58291.09 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Business | Active | Closed | 2020-12-10 | Actual | N/A | N/A | 370608.11 | Actual | N/A | N/A | 1440 | 696.938 | 0 | 370608.11 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 0 | 115889.87 | REDACTED
REDACTED | N/A | SAN MATEO | ATHERTON | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-02-17 | Actual | 205 | Design | 161716.46 | Actual | 788.8608 | Not Outlier | 180 | 167.6142 | 0 | 161716.46 | 0 | Unknown | N/A | No | No | No | Urban | 1 | 67609.99 | REDACTED
REDACTED | N/A | FRESNO | FRESNO | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-12-07 | Actual | N/A | N/A | 190287.92 | Actual | N/A | N/A | 277 | 227.4393 | 0 | 190287.92 | 0 | Unknown | N/A | Yes | N/A | N/A | Urban | 0 | 82204.65 | REDACTED
REDACTED | N/A | SUTTER | NICOLAUS | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2020-12-04 | Actual | N/A | N/A | 147374.22 | Actual | N/A | N/A | 400 | 115.8968 | 0 | 147374.22 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 0 | 50707.63 | REDACTED
REDACTED | N/A | SAN MATEO | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Individual | Active | Closing | 2021-06-17 | Actual | N/A | N/A | 103488.26 | Actual | N/A | N/A | 162 | Not Available | 0 | 103488.26 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 2 | 23763.18 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | EL PASO DE ROBLES | N/A | REDACTED | REDACTED | C | Government Agency | Active | Closing | 2021-05-27 | Actual | N/A | N/A | 68513.42 | Actual | N/A | N/A | 2199 | Not Available | 0 | 68513.42 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 0 | 56793 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | SAN LUIS OBISPO | N/A | REDACTED | REDACTED | C | Individual | Active | Closed | 2021-09-10 | Actual | N/A | N/A | 104393.59 | Actual | N/A | N/A | 216 | 420.9556 | 0 | 104393.59 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 0 | 50954.23 | REDACTED
REDACTED | N/A | SANTA CLARA | LOS ALTOS | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-06-21 | Actual | 113 | Design | 78133.96 | Actual | 691.451 | Not Outlier | 112 | Not Available | 0 | 78133.96 | 0 | Unknown | N/A | No | No | No | Urban | 0 | 21055.91 | REDACTED
REDACTED | N/A | SAN MATEO | SAN CARLOS | N/A | REDACTED | REDACTED | C | Contractor | Active | Closing | 2021-05-16 | Actual | N/A | N/A | 183459.79 | Actual | N/A | N/A | 278 | 255.0083 | 0 | 183459.79 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 2 | 61452.02 | REDACTED
REDACTED | N/A | MADERA | MADERA | N/A | REDACTED | REDACTED | C | Contractor | Active | Closing | 2021-07-16 | Actual | N/A | N/A | 385002.89 | Actual | N/A | N/A | 1320 | 605.9851 | 1 | 385002.89 | 0 | Unknown | N/A | Yes | N/A | N/A | Urban | 2 | 215102.5 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | PASO ROBLES | N/A | REDACTED | REDACTED | C | Individual | Active | Closing | 2021-05-18 | Actual | N/A | N/A | 63389.61 | Actual | N/A | N/A | 320 | 565.4234 | 0 | 63389.61 | 0 | Unknown | N/A | No | N/A | N/A | Urban | 0 | 41324.34 | REDACTED
REDACTED | N/A | NAPA | NAPA | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 260323.78 | EAC | TBD | N/A | TBD | 308.0275 | TBD | 260323.78 | 0 | No | N/A | No | N/A | N/A | Urban | TBD | 104402.86 | REDACTED
REDACTED | N/A | SAN JOAQUIN | STOCKTON | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2021-09-15 | Actual | N/A | N/A | 111804.3 | Actual | N/A | N/A | 512.4278 | 481.2845 | Not Available | 111804.3 | 0 | Unknown | N/A | Yes | N/A | N/A | Urban | 3 | 148540.21 | REDACTED
REDACTED | N/A | SONOMA | PETALUMA | N/A | REDACTED | REDACTED | C | Contractor | Active | Closing | 2021-11-16 | Actual | N/A | N/A | 106361.87 | Actual | N/A | N/A | 147.6 | 1183.9215 | Not Available | 106361.87 | 0 | Unknown | N/A | No | N/A | N/A | Rural | 4 | 74290.56 | REDACTED
REDACTED | N/A | CONTRA COSTA | RICHMOND | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 2665.35 | EAC | TBD | N/A | TBD | TBD | TBD | 2665.35 | 0 | TBD | N/A | Yes | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | YUBA | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 766.46 | EAC | TBD | N/A | TBD | TBD | TBD | 766.46 | 0 | TBD | N/A | No | N/A | N/A | Rural | TBD | 5000 | REDACTED
REDACTED | N/A | ALAMEDA | FREMONT | N/A | REDACTED | REDACTED | C | Contractor | Active | Estimating/Design | TBD | TBD | TBD | TBD | 3014.44 | EAC | TBD | N/A | TBD | TBD | TBD | 3014.44 | 0 | TBD | N/A | No | N/A | N/A | Urban | TBD | 4000 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | SANTA CLARA | MOUNTAIN VIEW | N/A | REDACTED | REDACTED | C | Business | Active | Planning | TBD | TBD | TBD | TBD | 3351.25 | EAC | TBD | N/A | TBD | TBD | TBD | 3351.25 | 0 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | ATASCADERO | N/A | REDACTED | REDACTED | C | Individual | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1522.06 | EAC | TBD | N/A | TBD | TBD | TBD | 1522.06 | 0 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | NAPA | NAPA | N/A | REDACTED | REDACTED | C | Contractor | Active | Planning | 2023-02-25 | Forecast | TBD | TBD | 964.41 | EAC | TBD | N/A | TBD | TBD | TBD | 964.41 | 0 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | ATASCADERO | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 122.94 | EAC | TBD | N/A | TBD | TBD | TBD | 122.94 | 0 | TBD | N/A | No | N/A | N/A | Urban | TBD | 35784.54 | REDACTED
REDACTED | N/A | SANTA CLARA | SAN JOSE | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1827.16 | EAC | TBD | N/A | TBD | TBD | TBD | 1827.16 | 0 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SANTA CLARA | SAN JOSE | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 2245.24 | EAC | TBD | N/A | TBD | TBD | TBD | 2245.24 | 0 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | ALAMEDA | SAN LEANDRO | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | 2023-12-19 | Forecast | TBD | TBD | 5989.49 | EAC | TBD | N/A | TBD | TBD | TBD | 5989.49 | 0 | TBD | N/A | Yes | N/A | N/A | Urban | TBD | 191200.38 | REDACTED
REDACTED | N/A | SANTA CLARA | LOS ALTOS | N/A | REDACTED | REDACTED | C | Individual | Active | Estimating/Design | TBD | TBD | TBD | TBD | 7392.38 | EAC | TBD | N/A | TBD | TBD | TBD | 7392.38 | 0 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SAN MATEO | SAN MATEO | N/A | REDACTED | REDACTED | C | Government Agency | Active | Estimating/Design | TBD | TBD | TBD | TBD | 2687.65 | EAC | TBD | N/A | TBD | TBD | TBD | 2687.65 | 1504.93 | TBD | N/A | No | N/A | N/A | Urban | TBD | 2500 | REDACTED
REDACTED | N/A | SAN LUIS OBISPO | PASO ROBLES | N/A | REDACTED | REDACTED | C | Business | Active | Estimating/Design | TBD | TBD | TBD | TBD | 1151.39 | EAC | TBD | N/A | TBD | 211.7061 | TBD | 1151.39 | 0 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SONOMA | SANTA ROSA | N/A | REDACTED | REDACTED | C | Business | Active | Construction | TBD | TBD | TBD | TBD | 1819.52 | EAC | TBD | N/A | TBD | TBD | TBD | 1819.52 | 0 | Unknown | N/A | No | N/A | N/A | Urban | TBD | 84797.69 | REDACTED
REDACTED | N/A | SANTA CLARA | SAN JOSE | N/A | REDACTED | REDACTED | C | Contractor | Active | Estimating/Design | 2023-02-15 | Forecast | TBD | TBD | 371.7 | EAC | TBD | N/A | TBD | TBD | TBD | 371.7 | 0 | TBD | N/A | No | N/A | N/A | Urban | TBD | TBD | REDACTED
REDACTED | N/A | SAN MATEO | MENLO PARK | N/A | REDACTED | REDACTED | C | Business | Active | Planning | TBD | TBD | TBD | TBD | 691.6 | EAC | TBD | N/A | TBD | TBD | TBD | 691.6 | 0 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | SAN MATEO | MENLO PARK | N/A | REDACTED | REDACTED | C | Business | Active | Planning | TBD | TBD | TBD | TBD | 1658.8 | EAC | TBD | N/A | TBD | TBD | TBD | 1658.8 | 0 | TBD | N/A | No | N/A | N/A | Urban | TBD | 0 | REDACTED
REDACTED | N/A | KERN | UNINCORPORATED | N/A | REDACTED | REDACTED | C | Business | Active | Closing | 2022-08-25 | Actual | N/A | TBD | 99652.12 | Actual | N/A | N/A | Not Available | Not Available | Not Available | 99652.12 | 98894.44 | Unknown | N/A | Yes | N/A | N/A | Urban | Not Available | 9356.49 | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
REDACTED | N/A | N/A | N/A | N/A | REDACTED | REDACTED | C | N/A | Cancelled | Cancelled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REDACTED
Note on G5: Note: For Rule 20A, project name/identifier includes 3 parts: Project Name, Project ID, and Order Number. For Rule 20B and 20C, project name/identifier includes 2 parts: Project Name and Order Number.
Note on H5: Note: For Rule 20B and 20C, project address is either from the application or derived from geodatabase data
Note on K5: Note: Projects in "Hold" status defined as projects that have significant issues that need to be resolved before moving forward (e.g., significant work credit shortage)
Note on M5: Note: Some projects do not have forecasted project completion date at time of Annual Report submission
Note on N5: Note: Some projects do not have forecasted project completion date at time of Annual Report submission
Note on O5: Note: Trench length includes main line and services for completed projects in 2020-2022. Projects with "see 1st sponsor" are multi-sponsor projects. Information intentionally omitted to avoid double-counting trench length. "N/A" responses for Rule 20B and 20C projects where PG&E is not the trench lead.
Note on P5: Note: PG&E defines Estimated or "Preliminary" as a ballpark measurement using measuring wheel or Google Earth. "Design" is defined as data from Estimating/Design. "N/A" responses for Rule 20B and 20C projects where PG&E is not the trench lead.
Note on S5: Note: Project Cost divided by Trench Length. Projects with "see 1st sponsor" are multi-sponsor projects. Information intentionally omitted to avoid duplicate cost/ft calculation. "N/A" responses for Rule 20B and 20C projects where PG&E is not the trench lead.
Note on T5: Note: "N/A" responses for Rule 20B and 20C projects where PG&E is not the trench lead.
Note on U5: Note: Projects with "see 1st sponsor" are multi-sponsor projects. Information intentionally omitted to avoid double-counting footage data.
Note on V5: Note: Projects with "see 1st sponsor" are multi-sponsor projects. Information intentionally omitted to avoid double-counting footage data.
Note on W5: Note: Projects with "see 1st sponsor" are multi-sponsor projects. Information intentionally omitted to avoid double-counting meter data.
Note on AC5: Note: "N/A" responses for Rule 20B and 20C projects where PG&E is not the trench lead.
Note on AD5: Note: "N/A" responses for Rule 20B and 20C projects where PG&E is not the trench lead.
Note on AF5: Note: Projects with "see 1st sponsor" are multi-sponsor projects. Information intentionally omitted to avoid double-counting poles removed data.
Note on C86: Note: Other project sponsor was originally Butte County. However, due to entire utility underground district recently being annexed by Oroville from Butte County, Butte County is no longer a project sponsor.
Note on K86: Note: Pending confirmation from Butte County that it will contribute work credits for this project
Note on K93: Note: Community is exploring options to reduce project scope
Note on K109: Note: Project will not move forward until more progress is made on Mission Road. Project on pause.
Note on K138: Note: Community is exploring options to reduce project scope
Note on K166: Note: Community is exploring options to reduce project scope
Note on K184: Note: Menlo Park has sufficient work credits for Middlefield Rd but not enough for Menlo Ave and Alma St
Note on K185: Note: Menlo Park has sufficient work credits for Middlefield Rd but not enough for Menlo Ave and Alma St
Note on K208: Note: Project in "Hold" status due to San Luis Obispo County's insufficient work credits
Note on K209: Note: Project in "Hold" status due to San Luis Obispo County's insufficient work credits
Note on AA211: Note: Public interest criteria response reflects most current information and not end of year (2022) information.
Note on K212: Note: El Dorado County has indicated in 2023 that it will move forward with this project as a Rule 20B
Note on AA212: Note: Public interest criteria response reflects most current information and not end of year (2022) information.

## Community - By Tranche
PG&E Rule 20 Community Data
Note: The data provided in the conversion report is now being reported in the new annual report.
Tranche 1 (High Priority) | [22 empty] | Tranche 2 | [5 empty] | Tranche 3 (Low Priority)
Project Sponsor | Work Credits Redeemed for Rule 20A Projects, Reporting Period | Number of Customers | Outstanding Work Credit Debt | Years of Work Credit Debt (Active Work Credit Debt / Next Year Allocation) | Miles of Primary Overhead Converted Under Rule 20A, Reporting Period (Projects Reported in Closing/Closed Phase Only) | Miles of Primary Overhead Converted Under Rule 20B, Reporting Period (Projects Reported in Closing/Closed Phase Only) | Miles of Primary Overhead Converted Under Rule 20C, Reporting Period (Projects Reported in Closing/Closed Phase Only) | Miles of Primary Overhead Converted Under Rule 20D, Reporting Period (Projects Reported in Closing/Closed Phase Only) | Miles Trenched Under Rule 20A, Reporting Period | Miles Trenched Under Rule 20D, Reporting Period (SDG&E Only) | Total Cost of Projects Completed Under Rule 20A, Reporting Period | Total Cost of Projects Completed Under Rule 20B, Reporting Period (IOU Work Only) | Total Cost of Projects Completed Under Rule 20C, Reporting Period (IOU Work Only) | Total Cost of Projects Completed Under Rule 20D, Reporting Period (IOU Work Only, SDG&E Only) | Work Credit Ledger Balance, End of Reporting Period (Balance from Prior Year - Work Credit Deductions) | Work Credit Allocation, Next Year | Work Credit Balance, (Column Q + Column R) | Number of Projects in Planning Phase, Reporting Period | Number of Projects in Estimating/Design Phase, Reporting Period | Number of Projects in Construction Phase, Reporting Period | Number of Projects in Closing Phase, Reporting Period | Number of Projects in Closed Phase, Reporting Period | Work Credits Redeemed for Rule 20A Projects Divided by Number of Customers | Work Credits Used in 2022 | Projects in Top 25% DAC as Defined by CalEnviroScreen? | Total Trenched Miles, Last Year of Reporting Period (Projects Reported in Closing/Closed Phase Only) | Work Credits Added Through Transfer from Other Community, Reporting Period (Any Allowable Method of Transfer) | In Shape File? | Urban/Urban Cluster/Rural Community as Defined in the American Community Survey | Number of Rule 20A Projects Completed to Date | Number of Rule 20B Projects Completed to Date | Number of Rule 20C Projects Completed to Date | Number of Rule 20D Projects Completed to Date (SDG&E Only) | Project Sponsor Active/Inactive?
ALAMEDA COUNTY | 0 | 55320 | N/A | N/A | 0.39751 | 0.13232 | N/A | N/A | 0.875 | N/A | 4542867.99 | 5580587.02 | N/A | N/A | 8925090.96 | 0 | 8925090.96 | 1 | 2 | 1 | 2 | 0 | 0 | 0 | No | 1.5234 | 0 | Yes | Urban, Rural | 1 | 1 | N/A | N/A | Active
ALBANY | 0 | 7432 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 293163.91 | 0 | 293163.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Active
ALPINE COUNTY | 0 | 666 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 26985 | 0 | 26985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -2586 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
AMADOR CITY | 0 | 169 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 50513 | 0 | 50513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -4842 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
AMADOR COUNTY | 0 | 13893 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 125268.45 | 0 | 125268.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -12007 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
AMERICAN CANYON | 0 | 6434 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 607282 | 0 | 607282 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
ANDERSON | 0 | 5760 | -1895971.38 | #DIV/0! | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | -1895971.38 | 0 | -1895971.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
ANGELS CAMP | 0 | 2235 | -574772 | #DIV/0! | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | -574772 | 0 | -574772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
ANTIOCH | 0 | 40220 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1307137.17 | 0 | 1307137.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -125286 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
ARCATA | 0 | 8861 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1959292.14 | 0 | 1959292.14 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
ARROYO GRANDE | 0 | 8583 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2190500.85 | 0 | 2190500.85 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
ARVIN | 0 | 5223 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 933659 | 0 | 933659 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Rural | 0 | N/A | N/A | N/A | Active
ATASCADERO | 0 | 13943 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3240382 | 0 | 3240382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -310584 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
ATHERTON | 0 | 2704 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 38728 | 0 | 38728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -3712 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
ATWATER | 0 | 9841 | -667497.52 | #DIV/0! | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | -667497.52 | 0 | -667497.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
AUBURN | 0 | 7926 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 162911.6 | 0 | 162911.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -15615 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
AVENAL | 0 | 2841 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 810329 | 0 | 810329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -77668 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
BAKERSFIELD | 4707551.56 | 149205 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 8223525.72 | 0 | 8223525.72 | 0 | 1 | 0 | 0 | 0 | 31.5509 | 0 | N/A | 0 | 1526931 | Yes | Urban | 0 | N/A | N/A | N/A | Active
BELMONT | 4443414.01 | 11921 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1681732.99 | 0 | 1681732.99 | 0 | 0 | 0 | 0 | 0 | 372.7384 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Active
BELVEDERE | 0 | 1037 | -246358 | #DIV/0! | N/A | 1.194 | N/A | N/A | N/A | N/A | N/A | 1666711.67 | N/A | N/A | -246358 | 0 | -246358 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | No | 0 | 0 | Yes | Urban | 0 | 1 | N/A | N/A | Inactive
BENICIA | 0 | 13226 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2400181 | 0 | 2400181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -230053 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
BERKELEY | 0 | 55773 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 10768371.9 | 0 | 10768371.9 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 162727 | Yes | Urban | 0 | N/A | N/A | N/A | Active
BIGGS | 0 | 19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 13893 | 0 | 13893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -1332 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
BLUE LAKE | 0 | 666 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 352247 | 0 | 352247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -33762 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
BRENTWOOD | 0 | 23326 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 418961.21 | 0 | 418961.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Active
BRISBANE | 0 | 2536 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 62004 | 0 | 62004 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
BUELLTON | 0 | 2289 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 213971 | 0 | 213971 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
BURLINGAME | 0 | 15412 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 17687053 | 0 | 17687053 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
BUTTE COUNTY | 0 | 38172 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 7745480 | 0 | 7745480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
CALAVERAS COUNTY | 0 | 29611 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 9943982.31 | 0 | 9943982.31 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Rural | 0 | N/A | N/A | N/A | Active
CALISTOGA | 0 | 2298 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 770066 | 0 | 770066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -73809 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
CAMPBELL | 0 | 20920 | -2423687.09 | #DIV/0! | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | -2423687.09 | 0 | -2423687.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Active
CAPITOLA | 0 | 6138 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3075156.78 | 0 | 3075156.78 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 839917 | Yes | Urban | 0 | N/A | N/A | N/A | Active
CARMEL | 0 | 3904 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 900349 | 0 | 900349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -86297 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
CHICO | 0 | 47604 | N/A | N/A | 1.3753 | N/A | N/A | N/A | 1.2869 | N/A | 5238108.64 | N/A | N/A | N/A | 9302257.78 | 0 | 9302257.78 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | No | 1.2869 | 0 | Yes | Urban | 1 | N/A | N/A | N/A | Active
CHOWCHILLA | 0 | 5228 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2491816 | 0 | 2491816 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
CLAYTON | 0 | 4372 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 423138 | 0 | 423138 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
CLEARLAKE | 0 | 8623 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3161634 | 0 | 3161634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -303036 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
CLOVERDALE | 0 | 3879 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 839220 | 0 | 839220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -80438 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
CLOVIS | 0 | 46624 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2239293.9 | 0 | 2239293.9 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
COALINGA | 0 | 5121 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1934592 | 0 | 1934592 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
COLFAX | 0 | 1127 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 213940.17 | 0 | 213940.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -20506 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
COLMA | 0 | 798 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 18442 | 0 | 18442 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
COLUSA | 1080069 | 2929 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368.7501 | 88 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Active
COLUSA COUNTY | 4366033.75 | 7173 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1074260.25 | 0 | 1074260.25 | 0 | 0 | 0 | 0 | 0 | 608.6761 | -88 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Active
CONCORD | 0 | 51859 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 9462995.03 | 0 | 9462995.03 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
CONTRA COSTA COUNTY | 0 | 70235 | N/A | N/A | 1.2906 | N/A | N/A | N/A | 2.1235 | N/A | 9142659.5 | N/A | N/A | N/A | 19056296 | 0 | 19056296 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | Yes | 2.1235 | 0 | Yes | Urban | 1 | N/A | N/A | N/A | Active
CORCORAN | 0 | 4783 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 71434 | 0 | 71434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -6847 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
CORNING | 0 | 3496 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 499239.89 | 0 | 499239.89 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
CORTE MADERA | 0 | 4963 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 388107.48 | 0 | 388107.48 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
COTATI | 0 | 3887 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 676812 | 0 | 676812 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
CUPERTINO | 0 | 23575 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 5203445 | 0 | 5203445 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
DALY CITY | 0 | 34319 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1928506.16 | 0 | 1928506.16 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
DANVILLE | 0 | 17776 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1153685 | 0 | 1153685 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
DAVIS | 0 | 29598 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4023853.73 | 0 | 4023853.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Active
DEL REY OAKS | 0 | 831 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 366818 | 0 | 366818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -35159 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
DINUBA | 0 | 7730 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1387655 | 0 | 1387655 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
DIXON | 0 | 7645 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 867180 | 0 | 867180 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
DOS PALOS | 0 | 2099 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 817708 | 0 | 817708 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
DUBLIN | 1251425.68 | 26977 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 822321.12 | 0 | 822321.12 | 0 | 0 | 0 | 0 | 0 | 46.3886 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Active
EAST PALO ALTO | 26765.14 | 7854 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 992117.45 | 0 | 992117.45 | 0 | 0 | 0 | 0 | 0 | 3.4078 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Active
EL CERRITO | 0 | 11748 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2967570 | 0 | 2967570 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
EL DORADO COUNTY | 0 | 69825 | N/A | N/A | 1.7847 | N/A | N/A | N/A | 3.1362 | N/A | 11272738.55 | N/A | N/A | N/A | 19142492 | 0 | 19142492 | 2 | 1 | 0 | 3 | 0 | 0 | 0 | No | 3.1362 | 0 | Yes | Urban, Urban Cluster, Rural | 3 | N/A | N/A | N/A | Active
EMERYVILLE | 0 | 8374 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1068132 | 0 | 1068132 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
ESCALON | 0 | 2644 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 715210 | 0 | 715210 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
EUREKA | 0 | 14188 | N/A | N/A | 0.73777 | N/A | 0.033286 | N/A | 1.6616 | N/A | 7883983.44 | N/A | 107197.23 | N/A | 7755089.55 | 0 | 7755089.55 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | No | 1.6616 | 1410083 | Yes | Urban Cluster | 1 | N/A | 1 | N/A | Active
FAIRFAX | 0 | 3648 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 756117 | 0 | 756117 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
FAIRFIELD | 0 | 42682 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 6631047.22 | 0 | 6631047.22 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
FERNDALE | 0 | 956 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2938709 | 0 | 2938709 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Rural | 0 | N/A | N/A | N/A | Active
FIREBAUGH | 0 | 2517 | -936767.29 | #DIV/0! | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | -936767.29 | 0 | -936767.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
FORT BRAGG | 0 | 4076 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1355923 | 0 | 1355923 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
FORTUNA | 3939197.67 | 5772 | -15219.67 | #DIV/0! | 0.5482 | N/A | N/A | N/A | 1.5161 | N/A | 3939197.67 | N/A | N/A | N/A | -15219.67 | 0 | -15219.67 | 0 | 0 | 0 | 0 | 1 | 682.4667 | 0 | No | 1.5161 | 0 | Yes | Urban Cluster | 1 | N/A | N/A | N/A | Active
FOSTER CITY | 0 | 14794 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 150254 | 0 | 150254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -14402 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
FOWLER | 0 | 2421 | -220082.34 | #DIV/0! | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | -220082.34 | 0 | -220082.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
FREMONT | 0 | 87269 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 9509670.85 | 0 | 9509670.85 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
FRESNO | 0 | 206446 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 14682108.54 | 0 | 14682108.54 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
FRESNO COUNTY | 0 | 86220 | N/A | N/A | N/A | N/A | 0.14476 | N/A | N/A | N/A | N/A | N/A | 396701.72 | N/A | 14678374.04 | 0 | 14678374.04 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | No | 0 | 0 | Yes | Rural | 0 | N/A | 1 | N/A | Active
GILROY | 0 | 19670 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3487341 | 0 | 3487341 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
GLENN COUNTY | 0 | 9319 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3430331 | 0 | 3430331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -328790 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
GONZALES | 0 | 2373 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 495616 | 0 | 495616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -47504 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
GRASS VALLEY | 0 | 8061 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 915823.39 | 0 | 915823.39 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
GREENFIELD | 0 | 4408 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1022667 | 0 | 1022667 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
GROVER BEACH | 0 | 6526 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1100895.07 | 0 | 1100895.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -105519 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
GUADALUPE | 0 | 2307 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 457152 | 0 | 457152 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
GUSTINE | 0 | 2349 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 395940 | 0 | 395940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -37950 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
HALF MOON BAY | 1158325.27 | 4986 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 262505.73 | 0 | 262505.73 | 0 | 0 | 0 | 0 | 0 | 232.3155 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Active
HAYWARD | 2581940.98 | 57133 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 477855.86 | 0 | 477855.86 | 0 | 1 | 0 | 0 | 0 | 45.1918 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
HEALDSBURG | 0 | 169 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 41379.87 | 0 | 41379.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Active
HERCULES | 0 | 9633 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1111550 | 0 | 1111550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -106540 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
HILLSBOROUGH | 0 | 4095 | -776993.42 | #DIV/0! | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | -776993.42 | 0 | -776993.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
HOLLISTER | 0 | 13448 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 810737 | 0 | 810737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -77707 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
HUMBOLDT COUNTY | 0 | 36673 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2542651.56 | 0 | 2542651.56 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -49000 | Yes | Rural | 0 | N/A | N/A | N/A | Active
HURON | 0 | 1727 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 225895 | 0 | 225895 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
IONE | 0 | 2272 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 523986 | 0 | 523986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -50223 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
ISLETON | 0 | 541 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 319244 | 0 | 319244 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Rural | 0 | N/A | N/A | N/A | Active
JACKSON | 0 | 3017 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 175697 | 0 | 175697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -16840 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
KERMAN | 0 | 5024 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 595921 | 0 | 595921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -57118 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
KERN COUNTY | 0 | 88818 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 25726397.38 | 0 | 25726397.38 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
KING CITY | 0 | 3949 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 126220 | 0 | 126220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -12098 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
KINGS COUNTY | 0 | 9725 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2107958 | 0 | 2107958 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Rural | 0 | N/A | N/A | N/A | Active
KINGSBURG | 0 | 5097 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1365406 | 0 | 1365406 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
LAFAYETTE | 0 | 11100 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1055308 | 0 | 1055308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -101149 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
LAKE COUNTY | 0 | 27499 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 9559657.47 | 0 | 9559657.47 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Rural | 0 | N/A | N/A | N/A | Active
LAKEPORT | 0 | 3199 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1070858 | 0 | 1070858 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
LARKSPUR | 0 | 6967 | N/A | N/A | 1.0511 | N/A | N/A | N/A | 0.50966 | N/A | 2705638.23 | N/A | N/A | N/A | 2713681 | 0 | 2713681 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | No | 0.50966 | 611340 | Yes | Urban | 1 | N/A | N/A | N/A | Active
LASSEN COUNTY | 0 | 939 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 409125 | 0 | 409125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -39214 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
LATHROP | 0 | 6461 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 441912.53 | 0 | 441912.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -42356 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
LEMOORE | 0 | 10328 | -241252.44 | #DIV/0! | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | -241252.44 | 0 | -241252.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
LINCOLN | 0 | 20638 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1461796 | 0 | 1461796 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
LIVE OAK | 0 | 3112 | N/A | N/A | 1.2059 | N/A | N/A | N/A | 1.7282 | N/A | 4832399.04 | N/A | N/A | N/A | 4590635 | 0 | 4590635 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | No | 1.7282 | 0 | Yes | Urban Cluster | 1 | N/A | N/A | N/A | Active
LIVERMORE | 0 | 36603 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3938640.36 | 0 | 3938640.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Active
LIVINGSTON | 0 | 2709 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 739589 | 0 | 739589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -70888 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
LOOMIS | 0 | 3245 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1059903 | 0 | 1059903 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
LOS ALTOS | 0 | 12613 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1035154.63 | 0 | 1035154.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Active
LOS ALTOS HILLS | 0 | 3239 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4656260.79 | 0 | 4656260.79 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
LOS BANOS | 0 | 14400 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1589735.68 | 0 | 1589735.68 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
LOS GATOS | 0 | 15307 | N/A | N/A | 0.61559 | N/A | N/A | N/A | 1.0095 | N/A | 5076499.33 | N/A | N/A | N/A | 4940464 | 0 | 4940464 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | No | 1.0095 | 706311 | Yes | Urban | 1 | N/A | N/A | N/A | Active
MADERA | 0 | 20631 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 465509.62 | 0 | 465509.62 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | N/A | 0 | -44618 | Yes | Urban | 0 | N/A | N/A | N/A | Inactive
MADERA COUNTY | 0 | 40430 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4713049.87 | 0 | 4713049.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Active
MANTECA | 0 | 30041 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4620644 | 0 | 4620644 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
MARICOPA | 0 | 516 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 307863 | 0 | 307863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -29508 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
MARIN COUNTY | 0 | 30280 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4943239.19 | 0 | 4943239.19 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban, Rural | 0 | N/A | N/A | N/A | Active
MARINA | 0 | 8640 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1905932 | 0 | 1905932 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
MARIPOSA COUNTY | 0 | 11826 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 223070 | 0 | 223070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -21381 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
MARTINEZ | 0 | 16780 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1607039.11 | 0 | 1607039.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -154032 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
MARYSVILLE | 0 | 6184 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2755994 | 0 | 2755994 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
MCFARLAND | 0 | 2599 | N/A | N/A | 1.0082 | N/A | N/A | N/A | 1.6042 | N/A | 2741393.96 | N/A | N/A | N/A | 4485637 | 0 | 4485637 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Yes | 1.6042 | 0 | Yes | Rural | 1 | N/A | N/A | N/A | Active
MENDOCINO COUNTY | 0 | 32095 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 9107945.44 | 0 | 9107945.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
MENDOTA | 0 | 3123 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 846888 | 0 | 846888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -81172 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
MENLO PARK | 0 | 15709 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 6461971 | 0 | 6461971 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
MERCED | 0 | 27001 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 848116 | 0 | 848116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Active
MERCED COUNTY | 5124510.54 | 31179 | N/A | N/A | 0.92829 | N/A | N/A | N/A | 1.9403 | N/A | 5124510.54 | N/A | N/A | N/A | 1652770.42 | 0 | 1652770.42 | 1 | 0 | 0 | 0 | 1 | 164.3578 | 0 | Yes | 1.9403 | 0 | Yes | Urban | 1 | N/A | N/A | N/A | Active
MILL VALLEY | 0 | 6838 | -488446.66 | #DIV/0! | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | -488446.66 | 0 | -488446.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
MILLBRAE | 0 | 9374 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3573882 | 0 | 3573882 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
MILPITAS | 352492.23 | 28550 | N/A | N/A | 0 | N/A | N/A | N/A | 0 | N/A | 352492.23 | N/A | N/A | N/A | 4565337.77 | 0 | 4565337.77 | 0 | 1 | 0 | 0 | 1 | 12.3465 | 5521.79 | No | 0 | 0 | Yes | Urban | 1 | N/A | N/A | N/A | Active
MONTE SERENO | 0 | 1274 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 494517 | 0 | 494517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -47398 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
MONTEREY | 0 | 15622 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4745057.16 | 0 | 4745057.16 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
MONTEREY COUNTY | 0 | 49504 | N/A | N/A | 1.58 | N/A | N/A | N/A | 2.7172 | N/A | 6726105.01 | N/A | N/A | N/A | 15565230.45 | 0 | 15565230.45 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | No | 2.7172 | 0 | Yes | Urban, Urban Cluster, Rural | 1 | N/A | N/A | N/A | Active
MORAGA | 0 | 6448 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 410200.24 | 0 | 410200.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Active
MORGAN HILL | 0 | 16815 | N/A | N/A | N/A | N/A | 0.11256 | N/A | N/A | N/A | N/A | N/A | 650255.54 | N/A | 489283.2 | 0 | 489283.2 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | No | 0 | 0 | Yes | Urban | 0 | N/A | 1 | N/A | Active
MORRO BAY | 0 | 6772 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2419866.78 | 0 | 2419866.78 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Rural | 0 | N/A | N/A | N/A | Active
MOUNTAIN VIEW | 0 | 39120 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 5011506.5 | 0 | 5011506.5 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
NAPA | 0 | 33649 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 9920852 | 0 | 9920852 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
NAPA COUNTY | 0 | 15862 | -10876510.58 | #DIV/0! | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | -10876510.58 | 0 | -10876510.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
NEVADA CITY | 0 | 2292 | N/A | N/A | 0.11728 | N/A | N/A | N/A | 0.22519 | N/A | 843738.34 | N/A | N/A | N/A | 1201676 | 0 | 1201676 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | No | 0.22519 | 0 | Yes | Urban Cluster | 1 | N/A | N/A | N/A | Active
NEVADA COUNTY | 0 | 33534 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 9562531.89 | 0 | 9562531.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Active
NEWARK | 0 | 17091 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3063527 | 0 | 3063527 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
NEWMAN | 0 | 4058 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1239175.55 | 0 | 1239175.55 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
NOVATO | 0 | 23959 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4896555 | 0 | 4896555 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
OAKDALE | 0 | 8272 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 33530.59 | 0 | 33530.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Active
OAKLAND | -29864 | 188310 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 28893476.38 | 0 | 28893476.38 | 2 | 0 | 0 | 0 | 0 | -0.15859 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
OAKLEY | 0 | 14174 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1089197 | 0 | 1089197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -104397 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
ORANGE COVE | 0 | 2744 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1051711 | 0 | 1051711 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
ORINDA | 0 | 7627 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2663090 | 0 | 2663090 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
ORLAND | 0 | 3639 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1230656 | 0 | 1230656 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
OROVILLE | 0 | 9443 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1460596.16 | 0 | 1460596.16 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
PACIFIC GROVE | 0 | 8670 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2507472.97 | 0 | 2507472.97 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
PACIFICA | 5555654.92 | 15440 | -80017.05 | #DIV/0! | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | -80017.05 | 0 | -80017.05 | 0 | 0 | 0 | 0 | 0 | 359.8222 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Active
PARADISE | 0 | 2153 | N/A | N/A | 0.8633 | N/A | N/A | N/A | 3.0134 | N/A | 6302339.3 | N/A | N/A | N/A | 6198647.75 | 0 | 6198647.75 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | No | 3.0134 | 0 | Yes | Urban Cluster | 2 | N/A | N/A | N/A | Active
PARLIER | 0 | 3886 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 652516.73 | 0 | 652516.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Active
PASO ROBLES | 0 | 14992 | N/A | N/A | N/A | N/A | 0.41648 | N/A | N/A | N/A | N/A | N/A | 68513.42 | N/A | 99771.82 | 0 | 99771.82 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | No | 0 | 0 | Yes | Urban | 0 | N/A | 1 | N/A | Active
PETALUMA | 0 | 26929 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2171326.53 | 0 | 2171326.53 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
PIEDMONT | 0 | 3952 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 775881 | 0 | 775881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -74367 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
PINOLE | 0 | 7852 | N/A | N/A | 0.30404 | N/A | N/A | N/A | 0.61742 | N/A | 2945446.22 | N/A | N/A | N/A | 2945447 | 0 | 2945447 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | No | 0.61742 | 555532 | Yes | Urban | 1 | N/A | N/A | N/A | Active
PISMO BEACH | 5338242.63 | 5892 | -315752.59 | #DIV/0! | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | -315752.59 | 0 | -315752.59 | 0 | 0 | 0 | 0 | 0 | 906.0154 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Active
PITTSBURG | 0 | 25097 | N/A | N/A | 0.35594 | N/A | N/A | N/A | 0.78409 | N/A | 3714973.5 | N/A | N/A | N/A | 3714974 | 0 | 3714974 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | No | 0.78409 | 419275 | Yes | Urban | 1 | N/A | N/A | N/A | Active
PLACER COUNTY | 0 | 43747 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 89727.98 | 0 | 89727.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Active
PLACERVILLE | 0 | 5825 | -149909.79 | #DIV/0! | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | -149909.79 | 0 | -149909.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
PLEASANT HILL | 0 | 15947 | N/A | N/A | N/A | 0.3822 | N/A | N/A | N/A | N/A | N/A | 93290.27 | N/A | N/A | 2556814.36 | 0 | 2556814.36 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | No | 0 | -245066 | Yes | Urban | 0 | 1 | N/A | N/A | Inactive
PLEASANTON | 0 | 32136 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 879255.97 | 0 | 879255.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Active
PLUMAS COUNTY | 0 | 11197 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1547833.38 | 0 | 1547833.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Active
PLYMOUTH | 0 | 564 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 219392 | 0 | 219392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -21028 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
POINT ARENA | 0 | 350 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 153399 | 0 | 153399 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Rural | 0 | N/A | N/A | N/A | Active
PORTOLA VALLEY | 0 | 1730 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 559123 | 0 | 559123 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Rural | 0 | N/A | N/A | N/A | Active
RED BLUFF | 0 | 7692 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1555731 | 0 | 1555731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -149114 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
REDWOOD CITY | 0 | 34678 | N/A | N/A | 1.086 | N/A | N/A | N/A | 1.7311 | N/A | 8368718.63 | N/A | N/A | N/A | 9493176 | 0 | 9493176 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | No | 1.7311 | 0 | Yes | Urban | 1 | N/A | N/A | N/A | Active
REEDLEY | 2493012.88 | 8431 | N/A | N/A | N/A | N/A | 0.098106 | N/A | N/A | N/A | N/A | N/A | 477483.99 | N/A | 2695845.12 | 0 | 2695845.12 | 1 | 0 | 0 | 1 | 0 | 295.696 | 0 | No | 0 | 0 | Yes | Urban Cluster, Rural | 0 | N/A | 1 | N/A | Active
RICHMOND | 0 | 43650 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 7686942.77 | 0 | 7686942.77 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
RIO DELL | 0 | 1606 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 504072 | 0 | 504072 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
RIO VISTA | 0 | 5821 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 830509 | 0 | 830509 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
RIPON | 0 | 4348 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 122405.6 | 0 | 122405.6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
RIVERBANK | 0 | 5364 | -1547500.41 | #DIV/0! | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | -1547500.41 | 0 | -1547500.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
ROCKLIN | 0 | 28508 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 459906 | 0 | 459906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -44081 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
ROHNERT PARK | 0 | 18419 | N/A | N/A | 0.39953 | 0.18951 | N/A | N/A | 0.42992 | N/A | 1919094.67 | 481950.33 | N/A | N/A | 2577697.82 | 0 | 2577697.82 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | No | 0.42992 | 0 | Yes | Urban, Rural | 1 | 1 | N/A | N/A | Active
ROSEVILLE | 0 | 14 | N/A | N/A | N/A | 0.52652 | N/A | N/A | N/A | N/A | N/A | 573967.82 | N/A | N/A | 17995 | 0 | 17995 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | No | 0 | -1725 | Yes | Urban | 0 | 1 | N/A | N/A | Inactive
ROSS | 0 | 968 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 290003 | 0 | 290003 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
SACRAMENTO COUNTY | 0 | 1924 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1020565 | 0 | 1020565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -97819 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
SALINAS | 0 | 48159 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3951690.85 | 0 | 3951690.85 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
SAN ANSELMO | 0 | 6037 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 892402 | 0 | 892402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -85535 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
SAN BENITO COUNTY | 0 | 9552 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3868263 | 0 | 3868263 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Rural | 0 | N/A | N/A | N/A | Active
SAN BRUNO | 0 | 16665 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 6566864 | 0 | 6566864 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
SAN CARLOS | 0 | 14661 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 270887.97 | 0 | 270887.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 49000 | N/A | N/A | 0 | N/A | N/A | N/A | Active
SAN FRANCISCO | 0 | 406101 | -33773008.55 | #DIV/0! | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | -33773008.55 | 0 | -33773008.55 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
SAN JOAQUIN | 0 | 1085 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 395365 | 0 | 395365 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
SAN JOAQUIN COUNTY | 0 | 61647 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 18671519.96 | 0 | 18671519.96 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
SAN JOSE | 2956912.61 | 361409 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 37891718.96 | 0 | 37891718.96 | 3 | 2 | 1 | 0 | 0 | 8.1816 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
SAN JUAN BAUTISTA | 0 | 1009 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 362438 | 0 | 362438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -34739 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
SAN LEANDRO | 0 | 35799 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 8139760.2 | 0 | 8139760.2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
SAN LUIS OBISPO | 0 | 23943 | -338590.87 | #DIV/0! | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | -338590.87 | 0 | -338590.87 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Inactive
SAN LUIS OBISPO COUNTY | 0 | 60671 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 724221.71 | 0 | 724221.71 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban, Rural | 0 | N/A | N/A | N/A | Active
SAN MATEO | 0 | 44274 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 10901360.2 | 0 | 10901360.2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
SAN MATEO COUNTY | 2048060.08 | 24813 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 7711921.85 | 0 | 7711921.85 | 0 | 2 | 0 | 0 | 0 | 82.5398 | 0 | N/A | 0 | 0 | Yes | Urban, Rural | 0 | N/A | N/A | N/A | Active
SAN PABLO | 0 | 10648 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 938601.03 | 0 | 938601.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Active
SAN RAFAEL | 0 | 27937 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 5790354.04 | 0 | 5790354.04 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
SAN RAMON | 0 | 31864 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2071985.11 | 0 | 2071985.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -198596 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
SAND CITY | 0 | 447 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 221664 | 0 | 221664 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
SANGER | 0 | 8789 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1273876 | 0 | 1273876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -122099 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
SANTA BARBARA COUNTY | -157.55 | 27916 | N/A | N/A | 1.1421 | N/A | N/A | N/A | 1.8723 | N/A | 6775926.46 | N/A | N/A | N/A | 6767282.55 | 0 | 6767282.55 | 0 | 0 | 0 | 1 | 0 | -0.0056437 | 0 | No | 1.8723 | 590689 | Yes | Urban | 1 | N/A | N/A | N/A | Active
SANTA CLARA COUNTY | 528738.35 | 26600 | N/A | N/A | 0.96666 | N/A | N/A | N/A | 1.1614 | N/A | 4007899.57 | N/A | N/A | N/A | 17197849.48 | 0 | 17197849.48 | 1 | 0 | 0 | 1 | 1 | 19.8774 | 8282.68 | No | 1.1614 | 0 | Yes | Urban | 2 | N/A | N/A | N/A | Active
SANTA CRUZ | 0 | 24049 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3482408.41 | 0 | 3482408.41 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
SANTA CRUZ COUNTY | 0 | 57280 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 18588311.91 | 0 | 18588311.91 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban, Rural | 0 | N/A | N/A | N/A | Active
SANTA MARIA | 0 | 32410 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 7382889 | 0 | 7382889 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
SANTA ROSA | 0 | 76073 | N/A | N/A | 1.353 | N/A | N/A | N/A | 1.7886 | N/A | 5139134.87 | N/A | N/A | N/A | 5574659.35 | 0 | 5574659.35 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | No | 1.7886 | 0 | Yes | Urban | 1 | N/A | N/A | N/A | Active
SARATOGA | 0 | 11816 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 174023 | 0 | 174023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -16680 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
SAUSALITO | 0 | 5241 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1862547.88 | 0 | 1862547.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -178522 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
SCOTTS VALLEY | 0 | 5293 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1182450 | 0 | 1182450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -113336 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
SEASIDE | 0 | 11416 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 602902 | 0 | 602902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -57787 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
SEBASTOPOL | 0 | 4409 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 991022 | 0 | 991022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -94987 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
SELMA | 0 | 8378 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1898930 | 0 | 1898930 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
SHAFTER | 0 | 6207 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1508451 | 0 | 1508451 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
SHASTA COUNTY | 0 | 33499 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2796249.75 | 0 | 2796249.75 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Rural | 0 | N/A | N/A | N/A | Active
SHASTA LAKE | 0 | 47 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 8763 | 0 | 8763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -840 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
SIERRA COUNTY | 0 | 1195 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 488564 | 0 | 488564 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Rural | 0 | N/A | N/A | N/A | Active
SISKIYOU COUNTY | 0 | 65 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 36782 | 0 | 36782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -3525 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
SOLANO COUNTY | 0 | 10985 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3944849 | 0 | 3944849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -378106 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
SOLEDAD | 0 | 4697 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 853315 | 0 | 853315 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
SOLVANG | 0 | 3122 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1216582 | 0 | 1216582 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
SONOMA | 0 | 6414 | -13935.78 | #DIV/0! | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | -13935.78 | 0 | -13935.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
SONOMA COUNTY | 0 | 74591 | N/A | N/A | 0 | N/A | N/A | N/A | 0 | N/A | 700791.12 | N/A | N/A | N/A | 22439666.54 | 0 | 22439666.54 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | No | 0 | 0 | Yes | Urban, Urban Cluster, Rural | 1 | N/A | N/A | N/A | Active
SONORA | 0 | 3341 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 885375 | 0 | 885375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -84861 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
SOUTH SAN FRANCISCO | 2660362.16 | 25360 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 6364954.84 | 0 | 6364954.84 | 1 | 1 | 0 | 0 | 0 | 104.9039 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
ST HELENA | 0 | 3483 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 73885 | 0 | 73885 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -7082 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Inactive
STANISLAUS COUNTY | 0 | 8772 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 396319 | 0 | 396319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -37986 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
STOCKTON | 0 | 112788 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 15505185.84 | 0 | 15505185.84 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
SUISUN CITY | 0 | 10134 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1126351 | 0 | 1126351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -107959 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
SUNNYVALE | 0 | 62453 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 12344684.74 | 0 | 12344684.74 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
SUTTER COUNTY | 0 | 13152 | N/A | N/A | 0.1808 | N/A | N/A | N/A | 0.4339 | N/A | 1970980.55 | N/A | N/A | N/A | 2597013 | 0 | 2597013 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | No | 0.4339 | 0 | Yes | Rural | 1 | N/A | N/A | N/A | Active
SUTTER CREEK | 0 | 1763 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 597220 | 0 | 597220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -57242 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
TAFT | 0 | 3280 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1202989 | 0 | 1202989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -115304 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
TEHAMA | 0 | 232 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 75802 | 0 | 75802 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
TEHAMA COUNTY | 0 | 22371 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 9349725 | 0 | 9349725 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
TIBURON | 165204.95 | 4561 | N/A | N/A | N/A | 0.94223 | N/A | N/A | N/A | N/A | N/A | 419902.93 | N/A | N/A | 1153921.05 | 0 | 1153921.05 | 1 | 0 | 1 | 1 | 0 | 36.2212 | 165204.95 | No | 0 | 0 | Yes | Urban | 0 | 1 | N/A | N/A | Active
TRACY | 0 | 30977 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3582148.3 | 0 | 3582148.3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
TRINIDAD | 0 | 280 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2894 | 0 | 2894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -277 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
TRINITY COUNTY | 0 | 1768 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 17696 | 0 | 17696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -1696 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
TULARE COUNTY | 0 | 16504 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 6680928 | 0 | 6680928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -640351 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
TUOLUMNE COUNTY | 0 | 31817 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 10349693 | 0 | 10349693 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Rural | 0 | N/A | N/A | N/A | Active
UNION CITY | 0 | 23993 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1300491.19 | 0 | 1300491.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Active
VACAVILLE | 0 | 39573 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4665475.36 | 0 | 4665475.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Active
VALLEJO | 0 | 48119 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 11326588 | 0 | 11326588 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
WALNUT CREEK | 0 | 37503 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4882060.22 | 0 | 4882060.22 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
WASCO | 0 | 6954 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1761660 | 0 | 1761660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -168852 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
WATSONVILLE | 0 | 15720 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2201125.22 | 0 | 2201125.22 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
WEST SACRAMENTO | 0 | 22236 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1923012.32 | 0 | 1923012.32 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
WHEATLAND | 0 | 1557 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 379547 | 0 | 379547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -36379 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
WILLIAMS | 0 | 2051 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 38652 | 0 | 38652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -3705 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
WILLITS | 0 | 2778 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 885426 | 0 | 885426 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
WILLOWS | 0 | 3077 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 23743 | 0 | 23743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -2276 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
WINDSOR | 0 | 9888 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 783485 | 0 | 783485 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
WINTERS | 0 | 2628 | N/A | N/A | 0.030038 | N/A | N/A | N/A | 0.13902 | N/A | 1094862.11 | N/A | N/A | N/A | 1175116 | 0 | 1175116 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | No | 0.13902 | 632921 | Yes | Urban Cluster | 1 | N/A | N/A | N/A | Active
WOODLAND | 0 | 24254 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2789033.07 | 0 | 2789033.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -267323 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
WOODSIDE | 0 | 2311 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 895101 | 0 | 895101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -85794 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
YOLO COUNTY | 0 | 13201 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2596144.63 | 0 | 2596144.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | -906344 | N/A | N/A | 0 | N/A | N/A | N/A | Inactive
YOUNTVILLE | 0 | 1177 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 195838 | 0 | 195838 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban Cluster | 0 | N/A | N/A | N/A | Active
YUBA CITY | 0 | 27599 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 6444389.15 | 0 | 6444389.15 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | Yes | Urban | 0 | N/A | N/A | N/A | Active
YUBA COUNTY | 0 | 26167 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2771571.75 | 0 | 2771571.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 0 | N/A | N/A | 0 | N/A | N/A | N/A | Active
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban Cluster | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.041188 | N/A | N/A | N/A | N/A | N/A | 245081.82 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 174009.14 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.09867 | N/A | N/A | N/A | N/A | N/A | 217258.41 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.13151 | N/A | N/A | N/A | N/A | N/A | 226725.16 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.22408 | N/A | N/A | N/A | N/A | N/A | 46042.15 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.15291 | N/A | N/A | N/A | N/A | N/A | 343852.8 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.15663 | N/A | N/A | N/A | N/A | N/A | 782349.55 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.067235 | N/A | N/A | N/A | N/A | N/A | 144616.14 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.26117 | N/A | N/A | N/A | N/A | N/A | 448747.57 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.033523 | N/A | N/A | N/A | N/A | N/A | 80431.41 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.063359 | N/A | N/A | N/A | N/A | N/A | 250636.45 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.14583 | N/A | N/A | N/A | N/A | N/A | 106091.62 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban Cluster | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.058712 | N/A | N/A | N/A | N/A | N/A | 245345.3 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban Cluster | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.025748 | N/A | N/A | N/A | N/A | N/A | 79702.5 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.020189 | N/A | N/A | N/A | N/A | N/A | 40214.77 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.18244 | N/A | N/A | N/A | N/A | N/A | 365116.66 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.043527 | N/A | N/A | N/A | N/A | N/A | 272822.87 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.74815 | N/A | N/A | N/A | N/A | N/A | 1540938.79 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 2 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 2 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.037903 | N/A | N/A | N/A | N/A | N/A | 12561.69 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.51917 | N/A | N/A | N/A | N/A | N/A | 583487.36 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.021212 | N/A | N/A | N/A | N/A | N/A | 19998.95 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.023444 | N/A | N/A | N/A | N/A | N/A | 174227.32 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.1572 | N/A | N/A | N/A | N/A | N/A | 11429.57 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 1.9386 | N/A | N/A | N/A | N/A | N/A | 540624.65 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 1.1251 | N/A | N/A | N/A | N/A | N/A | 916144.74 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 1 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | 2 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.042455 | N/A | N/A | N/A | N/A | N/A | 563580.17 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.102 | N/A | N/A | N/A | N/A | N/A | 579134.22 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.10985 | N/A | N/A | N/A | N/A | N/A | 174509.71 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.012121 | N/A | N/A | N/A | N/A | N/A | 92764.2 | N/A | N/A | N/A | N/A | 0 | 3 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.061783 | N/A | N/A | N/A | N/A | N/A | 122902.38 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.067816 | N/A | N/A | N/A | N/A | N/A | 102512.79 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0.062707 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.40511 | N/A | N/A | N/A | N/A | N/A | 200128.79 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.18254 | N/A | N/A | N/A | N/A | N/A | 252726.96 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.022727 | N/A | N/A | N/A | N/A | N/A | 602901.22 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.043485 | N/A | N/A | N/A | N/A | N/A | 217357.39 | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.034468 | N/A | N/A | N/A | N/A | N/A | 243549.39 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.275 | N/A | N/A | N/A | N/A | N/A | 237221.66 | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.076357 | N/A | N/A | N/A | N/A | N/A | 658792.75 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 2 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.045987 | N/A | N/A | N/A | N/A | N/A | 227866.26 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.69841 | N/A | N/A | N/A | N/A | N/A | 288324.55 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 2 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 2 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.1733 | N/A | N/A | N/A | N/A | N/A | 265276.75 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.3273 | N/A | N/A | N/A | N/A | N/A | 904729.23 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.085229 | N/A | N/A | N/A | N/A | N/A | 147264.39 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.021932 | N/A | N/A | N/A | N/A | N/A | 238790.14 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.1298 | N/A | N/A | N/A | N/A | N/A | 213621.64 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 1 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.072348 | N/A | N/A | N/A | N/A | N/A | 54208.96 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.23988 | N/A | N/A | N/A | N/A | N/A | 484714.77 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.12862 | N/A | N/A | N/A | N/A | N/A | 228231.46 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 2 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.045087 | N/A | N/A | N/A | N/A | N/A | 99522.46 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.16228 | N/A | N/A | N/A | N/A | N/A | 375981.65 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 220265.74 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 54820.23 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.10652 | N/A | N/A | N/A | N/A | N/A | 230581.61 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.044936 | N/A | N/A | N/A | N/A | N/A | 238568.16 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.0056818 | N/A | N/A | N/A | N/A | N/A | 94148.55 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.32538 | N/A | N/A | N/A | N/A | N/A | 498374.98 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.0097538 | N/A | N/A | N/A | N/A | N/A | 155249.57 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban Cluster | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.052652 | N/A | N/A | N/A | N/A | N/A | 183459.79 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.12031 | N/A | N/A | N/A | N/A | N/A | 286326.68 | N/A | N/A | N/A | N/A | 2 | 0 | 1 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban, Urban Cluster | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.011345 | N/A | N/A | N/A | N/A | N/A | 12025.63 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.007803 | N/A | N/A | N/A | N/A | N/A | 114229.4 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.13258 | N/A | N/A | N/A | N/A | N/A | 83677.7 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0.074811 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.62765 | N/A | N/A | N/A | N/A | N/A | 282754.17 | N/A | N/A | N/A | N/A | N/A | 0 | 3 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.027114 | N/A | N/A | N/A | N/A | N/A | 290166.88 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.044886 | N/A | N/A | N/A | N/A | N/A | 1359586.37 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 2 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.14073 | N/A | N/A | N/A | N/A | N/A | 108703.11 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 1.2869 | N/A | N/A | N/A | N/A | N/A | 984645.22 | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban, Rural | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.12596 | N/A | N/A | N/A | N/A | N/A | 186271.96 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.71875 | N/A | N/A | N/A | N/A | N/A | 557853.65 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 2 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban, Urban Cluster | N/A | 2 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.36364 | N/A | N/A | N/A | N/A | N/A | 350741.19 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.014655 | N/A | N/A | N/A | N/A | N/A | 412551.53 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.032831 | N/A | N/A | N/A | N/A | N/A | 204895.76 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.1375 | 0.13023 | N/A | N/A | N/A | N/A | 200036.19 | 322401.5 | N/A | N/A | N/A | N/A | 2 | 0 | 1 | 2 | 0 | N/A | N/A | Yes, No | 0 | N/A | Yes | Urban, Urban Cluster | N/A | 1 | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.040909 | N/A | N/A | N/A | N/A | N/A | 104393.59 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.029225 | N/A | N/A | N/A | N/A | N/A | 186943.52 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.095644 | N/A | N/A | N/A | N/A | N/A | 122601.52 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.18794 | N/A | N/A | N/A | N/A | N/A | 963335.73 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 3 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban, Urban Cluster | N/A | 3 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2 | 2 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban, Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.05428 | N/A | N/A | N/A | N/A | N/A | 63300.49 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.17367 | N/A | N/A | N/A | N/A | N/A | 1156884.5 | N/A | N/A | N/A | N/A | N/A | 0 | 2 | 1 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.76458 | N/A | N/A | N/A | N/A | N/A | 351511.32 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Rural | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.36686 | N/A | N/A | N/A | N/A | N/A | 405821.75 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0.14797 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.19886 | N/A | N/A | N/A | N/A | N/A | 1612891.98 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.054394 | N/A | N/A | N/A | N/A | N/A | 478552.12 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0.067368 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 1.0636 | N/A | N/A | N/A | N/A | N/A | 974790.57 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 2 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 2 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.14247 | N/A | N/A | N/A | N/A | N/A | 77283.39 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.28684 | N/A | N/A | N/A | N/A | N/A | 852676.86 | N/A | N/A | N/A | N/A | 1 | 2 | 0 | 2 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban, Urban Cluster | N/A | N/A | 2 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.30763 | N/A | N/A | N/A | N/A | N/A | 416265.29 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 230439.4 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.21912 | N/A | N/A | N/A | N/A | N/A | 261162.8 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 2 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 2 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.29261 | N/A | N/A | N/A | N/A | N/A | 617478.23 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.031602 | N/A | N/A | N/A | N/A | N/A | 435199.12 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.03447 | N/A | N/A | N/A | N/A | N/A | 308732.59 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.3286 | N/A | N/A | N/A | N/A | N/A | 377432.25 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.053127 | N/A | N/A | N/A | N/A | N/A | 379681.3 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.077038 | N/A | N/A | N/A | N/A | N/A | 373695.35 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.014604 | N/A | N/A | N/A | N/A | N/A | 204272.42 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.035606 | N/A | N/A | N/A | N/A | N/A | 30949.6 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 1.0475 | N/A | N/A | N/A | N/A | N/A | 569359.37 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 2 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban, Rural | N/A | 2 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.19602 | N/A | N/A | N/A | N/A | N/A | 150798.99 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.024828 | N/A | N/A | N/A | N/A | N/A | 643000.93 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0.1714 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.27273 | N/A | N/A | N/A | N/A | N/A | 370608.11 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.088672 | N/A | N/A | N/A | N/A | N/A | 248252.29 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.092036 | N/A | N/A | N/A | N/A | N/A | 196599.96 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.16439 | 0.10593 | N/A | N/A | N/A | N/A | 750275.71 | 549309.04 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 2 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban, Urban Cluster | N/A | 1 | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.42898 | N/A | N/A | N/A | N/A | N/A | 333615.47 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.14138 | N/A | N/A | N/A | N/A | N/A | 77287.88 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.034138 | N/A | N/A | N/A | N/A | N/A | 9534.4 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban Cluster | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 2 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.34621 | N/A | N/A | N/A | N/A | N/A | 651343.9 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 341489.36 | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.21856 | N/A | N/A | N/A | N/A | N/A | 238420.94 | N/A | N/A | N/A | N/A | N/A | 0 | 4 | 1 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban, Rural | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.14714 | N/A | N/A | N/A | N/A | N/A | 420532.53 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 201695.05 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.375 | N/A | N/A | N/A | N/A | N/A | 720668.05 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Rural | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.14998 | N/A | N/A | N/A | N/A | N/A | 291365.06 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.39223 | N/A | N/A | N/A | N/A | N/A | 981941.59 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.14089 | N/A | N/A | N/A | N/A | N/A | 114093.42 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban Cluster | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.046029 | N/A | N/A | N/A | N/A | N/A | 286576.62 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban Cluster | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.21402 | N/A | N/A | N/A | N/A | N/A | 466755.29 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.10311 | N/A | N/A | N/A | N/A | N/A | 315079.93 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | No | 0 | N/A | Yes | Urban Cluster | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.1677 | N/A | N/A | N/A | N/A | N/A | 104584.57 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.19566 | N/A | N/A | N/A | N/A | N/A | 133234.36 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.33144 | N/A | N/A | N/A | N/A | N/A | 590960.47 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.26139 | N/A | N/A | N/A | N/A | N/A | 545909.37 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.088066 | N/A | N/A | N/A | N/A | N/A | 245322.61 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban Cluster | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.024621 | N/A | N/A | N/A | N/A | N/A | 660731.38 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.11948 | N/A | N/A | N/A | N/A | N/A | 231315.34 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.94678 | N/A | N/A | N/A | N/A | N/A | 620778.9 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.35133 | N/A | N/A | N/A | N/A | N/A | 781388.7 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.031629 | N/A | N/A | N/A | N/A | N/A | 283554.21 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 1.718 | N/A | N/A | N/A | N/A | N/A | 544605.22 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban Cluster | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.029489 | N/A | N/A | N/A | N/A | N/A | 128503.9 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.18266 | N/A | N/A | N/A | N/A | N/A | 118752.84 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban Cluster | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.021212 | N/A | N/A | N/A | N/A | N/A | 78133.96 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0.021402 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.078504 | N/A | N/A | N/A | N/A | N/A | 427750.83 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.75682 | 0.22135 | N/A | N/A | N/A | N/A | 907214.49 | 201418.94 | N/A | N/A | N/A | N/A | 2 | 1 | 2 | 5 | 1 | N/A | N/A | Yes, No | 0 | N/A | Yes | Urban, Urban Cluster, Rural | N/A | 4 | 2 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban Cluster | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban Cluster | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 3.7191 | N/A | N/A | N/A | N/A | N/A | 904992.97 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Rural | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.29489 | N/A | N/A | N/A | N/A | N/A | 372380.85 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 2.4388 | N/A | N/A | N/A | N/A | N/A | 1819886.44 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.79735 | N/A | N/A | N/A | N/A | N/A | 218461.83 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban Cluster | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.060077 | N/A | N/A | N/A | N/A | N/A | 177643.25 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0.055149 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 60939.33 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.02893 | N/A | N/A | N/A | N/A | N/A | 29755.7 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban Cluster | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 3.0057 | N/A | N/A | N/A | N/A | N/A | 649583.35 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.032955 | N/A | N/A | N/A | N/A | N/A | 136077.89 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.0075758 | N/A | N/A | N/A | N/A | N/A | 212169.32 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.29886 | N/A | N/A | N/A | N/A | N/A | 376101.89 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 1.9231 | 0.10662 | N/A | N/A | N/A | N/A | 1484329.38 | 296667.79 | N/A | N/A | N/A | N/A | 4 | 4 | 2 | 6 | 1 | N/A | N/A | Yes, No | 0 | N/A | Yes | Urban, Rural | N/A | 5 | 2 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.48333 | N/A | N/A | N/A | N/A | N/A | 253440.32 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 2 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban, Rural | N/A | N/A | 2 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.030907 | N/A | N/A | N/A | N/A | N/A | 77753.14 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.033144 | N/A | N/A | N/A | N/A | N/A | 1089423.99 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban, Urban Cluster | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.030682 | N/A | N/A | N/A | N/A | N/A | 103488.26 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.044114 | N/A | N/A | N/A | N/A | N/A | 124706.44 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0.021591 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 1 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.067833 | N/A | N/A | N/A | N/A | N/A | 206000.53 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban Cluster | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.0085227 | N/A | N/A | N/A | N/A | N/A | 111002.63 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban Cluster | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.18068 | N/A | N/A | N/A | N/A | N/A | 543437.67 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.089943 | N/A | N/A | N/A | N/A | N/A | 323519.39 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.031362 | N/A | N/A | N/A | N/A | N/A | 810624.33 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0.05322 | N/A | Yes | Urban Cluster | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 99652.12 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.039972 | N/A | N/A | N/A | N/A | N/A | 167859.19 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.027955 | N/A | N/A | N/A | N/A | N/A | 106361.87 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban Cluster | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.18674 | N/A | N/A | N/A | N/A | N/A | 383768.34 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Rural | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 48422.74 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban Cluster | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.48201 | N/A | N/A | N/A | N/A | N/A | 374464.3 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban Cluster | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 1.1692 | N/A | N/A | N/A | N/A | N/A | 1285410.43 | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 2 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban, Rural | N/A | 2 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.0085227 | N/A | N/A | N/A | N/A | N/A | 110991.77 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.05472 | N/A | N/A | N/A | N/A | N/A | 167600.12 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban Cluster | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.15813 | N/A | N/A | N/A | N/A | N/A | 698897.89 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.022538 | N/A | N/A | N/A | N/A | N/A | 52330.68 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.081566 | N/A | N/A | N/A | N/A | N/A | 105269.39 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.075758 | N/A | N/A | N/A | N/A | N/A | 147374.22 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.010398 | N/A | N/A | N/A | N/A | N/A | 124768.73 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.74735 | N/A | N/A | N/A | N/A | N/A | 211354.4 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.28811 | N/A | N/A | N/A | N/A | N/A | 343501.36 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 2 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | 2 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.23864 | N/A | N/A | N/A | N/A | N/A | 146088.24 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.027133 | N/A | N/A | N/A | N/A | N/A | 578380.12 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.2197 | N/A | N/A | N/A | N/A | N/A | 300966.54 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.1315 | N/A | N/A | N/A | N/A | N/A | 729553.99 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.084485 | N/A | N/A | N/A | N/A | N/A | 235132.46 | N/A | N/A | N/A | N/A | N/A | 1 | 1 | 1 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban, Urban Cluster, Rural | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.061847 | N/A | N/A | N/A | N/A | N/A | 138982.96 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.34261 | N/A | N/A | N/A | N/A | N/A | 318185.07 | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.25324 | N/A | N/A | N/A | N/A | N/A | 516151.43 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 2 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 2 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.33144 | N/A | N/A | N/A | N/A | N/A | 289195.57 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.083225 | N/A | N/A | N/A | N/A | N/A | 364534.06 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.14786 | N/A | N/A | N/A | N/A | N/A | 763919.19 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.02983 | N/A | N/A | N/A | N/A | N/A | 34620.58 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.10622 | N/A | N/A | N/A | N/A | N/A | 116717.54 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 56752.04 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.014205 | N/A | N/A | N/A | N/A | N/A | 210999.5 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 2 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban, Urban Cluster | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.18504 | N/A | N/A | N/A | N/A | N/A | 464181.39 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.083356 | N/A | N/A | N/A | N/A | N/A | 154442.35 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.15202 | N/A | N/A | N/A | N/A | N/A | 493270.22 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.74867 | N/A | N/A | N/A | N/A | N/A | 986447.93 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.79337 | 0.0428 | N/A | N/A | N/A | N/A | 1611760.65 | 172749.56 | N/A | N/A | N/A | N/A | 0 | 4 | 2 | 3 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban, Urban Cluster, Rural | N/A | 3 | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 1.1111 | N/A | N/A | N/A | N/A | N/A | 1534747.93 | N/A | N/A | N/A | N/A | N/A | 0 | 4 | 0 | 2 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban, Rural | N/A | 2 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.011364 | N/A | N/A | N/A | N/A | N/A | 354008.39 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 4 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.14151 | N/A | N/A | N/A | N/A | N/A | 140553.59 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.3447 | N/A | N/A | N/A | N/A | N/A | 260240.74 | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.011364 | N/A | N/A | N/A | N/A | N/A | 88417.48 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.043083 | N/A | N/A | N/A | N/A | N/A | 449467.27 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.057564 | N/A | N/A | N/A | N/A | N/A | 89310.77 | N/A | N/A | N/A | N/A | 0 | 3 | 1 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.034008 | N/A | N/A | N/A | N/A | N/A | 37488.01 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.032992 | N/A | N/A | N/A | N/A | N/A | 156770.9 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.045564 | N/A | N/A | N/A | N/A | N/A | 151873.35 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban Cluster | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban Cluster | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.26042 | N/A | N/A | N/A | N/A | N/A | 61123.76 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban Cluster | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.34269 | N/A | N/A | N/A | N/A | N/A | 1173428.99 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.052462 | N/A | N/A | N/A | N/A | N/A | 190287.92 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.026326 | N/A | N/A | N/A | N/A | N/A | 446587.36 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.050585 | N/A | N/A | N/A | N/A | N/A | 61546.18 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.38317 | N/A | N/A | N/A | N/A | N/A | 293185.78 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 1.0227 | N/A | N/A | N/A | N/A | N/A | 211676.74 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.034091 | N/A | N/A | N/A | N/A | N/A | 161716.46 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0.038826 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.0028409 | N/A | N/A | N/A | N/A | N/A | 182348.47 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | No | 0 | N/A | Yes | Urban Cluster | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban Cluster | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.77784 | N/A | N/A | N/A | N/A | N/A | 978686.25 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 2 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban, Rural | N/A | 2 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.034697 | N/A | N/A | N/A | N/A | N/A | 30732.88 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.12581 | N/A | N/A | N/A | N/A | N/A | 378618.54 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban Cluster | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.060606 | N/A | N/A | N/A | N/A | N/A | 63389.61 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.133 | N/A | N/A | N/A | N/A | N/A | 512480.89 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0 | N/A | N/A | N/A | N/A | N/A | 87872.64 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 1.6273 | N/A | N/A | N/A | N/A | N/A | 543071.49 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | Yes | 0 | N/A | Yes | Urban Cluster | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.16915 | N/A | N/A | N/A | N/A | N/A | 212211.37 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 2 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 2.4364 | N/A | N/A | N/A | N/A | N/A | 1091761.71 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0.85019 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.014205 | N/A | N/A | N/A | N/A | N/A | 72880.47 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.08964 | N/A | N/A | N/A | N/A | N/A | 175530.84 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.57973 | 0.0094697 | N/A | N/A | N/A | N/A | 747461.71 | 84584.96 | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 2 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban, Rural | N/A | 1 | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.15817 | N/A | N/A | N/A | N/A | N/A | 344530.99 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban Cluster | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban Cluster | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.08536 | N/A | N/A | N/A | N/A | N/A | 471649.97 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban Cluster | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.048403 | N/A | N/A | N/A | N/A | N/A | 218036.75 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.29545 | 0.06261 | N/A | N/A | N/A | N/A | 390634.74 | 354514.39 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 2 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.21723 | N/A | N/A | N/A | N/A | N/A | 534558.29 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.033589 | N/A | N/A | N/A | N/A | N/A | 234572.71 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.556 | N/A | N/A | N/A | N/A | N/A | 804651.48 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 2 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 2 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.065483 | N/A | N/A | N/A | N/A | N/A | 147760.33 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.10076 | N/A | N/A | N/A | N/A | N/A | 446027.71 | N/A | N/A | N/A | N/A | 1 | 1 | 0 | 2 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 2 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.079555 | N/A | N/A | N/A | N/A | N/A | 21380.55 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.1839 | N/A | N/A | N/A | N/A | N/A | 89692.32 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.070009 | N/A | N/A | N/A | N/A | N/A | 325528.78 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.76648 | N/A | N/A | N/A | N/A | N/A | 362486.71 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.12055 | N/A | N/A | N/A | N/A | N/A | 1123894.9 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.14695 | N/A | N/A | N/A | N/A | N/A | 841528.06 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.025568 | N/A | N/A | N/A | N/A | N/A | 144103.99 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban Cluster | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 1.661 | 0.017614 | N/A | N/A | N/A | N/A | 1002950.68 | 74471.28 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 2 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.17765 | N/A | N/A | N/A | N/A | N/A | 223454.03 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.62708 | N/A | N/A | N/A | N/A | N/A | 189773.17 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.53352 | N/A | N/A | N/A | N/A | N/A | 151072.63 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | Yes | 0 | N/A | Yes | Rural | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.15906 | N/A | N/A | N/A | N/A | N/A | 219650.71 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.34261 | N/A | N/A | N/A | N/A | N/A | 203853.97 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.073508 | N/A | N/A | N/A | N/A | N/A | 288253.46 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 2 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.045172 | N/A | N/A | N/A | N/A | N/A | 554374.88 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.068063 | N/A | N/A | N/A | N/A | N/A | 128813.25 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban Cluster | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban, Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.59457 | N/A | N/A | N/A | N/A | N/A | 897586.78 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 2 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban, Rural | N/A | 2 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.33598 | N/A | N/A | N/A | N/A | N/A | 439880.06 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 1.4312 | N/A | N/A | N/A | N/A | N/A | 272486.35 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.32949 | N/A | N/A | N/A | N/A | N/A | 569917.65 | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 2 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | 2 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.099052 | N/A | N/A | N/A | N/A | N/A | 451728.97 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0.11061 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.05096 | N/A | N/A | N/A | N/A | N/A | 517203.03 | N/A | N/A | N/A | N/A | N/A | 0 | 2 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.48201 | N/A | N/A | N/A | N/A | N/A | 385536.57 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.056458 | N/A | N/A | N/A | N/A | N/A | 182426.16 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.32405 | N/A | N/A | N/A | N/A | N/A | 48712.31 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban Cluster | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.075763 | N/A | N/A | N/A | N/A | N/A | 331497.57 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.057182 | N/A | N/A | N/A | N/A | N/A | 144091.5 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.043561 | N/A | N/A | N/A | N/A | N/A | 83369.28 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.35097 | N/A | N/A | N/A | N/A | N/A | 305866.46 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.092066 | N/A | N/A | N/A | N/A | N/A | 323072.73 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.070097 | N/A | N/A | N/A | N/A | N/A | 36378.56 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 1.0764 | N/A | N/A | N/A | N/A | N/A | 605476.69 | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 2 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban, Rural | N/A | N/A | 2 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.19464 | N/A | N/A | N/A | N/A | N/A | 563690.98 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.14961 | N/A | N/A | N/A | N/A | N/A | 355708 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.079148 | N/A | N/A | N/A | N/A | N/A | 169471.16 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.12153 | N/A | N/A | N/A | N/A | N/A | 354341.48 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban Cluster | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.90852 | N/A | N/A | N/A | N/A | N/A | 2004167.23 | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 4 | 0 | N/A | N/A | Yes, No | 0 | N/A | Yes | Urban Cluster, Rural | N/A | 4 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.099432 | N/A | N/A | N/A | N/A | N/A | 317375.42 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.052661 | N/A | N/A | N/A | N/A | N/A | 305233.51 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.28561 | N/A | N/A | N/A | N/A | N/A | 476269.2 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 1 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.1666 | N/A | N/A | N/A | N/A | N/A | 505338.66 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 2 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 2 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.29043 | N/A | N/A | N/A | N/A | N/A | 347650.73 | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban, Rural | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.099093 | N/A | N/A | N/A | N/A | N/A | 346130.18 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 2 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 2 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.03553 | N/A | N/A | N/A | N/A | N/A | 100153.3 | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.16477 | N/A | N/A | N/A | N/A | N/A | 225789.37 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.050513 | N/A | N/A | N/A | N/A | N/A | 176173.2 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.79867 | 0.26586 | N/A | N/A | N/A | N/A | 519268.94 | 810086.7 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 2 | 0 | N/A | N/A | Yes | 0.94956 | N/A | Yes | Rural | N/A | 1 | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.81989 | N/A | N/A | N/A | N/A | N/A | 474901.3 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 2 | 0 | N/A | N/A | Yes, No | 0 | N/A | Yes | Urban, Urban Cluster | N/A | 2 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.1041 | N/A | N/A | N/A | N/A | N/A | 99388.67 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Rural | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.13075 | N/A | N/A | N/A | N/A | N/A | 57326.38 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 3.4948 | N/A | N/A | N/A | N/A | N/A | 373498.48 | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | 0.48636 | N/A | N/A | N/A | N/A | N/A | 325618.07 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | Yes | 0 | N/A | Yes | Urban Cluster | N/A | 1 | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.087405 | N/A | N/A | N/A | N/A | N/A | 142093.77 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | No | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.13277 | N/A | N/A | N/A | N/A | N/A | 399887.53 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 1 | N/A | N/A | Yes | 0 | N/A | Yes | Urban | N/A | N/A | 1 | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 0 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Rural | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | 1 | 0 | 0 | 0 | N/A | N/A | N/A | 0 | N/A | Yes | Urban | N/A | N/A | N/A | N/A | N/A
REDACTED | N/A | N/A | N/A | N/A | N/A | N/A | 0.036201 | N/A | N/A | N/A | N/A | N/A | 210207.95 | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 1 | 0 | N/A | N/A | Yes | 0 | N/A | Yes | Urban Cluster | N/A | N/A | 1 | N/A | N/A
Note on C5: Note: PG&E defines Work Credits Redeemed as work credits deducted from community's ledger in 2020-2022
Note on G5: Note: Aggregate miles of Centerline Footage of Primary OH Line Converted in Closing/Closed Stage in Projects tab for Rule 20A projects. Cancelled projects were excluded.
Note on H5: Note: Aggregate miles of Centerline Footage of Primary OH Line Converted in Closing/Closed Stage in Projects tab for Rule 20B projects. Cancelled projects were excluded.
Note on I5: Note: Aggregate miles of Centerline Footage of Primary OH Line Converted in Closing/Closed Stage in Projects tab for Rule 20C projects. Cancelled projects were excluded.
Note on K5: Note: Aggregate miles of trench length for Rule 20A projects with construction complete (CN24) dates in 2020-2022. Cancelled projects were excluded.
Note on M5: Note: Aggregate cost of Rule 20A projects with construction complete (CN24) dates in 2020-2022. Cancelled projects were excluded.
Note on N5: Note: Aggregate cost of Rule 20B projects with construction complete (CN24) dates in 2020-2022. Cancelled projects were excluded.
Note on O5: Note: Aggregate cost of Rule 20C projects with construction complete (CN24) dates in 2020-2022. Cancelled projects were excluded.
Note on T5: Note: Aggregate number of projects in Planning Stage in 2020-2022. Cancelled projects were excluded.
Note on U5: Note: Aggregate number of projects in Estimating/Design Stage in 2020-2022. Cancelled projects were excluded.
Note on V5: Note: Aggregate number of projects in Construction Stage in 2020-2022. Cancelled projects were excluded.
Note on W5: Note: Aggregate number of projects in Closing Stage in 2020-2022. Cancelled projects were excluded.
Note on X5: Note: Aggregate number of projects in Closed Stage in 2020-2022. Cancelled projects were excluded.
Note on Y5: Note: Work Credits Redeemed for Rule 20A Projects, Reporting Period divided by Number of Customers
Note on Z5: Note: PG&E defines Work Credits Used as work credits deducted from community's ledger in 2022 excluding work credit transfers
Note on AA5: Note: Project Sponsors with multiple projects that have multiple designations will report all applicable designations. Cancelled projects were excluded. Project Sponsors with no projects will report "N/A".
Note on AB5: Note: Aggregate miles of trench length in Closing/Closed Stage in 2022. Cancelled projects were excluded.
Note on AC5: Note: Per instructions from CPUC ED Staff (Julian Enis on 3/16/23), show work credit transfers that occurred in 2022 only (not reporting period 2020-2022)
Note on AD5: Note: Project Sponsors with projects that have a polygon or point in geodatabase will report "Yes". Project Sponsors with no projects will report "N/A". Cancelled projects were excluded.
Note on AE5: Note: Project Sponsors with multiple projects that have multiple designations will report all applicable designations. Cancelled projects were excluded. Project Sponsors with no projects will report "N/A".
Note on AF5: Note: Aggregate number of Rule 20A projects with construction complete (CN24) dates in 2020-2022. Cancelled projects were excluded.
Note on AG5: Note: Aggregate number of Rule 20B projects with construction complete (CN24) dates in 2020-2022. Cancelled projects were excluded.
Note on AH5: Note: Aggregate number of Rule 20C projects with construction complete (CN24) dates in 2020-2022. Cancelled projects were excluded.
Note on AC97: Note: Work credit transfer to correct loan repayment made in error in 2021.
Note on AC197: Note: Work credit transfer to correct loan repayment made in error in 2021.